## Executive Summary
MEGAPROJECT COMMERCIAL COST CONTROL & VARIATION ANALYTICS
Executive Cost Governance ¦ Earned Value Management (EVM) ¦ Variation & Contingency Analytics ¦ FY2024-2026
TOTAL APPROVED BUDGET (BAC) |  | CERTIFIED TO DATE (AC) |  | PORTFOLIO COST VARIANCE | CONTINGENCY BURN RATE | PORTFOLIO CPI
1148524151.69 |  | 825453726.54 |  | -129156543.5105 | 439% | 0.84353
Portfolio Financial Health & Earned Value Governance
Key Financial Metric | Portfolio Value |  | Commercial Definition & Governance Implication
Original Contract Sum (Baseline) | 850000000 |  | Approved baseline budget across all 10 packages
Approved Variation Orders | 298524151.69 |  | Authorized change orders added to contract sum
Budget at Completion (BAC) | 1148524151.69 |  | Total authorized commercial budget baseline
Earned Value (EV) | 696297183.0295 |  | Budgeted value of work physically completed to date
Actual Cost / Certified to Date (AC) | 825453726.54 |  | Gross valuation of certified work completed
Cost Variance ($) [EV - AC] | -129156543.5105 |  | Positive = Favorable / Under Budget ¦ Negative = Cost Overrun
Cost Performance Index (CPI) [EV / AC] | 0.84353 |  | CPI > 1.00 implies cost efficiency ¦ < 1.00 implies cost overrun
Estimate at Completion (EAC) [BAC / CPI] | 1445379342.7186 |  | Projected final completion cost based on current efficiency
Variance at Completion (VAC) [BAC - EAC] | -296855191.0286 |  | Projected final cost variance at project completion
Total Contingency Budget Allocated | 68000000 |  | Contingency reserve committed for unforeseen scope changes
Remaining Contingency Balance | -230524151.69 |  | Contingency reserve minus approved variations
Pending Variations Claimed Amount | 154422130.76 |  | Total contractor claims currently awaiting evaluation
Net Contingency Exposure Risk | 384946282.45 |  | Pending Claims minus Remaining Contingency (Deficit Risk)

## Package Variance
WORK PACKAGE COST VARIANCE & EARNED VALUE MANAGEMENT
Dynamic SUMIFS Linked to Transaction Ledgers ¦ BAC vs. EAC ¦ CPI ¦ Exposure Risk vs. Contingency
Package ID | Package Scope Description | Original Budget | Approved VOs | Budget at Completion (BAC) | Physical % | Earned Value (EV) | Certified to Date (AC) | Cost Variance ($) | Cost Variance (%) | CPI | Estimate at Completion (EAC) | Variance at Completion (VAC) | Contingency Budget | Contingency Burn % | Pending VOs Claimed | Remaining Contingency | Net Exposure Risk ($) | Performance Status
PKG-01 | Earthworks & Ground Remediation | 45000000 | 30235645.23 | 75235645.23 | 82% | 61693229.0886 | 83313022.56 | -21619793.4714 | -35.04% | 0.7405 | 101601247.0244 | -26365601.7944 | 3600000 | 839.9% | 16187088.39 | -26635645.23 | 42822733.62 | OVER BUDGET / OVERRUN
PKG-02 | Tunnels & Underground Boring (Twin TBM) | 165000000 | 30263315.55 | 195263315.55 | 74% | 144494853.507 | 82443873.78 | 62050979.727 | 42.94% | 1.7526 | 111410640.2432 | 83852675.3068 | 13200000 | 229.3% | 13177168.11 | -17063315.55 | 30240483.66 | FAVORABLE / EFFICIENT
PKG-03 | Elevated Viaducts & Guideway | 115000000 | 29054576.04 | 144054576.04 | 68% | 97957111.7072 | 84471826.64 | 13485285.0672 | 13.77% | 1.1596 | 124223274.4706 | 19831301.5694 | 9200000 | 315.8% | 16452948.84 | -19854576.04 | 36307524.88 | FAVORABLE / EFFICIENT
PKG-04 | Underground Station Structures (3 Nos) | 135000000 | 25681709.85 | 160681709.85 | 61% | 98015843.0085 | 81966168.69 | 16049674.3185 | 16.37% | 1.1958 | 134370768.3443 | 26310941.5057 | 10800000 | 237.8% | 15446976.97 | -14881709.85 | 30328686.82 | FAVORABLE / EFFICIENT
PKG-05 | Elevated Station Terminals & Architecture | 75000000 | 30552444.97 | 105552444.97 | 55% | 58053844.7335 | 82324918.6 | -24271073.8665 | -41.81% | 0.70518 | 149681670.1818 | -44129225.2118 | 6000000 | 509.2% | 16414904.23 | -24552444.97 | 40967349.2 | OVER BUDGET / OVERRUN
PKG-06 | Trackwork, Turnouts & Third Rail | 58000000 | 32251338.57 | 90251338.57 | 52% | 46930696.0564 | 82983163.41 | -36052467.3536 | -76.82% | 0.56554 | 159583006.5577 | -69331667.9877 | 4640000 | 695.1% | 13606069.89 | -27611338.57 | 41217408.46 | OVER BUDGET / OVERRUN
PKG-07 | MEP & Environmental Control Systems | 88000000 | 28803347.78 | 116803347.78 | 48% | 56065606.9344 | 84406372.88 | -28340765.9456 | -50.55% | 0.66423 | 175846610.1667 | -59043262.3867 | 7040000 | 409.1% | 14364010.78 | -21763347.78 | 36127358.56 | OVER BUDGET / OVERRUN
PKG-08 | Traction Power Substation & Catenary | 62000000 | 29714200.63 | 91714200.63 | 45% | 41271390.2835 | 82855498.63 | -41584108.3465 | -100.8% | 0.49811 | 184123330.2889 | -92409129.6589 | 4960000 | 599.1% | 17850090.81 | -24754200.63 | 42604291.44 | OVER BUDGET / OVERRUN
PKG-09 | CBTC Signalling & Telecoms | 72000000 | 33210787.59 | 105210787.59 | 40% | 42084315.036 | 80896188.52 | -38811873.484 | -92.22% | 0.52023 | 202240471.3 | -97029683.71 | 5760000 | 576.6% | 12914088.14 | -27450787.59 | 40364875.73 | OVER BUDGET / OVERRUN
PKG-10 | Interchange Highway & Utility Diversions | 35000000 | 28756785.48 | 63756785.48 | 78% | 49730292.6744 | 79792692.83 | -30062400.1556 | -60.45% | 0.62324 | 102298324.141 | -38541538.661 | 2800000 | 1027% | 18008784.6 | -25956785.48 | 43965570.08 | OVER BUDGET / OVERRUN
Total | Portfolio Summary | 850000000 | 298524151.69 | 1148524151.69 | 60.63% | 696297183.0295 | 825453726.54 | -129156543.5105 | -18.55% | 0.84353 | 1445379342.7186 | -296855191.0286 | 68000000 | 439% | 154422130.76 | -230524151.69 | 384946282.45 | NET PORTFOLIO OVERRUN

## Interactive Slicers
INTERACTIVE PAYMENT & CERTIFICATE SLICER DASHBOARD
Dynamic Pivot Table Driven by Connected Slicers for Package, Payment Status, and Quarter
Slicer Controls & Parameter Filtering
Select any Work Package or Payment Status buttons on the slicers to filter transaction totals dynamically.
Total Certified ($) | Column Labels
Row Labels | Approved Pending Payment | Disputed | Paid | Under Review | Grand Total
PKG-01 | 13304816.76 | 1287885.84 | 61646575.29 | 7073744.67 | 83313022.56
PKG-02 | 12845642.53 | 2169609.25 | 57184025.06 | 10244596.94 | 82443873.78
PKG-03 | 11747320.55 | 2522079.55 | 62241962.93 | 7960463.61 | 84471826.64
PKG-04 | 10257677.48 | 4103925.85 | 58859254.46 | 8745310.9 | 81966168.69
PKG-05 | 14830241.76 | 2999648.99 | 55970517.58 | 8524510.27 | 82324918.6
PKG-06 | 10915051.67 | 3443588.41 | 61878159.17 | 6746364.16 | 82983163.41
PKG-07 | 12417553.47 | 2894960.21 | 60942765.43 | 8151093.77 | 84406372.88
PKG-08 | 11831676.94 | 3472290.91 | 59724050.92 | 7827479.86 | 82855498.63
PKG-09 | 10952569.8 | 3023804.75 | 57560967.61 | 9358846.36 | 80896188.52
PKG-10 | 10567118.19 | 3512068.53 | 58262260.36 | 7451245.75 | 79792692.83
Grand Total | 119669669.15 | 29429862.29 | 594270538.81 | 82083656.29 | 825453726.54
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.

## Actual Expenditures
Expense_ID | Date | Item_Code | Package_ID | Invoice_No | Certified_Qty | Certified_Amount | Retained_Amount | Payment_Status | Net_Certified_Amount | Quarter
EXP-000150 | 2024-01-15 | BOQ-PKG-10-00150 | PKG-10 | INV-PKG-10-011-00150 | 412.18 | 184944.94 | 9247.25 | Paid | 175697.69 | 2024-Q1
EXP-000764 | 2024-01-15 | BOQ-PKG-04-00764 | PKG-04 | INV-PKG-04-030-00764 | 421.9 | 53515.85 | 2675.79 | Paid | 50840.06 | 2024-Q1
EXP-000830 | 2024-01-15 | BOQ-PKG-10-00830 | PKG-10 | INV-PKG-10-026-00830 | 61.49 | 203959.86 | 10197.99 | Paid | 193761.87 | 2024-Q1
EXP-002259 | 2024-01-15 | BOQ-PKG-09-00269 | PKG-09 | INV-PKG-09-020-02259 | 275.7 | 93364.63 | 4668.23 | Paid | 88696.4 | 2024-Q1
EXP-002517 | 2024-01-15 | BOQ-PKG-07-00527 | PKG-07 | INV-PKG-07-033-02517 | 344.61 | 163507.8 | 8175.39 | Under Review | 155332.41 | 2024-Q1
EXP-003106 | 2024-01-15 | BOQ-PKG-06-01116 | PKG-06 | INV-PKG-06-027-03106 | 362.91 | 196974.3 | 9848.72 | Paid | 187125.58 | 2024-Q1
EXP-003594 | 2024-01-15 | BOQ-PKG-04-01604 | PKG-04 | INV-PKG-04-025-03594 | 419.65 | 127895.21 | 6394.76 | Paid | 121500.45 | 2024-Q1
EXP-004595 | 2024-01-15 | BOQ-PKG-05-00615 | PKG-05 | INV-PKG-05-011-04595 | 315.16 | 125984.27 | 6299.21 | Paid | 119685.06 | 2024-Q1
EXP-004653 | 2024-01-15 | BOQ-PKG-03-00673 | PKG-03 | INV-PKG-03-034-04653 | 405.2 | 40619.95 | 2031 | Paid | 38588.95 | 2024-Q1
EXP-005834 | 2024-01-15 | BOQ-PKG-04-01854 | PKG-04 | INV-PKG-04-025-05834 | 119.92 | 194456.84 | 9722.84 | Paid | 184734 | 2024-Q1
EXP-006034 | 2024-01-15 | BOQ-PKG-04-00064 | PKG-04 | INV-PKG-04-015-06034 | 414.83 | 184026.33 | 9201.32 | Paid | 174825.01 | 2024-Q1
EXP-002473 | 2024-01-16 | BOQ-PKG-03-00483 | PKG-03 | INV-PKG-03-024-02473 | 330.64 | 167470.75 | 8373.54 | Paid | 159097.21 | 2024-Q1
EXP-003911 | 2024-01-16 | BOQ-PKG-01-01921 | PKG-01 | INV-PKG-01-027-03911 | 435.79 | 69467.32 | 3473.37 | Paid | 65993.95 | 2024-Q1
EXP-006678 | 2024-01-16 | BOQ-PKG-08-00708 | PKG-08 | INV-PKG-08-029-06678 | 422.93 | 105454.36 | 5272.72 | Paid | 100181.64 | 2024-Q1
EXP-006793 | 2024-01-16 | BOQ-PKG-03-00823 | PKG-03 | INV-PKG-03-004-06793 | 262.9 | 181337.85 | 9066.89 | Paid | 172270.96 | 2024-Q1
EXP-000901 | 2024-01-17 | BOQ-PKG-01-00901 | PKG-01 | INV-PKG-01-027-00901 | 115.33 | 203841.62 | 10192.08 | Approved Pending Payment | 193649.54 | 2024-Q1
EXP-003569 | 2024-01-17 | BOQ-PKG-09-01579 | PKG-09 | INV-PKG-09-035-03569 | 358.94 | 86885.31 | 4344.27 | Paid | 82541.04 | 2024-Q1
EXP-004985 | 2024-01-17 | BOQ-PKG-05-01005 | PKG-05 | INV-PKG-05-016-04985 | 249.2 | 97297.74 | 4864.89 | Paid | 92432.85 | 2024-Q1
EXP-005087 | 2024-01-17 | BOQ-PKG-07-01107 | PKG-07 | INV-PKG-07-013-05087 | 160.41 | 37988.22 | 1899.41 | Paid | 36088.81 | 2024-Q1
EXP-005931 | 2024-01-17 | BOQ-PKG-01-01951 | PKG-01 | INV-PKG-01-017-05931 | 84.62 | 181980.52 | 9099.03 | Paid | 172881.49 | 2024-Q1
EXP-006073 | 2024-01-17 | BOQ-PKG-03-00103 | PKG-03 | INV-PKG-03-019-06073 | 285.34 | 100988.85 | 5049.44 | Approved Pending Payment | 95939.41 | 2024-Q1
EXP-006164 | 2024-01-17 | BOQ-PKG-04-00194 | PKG-04 | INV-PKG-04-005-06164 | 123 | 121011.54 | 6050.58 | Paid | 114960.96 | 2024-Q1
EXP-006673 | 2024-01-17 | BOQ-PKG-03-00703 | PKG-03 | INV-PKG-03-024-06673 | 448.67 | 64044.63 | 3202.23 | Under Review | 60842.4 | 2024-Q1
EXP-001797 | 2024-01-18 | BOQ-PKG-07-01797 | PKG-07 | INV-PKG-07-013-01797 | 17.3 | 173574.24 | 8678.71 | Paid | 164895.53 | 2024-Q1
EXP-001810 | 2024-01-18 | BOQ-PKG-10-01810 | PKG-10 | INV-PKG-10-026-01810 | 22.81 | 59927.87 | 2996.39 | Paid | 56931.48 | 2024-Q1
EXP-001822 | 2024-01-18 | BOQ-PKG-02-01822 | PKG-02 | INV-PKG-02-003-01822 | 157.61 | 207963.82 | 10398.19 | Paid | 197565.63 | 2024-Q1
EXP-003268 | 2024-01-18 | BOQ-PKG-08-01278 | PKG-08 | INV-PKG-08-014-03268 | 352.85 | 150005.82 | 7500.29 | Disputed | 142505.53 | 2024-Q1
EXP-006832 | 2024-01-18 | BOQ-PKG-02-00862 | PKG-02 | INV-PKG-02-008-06832 | 205.39 | 184190.74 | 9209.54 | Approved Pending Payment | 174981.2 | 2024-Q1
EXP-006931 | 2024-01-18 | BOQ-PKG-01-00961 | PKG-01 | INV-PKG-01-002-06931 | 425.28 | 73532.63 | 3676.63 | Approved Pending Payment | 69856 | 2024-Q1
EXP-001178 | 2024-01-19 | BOQ-PKG-08-01178 | PKG-08 | INV-PKG-08-024-01178 | 195.38 | 62767.38 | 3138.37 | Paid | 59629.01 | 2024-Q1
EXP-001604 | 2024-01-19 | BOQ-PKG-04-01604 | PKG-04 | INV-PKG-04-030-01604 | 393.78 | 84112.6 | 4205.63 | Paid | 79906.97 | 2024-Q1
EXP-001845 | 2024-01-19 | BOQ-PKG-05-01845 | PKG-05 | INV-PKG-05-026-01845 | 231.56 | 130908.99 | 6545.45 | Paid | 124363.54 | 2024-Q1
EXP-002405 | 2024-01-19 | BOQ-PKG-05-00415 | PKG-05 | INV-PKG-05-026-02405 | 5.15 | 107981.31 | 5399.07 | Disputed | 102582.24 | 2024-Q1
EXP-002981 | 2024-01-19 | BOQ-PKG-01-00991 | PKG-01 | INV-PKG-01-007-02981 | 186.79 | 139670.44 | 6983.52 | Approved Pending Payment | 132686.92 | 2024-Q1
EXP-005531 | 2024-01-19 | BOQ-PKG-01-01551 | PKG-01 | INV-PKG-01-002-05531 | 384.76 | 39342.3 | 1967.12 | Under Review | 37375.18 | 2024-Q1
EXP-006581 | 2024-01-19 | BOQ-PKG-01-00611 | PKG-01 | INV-PKG-01-002-06581 | 108.65 | 106531.38 | 5326.57 | Under Review | 101204.81 | 2024-Q1
EXP-006626 | 2024-01-19 | BOQ-PKG-06-00656 | PKG-06 | INV-PKG-06-012-06626 | 368.3 | 82829.67 | 4141.48 | Paid | 78688.19 | 2024-Q1
EXP-006681 | 2024-01-19 | BOQ-PKG-01-00711 | PKG-01 | INV-PKG-01-032-06681 | 140.03 | 108188.62 | 5409.43 | Paid | 102779.19 | 2024-Q1
EXP-000185 | 2024-01-20 | BOQ-PKG-05-00185 | PKG-05 | INV-PKG-05-011-00185 | 220.32 | 46242.08 | 2312.1 | Under Review | 43929.98 | 2024-Q1
EXP-001211 | 2024-01-20 | BOQ-PKG-01-01211 | PKG-01 | INV-PKG-01-022-01211 | 443.27 | 193653.14 | 9682.66 | Paid | 183970.48 | 2024-Q1
EXP-001360 | 2024-01-20 | BOQ-PKG-10-01360 | PKG-10 | INV-PKG-10-031-01360 | 138.93 | 167543.28 | 8377.16 | Paid | 159166.12 | 2024-Q1
EXP-001387 | 2024-01-20 | BOQ-PKG-07-01387 | PKG-07 | INV-PKG-07-023-01387 | 294.84 | 63626.33 | 3181.32 | Approved Pending Payment | 60445.01 | 2024-Q1
EXP-001694 | 2024-01-20 | BOQ-PKG-04-01694 | PKG-04 | INV-PKG-04-015-01694 | 231 | 213545.98 | 10677.3 | Paid | 202868.68 | 2024-Q1
EXP-003683 | 2024-01-20 | BOQ-PKG-03-01693 | PKG-03 | INV-PKG-03-009-03683 | 229.67 | 112030.79 | 5601.54 | Paid | 106429.25 | 2024-Q1
EXP-004084 | 2024-01-20 | BOQ-PKG-04-00104 | PKG-04 | INV-PKG-04-025-04084 | 66.15 | 103013.84 | 5150.69 | Under Review | 97863.15 | 2024-Q1
EXP-005720 | 2024-01-20 | BOQ-PKG-10-01740 | PKG-10 | INV-PKG-10-016-05720 | 95.78 | 115767.5 | 5788.38 | Paid | 109979.12 | 2024-Q1
EXP-006184 | 2024-01-20 | BOQ-PKG-04-00214 | PKG-04 | INV-PKG-04-025-06184 | 226.99 | 106125.54 | 5306.28 | Paid | 100819.26 | 2024-Q1
EXP-006396 | 2024-01-20 | BOQ-PKG-06-00426 | PKG-06 | INV-PKG-06-027-06396 | 57.45 | 133116.49 | 6655.82 | Paid | 126460.67 | 2024-Q1
EXP-006759 | 2024-01-20 | BOQ-PKG-09-00789 | PKG-09 | INV-PKG-09-005-06759 | 122.33 | 98603.34 | 4930.17 | Paid | 93673.17 | 2024-Q1
EXP-000159 | 2024-01-21 | BOQ-PKG-09-00159 | PKG-09 | INV-PKG-09-020-00159 | 184.55 | 69461.73 | 3473.09 | Paid | 65988.64 | 2024-Q1
EXP-000252 | 2024-01-21 | BOQ-PKG-02-00252 | PKG-02 | INV-PKG-02-008-00252 | 312.82 | 142088.29 | 7104.41 | Paid | 134983.88 | 2024-Q1
EXP-000475 | 2024-01-21 | BOQ-PKG-05-00475 | PKG-05 | INV-PKG-05-021-00475 | 235.6 | 31112.38 | 1555.62 | Under Review | 29556.76 | 2024-Q1
EXP-000841 | 2024-01-21 | BOQ-PKG-01-00841 | PKG-01 | INV-PKG-01-002-00841 | 73.06 | 38248.68 | 1912.43 | Paid | 36336.25 | 2024-Q1
EXP-002309 | 2024-01-21 | BOQ-PKG-09-00319 | PKG-09 | INV-PKG-09-035-02309 | 445.43 | 94394.88 | 4719.74 | Paid | 89675.14 | 2024-Q1
EXP-004539 | 2024-01-21 | BOQ-PKG-09-00559 | PKG-09 | INV-PKG-09-025-04539 | 60.61 | 206657.32 | 10332.87 | Disputed | 196324.45 | 2024-Q1
EXP-005701 | 2024-01-21 | BOQ-PKG-01-01721 | PKG-01 | INV-PKG-01-032-05701 | 415.43 | 37505.55 | 1875.28 | Paid | 35630.27 | 2024-Q1
EXP-005763 | 2024-01-21 | BOQ-PKG-03-01783 | PKG-03 | INV-PKG-03-024-05763 | 64.6 | 47835.48 | 2391.77 | Paid | 45443.71 | 2024-Q1
EXP-006145 | 2024-01-21 | BOQ-PKG-05-00175 | PKG-05 | INV-PKG-05-021-06145 | 189.09 | 165125.2 | 8256.26 | Paid | 156868.94 | 2024-Q1
EXP-006233 | 2024-01-21 | BOQ-PKG-03-00263 | PKG-03 | INV-PKG-03-004-06233 | 393.28 | 34861.86 | 1743.09 | Paid | 33118.77 | 2024-Q1
EXP-006766 | 2024-01-21 | BOQ-PKG-06-00796 | PKG-06 | INV-PKG-06-012-06766 | 325.14 | 98008.08 | 4900.4 | Disputed | 93107.68 | 2024-Q1
EXP-001084 | 2024-01-22 | BOQ-PKG-04-01084 | PKG-04 | INV-PKG-04-035-01084 | 9.12 | 109830.48 | 5491.52 | Paid | 104338.96 | 2024-Q1
EXP-001559 | 2024-01-22 | BOQ-PKG-09-01559 | PKG-09 | INV-PKG-09-020-01559 | 54.11 | 67153.9 | 3357.7 | Disputed | 63796.2 | 2024-Q1
EXP-002404 | 2024-01-22 | BOQ-PKG-04-00414 | PKG-04 | INV-PKG-04-025-02404 | 259.84 | 160875.39 | 8043.77 | Under Review | 152831.62 | 2024-Q1
EXP-002602 | 2024-01-22 | BOQ-PKG-02-00612 | PKG-02 | INV-PKG-02-013-02602 | 137.01 | 78797.24 | 3939.86 | Disputed | 74857.38 | 2024-Q1
EXP-005779 | 2024-01-22 | BOQ-PKG-09-01799 | PKG-09 | INV-PKG-09-005-05779 | 425.79 | 128267.04 | 6413.35 | Paid | 121853.69 | 2024-Q1
EXP-000625 | 2024-01-23 | BOQ-PKG-05-00625 | PKG-05 | INV-PKG-05-031-00625 | 94.62 | 204802.47 | 10240.12 | Paid | 194562.35 | 2024-Q1
EXP-000651 | 2024-01-23 | BOQ-PKG-01-00651 | PKG-01 | INV-PKG-01-022-00651 | 201.87 | 32651.03 | 1632.55 | Paid | 31018.48 | 2024-Q1
EXP-000941 | 2024-01-23 | BOQ-PKG-01-00941 | PKG-01 | INV-PKG-01-032-00941 | 364.63 | 57308.06 | 2865.4 | Paid | 54442.66 | 2024-Q1
EXP-001153 | 2024-01-23 | BOQ-PKG-03-01153 | PKG-03 | INV-PKG-03-034-01153 | 19.67 | 185633.43 | 9281.67 | Paid | 176351.76 | 2024-Q1
EXP-002083 | 2024-01-23 | BOQ-PKG-03-00093 | PKG-03 | INV-PKG-03-019-02083 | 375.96 | 40674.64 | 2033.73 | Paid | 38640.91 | 2024-Q1
EXP-005237 | 2024-01-23 | BOQ-PKG-07-01257 | PKG-07 | INV-PKG-07-023-05237 | 241.45 | 196374.47 | 9818.72 | Paid | 186555.75 | 2024-Q1
EXP-005696 | 2024-01-23 | BOQ-PKG-06-01716 | PKG-06 | INV-PKG-06-027-05696 | 352.54 | 185932.45 | 9296.62 | Paid | 176635.83 | 2024-Q1
EXP-005903 | 2024-01-23 | BOQ-PKG-03-01923 | PKG-03 | INV-PKG-03-024-05903 | 430.06 | 49060.02 | 2453 | Paid | 46607.02 | 2024-Q1
EXP-006606 | 2024-01-23 | BOQ-PKG-06-00636 | PKG-06 | INV-PKG-06-027-06606 | 295.07 | 141899.92 | 7095 | Paid | 134804.92 | 2024-Q1
EXP-006883 | 2024-01-23 | BOQ-PKG-03-00913 | PKG-03 | INV-PKG-03-024-06883 | 133.32 | 26278.98 | 1313.95 | Paid | 24965.03 | 2024-Q1
EXP-002892 | 2024-01-24 | BOQ-PKG-02-00902 | PKG-02 | INV-PKG-02-023-02892 | 169.47 | 136717.01 | 6835.85 | Approved Pending Payment | 129881.16 | 2024-Q1
EXP-003424 | 2024-01-24 | BOQ-PKG-04-01434 | PKG-04 | INV-PKG-04-030-03424 | 353.22 | 34619.31 | 1730.97 | Paid | 32888.34 | 2024-Q1
EXP-003765 | 2024-01-24 | BOQ-PKG-05-01775 | PKG-05 | INV-PKG-05-021-03765 | 363.22 | 122293.99 | 6114.7 | Under Review | 116179.29 | 2024-Q1
EXP-004814 | 2024-01-24 | BOQ-PKG-04-00834 | PKG-04 | INV-PKG-04-020-04814 | 131.98 | 57697.92 | 2884.9 | Approved Pending Payment | 54813.02 | 2024-Q1
EXP-005522 | 2024-01-24 | BOQ-PKG-02-01542 | PKG-02 | INV-PKG-02-028-05522 | 266.59 | 187853.21 | 9392.66 | Approved Pending Payment | 178460.55 | 2024-Q1
EXP-001464 | 2024-01-25 | BOQ-PKG-04-01464 | PKG-04 | INV-PKG-04-030-01464 | 208.84 | 49178.06 | 2458.9 | Paid | 46719.16 | 2024-Q1
EXP-001483 | 2024-01-25 | BOQ-PKG-03-01483 | PKG-03 | INV-PKG-03-014-01483 | 80.56 | 147052.17 | 7352.61 | Approved Pending Payment | 139699.56 | 2024-Q1
EXP-002278 | 2024-01-25 | BOQ-PKG-08-00288 | PKG-08 | INV-PKG-08-004-02278 | 388.44 | 103991.56 | 5199.58 | Paid | 98791.98 | 2024-Q1
EXP-003567 | 2024-01-25 | BOQ-PKG-07-01577 | PKG-07 | INV-PKG-07-033-03567 | 106.1 | 82901.25 | 4145.06 | Paid | 78756.19 | 2024-Q1
EXP-004115 | 2024-01-25 | BOQ-PKG-05-00135 | PKG-05 | INV-PKG-05-021-04115 | 347.77 | 142281.94 | 7114.1 | Paid | 135167.84 | 2024-Q1
EXP-004246 | 2024-01-25 | BOQ-PKG-06-00266 | PKG-06 | INV-PKG-06-012-04246 | 216.62 | 87869.75 | 4393.49 | Paid | 83476.26 | 2024-Q1
EXP-004756 | 2024-01-25 | BOQ-PKG-06-00776 | PKG-06 | INV-PKG-06-032-04756 | 152.27 | 30393.36 | 1519.67 | Paid | 28873.69 | 2024-Q1
EXP-006846 | 2024-01-25 | BOQ-PKG-06-00876 | PKG-06 | INV-PKG-06-022-06846 | 445.18 | 114626.08 | 5731.3 | Paid | 108894.78 | 2024-Q1
EXP-001081 | 2024-01-26 | BOQ-PKG-01-01081 | PKG-01 | INV-PKG-01-032-01081 | 138.79 | 130589.86 | 6529.49 | Paid | 124060.37 | 2024-Q1
EXP-001256 | 2024-01-26 | BOQ-PKG-06-01256 | PKG-06 | INV-PKG-06-032-01256 | 266.61 | 120992.58 | 6049.63 | Paid | 114942.95 | 2024-Q1
EXP-001573 | 2024-01-26 | BOQ-PKG-03-01573 | PKG-03 | INV-PKG-03-034-01573 | 269.18 | 192035.14 | 9601.76 | Disputed | 182433.38 | 2024-Q1
EXP-001646 | 2024-01-26 | BOQ-PKG-06-01646 | PKG-06 | INV-PKG-06-002-01646 | 404.71 | 130943.2 | 6547.16 | Paid | 124396.04 | 2024-Q1
EXP-002275 | 2024-01-26 | BOQ-PKG-05-00285 | PKG-05 | INV-PKG-05-001-02275 | 222.45 | 148942.82 | 7447.14 | Paid | 141495.68 | 2024-Q1
EXP-002568 | 2024-01-26 | BOQ-PKG-08-00578 | PKG-08 | INV-PKG-08-014-02568 | 152.77 | 35620.11 | 1781.01 | Approved Pending Payment | 33839.1 | 2024-Q1
EXP-002877 | 2024-01-26 | BOQ-PKG-07-00887 | PKG-07 | INV-PKG-07-008-02877 | 285.46 | 88158.2 | 4407.91 | Paid | 83750.29 | 2024-Q1
EXP-005705 | 2024-01-26 | BOQ-PKG-05-01725 | PKG-05 | INV-PKG-05-001-05705 | 54.36 | 149207.31 | 7460.37 | Under Review | 141746.94 | 2024-Q1
EXP-006769 | 2024-01-26 | BOQ-PKG-09-00799 | PKG-09 | INV-PKG-09-015-06769 | 210.57 | 122707.05 | 6135.35 | Paid | 116571.7 | 2024-Q1
EXP-000036 | 2024-01-27 | BOQ-PKG-06-00036 | PKG-06 | INV-PKG-06-002-00036 | 245.43 | 189412.67 | 9470.63 | Paid | 179942.04 | 2024-Q1
EXP-000403 | 2024-01-27 | BOQ-PKG-03-00403 | PKG-03 | INV-PKG-03-019-00403 | 246.2 | 109734.78 | 5486.74 | Paid | 104248.04 | 2024-Q1
EXP-001957 | 2024-01-27 | BOQ-PKG-07-01957 | PKG-07 | INV-PKG-07-033-01957 | 219.35 | 35649.05 | 1782.45 | Approved Pending Payment | 33866.6 | 2024-Q1
EXP-004650 | 2024-01-27 | BOQ-PKG-10-00670 | PKG-10 | INV-PKG-10-031-04650 | 149.49 | 38642.47 | 1932.12 | Disputed | 36710.35 | 2024-Q1
EXP-006386 | 2024-01-27 | BOQ-PKG-06-00416 | PKG-06 | INV-PKG-06-017-06386 | 8.12 | 143235.6 | 7161.78 | Approved Pending Payment | 136073.82 | 2024-Q1
EXP-000402 | 2024-01-28 | BOQ-PKG-02-00402 | PKG-02 | INV-PKG-02-018-00402 | 257.25 | 200577.12 | 10028.86 | Approved Pending Payment | 190548.26 | 2024-Q1
EXP-000858 | 2024-01-28 | BOQ-PKG-08-00858 | PKG-08 | INV-PKG-08-019-00858 | 297.42 | 92909.47 | 4645.47 | Paid | 88264 | 2024-Q1
EXP-001208 | 2024-01-28 | BOQ-PKG-08-01208 | PKG-08 | INV-PKG-08-019-01208 | 8.1 | 66621.75 | 3331.09 | Paid | 63290.66 | 2024-Q1
EXP-001232 | 2024-01-28 | BOQ-PKG-02-01232 | PKG-02 | INV-PKG-02-008-01232 | 58.06 | 145894.55 | 7294.73 | Paid | 138599.82 | 2024-Q1
EXP-003252 | 2024-01-28 | BOQ-PKG-02-01262 | PKG-02 | INV-PKG-02-033-03252 | 57.58 | 192690.9 | 9634.54 | Paid | 183056.36 | 2024-Q1
EXP-004982 | 2024-01-28 | BOQ-PKG-02-01002 | PKG-02 | INV-PKG-02-013-04982 | 410.79 | 77547.37 | 3877.37 | Paid | 73670 | 2024-Q1
EXP-006490 | 2024-01-28 | BOQ-PKG-10-00520 | PKG-10 | INV-PKG-10-016-06490 | 308.22 | 181267.71 | 9063.39 | Approved Pending Payment | 172204.32 | 2024-Q1
EXP-006916 | 2024-01-28 | BOQ-PKG-06-00946 | PKG-06 | INV-PKG-06-022-06916 | 202.47 | 56667.45 | 2833.37 | Paid | 53834.08 | 2024-Q1
EXP-000818 | 2024-01-29 | BOQ-PKG-08-00818 | PKG-08 | INV-PKG-08-014-00818 | 219.1 | 85838 | 4291.9 | Paid | 81546.1 | 2024-Q1
EXP-001172 | 2024-01-29 | BOQ-PKG-02-01172 | PKG-02 | INV-PKG-02-018-01172 | 401.06 | 70926.95 | 3546.35 | Approved Pending Payment | 67380.6 | 2024-Q1
EXP-006399 | 2024-01-29 | BOQ-PKG-09-00429 | PKG-09 | INV-PKG-09-030-06399 | 440.12 | 95011.96 | 4750.6 | Paid | 90261.36 | 2024-Q1
EXP-000016 | 2024-01-30 | BOQ-PKG-06-00016 | PKG-06 | INV-PKG-06-017-00016 | 369.18 | 32391.91 | 1619.6 | Disputed | 30772.31 | 2024-Q1
EXP-000032 | 2024-01-30 | BOQ-PKG-02-00032 | PKG-02 | INV-PKG-02-033-00032 | 329.31 | 85435.14 | 4271.76 | Paid | 81163.38 | 2024-Q1
EXP-000542 | 2024-01-30 | BOQ-PKG-02-00542 | PKG-02 | INV-PKG-02-018-00542 | 170.83 | 89911.32 | 4495.57 | Paid | 85415.75 | 2024-Q1
EXP-003556 | 2024-01-30 | BOQ-PKG-06-01566 | PKG-06 | INV-PKG-06-022-03556 | 378.59 | 163765.6 | 8188.28 | Paid | 155577.32 | 2024-Q1
EXP-006141 | 2024-01-30 | BOQ-PKG-01-00171 | PKG-01 | INV-PKG-01-017-06141 | 42.18 | 114995.94 | 5749.8 | Approved Pending Payment | 109246.14 | 2024-Q1
EXP-006239 | 2024-01-30 | BOQ-PKG-09-00269 | PKG-09 | INV-PKG-09-010-06239 | 99.6 | 66792.72 | 3339.64 | Paid | 63453.08 | 2024-Q1
EXP-002217 | 2024-01-31 | BOQ-PKG-07-00227 | PKG-07 | INV-PKG-07-013-02217 | 72.47 | 40291.62 | 2014.58 | Paid | 38277.04 | 2024-Q1
EXP-002957 | 2024-01-31 | BOQ-PKG-07-00967 | PKG-07 | INV-PKG-07-018-02957 | 112.63 | 103031.06 | 5151.55 | Under Review | 97879.51 | 2024-Q1
EXP-003522 | 2024-01-31 | BOQ-PKG-02-01532 | PKG-02 | INV-PKG-02-023-03522 | 285.58 | 145968.16 | 7298.41 | Paid | 138669.75 | 2024-Q1
EXP-003977 | 2024-01-31 | BOQ-PKG-07-01987 | PKG-07 | INV-PKG-07-023-03977 | 327.49 | 140561.82 | 7028.09 | Approved Pending Payment | 133533.73 | 2024-Q1
EXP-004148 | 2024-01-31 | BOQ-PKG-08-00168 | PKG-08 | INV-PKG-08-019-04148 | 175.34 | 175536.24 | 8776.81 | Paid | 166759.43 | 2024-Q1
EXP-006060 | 2024-01-31 | BOQ-PKG-10-00090 | PKG-10 | INV-PKG-10-006-06060 | 220.8 | 63210.48 | 3160.52 | Paid | 60049.96 | 2024-Q1
EXP-006344 | 2024-01-31 | BOQ-PKG-04-00374 | PKG-04 | INV-PKG-04-010-06344 | 281.33 | 192138.48 | 9606.92 | Disputed | 182531.56 | 2024-Q1
EXP-000622 | 2024-02-01 | BOQ-PKG-02-00622 | PKG-02 | INV-PKG-02-028-00622 | 296.03 | 137358.26 | 6867.91 | Paid | 130490.35 | 2024-Q1
EXP-002152 | 2024-02-01 | BOQ-PKG-02-00162 | PKG-02 | INV-PKG-02-018-02152 | 32.58 | 195235.8 | 9761.79 | Paid | 185474.01 | 2024-Q1
EXP-002739 | 2024-02-01 | BOQ-PKG-09-00749 | PKG-09 | INV-PKG-09-010-02739 | 321.5 | 152223.1 | 7611.16 | Paid | 144611.94 | 2024-Q1
EXP-004867 | 2024-02-01 | BOQ-PKG-07-00887 | PKG-07 | INV-PKG-07-003-04867 | 269.79 | 132522.18 | 6626.11 | Approved Pending Payment | 125896.07 | 2024-Q1
EXP-005436 | 2024-02-01 | BOQ-PKG-06-01456 | PKG-06 | INV-PKG-06-012-05436 | 27.97 | 27171.6 | 1358.58 | Paid | 25813.02 | 2024-Q1
EXP-000957 | 2024-02-02 | BOQ-PKG-07-00957 | PKG-07 | INV-PKG-07-013-00957 | 303.76 | 125415.18 | 6270.76 | Paid | 119144.42 | 2024-Q1
EXP-001125 | 2024-02-02 | BOQ-PKG-05-01125 | PKG-05 | INV-PKG-05-006-01125 | 348.76 | 53859.6 | 2692.98 | Paid | 51166.62 | 2024-Q1
EXP-003420 | 2024-02-02 | BOQ-PKG-10-01430 | PKG-10 | INV-PKG-10-026-03420 | 114.21 | 141202.67 | 7060.13 | Paid | 134142.54 | 2024-Q1
EXP-003927 | 2024-02-02 | BOQ-PKG-07-01937 | PKG-07 | INV-PKG-07-008-03927 | 292.53 | 137594.82 | 6879.74 | Paid | 130715.08 | 2024-Q1
EXP-001229 | 2024-02-03 | BOQ-PKG-09-01229 | PKG-09 | INV-PKG-09-005-01229 | 115.97 | 193492.44 | 9674.62 | Paid | 183817.82 | 2024-Q1
EXP-003734 | 2024-02-03 | BOQ-PKG-04-01744 | PKG-04 | INV-PKG-04-025-03734 | 438.16 | 66152.86 | 3307.64 | Paid | 62845.22 | 2024-Q1
EXP-005312 | 2024-02-03 | BOQ-PKG-02-01332 | PKG-02 | INV-PKG-02-028-05312 | 93.79 | 108823.1 | 5441.16 | Paid | 103381.94 | 2024-Q1
EXP-006059 | 2024-02-03 | BOQ-PKG-09-00089 | PKG-09 | INV-PKG-09-005-06059 | 204.17 | 210248.29 | 10512.41 | Paid | 199735.88 | 2024-Q1
EXP-001922 | 2024-02-04 | BOQ-PKG-02-01922 | PKG-02 | INV-PKG-02-033-01922 | 425.16 | 53488.24 | 2674.41 | Paid | 50813.83 | 2024-Q1
EXP-002700 | 2024-02-04 | BOQ-PKG-10-00710 | PKG-10 | INV-PKG-10-006-02700 | 165.21 | 192850.18 | 9642.51 | Paid | 183207.67 | 2024-Q1
EXP-003445 | 2024-02-04 | BOQ-PKG-05-01455 | PKG-05 | INV-PKG-05-016-03445 | 269.34 | 186319.66 | 9315.98 | Paid | 177003.68 | 2024-Q1
EXP-003698 | 2024-02-04 | BOQ-PKG-08-01708 | PKG-08 | INV-PKG-08-024-03698 | 347.08 | 201642.21 | 10082.11 | Paid | 191560.1 | 2024-Q1
EXP-003879 | 2024-02-04 | BOQ-PKG-09-01889 | PKG-09 | INV-PKG-09-030-03879 | 447.17 | 59137.75 | 2956.89 | Paid | 56180.86 | 2024-Q1
EXP-004601 | 2024-02-04 | BOQ-PKG-01-00621 | PKG-01 | INV-PKG-01-017-04601 | 133.25 | 33413.25 | 1670.66 | Paid | 31742.59 | 2024-Q1
EXP-004873 | 2024-02-04 | BOQ-PKG-03-00893 | PKG-03 | INV-PKG-03-009-04873 | 276.51 | 106328.45 | 5316.42 | Paid | 101012.03 | 2024-Q1
EXP-005489 | 2024-02-04 | BOQ-PKG-09-01509 | PKG-09 | INV-PKG-09-030-05489 | 311.15 | 125672.18 | 6283.61 | Paid | 119388.57 | 2024-Q1
EXP-005508 | 2024-02-04 | BOQ-PKG-08-01528 | PKG-08 | INV-PKG-08-014-05508 | 367.4 | 44938.34 | 2246.92 | Paid | 42691.42 | 2024-Q1
EXP-000834 | 2024-02-05 | BOQ-PKG-04-00834 | PKG-04 | INV-PKG-04-030-00834 | 140.16 | 193164.83 | 9658.24 | Paid | 183506.59 | 2024-Q1
EXP-000910 | 2024-02-05 | BOQ-PKG-10-00910 | PKG-10 | INV-PKG-10-001-00910 | 202.63 | 172221.5 | 8611.08 | Paid | 163610.42 | 2024-Q1
EXP-001185 | 2024-02-05 | BOQ-PKG-05-01185 | PKG-05 | INV-PKG-05-031-01185 | 170.99 | 51954.65 | 2597.73 | Under Review | 49356.92 | 2024-Q1
EXP-001415 | 2024-02-05 | BOQ-PKG-05-01415 | PKG-05 | INV-PKG-05-016-01415 | 64.35 | 149624.37 | 7481.22 | Disputed | 142143.15 | 2024-Q1
EXP-001435 | 2024-02-05 | BOQ-PKG-05-01435 | PKG-05 | INV-PKG-05-001-01435 | 276.23 | 92004.53 | 4600.23 | Approved Pending Payment | 87404.3 | 2024-Q1
EXP-001830 | 2024-02-05 | BOQ-PKG-10-01830 | PKG-10 | INV-PKG-10-011-01830 | 81.32 | 131462.95 | 6573.15 | Paid | 124889.8 | 2024-Q1
EXP-002690 | 2024-02-05 | BOQ-PKG-10-00700 | PKG-10 | INV-PKG-10-031-02690 | 70.7 | 29962.59 | 1498.13 | Paid | 28464.46 | 2024-Q1
EXP-002979 | 2024-02-05 | BOQ-PKG-09-00989 | PKG-09 | INV-PKG-09-005-02979 | 159.33 | 149487.29 | 7474.36 | Under Review | 142012.93 | 2024-Q1
EXP-003045 | 2024-02-05 | BOQ-PKG-05-01055 | PKG-05 | INV-PKG-05-001-03045 | 154.96 | 178879.17 | 8943.96 | Paid | 169935.21 | 2024-Q1
EXP-003674 | 2024-02-05 | BOQ-PKG-04-01684 | PKG-04 | INV-PKG-04-035-03674 | 67.85 | 104300.71 | 5215.04 | Approved Pending Payment | 99085.67 | 2024-Q1
EXP-004813 | 2024-02-05 | BOQ-PKG-03-00833 | PKG-03 | INV-PKG-03-019-04813 | 321.9 | 102142.02 | 5107.1 | Paid | 97034.92 | 2024-Q1
EXP-004833 | 2024-02-05 | BOQ-PKG-03-00853 | PKG-03 | INV-PKG-03-004-04833 | 196.87 | 101060.47 | 5053.02 | Approved Pending Payment | 96007.45 | 2024-Q1
EXP-003689 | 2024-02-06 | BOQ-PKG-09-01699 | PKG-09 | INV-PKG-09-015-03689 | 423.14 | 139567.38 | 6978.37 | Paid | 132589.01 | 2024-Q1
EXP-004415 | 2024-02-06 | BOQ-PKG-05-00435 | PKG-05 | INV-PKG-05-006-04415 | 197.13 | 127593.92 | 6379.7 | Paid | 121214.22 | 2024-Q1
EXP-006472 | 2024-02-06 | BOQ-PKG-02-00502 | PKG-02 | INV-PKG-02-033-06472 | 233.05 | 92574.31 | 4628.72 | Paid | 87945.59 | 2024-Q1
EXP-000318 | 2024-02-07 | BOQ-PKG-08-00318 | PKG-08 | INV-PKG-08-004-00318 | 315.03 | 163563.99 | 8178.2 | Disputed | 155385.79 | 2024-Q1
EXP-002764 | 2024-02-07 | BOQ-PKG-04-00774 | PKG-04 | INV-PKG-04-035-02764 | 204.47 | 136017.1 | 6800.86 | Approved Pending Payment | 129216.24 | 2024-Q1
EXP-003499 | 2024-02-07 | BOQ-PKG-09-01509 | PKG-09 | INV-PKG-09-035-03499 | 34.36 | 150327.68 | 7516.38 | Paid | 142811.3 | 2024-Q1
EXP-004171 | 2024-02-07 | BOQ-PKG-01-00191 | PKG-01 | INV-PKG-01-007-04171 | 245.85 | 190423.8 | 9521.19 | Paid | 180902.61 | 2024-Q1
EXP-005099 | 2024-02-07 | BOQ-PKG-09-01119 | PKG-09 | INV-PKG-09-025-05099 | 357.8 | 24024.21 | 1201.21 | Paid | 22823 | 2024-Q1
EXP-006745 | 2024-02-07 | BOQ-PKG-05-00775 | PKG-05 | INV-PKG-05-026-06745 | 237.36 | 172264.82 | 8613.24 | Approved Pending Payment | 163651.58 | 2024-Q1
EXP-000760 | 2024-02-08 | BOQ-PKG-10-00760 | PKG-10 | INV-PKG-10-026-00760 | 156.77 | 179337.03 | 8966.85 | Paid | 170370.18 | 2024-Q1
EXP-002013 | 2024-02-08 | BOQ-PKG-03-00023 | PKG-03 | INV-PKG-03-019-02013 | 73 | 136270.49 | 6813.52 | Paid | 129456.97 | 2024-Q1
EXP-002332 | 2024-02-08 | BOQ-PKG-02-00342 | PKG-02 | INV-PKG-02-023-02332 | 256.6 | 42973.12 | 2148.66 | Approved Pending Payment | 40824.46 | 2024-Q1
EXP-002335 | 2024-02-08 | BOQ-PKG-05-00345 | PKG-05 | INV-PKG-05-026-02335 | 110.48 | 165057.69 | 8252.88 | Approved Pending Payment | 156804.81 | 2024-Q1
EXP-002513 | 2024-02-08 | BOQ-PKG-03-00523 | PKG-03 | INV-PKG-03-029-02513 | 205.53 | 166167.69 | 8308.38 | Paid | 157859.31 | 2024-Q1
EXP-003460 | 2024-02-08 | BOQ-PKG-10-01470 | PKG-10 | INV-PKG-10-031-03460 | 249.18 | 131926.13 | 6596.31 | Paid | 125329.82 | 2024-Q1
EXP-004778 | 2024-02-08 | BOQ-PKG-08-00798 | PKG-08 | INV-PKG-08-019-04778 | 150.59 | 102362.33 | 5118.12 | Under Review | 97244.21 | 2024-Q1
EXP-005051 | 2024-02-08 | BOQ-PKG-01-01071 | PKG-01 | INV-PKG-01-012-05051 | 202.18 | 138401.11 | 6920.06 | Paid | 131481.05 | 2024-Q1
EXP-005434 | 2024-02-08 | BOQ-PKG-04-01454 | PKG-04 | INV-PKG-04-010-05434 | 417.16 | 205090.82 | 10254.54 | Paid | 194836.28 | 2024-Q1
EXP-001900 | 2024-02-09 | BOQ-PKG-10-01900 | PKG-10 | INV-PKG-10-011-01900 | 45.91 | 151163.33 | 7558.17 | Under Review | 143605.16 | 2024-Q1
EXP-003553 | 2024-02-09 | BOQ-PKG-03-01563 | PKG-03 | INV-PKG-03-019-03553 | 135.11 | 98231.93 | 4911.6 | Paid | 93320.33 | 2024-Q1
EXP-004507 | 2024-02-09 | BOQ-PKG-07-00527 | PKG-07 | INV-PKG-07-028-04507 | 269.25 | 77880.07 | 3894 | Paid | 73986.07 | 2024-Q1
EXP-004509 | 2024-02-09 | BOQ-PKG-09-00529 | PKG-09 | INV-PKG-09-030-04509 | 296.64 | 131451.27 | 6572.56 | Paid | 124878.71 | 2024-Q1
EXP-004568 | 2024-02-09 | BOQ-PKG-08-00588 | PKG-08 | INV-PKG-08-019-04568 | 297.29 | 37891.72 | 1894.59 | Approved Pending Payment | 35997.13 | 2024-Q1
EXP-005605 | 2024-02-09 | BOQ-PKG-05-01625 | PKG-05 | INV-PKG-05-006-05605 | 8.54 | 67374.65 | 3368.73 | Under Review | 64005.92 | 2024-Q1
EXP-006444 | 2024-02-09 | BOQ-PKG-04-00474 | PKG-04 | INV-PKG-04-005-06444 | 98.08 | 182051.06 | 9102.55 | Paid | 172948.51 | 2024-Q1
EXP-001755 | 2024-02-10 | BOQ-PKG-05-01755 | PKG-05 | INV-PKG-05-006-01755 | 66 | 54312.58 | 2715.63 | Paid | 51596.95 | 2024-Q1
EXP-003752 | 2024-02-10 | BOQ-PKG-02-01762 | PKG-02 | INV-PKG-02-008-03752 | 251.86 | 53410.51 | 2670.53 | Under Review | 50739.98 | 2024-Q1
EXP-005068 | 2024-02-10 | BOQ-PKG-08-01088 | PKG-08 | INV-PKG-08-029-05068 | 169.61 | 118749.84 | 5937.49 | Paid | 112812.35 | 2024-Q1
EXP-005581 | 2024-02-10 | BOQ-PKG-01-01601 | PKG-01 | INV-PKG-01-017-05581 | 238.99 | 43391.7 | 2169.58 | Under Review | 41222.12 | 2024-Q1
EXP-005878 | 2024-02-10 | BOQ-PKG-08-01898 | PKG-08 | INV-PKG-08-034-05878 | 39.58 | 159455.99 | 7972.8 | Paid | 151483.19 | 2024-Q1
EXP-002031 | 2024-02-11 | BOQ-PKG-01-00041 | PKG-01 | INV-PKG-01-002-02031 | 189.6 | 104615.74 | 5230.79 | Paid | 99384.95 | 2024-Q1
EXP-002086 | 2024-02-11 | BOQ-PKG-06-00096 | PKG-06 | INV-PKG-06-022-02086 | 23.02 | 141647.18 | 7082.36 | Paid | 134564.82 | 2024-Q1
EXP-003330 | 2024-02-11 | BOQ-PKG-10-01340 | PKG-10 | INV-PKG-10-006-03330 | 419.28 | 208228.36 | 10411.42 | Under Review | 197816.94 | 2024-Q1
EXP-004139 | 2024-02-11 | BOQ-PKG-09-00159 | PKG-09 | INV-PKG-09-010-04139 | 200.7 | 120346.63 | 6017.33 | Paid | 114329.3 | 2024-Q1
EXP-004688 | 2024-02-11 | BOQ-PKG-08-00708 | PKG-08 | INV-PKG-08-034-04688 | 352.48 | 119962.71 | 5998.14 | Disputed | 113964.57 | 2024-Q1
EXP-005528 | 2024-02-11 | BOQ-PKG-08-01548 | PKG-08 | INV-PKG-08-034-05528 | 214.53 | 62160.84 | 3108.04 | Paid | 59052.8 | 2024-Q1
EXP-006085 | 2024-02-11 | BOQ-PKG-05-00115 | PKG-05 | INV-PKG-05-031-06085 | 22.87 | 38104.5 | 1905.22 | Paid | 36199.28 | 2024-Q1
EXP-006851 | 2024-02-11 | BOQ-PKG-01-00881 | PKG-01 | INV-PKG-01-027-06851 | 260.14 | 87765.46 | 4388.27 | Paid | 83377.19 | 2024-Q1
EXP-006885 | 2024-02-11 | BOQ-PKG-05-00915 | PKG-05 | INV-PKG-05-026-06885 | 351.07 | 36608.46 | 1830.42 | Under Review | 34778.04 | 2024-Q1
EXP-001014 | 2024-02-12 | BOQ-PKG-04-01014 | PKG-04 | INV-PKG-04-035-01014 | 181.77 | 135245.8 | 6762.29 | Paid | 128483.51 | 2024-Q1
EXP-002535 | 2024-02-12 | BOQ-PKG-05-00545 | PKG-05 | INV-PKG-05-016-02535 | 14.24 | 101164.43 | 5058.22 | Under Review | 96106.21 | 2024-Q1
EXP-004096 | 2024-02-12 | BOQ-PKG-06-00116 | PKG-06 | INV-PKG-06-002-04096 | 284.3 | 93955.51 | 4697.78 | Paid | 89257.73 | 2024-Q1
EXP-005058 | 2024-02-12 | BOQ-PKG-08-01078 | PKG-08 | INV-PKG-08-019-05058 | 361.3 | 79590.13 | 3979.51 | Approved Pending Payment | 75610.62 | 2024-Q1
EXP-005655 | 2024-02-12 | BOQ-PKG-05-01675 | PKG-05 | INV-PKG-05-021-05655 | 277.68 | 140835.38 | 7041.77 | Paid | 133793.61 | 2024-Q1
EXP-006093 | 2024-02-12 | BOQ-PKG-03-00123 | PKG-03 | INV-PKG-03-004-06093 | 268.76 | 131299.94 | 6565 | Paid | 124734.94 | 2024-Q1
EXP-000746 | 2024-02-13 | BOQ-PKG-06-00746 | PKG-06 | INV-PKG-06-012-00746 | 251.61 | 166705.2 | 8335.26 | Approved Pending Payment | 158369.94 | 2024-Q1
EXP-000798 | 2024-02-13 | BOQ-PKG-08-00798 | PKG-08 | INV-PKG-08-029-00798 | 127.33 | 29874.06 | 1493.7 | Under Review | 28380.36 | 2024-Q1
EXP-001724 | 2024-02-13 | BOQ-PKG-04-01724 | PKG-04 | INV-PKG-04-010-01724 | 314.49 | 106230.36 | 5311.52 | Paid | 100918.84 | 2024-Q1
EXP-002392 | 2024-02-13 | BOQ-PKG-02-00402 | PKG-02 | INV-PKG-02-013-02392 | 170.06 | 55081.45 | 2754.07 | Under Review | 52327.38 | 2024-Q1
EXP-002503 | 2024-02-13 | BOQ-PKG-03-00513 | PKG-03 | INV-PKG-03-019-02503 | 78.72 | 96306.53 | 4815.33 | Paid | 91491.2 | 2024-Q1
EXP-002649 | 2024-02-13 | BOQ-PKG-09-00659 | PKG-09 | INV-PKG-09-025-02649 | 244.1 | 197797.37 | 9889.87 | Disputed | 187907.5 | 2024-Q1
EXP-003075 | 2024-02-13 | BOQ-PKG-05-01085 | PKG-05 | INV-PKG-05-031-03075 | 45.6 | 38014.28 | 1900.71 | Approved Pending Payment | 36113.57 | 2024-Q1
EXP-003509 | 2024-02-13 | BOQ-PKG-09-01519 | PKG-09 | INV-PKG-09-010-03509 | 439.77 | 59143.22 | 2957.16 | Paid | 56186.06 | 2024-Q1
EXP-003824 | 2024-02-13 | BOQ-PKG-04-01834 | PKG-04 | INV-PKG-04-010-03824 | 197.87 | 154909.22 | 7745.46 | Paid | 147163.76 | 2024-Q1
EXP-003901 | 2024-02-13 | BOQ-PKG-01-01911 | PKG-01 | INV-PKG-01-017-03901 | 265.72 | 139460.64 | 6973.03 | Paid | 132487.61 | 2024-Q1
EXP-004281 | 2024-02-13 | BOQ-PKG-01-00301 | PKG-01 | INV-PKG-01-012-04281 | 389.77 | 96125.92 | 4806.3 | Paid | 91319.62 | 2024-Q1
EXP-004519 | 2024-02-13 | BOQ-PKG-09-00539 | PKG-09 | INV-PKG-09-005-04519 | 401.41 | 164380.74 | 8219.04 | Disputed | 156161.7 | 2024-Q1
EXP-000436 | 2024-02-14 | BOQ-PKG-06-00436 | PKG-06 | INV-PKG-06-017-00436 | 335.79 | 154459.86 | 7722.99 | Approved Pending Payment | 146736.87 | 2024-Q1
EXP-001233 | 2024-02-14 | BOQ-PKG-03-01233 | PKG-03 | INV-PKG-03-009-01233 | 213.84 | 194999.3 | 9749.96 | Paid | 185249.34 | 2024-Q1
EXP-001498 | 2024-02-14 | BOQ-PKG-08-01498 | PKG-08 | INV-PKG-08-029-01498 | 64.36 | 148665.2 | 7433.26 | Approved Pending Payment | 141231.94 | 2024-Q1
EXP-003496 | 2024-02-14 | BOQ-PKG-06-01506 | PKG-06 | INV-PKG-06-032-03496 | 64.5 | 144433.62 | 7221.68 | Approved Pending Payment | 137211.94 | 2024-Q1
EXP-004655 | 2024-02-14 | BOQ-PKG-05-00675 | PKG-05 | INV-PKG-05-001-04655 | 311.95 | 38140.47 | 1907.02 | Paid | 36233.45 | 2024-Q1
EXP-005028 | 2024-02-14 | BOQ-PKG-08-01048 | PKG-08 | INV-PKG-08-024-05028 | 335.82 | 70116.61 | 3505.83 | Paid | 66610.78 | 2024-Q1
EXP-005261 | 2024-02-14 | BOQ-PKG-01-01281 | PKG-01 | INV-PKG-01-012-05261 | 274.74 | 81748.94 | 4087.45 | Approved Pending Payment | 77661.49 | 2024-Q1
EXP-006398 | 2024-02-14 | BOQ-PKG-08-00428 | PKG-08 | INV-PKG-08-029-06398 | 384.22 | 205820.03 | 10291 | Under Review | 195529.03 | 2024-Q1
EXP-000340 | 2024-02-15 | BOQ-PKG-10-00340 | PKG-10 | INV-PKG-10-026-00340 | 263.01 | 55940.49 | 2797.02 | Paid | 53143.47 | 2024-Q1
EXP-000747 | 2024-02-15 | BOQ-PKG-07-00747 | PKG-07 | INV-PKG-07-013-00747 | 168.2 | 67919.83 | 3395.99 | Paid | 64523.84 | 2024-Q1
EXP-002255 | 2024-02-15 | BOQ-PKG-05-00265 | PKG-05 | INV-PKG-05-016-02255 | 235.07 | 61886.48 | 3094.32 | Paid | 58792.16 | 2024-Q1
EXP-002381 | 2024-02-15 | BOQ-PKG-01-00391 | PKG-01 | INV-PKG-01-002-02381 | 228.77 | 80515.3 | 4025.77 | Approved Pending Payment | 76489.53 | 2024-Q1
EXP-002729 | 2024-02-15 | BOQ-PKG-09-00739 | PKG-09 | INV-PKG-09-035-02729 | 275.54 | 208861.64 | 10443.08 | Paid | 198418.56 | 2024-Q1
EXP-004258 | 2024-02-15 | BOQ-PKG-08-00278 | PKG-08 | INV-PKG-08-024-04258 | 257.49 | 54193.54 | 2709.68 | Paid | 51483.86 | 2024-Q1
EXP-004287 | 2024-02-15 | BOQ-PKG-07-00307 | PKG-07 | INV-PKG-07-018-04287 | 189.26 | 174975.4 | 8748.77 | Paid | 166226.63 | 2024-Q1
EXP-004917 | 2024-02-15 | BOQ-PKG-07-00937 | PKG-07 | INV-PKG-07-018-04917 | 326.11 | 60712.02 | 3035.6 | Paid | 57676.42 | 2024-Q1
EXP-005512 | 2024-02-15 | BOQ-PKG-02-01532 | PKG-02 | INV-PKG-02-018-05512 | 255.07 | 167894.82 | 8394.74 | Paid | 159500.08 | 2024-Q1
EXP-006773 | 2024-02-15 | BOQ-PKG-03-00803 | PKG-03 | INV-PKG-03-019-06773 | 443.28 | 179838.89 | 8991.94 | Paid | 170846.95 | 2024-Q1
EXP-000007 | 2024-02-16 | BOQ-PKG-07-00007 | PKG-07 | INV-PKG-07-008-00007 | 179.4 | 150406.13 | 7520.31 | Paid | 142885.82 | 2024-Q1
EXP-000310 | 2024-02-16 | BOQ-PKG-10-00310 | PKG-10 | INV-PKG-10-031-00310 | 289.34 | 38945.46 | 1947.27 | Paid | 36998.19 | 2024-Q1
EXP-003625 | 2024-02-16 | BOQ-PKG-05-01635 | PKG-05 | INV-PKG-05-021-03625 | 365.71 | 48839.78 | 2441.99 | Paid | 46397.79 | 2024-Q1
EXP-000420 | 2024-02-17 | BOQ-PKG-10-00420 | PKG-10 | INV-PKG-10-001-00420 | 148.8 | 126037.85 | 6301.89 | Paid | 119735.96 | 2024-Q1
EXP-003047 | 2024-02-17 | BOQ-PKG-07-01057 | PKG-07 | INV-PKG-07-003-03047 | 336.93 | 141122.04 | 7056.1 | Paid | 134065.94 | 2024-Q1
EXP-004296 | 2024-02-17 | BOQ-PKG-06-00316 | PKG-06 | INV-PKG-06-027-04296 | 377.03 | 186264.12 | 9313.21 | Approved Pending Payment | 176950.91 | 2024-Q1
EXP-004360 | 2024-02-17 | BOQ-PKG-10-00380 | PKG-10 | INV-PKG-10-021-04360 | 373.81 | 101846.39 | 5092.32 | Paid | 96754.07 | 2024-Q1
EXP-004466 | 2024-02-17 | BOQ-PKG-06-00486 | PKG-06 | INV-PKG-06-022-04466 | 127.68 | 204745.88 | 10237.29 | Paid | 194508.59 | 2024-Q1
EXP-004540 | 2024-02-17 | BOQ-PKG-10-00560 | PKG-10 | INV-PKG-10-026-04540 | 307.7 | 32919.23 | 1645.96 | Paid | 31273.27 | 2024-Q1
EXP-005972 | 2024-02-17 | BOQ-PKG-02-00002 | PKG-02 | INV-PKG-02-023-05972 | 21.48 | 41912.16 | 2095.61 | Under Review | 39816.55 | 2024-Q1
EXP-006534 | 2024-02-17 | BOQ-PKG-04-00564 | PKG-04 | INV-PKG-04-025-06534 | 89.51 | 35413.51 | 1770.68 | Paid | 33642.83 | 2024-Q1
EXP-006740 | 2024-02-17 | BOQ-PKG-10-00770 | PKG-10 | INV-PKG-10-021-06740 | 432.63 | 129620.58 | 6481.03 | Under Review | 123139.55 | 2024-Q1
EXP-000218 | 2024-02-18 | BOQ-PKG-08-00218 | PKG-08 | INV-PKG-08-009-00218 | 216.27 | 89590.29 | 4479.51 | Paid | 85110.78 | 2024-Q1
EXP-000223 | 2024-02-18 | BOQ-PKG-03-00223 | PKG-03 | INV-PKG-03-014-00223 | 28.47 | 174309.46 | 8715.47 | Paid | 165593.99 | 2024-Q1
EXP-002140 | 2024-02-18 | BOQ-PKG-10-00150 | PKG-10 | INV-PKG-10-006-02140 | 87.58 | 165541.21 | 8277.06 | Under Review | 157264.15 | 2024-Q1
EXP-003023 | 2024-02-18 | BOQ-PKG-03-01033 | PKG-03 | INV-PKG-03-014-03023 | 360.54 | 48614.06 | 2430.7 | Paid | 46183.36 | 2024-Q1
EXP-004717 | 2024-02-18 | BOQ-PKG-07-00737 | PKG-07 | INV-PKG-07-028-04717 | 104.44 | 142815.91 | 7140.8 | Paid | 135675.11 | 2024-Q1
EXP-006115 | 2024-02-18 | BOQ-PKG-05-00145 | PKG-05 | INV-PKG-05-026-06115 | 446.32 | 204145.05 | 10207.25 | Paid | 193937.8 | 2024-Q1
EXP-006263 | 2024-02-18 | BOQ-PKG-03-00293 | PKG-03 | INV-PKG-03-034-06263 | 333.96 | 151796.05 | 7589.8 | Under Review | 144206.25 | 2024-Q1
EXP-006479 | 2024-02-18 | BOQ-PKG-09-00509 | PKG-09 | INV-PKG-09-005-06479 | 193.85 | 214689.55 | 10734.48 | Paid | 203955.07 | 2024-Q1
EXP-000471 | 2024-02-19 | BOQ-PKG-01-00471 | PKG-01 | INV-PKG-01-017-00471 | 324.15 | 124491.34 | 6224.57 | Paid | 118266.77 | 2024-Q1
EXP-000765 | 2024-02-19 | BOQ-PKG-05-00765 | PKG-05 | INV-PKG-05-031-00765 | 59.76 | 205089.32 | 10254.47 | Paid | 194834.85 | 2024-Q1
EXP-001305 | 2024-02-19 | BOQ-PKG-05-01305 | PKG-05 | INV-PKG-05-011-01305 | 16.72 | 159632.82 | 7981.64 | Approved Pending Payment | 151651.18 | 2024-Q1
EXP-001348 | 2024-02-19 | BOQ-PKG-08-01348 | PKG-08 | INV-PKG-08-019-01348 | 131.88 | 58111.6 | 2905.58 | Paid | 55206.02 | 2024-Q1
EXP-002383 | 2024-02-19 | BOQ-PKG-03-00393 | PKG-03 | INV-PKG-03-004-02383 | 227.62 | 184733.22 | 9236.66 | Paid | 175496.56 | 2024-Q1
EXP-004263 | 2024-02-19 | BOQ-PKG-03-00283 | PKG-03 | INV-PKG-03-029-04263 | 110.49 | 170834.03 | 8541.7 | Paid | 162292.33 | 2024-Q1
EXP-006131 | 2024-02-19 | BOQ-PKG-01-00161 | PKG-01 | INV-PKG-01-007-06131 | 310.9 | 216166.32 | 10808.32 | Paid | 205358 | 2024-Q1
EXP-000605 | 2024-02-20 | BOQ-PKG-05-00605 | PKG-05 | INV-PKG-05-011-00605 | 88.11 | 182884.77 | 9144.24 | Paid | 173740.53 | 2024-Q1
EXP-000737 | 2024-02-20 | BOQ-PKG-07-00737 | PKG-07 | INV-PKG-07-003-00737 | 281.55 | 169181.74 | 8459.09 | Paid | 160722.65 | 2024-Q1
EXP-002085 | 2024-02-20 | BOQ-PKG-05-00095 | PKG-05 | INV-PKG-05-021-02085 | 196.27 | 36523.3 | 1826.17 | Paid | 34697.13 | 2024-Q1
EXP-003373 | 2024-02-20 | BOQ-PKG-03-01383 | PKG-03 | INV-PKG-03-014-03373 | 395.46 | 82442.69 | 4122.13 | Under Review | 78320.56 | 2024-Q1
EXP-000321 | 2024-02-21 | BOQ-PKG-01-00321 | PKG-01 | INV-PKG-01-007-00321 | 166.22 | 181048.02 | 9052.4 | Paid | 171995.62 | 2024-Q1
EXP-000480 | 2024-02-21 | BOQ-PKG-10-00480 | PKG-10 | INV-PKG-10-026-00480 | 334.88 | 185002.87 | 9250.14 | Under Review | 175752.73 | 2024-Q1
EXP-000590 | 2024-02-21 | BOQ-PKG-10-00590 | PKG-10 | INV-PKG-10-031-00590 | 184.35 | 147394.5 | 7369.72 | Paid | 140024.78 | 2024-Q1
EXP-002391 | 2024-02-21 | BOQ-PKG-01-00401 | PKG-01 | INV-PKG-01-012-02391 | 150.46 | 182752.27 | 9137.61 | Paid | 173614.66 | 2024-Q1
EXP-003079 | 2024-02-21 | BOQ-PKG-09-01089 | PKG-09 | INV-PKG-09-035-03079 | 335.44 | 87214.52 | 4360.73 | Paid | 82853.79 | 2024-Q1
EXP-003724 | 2024-02-21 | BOQ-PKG-04-01734 | PKG-04 | INV-PKG-04-015-03724 | 407.62 | 179897.84 | 8994.89 | Paid | 170902.95 | 2024-Q1
EXP-005246 | 2024-02-21 | BOQ-PKG-06-01266 | PKG-06 | INV-PKG-06-032-05246 | 297.74 | 177613.75 | 8880.69 | Paid | 168733.06 | 2024-Q1
EXP-005248 | 2024-02-21 | BOQ-PKG-08-01268 | PKG-08 | INV-PKG-08-034-05248 | 48.91 | 41900.81 | 2095.04 | Paid | 39805.77 | 2024-Q1
EXP-005355 | 2024-02-21 | BOQ-PKG-05-01375 | PKG-05 | INV-PKG-05-001-05355 | 159.83 | 111681.53 | 5584.08 | Paid | 106097.45 | 2024-Q1
EXP-005497 | 2024-02-21 | BOQ-PKG-07-01517 | PKG-07 | INV-PKG-07-003-05497 | 106.35 | 192664.62 | 9633.23 | Approved Pending Payment | 183031.39 | 2024-Q1
EXP-006884 | 2024-02-21 | BOQ-PKG-04-00914 | PKG-04 | INV-PKG-04-025-06884 | 302.87 | 191884.44 | 9594.22 | Approved Pending Payment | 182290.22 | 2024-Q1
EXP-003382 | 2024-02-22 | BOQ-PKG-02-01392 | PKG-02 | INV-PKG-02-023-03382 | 415.38 | 62414.22 | 3120.71 | Paid | 59293.51 | 2024-Q1
EXP-003679 | 2024-02-22 | BOQ-PKG-09-01689 | PKG-09 | INV-PKG-09-005-03679 | 414.36 | 118625.03 | 5931.25 | Approved Pending Payment | 112693.78 | 2024-Q1
EXP-004078 | 2024-02-22 | BOQ-PKG-08-00098 | PKG-08 | INV-PKG-08-019-04078 | 35.68 | 151307.37 | 7565.37 | Paid | 143742 | 2024-Q1
EXP-004921 | 2024-02-22 | BOQ-PKG-01-00941 | PKG-01 | INV-PKG-01-022-04921 | 108.43 | 194668.87 | 9733.44 | Paid | 184935.43 | 2024-Q1
EXP-000972 | 2024-02-23 | BOQ-PKG-02-00972 | PKG-02 | INV-PKG-02-028-00972 | 228.87 | 137397.72 | 6869.89 | Paid | 130527.83 | 2024-Q1
EXP-001258 | 2024-02-23 | BOQ-PKG-08-01258 | PKG-08 | INV-PKG-08-034-01258 | 214.63 | 96779.38 | 4838.97 | Paid | 91940.41 | 2024-Q1
EXP-001507 | 2024-02-23 | BOQ-PKG-07-01507 | PKG-07 | INV-PKG-07-003-01507 | 271.22 | 181840.51 | 9092.03 | Approved Pending Payment | 172748.48 | 2024-Q1
EXP-004116 | 2024-02-23 | BOQ-PKG-06-00136 | PKG-06 | INV-PKG-06-022-04116 | 90.64 | 105896.44 | 5294.82 | Paid | 100601.62 | 2024-Q1
EXP-004150 | 2024-02-23 | BOQ-PKG-10-00170 | PKG-10 | INV-PKG-10-021-04150 | 309.2 | 189411.68 | 9470.58 | Paid | 179941.1 | 2024-Q1
EXP-004271 | 2024-02-23 | BOQ-PKG-01-00291 | PKG-01 | INV-PKG-01-002-04271 | 337.01 | 67830.39 | 3391.52 | Paid | 64438.87 | 2024-Q1
EXP-004455 | 2024-02-23 | BOQ-PKG-05-00475 | PKG-05 | INV-PKG-05-011-04455 | 304.71 | 207343.6 | 10367.18 | Paid | 196976.42 | 2024-Q1
EXP-006395 | 2024-02-23 | BOQ-PKG-05-00425 | PKG-05 | INV-PKG-05-026-06395 | 336.53 | 211609.61 | 10580.48 | Under Review | 201029.13 | 2024-Q1
EXP-001055 | 2024-02-24 | BOQ-PKG-05-01055 | PKG-05 | INV-PKG-05-006-01055 | 286.92 | 69263.16 | 3463.16 | Approved Pending Payment | 65800 | 2024-Q1
EXP-002178 | 2024-02-24 | BOQ-PKG-08-00188 | PKG-08 | INV-PKG-08-009-02178 | 305.73 | 98380.72 | 4919.04 | Paid | 93461.68 | 2024-Q1
EXP-004818 | 2024-02-24 | BOQ-PKG-08-00838 | PKG-08 | INV-PKG-08-024-04818 | 48.9 | 122058.45 | 6102.92 | Approved Pending Payment | 115955.53 | 2024-Q1
EXP-005218 | 2024-02-24 | BOQ-PKG-08-01238 | PKG-08 | INV-PKG-08-004-05218 | 66.14 | 76090.17 | 3804.51 | Disputed | 72285.66 | 2024-Q1
EXP-005769 | 2024-02-24 | BOQ-PKG-09-01789 | PKG-09 | INV-PKG-09-030-05769 | 65.87 | 112018.8 | 5600.94 | Approved Pending Payment | 106417.86 | 2024-Q1
EXP-006273 | 2024-02-24 | BOQ-PKG-03-00303 | PKG-03 | INV-PKG-03-009-06273 | 447.1 | 27914.22 | 1395.71 | Paid | 26518.51 | 2024-Q1
EXP-006285 | 2024-02-24 | BOQ-PKG-05-00315 | PKG-05 | INV-PKG-05-021-06285 | 361.97 | 48232.54 | 2411.63 | Paid | 45820.91 | 2024-Q1
EXP-006569 | 2024-02-24 | BOQ-PKG-09-00599 | PKG-09 | INV-PKG-09-025-06569 | 98.62 | 160889.62 | 8044.48 | Paid | 152845.14 | 2024-Q1
EXP-000732 | 2024-02-25 | BOQ-PKG-02-00732 | PKG-02 | INV-PKG-02-033-00732 | 150.35 | 135441.76 | 6772.09 | Paid | 128669.67 | 2024-Q1
EXP-002497 | 2024-02-25 | BOQ-PKG-07-00507 | PKG-07 | INV-PKG-07-013-02497 | 377.83 | 56468.08 | 2823.4 | Paid | 53644.68 | 2024-Q1
EXP-003174 | 2024-02-25 | BOQ-PKG-04-01184 | PKG-04 | INV-PKG-04-025-03174 | 75.15 | 35764.24 | 1788.21 | Paid | 33976.03 | 2024-Q1
EXP-003215 | 2024-02-25 | BOQ-PKG-05-01225 | PKG-05 | INV-PKG-05-031-03215 | 345.78 | 130061.45 | 6503.07 | Approved Pending Payment | 123558.38 | 2024-Q1
EXP-004511 | 2024-02-25 | BOQ-PKG-01-00531 | PKG-01 | INV-PKG-01-032-04511 | 213.83 | 168285 | 8414.25 | Paid | 159870.75 | 2024-Q1
EXP-004742 | 2024-02-25 | BOQ-PKG-02-00762 | PKG-02 | INV-PKG-02-018-04742 | 319.24 | 76727.25 | 3836.36 | Paid | 72890.89 | 2024-Q1
EXP-005227 | 2024-02-25 | BOQ-PKG-07-01247 | PKG-07 | INV-PKG-07-013-05227 | 89.16 | 145802.08 | 7290.1 | Paid | 138511.98 | 2024-Q1
EXP-005730 | 2024-02-25 | BOQ-PKG-10-01750 | PKG-10 | INV-PKG-10-026-05730 | 347.83 | 54338.6 | 2716.93 | Paid | 51621.67 | 2024-Q1
EXP-005985 | 2024-02-25 | BOQ-PKG-05-00015 | PKG-05 | INV-PKG-05-001-05985 | 314.44 | 204637.95 | 10231.9 | Approved Pending Payment | 194406.05 | 2024-Q1
EXP-006659 | 2024-02-25 | BOQ-PKG-09-00689 | PKG-09 | INV-PKG-09-010-06659 | 61.48 | 190155.94 | 9507.8 | Paid | 180648.14 | 2024-Q1
EXP-001058 | 2024-02-26 | BOQ-PKG-08-01058 | PKG-08 | INV-PKG-08-009-01058 | 136.92 | 74128.07 | 3706.4 | Paid | 70421.67 | 2024-Q1
EXP-001094 | 2024-02-26 | BOQ-PKG-04-01094 | PKG-04 | INV-PKG-04-010-01094 | 436.91 | 155452.33 | 7772.62 | Paid | 147679.71 | 2024-Q1
EXP-002074 | 2024-02-26 | BOQ-PKG-04-00084 | PKG-04 | INV-PKG-04-010-02074 | 71.9 | 100483.76 | 5024.19 | Paid | 95459.57 | 2024-Q1
EXP-002407 | 2024-02-26 | BOQ-PKG-07-00417 | PKG-07 | INV-PKG-07-028-02407 | 154.13 | 100746.78 | 5037.34 | Paid | 95709.44 | 2024-Q1
EXP-002779 | 2024-02-26 | BOQ-PKG-09-00789 | PKG-09 | INV-PKG-09-015-02779 | 431.08 | 198361.62 | 9918.08 | Approved Pending Payment | 188443.54 | 2024-Q1
EXP-002911 | 2024-02-26 | BOQ-PKG-01-00921 | PKG-01 | INV-PKG-01-007-02911 | 103.37 | 107576.21 | 5378.81 | Paid | 102197.4 | 2024-Q1
EXP-003575 | 2024-02-26 | BOQ-PKG-05-01585 | PKG-05 | INV-PKG-05-006-03575 | 17.99 | 136246.58 | 6812.33 | Approved Pending Payment | 129434.25 | 2024-Q1
EXP-003907 | 2024-02-26 | BOQ-PKG-07-01917 | PKG-07 | INV-PKG-07-023-03907 | 169.27 | 114444.39 | 5722.22 | Paid | 108722.17 | 2024-Q1
EXP-004972 | 2024-02-26 | BOQ-PKG-02-00992 | PKG-02 | INV-PKG-02-003-04972 | 134.77 | 175344.41 | 8767.22 | Paid | 166577.19 | 2024-Q1
EXP-005409 | 2024-02-26 | BOQ-PKG-09-01429 | PKG-09 | INV-PKG-09-020-05409 | 163.39 | 146411.87 | 7320.59 | Under Review | 139091.28 | 2024-Q1
EXP-005452 | 2024-02-26 | BOQ-PKG-02-01472 | PKG-02 | INV-PKG-02-028-05452 | 138.7 | 83841.84 | 4192.09 | Paid | 79649.75 | 2024-Q1
EXP-006762 | 2024-02-26 | BOQ-PKG-02-00792 | PKG-02 | INV-PKG-02-008-06762 | 165.31 | 70963.64 | 3548.18 | Paid | 67415.46 | 2024-Q1
EXP-002727 | 2024-02-27 | BOQ-PKG-07-00737 | PKG-07 | INV-PKG-07-033-02727 | 165.92 | 163486.43 | 8174.32 | Paid | 155312.11 | 2024-Q1
EXP-002754 | 2024-02-27 | BOQ-PKG-04-00764 | PKG-04 | INV-PKG-04-025-02754 | 444.12 | 71033.21 | 3551.66 | Paid | 67481.55 | 2024-Q1
EXP-006159 | 2024-02-27 | BOQ-PKG-09-00189 | PKG-09 | INV-PKG-09-035-06159 | 101.43 | 99196.59 | 4959.83 | Paid | 94236.76 | 2024-Q1
EXP-000654 | 2024-02-28 | BOQ-PKG-04-00654 | PKG-04 | INV-PKG-04-025-00654 | 302.5 | 180142.03 | 9007.1 | Approved Pending Payment | 171134.93 | 2024-Q1
EXP-000714 | 2024-02-28 | BOQ-PKG-04-00714 | PKG-04 | INV-PKG-04-015-00714 | 351.89 | 72934.27 | 3646.71 | Paid | 69287.56 | 2024-Q1
EXP-001851 | 2024-02-28 | BOQ-PKG-01-01851 | PKG-01 | INV-PKG-01-032-01851 | 197.39 | 171788.48 | 8589.42 | Paid | 163199.06 | 2024-Q1
EXP-004574 | 2024-02-28 | BOQ-PKG-04-00594 | PKG-04 | INV-PKG-04-025-04574 | 377.87 | 189927.41 | 9496.37 | Paid | 180431.04 | 2024-Q1
EXP-005048 | 2024-02-28 | BOQ-PKG-08-01068 | PKG-08 | INV-PKG-08-009-05048 | 141.15 | 145822.57 | 7291.13 | Paid | 138531.44 | 2024-Q1
EXP-005456 | 2024-02-28 | BOQ-PKG-06-01476 | PKG-06 | INV-PKG-06-032-05456 | 388.26 | 55174.26 | 2758.71 | Paid | 52415.55 | 2024-Q1
EXP-006307 | 2024-02-28 | BOQ-PKG-07-00337 | PKG-07 | INV-PKG-07-008-06307 | 298.46 | 135488.99 | 6774.45 | Paid | 128714.54 | 2024-Q1
EXP-006643 | 2024-02-28 | BOQ-PKG-03-00673 | PKG-03 | INV-PKG-03-029-06643 | 80.92 | 98989.39 | 4949.47 | Paid | 94039.92 | 2024-Q1
EXP-006852 | 2024-02-28 | BOQ-PKG-02-00882 | PKG-02 | INV-PKG-02-028-06852 | 25.03 | 64830.19 | 3241.51 | Paid | 61588.68 | 2024-Q1
EXP-000487 | 2024-02-29 | BOQ-PKG-07-00487 | PKG-07 | INV-PKG-07-033-00487 | 161.74 | 182373.14 | 9118.66 | Paid | 173254.48 | 2024-Q1
EXP-000888 | 2024-02-29 | BOQ-PKG-08-00888 | PKG-08 | INV-PKG-08-014-00888 | 350.06 | 133155.91 | 6657.8 | Paid | 126498.11 | 2024-Q1
EXP-001357 | 2024-02-29 | BOQ-PKG-07-01357 | PKG-07 | INV-PKG-07-028-01357 | 186.5 | 152247.87 | 7612.39 | Approved Pending Payment | 144635.48 | 2024-Q1
EXP-002250 | 2024-02-29 | BOQ-PKG-10-00260 | PKG-10 | INV-PKG-10-011-02250 | 70.69 | 91376.29 | 4568.81 | Under Review | 86807.48 | 2024-Q1
EXP-002799 | 2024-02-29 | BOQ-PKG-09-00809 | PKG-09 | INV-PKG-09-035-02799 | 290.34 | 36627.61 | 1831.38 | Paid | 34796.23 | 2024-Q1
EXP-003555 | 2024-02-29 | BOQ-PKG-05-01565 | PKG-05 | INV-PKG-05-021-03555 | 253.98 | 160257.7 | 8012.89 | Paid | 152244.81 | 2024-Q1
EXP-003656 | 2024-02-29 | BOQ-PKG-06-01666 | PKG-06 | INV-PKG-06-017-03656 | 354.29 | 92813.34 | 4640.67 | Approved Pending Payment | 88172.67 | 2024-Q1
EXP-005589 | 2024-02-29 | BOQ-PKG-09-01609 | PKG-09 | INV-PKG-09-025-05589 | 183.61 | 55119.43 | 2755.97 | Paid | 52363.46 | 2024-Q1
EXP-004133 | 2024-03-01 | BOQ-PKG-03-00153 | PKG-03 | INV-PKG-03-004-04133 | 76.6 | 75897.43 | 3794.87 | Paid | 72102.56 | 2024-Q1
EXP-001679 | 2024-03-02 | BOQ-PKG-09-01679 | PKG-09 | INV-PKG-09-035-01679 | 181.49 | 91453.78 | 4572.69 | Under Review | 86881.09 | 2024-Q1
EXP-002439 | 2024-03-02 | BOQ-PKG-09-00449 | PKG-09 | INV-PKG-09-025-02439 | 295.74 | 189248.6 | 9462.43 | Disputed | 179786.17 | 2024-Q1
EXP-004349 | 2024-03-02 | BOQ-PKG-09-00369 | PKG-09 | INV-PKG-09-010-04349 | 92.46 | 65709.85 | 3285.49 | Paid | 62424.36 | 2024-Q1
EXP-005198 | 2024-03-02 | BOQ-PKG-08-01218 | PKG-08 | INV-PKG-08-019-05198 | 134.27 | 177202.42 | 8860.12 | Paid | 168342.3 | 2024-Q1
EXP-006863 | 2024-03-02 | BOQ-PKG-03-00893 | PKG-03 | INV-PKG-03-004-06863 | 251.58 | 74619.61 | 3730.98 | Paid | 70888.63 | 2024-Q1
EXP-001466 | 2024-03-03 | BOQ-PKG-06-01466 | PKG-06 | INV-PKG-06-032-01466 | 429.65 | 51328.84 | 2566.44 | Paid | 48762.4 | 2024-Q1
EXP-001838 | 2024-03-03 | BOQ-PKG-08-01838 | PKG-08 | INV-PKG-08-019-01838 | 181.07 | 59436.84 | 2971.84 | Paid | 56465 | 2024-Q1
EXP-001870 | 2024-03-03 | BOQ-PKG-10-01870 | PKG-10 | INV-PKG-10-016-01870 | 224.52 | 78124.69 | 3906.23 | Disputed | 74218.46 | 2024-Q1
EXP-002047 | 2024-03-03 | BOQ-PKG-07-00057 | PKG-07 | INV-PKG-07-018-02047 | 431.64 | 77900.36 | 3895.02 | Paid | 74005.34 | 2024-Q1
EXP-002350 | 2024-03-03 | BOQ-PKG-10-00360 | PKG-10 | INV-PKG-10-006-02350 | 218.3 | 157608.05 | 7880.4 | Paid | 149727.65 | 2024-Q1
EXP-002886 | 2024-03-03 | BOQ-PKG-06-00896 | PKG-06 | INV-PKG-06-017-02886 | 398 | 178817.76 | 8940.89 | Paid | 169876.87 | 2024-Q1
EXP-002955 | 2024-03-03 | BOQ-PKG-05-00965 | PKG-05 | INV-PKG-05-016-02955 | 251.3 | 76736.94 | 3836.85 | Approved Pending Payment | 72900.09 | 2024-Q1
EXP-003243 | 2024-03-03 | BOQ-PKG-03-01253 | PKG-03 | INV-PKG-03-024-03243 | 275.62 | 145679.29 | 7283.96 | Paid | 138395.33 | 2024-Q1
EXP-003690 | 2024-03-03 | BOQ-PKG-10-01700 | PKG-10 | INV-PKG-10-016-03690 | 276.18 | 138578.25 | 6928.91 | Paid | 131649.34 | 2024-Q1
EXP-004206 | 2024-03-03 | BOQ-PKG-06-00226 | PKG-06 | INV-PKG-06-007-04206 | 103.44 | 68758.89 | 3437.94 | Paid | 65320.95 | 2024-Q1
EXP-000429 | 2024-03-04 | BOQ-PKG-09-00429 | PKG-09 | INV-PKG-09-010-00429 | 55.57 | 25634.22 | 1281.71 | Approved Pending Payment | 24352.51 | 2024-Q1
EXP-000507 | 2024-03-04 | BOQ-PKG-07-00507 | PKG-07 | INV-PKG-07-018-00507 | 353.37 | 186064.05 | 9303.2 | Paid | 176760.85 | 2024-Q1
EXP-000586 | 2024-03-04 | BOQ-PKG-06-00586 | PKG-06 | INV-PKG-06-027-00586 | 107.79 | 178446.16 | 8922.31 | Paid | 169523.85 | 2024-Q1
EXP-000638 | 2024-03-04 | BOQ-PKG-08-00638 | PKG-08 | INV-PKG-08-009-00638 | 387.59 | 107461.38 | 5373.07 | Paid | 102088.31 | 2024-Q1
EXP-005252 | 2024-03-04 | BOQ-PKG-02-01272 | PKG-02 | INV-PKG-02-003-05252 | 302.49 | 72116.89 | 3605.84 | Paid | 68511.05 | 2024-Q1
EXP-005627 | 2024-03-04 | BOQ-PKG-07-01647 | PKG-07 | INV-PKG-07-028-05627 | 287.72 | 142005.47 | 7100.27 | Under Review | 134905.2 | 2024-Q1
EXP-006615 | 2024-03-04 | BOQ-PKG-05-00645 | PKG-05 | INV-PKG-05-001-06615 | 350.07 | 196839.19 | 9841.96 | Approved Pending Payment | 186997.23 | 2024-Q1
EXP-006641 | 2024-03-04 | BOQ-PKG-01-00671 | PKG-01 | INV-PKG-01-027-06641 | 260.51 | 195255.38 | 9762.77 | Paid | 185492.61 | 2024-Q1
EXP-000135 | 2024-03-05 | BOQ-PKG-05-00135 | PKG-05 | INV-PKG-05-031-00135 | 324.27 | 115796.88 | 5789.84 | Paid | 110007.04 | 2024-Q1
EXP-000439 | 2024-03-05 | BOQ-PKG-09-00439 | PKG-09 | INV-PKG-09-020-00439 | 283.5 | 35014.1 | 1750.7 | Paid | 33263.4 | 2024-Q1
EXP-002524 | 2024-03-05 | BOQ-PKG-04-00534 | PKG-04 | INV-PKG-04-005-02524 | 85.22 | 142557.77 | 7127.89 | Approved Pending Payment | 135429.88 | 2024-Q1
EXP-003127 | 2024-03-05 | BOQ-PKG-07-01137 | PKG-07 | INV-PKG-07-013-03127 | 39.88 | 27533.01 | 1376.65 | Approved Pending Payment | 26156.36 | 2024-Q1
EXP-003363 | 2024-03-05 | BOQ-PKG-03-01373 | PKG-03 | INV-PKG-03-004-03363 | 353.08 | 136907.71 | 6845.39 | Approved Pending Payment | 130062.32 | 2024-Q1
EXP-000072 | 2024-03-06 | BOQ-PKG-02-00072 | PKG-02 | INV-PKG-02-003-00072 | 271.76 | 190667.22 | 9533.36 | Paid | 181133.86 | 2024-Q1
EXP-000154 | 2024-03-06 | BOQ-PKG-04-00154 | PKG-04 | INV-PKG-04-015-00154 | 89.49 | 30946.92 | 1547.35 | Approved Pending Payment | 29399.57 | 2024-Q1
EXP-000781 | 2024-03-06 | BOQ-PKG-01-00781 | PKG-01 | INV-PKG-01-012-00781 | 208.47 | 130403.38 | 6520.17 | Paid | 123883.21 | 2024-Q1
EXP-001709 | 2024-03-06 | BOQ-PKG-09-01709 | PKG-09 | INV-PKG-09-030-01709 | 379.78 | 143868.78 | 7193.44 | Paid | 136675.34 | 2024-Q1
EXP-003545 | 2024-03-06 | BOQ-PKG-05-01555 | PKG-05 | INV-PKG-05-011-03545 | 442.03 | 192144.55 | 9607.23 | Approved Pending Payment | 182537.32 | 2024-Q1
EXP-004682 | 2024-03-06 | BOQ-PKG-02-00702 | PKG-02 | INV-PKG-02-028-04682 | 311.57 | 139284.53 | 6964.23 | Paid | 132320.3 | 2024-Q1
EXP-004996 | 2024-03-06 | BOQ-PKG-06-01016 | PKG-06 | INV-PKG-06-027-04996 | 401.09 | 78687.89 | 3934.39 | Paid | 74753.5 | 2024-Q1
EXP-006041 | 2024-03-06 | BOQ-PKG-01-00071 | PKG-01 | INV-PKG-01-022-06041 | 266.56 | 162424.14 | 8121.21 | Paid | 154302.93 | 2024-Q1
EXP-000322 | 2024-03-07 | BOQ-PKG-02-00322 | PKG-02 | INV-PKG-02-008-00322 | 194.97 | 115253.53 | 5762.68 | Paid | 109490.85 | 2024-Q1
EXP-000498 | 2024-03-07 | BOQ-PKG-08-00498 | PKG-08 | INV-PKG-08-009-00498 | 244.46 | 38371.72 | 1918.59 | Approved Pending Payment | 36453.13 | 2024-Q1
EXP-000777 | 2024-03-07 | BOQ-PKG-07-00777 | PKG-07 | INV-PKG-07-008-00777 | 93.17 | 25911.16 | 1295.56 | Paid | 24615.6 | 2024-Q1
EXP-002299 | 2024-03-07 | BOQ-PKG-09-00309 | PKG-09 | INV-PKG-09-025-02299 | 350.34 | 133853.13 | 6692.66 | Paid | 127160.47 | 2024-Q1
EXP-002789 | 2024-03-07 | BOQ-PKG-09-00799 | PKG-09 | INV-PKG-09-025-02789 | 423.73 | 130235.82 | 6511.79 | Paid | 123724.03 | 2024-Q1
EXP-003611 | 2024-03-07 | BOQ-PKG-01-01621 | PKG-01 | INV-PKG-01-007-03611 | 268.3 | 156891.97 | 7844.6 | Under Review | 149047.37 | 2024-Q1
EXP-003867 | 2024-03-07 | BOQ-PKG-07-01877 | PKG-07 | INV-PKG-07-018-03867 | 324.06 | 41384.12 | 2069.21 | Paid | 39314.91 | 2024-Q1
EXP-003873 | 2024-03-07 | BOQ-PKG-03-01883 | PKG-03 | INV-PKG-03-024-03873 | 260.42 | 196301.54 | 9815.08 | Approved Pending Payment | 186486.46 | 2024-Q1
EXP-006212 | 2024-03-07 | BOQ-PKG-02-00242 | PKG-02 | INV-PKG-02-018-06212 | 92.72 | 112185.07 | 5609.25 | Paid | 106575.82 | 2024-Q1
EXP-006270 | 2024-03-07 | BOQ-PKG-10-00300 | PKG-10 | INV-PKG-10-006-06270 | 91.73 | 194569.56 | 9728.48 | Approved Pending Payment | 184841.08 | 2024-Q1
EXP-000368 | 2024-03-08 | BOQ-PKG-08-00368 | PKG-08 | INV-PKG-08-019-00368 | 58.57 | 136819.99 | 6841 | Paid | 129978.99 | 2024-Q1
EXP-003895 | 2024-03-08 | BOQ-PKG-05-01905 | PKG-05 | INV-PKG-05-011-03895 | 426.81 | 25563.34 | 1278.17 | Approved Pending Payment | 24285.17 | 2024-Q1
EXP-004167 | 2024-03-08 | BOQ-PKG-07-00187 | PKG-07 | INV-PKG-07-003-04167 | 268.21 | 92655.23 | 4632.76 | Under Review | 88022.47 | 2024-Q1
EXP-004195 | 2024-03-08 | BOQ-PKG-05-00215 | PKG-05 | INV-PKG-05-031-04195 | 426.96 | 60479.77 | 3023.99 | Paid | 57455.78 | 2024-Q1
EXP-005049 | 2024-03-08 | BOQ-PKG-09-01069 | PKG-09 | INV-PKG-09-010-05049 | 216.36 | 60930.26 | 3046.51 | Paid | 57883.75 | 2024-Q1
EXP-005639 | 2024-03-08 | BOQ-PKG-09-01659 | PKG-09 | INV-PKG-09-005-05639 | 152.82 | 40205.88 | 2010.29 | Paid | 38195.59 | 2024-Q1
EXP-005960 | 2024-03-08 | BOQ-PKG-10-01980 | PKG-10 | INV-PKG-10-011-05960 | 280.54 | 145642.91 | 7282.15 | Paid | 138360.76 | 2024-Q1
EXP-000250 | 2024-03-09 | BOQ-PKG-10-00250 | PKG-10 | INV-PKG-10-006-00250 | 264.57 | 183898.3 | 9194.91 | Paid | 174703.39 | 2024-Q1
EXP-000332 | 2024-03-09 | BOQ-PKG-02-00332 | PKG-02 | INV-PKG-02-018-00332 | 266.57 | 174006.32 | 8700.32 | Paid | 165306 | 2024-Q1
EXP-000565 | 2024-03-09 | BOQ-PKG-05-00565 | PKG-05 | INV-PKG-05-006-00565 | 54.19 | 64719.01 | 3235.95 | Paid | 61483.06 | 2024-Q1
EXP-002271 | 2024-03-09 | BOQ-PKG-01-00281 | PKG-01 | INV-PKG-01-032-02271 | 422.08 | 135482.44 | 6774.12 | Paid | 128708.32 | 2024-Q1
EXP-002785 | 2024-03-09 | BOQ-PKG-05-00795 | PKG-05 | INV-PKG-05-021-02785 | 174.45 | 185351.79 | 9267.59 | Paid | 176084.2 | 2024-Q1
EXP-004130 | 2024-03-09 | BOQ-PKG-10-00150 | PKG-10 | INV-PKG-10-001-04130 | 219.63 | 61280.29 | 3064.01 | Paid | 58216.28 | 2024-Q1
EXP-004428 | 2024-03-09 | BOQ-PKG-08-00448 | PKG-08 | INV-PKG-08-019-04428 | 60.54 | 105255.52 | 5262.78 | Paid | 99992.74 | 2024-Q1
EXP-005607 | 2024-03-09 | BOQ-PKG-07-01627 | PKG-07 | INV-PKG-07-008-05607 | 115.43 | 33415.69 | 1670.78 | Paid | 31744.91 | 2024-Q1
EXP-005660 | 2024-03-09 | BOQ-PKG-10-01680 | PKG-10 | INV-PKG-10-026-05660 | 297.9 | 122599.97 | 6130 | Paid | 116469.97 | 2024-Q1
EXP-001499 | 2024-03-10 | BOQ-PKG-09-01499 | PKG-09 | INV-PKG-09-030-01499 | 100.89 | 209278.35 | 10463.92 | Paid | 198814.43 | 2024-Q1
EXP-002881 | 2024-03-10 | BOQ-PKG-01-00891 | PKG-01 | INV-PKG-01-012-02881 | 102.02 | 204003.78 | 10200.19 | Paid | 193803.59 | 2024-Q1
EXP-003077 | 2024-03-10 | BOQ-PKG-07-01087 | PKG-07 | INV-PKG-07-033-03077 | 384.2 | 162813.23 | 8140.66 | Paid | 154672.57 | 2024-Q1
EXP-004740 | 2024-03-10 | BOQ-PKG-10-00760 | PKG-10 | INV-PKG-10-016-04740 | 79.53 | 100300.26 | 5015.01 | Paid | 95285.25 | 2024-Q1
EXP-006522 | 2024-03-10 | BOQ-PKG-02-00552 | PKG-02 | INV-PKG-02-013-06522 | 429.1 | 61168.07 | 3058.4 | Paid | 58109.67 | 2024-Q1
EXP-000022 | 2024-03-11 | BOQ-PKG-02-00022 | PKG-02 | INV-PKG-02-023-00022 | 63.28 | 140836.96 | 7041.85 | Paid | 133795.11 | 2024-Q1
EXP-000077 | 2024-03-11 | BOQ-PKG-07-00077 | PKG-07 | INV-PKG-07-008-00077 | 273.94 | 166833.64 | 8341.68 | Paid | 158491.96 | 2024-Q1
EXP-000096 | 2024-03-11 | BOQ-PKG-06-00096 | PKG-06 | INV-PKG-06-027-00096 | 312.96 | 49744.71 | 2487.24 | Paid | 47257.47 | 2024-Q1
EXP-002666 | 2024-03-11 | BOQ-PKG-06-00676 | PKG-06 | INV-PKG-06-007-02666 | 80.38 | 165787.87 | 8289.39 | Paid | 157498.48 | 2024-Q1
EXP-003004 | 2024-03-11 | BOQ-PKG-04-01014 | PKG-04 | INV-PKG-04-030-03004 | 106.22 | 71724.71 | 3586.24 | Approved Pending Payment | 68138.47 | 2024-Q1
EXP-003507 | 2024-03-11 | BOQ-PKG-07-01517 | PKG-07 | INV-PKG-07-008-03507 | 374.38 | 55288.57 | 2764.43 | Paid | 52524.14 | 2024-Q1
EXP-003735 | 2024-03-11 | BOQ-PKG-05-01745 | PKG-05 | INV-PKG-05-026-03735 | 215.12 | 123768.76 | 6188.44 | Approved Pending Payment | 117580.32 | 2024-Q1
EXP-004356 | 2024-03-11 | BOQ-PKG-06-00376 | PKG-06 | INV-PKG-06-017-04356 | 398.02 | 148288.99 | 7414.45 | Paid | 140874.54 | 2024-Q1
EXP-004736 | 2024-03-11 | BOQ-PKG-06-00756 | PKG-06 | INV-PKG-06-012-04736 | 169.92 | 62394.63 | 3119.73 | Paid | 59274.9 | 2024-Q1
EXP-005041 | 2024-03-11 | BOQ-PKG-01-01061 | PKG-01 | INV-PKG-01-002-05041 | 404.21 | 120160.46 | 6008.02 | Paid | 114152.44 | 2024-Q1
EXP-005388 | 2024-03-11 | BOQ-PKG-08-01408 | PKG-08 | INV-PKG-08-034-05388 | 319.1 | 94133.22 | 4706.66 | Disputed | 89426.56 | 2024-Q1
EXP-005719 | 2024-03-11 | BOQ-PKG-09-01739 | PKG-09 | INV-PKG-09-015-05719 | 386.23 | 165735.54 | 8286.78 | Paid | 157448.76 | 2024-Q1
EXP-001610 | 2024-03-12 | BOQ-PKG-10-01610 | PKG-10 | INV-PKG-10-001-01610 | 338.36 | 128933.99 | 6446.7 | Paid | 122487.29 | 2024-Q1
EXP-002292 | 2024-03-12 | BOQ-PKG-02-00302 | PKG-02 | INV-PKG-02-018-02292 | 359.93 | 30951.16 | 1547.56 | Paid | 29403.6 | 2024-Q1
EXP-003245 | 2024-03-12 | BOQ-PKG-05-01255 | PKG-05 | INV-PKG-05-026-03245 | 179.15 | 111779.34 | 5588.97 | Under Review | 106190.37 | 2024-Q1
EXP-004405 | 2024-03-12 | BOQ-PKG-05-00425 | PKG-05 | INV-PKG-05-031-04405 | 95.43 | 114467.96 | 5723.4 | Paid | 108744.56 | 2024-Q1
EXP-004625 | 2024-03-12 | BOQ-PKG-05-00645 | PKG-05 | INV-PKG-05-006-04625 | 127.36 | 68646 | 3432.3 | Paid | 65213.7 | 2024-Q1
EXP-005102 | 2024-03-12 | BOQ-PKG-02-01122 | PKG-02 | INV-PKG-02-028-05102 | 353.96 | 185925.04 | 9296.25 | Paid | 176628.79 | 2024-Q1
EXP-006091 | 2024-03-12 | BOQ-PKG-01-00121 | PKG-01 | INV-PKG-01-002-06091 | 415.46 | 189983.13 | 9499.16 | Paid | 180483.97 | 2024-Q1
EXP-000081 | 2024-03-13 | BOQ-PKG-01-00081 | PKG-01 | INV-PKG-01-012-00081 | 36.66 | 131763.29 | 6588.16 | Under Review | 125175.13 | 2024-Q1
EXP-000684 | 2024-03-13 | BOQ-PKG-04-00684 | PKG-04 | INV-PKG-04-020-00684 | 77.31 | 193835.34 | 9691.77 | Paid | 184143.57 | 2024-Q1
EXP-002778 | 2024-03-13 | BOQ-PKG-08-00788 | PKG-08 | INV-PKG-08-014-02778 | 41.33 | 79758.62 | 3987.93 | Paid | 75770.69 | 2024-Q1
EXP-004129 | 2024-03-13 | BOQ-PKG-09-00149 | PKG-09 | INV-PKG-09-035-04129 | 367.66 | 91038.07 | 4551.9 | Paid | 86486.17 | 2024-Q1
EXP-004310 | 2024-03-13 | BOQ-PKG-10-00330 | PKG-10 | INV-PKG-10-006-04310 | 102.24 | 185049.82 | 9252.49 | Paid | 175797.33 | 2024-Q1
EXP-004651 | 2024-03-13 | BOQ-PKG-01-00671 | PKG-01 | INV-PKG-01-032-04651 | 197.56 | 27918 | 1395.9 | Paid | 26522.1 | 2024-Q1
EXP-004660 | 2024-03-13 | BOQ-PKG-10-00680 | PKG-10 | INV-PKG-10-006-04660 | 145.78 | 103014.35 | 5150.72 | Paid | 97863.63 | 2024-Q1
EXP-005197 | 2024-03-13 | BOQ-PKG-07-01217 | PKG-07 | INV-PKG-07-018-05197 | 41.28 | 25858.55 | 1292.93 | Paid | 24565.62 | 2024-Q1
EXP-006502 | 2024-03-13 | BOQ-PKG-02-00532 | PKG-02 | INV-PKG-02-028-06502 | 284.07 | 165601.41 | 8280.07 | Paid | 157321.34 | 2024-Q1
EXP-001574 | 2024-03-14 | BOQ-PKG-04-01574 | PKG-04 | INV-PKG-04-035-01574 | 406.84 | 173374.34 | 8668.72 | Disputed | 164705.62 | 2024-Q1
EXP-001836 | 2024-03-14 | BOQ-PKG-06-01836 | PKG-06 | INV-PKG-06-017-01836 | 84.89 | 48716.31 | 2435.82 | Paid | 46280.49 | 2024-Q1
EXP-002557 | 2024-03-14 | BOQ-PKG-07-00567 | PKG-07 | INV-PKG-07-003-02557 | 415.34 | 57133.94 | 2856.7 | Approved Pending Payment | 54277.24 | 2024-Q1
EXP-006784 | 2024-03-14 | BOQ-PKG-04-00814 | PKG-04 | INV-PKG-04-030-06784 | 277.39 | 120567.43 | 6028.37 | Paid | 114539.06 | 2024-Q1
EXP-000832 | 2024-03-15 | BOQ-PKG-02-00832 | PKG-02 | INV-PKG-02-028-00832 | 181.33 | 204516.86 | 10225.84 | Paid | 194291.02 | 2024-Q1
EXP-001883 | 2024-03-15 | BOQ-PKG-03-01883 | PKG-03 | INV-PKG-03-029-01883 | 152.01 | 69138.61 | 3456.93 | Paid | 65681.68 | 2024-Q1
EXP-001917 | 2024-03-15 | BOQ-PKG-07-01917 | PKG-07 | INV-PKG-07-028-01917 | 163.61 | 136764.57 | 6838.23 | Paid | 129926.34 | 2024-Q1
EXP-003143 | 2024-03-15 | BOQ-PKG-03-01153 | PKG-03 | INV-PKG-03-029-03143 | 34.3 | 31691.3 | 1584.56 | Paid | 30106.74 | 2024-Q1
EXP-004616 | 2024-03-15 | BOQ-PKG-06-00636 | PKG-06 | INV-PKG-06-032-04616 | 87.65 | 101491.04 | 5074.55 | Paid | 96416.49 | 2024-Q1
EXP-006868 | 2024-03-15 | BOQ-PKG-08-00898 | PKG-08 | INV-PKG-08-009-06868 | 193.56 | 118743.33 | 5937.17 | Paid | 112806.16 | 2024-Q1
EXP-000477 | 2024-03-16 | BOQ-PKG-07-00477 | PKG-07 | INV-PKG-07-023-00477 | 212.25 | 68631.54 | 3431.58 | Paid | 65199.96 | 2024-Q1
EXP-001240 | 2024-03-16 | BOQ-PKG-10-01240 | PKG-10 | INV-PKG-10-016-01240 | 344.38 | 104775.39 | 5238.77 | Approved Pending Payment | 99536.62 | 2024-Q1
EXP-001585 | 2024-03-16 | BOQ-PKG-05-01585 | PKG-05 | INV-PKG-05-011-01585 | 438.82 | 150143.85 | 7507.19 | Paid | 142636.66 | 2024-Q1
EXP-003437 | 2024-03-16 | BOQ-PKG-07-01447 | PKG-07 | INV-PKG-07-008-03437 | 39.69 | 158027.75 | 7901.39 | Paid | 150126.36 | 2024-Q1
EXP-003646 | 2024-03-16 | BOQ-PKG-06-01656 | PKG-06 | INV-PKG-06-007-03646 | 179.03 | 76417.12 | 3820.86 | Paid | 72596.26 | 2024-Q1
EXP-003898 | 2024-03-16 | BOQ-PKG-08-01908 | PKG-08 | INV-PKG-08-014-03898 | 328.07 | 97740.38 | 4887.02 | Paid | 92853.36 | 2024-Q1
EXP-004901 | 2024-03-16 | BOQ-PKG-01-00921 | PKG-01 | INV-PKG-01-002-04901 | 434.54 | 51439.76 | 2571.99 | Approved Pending Payment | 48867.77 | 2024-Q1
EXP-005063 | 2024-03-16 | BOQ-PKG-03-01083 | PKG-03 | INV-PKG-03-024-05063 | 281.68 | 182688.57 | 9134.43 | Paid | 173554.14 | 2024-Q1
EXP-005085 | 2024-03-16 | BOQ-PKG-05-01105 | PKG-05 | INV-PKG-05-011-05085 | 231.89 | 210655.79 | 10532.79 | Paid | 200123 | 2024-Q1
EXP-005195 | 2024-03-16 | BOQ-PKG-05-01215 | PKG-05 | INV-PKG-05-016-05195 | 148.08 | 91722.02 | 4586.1 | Approved Pending Payment | 87135.92 | 2024-Q1
EXP-005767 | 2024-03-16 | BOQ-PKG-07-01787 | PKG-07 | INV-PKG-07-028-05767 | 252.91 | 142018.57 | 7100.93 | Approved Pending Payment | 134917.64 | 2024-Q1
EXP-000685 | 2024-03-17 | BOQ-PKG-05-00685 | PKG-05 | INV-PKG-05-021-00685 | 312.32 | 129834.84 | 6491.74 | Paid | 123343.1 | 2024-Q1
EXP-001379 | 2024-03-17 | BOQ-PKG-09-01379 | PKG-09 | INV-PKG-09-015-01379 | 281.86 | 130919.22 | 6545.96 | Under Review | 124373.26 | 2024-Q1
EXP-001449 | 2024-03-17 | BOQ-PKG-09-01449 | PKG-09 | INV-PKG-09-015-01449 | 183.64 | 172166.74 | 8608.34 | Paid | 163558.4 | 2024-Q1
EXP-003645 | 2024-03-17 | BOQ-PKG-05-01655 | PKG-05 | INV-PKG-05-006-03645 | 41.41 | 48705.49 | 2435.27 | Paid | 46270.22 | 2024-Q1
EXP-004570 | 2024-03-17 | BOQ-PKG-10-00590 | PKG-10 | INV-PKG-10-021-04570 | 61.42 | 48004.54 | 2400.23 | Paid | 45604.31 | 2024-Q1
EXP-005136 | 2024-03-17 | BOQ-PKG-06-01156 | PKG-06 | INV-PKG-06-027-05136 | 398.25 | 162974.96 | 8148.75 | Paid | 154826.21 | 2024-Q1
EXP-000626 | 2024-03-18 | BOQ-PKG-06-00626 | PKG-06 | INV-PKG-06-032-00626 | 17.55 | 71715.24 | 3585.76 | Paid | 68129.48 | 2024-Q1
EXP-001199 | 2024-03-18 | BOQ-PKG-09-01199 | PKG-09 | INV-PKG-09-010-01199 | 439.36 | 195643.51 | 9782.18 | Paid | 185861.33 | 2024-Q1
EXP-001980 | 2024-03-18 | BOQ-PKG-10-01980 | PKG-10 | INV-PKG-10-021-01980 | 234.64 | 89729.25 | 4486.46 | Under Review | 85242.79 | 2024-Q1
EXP-003532 | 2024-03-18 | BOQ-PKG-02-01542 | PKG-02 | INV-PKG-02-033-03532 | 8.86 | 55090.22 | 2754.51 | Paid | 52335.71 | 2024-Q1
EXP-004119 | 2024-03-18 | BOQ-PKG-09-00139 | PKG-09 | INV-PKG-09-025-04119 | 125.56 | 97745.25 | 4887.26 | Paid | 92857.99 | 2024-Q1
EXP-004372 | 2024-03-18 | BOQ-PKG-02-00392 | PKG-02 | INV-PKG-02-033-04372 | 342.56 | 109277.81 | 5463.89 | Paid | 103813.92 | 2024-Q1
EXP-005613 | 2024-03-18 | BOQ-PKG-03-01633 | PKG-03 | INV-PKG-03-014-05613 | 355.59 | 149101.21 | 7455.06 | Under Review | 141646.15 | 2024-Q1
EXP-006366 | 2024-03-18 | BOQ-PKG-06-00396 | PKG-06 | INV-PKG-06-032-06366 | 52.17 | 126684.14 | 6334.21 | Paid | 120349.93 | 2024-Q1
EXP-000161 | 2024-03-19 | BOQ-PKG-01-00161 | PKG-01 | INV-PKG-01-022-00161 | 88.27 | 125579.18 | 6278.96 | Paid | 119300.22 | 2024-Q1
EXP-002207 | 2024-03-19 | BOQ-PKG-07-00217 | PKG-07 | INV-PKG-07-003-02207 | 81.29 | 207222.01 | 10361.1 | Under Review | 196860.91 | 2024-Q1
EXP-004750 | 2024-03-19 | BOQ-PKG-10-00770 | PKG-10 | INV-PKG-10-026-04750 | 129.73 | 30051.33 | 1502.57 | Paid | 28548.76 | 2024-Q1
EXP-004823 | 2024-03-19 | BOQ-PKG-03-00843 | PKG-03 | INV-PKG-03-029-04823 | 97.81 | 178931.17 | 8946.56 | Paid | 169984.61 | 2024-Q1
EXP-005078 | 2024-03-19 | BOQ-PKG-08-01098 | PKG-08 | INV-PKG-08-004-05078 | 24.63 | 100441.89 | 5022.09 | Approved Pending Payment | 95419.8 | 2024-Q1
EXP-005176 | 2024-03-19 | BOQ-PKG-06-01196 | PKG-06 | INV-PKG-06-032-05176 | 150.11 | 38018.56 | 1900.93 | Paid | 36117.63 | 2024-Q1
EXP-006558 | 2024-03-19 | BOQ-PKG-08-00588 | PKG-08 | INV-PKG-08-014-06558 | 49.19 | 72162.86 | 3608.14 | Paid | 68554.72 | 2024-Q1
EXP-002184 | 2024-03-20 | BOQ-PKG-04-00194 | PKG-04 | INV-PKG-04-015-02184 | 244.14 | 51759.61 | 2587.98 | Paid | 49171.63 | 2024-Q1
EXP-002369 | 2024-03-20 | BOQ-PKG-09-00379 | PKG-09 | INV-PKG-09-025-02369 | 391.26 | 172928.61 | 8646.43 | Paid | 164282.18 | 2024-Q1
EXP-002498 | 2024-03-20 | BOQ-PKG-08-00508 | PKG-08 | INV-PKG-08-014-02498 | 219.26 | 56543.62 | 2827.18 | Paid | 53716.44 | 2024-Q1
EXP-004276 | 2024-03-20 | BOQ-PKG-06-00296 | PKG-06 | INV-PKG-06-007-04276 | 49.71 | 125730.36 | 6286.52 | Paid | 119443.84 | 2024-Q1
EXP-004459 | 2024-03-20 | BOQ-PKG-09-00479 | PKG-09 | INV-PKG-09-015-04459 | 47.09 | 85207.88 | 4260.39 | Paid | 80947.49 | 2024-Q1
EXP-000920 | 2024-03-21 | BOQ-PKG-10-00920 | PKG-10 | INV-PKG-10-011-00920 | 306.54 | 55520.6 | 2776.03 | Paid | 52744.57 | 2024-Q1
EXP-002044 | 2024-03-21 | BOQ-PKG-04-00054 | PKG-04 | INV-PKG-04-015-02044 | 73.37 | 169584.67 | 8479.23 | Paid | 161105.44 | 2024-Q1
EXP-002603 | 2024-03-21 | BOQ-PKG-03-00613 | PKG-03 | INV-PKG-03-014-02603 | 214.73 | 122290.06 | 6114.5 | Paid | 116175.56 | 2024-Q1
EXP-004061 | 2024-03-21 | BOQ-PKG-01-00081 | PKG-01 | INV-PKG-01-002-04061 | 265.03 | 132660.33 | 6633.02 | Paid | 126027.31 | 2024-Q1
EXP-004269 | 2024-03-21 | BOQ-PKG-09-00289 | PKG-09 | INV-PKG-09-035-04269 | 104.42 | 105857.55 | 5292.88 | Paid | 100564.67 | 2024-Q1
EXP-004671 | 2024-03-21 | BOQ-PKG-01-00691 | PKG-01 | INV-PKG-01-017-04671 | 242.63 | 201777.5 | 10088.88 | Paid | 191688.62 | 2024-Q1
EXP-005872 | 2024-03-21 | BOQ-PKG-02-01892 | PKG-02 | INV-PKG-02-028-05872 | 216.89 | 195445.49 | 9772.27 | Paid | 185673.22 | 2024-Q1
EXP-006362 | 2024-03-21 | BOQ-PKG-02-00392 | PKG-02 | INV-PKG-02-028-06362 | 396.24 | 135195.57 | 6759.78 | Paid | 128435.79 | 2024-Q1
EXP-006873 | 2024-03-21 | BOQ-PKG-03-00903 | PKG-03 | INV-PKG-03-014-06873 | 429.22 | 128268.37 | 6413.42 | Paid | 121854.95 | 2024-Q1
EXP-001088 | 2024-03-22 | BOQ-PKG-08-01088 | PKG-08 | INV-PKG-08-004-01088 | 271.19 | 73463.71 | 3673.19 | Paid | 69790.52 | 2024-Q1
EXP-001530 | 2024-03-22 | BOQ-PKG-10-01530 | PKG-10 | INV-PKG-10-026-01530 | 343.45 | 113188.52 | 5659.43 | Paid | 107529.09 | 2024-Q1
EXP-002909 | 2024-03-22 | BOQ-PKG-09-00919 | PKG-09 | INV-PKG-09-005-02909 | 152.64 | 113887.05 | 5694.35 | Paid | 108192.7 | 2024-Q1
EXP-004217 | 2024-03-22 | BOQ-PKG-07-00237 | PKG-07 | INV-PKG-07-018-04217 | 196.15 | 159487.46 | 7974.37 | Paid | 151513.09 | 2024-Q1
EXP-004647 | 2024-03-22 | BOQ-PKG-07-00667 | PKG-07 | INV-PKG-07-028-04647 | 15.06 | 113131.47 | 5656.57 | Paid | 107474.9 | 2024-Q1
EXP-000577 | 2024-03-23 | BOQ-PKG-07-00577 | PKG-07 | INV-PKG-07-018-00577 | 409.51 | 196057.59 | 9802.88 | Paid | 186254.71 | 2024-Q1
EXP-000735 | 2024-03-23 | BOQ-PKG-05-00735 | PKG-05 | INV-PKG-05-001-00735 | 70.62 | 38533.52 | 1926.68 | Approved Pending Payment | 36606.84 | 2024-Q1
EXP-000743 | 2024-03-23 | BOQ-PKG-03-00743 | PKG-03 | INV-PKG-03-009-00743 | 397.09 | 72382.83 | 3619.14 | Under Review | 68763.69 | 2024-Q1
EXP-001276 | 2024-03-23 | BOQ-PKG-06-01276 | PKG-06 | INV-PKG-06-017-01276 | 354.85 | 91366.33 | 4568.32 | Paid | 86798.01 | 2024-Q1
EXP-001686 | 2024-03-23 | BOQ-PKG-06-01686 | PKG-06 | INV-PKG-06-007-01686 | 24.38 | 66882.21 | 3344.11 | Disputed | 63538.1 | 2024-Q1
EXP-001739 | 2024-03-23 | BOQ-PKG-09-01739 | PKG-09 | INV-PKG-09-025-01739 | 46.95 | 128104.03 | 6405.2 | Paid | 121698.83 | 2024-Q1
EXP-003422 | 2024-03-23 | BOQ-PKG-02-01432 | PKG-02 | INV-PKG-02-028-03422 | 447.35 | 185884.23 | 9294.21 | Paid | 176590.02 | 2024-Q1
EXP-000474 | 2024-03-24 | BOQ-PKG-04-00474 | PKG-04 | INV-PKG-04-020-00474 | 126.78 | 208476.89 | 10423.84 | Paid | 198053.05 | 2024-Q1
EXP-002005 | 2024-03-24 | BOQ-PKG-05-00015 | PKG-05 | INV-PKG-05-011-02005 | 44.82 | 145520.13 | 7276.01 | Approved Pending Payment | 138244.12 | 2024-Q1
EXP-002481 | 2024-03-24 | BOQ-PKG-01-00491 | PKG-01 | INV-PKG-01-032-02481 | 271.94 | 122396.79 | 6119.84 | Under Review | 116276.95 | 2024-Q1
EXP-003710 | 2024-03-24 | BOQ-PKG-10-01720 | PKG-10 | INV-PKG-10-001-03710 | 298.5 | 159526.62 | 7976.33 | Approved Pending Payment | 151550.29 | 2024-Q1
EXP-003860 | 2024-03-24 | BOQ-PKG-10-01870 | PKG-10 | INV-PKG-10-011-03860 | 88.57 | 164413.41 | 8220.67 | Paid | 156192.74 | 2024-Q1
EXP-004001 | 2024-03-24 | BOQ-PKG-01-00021 | PKG-01 | INV-PKG-01-012-04001 | 159.99 | 163598.72 | 8179.94 | Paid | 155418.78 | 2024-Q1
EXP-004944 | 2024-03-24 | BOQ-PKG-04-00964 | PKG-04 | INV-PKG-04-010-04944 | 273.7 | 216958.29 | 10847.91 | Approved Pending Payment | 206110.38 | 2024-Q1
EXP-006054 | 2024-03-24 | BOQ-PKG-04-00084 | PKG-04 | INV-PKG-04-035-06054 | 291.11 | 58010.16 | 2900.51 | Under Review | 55109.65 | 2024-Q1
EXP-006876 | 2024-03-24 | BOQ-PKG-06-00906 | PKG-06 | INV-PKG-06-017-06876 | 425.08 | 76134.79 | 3806.74 | Paid | 72328.05 | 2024-Q1
EXP-001008 | 2024-03-25 | BOQ-PKG-08-01008 | PKG-08 | INV-PKG-08-029-01008 | 51.18 | 169374.42 | 8468.72 | Paid | 160905.7 | 2024-Q1
EXP-001334 | 2024-03-25 | BOQ-PKG-04-01334 | PKG-04 | INV-PKG-04-005-01334 | 401.7 | 189240.58 | 9462.03 | Paid | 179778.55 | 2024-Q1
EXP-003100 | 2024-03-25 | BOQ-PKG-10-01110 | PKG-10 | INV-PKG-10-021-03100 | 72.76 | 31787.68 | 1589.38 | Under Review | 30198.3 | 2024-Q1
EXP-004430 | 2024-03-25 | BOQ-PKG-10-00450 | PKG-10 | INV-PKG-10-021-04430 | 110.12 | 35033.39 | 1751.67 | Approved Pending Payment | 33281.72 | 2024-Q1
EXP-006260 | 2024-03-25 | BOQ-PKG-10-00290 | PKG-10 | INV-PKG-10-031-06260 | 254.56 | 202027.56 | 10101.38 | Paid | 191926.18 | 2024-Q1
EXP-000221 | 2024-03-26 | BOQ-PKG-01-00221 | PKG-01 | INV-PKG-01-012-00221 | 52.24 | 176629.55 | 8831.48 | Paid | 167798.07 | 2024-Q1
EXP-000314 | 2024-03-26 | BOQ-PKG-04-00314 | PKG-04 | INV-PKG-04-035-00314 | 55.02 | 32514.48 | 1625.72 | Paid | 30888.76 | 2024-Q1
EXP-001649 | 2024-03-26 | BOQ-PKG-09-01649 | PKG-09 | INV-PKG-09-005-01649 | 37.65 | 60433.25 | 3021.66 | Approved Pending Payment | 57411.59 | 2024-Q1
EXP-002446 | 2024-03-26 | BOQ-PKG-06-00456 | PKG-06 | INV-PKG-06-032-02446 | 421.72 | 79137.46 | 3956.87 | Paid | 75180.59 | 2024-Q1
EXP-003232 | 2024-03-26 | BOQ-PKG-02-01242 | PKG-02 | INV-PKG-02-013-03232 | 117.03 | 58403.75 | 2920.19 | Paid | 55483.56 | 2024-Q1
EXP-003597 | 2024-03-26 | BOQ-PKG-07-01607 | PKG-07 | INV-PKG-07-028-03597 | 195.72 | 69280.22 | 3464.01 | Approved Pending Payment | 65816.21 | 2024-Q1
EXP-003745 | 2024-03-26 | BOQ-PKG-05-01755 | PKG-05 | INV-PKG-05-001-03745 | 323.28 | 167577.98 | 8378.9 | Approved Pending Payment | 159199.08 | 2024-Q1
EXP-005406 | 2024-03-26 | BOQ-PKG-06-01426 | PKG-06 | INV-PKG-06-017-05406 | 281.45 | 72404.34 | 3620.22 | Paid | 68784.12 | 2024-Q1
EXP-005631 | 2024-03-26 | BOQ-PKG-01-01651 | PKG-01 | INV-PKG-01-032-05631 | 194.86 | 64242.19 | 3212.11 | Paid | 61030.08 | 2024-Q1
EXP-006550 | 2024-03-26 | BOQ-PKG-10-00580 | PKG-10 | INV-PKG-10-006-06550 | 191.96 | 142510.84 | 7125.54 | Approved Pending Payment | 135385.3 | 2024-Q1
EXP-006774 | 2024-03-26 | BOQ-PKG-04-00804 | PKG-04 | INV-PKG-04-020-06774 | 247.51 | 77904.75 | 3895.24 | Paid | 74009.51 | 2024-Q1
EXP-006875 | 2024-03-26 | BOQ-PKG-05-00905 | PKG-05 | INV-PKG-05-016-06875 | 268.75 | 118216.3 | 5910.82 | Paid | 112305.48 | 2024-Q1
EXP-000087 | 2024-03-27 | BOQ-PKG-07-00087 | PKG-07 | INV-PKG-07-018-00087 | 6.86 | 150772.44 | 7538.62 | Paid | 143233.82 | 2024-Q1
EXP-001046 | 2024-03-27 | BOQ-PKG-06-01046 | PKG-06 | INV-PKG-06-032-01046 | 228 | 155680.13 | 7784.01 | Paid | 147896.12 | 2024-Q1
EXP-001388 | 2024-03-27 | BOQ-PKG-08-01388 | PKG-08 | INV-PKG-08-024-01388 | 52.34 | 117388 | 5869.4 | Paid | 111518.6 | 2024-Q1
EXP-001628 | 2024-03-27 | BOQ-PKG-08-01628 | PKG-08 | INV-PKG-08-019-01628 | 215.5 | 177623.83 | 8881.19 | Approved Pending Payment | 168742.64 | 2024-Q1
EXP-002266 | 2024-03-27 | BOQ-PKG-06-00276 | PKG-06 | INV-PKG-06-027-02266 | 273.6 | 203237.38 | 10161.87 | Paid | 193075.51 | 2024-Q1
EXP-002546 | 2024-03-27 | BOQ-PKG-06-00556 | PKG-06 | INV-PKG-06-027-02546 | 414.74 | 207429.5 | 10371.48 | Paid | 197058.02 | 2024-Q1
EXP-002825 | 2024-03-27 | BOQ-PKG-05-00835 | PKG-05 | INV-PKG-05-026-02825 | 263.19 | 47881.04 | 2394.05 | Paid | 45486.99 | 2024-Q1
EXP-003828 | 2024-03-27 | BOQ-PKG-08-01838 | PKG-08 | INV-PKG-08-014-03828 | 243.88 | 147448.22 | 7372.41 | Paid | 140075.81 | 2024-Q1
EXP-004209 | 2024-03-27 | BOQ-PKG-09-00229 | PKG-09 | INV-PKG-09-010-04209 | 94.87 | 146090.91 | 7304.55 | Paid | 138786.36 | 2024-Q1
EXP-004928 | 2024-03-27 | BOQ-PKG-08-00948 | PKG-08 | INV-PKG-08-029-04928 | 76.17 | 179049.08 | 8952.45 | Approved Pending Payment | 170096.63 | 2024-Q1
EXP-006848 | 2024-03-27 | BOQ-PKG-08-00878 | PKG-08 | INV-PKG-08-024-06848 | 364.43 | 80163.77 | 4008.19 | Paid | 76155.58 | 2024-Q1
EXP-006959 | 2024-03-27 | BOQ-PKG-09-00989 | PKG-09 | INV-PKG-09-030-06959 | 231.58 | 152324.31 | 7616.22 | Paid | 144708.09 | 2024-Q1
EXP-000327 | 2024-03-28 | BOQ-PKG-07-00327 | PKG-07 | INV-PKG-07-013-00327 | 303.49 | 173731.2 | 8686.56 | Paid | 165044.64 | 2024-Q1
EXP-002003 | 2024-03-28 | BOQ-PKG-03-00013 | PKG-03 | INV-PKG-03-009-02003 | 269 | 58646.67 | 2932.33 | Under Review | 55714.34 | 2024-Q1
EXP-002378 | 2024-03-28 | BOQ-PKG-08-00388 | PKG-08 | INV-PKG-08-034-02378 | 360.95 | 202477.22 | 10123.86 | Paid | 192353.36 | 2024-Q1
EXP-003235 | 2024-03-28 | BOQ-PKG-05-01245 | PKG-05 | INV-PKG-05-016-03235 | 29.87 | 68201.25 | 3410.06 | Paid | 64791.19 | 2024-Q1
EXP-003339 | 2024-03-28 | BOQ-PKG-09-01349 | PKG-09 | INV-PKG-09-015-03339 | 183.48 | 132592.96 | 6629.65 | Approved Pending Payment | 125963.31 | 2024-Q1
EXP-003882 | 2024-03-28 | BOQ-PKG-02-01892 | PKG-02 | INV-PKG-02-033-03882 | 58.83 | 208152.16 | 10407.61 | Paid | 197744.55 | 2024-Q1
EXP-004584 | 2024-03-28 | BOQ-PKG-04-00604 | PKG-04 | INV-PKG-04-035-04584 | 41.18 | 167259.67 | 8362.98 | Paid | 158896.69 | 2024-Q1
EXP-005142 | 2024-03-28 | BOQ-PKG-02-01162 | PKG-02 | INV-PKG-02-033-05142 | 340.39 | 193898.74 | 9694.94 | Paid | 184203.8 | 2024-Q1
EXP-005309 | 2024-03-28 | BOQ-PKG-09-01329 | PKG-09 | INV-PKG-09-025-05309 | 210.91 | 156916.99 | 7845.85 | Paid | 149071.14 | 2024-Q1
EXP-000391 | 2024-03-29 | BOQ-PKG-01-00391 | PKG-01 | INV-PKG-01-007-00391 | 152.26 | 72982.98 | 3649.15 | Paid | 69333.83 | 2024-Q1
EXP-000680 | 2024-03-29 | BOQ-PKG-10-00680 | PKG-10 | INV-PKG-10-016-00680 | 239.65 | 99832.27 | 4991.61 | Paid | 94840.66 | 2024-Q1
EXP-000704 | 2024-03-29 | BOQ-PKG-04-00704 | PKG-04 | INV-PKG-04-005-00704 | 37.3 | 178593.07 | 8929.65 | Paid | 169663.42 | 2024-Q1
EXP-001111 | 2024-03-29 | BOQ-PKG-01-01111 | PKG-01 | INV-PKG-01-027-01111 | 420.37 | 94215.91 | 4710.8 | Paid | 89505.11 | 2024-Q1
EXP-001713 | 2024-03-29 | BOQ-PKG-03-01713 | PKG-03 | INV-PKG-03-034-01713 | 194.64 | 196104.57 | 9805.23 | Paid | 186299.34 | 2024-Q1
EXP-001955 | 2024-03-29 | BOQ-PKG-05-01955 | PKG-05 | INV-PKG-05-031-01955 | 128.22 | 68945.92 | 3447.3 | Paid | 65498.62 | 2024-Q1
EXP-002347 | 2024-03-29 | BOQ-PKG-07-00357 | PKG-07 | INV-PKG-07-003-02347 | 424.71 | 43674.56 | 2183.73 | Paid | 41490.83 | 2024-Q1
EXP-002653 | 2024-03-29 | BOQ-PKG-03-00663 | PKG-03 | INV-PKG-03-029-02653 | 243.31 | 80519.3 | 4025.96 | Paid | 76493.34 | 2024-Q1
EXP-002761 | 2024-03-29 | BOQ-PKG-01-00771 | PKG-01 | INV-PKG-01-032-02761 | 257.47 | 100119.23 | 5005.96 | Paid | 95113.27 | 2024-Q1
EXP-003402 | 2024-03-29 | BOQ-PKG-02-01412 | PKG-02 | INV-PKG-02-008-03402 | 372.22 | 127819.51 | 6390.98 | Paid | 121428.53 | 2024-Q1
EXP-004020 | 2024-03-29 | BOQ-PKG-10-00040 | PKG-10 | INV-PKG-10-031-04020 | 83.04 | 73672.34 | 3683.62 | Paid | 69988.72 | 2024-Q1
EXP-005000 | 2024-03-29 | BOQ-PKG-10-01020 | PKG-10 | INV-PKG-10-031-05000 | 36.01 | 135736.11 | 6786.81 | Under Review | 128949.3 | 2024-Q1
EXP-000658 | 2024-03-30 | BOQ-PKG-08-00658 | PKG-08 | INV-PKG-08-029-00658 | 90.21 | 95938.75 | 4796.94 | Paid | 91141.81 | 2024-Q1
EXP-002570 | 2024-03-30 | BOQ-PKG-10-00580 | PKG-10 | INV-PKG-10-016-02570 | 266.37 | 28870.94 | 1443.55 | Paid | 27427.39 | 2024-Q1
EXP-003510 | 2024-03-30 | BOQ-PKG-10-01520 | PKG-10 | INV-PKG-10-011-03510 | 273.09 | 176288.1 | 8814.41 | Approved Pending Payment | 167473.69 | 2024-Q1
EXP-003736 | 2024-03-30 | BOQ-PKG-06-01746 | PKG-06 | INV-PKG-06-027-03736 | 98.08 | 79701.89 | 3985.09 | Paid | 75716.8 | 2024-Q1
EXP-003748 | 2024-03-30 | BOQ-PKG-08-01758 | PKG-08 | INV-PKG-08-004-03748 | 114.08 | 69289.54 | 3464.48 | Paid | 65825.06 | 2024-Q1
EXP-004479 | 2024-03-30 | BOQ-PKG-09-00499 | PKG-09 | INV-PKG-09-035-04479 | 150 | 105011.42 | 5250.57 | Paid | 99760.85 | 2024-Q1
EXP-006220 | 2024-03-30 | BOQ-PKG-10-00250 | PKG-10 | INV-PKG-10-026-06220 | 34.09 | 80444.59 | 4022.23 | Paid | 76422.36 | 2024-Q1
EXP-000065 | 2024-03-31 | BOQ-PKG-05-00065 | PKG-05 | INV-PKG-05-031-00065 | 423.11 | 166049.47 | 8302.47 | Approved Pending Payment | 157747 | 2024-Q1
EXP-000066 | 2024-03-31 | BOQ-PKG-06-00066 | PKG-06 | INV-PKG-06-032-00066 | 217.19 | 145228.56 | 7261.43 | Approved Pending Payment | 137967.13 | 2024-Q1
EXP-000184 | 2024-03-31 | BOQ-PKG-04-00184 | PKG-04 | INV-PKG-04-010-00184 | 70.49 | 77016.58 | 3850.83 | Under Review | 73165.75 | 2024-Q1
EXP-002101 | 2024-03-31 | BOQ-PKG-01-00111 | PKG-01 | INV-PKG-01-002-02101 | 255 | 26294.89 | 1314.74 | Paid | 24980.15 | 2024-Q1
EXP-002475 | 2024-03-31 | BOQ-PKG-05-00485 | PKG-05 | INV-PKG-05-026-02475 | 341.2 | 26636.88 | 1331.84 | Paid | 25305.04 | 2024-Q1
EXP-003580 | 2024-04-01 | BOQ-PKG-10-01590 | PKG-10 | INV-PKG-10-011-03580 | 308.55 | 177720.8 | 8886.04 | Paid | 168834.76 | 2024-Q2
EXP-003630 | 2024-04-01 | BOQ-PKG-10-01640 | PKG-10 | INV-PKG-10-026-03630 | 108.49 | 203614.57 | 10180.73 | Paid | 193433.84 | 2024-Q2
EXP-002300 | 2024-04-02 | BOQ-PKG-10-00310 | PKG-10 | INV-PKG-10-026-02300 | 332.5 | 130451.87 | 6522.59 | Paid | 123929.28 | 2024-Q2
EXP-002817 | 2024-04-02 | BOQ-PKG-07-00827 | PKG-07 | INV-PKG-07-018-02817 | 401.95 | 193487.71 | 9674.39 | Paid | 183813.32 | 2024-Q2
EXP-003535 | 2024-04-02 | BOQ-PKG-05-01545 | PKG-05 | INV-PKG-05-001-03535 | 303.43 | 141538.91 | 7076.95 | Approved Pending Payment | 134461.96 | 2024-Q2
EXP-000003 | 2024-04-03 | BOQ-PKG-03-00003 | PKG-03 | INV-PKG-03-004-00003 | 98.95 | 158653.48 | 7932.67 | Paid | 150720.81 | 2024-Q2
EXP-000969 | 2024-04-03 | BOQ-PKG-09-00969 | PKG-09 | INV-PKG-09-025-00969 | 446.8 | 46086.76 | 2304.34 | Under Review | 43782.42 | 2024-Q2
EXP-001782 | 2024-04-03 | BOQ-PKG-02-01782 | PKG-02 | INV-PKG-02-033-01782 | 156.11 | 84889.35 | 4244.47 | Approved Pending Payment | 80644.88 | 2024-Q2
EXP-001881 | 2024-04-03 | BOQ-PKG-01-01881 | PKG-01 | INV-PKG-01-027-01881 | 76.52 | 159971.34 | 7998.57 | Paid | 151972.77 | 2024-Q2
EXP-003804 | 2024-04-03 | BOQ-PKG-04-01814 | PKG-04 | INV-PKG-04-025-03804 | 381.43 | 188979.12 | 9448.96 | Paid | 179530.16 | 2024-Q2
EXP-004506 | 2024-04-03 | BOQ-PKG-06-00526 | PKG-06 | INV-PKG-06-027-04506 | 241 | 63206.6 | 3160.33 | Paid | 60046.27 | 2024-Q2
EXP-004939 | 2024-04-03 | BOQ-PKG-09-00959 | PKG-09 | INV-PKG-09-005-04939 | 101.96 | 163884.4 | 8194.22 | Disputed | 155690.18 | 2024-Q2
EXP-005951 | 2024-04-03 | BOQ-PKG-01-01971 | PKG-01 | INV-PKG-01-002-05951 | 39.12 | 136622.18 | 6831.11 | Paid | 129791.07 | 2024-Q2
EXP-006565 | 2024-04-03 | BOQ-PKG-05-00595 | PKG-05 | INV-PKG-05-021-06565 | 316.05 | 111956.6 | 5597.83 | Paid | 106358.77 | 2024-Q2
EXP-006761 | 2024-04-03 | BOQ-PKG-01-00791 | PKG-01 | INV-PKG-01-007-06761 | 318.31 | 110769.07 | 5538.45 | Paid | 105230.62 | 2024-Q2
EXP-000388 | 2024-04-04 | BOQ-PKG-08-00388 | PKG-08 | INV-PKG-08-004-00388 | 443.14 | 145870.21 | 7293.51 | Paid | 138576.7 | 2024-Q2
EXP-000711 | 2024-04-04 | BOQ-PKG-01-00711 | PKG-01 | INV-PKG-01-012-00711 | 58.08 | 65870.85 | 3293.54 | Approved Pending Payment | 62577.31 | 2024-Q2
EXP-001362 | 2024-04-04 | BOQ-PKG-02-01362 | PKG-02 | INV-PKG-02-033-01362 | 102.9 | 26016.44 | 1300.82 | Paid | 24715.62 | 2024-Q2
EXP-002377 | 2024-04-04 | BOQ-PKG-07-00387 | PKG-07 | INV-PKG-07-033-02377 | 443.48 | 131194.69 | 6559.73 | Paid | 124634.96 | 2024-Q2
EXP-002616 | 2024-04-04 | BOQ-PKG-06-00626 | PKG-06 | INV-PKG-06-027-02616 | 213.88 | 201540.55 | 10077.03 | Paid | 191463.52 | 2024-Q2
EXP-003654 | 2024-04-04 | BOQ-PKG-04-01664 | PKG-04 | INV-PKG-04-015-03654 | 264.33 | 182275.39 | 9113.77 | Paid | 173161.62 | 2024-Q2
EXP-004333 | 2024-04-04 | BOQ-PKG-03-00353 | PKG-03 | INV-PKG-03-029-04333 | 122.14 | 107628.75 | 5381.44 | Paid | 102247.31 | 2024-Q2
EXP-005123 | 2024-04-04 | BOQ-PKG-03-01143 | PKG-03 | INV-PKG-03-014-05123 | 369.35 | 90111.57 | 4505.58 | Disputed | 85605.99 | 2024-Q2
EXP-005286 | 2024-04-04 | BOQ-PKG-06-01306 | PKG-06 | INV-PKG-06-002-05286 | 100.02 | 67509.35 | 3375.47 | Paid | 64133.88 | 2024-Q2
EXP-000514 | 2024-04-05 | BOQ-PKG-04-00514 | PKG-04 | INV-PKG-04-025-00514 | 253.82 | 114532.24 | 5726.61 | Paid | 108805.63 | 2024-Q2
EXP-000857 | 2024-04-05 | BOQ-PKG-07-00857 | PKG-07 | INV-PKG-07-018-00857 | 86.64 | 159342.71 | 7967.14 | Approved Pending Payment | 151375.57 | 2024-Q2
EXP-001944 | 2024-04-05 | BOQ-PKG-04-01944 | PKG-04 | INV-PKG-04-020-01944 | 426.36 | 76726.09 | 3836.3 | Paid | 72889.79 | 2024-Q2
EXP-002968 | 2024-04-05 | BOQ-PKG-08-00978 | PKG-08 | INV-PKG-08-029-02968 | 121.5 | 46433.62 | 2321.68 | Paid | 44111.94 | 2024-Q2
EXP-003822 | 2024-04-05 | BOQ-PKG-02-01832 | PKG-02 | INV-PKG-02-008-03822 | 164.67 | 103521.03 | 5176.05 | Paid | 98344.98 | 2024-Q2
EXP-004439 | 2024-04-05 | BOQ-PKG-09-00459 | PKG-09 | INV-PKG-09-030-04439 | 87.74 | 60219.68 | 3010.98 | Paid | 57208.7 | 2024-Q2
EXP-006067 | 2024-04-05 | BOQ-PKG-07-00097 | PKG-07 | INV-PKG-07-013-06067 | 271.07 | 29311.39 | 1465.57 | Paid | 27845.82 | 2024-Q2
EXP-006195 | 2024-04-05 | BOQ-PKG-05-00225 | PKG-05 | INV-PKG-05-001-06195 | 141.93 | 114343.05 | 5717.15 | Approved Pending Payment | 108625.9 | 2024-Q2
EXP-006725 | 2024-04-05 | BOQ-PKG-05-00755 | PKG-05 | INV-PKG-05-006-06725 | 392.2 | 139966.76 | 6998.34 | Paid | 132968.42 | 2024-Q2
EXP-002308 | 2024-04-06 | BOQ-PKG-08-00318 | PKG-08 | INV-PKG-08-034-02308 | 30.34 | 93562.87 | 4678.14 | Paid | 88884.73 | 2024-Q2
EXP-003198 | 2024-04-06 | BOQ-PKG-08-01208 | PKG-08 | INV-PKG-08-014-03198 | 333.51 | 75674.84 | 3783.74 | Paid | 71891.1 | 2024-Q2
EXP-003536 | 2024-04-06 | BOQ-PKG-06-01546 | PKG-06 | INV-PKG-06-002-03536 | 222.8 | 26737.2 | 1336.86 | Approved Pending Payment | 25400.34 | 2024-Q2
EXP-003991 | 2024-04-06 | BOQ-PKG-01-00011 | PKG-01 | INV-PKG-01-002-03991 | 135.07 | 33181.3 | 1659.07 | Paid | 31522.23 | 2024-Q2
EXP-004038 | 2024-04-06 | BOQ-PKG-08-00058 | PKG-08 | INV-PKG-08-014-04038 | 403.34 | 177712.89 | 8885.64 | Paid | 168827.25 | 2024-Q2
EXP-004216 | 2024-04-06 | BOQ-PKG-06-00236 | PKG-06 | INV-PKG-06-017-04216 | 422.81 | 82130.91 | 4106.55 | Paid | 78024.36 | 2024-Q2
EXP-004884 | 2024-04-06 | BOQ-PKG-04-00904 | PKG-04 | INV-PKG-04-020-04884 | 252.43 | 203507.8 | 10175.39 | Paid | 193332.41 | 2024-Q2
EXP-004954 | 2024-04-06 | BOQ-PKG-04-00974 | PKG-04 | INV-PKG-04-020-04954 | 284.11 | 94951.52 | 4747.58 | Paid | 90203.94 | 2024-Q2
EXP-006712 | 2024-04-06 | BOQ-PKG-02-00742 | PKG-02 | INV-PKG-02-028-06712 | 273.56 | 149845.6 | 7492.28 | Paid | 142353.32 | 2024-Q2
EXP-006780 | 2024-04-06 | BOQ-PKG-10-00810 | PKG-10 | INV-PKG-10-026-06780 | 14.53 | 103741.86 | 5187.09 | Approved Pending Payment | 98554.77 | 2024-Q2
EXP-006995 | 2024-04-06 | BOQ-PKG-05-01025 | PKG-05 | INV-PKG-05-031-06995 | 429.26 | 173527.39 | 8676.37 | Under Review | 164851.02 | 2024-Q2
EXP-000172 | 2024-04-07 | BOQ-PKG-02-00172 | PKG-02 | INV-PKG-02-033-00172 | 172.93 | 97500.28 | 4875.01 | Paid | 92625.27 | 2024-Q2
EXP-000206 | 2024-04-07 | BOQ-PKG-06-00206 | PKG-06 | INV-PKG-06-032-00206 | 350.68 | 177644.65 | 8882.23 | Paid | 168762.42 | 2024-Q2
EXP-000366 | 2024-04-07 | BOQ-PKG-06-00366 | PKG-06 | INV-PKG-06-017-00366 | 157.29 | 209278.51 | 10463.93 | Paid | 198814.58 | 2024-Q2
EXP-000483 | 2024-04-07 | BOQ-PKG-03-00483 | PKG-03 | INV-PKG-03-029-00483 | 189.08 | 166486.35 | 8324.32 | Disputed | 158162.03 | 2024-Q2
EXP-002311 | 2024-04-07 | BOQ-PKG-01-00321 | PKG-01 | INV-PKG-01-002-02311 | 296.85 | 187894.89 | 9394.74 | Paid | 178500.15 | 2024-Q2
EXP-003071 | 2024-04-07 | BOQ-PKG-01-01081 | PKG-01 | INV-PKG-01-027-03071 | 387.49 | 138527.71 | 6926.39 | Paid | 131601.32 | 2024-Q2
EXP-003922 | 2024-04-07 | BOQ-PKG-02-01932 | PKG-02 | INV-PKG-02-003-03922 | 225.41 | 203878.27 | 10193.91 | Paid | 193684.36 | 2024-Q2
EXP-004197 | 2024-04-07 | BOQ-PKG-07-00217 | PKG-07 | INV-PKG-07-033-04197 | 284.38 | 111960.92 | 5598.05 | Paid | 106362.87 | 2024-Q2
EXP-004765 | 2024-04-07 | BOQ-PKG-05-00785 | PKG-05 | INV-PKG-05-006-04765 | 344.11 | 56241.43 | 2812.07 | Paid | 53429.36 | 2024-Q2
EXP-005335 | 2024-04-07 | BOQ-PKG-05-01355 | PKG-05 | INV-PKG-05-016-05335 | 259.98 | 96613.38 | 4830.67 | Paid | 91782.71 | 2024-Q2
EXP-005915 | 2024-04-07 | BOQ-PKG-05-01935 | PKG-05 | INV-PKG-05-001-05915 | 93.27 | 159193.69 | 7959.68 | Paid | 151234.01 | 2024-Q2
EXP-006531 | 2024-04-07 | BOQ-PKG-01-00561 | PKG-01 | INV-PKG-01-022-06531 | 281.52 | 190042.73 | 9502.14 | Paid | 180540.59 | 2024-Q2
EXP-006818 | 2024-04-07 | BOQ-PKG-08-00848 | PKG-08 | INV-PKG-08-029-06818 | 47.31 | 179901.78 | 8995.09 | Paid | 170906.69 | 2024-Q2
EXP-000535 | 2024-04-08 | BOQ-PKG-05-00535 | PKG-05 | INV-PKG-05-011-00535 | 389.92 | 81689.79 | 4084.49 | Paid | 77605.3 | 2024-Q2
EXP-001180 | 2024-04-08 | BOQ-PKG-10-01180 | PKG-10 | INV-PKG-10-026-01180 | 30.88 | 95055.41 | 4752.77 | Paid | 90302.64 | 2024-Q2
EXP-001366 | 2024-04-08 | BOQ-PKG-06-01366 | PKG-06 | INV-PKG-06-002-01366 | 134.62 | 95492.92 | 4774.65 | Paid | 90718.27 | 2024-Q2
EXP-004690 | 2024-04-08 | BOQ-PKG-10-00710 | PKG-10 | INV-PKG-10-001-04690 | 299.21 | 145408.84 | 7270.44 | Paid | 138138.4 | 2024-Q2
EXP-005591 | 2024-04-08 | BOQ-PKG-01-01611 | PKG-01 | INV-PKG-01-027-05591 | 330.56 | 63877.11 | 3193.86 | Disputed | 60683.25 | 2024-Q2
EXP-006258 | 2024-04-08 | BOQ-PKG-08-00288 | PKG-08 | INV-PKG-08-029-06258 | 449.18 | 166490.35 | 8324.52 | Paid | 158165.83 | 2024-Q2
EXP-000550 | 2024-04-09 | BOQ-PKG-10-00550 | PKG-10 | INV-PKG-10-026-00550 | 155.12 | 42156.67 | 2107.83 | Approved Pending Payment | 40048.84 | 2024-Q2
EXP-002623 | 2024-04-09 | BOQ-PKG-03-00633 | PKG-03 | INV-PKG-03-034-02623 | 308.96 | 200423.82 | 10021.19 | Under Review | 190402.63 | 2024-Q2
EXP-003378 | 2024-04-09 | BOQ-PKG-08-01388 | PKG-08 | INV-PKG-08-019-03378 | 396.88 | 196931.99 | 9846.6 | Paid | 187085.39 | 2024-Q2
EXP-003446 | 2024-04-09 | BOQ-PKG-06-01456 | PKG-06 | INV-PKG-06-017-03446 | 316.32 | 154630.31 | 7731.52 | Paid | 146898.79 | 2024-Q2
EXP-005847 | 2024-04-09 | BOQ-PKG-07-01867 | PKG-07 | INV-PKG-07-003-05847 | 247.83 | 154244.64 | 7712.23 | Approved Pending Payment | 146532.41 | 2024-Q2
EXP-006546 | 2024-04-09 | BOQ-PKG-06-00576 | PKG-06 | INV-PKG-06-002-06546 | 211.71 | 55813.09 | 2790.65 | Paid | 53022.44 | 2024-Q2
EXP-000623 | 2024-04-10 | BOQ-PKG-03-00623 | PKG-03 | INV-PKG-03-029-00623 | 415.83 | 148176.31 | 7408.82 | Paid | 140767.49 | 2024-Q2
EXP-001418 | 2024-04-10 | BOQ-PKG-08-01418 | PKG-08 | INV-PKG-08-019-01418 | 26.86 | 86501.2 | 4325.06 | Paid | 82176.14 | 2024-Q2
EXP-001593 | 2024-04-10 | BOQ-PKG-03-01593 | PKG-03 | INV-PKG-03-019-01593 | 62.38 | 70609.66 | 3530.48 | Under Review | 67079.18 | 2024-Q2
EXP-005576 | 2024-04-10 | BOQ-PKG-06-01596 | PKG-06 | INV-PKG-06-012-05576 | 189.24 | 191049.09 | 9552.45 | Under Review | 181496.64 | 2024-Q2
EXP-005851 | 2024-04-10 | BOQ-PKG-01-01871 | PKG-01 | INV-PKG-01-007-05851 | 321.21 | 99057.71 | 4952.89 | Paid | 94104.82 | 2024-Q2
EXP-006325 | 2024-04-10 | BOQ-PKG-05-00355 | PKG-05 | INV-PKG-05-026-06325 | 311.03 | 154758.7 | 7737.94 | Paid | 147020.76 | 2024-Q2
EXP-001190 | 2024-04-11 | BOQ-PKG-10-01190 | PKG-10 | INV-PKG-10-001-01190 | 203.03 | 216086.47 | 10804.32 | Under Review | 205282.15 | 2024-Q2
EXP-003193 | 2024-04-11 | BOQ-PKG-03-01203 | PKG-03 | INV-PKG-03-009-03193 | 261.04 | 211785.88 | 10589.29 | Paid | 201196.59 | 2024-Q2
EXP-003456 | 2024-04-11 | BOQ-PKG-06-01466 | PKG-06 | INV-PKG-06-027-03456 | 165.15 | 75200.84 | 3760.04 | Disputed | 71440.8 | 2024-Q2
EXP-004205 | 2024-04-11 | BOQ-PKG-05-00225 | PKG-05 | INV-PKG-05-006-04205 | 32.04 | 141740.4 | 7087.02 | Paid | 134653.38 | 2024-Q2
EXP-004558 | 2024-04-11 | BOQ-PKG-08-00578 | PKG-08 | INV-PKG-08-009-04558 | 79.57 | 92926.64 | 4646.33 | Paid | 88280.31 | 2024-Q2
EXP-001044 | 2024-04-12 | BOQ-PKG-04-01044 | PKG-04 | INV-PKG-04-030-01044 | 333.76 | 206007.3 | 10300.36 | Paid | 195706.94 | 2024-Q2
EXP-001049 | 2024-04-12 | BOQ-PKG-09-01049 | PKG-09 | INV-PKG-09-035-01049 | 267.22 | 121034.43 | 6051.72 | Under Review | 114982.71 | 2024-Q2
EXP-001841 | 2024-04-12 | BOQ-PKG-01-01841 | PKG-01 | INV-PKG-01-022-01841 | 25.44 | 43677.96 | 2183.9 | Paid | 41494.06 | 2024-Q2
EXP-003161 | 2024-04-12 | BOQ-PKG-01-01171 | PKG-01 | INV-PKG-01-012-03161 | 281.4 | 72500.95 | 3625.05 | Paid | 68875.9 | 2024-Q2
EXP-003865 | 2024-04-12 | BOQ-PKG-05-01875 | PKG-05 | INV-PKG-05-016-03865 | 129.46 | 86975.45 | 4348.77 | Paid | 82626.68 | 2024-Q2
EXP-004726 | 2024-04-12 | BOQ-PKG-06-00746 | PKG-06 | INV-PKG-06-002-04726 | 251.2 | 151107.9 | 7555.4 | Paid | 143552.5 | 2024-Q2
EXP-004771 | 2024-04-12 | BOQ-PKG-01-00791 | PKG-01 | INV-PKG-01-012-04771 | 113.32 | 113234.72 | 5661.74 | Under Review | 107572.98 | 2024-Q2
EXP-005495 | 2024-04-12 | BOQ-PKG-05-01515 | PKG-05 | INV-PKG-05-001-05495 | 425.05 | 160283.56 | 8014.18 | Paid | 152269.38 | 2024-Q2
EXP-005632 | 2024-04-12 | BOQ-PKG-02-01652 | PKG-02 | INV-PKG-02-033-05632 | 254.35 | 30040.91 | 1502.05 | Paid | 28538.86 | 2024-Q2
EXP-006007 | 2024-04-12 | BOQ-PKG-07-00037 | PKG-07 | INV-PKG-07-023-06007 | 260.67 | 186549.91 | 9327.5 | Approved Pending Payment | 177222.41 | 2024-Q2
EXP-002041 | 2024-04-13 | BOQ-PKG-01-00051 | PKG-01 | INV-PKG-01-012-02041 | 145.26 | 185103.13 | 9255.16 | Paid | 175847.97 | 2024-Q2
EXP-003806 | 2024-04-13 | BOQ-PKG-06-01816 | PKG-06 | INV-PKG-06-027-03806 | 137.03 | 195855.88 | 9792.79 | Under Review | 186063.09 | 2024-Q2
EXP-004852 | 2024-04-13 | BOQ-PKG-02-00872 | PKG-02 | INV-PKG-02-023-04852 | 438.83 | 46675.19 | 2333.76 | Paid | 44341.43 | 2024-Q2
EXP-004860 | 2024-04-13 | BOQ-PKG-10-00880 | PKG-10 | INV-PKG-10-031-04860 | 280.96 | 116174.01 | 5808.7 | Paid | 110365.31 | 2024-Q2
EXP-001599 | 2024-04-14 | BOQ-PKG-09-01599 | PKG-09 | INV-PKG-09-025-01599 | 147.74 | 97148.26 | 4857.41 | Paid | 92290.85 | 2024-Q2
EXP-001614 | 2024-04-14 | BOQ-PKG-04-01614 | PKG-04 | INV-PKG-04-005-01614 | 181.23 | 212534.96 | 10626.75 | Paid | 201908.21 | 2024-Q2
EXP-002828 | 2024-04-14 | BOQ-PKG-08-00838 | PKG-08 | INV-PKG-08-029-02828 | 193.64 | 198226.65 | 9911.33 | Approved Pending Payment | 188315.32 | 2024-Q2
EXP-003529 | 2024-04-14 | BOQ-PKG-09-01539 | PKG-09 | INV-PKG-09-030-03529 | 91.33 | 183052.31 | 9152.62 | Paid | 173899.69 | 2024-Q2
EXP-004434 | 2024-04-14 | BOQ-PKG-04-00454 | PKG-04 | INV-PKG-04-025-04434 | 117.78 | 42754.11 | 2137.71 | Paid | 40616.4 | 2024-Q2
EXP-004541 | 2024-04-14 | BOQ-PKG-01-00561 | PKG-01 | INV-PKG-01-027-04541 | 257.78 | 77192.38 | 3859.62 | Paid | 73332.76 | 2024-Q2
EXP-005433 | 2024-04-14 | BOQ-PKG-03-01453 | PKG-03 | INV-PKG-03-009-05433 | 286.1 | 183333.15 | 9166.66 | Approved Pending Payment | 174166.49 | 2024-Q2
EXP-005684 | 2024-04-14 | BOQ-PKG-04-01704 | PKG-04 | INV-PKG-04-015-05684 | 370.95 | 61527.34 | 3076.37 | Paid | 58450.97 | 2024-Q2
EXP-006178 | 2024-04-14 | BOQ-PKG-08-00208 | PKG-08 | INV-PKG-08-019-06178 | 139.84 | 65590.76 | 3279.54 | Paid | 62311.22 | 2024-Q2
EXP-006877 | 2024-04-14 | BOQ-PKG-07-00907 | PKG-07 | INV-PKG-07-018-06877 | 84.48 | 103647.96 | 5182.4 | Paid | 98465.56 | 2024-Q2
EXP-003610 | 2024-04-15 | BOQ-PKG-10-01620 | PKG-10 | INV-PKG-10-006-03610 | 236.51 | 125525.44 | 6276.27 | Disputed | 119249.17 | 2024-Q2
EXP-003921 | 2024-04-15 | BOQ-PKG-01-01931 | PKG-01 | INV-PKG-01-002-03921 | 447.2 | 163664.75 | 8183.24 | Paid | 155481.51 | 2024-Q2
EXP-004092 | 2024-04-15 | BOQ-PKG-02-00112 | PKG-02 | INV-PKG-02-033-04092 | 212.8 | 129358.24 | 6467.91 | Paid | 122890.33 | 2024-Q2
EXP-004390 | 2024-04-15 | BOQ-PKG-10-00410 | PKG-10 | INV-PKG-10-016-04390 | 171.05 | 103408.32 | 5170.42 | Disputed | 98237.9 | 2024-Q2
EXP-004450 | 2024-04-15 | BOQ-PKG-10-00470 | PKG-10 | INV-PKG-10-006-04450 | 403.13 | 152107.93 | 7605.4 | Paid | 144502.53 | 2024-Q2
EXP-004512 | 2024-04-15 | BOQ-PKG-02-00532 | PKG-02 | INV-PKG-02-033-04512 | 174.71 | 193779.69 | 9688.98 | Paid | 184090.71 | 2024-Q2
EXP-004843 | 2024-04-15 | BOQ-PKG-03-00863 | PKG-03 | INV-PKG-03-014-04843 | 217.56 | 202425.25 | 10121.26 | Paid | 192303.99 | 2024-Q2
EXP-005241 | 2024-04-15 | BOQ-PKG-01-01261 | PKG-01 | INV-PKG-01-027-05241 | 359.62 | 54890.98 | 2744.55 | Paid | 52146.43 | 2024-Q2
EXP-002054 | 2024-04-16 | BOQ-PKG-04-00064 | PKG-04 | INV-PKG-04-025-02054 | 22.91 | 163613.9 | 8180.7 | Disputed | 155433.2 | 2024-Q2
EXP-002055 | 2024-04-16 | BOQ-PKG-05-00065 | PKG-05 | INV-PKG-05-026-02055 | 385.75 | 116466.26 | 5823.31 | Approved Pending Payment | 110642.95 | 2024-Q2
EXP-000089 | 2024-04-17 | BOQ-PKG-09-00089 | PKG-09 | INV-PKG-09-020-00089 | 430.74 | 138278.5 | 6913.92 | Paid | 131364.58 | 2024-Q2
EXP-000547 | 2024-04-17 | BOQ-PKG-07-00547 | PKG-07 | INV-PKG-07-023-00547 | 108.27 | 160261.49 | 8013.07 | Approved Pending Payment | 152248.42 | 2024-Q2
EXP-002856 | 2024-04-17 | BOQ-PKG-06-00866 | PKG-06 | INV-PKG-06-022-02856 | 69.41 | 82847.09 | 4142.35 | Paid | 78704.74 | 2024-Q2
EXP-003099 | 2024-04-17 | BOQ-PKG-09-01109 | PKG-09 | INV-PKG-09-020-03099 | 439.09 | 49177.79 | 2458.89 | Paid | 46718.9 | 2024-Q2
EXP-006384 | 2024-04-17 | BOQ-PKG-04-00414 | PKG-04 | INV-PKG-04-015-06384 | 71.3 | 135018.75 | 6750.94 | Approved Pending Payment | 128267.81 | 2024-Q2
EXP-006977 | 2024-04-17 | BOQ-PKG-07-01007 | PKG-07 | INV-PKG-07-013-06977 | 120.92 | 119557.57 | 5977.88 | Under Review | 113579.69 | 2024-Q2
EXP-000812 | 2024-04-18 | BOQ-PKG-02-00812 | PKG-02 | INV-PKG-02-008-00812 | 125.76 | 181389.2 | 9069.46 | Disputed | 172319.74 | 2024-Q2
EXP-001068 | 2024-04-18 | BOQ-PKG-08-01068 | PKG-08 | INV-PKG-08-019-01068 | 363.23 | 94082.34 | 4704.12 | Approved Pending Payment | 89378.22 | 2024-Q2
EXP-002361 | 2024-04-18 | BOQ-PKG-01-00371 | PKG-01 | INV-PKG-01-017-02361 | 308.78 | 70543.22 | 3527.16 | Paid | 67016.06 | 2024-Q2
EXP-000814 | 2024-04-19 | BOQ-PKG-04-00814 | PKG-04 | INV-PKG-04-010-00814 | 319.85 | 30621.15 | 1531.06 | Paid | 29090.09 | 2024-Q2
EXP-001184 | 2024-04-19 | BOQ-PKG-04-01184 | PKG-04 | INV-PKG-04-030-01184 | 324.4 | 154778.66 | 7738.93 | Paid | 147039.73 | 2024-Q2
EXP-001496 | 2024-04-19 | BOQ-PKG-06-01496 | PKG-06 | INV-PKG-06-027-01496 | 193.54 | 83865.46 | 4193.27 | Under Review | 79672.19 | 2024-Q2
EXP-001534 | 2024-04-19 | BOQ-PKG-04-01534 | PKG-04 | INV-PKG-04-030-01534 | 161.83 | 95421.79 | 4771.09 | Approved Pending Payment | 90650.7 | 2024-Q2
EXP-001572 | 2024-04-19 | BOQ-PKG-02-01572 | PKG-02 | INV-PKG-02-033-01572 | 266.97 | 163881.61 | 8194.08 | Paid | 155687.53 | 2024-Q2
EXP-001603 | 2024-04-19 | BOQ-PKG-03-01603 | PKG-03 | INV-PKG-03-029-01603 | 74.24 | 195827.62 | 9791.38 | Disputed | 186036.24 | 2024-Q2
EXP-001714 | 2024-04-19 | BOQ-PKG-04-01714 | PKG-04 | INV-PKG-04-035-01714 | 274.48 | 152567.44 | 7628.37 | Under Review | 144939.07 | 2024-Q2
EXP-002222 | 2024-04-19 | BOQ-PKG-02-00232 | PKG-02 | INV-PKG-02-018-02222 | 364.34 | 49555.93 | 2477.8 | Paid | 47078.13 | 2024-Q2
EXP-004321 | 2024-04-19 | BOQ-PKG-01-00341 | PKG-01 | INV-PKG-01-017-04321 | 370.45 | 46735.83 | 2336.79 | Paid | 44399.04 | 2024-Q2
EXP-004930 | 2024-04-19 | BOQ-PKG-10-00950 | PKG-10 | INV-PKG-10-031-04930 | 288.16 | 159968.46 | 7998.42 | Paid | 151970.04 | 2024-Q2
EXP-006323 | 2024-04-19 | BOQ-PKG-03-00353 | PKG-03 | INV-PKG-03-024-06323 | 180.05 | 53103.94 | 2655.2 | Paid | 50448.74 | 2024-Q2
EXP-006578 | 2024-04-19 | BOQ-PKG-08-00608 | PKG-08 | INV-PKG-08-034-06578 | 349.87 | 79834.41 | 3991.72 | Paid | 75842.69 | 2024-Q2
EXP-006623 | 2024-04-19 | BOQ-PKG-03-00653 | PKG-03 | INV-PKG-03-009-06623 | 252.47 | 90405.85 | 4520.29 | Paid | 85885.56 | 2024-Q2
EXP-000329 | 2024-04-20 | BOQ-PKG-09-00329 | PKG-09 | INV-PKG-09-015-00329 | 410.45 | 180744.47 | 9037.22 | Paid | 171707.25 | 2024-Q2
EXP-001688 | 2024-04-20 | BOQ-PKG-08-01688 | PKG-08 | INV-PKG-08-009-01688 | 54.93 | 133829.61 | 6691.48 | Paid | 127138.13 | 2024-Q2
EXP-001768 | 2024-04-20 | BOQ-PKG-08-01768 | PKG-08 | INV-PKG-08-019-01768 | 357.55 | 202284.89 | 10114.24 | Paid | 192170.65 | 2024-Q2
EXP-002051 | 2024-04-20 | BOQ-PKG-01-00061 | PKG-01 | INV-PKG-01-022-02051 | 318.68 | 64120.89 | 3206.04 | Under Review | 60914.85 | 2024-Q2
EXP-004544 | 2024-04-20 | BOQ-PKG-04-00564 | PKG-04 | INV-PKG-04-030-04544 | 39.68 | 27731.71 | 1386.59 | Paid | 26345.12 | 2024-Q2
EXP-004716 | 2024-04-20 | BOQ-PKG-06-00736 | PKG-06 | INV-PKG-06-027-04716 | 329.69 | 121755.68 | 6087.78 | Paid | 115667.9 | 2024-Q2
EXP-005739 | 2024-04-20 | BOQ-PKG-09-01759 | PKG-09 | INV-PKG-09-035-05739 | 248.83 | 130014.33 | 6500.72 | Paid | 123513.61 | 2024-Q2
EXP-005756 | 2024-04-20 | BOQ-PKG-06-01776 | PKG-06 | INV-PKG-06-017-05756 | 416.21 | 144565.63 | 7228.28 | Paid | 137337.35 | 2024-Q2
EXP-000018 | 2024-04-21 | BOQ-PKG-08-00018 | PKG-08 | INV-PKG-08-019-00018 | 61.05 | 209572.67 | 10478.63 | Approved Pending Payment | 199094.04 | 2024-Q2
EXP-000432 | 2024-04-21 | BOQ-PKG-02-00432 | PKG-02 | INV-PKG-02-013-00432 | 187.67 | 200309.18 | 10015.46 | Approved Pending Payment | 190293.72 | 2024-Q2
EXP-001653 | 2024-04-21 | BOQ-PKG-03-01653 | PKG-03 | INV-PKG-03-009-01653 | 28.57 | 189836.77 | 9491.84 | Paid | 180344.93 | 2024-Q2
EXP-005773 | 2024-04-21 | BOQ-PKG-03-01793 | PKG-03 | INV-PKG-03-034-05773 | 33.82 | 160984.16 | 8049.21 | Under Review | 152934.95 | 2024-Q2
EXP-005953 | 2024-04-21 | BOQ-PKG-03-01973 | PKG-03 | INV-PKG-03-004-05953 | 449.91 | 55384.64 | 2769.23 | Under Review | 52615.41 | 2024-Q2
EXP-006077 | 2024-04-21 | BOQ-PKG-07-00107 | PKG-07 | INV-PKG-07-023-06077 | 154.89 | 37595.53 | 1879.78 | Approved Pending Payment | 35715.75 | 2024-Q2
EXP-006530 | 2024-04-21 | BOQ-PKG-10-00560 | PKG-10 | INV-PKG-10-021-06530 | 153.05 | 55218.73 | 2760.94 | Paid | 52457.79 | 2024-Q2
EXP-006908 | 2024-04-21 | BOQ-PKG-08-00938 | PKG-08 | INV-PKG-08-014-06908 | 143.33 | 38306.23 | 1915.31 | Paid | 36390.92 | 2024-Q2
EXP-001426 | 2024-04-22 | BOQ-PKG-06-01426 | PKG-06 | INV-PKG-06-027-01426 | 356.25 | 121323.73 | 6066.19 | Paid | 115257.54 | 2024-Q2
EXP-001868 | 2024-04-22 | BOQ-PKG-08-01868 | PKG-08 | INV-PKG-08-014-01868 | 92.95 | 116936.3 | 5846.82 | Paid | 111089.48 | 2024-Q2
EXP-002434 | 2024-04-22 | BOQ-PKG-04-00444 | PKG-04 | INV-PKG-04-020-02434 | 354.46 | 152348.28 | 7617.41 | Under Review | 144730.87 | 2024-Q2
EXP-003566 | 2024-04-22 | BOQ-PKG-06-01576 | PKG-06 | INV-PKG-06-032-03566 | 6.21 | 80285.03 | 4014.25 | Paid | 76270.78 | 2024-Q2
EXP-004177 | 2024-04-22 | BOQ-PKG-07-00197 | PKG-07 | INV-PKG-07-013-04177 | 236.23 | 134270.8 | 6713.54 | Paid | 127557.26 | 2024-Q2
EXP-004755 | 2024-04-22 | BOQ-PKG-05-00775 | PKG-05 | INV-PKG-05-031-04755 | 65.35 | 181748.53 | 9087.43 | Paid | 172661.1 | 2024-Q2
EXP-000312 | 2024-04-23 | BOQ-PKG-02-00312 | PKG-02 | INV-PKG-02-033-00312 | 69.75 | 188122.64 | 9406.13 | Paid | 178716.51 | 2024-Q2
EXP-000349 | 2024-04-23 | BOQ-PKG-09-00349 | PKG-09 | INV-PKG-09-035-00349 | 193.21 | 167636.9 | 8381.84 | Paid | 159255.06 | 2024-Q2
EXP-001313 | 2024-04-23 | BOQ-PKG-03-01313 | PKG-03 | INV-PKG-03-019-01313 | 277.56 | 165108.34 | 8255.42 | Under Review | 156852.92 | 2024-Q2
EXP-003009 | 2024-04-23 | BOQ-PKG-09-01019 | PKG-09 | INV-PKG-09-035-03009 | 403.91 | 137786.71 | 6889.34 | Paid | 130897.37 | 2024-Q2
EXP-003392 | 2024-04-23 | BOQ-PKG-02-01402 | PKG-02 | INV-PKG-02-033-03392 | 164.97 | 51093.7 | 2554.68 | Paid | 48539.02 | 2024-Q2
EXP-004488 | 2024-04-23 | BOQ-PKG-08-00508 | PKG-08 | INV-PKG-08-009-04488 | 48.13 | 171100.36 | 8555.02 | Approved Pending Payment | 162545.34 | 2024-Q2
EXP-004526 | 2024-04-23 | BOQ-PKG-06-00546 | PKG-06 | INV-PKG-06-012-04526 | 265.83 | 49779.62 | 2488.98 | Paid | 47290.64 | 2024-Q2
EXP-004784 | 2024-04-23 | BOQ-PKG-04-00804 | PKG-04 | INV-PKG-04-025-04784 | 166.3 | 80665.27 | 4033.26 | Under Review | 76632.01 | 2024-Q2
EXP-006097 | 2024-04-23 | BOQ-PKG-07-00127 | PKG-07 | INV-PKG-07-008-06097 | 389.72 | 115809.6 | 5790.48 | Approved Pending Payment | 110019.12 | 2024-Q2
EXP-006804 | 2024-04-23 | BOQ-PKG-04-00834 | PKG-04 | INV-PKG-04-015-06804 | 302.17 | 140004.91 | 7000.25 | Paid | 133004.66 | 2024-Q2
EXP-006839 | 2024-04-23 | BOQ-PKG-09-00869 | PKG-09 | INV-PKG-09-015-06839 | 65.73 | 134463.19 | 6723.16 | Paid | 127740.03 | 2024-Q2
EXP-000047 | 2024-04-24 | BOQ-PKG-07-00047 | PKG-07 | INV-PKG-07-013-00047 | 265.59 | 122954.55 | 6147.73 | Paid | 116806.82 | 2024-Q2
EXP-001672 | 2024-04-24 | BOQ-PKG-02-01672 | PKG-02 | INV-PKG-02-028-01672 | 88.81 | 120082.32 | 6004.12 | Paid | 114078.2 | 2024-Q2
EXP-003148 | 2024-04-24 | BOQ-PKG-08-01158 | PKG-08 | INV-PKG-08-034-03148 | 15.81 | 183676.87 | 9183.84 | Paid | 174493.03 | 2024-Q2
EXP-005718 | 2024-04-24 | BOQ-PKG-08-01738 | PKG-08 | INV-PKG-08-014-05718 | 129.56 | 68833.58 | 3441.68 | Disputed | 65391.9 | 2024-Q2
EXP-000163 | 2024-04-25 | BOQ-PKG-03-00163 | PKG-03 | INV-PKG-03-024-00163 | 429.26 | 34624.98 | 1731.25 | Paid | 32893.73 | 2024-Q2
EXP-000226 | 2024-04-25 | BOQ-PKG-06-00226 | PKG-06 | INV-PKG-06-017-00226 | 168.23 | 43402.19 | 2170.11 | Disputed | 41232.08 | 2024-Q2
EXP-000313 | 2024-04-25 | BOQ-PKG-03-00313 | PKG-03 | INV-PKG-03-034-00313 | 294.05 | 190785.38 | 9539.27 | Paid | 181246.11 | 2024-Q2
EXP-000766 | 2024-04-25 | BOQ-PKG-06-00766 | PKG-06 | INV-PKG-06-032-00766 | 325.16 | 180002.81 | 9000.14 | Paid | 171002.67 | 2024-Q2
EXP-001114 | 2024-04-25 | BOQ-PKG-04-01114 | PKG-04 | INV-PKG-04-030-01114 | 69.8 | 30110.46 | 1505.52 | Under Review | 28604.94 | 2024-Q2
EXP-001784 | 2024-04-25 | BOQ-PKG-04-01784 | PKG-04 | INV-PKG-04-035-01784 | 224.74 | 192800.46 | 9640.02 | Paid | 183160.44 | 2024-Q2
EXP-002037 | 2024-04-25 | BOQ-PKG-07-00047 | PKG-07 | INV-PKG-07-008-02037 | 46.2 | 151696.91 | 7584.85 | Paid | 144112.06 | 2024-Q2
EXP-002357 | 2024-04-25 | BOQ-PKG-07-00367 | PKG-07 | INV-PKG-07-013-02357 | 135.21 | 122627.61 | 6131.38 | Paid | 116496.23 | 2024-Q2
EXP-002694 | 2024-04-25 | BOQ-PKG-04-00704 | PKG-04 | INV-PKG-04-035-02694 | 67.14 | 117967.5 | 5898.38 | Paid | 112069.12 | 2024-Q2
EXP-003675 | 2024-04-25 | BOQ-PKG-05-01685 | PKG-05 | INV-PKG-05-001-03675 | 413.27 | 197225.02 | 9861.25 | Approved Pending Payment | 187363.77 | 2024-Q2
EXP-003676 | 2024-04-25 | BOQ-PKG-06-01686 | PKG-06 | INV-PKG-06-002-03676 | 199.97 | 50324.23 | 2516.21 | Paid | 47808.02 | 2024-Q2
EXP-003798 | 2024-04-25 | BOQ-PKG-08-01808 | PKG-08 | INV-PKG-08-019-03798 | 367.47 | 136964.52 | 6848.23 | Paid | 130116.29 | 2024-Q2
EXP-004182 | 2024-04-25 | BOQ-PKG-02-00202 | PKG-02 | INV-PKG-02-018-04182 | 107.28 | 26454.18 | 1322.71 | Paid | 25131.47 | 2024-Q2
EXP-004422 | 2024-04-25 | BOQ-PKG-02-00442 | PKG-02 | INV-PKG-02-013-04422 | 29.29 | 178436.68 | 8921.83 | Paid | 169514.85 | 2024-Q2
EXP-005278 | 2024-04-25 | BOQ-PKG-08-01298 | PKG-08 | INV-PKG-08-029-05278 | 92.97 | 170226.83 | 8511.34 | Approved Pending Payment | 161715.49 | 2024-Q2
EXP-006278 | 2024-04-25 | BOQ-PKG-08-00308 | PKG-08 | INV-PKG-08-014-06278 | 70.8 | 31873.17 | 1593.66 | Under Review | 30279.51 | 2024-Q2
EXP-006493 | 2024-04-25 | BOQ-PKG-03-00523 | PKG-03 | INV-PKG-03-019-06493 | 11.86 | 99992.38 | 4999.62 | Approved Pending Payment | 94992.76 | 2024-Q2
EXP-001262 | 2024-04-26 | BOQ-PKG-02-01262 | PKG-02 | INV-PKG-02-003-01262 | 195.4 | 42753.2 | 2137.66 | Paid | 40615.54 | 2024-Q2
EXP-001467 | 2024-04-26 | BOQ-PKG-07-01467 | PKG-07 | INV-PKG-07-033-01467 | 231.45 | 114651.6 | 5732.58 | Under Review | 108919.02 | 2024-Q2
EXP-001891 | 2024-04-26 | BOQ-PKG-01-01891 | PKG-01 | INV-PKG-01-002-01891 | 421.11 | 78397.9 | 3919.9 | Paid | 74478 | 2024-Q2
EXP-003593 | 2024-04-26 | BOQ-PKG-03-01603 | PKG-03 | INV-PKG-03-024-03593 | 368.32 | 165984.79 | 8299.24 | Paid | 157685.55 | 2024-Q2
EXP-004248 | 2024-04-26 | BOQ-PKG-08-00268 | PKG-08 | INV-PKG-08-014-04248 | 292.93 | 162741.69 | 8137.08 | Paid | 154604.61 | 2024-Q2
EXP-004320 | 2024-04-26 | BOQ-PKG-10-00340 | PKG-10 | INV-PKG-10-016-04320 | 122.95 | 36451.1 | 1822.56 | Disputed | 34628.54 | 2024-Q2
EXP-004665 | 2024-04-26 | BOQ-PKG-05-00685 | PKG-05 | INV-PKG-05-011-04665 | 290.07 | 201498.4 | 10074.92 | Disputed | 191423.48 | 2024-Q2
EXP-005291 | 2024-04-26 | BOQ-PKG-01-01311 | PKG-01 | INV-PKG-01-007-05291 | 354.25 | 58701.55 | 2935.08 | Under Review | 55766.47 | 2024-Q2
EXP-005923 | 2024-04-26 | BOQ-PKG-03-01943 | PKG-03 | INV-PKG-03-009-05923 | 246.04 | 91735.46 | 4586.77 | Paid | 87148.69 | 2024-Q2
EXP-006261 | 2024-04-26 | BOQ-PKG-01-00291 | PKG-01 | INV-PKG-01-032-06261 | 264.47 | 188849.86 | 9442.49 | Under Review | 179407.37 | 2024-Q2
EXP-006527 | 2024-04-26 | BOQ-PKG-07-00557 | PKG-07 | INV-PKG-07-018-06527 | 46.98 | 155453.01 | 7772.65 | Paid | 147680.36 | 2024-Q2
EXP-006981 | 2024-04-26 | BOQ-PKG-01-01011 | PKG-01 | INV-PKG-01-017-06981 | 392.04 | 165135.68 | 8256.78 | Paid | 156878.9 | 2024-Q2
EXP-000703 | 2024-04-27 | BOQ-PKG-03-00703 | PKG-03 | INV-PKG-03-004-00703 | 181.79 | 87303.75 | 4365.19 | Under Review | 82938.56 | 2024-Q2
EXP-001192 | 2024-04-27 | BOQ-PKG-02-01192 | PKG-02 | INV-PKG-02-003-01192 | 215.39 | 154776.59 | 7738.83 | Approved Pending Payment | 147037.76 | 2024-Q2
EXP-001521 | 2024-04-27 | BOQ-PKG-01-01521 | PKG-01 | INV-PKG-01-017-01521 | 116.58 | 194176.56 | 9708.83 | Paid | 184467.73 | 2024-Q2
EXP-002942 | 2024-04-27 | BOQ-PKG-02-00952 | PKG-02 | INV-PKG-02-003-02942 | 327.34 | 50270.13 | 2513.51 | Paid | 47756.62 | 2024-Q2
EXP-004779 | 2024-04-27 | BOQ-PKG-09-00799 | PKG-09 | INV-PKG-09-020-04779 | 235.9 | 96189.28 | 4809.46 | Under Review | 91379.82 | 2024-Q2
EXP-004993 | 2024-04-27 | BOQ-PKG-03-01013 | PKG-03 | INV-PKG-03-024-04993 | 133.89 | 157492.57 | 7874.63 | Paid | 149617.94 | 2024-Q2
EXP-006130 | 2024-04-27 | BOQ-PKG-10-00160 | PKG-10 | INV-PKG-10-006-06130 | 169.06 | 125878.46 | 6293.92 | Paid | 119584.54 | 2024-Q2
EXP-006644 | 2024-04-27 | BOQ-PKG-04-00674 | PKG-04 | INV-PKG-04-030-06644 | 165.57 | 171765.69 | 8588.28 | Paid | 163177.41 | 2024-Q2
EXP-000389 | 2024-04-28 | BOQ-PKG-09-00389 | PKG-09 | INV-PKG-09-005-00389 | 434.8 | 57228 | 2861.4 | Paid | 54366.6 | 2024-Q2
EXP-001946 | 2024-04-28 | BOQ-PKG-06-01946 | PKG-06 | INV-PKG-06-022-01946 | 254.13 | 72657.59 | 3632.88 | Approved Pending Payment | 69024.71 | 2024-Q2
EXP-002232 | 2024-04-28 | BOQ-PKG-02-00242 | PKG-02 | INV-PKG-02-028-02232 | 17.23 | 73684.14 | 3684.21 | Approved Pending Payment | 69999.93 | 2024-Q2
EXP-002413 | 2024-04-28 | BOQ-PKG-03-00423 | PKG-03 | INV-PKG-03-034-02413 | 403.47 | 31429.49 | 1571.47 | Paid | 29858.02 | 2024-Q2
EXP-004022 | 2024-04-28 | BOQ-PKG-02-00042 | PKG-02 | INV-PKG-02-033-04022 | 50.26 | 161773.92 | 8088.7 | Paid | 153685.22 | 2024-Q2
EXP-004695 | 2024-04-28 | BOQ-PKG-05-00715 | PKG-05 | INV-PKG-05-006-04695 | 146.95 | 180253.74 | 9012.69 | Paid | 171241.05 | 2024-Q2
EXP-005159 | 2024-04-28 | BOQ-PKG-09-01179 | PKG-09 | INV-PKG-09-015-05159 | 38.31 | 93763.27 | 4688.16 | Paid | 89075.11 | 2024-Q2
EXP-005609 | 2024-04-28 | BOQ-PKG-09-01629 | PKG-09 | INV-PKG-09-010-05609 | 139.3 | 29334.8 | 1466.74 | Paid | 27868.06 | 2024-Q2
EXP-001582 | 2024-04-29 | BOQ-PKG-02-01582 | PKG-02 | INV-PKG-02-008-01582 | 113.51 | 79930.98 | 3996.55 | Paid | 75934.43 | 2024-Q2
EXP-001627 | 2024-04-29 | BOQ-PKG-07-01627 | PKG-07 | INV-PKG-07-018-01627 | 326.63 | 75737.6 | 3786.88 | Disputed | 71950.72 | 2024-Q2
EXP-003279 | 2024-04-29 | BOQ-PKG-09-01289 | PKG-09 | INV-PKG-09-025-03279 | 190.2 | 170622.32 | 8531.12 | Paid | 162091.2 | 2024-Q2
EXP-003448 | 2024-04-29 | BOQ-PKG-08-01458 | PKG-08 | INV-PKG-08-019-03448 | 308.75 | 214293.87 | 10714.69 | Under Review | 203579.18 | 2024-Q2
EXP-004701 | 2024-04-29 | BOQ-PKG-01-00721 | PKG-01 | INV-PKG-01-012-04701 | 23.24 | 87165.93 | 4358.3 | Approved Pending Payment | 82807.63 | 2024-Q2
EXP-000980 | 2024-04-30 | BOQ-PKG-10-00980 | PKG-10 | INV-PKG-10-001-00980 | 47.22 | 85261.36 | 4263.07 | Paid | 80998.29 | 2024-Q2
EXP-001075 | 2024-04-30 | BOQ-PKG-05-01075 | PKG-05 | INV-PKG-05-026-01075 | 159.74 | 183192.76 | 9159.64 | Paid | 174033.12 | 2024-Q2
EXP-001101 | 2024-04-30 | BOQ-PKG-01-01101 | PKG-01 | INV-PKG-01-017-01101 | 134.59 | 141917.42 | 7095.87 | Under Review | 134821.55 | 2024-Q2
EXP-002366 | 2024-04-30 | BOQ-PKG-06-00376 | PKG-06 | INV-PKG-06-022-02366 | 67.77 | 182600.45 | 9130.02 | Paid | 173470.43 | 2024-Q2
EXP-005137 | 2024-04-30 | BOQ-PKG-07-01157 | PKG-07 | INV-PKG-07-028-05137 | 317.64 | 182026.59 | 9101.33 | Paid | 172925.26 | 2024-Q2
EXP-005594 | 2024-04-30 | BOQ-PKG-04-01614 | PKG-04 | INV-PKG-04-030-05594 | 257.58 | 90498.2 | 4524.91 | Paid | 85973.29 | 2024-Q2
EXP-000529 | 2024-05-01 | BOQ-PKG-09-00529 | PKG-09 | INV-PKG-09-005-00529 | 185.83 | 114872.86 | 5743.64 | Approved Pending Payment | 109129.22 | 2024-Q2
EXP-000559 | 2024-05-01 | BOQ-PKG-09-00559 | PKG-09 | INV-PKG-09-035-00559 | 392.16 | 138958.72 | 6947.94 | Paid | 132010.78 | 2024-Q2
EXP-001167 | 2024-05-01 | BOQ-PKG-07-01167 | PKG-07 | INV-PKG-07-013-01167 | 373.58 | 72503.02 | 3625.15 | Under Review | 68877.87 | 2024-Q2
EXP-001654 | 2024-05-01 | BOQ-PKG-04-01654 | PKG-04 | INV-PKG-04-010-01654 | 19.76 | 42461.4 | 2123.07 | Disputed | 40338.33 | 2024-Q2
EXP-001748 | 2024-05-01 | BOQ-PKG-08-01748 | PKG-08 | INV-PKG-08-034-01748 | 37.18 | 165510.21 | 8275.51 | Paid | 157234.7 | 2024-Q2
EXP-002001 | 2024-05-01 | BOQ-PKG-01-00011 | PKG-01 | INV-PKG-01-007-02001 | 380.01 | 70986.18 | 3549.31 | Under Review | 67436.87 | 2024-Q2
EXP-002367 | 2024-05-01 | BOQ-PKG-07-00377 | PKG-07 | INV-PKG-07-023-02367 | 28.77 | 139833.91 | 6991.7 | Paid | 132842.21 | 2024-Q2
EXP-002842 | 2024-05-01 | BOQ-PKG-02-00852 | PKG-02 | INV-PKG-02-008-02842 | 34.23 | 160679.42 | 8033.97 | Under Review | 152645.45 | 2024-Q2
EXP-003258 | 2024-05-01 | BOQ-PKG-08-01268 | PKG-08 | INV-PKG-08-004-03258 | 270.57 | 89793.69 | 4489.68 | Paid | 85304.01 | 2024-Q2
EXP-003785 | 2024-05-01 | BOQ-PKG-05-01795 | PKG-05 | INV-PKG-05-006-03785 | 298.38 | 203992.39 | 10199.62 | Paid | 193792.77 | 2024-Q2
EXP-005626 | 2024-05-01 | BOQ-PKG-06-01646 | PKG-06 | INV-PKG-06-027-05626 | 73.37 | 206218.14 | 10310.91 | Paid | 195907.23 | 2024-Q2
EXP-006711 | 2024-05-01 | BOQ-PKG-01-00741 | PKG-01 | INV-PKG-01-027-06711 | 159.29 | 90369.43 | 4518.47 | Paid | 85850.96 | 2024-Q2
EXP-006782 | 2024-05-01 | BOQ-PKG-02-00812 | PKG-02 | INV-PKG-02-028-06782 | 147.02 | 25727.85 | 1286.39 | Approved Pending Payment | 24441.46 | 2024-Q2
EXP-003663 | 2024-05-02 | BOQ-PKG-03-01673 | PKG-03 | INV-PKG-03-024-03663 | 379.89 | 113538.27 | 5676.91 | Paid | 107861.36 | 2024-Q2
EXP-004152 | 2024-05-02 | BOQ-PKG-02-00172 | PKG-02 | INV-PKG-02-023-04152 | 233.41 | 125711.45 | 6285.57 | Paid | 119425.88 | 2024-Q2
EXP-005465 | 2024-05-02 | BOQ-PKG-05-01485 | PKG-05 | INV-PKG-05-006-05465 | 397.59 | 142069.75 | 7103.49 | Paid | 134966.26 | 2024-Q2
EXP-006789 | 2024-05-02 | BOQ-PKG-09-00819 | PKG-09 | INV-PKG-09-035-06789 | 199.02 | 166843.3 | 8342.16 | Under Review | 158501.14 | 2024-Q2
EXP-000057 | 2024-05-03 | BOQ-PKG-07-00057 | PKG-07 | INV-PKG-07-023-00057 | 398.06 | 100495.39 | 5024.77 | Paid | 95470.62 | 2024-Q2
EXP-001115 | 2024-05-03 | BOQ-PKG-05-01115 | PKG-05 | INV-PKG-05-031-01115 | 426.09 | 162597.81 | 8129.89 | Paid | 154467.92 | 2024-Q2
EXP-001566 | 2024-05-03 | BOQ-PKG-06-01566 | PKG-06 | INV-PKG-06-027-01566 | 328.06 | 32362.6 | 1618.13 | Paid | 30744.47 | 2024-Q2
EXP-003163 | 2024-05-03 | BOQ-PKG-03-01173 | PKG-03 | INV-PKG-03-014-03163 | 232.36 | 112759.94 | 5638 | Paid | 107121.94 | 2024-Q2
EXP-005118 | 2024-05-03 | BOQ-PKG-08-01138 | PKG-08 | INV-PKG-08-009-05118 | 169.45 | 89240.43 | 4462.02 | Paid | 84778.41 | 2024-Q2
EXP-000526 | 2024-05-04 | BOQ-PKG-06-00526 | PKG-06 | INV-PKG-06-002-00526 | 62.43 | 128422.14 | 6421.11 | Paid | 122001.03 | 2024-Q2
EXP-000999 | 2024-05-04 | BOQ-PKG-09-00999 | PKG-09 | INV-PKG-09-020-00999 | 270.43 | 72800.9 | 3640.04 | Paid | 69160.86 | 2024-Q2
EXP-004668 | 2024-05-04 | BOQ-PKG-08-00688 | PKG-08 | INV-PKG-08-014-04668 | 414.29 | 145701.28 | 7285.06 | Approved Pending Payment | 138416.22 | 2024-Q2
EXP-005074 | 2024-05-04 | BOQ-PKG-04-01094 | PKG-04 | INV-PKG-04-035-05074 | 44.09 | 148582.87 | 7429.14 | Paid | 141153.73 | 2024-Q2
EXP-006122 | 2024-05-04 | BOQ-PKG-02-00152 | PKG-02 | INV-PKG-02-033-06122 | 167.93 | 73300.47 | 3665.02 | Paid | 69635.45 | 2024-Q2
EXP-001317 | 2024-05-05 | BOQ-PKG-07-01317 | PKG-07 | INV-PKG-07-023-01317 | 431.42 | 40068.23 | 2003.41 | Paid | 38064.82 | 2024-Q2
EXP-002241 | 2024-05-05 | BOQ-PKG-01-00251 | PKG-01 | INV-PKG-01-002-02241 | 83.26 | 168771.07 | 8438.55 | Paid | 160332.52 | 2024-Q2
EXP-005194 | 2024-05-05 | BOQ-PKG-04-01214 | PKG-04 | INV-PKG-04-015-05194 | 69.62 | 40742.26 | 2037.11 | Paid | 38705.15 | 2024-Q2
EXP-005219 | 2024-05-05 | BOQ-PKG-09-01239 | PKG-09 | INV-PKG-09-005-05219 | 68.5 | 95254.44 | 4762.72 | Paid | 90491.72 | 2024-Q2
EXP-005537 | 2024-05-05 | BOQ-PKG-07-01557 | PKG-07 | INV-PKG-07-008-05537 | 194.61 | 58544.99 | 2927.25 | Under Review | 55617.74 | 2024-Q2
EXP-000035 | 2024-05-06 | BOQ-PKG-05-00035 | PKG-05 | INV-PKG-05-001-00035 | 5.01 | 155139.95 | 7757 | Paid | 147382.95 | 2024-Q2
EXP-002188 | 2024-05-06 | BOQ-PKG-08-00198 | PKG-08 | INV-PKG-08-019-02188 | 352.44 | 93559.4 | 4677.97 | Paid | 88881.43 | 2024-Q2
EXP-003298 | 2024-05-06 | BOQ-PKG-08-01308 | PKG-08 | INV-PKG-08-009-03298 | 120.04 | 190095.23 | 9504.76 | Paid | 180590.47 | 2024-Q2
EXP-003858 | 2024-05-06 | BOQ-PKG-08-01868 | PKG-08 | INV-PKG-08-009-03858 | 111.73 | 60858.28 | 3042.91 | Under Review | 57815.37 | 2024-Q2
EXP-004467 | 2024-05-06 | BOQ-PKG-07-00487 | PKG-07 | INV-PKG-07-023-04467 | 272.82 | 204365.06 | 10218.25 | Approved Pending Payment | 194146.81 | 2024-Q2
EXP-005574 | 2024-05-06 | BOQ-PKG-04-01594 | PKG-04 | INV-PKG-04-010-05574 | 129.36 | 146990.68 | 7349.53 | Paid | 139641.15 | 2024-Q2
EXP-005976 | 2024-05-06 | BOQ-PKG-06-00006 | PKG-06 | INV-PKG-06-027-05976 | 317.62 | 91951.94 | 4597.6 | Paid | 87354.34 | 2024-Q2
EXP-006980 | 2024-05-06 | BOQ-PKG-10-01010 | PKG-10 | INV-PKG-10-016-06980 | 412.08 | 34251.15 | 1712.56 | Under Review | 32538.59 | 2024-Q2
EXP-000131 | 2024-05-07 | BOQ-PKG-01-00131 | PKG-01 | INV-PKG-01-027-00131 | 143.87 | 178673.79 | 8933.69 | Paid | 169740.1 | 2024-Q2
EXP-000152 | 2024-05-07 | BOQ-PKG-02-00152 | PKG-02 | INV-PKG-02-013-00152 | 233.01 | 88195.47 | 4409.77 | Paid | 83785.7 | 2024-Q2
EXP-000616 | 2024-05-07 | BOQ-PKG-06-00616 | PKG-06 | INV-PKG-06-022-00616 | 362.18 | 72241.66 | 3612.08 | Under Review | 68629.58 | 2024-Q2
EXP-001487 | 2024-05-07 | BOQ-PKG-07-01487 | PKG-07 | INV-PKG-07-018-01487 | 190.44 | 36343.86 | 1817.19 | Paid | 34526.67 | 2024-Q2
EXP-002048 | 2024-05-07 | BOQ-PKG-08-00058 | PKG-08 | INV-PKG-08-019-02048 | 40.8 | 52118.05 | 2605.9 | Paid | 49512.15 | 2024-Q2
EXP-004193 | 2024-05-07 | BOQ-PKG-03-00213 | PKG-03 | INV-PKG-03-029-04193 | 76.65 | 128025.05 | 6401.25 | Paid | 121623.8 | 2024-Q2
EXP-004906 | 2024-05-07 | BOQ-PKG-06-00926 | PKG-06 | INV-PKG-06-007-04906 | 95.2 | 53816.19 | 2690.81 | Approved Pending Payment | 51125.38 | 2024-Q2
EXP-005042 | 2024-05-07 | BOQ-PKG-02-01062 | PKG-02 | INV-PKG-02-003-05042 | 214.75 | 150394.41 | 7519.72 | Paid | 142874.69 | 2024-Q2
EXP-005281 | 2024-05-07 | BOQ-PKG-01-01301 | PKG-01 | INV-PKG-01-032-05281 | 78.38 | 197533.35 | 9876.67 | Paid | 187656.68 | 2024-Q2
EXP-006466 | 2024-05-07 | BOQ-PKG-06-00496 | PKG-06 | INV-PKG-06-027-06466 | 182.64 | 64314.47 | 3215.72 | Paid | 61098.75 | 2024-Q2
EXP-000151 | 2024-05-08 | BOQ-PKG-01-00151 | PKG-01 | INV-PKG-01-012-00151 | 35.08 | 164467.43 | 8223.37 | Paid | 156244.06 | 2024-Q2
EXP-000457 | 2024-05-08 | BOQ-PKG-07-00457 | PKG-07 | INV-PKG-07-003-00457 | 383.93 | 55156.67 | 2757.83 | Approved Pending Payment | 52398.84 | 2024-Q2
EXP-000833 | 2024-05-08 | BOQ-PKG-03-00833 | PKG-03 | INV-PKG-03-029-00833 | 318.07 | 142914.93 | 7145.75 | Under Review | 135769.18 | 2024-Q2
EXP-001576 | 2024-05-08 | BOQ-PKG-06-01576 | PKG-06 | INV-PKG-06-002-01576 | 241.73 | 92628.56 | 4631.43 | Approved Pending Payment | 87997.13 | 2024-Q2
EXP-002594 | 2024-05-08 | BOQ-PKG-04-00604 | PKG-04 | INV-PKG-04-005-02594 | 392.29 | 192764.54 | 9638.23 | Paid | 183126.31 | 2024-Q2
EXP-003328 | 2024-05-08 | BOQ-PKG-08-01338 | PKG-08 | INV-PKG-08-004-03328 | 135.72 | 205592.19 | 10279.61 | Paid | 195312.58 | 2024-Q2
EXP-004233 | 2024-05-08 | BOQ-PKG-03-00253 | PKG-03 | INV-PKG-03-034-04233 | 279.57 | 139915.34 | 6995.77 | Paid | 132919.57 | 2024-Q2
EXP-004353 | 2024-05-08 | BOQ-PKG-03-00373 | PKG-03 | INV-PKG-03-014-04353 | 404.37 | 38312.16 | 1915.61 | Paid | 36396.55 | 2024-Q2
EXP-006246 | 2024-05-08 | BOQ-PKG-06-00276 | PKG-06 | INV-PKG-06-017-06246 | 296.18 | 117110.9 | 5855.54 | Paid | 111255.36 | 2024-Q2
EXP-000792 | 2024-05-09 | BOQ-PKG-02-00792 | PKG-02 | INV-PKG-02-023-00792 | 231.84 | 131745.3 | 6587.26 | Paid | 125158.04 | 2024-Q2
EXP-001307 | 2024-05-09 | BOQ-PKG-07-01307 | PKG-07 | INV-PKG-07-013-01307 | 252.45 | 84605.47 | 4230.27 | Paid | 80375.2 | 2024-Q2
EXP-001549 | 2024-05-09 | BOQ-PKG-09-01549 | PKG-09 | INV-PKG-09-010-01549 | 389.77 | 116725.64 | 5836.28 | Paid | 110889.36 | 2024-Q2
EXP-001887 | 2024-05-09 | BOQ-PKG-07-01887 | PKG-07 | INV-PKG-07-033-01887 | 100.67 | 30009.83 | 1500.49 | Under Review | 28509.34 | 2024-Q2
EXP-004562 | 2024-05-09 | BOQ-PKG-02-00582 | PKG-02 | INV-PKG-02-013-04562 | 145.27 | 143514.2 | 7175.71 | Paid | 136338.49 | 2024-Q2
EXP-004948 | 2024-05-09 | BOQ-PKG-08-00968 | PKG-08 | INV-PKG-08-014-04948 | 318.99 | 198097.75 | 9904.89 | Paid | 188192.86 | 2024-Q2
EXP-002768 | 2024-05-10 | BOQ-PKG-08-00778 | PKG-08 | INV-PKG-08-004-02768 | 214.86 | 144922.66 | 7246.13 | Paid | 137676.53 | 2024-Q2
EXP-003827 | 2024-05-10 | BOQ-PKG-07-01837 | PKG-07 | INV-PKG-07-013-03827 | 101.49 | 190602.37 | 9530.12 | Under Review | 181072.25 | 2024-Q2
EXP-005402 | 2024-05-10 | BOQ-PKG-02-01422 | PKG-02 | INV-PKG-02-013-05402 | 80.51 | 85739.31 | 4286.97 | Under Review | 81452.34 | 2024-Q2
EXP-006544 | 2024-05-10 | BOQ-PKG-04-00574 | PKG-04 | INV-PKG-04-035-06544 | 23.9 | 174383.7 | 8719.19 | Paid | 165664.51 | 2024-Q2
EXP-000085 | 2024-05-11 | BOQ-PKG-05-00085 | PKG-05 | INV-PKG-05-016-00085 | 235.76 | 69064.24 | 3453.21 | Disputed | 65611.03 | 2024-Q2
EXP-000165 | 2024-05-11 | BOQ-PKG-05-00165 | PKG-05 | INV-PKG-05-026-00165 | 36.39 | 189036.93 | 9451.85 | Approved Pending Payment | 179585.08 | 2024-Q2
EXP-004949 | 2024-05-11 | BOQ-PKG-09-00969 | PKG-09 | INV-PKG-09-015-04949 | 196.6 | 80110.5 | 4005.52 | Paid | 76104.98 | 2024-Q2
EXP-005141 | 2024-05-11 | BOQ-PKG-01-01161 | PKG-01 | INV-PKG-01-032-05141 | 117.04 | 129871.61 | 6493.58 | Paid | 123378.03 | 2024-Q2
EXP-005699 | 2024-05-11 | BOQ-PKG-09-01719 | PKG-09 | INV-PKG-09-030-05699 | 133 | 156735.45 | 7836.77 | Approved Pending Payment | 148898.68 | 2024-Q2
EXP-005843 | 2024-05-11 | BOQ-PKG-03-01863 | PKG-03 | INV-PKG-03-034-05843 | 344.33 | 87461.83 | 4373.09 | Paid | 83088.74 | 2024-Q2
EXP-006271 | 2024-05-11 | BOQ-PKG-01-00301 | PKG-01 | INV-PKG-01-007-06271 | 65.07 | 46151.25 | 2307.56 | Paid | 43843.69 | 2024-Q2
EXP-000976 | 2024-05-12 | BOQ-PKG-06-00976 | PKG-06 | INV-PKG-06-032-00976 | 100.35 | 36188.09 | 1809.4 | Paid | 34378.69 | 2024-Q2
EXP-003310 | 2024-05-12 | BOQ-PKG-10-01320 | PKG-10 | INV-PKG-10-021-03310 | 439.7 | 215058.3 | 10752.92 | Paid | 204305.38 | 2024-Q2
EXP-003457 | 2024-05-12 | BOQ-PKG-07-01467 | PKG-07 | INV-PKG-07-028-03457 | 170.86 | 203794.28 | 10189.71 | Paid | 193604.57 | 2024-Q2
EXP-004744 | 2024-05-12 | BOQ-PKG-04-00764 | PKG-04 | INV-PKG-04-020-04744 | 420.32 | 137784.53 | 6889.23 | Paid | 130895.3 | 2024-Q2
EXP-005222 | 2024-05-12 | BOQ-PKG-02-01242 | PKG-02 | INV-PKG-02-008-05222 | 337.35 | 139572.21 | 6978.61 | Paid | 132593.6 | 2024-Q2
EXP-005231 | 2024-05-12 | BOQ-PKG-01-01251 | PKG-01 | INV-PKG-01-017-05231 | 25.01 | 196321.07 | 9816.05 | Under Review | 186505.02 | 2024-Q2
EXP-001036 | 2024-05-13 | BOQ-PKG-06-01036 | PKG-06 | INV-PKG-06-022-01036 | 420.03 | 138599.34 | 6929.97 | Paid | 131669.37 | 2024-Q2
EXP-001238 | 2024-05-13 | BOQ-PKG-08-01238 | PKG-08 | INV-PKG-08-014-01238 | 191.21 | 88258.73 | 4412.94 | Paid | 83845.79 | 2024-Q2
EXP-004106 | 2024-05-13 | BOQ-PKG-06-00126 | PKG-06 | INV-PKG-06-012-04106 | 47.98 | 178932.2 | 8946.61 | Paid | 169985.59 | 2024-Q2
EXP-004200 | 2024-05-13 | BOQ-PKG-10-00220 | PKG-10 | INV-PKG-10-001-04200 | 34.04 | 129082.21 | 6454.11 | Paid | 122628.1 | 2024-Q2
EXP-004325 | 2024-05-13 | BOQ-PKG-05-00345 | PKG-05 | INV-PKG-05-021-04325 | 276.03 | 134708.4 | 6735.42 | Approved Pending Payment | 127972.98 | 2024-Q2
EXP-005939 | 2024-05-13 | BOQ-PKG-09-01959 | PKG-09 | INV-PKG-09-025-05939 | 254.61 | 185540.21 | 9277.01 | Paid | 176263.2 | 2024-Q2
EXP-006039 | 2024-05-13 | BOQ-PKG-09-00069 | PKG-09 | INV-PKG-09-020-06039 | 200.51 | 55371.42 | 2768.57 | Paid | 52602.85 | 2024-Q2
EXP-000598 | 2024-05-14 | BOQ-PKG-08-00598 | PKG-08 | INV-PKG-08-004-00598 | 379.94 | 92712.2 | 4635.61 | Paid | 88076.59 | 2024-Q2
EXP-000815 | 2024-05-14 | BOQ-PKG-05-00815 | PKG-05 | INV-PKG-05-011-00815 | 83.17 | 206306.28 | 10315.31 | Approved Pending Payment | 195990.97 | 2024-Q2
EXP-000960 | 2024-05-14 | BOQ-PKG-10-00960 | PKG-10 | INV-PKG-10-016-00960 | 438.29 | 68432.68 | 3421.63 | Paid | 65011.05 | 2024-Q2
EXP-001273 | 2024-05-14 | BOQ-PKG-03-01273 | PKG-03 | INV-PKG-03-014-01273 | 256.71 | 51271.66 | 2563.58 | Under Review | 48708.08 | 2024-Q2
EXP-001966 | 2024-05-14 | BOQ-PKG-06-01966 | PKG-06 | INV-PKG-06-007-01966 | 181.19 | 73404.82 | 3670.24 | Paid | 69734.58 | 2024-Q2
EXP-002191 | 2024-05-14 | BOQ-PKG-01-00201 | PKG-01 | INV-PKG-01-022-02191 | 228.63 | 127098.64 | 6354.93 | Paid | 120743.71 | 2024-Q2
EXP-002738 | 2024-05-14 | BOQ-PKG-08-00748 | PKG-08 | INV-PKG-08-009-02738 | 230.25 | 122877.75 | 6143.89 | Paid | 116733.86 | 2024-Q2
EXP-003803 | 2024-05-14 | BOQ-PKG-03-01813 | PKG-03 | INV-PKG-03-024-03803 | 303.97 | 23860.24 | 1193.01 | Paid | 22667.23 | 2024-Q2
EXP-000320 | 2024-05-15 | BOQ-PKG-10-00320 | PKG-10 | INV-PKG-10-006-00320 | 294.33 | 214068.78 | 10703.44 | Paid | 203365.34 | 2024-Q2
EXP-001973 | 2024-05-15 | BOQ-PKG-03-01973 | PKG-03 | INV-PKG-03-014-01973 | 232.89 | 74023.34 | 3701.17 | Paid | 70322.17 | 2024-Q2
EXP-002897 | 2024-05-15 | BOQ-PKG-07-00907 | PKG-07 | INV-PKG-07-028-02897 | 363.55 | 135175.12 | 6758.76 | Paid | 128416.36 | 2024-Q2
EXP-006247 | 2024-05-15 | BOQ-PKG-07-00277 | PKG-07 | INV-PKG-07-018-06247 | 393.06 | 38453.57 | 1922.68 | Paid | 36530.89 | 2024-Q2
EXP-006915 | 2024-05-15 | BOQ-PKG-05-00945 | PKG-05 | INV-PKG-05-021-06915 | 32.3 | 80695.52 | 4034.78 | Paid | 76660.74 | 2024-Q2
EXP-000665 | 2024-05-16 | BOQ-PKG-05-00665 | PKG-05 | INV-PKG-05-001-00665 | 196.49 | 77513.21 | 3875.66 | Paid | 73637.55 | 2024-Q2
EXP-002075 | 2024-05-16 | BOQ-PKG-05-00085 | PKG-05 | INV-PKG-05-011-02075 | 208.15 | 73800.14 | 3690.01 | Paid | 70110.13 | 2024-Q2
EXP-004834 | 2024-05-16 | BOQ-PKG-04-00854 | PKG-04 | INV-PKG-04-005-04834 | 412.32 | 128700.23 | 6435.01 | Disputed | 122265.22 | 2024-Q2
EXP-005688 | 2024-05-16 | BOQ-PKG-08-01708 | PKG-08 | INV-PKG-08-019-05688 | 262.29 | 172348.59 | 8617.43 | Paid | 163731.16 | 2024-Q2
EXP-006109 | 2024-05-16 | BOQ-PKG-09-00139 | PKG-09 | INV-PKG-09-020-06109 | 381.32 | 159561.31 | 7978.07 | Under Review | 151583.24 | 2024-Q2
EXP-006347 | 2024-05-16 | BOQ-PKG-07-00377 | PKG-07 | INV-PKG-07-013-06347 | 60.77 | 177424.71 | 8871.24 | Paid | 168553.47 | 2024-Q2
EXP-000336 | 2024-05-17 | BOQ-PKG-06-00336 | PKG-06 | INV-PKG-06-022-00336 | 305.91 | 190927.04 | 9546.35 | Paid | 181380.69 | 2024-Q2
EXP-001578 | 2024-05-17 | BOQ-PKG-08-01578 | PKG-08 | INV-PKG-08-004-01578 | 41.17 | 28110.21 | 1405.51 | Paid | 26704.7 | 2024-Q2
EXP-002310 | 2024-05-17 | BOQ-PKG-10-00320 | PKG-10 | INV-PKG-10-001-02310 | 359.92 | 156807.35 | 7840.37 | Paid | 148966.98 | 2024-Q2
EXP-003048 | 2024-05-17 | BOQ-PKG-08-01058 | PKG-08 | INV-PKG-08-004-03048 | 392.86 | 91657.63 | 4582.88 | Paid | 87074.75 | 2024-Q2
EXP-004581 | 2024-05-17 | BOQ-PKG-01-00601 | PKG-01 | INV-PKG-01-032-04581 | 109.55 | 134240.87 | 6712.04 | Paid | 127528.83 | 2024-Q2
EXP-006228 | 2024-05-17 | BOQ-PKG-08-00258 | PKG-08 | INV-PKG-08-034-06228 | 278.5 | 66831.37 | 3341.57 | Paid | 63489.8 | 2024-Q2
EXP-000504 | 2024-05-18 | BOQ-PKG-04-00504 | PKG-04 | INV-PKG-04-015-00504 | 170.47 | 28135.16 | 1406.76 | Approved Pending Payment | 26728.4 | 2024-Q2
EXP-000568 | 2024-05-18 | BOQ-PKG-08-00568 | PKG-08 | INV-PKG-08-009-00568 | 109.83 | 203624.57 | 10181.23 | Paid | 193443.34 | 2024-Q2
EXP-000869 | 2024-05-18 | BOQ-PKG-09-00869 | PKG-09 | INV-PKG-09-030-00869 | 314.82 | 62126.74 | 3106.34 | Paid | 59020.4 | 2024-Q2
EXP-001974 | 2024-05-18 | BOQ-PKG-04-01974 | PKG-04 | INV-PKG-04-015-01974 | 316.05 | 109389.43 | 5469.47 | Paid | 103919.96 | 2024-Q2
EXP-002386 | 2024-05-18 | BOQ-PKG-06-00396 | PKG-06 | INV-PKG-06-007-02386 | 420.61 | 49681.89 | 2484.09 | Paid | 47197.8 | 2024-Q2
EXP-002572 | 2024-05-18 | BOQ-PKG-02-00582 | PKG-02 | INV-PKG-02-018-02572 | 268.65 | 144037.96 | 7201.9 | Approved Pending Payment | 136836.06 | 2024-Q2
EXP-003226 | 2024-05-18 | BOQ-PKG-06-01236 | PKG-06 | INV-PKG-06-007-03226 | 397.64 | 180766.19 | 9038.31 | Paid | 171727.88 | 2024-Q2
EXP-003240 | 2024-05-18 | BOQ-PKG-10-01250 | PKG-10 | INV-PKG-10-021-03240 | 392.45 | 27851.45 | 1392.57 | Paid | 26458.88 | 2024-Q2
EXP-004386 | 2024-05-18 | BOQ-PKG-06-00406 | PKG-06 | INV-PKG-06-012-04386 | 371.33 | 169305.82 | 8465.29 | Paid | 160840.53 | 2024-Q2
EXP-005619 | 2024-05-18 | BOQ-PKG-09-01639 | PKG-09 | INV-PKG-09-020-05619 | 110 | 128320 | 6416 | Paid | 121904 | 2024-Q2
EXP-006123 | 2024-05-18 | BOQ-PKG-03-00153 | PKG-03 | INV-PKG-03-034-06123 | 276.83 | 154841.97 | 7742.1 | Paid | 147099.87 | 2024-Q2
EXP-006391 | 2024-05-18 | BOQ-PKG-01-00421 | PKG-01 | INV-PKG-01-022-06391 | 24.29 | 144752.09 | 7237.6 | Paid | 137514.49 | 2024-Q2
EXP-001545 | 2024-05-19 | BOQ-PKG-05-01545 | PKG-05 | INV-PKG-05-006-01545 | 225.5 | 43314.33 | 2165.72 | Paid | 41148.61 | 2024-Q2
EXP-002170 | 2024-05-19 | BOQ-PKG-10-00180 | PKG-10 | INV-PKG-10-001-02170 | 230.92 | 154787.25 | 7739.36 | Approved Pending Payment | 147047.89 | 2024-Q2
EXP-004606 | 2024-05-19 | BOQ-PKG-06-00626 | PKG-06 | INV-PKG-06-022-04606 | 406.5 | 169388.02 | 8469.4 | Paid | 160918.62 | 2024-Q2
EXP-004836 | 2024-05-19 | BOQ-PKG-06-00856 | PKG-06 | INV-PKG-06-007-04836 | 51.37 | 156091.99 | 7804.6 | Paid | 148287.39 | 2024-Q2
EXP-006580 | 2024-05-19 | BOQ-PKG-10-00610 | PKG-10 | INV-PKG-10-001-06580 | 227.27 | 68206.28 | 3410.31 | Under Review | 64795.97 | 2024-Q2
EXP-006693 | 2024-05-19 | BOQ-PKG-03-00723 | PKG-03 | INV-PKG-03-009-06693 | 92.7 | 51174.92 | 2558.75 | Paid | 48616.17 | 2024-Q2
EXP-006765 | 2024-05-19 | BOQ-PKG-05-00795 | PKG-05 | INV-PKG-05-011-06765 | 133.05 | 203591.54 | 10179.58 | Paid | 193411.96 | 2024-Q2
EXP-000307 | 2024-05-20 | BOQ-PKG-07-00307 | PKG-07 | INV-PKG-07-028-00307 | 417.85 | 188972.35 | 9448.62 | Paid | 179523.73 | 2024-Q2
EXP-001476 | 2024-05-20 | BOQ-PKG-06-01476 | PKG-06 | INV-PKG-06-007-01476 | 54.19 | 199961.52 | 9998.08 | Paid | 189963.44 | 2024-Q2
EXP-003362 | 2024-05-20 | BOQ-PKG-02-01372 | PKG-02 | INV-PKG-02-003-03362 | 228.42 | 165986.7 | 8299.34 | Under Review | 157687.36 | 2024-Q2
EXP-003419 | 2024-05-20 | BOQ-PKG-09-01429 | PKG-09 | INV-PKG-09-025-03419 | 117.6 | 30738.6 | 1536.93 | Paid | 29201.67 | 2024-Q2
EXP-004426 | 2024-05-20 | BOQ-PKG-06-00446 | PKG-06 | INV-PKG-06-017-04426 | 7.38 | 76953.95 | 3847.7 | Paid | 73106.25 | 2024-Q2
EXP-005288 | 2024-05-20 | BOQ-PKG-08-01308 | PKG-08 | INV-PKG-08-004-05288 | 290.76 | 178108.57 | 8905.43 | Paid | 169203.14 | 2024-Q2
EXP-006628 | 2024-05-20 | BOQ-PKG-08-00658 | PKG-08 | INV-PKG-08-014-06628 | 386.39 | 44484.09 | 2224.2 | Paid | 42259.89 | 2024-Q2
EXP-006861 | 2024-05-20 | BOQ-PKG-01-00891 | PKG-01 | INV-PKG-01-002-06861 | 421.62 | 37855.02 | 1892.75 | Approved Pending Payment | 35962.27 | 2024-Q2
EXP-000264 | 2024-05-21 | BOQ-PKG-04-00264 | PKG-04 | INV-PKG-04-020-00264 | 213.14 | 136296.78 | 6814.84 | Paid | 129481.94 | 2024-Q2
EXP-002148 | 2024-05-21 | BOQ-PKG-08-00158 | PKG-08 | INV-PKG-08-014-02148 | 420.02 | 186318.96 | 9315.95 | Paid | 177003.01 | 2024-Q2
EXP-004590 | 2024-05-21 | BOQ-PKG-10-00610 | PKG-10 | INV-PKG-10-006-04590 | 176.49 | 56880.95 | 2844.05 | Paid | 54036.9 | 2024-Q2
EXP-005464 | 2024-05-21 | BOQ-PKG-04-01484 | PKG-04 | INV-PKG-04-005-05464 | 38.94 | 42442.92 | 2122.15 | Paid | 40320.77 | 2024-Q2
EXP-006058 | 2024-05-21 | BOQ-PKG-08-00088 | PKG-08 | INV-PKG-08-004-06058 | 231.91 | 69772.78 | 3488.64 | Paid | 66284.14 | 2024-Q2
EXP-006265 | 2024-05-21 | BOQ-PKG-05-00295 | PKG-05 | INV-PKG-05-001-06265 | 349.87 | 122029.46 | 6101.47 | Paid | 115927.99 | 2024-Q2
EXP-006276 | 2024-05-21 | BOQ-PKG-06-00306 | PKG-06 | INV-PKG-06-012-06276 | 207.7 | 205048.25 | 10252.41 | Paid | 194795.84 | 2024-Q2
EXP-006555 | 2024-05-21 | BOQ-PKG-05-00585 | PKG-05 | INV-PKG-05-011-06555 | 163.48 | 84487.85 | 4224.39 | Paid | 80263.46 | 2024-Q2
EXP-003426 | 2024-05-22 | BOQ-PKG-06-01436 | PKG-06 | INV-PKG-06-032-03426 | 300.32 | 118119.91 | 5906 | Paid | 112213.91 | 2024-Q2
EXP-003469 | 2024-05-22 | BOQ-PKG-09-01479 | PKG-09 | INV-PKG-09-005-03469 | 145.12 | 94211.94 | 4710.6 | Paid | 89501.34 | 2024-Q2
EXP-005493 | 2024-05-22 | BOQ-PKG-03-01513 | PKG-03 | INV-PKG-03-034-05493 | 262.96 | 158718.29 | 7935.91 | Paid | 150782.38 | 2024-Q2
EXP-006561 | 2024-05-22 | BOQ-PKG-01-00591 | PKG-01 | INV-PKG-01-017-06561 | 232.28 | 134704.84 | 6735.24 | Paid | 127969.6 | 2024-Q2
EXP-002650 | 2024-05-23 | BOQ-PKG-10-00660 | PKG-10 | INV-PKG-10-026-02650 | 257.9 | 173303.43 | 8665.17 | Paid | 164638.26 | 2024-Q2
EXP-003986 | 2024-05-23 | BOQ-PKG-06-00006 | PKG-06 | INV-PKG-06-032-03986 | 239.01 | 121548.11 | 6077.41 | Approved Pending Payment | 115470.7 | 2024-Q2
EXP-004410 | 2024-05-23 | BOQ-PKG-10-00430 | PKG-10 | INV-PKG-10-001-04410 | 120.46 | 107632.14 | 5381.61 | Under Review | 102250.53 | 2024-Q2
EXP-005457 | 2024-05-23 | BOQ-PKG-07-01477 | PKG-07 | INV-PKG-07-033-05457 | 301.28 | 155376.46 | 7768.82 | Paid | 147607.64 | 2024-Q2
EXP-005811 | 2024-05-23 | BOQ-PKG-01-01831 | PKG-01 | INV-PKG-01-002-05811 | 325.72 | 155078.01 | 7753.9 | Under Review | 147324.11 | 2024-Q2
EXP-002185 | 2024-05-24 | BOQ-PKG-05-00195 | PKG-05 | INV-PKG-05-016-02185 | 76.43 | 37413.01 | 1870.65 | Paid | 35542.36 | 2024-Q2
EXP-003014 | 2024-05-24 | BOQ-PKG-04-01024 | PKG-04 | INV-PKG-04-005-03014 | 94.84 | 99431.62 | 4971.58 | Paid | 94460.04 | 2024-Q2
EXP-004290 | 2024-05-24 | BOQ-PKG-10-00310 | PKG-10 | INV-PKG-10-021-04290 | 22.77 | 33873.56 | 1693.68 | Paid | 32179.88 | 2024-Q2
EXP-005494 | 2024-05-24 | BOQ-PKG-04-01514 | PKG-04 | INV-PKG-04-035-05494 | 227.27 | 189726.28 | 9486.31 | Paid | 180239.97 | 2024-Q2
EXP-006542 | 2024-05-24 | BOQ-PKG-02-00572 | PKG-02 | INV-PKG-02-033-06542 | 263.31 | 156708.32 | 7835.42 | Approved Pending Payment | 148872.9 | 2024-Q2
EXP-001022 | 2024-05-25 | BOQ-PKG-02-01022 | PKG-02 | INV-PKG-02-008-01022 | 182.57 | 202457.34 | 10122.87 | Paid | 192334.47 | 2024-Q2
EXP-001151 | 2024-05-25 | BOQ-PKG-01-01151 | PKG-01 | INV-PKG-01-032-01151 | 337.93 | 114101.71 | 5705.09 | Approved Pending Payment | 108396.62 | 2024-Q2
EXP-002071 | 2024-05-25 | BOQ-PKG-01-00081 | PKG-01 | INV-PKG-01-007-02071 | 63.87 | 44324.55 | 2216.23 | Paid | 42108.32 | 2024-Q2
EXP-004748 | 2024-05-25 | BOQ-PKG-08-00768 | PKG-08 | INV-PKG-08-024-04748 | 384.46 | 28165.16 | 1408.26 | Paid | 26756.9 | 2024-Q2
EXP-005257 | 2024-05-25 | BOQ-PKG-07-01277 | PKG-07 | INV-PKG-07-008-05257 | 203.57 | 145620.51 | 7281.03 | Paid | 138339.48 | 2024-Q2
EXP-000283 | 2024-05-26 | BOQ-PKG-03-00283 | PKG-03 | INV-PKG-03-004-00283 | 258.3 | 187210.93 | 9360.55 | Paid | 177850.38 | 2024-Q2
EXP-000750 | 2024-05-26 | BOQ-PKG-10-00750 | PKG-10 | INV-PKG-10-016-00750 | 47.78 | 106716.54 | 5335.83 | Paid | 101380.71 | 2024-Q2
EXP-001066 | 2024-05-26 | BOQ-PKG-06-01066 | PKG-06 | INV-PKG-06-017-01066 | 117.32 | 156352.53 | 7817.63 | Paid | 148534.9 | 2024-Q2
EXP-001338 | 2024-05-26 | BOQ-PKG-08-01338 | PKG-08 | INV-PKG-08-009-01338 | 6.51 | 70853.75 | 3542.69 | Paid | 67311.06 | 2024-Q2
EXP-001975 | 2024-05-26 | BOQ-PKG-05-01975 | PKG-05 | INV-PKG-05-016-01975 | 264.62 | 201277.78 | 10063.89 | Paid | 191213.89 | 2024-Q2
EXP-003317 | 2024-05-26 | BOQ-PKG-07-01327 | PKG-07 | INV-PKG-07-028-03317 | 25.26 | 127888.88 | 6394.44 | Paid | 121494.44 | 2024-Q2
EXP-004172 | 2024-05-26 | BOQ-PKG-02-00192 | PKG-02 | INV-PKG-02-008-04172 | 297.69 | 167962.38 | 8398.12 | Under Review | 159564.26 | 2024-Q2
EXP-004350 | 2024-05-26 | BOQ-PKG-10-00370 | PKG-10 | INV-PKG-10-011-04350 | 126.13 | 53646.75 | 2682.34 | Approved Pending Payment | 50964.41 | 2024-Q2
EXP-006011 | 2024-05-26 | BOQ-PKG-01-00041 | PKG-01 | INV-PKG-01-027-06011 | 182.55 | 73855.56 | 3692.78 | Paid | 70162.78 | 2024-Q2
EXP-006345 | 2024-05-26 | BOQ-PKG-05-00375 | PKG-05 | INV-PKG-05-011-06345 | 104.02 | 122047.21 | 6102.36 | Paid | 115944.85 | 2024-Q2
EXP-000794 | 2024-05-27 | BOQ-PKG-04-00794 | PKG-04 | INV-PKG-04-025-00794 | 283.1 | 165440.65 | 8272.03 | Paid | 157168.62 | 2024-Q2
EXP-000984 | 2024-05-27 | BOQ-PKG-04-00984 | PKG-04 | INV-PKG-04-005-00984 | 148.33 | 127574.44 | 6378.72 | Under Review | 121195.72 | 2024-Q2
EXP-002707 | 2024-05-27 | BOQ-PKG-07-00717 | PKG-07 | INV-PKG-07-013-02707 | 183.36 | 38123.56 | 1906.18 | Paid | 36217.38 | 2024-Q2
EXP-002747 | 2024-05-27 | BOQ-PKG-07-00757 | PKG-07 | INV-PKG-07-018-02747 | 331.85 | 185965.93 | 9298.3 | Paid | 176667.63 | 2024-Q2
EXP-004825 | 2024-05-27 | BOQ-PKG-05-00845 | PKG-05 | INV-PKG-05-031-04825 | 243.01 | 97964.65 | 4898.23 | Paid | 93066.42 | 2024-Q2
EXP-006757 | 2024-05-27 | BOQ-PKG-07-00787 | PKG-07 | INV-PKG-07-003-06757 | 85.63 | 177484.4 | 8874.22 | Paid | 168610.18 | 2024-Q2
EXP-006974 | 2024-05-27 | BOQ-PKG-04-01004 | PKG-04 | INV-PKG-04-010-06974 | 161.91 | 33179.28 | 1658.96 | Paid | 31520.32 | 2024-Q2
EXP-006994 | 2024-05-27 | BOQ-PKG-04-01024 | PKG-04 | INV-PKG-04-030-06994 | 30.24 | 121894.28 | 6094.71 | Paid | 115799.57 | 2024-Q2
EXP-000896 | 2024-05-28 | BOQ-PKG-06-00896 | PKG-06 | INV-PKG-06-022-00896 | 291.06 | 98666.45 | 4933.32 | Paid | 93733.13 | 2024-Q2
EXP-001447 | 2024-05-28 | BOQ-PKG-07-01447 | PKG-07 | INV-PKG-07-013-01447 | 321.12 | 142114.43 | 7105.72 | Approved Pending Payment | 135008.71 | 2024-Q2
EXP-001601 | 2024-05-28 | BOQ-PKG-01-01601 | PKG-01 | INV-PKG-01-027-01601 | 6.67 | 119503.95 | 5975.2 | Paid | 113528.75 | 2024-Q2
EXP-003933 | 2024-05-28 | BOQ-PKG-03-01943 | PKG-03 | INV-PKG-03-014-03933 | 206.56 | 27910.77 | 1395.54 | Disputed | 26515.23 | 2024-Q2
EXP-003956 | 2024-05-28 | BOQ-PKG-06-01966 | PKG-06 | INV-PKG-06-002-03956 | 142.49 | 31591.19 | 1579.56 | Paid | 30011.63 | 2024-Q2
EXP-005450 | 2024-05-28 | BOQ-PKG-10-01470 | PKG-10 | INV-PKG-10-026-05450 | 162.49 | 86777.08 | 4338.85 | Paid | 82438.23 | 2024-Q2
EXP-006143 | 2024-05-28 | BOQ-PKG-03-00173 | PKG-03 | INV-PKG-03-019-06143 | 149.11 | 83835.3 | 4191.77 | Approved Pending Payment | 79643.53 | 2024-Q2
EXP-000463 | 2024-05-29 | BOQ-PKG-03-00463 | PKG-03 | INV-PKG-03-009-00463 | 178.3 | 198784.97 | 9939.25 | Under Review | 188845.72 | 2024-Q2
EXP-000961 | 2024-05-29 | BOQ-PKG-01-00961 | PKG-01 | INV-PKG-01-017-00961 | 386.76 | 82621.11 | 4131.06 | Paid | 78490.05 | 2024-Q2
EXP-002894 | 2024-05-29 | BOQ-PKG-04-00904 | PKG-04 | INV-PKG-04-025-02894 | 151.41 | 103902.9 | 5195.15 | Paid | 98707.75 | 2024-Q2
EXP-004144 | 2024-05-29 | BOQ-PKG-04-00164 | PKG-04 | INV-PKG-04-015-04144 | 302.13 | 148442.31 | 7422.12 | Paid | 141020.19 | 2024-Q2
EXP-004731 | 2024-05-29 | BOQ-PKG-01-00751 | PKG-01 | INV-PKG-01-007-04731 | 61.79 | 201039.48 | 10051.97 | Paid | 190987.51 | 2024-Q2
EXP-005502 | 2024-05-29 | BOQ-PKG-02-01522 | PKG-02 | INV-PKG-02-008-05502 | 236.27 | 73891.17 | 3694.56 | Paid | 70196.61 | 2024-Q2
EXP-005539 | 2024-05-29 | BOQ-PKG-09-01559 | PKG-09 | INV-PKG-09-010-05539 | 388.69 | 112405.98 | 5620.3 | Disputed | 106785.68 | 2024-Q2
EXP-003614 | 2024-05-30 | BOQ-PKG-04-01624 | PKG-04 | INV-PKG-04-010-03614 | 77.35 | 56003.98 | 2800.2 | Paid | 53203.78 | 2024-Q2
EXP-004232 | 2024-05-30 | BOQ-PKG-02-00252 | PKG-02 | INV-PKG-02-033-04232 | 211.69 | 199352.71 | 9967.64 | Under Review | 189385.07 | 2024-Q2
EXP-004672 | 2024-05-30 | BOQ-PKG-02-00692 | PKG-02 | INV-PKG-02-018-04672 | 327.36 | 31737.76 | 1586.89 | Approved Pending Payment | 30150.87 | 2024-Q2
EXP-005963 | 2024-05-30 | BOQ-PKG-03-01983 | PKG-03 | INV-PKG-03-014-05963 | 224.47 | 37355.5 | 1867.78 | Paid | 35487.72 | 2024-Q2
EXP-006301 | 2024-05-30 | BOQ-PKG-01-00331 | PKG-01 | INV-PKG-01-002-06301 | 126.2 | 137514.31 | 6875.72 | Paid | 130638.59 | 2024-Q2
EXP-006891 | 2024-05-30 | BOQ-PKG-01-00921 | PKG-01 | INV-PKG-01-032-06891 | 270.01 | 143793.48 | 7189.67 | Paid | 136603.81 | 2024-Q2
EXP-001919 | 2024-05-31 | BOQ-PKG-09-01919 | PKG-09 | INV-PKG-09-030-01919 | 18.25 | 198653.52 | 9932.68 | Paid | 188720.84 | 2024-Q2
EXP-003359 | 2024-05-31 | BOQ-PKG-09-01369 | PKG-09 | INV-PKG-09-035-03359 | 50.93 | 134821.91 | 6741.1 | Approved Pending Payment | 128080.81 | 2024-Q2
EXP-003818 | 2024-05-31 | BOQ-PKG-08-01828 | PKG-08 | INV-PKG-08-004-03818 | 248.09 | 36537.83 | 1826.89 | Paid | 34710.94 | 2024-Q2
EXP-005855 | 2024-05-31 | BOQ-PKG-05-01875 | PKG-05 | INV-PKG-05-011-05855 | 119.24 | 72290.82 | 3614.54 | Paid | 68676.28 | 2024-Q2
EXP-006604 | 2024-05-31 | BOQ-PKG-04-00634 | PKG-04 | INV-PKG-04-025-06604 | 51.36 | 83138.56 | 4156.93 | Paid | 78981.63 | 2024-Q2
EXP-001013 | 2024-06-01 | BOQ-PKG-03-01013 | PKG-03 | INV-PKG-03-034-01013 | 145.75 | 202254.9 | 10112.75 | Paid | 192142.15 | 2024-Q2
EXP-002531 | 2024-06-01 | BOQ-PKG-01-00541 | PKG-01 | INV-PKG-01-012-02531 | 274.73 | 111625.47 | 5581.27 | Paid | 106044.2 | 2024-Q2
EXP-002697 | 2024-06-01 | BOQ-PKG-07-00707 | PKG-07 | INV-PKG-07-003-02697 | 107.35 | 134621.36 | 6731.07 | Paid | 127890.29 | 2024-Q2
EXP-003847 | 2024-06-01 | BOQ-PKG-07-01857 | PKG-07 | INV-PKG-07-033-03847 | 119.72 | 131480.44 | 6574.02 | Paid | 124906.42 | 2024-Q2
EXP-006116 | 2024-06-01 | BOQ-PKG-06-00146 | PKG-06 | INV-PKG-06-027-06116 | 151.47 | 94858.72 | 4742.94 | Under Review | 90115.78 | 2024-Q2
EXP-006139 | 2024-06-01 | BOQ-PKG-09-00169 | PKG-09 | INV-PKG-09-015-06139 | 31.59 | 118918.6 | 5945.93 | Approved Pending Payment | 112972.67 | 2024-Q2
EXP-006633 | 2024-06-01 | BOQ-PKG-03-00663 | PKG-03 | INV-PKG-03-019-06633 | 278.25 | 115065.05 | 5753.25 | Paid | 109311.8 | 2024-Q2
EXP-006824 | 2024-06-01 | BOQ-PKG-04-00854 | PKG-04 | INV-PKG-04-035-06824 | 251.31 | 211083.15 | 10554.16 | Approved Pending Payment | 200528.99 | 2024-Q2
EXP-000395 | 2024-06-02 | BOQ-PKG-05-00395 | PKG-05 | INV-PKG-05-011-00395 | 76.05 | 173017.7 | 8650.88 | Paid | 164366.82 | 2024-Q2
EXP-001485 | 2024-06-02 | BOQ-PKG-05-01485 | PKG-05 | INV-PKG-05-016-01485 | 206.39 | 187304.64 | 9365.23 | Approved Pending Payment | 177939.41 | 2024-Q2
EXP-001769 | 2024-06-02 | BOQ-PKG-09-01769 | PKG-09 | INV-PKG-09-020-01769 | 250.21 | 51390.19 | 2569.51 | Under Review | 48820.68 | 2024-Q2
EXP-002564 | 2024-06-02 | BOQ-PKG-04-00574 | PKG-04 | INV-PKG-04-010-02564 | 68.82 | 53290.6 | 2664.53 | Under Review | 50626.07 | 2024-Q2
EXP-003887 | 2024-06-02 | BOQ-PKG-07-01897 | PKG-07 | INV-PKG-07-003-03887 | 157.16 | 199941.51 | 9997.08 | Paid | 189944.43 | 2024-Q2
EXP-004330 | 2024-06-02 | BOQ-PKG-10-00350 | PKG-10 | INV-PKG-10-026-04330 | 357.39 | 113278.79 | 5663.94 | Paid | 107614.85 | 2024-Q2
EXP-005044 | 2024-06-02 | BOQ-PKG-04-01064 | PKG-04 | INV-PKG-04-005-05044 | 393.69 | 62519.73 | 3125.99 | Paid | 59393.74 | 2024-Q2
EXP-005091 | 2024-06-02 | BOQ-PKG-01-01111 | PKG-01 | INV-PKG-01-017-05091 | 439.53 | 66235.02 | 3311.75 | Paid | 62923.27 | 2024-Q2
EXP-005228 | 2024-06-02 | BOQ-PKG-08-01248 | PKG-08 | INV-PKG-08-014-05228 | 92.08 | 94286.84 | 4714.34 | Paid | 89572.5 | 2024-Q2
EXP-006666 | 2024-06-02 | BOQ-PKG-06-00696 | PKG-06 | INV-PKG-06-017-06666 | 181.14 | 95557.23 | 4777.86 | Paid | 90779.37 | 2024-Q2
EXP-001926 | 2024-06-03 | BOQ-PKG-06-01926 | PKG-06 | INV-PKG-06-002-01926 | 173.28 | 148373.66 | 7418.68 | Paid | 140954.98 | 2024-Q2
EXP-002069 | 2024-06-03 | BOQ-PKG-09-00079 | PKG-09 | INV-PKG-09-005-02069 | 14.85 | 142167.13 | 7108.36 | Disputed | 135058.77 | 2024-Q2
EXP-002815 | 2024-06-03 | BOQ-PKG-05-00825 | PKG-05 | INV-PKG-05-016-02815 | 365.3 | 180545.1 | 9027.26 | Paid | 171517.84 | 2024-Q2
EXP-003688 | 2024-06-03 | BOQ-PKG-08-01698 | PKG-08 | INV-PKG-08-014-03688 | 447.14 | 144993.81 | 7249.69 | Paid | 137744.12 | 2024-Q2
EXP-004299 | 2024-06-03 | BOQ-PKG-09-00319 | PKG-09 | INV-PKG-09-030-04299 | 238.85 | 181438.05 | 9071.9 | Paid | 172366.15 | 2024-Q2
EXP-004838 | 2024-06-03 | BOQ-PKG-08-00858 | PKG-08 | INV-PKG-08-009-04838 | 279.44 | 207657.4 | 10382.87 | Paid | 197274.53 | 2024-Q2
EXP-000842 | 2024-06-04 | BOQ-PKG-02-00842 | PKG-02 | INV-PKG-02-003-00842 | 112.24 | 199037.66 | 9951.88 | Paid | 189085.78 | 2024-Q2
EXP-002118 | 2024-06-04 | BOQ-PKG-08-00128 | PKG-08 | INV-PKG-08-019-02118 | 443.34 | 194015.58 | 9700.78 | Paid | 184314.8 | 2024-Q2
EXP-003015 | 2024-06-04 | BOQ-PKG-05-01025 | PKG-05 | INV-PKG-05-006-03015 | 6.95 | 212217.19 | 10610.86 | Paid | 201606.33 | 2024-Q2
EXP-003476 | 2024-06-04 | BOQ-PKG-06-01486 | PKG-06 | INV-PKG-06-012-03476 | 332.84 | 96427.47 | 4821.37 | Under Review | 91606.1 | 2024-Q2
EXP-004712 | 2024-06-04 | BOQ-PKG-02-00732 | PKG-02 | INV-PKG-02-023-04712 | 421.58 | 88535.66 | 4426.78 | Paid | 84108.88 | 2024-Q2
EXP-004999 | 2024-06-04 | BOQ-PKG-09-01019 | PKG-09 | INV-PKG-09-030-04999 | 344.98 | 145632.56 | 7281.63 | Paid | 138350.93 | 2024-Q2
EXP-005306 | 2024-06-04 | BOQ-PKG-06-01326 | PKG-06 | INV-PKG-06-022-05306 | 38.97 | 82273.76 | 4113.69 | Paid | 78160.07 | 2024-Q2
EXP-005387 | 2024-06-04 | BOQ-PKG-07-01407 | PKG-07 | INV-PKG-07-033-05387 | 299.75 | 140868.01 | 7043.4 | Paid | 133824.61 | 2024-Q2
EXP-006029 | 2024-06-04 | BOQ-PKG-09-00059 | PKG-09 | INV-PKG-09-010-06029 | 310.5 | 80379.85 | 4018.99 | Paid | 76360.86 | 2024-Q2
EXP-006101 | 2024-06-04 | BOQ-PKG-01-00131 | PKG-01 | INV-PKG-01-012-06101 | 103.88 | 190643.26 | 9532.16 | Paid | 181111.1 | 2024-Q2
EXP-006688 | 2024-06-04 | BOQ-PKG-08-00718 | PKG-08 | INV-PKG-08-004-06688 | 410.22 | 172253.74 | 8612.69 | Paid | 163641.05 | 2024-Q2
EXP-000783 | 2024-06-05 | BOQ-PKG-03-00783 | PKG-03 | INV-PKG-03-014-00783 | 229.09 | 172819.12 | 8640.96 | Paid | 164178.16 | 2024-Q2
EXP-001459 | 2024-06-05 | BOQ-PKG-09-01459 | PKG-09 | INV-PKG-09-025-01459 | 45.04 | 125221.69 | 6261.08 | Paid | 118960.61 | 2024-Q2
EXP-001696 | 2024-06-05 | BOQ-PKG-06-01696 | PKG-06 | INV-PKG-06-017-01696 | 105.72 | 110771.45 | 5538.57 | Paid | 105232.88 | 2024-Q2
EXP-002283 | 2024-06-05 | BOQ-PKG-03-00293 | PKG-03 | INV-PKG-03-009-02283 | 372.56 | 80220.65 | 4011.03 | Under Review | 76209.62 | 2024-Q2
EXP-002919 | 2024-06-05 | BOQ-PKG-09-00929 | PKG-09 | INV-PKG-09-015-02919 | 151.71 | 50373.47 | 2518.67 | Paid | 47854.8 | 2024-Q2
EXP-001757 | 2024-06-06 | BOQ-PKG-07-01757 | PKG-07 | INV-PKG-07-008-01757 | 281.15 | 103240.43 | 5162.02 | Approved Pending Payment | 98078.41 | 2024-Q2
EXP-001993 | 2024-06-06 | BOQ-PKG-03-00003 | PKG-03 | INV-PKG-03-034-01993 | 129.08 | 40456.26 | 2022.81 | Paid | 38433.45 | 2024-Q2
EXP-002112 | 2024-06-06 | BOQ-PKG-02-00122 | PKG-02 | INV-PKG-02-013-02112 | 277.13 | 70624.16 | 3531.21 | Paid | 67092.95 | 2024-Q2
EXP-003064 | 2024-06-06 | BOQ-PKG-04-01074 | PKG-04 | INV-PKG-04-020-03064 | 226.49 | 130566.93 | 6528.35 | Approved Pending Payment | 124038.58 | 2024-Q2
EXP-003340 | 2024-06-06 | BOQ-PKG-10-01350 | PKG-10 | INV-PKG-10-016-03340 | 168.37 | 46906.33 | 2345.32 | Paid | 44561.01 | 2024-Q2
EXP-003404 | 2024-06-06 | BOQ-PKG-04-01414 | PKG-04 | INV-PKG-04-010-03404 | 371.49 | 82205.25 | 4110.26 | Paid | 78094.99 | 2024-Q2
EXP-003428 | 2024-06-06 | BOQ-PKG-08-01438 | PKG-08 | INV-PKG-08-034-03428 | 193.19 | 170775.41 | 8538.77 | Paid | 162236.64 | 2024-Q2
EXP-003589 | 2024-06-06 | BOQ-PKG-09-01599 | PKG-09 | INV-PKG-09-020-03589 | 363.83 | 106299.22 | 5314.96 | Paid | 100984.26 | 2024-Q2
EXP-001210 | 2024-06-07 | BOQ-PKG-10-01210 | PKG-10 | INV-PKG-10-021-01210 | 410.94 | 192931.74 | 9646.59 | Paid | 183285.15 | 2024-Q2
EXP-001520 | 2024-06-07 | BOQ-PKG-10-01520 | PKG-10 | INV-PKG-10-016-01520 | 292.99 | 197982.5 | 9899.12 | Approved Pending Payment | 188083.38 | 2024-Q2
EXP-002451 | 2024-06-07 | BOQ-PKG-01-00461 | PKG-01 | INV-PKG-01-002-02451 | 21.97 | 155551 | 7777.55 | Paid | 147773.45 | 2024-Q2
EXP-003484 | 2024-06-07 | BOQ-PKG-04-01494 | PKG-04 | INV-PKG-04-020-03484 | 285.53 | 27345.62 | 1367.28 | Approved Pending Payment | 25978.34 | 2024-Q2
EXP-003685 | 2024-06-07 | BOQ-PKG-05-01695 | PKG-05 | INV-PKG-05-011-03685 | 25.81 | 121825.11 | 6091.26 | Paid | 115733.85 | 2024-Q2
EXP-004378 | 2024-06-07 | BOQ-PKG-08-00398 | PKG-08 | INV-PKG-08-004-04378 | 85.02 | 174927.35 | 8746.37 | Under Review | 166180.98 | 2024-Q2
EXP-004991 | 2024-06-07 | BOQ-PKG-01-01011 | PKG-01 | INV-PKG-01-022-04991 | 191.72 | 133233.01 | 6661.65 | Paid | 126571.36 | 2024-Q2
EXP-005518 | 2024-06-07 | BOQ-PKG-08-01538 | PKG-08 | INV-PKG-08-024-05518 | 115.92 | 150905.74 | 7545.29 | Paid | 143360.45 | 2024-Q2
EXP-005758 | 2024-06-07 | BOQ-PKG-08-01778 | PKG-08 | INV-PKG-08-019-05758 | 440.76 | 198105.38 | 9905.27 | Approved Pending Payment | 188200.11 | 2024-Q2
EXP-005825 | 2024-06-07 | BOQ-PKG-05-01845 | PKG-05 | INV-PKG-05-016-05825 | 147.56 | 143973.02 | 7198.65 | Paid | 136774.37 | 2024-Q2
EXP-000202 | 2024-06-08 | BOQ-PKG-02-00202 | PKG-02 | INV-PKG-02-028-00202 | 329.01 | 138475.61 | 6923.78 | Approved Pending Payment | 131551.83 | 2024-Q2
EXP-001286 | 2024-06-08 | BOQ-PKG-06-01286 | PKG-06 | INV-PKG-06-027-01286 | 124.83 | 135366.21 | 6768.31 | Paid | 128597.9 | 2024-Q2
EXP-001291 | 2024-06-08 | BOQ-PKG-01-01291 | PKG-01 | INV-PKG-01-032-01291 | 41.9 | 143448.97 | 7172.45 | Under Review | 136276.52 | 2024-Q2
EXP-001384 | 2024-06-08 | BOQ-PKG-04-01384 | PKG-04 | INV-PKG-04-020-01384 | 34.45 | 62382.81 | 3119.14 | Paid | 59263.67 | 2024-Q2
EXP-001678 | 2024-06-08 | BOQ-PKG-08-01678 | PKG-08 | INV-PKG-08-034-01678 | 374.61 | 88759.19 | 4437.96 | Approved Pending Payment | 84321.23 | 2024-Q2
EXP-003029 | 2024-06-08 | BOQ-PKG-09-01039 | PKG-09 | INV-PKG-09-020-03029 | 19.57 | 72651.42 | 3632.57 | Approved Pending Payment | 69018.85 | 2024-Q2
EXP-005323 | 2024-06-08 | BOQ-PKG-03-01343 | PKG-03 | INV-PKG-03-004-05323 | 109.01 | 75387.88 | 3769.39 | Approved Pending Payment | 71618.49 | 2024-Q2
EXP-005469 | 2024-06-08 | BOQ-PKG-09-01489 | PKG-09 | INV-PKG-09-010-05469 | 70.62 | 99731.81 | 4986.59 | Approved Pending Payment | 94745.22 | 2024-Q2
EXP-005600 | 2024-06-08 | BOQ-PKG-10-01620 | PKG-10 | INV-PKG-10-001-05600 | 215.12 | 41888.53 | 2094.43 | Approved Pending Payment | 39794.1 | 2024-Q2
EXP-006010 | 2024-06-08 | BOQ-PKG-10-00040 | PKG-10 | INV-PKG-10-026-06010 | 86.09 | 191083.82 | 9554.19 | Under Review | 181529.63 | 2024-Q2
EXP-000800 | 2024-06-09 | BOQ-PKG-10-00800 | PKG-10 | INV-PKG-10-031-00800 | 415.17 | 168367.71 | 8418.39 | Paid | 159949.32 | 2024-Q2
EXP-001921 | 2024-06-09 | BOQ-PKG-01-01921 | PKG-01 | INV-PKG-01-032-01921 | 64.29 | 63373.14 | 3168.66 | Paid | 60204.48 | 2024-Q2
EXP-003441 | 2024-06-09 | BOQ-PKG-01-01451 | PKG-01 | INV-PKG-01-012-03441 | 378.76 | 35267.2 | 1763.36 | Paid | 33503.84 | 2024-Q2
EXP-004942 | 2024-06-09 | BOQ-PKG-02-00962 | PKG-02 | INV-PKG-02-008-04942 | 227.32 | 170767.53 | 8538.38 | Paid | 162229.15 | 2024-Q2
EXP-005558 | 2024-06-09 | BOQ-PKG-08-01578 | PKG-08 | INV-PKG-08-029-05558 | 276.57 | 29325.51 | 1466.28 | Approved Pending Payment | 27859.23 | 2024-Q2
EXP-005891 | 2024-06-09 | BOQ-PKG-01-01911 | PKG-01 | INV-PKG-01-012-05891 | 389.85 | 204155.23 | 10207.76 | Paid | 193947.47 | 2024-Q2
EXP-000437 | 2024-06-10 | BOQ-PKG-07-00437 | PKG-07 | INV-PKG-07-018-00437 | 139.02 | 69720.21 | 3486.01 | Paid | 66234.2 | 2024-Q2
EXP-001899 | 2024-06-10 | BOQ-PKG-09-01899 | PKG-09 | INV-PKG-09-010-01899 | 270.19 | 69796.89 | 3489.84 | Paid | 66307.05 | 2024-Q2
EXP-002065 | 2024-06-10 | BOQ-PKG-05-00075 | PKG-05 | INV-PKG-05-001-02065 | 294.16 | 38652.39 | 1932.62 | Paid | 36719.77 | 2024-Q2
EXP-002859 | 2024-06-10 | BOQ-PKG-09-00869 | PKG-09 | INV-PKG-09-025-02859 | 189.4 | 144526.69 | 7226.33 | Paid | 137300.36 | 2024-Q2
EXP-003183 | 2024-06-10 | BOQ-PKG-03-01193 | PKG-03 | INV-PKG-03-034-03183 | 11.77 | 148004.61 | 7400.23 | Paid | 140604.38 | 2024-Q2
EXP-004594 | 2024-06-10 | BOQ-PKG-04-00614 | PKG-04 | INV-PKG-04-010-04594 | 282.28 | 36963.33 | 1848.17 | Paid | 35115.16 | 2024-Q2
EXP-006296 | 2024-06-10 | BOQ-PKG-06-00326 | PKG-06 | INV-PKG-06-032-06296 | 282.44 | 131701.97 | 6585.1 | Paid | 125116.87 | 2024-Q2
EXP-006951 | 2024-06-10 | BOQ-PKG-01-00981 | PKG-01 | INV-PKG-01-022-06951 | 248.99 | 207997.48 | 10399.87 | Paid | 197597.61 | 2024-Q2
EXP-000303 | 2024-06-11 | BOQ-PKG-03-00303 | PKG-03 | INV-PKG-03-024-00303 | 339.55 | 127745.12 | 6387.26 | Paid | 121357.86 | 2024-Q2
EXP-000444 | 2024-06-11 | BOQ-PKG-04-00444 | PKG-04 | INV-PKG-04-025-00444 | 113.33 | 177060.05 | 8853 | Paid | 168207.05 | 2024-Q2
EXP-000572 | 2024-06-11 | BOQ-PKG-02-00572 | PKG-02 | INV-PKG-02-013-00572 | 168.15 | 135812.51 | 6790.63 | Disputed | 129021.88 | 2024-Q2
EXP-000879 | 2024-06-11 | BOQ-PKG-09-00879 | PKG-09 | INV-PKG-09-005-00879 | 199.48 | 99912.01 | 4995.6 | Paid | 94916.41 | 2024-Q2
EXP-002125 | 2024-06-11 | BOQ-PKG-05-00135 | PKG-05 | INV-PKG-05-026-02125 | 117.83 | 39832.76 | 1991.64 | Approved Pending Payment | 37841.12 | 2024-Q2
EXP-003264 | 2024-06-11 | BOQ-PKG-04-01274 | PKG-04 | INV-PKG-04-010-03264 | 320.39 | 128103.55 | 6405.18 | Paid | 121698.37 | 2024-Q2
EXP-004214 | 2024-06-11 | BOQ-PKG-04-00234 | PKG-04 | INV-PKG-04-015-04214 | 29.37 | 97521.5 | 4876.08 | Paid | 92645.42 | 2024-Q2
EXP-005368 | 2024-06-11 | BOQ-PKG-08-01388 | PKG-08 | INV-PKG-08-014-05368 | 325.68 | 161601.86 | 8080.09 | Paid | 153521.77 | 2024-Q2
EXP-000490 | 2024-06-12 | BOQ-PKG-10-00490 | PKG-10 | INV-PKG-10-001-00490 | 426.67 | 164084.62 | 8204.23 | Paid | 155880.39 | 2024-Q2
EXP-001087 | 2024-06-12 | BOQ-PKG-07-01087 | PKG-07 | INV-PKG-07-003-01087 | 303.58 | 159680.66 | 7984.03 | Paid | 151696.63 | 2024-Q2
EXP-002538 | 2024-06-12 | BOQ-PKG-08-00548 | PKG-08 | INV-PKG-08-019-02538 | 284.29 | 195421.29 | 9771.06 | Paid | 185650.23 | 2024-Q2
EXP-002895 | 2024-06-12 | BOQ-PKG-05-00905 | PKG-05 | INV-PKG-05-026-02895 | 253.76 | 142793.26 | 7139.66 | Under Review | 135653.6 | 2024-Q2
EXP-002923 | 2024-06-12 | BOQ-PKG-03-00933 | PKG-03 | INV-PKG-03-019-02923 | 110.24 | 94372.3 | 4718.62 | Approved Pending Payment | 89653.68 | 2024-Q2
EXP-005024 | 2024-06-12 | BOQ-PKG-04-01044 | PKG-04 | INV-PKG-04-020-05024 | 427.42 | 116170.97 | 5808.55 | Paid | 110362.42 | 2024-Q2
EXP-005949 | 2024-06-12 | BOQ-PKG-09-01969 | PKG-09 | INV-PKG-09-035-05949 | 313.71 | 133896.85 | 6694.84 | Paid | 127202.01 | 2024-Q2
EXP-006244 | 2024-06-12 | BOQ-PKG-04-00274 | PKG-04 | INV-PKG-04-015-06244 | 279.59 | 136653.99 | 6832.7 | Paid | 129821.29 | 2024-Q2
EXP-000755 | 2024-06-13 | BOQ-PKG-05-00755 | PKG-05 | INV-PKG-05-021-00755 | 311.21 | 47591.92 | 2379.6 | Paid | 45212.32 | 2024-Q2
EXP-001131 | 2024-06-13 | BOQ-PKG-01-01131 | PKG-01 | INV-PKG-01-012-01131 | 314.43 | 44241.44 | 2212.07 | Paid | 42029.37 | 2024-Q2
EXP-001747 | 2024-06-13 | BOQ-PKG-07-01747 | PKG-07 | INV-PKG-07-033-01747 | 79.59 | 148103.47 | 7405.17 | Paid | 140698.3 | 2024-Q2
EXP-003537 | 2024-06-13 | BOQ-PKG-07-01547 | PKG-07 | INV-PKG-07-003-03537 | 157.04 | 55042.48 | 2752.12 | Paid | 52290.36 | 2024-Q2
EXP-005052 | 2024-06-13 | BOQ-PKG-02-01072 | PKG-02 | INV-PKG-02-013-05052 | 235.31 | 97677.11 | 4883.86 | Paid | 92793.25 | 2024-Q2
EXP-006513 | 2024-06-13 | BOQ-PKG-03-00543 | PKG-03 | INV-PKG-03-004-06513 | 348.55 | 161058.83 | 8052.94 | Paid | 153005.89 | 2024-Q2
EXP-000170 | 2024-06-14 | BOQ-PKG-10-00170 | PKG-10 | INV-PKG-10-031-00170 | 312.6 | 54403.73 | 2720.19 | Paid | 51683.54 | 2024-Q2
EXP-002238 | 2024-06-14 | BOQ-PKG-08-00248 | PKG-08 | INV-PKG-08-034-02238 | 26.07 | 60917.69 | 3045.88 | Approved Pending Payment | 57871.81 | 2024-Q2
EXP-002515 | 2024-06-14 | BOQ-PKG-05-00525 | PKG-05 | INV-PKG-05-031-02515 | 175.45 | 54902.98 | 2745.15 | Under Review | 52157.83 | 2024-Q2
EXP-003664 | 2024-06-14 | BOQ-PKG-04-01674 | PKG-04 | INV-PKG-04-025-03664 | 339.18 | 153028.8 | 7651.44 | Approved Pending Payment | 145377.36 | 2024-Q2
EXP-003769 | 2024-06-14 | BOQ-PKG-09-01779 | PKG-09 | INV-PKG-09-025-03769 | 311.94 | 137443.56 | 6872.18 | Paid | 130571.38 | 2024-Q2
EXP-003874 | 2024-06-14 | BOQ-PKG-04-01884 | PKG-04 | INV-PKG-04-025-03874 | 164.51 | 66506.77 | 3325.34 | Paid | 63181.43 | 2024-Q2
EXP-004266 | 2024-06-14 | BOQ-PKG-06-00286 | PKG-06 | INV-PKG-06-032-04266 | 279 | 185878.83 | 9293.94 | Approved Pending Payment | 176584.89 | 2024-Q2
EXP-006850 | 2024-06-14 | BOQ-PKG-10-00880 | PKG-10 | INV-PKG-10-026-06850 | 425.14 | 103488.2 | 5174.41 | Paid | 98313.79 | 2024-Q2
EXP-003172 | 2024-06-15 | BOQ-PKG-02-01182 | PKG-02 | INV-PKG-02-023-03172 | 232.34 | 93779.41 | 4688.97 | Under Review | 89090.44 | 2024-Q2
EXP-003442 | 2024-06-15 | BOQ-PKG-02-01452 | PKG-02 | INV-PKG-02-013-03442 | 231.14 | 25715.29 | 1285.76 | Under Review | 24429.53 | 2024-Q2
EXP-004015 | 2024-06-15 | BOQ-PKG-05-00035 | PKG-05 | INV-PKG-05-026-04015 | 143.5 | 114801.13 | 5740.06 | Paid | 109061.07 | 2024-Q2
EXP-004689 | 2024-06-15 | BOQ-PKG-09-00709 | PKG-09 | INV-PKG-09-035-04689 | 245.89 | 84049.32 | 4202.47 | Paid | 79846.85 | 2024-Q2
EXP-005865 | 2024-06-15 | BOQ-PKG-05-01885 | PKG-05 | INV-PKG-05-021-05865 | 8.74 | 79611.63 | 3980.58 | Paid | 75631.05 | 2024-Q2
EXP-000101 | 2024-06-16 | BOQ-PKG-01-00101 | PKG-01 | INV-PKG-01-032-00101 | 214.92 | 127978.33 | 6398.92 | Paid | 121579.41 | 2024-Q2
EXP-000186 | 2024-06-16 | BOQ-PKG-06-00186 | PKG-06 | INV-PKG-06-012-00186 | 434.8 | 63541.87 | 3177.09 | Paid | 60364.78 | 2024-Q2
EXP-005781 | 2024-06-16 | BOQ-PKG-01-01801 | PKG-01 | INV-PKG-01-007-05781 | 54.24 | 147212.61 | 7360.63 | Paid | 139851.98 | 2024-Q2
EXP-000061 | 2024-06-17 | BOQ-PKG-01-00061 | PKG-01 | INV-PKG-01-027-00061 | 331.79 | 60752.94 | 3037.65 | Paid | 57715.29 | 2024-Q2
EXP-000375 | 2024-06-17 | BOQ-PKG-05-00375 | PKG-05 | INV-PKG-05-026-00375 | 432.09 | 188151.27 | 9407.56 | Paid | 178743.71 | 2024-Q2
EXP-001432 | 2024-06-17 | BOQ-PKG-02-01432 | PKG-02 | INV-PKG-02-033-01432 | 142.92 | 194805.26 | 9740.26 | Disputed | 185065 | 2024-Q2
EXP-003356 | 2024-06-17 | BOQ-PKG-06-01366 | PKG-06 | INV-PKG-06-032-03356 | 261.68 | 199315.53 | 9965.78 | Paid | 189349.75 | 2024-Q2
EXP-005303 | 2024-06-17 | BOQ-PKG-03-01323 | PKG-03 | INV-PKG-03-019-05303 | 341.28 | 106484.78 | 5324.24 | Approved Pending Payment | 101160.54 | 2024-Q2
EXP-006932 | 2024-06-17 | BOQ-PKG-02-00962 | PKG-02 | INV-PKG-02-003-06932 | 215.93 | 31084.92 | 1554.25 | Approved Pending Payment | 29530.67 | 2024-Q2
EXP-001939 | 2024-06-18 | BOQ-PKG-09-01939 | PKG-09 | INV-PKG-09-015-01939 | 16.55 | 40057.79 | 2002.89 | Disputed | 38054.9 | 2024-Q2
EXP-004050 | 2024-06-18 | BOQ-PKG-10-00070 | PKG-10 | INV-PKG-10-026-04050 | 302.62 | 149139.91 | 7457 | Paid | 141682.91 | 2024-Q2
EXP-005449 | 2024-06-18 | BOQ-PKG-09-01469 | PKG-09 | INV-PKG-09-025-05449 | 184.54 | 188675.78 | 9433.79 | Paid | 179241.99 | 2024-Q2
EXP-006645 | 2024-06-18 | BOQ-PKG-05-00675 | PKG-05 | INV-PKG-05-031-06645 | 36.02 | 185749.99 | 9287.5 | Paid | 176462.49 | 2024-Q2
EXP-001541 | 2024-06-19 | BOQ-PKG-01-01541 | PKG-01 | INV-PKG-01-002-01541 | 110.38 | 115655.3 | 5782.76 | Under Review | 109872.54 | 2024-Q2
EXP-001554 | 2024-06-19 | BOQ-PKG-04-01554 | PKG-04 | INV-PKG-04-015-01554 | 7.49 | 31285.65 | 1564.28 | Paid | 29721.37 | 2024-Q2
EXP-002883 | 2024-06-19 | BOQ-PKG-03-00893 | PKG-03 | INV-PKG-03-014-02883 | 430.71 | 65526.37 | 3276.32 | Paid | 62250.05 | 2024-Q2
EXP-003050 | 2024-06-19 | BOQ-PKG-10-01060 | PKG-10 | INV-PKG-10-006-03050 | 228.87 | 113337.17 | 5666.86 | Approved Pending Payment | 107670.31 | 2024-Q2
EXP-003963 | 2024-06-19 | BOQ-PKG-03-01973 | PKG-03 | INV-PKG-03-009-03963 | 196.12 | 101976.29 | 5098.81 | Paid | 96877.48 | 2024-Q2
EXP-004891 | 2024-06-19 | BOQ-PKG-01-00911 | PKG-01 | INV-PKG-01-027-04891 | 119.33 | 106644.95 | 5332.25 | Paid | 101312.7 | 2024-Q2
EXP-005377 | 2024-06-19 | BOQ-PKG-07-01397 | PKG-07 | INV-PKG-07-023-05377 | 110.96 | 35191.65 | 1759.58 | Paid | 33432.07 | 2024-Q2
EXP-000207 | 2024-06-20 | BOQ-PKG-07-00207 | PKG-07 | INV-PKG-07-033-00207 | 319.44 | 125206.86 | 6260.34 | Paid | 118946.52 | 2024-Q2
EXP-001353 | 2024-06-20 | BOQ-PKG-03-01353 | PKG-03 | INV-PKG-03-024-01353 | 350.84 | 66831.45 | 3341.57 | Paid | 63489.88 | 2024-Q2
EXP-001398 | 2024-06-20 | BOQ-PKG-08-01398 | PKG-08 | INV-PKG-08-034-01398 | 71.53 | 133277.85 | 6663.89 | Paid | 126613.96 | 2024-Q2
EXP-003105 | 2024-06-20 | BOQ-PKG-05-01115 | PKG-05 | INV-PKG-05-026-03105 | 198.55 | 140573.03 | 7028.65 | Paid | 133544.38 | 2024-Q2
EXP-004225 | 2024-06-20 | BOQ-PKG-05-00245 | PKG-05 | INV-PKG-05-026-04225 | 405.89 | 131299.69 | 6564.98 | Paid | 124734.71 | 2024-Q2
EXP-004777 | 2024-06-20 | BOQ-PKG-07-00797 | PKG-07 | INV-PKG-07-018-04777 | 370.02 | 175485.39 | 8774.27 | Paid | 166711.12 | 2024-Q2
EXP-000367 | 2024-06-21 | BOQ-PKG-07-00367 | PKG-07 | INV-PKG-07-018-00367 | 443.85 | 174167.2 | 8708.36 | Paid | 165458.84 | 2024-Q2
EXP-001304 | 2024-06-21 | BOQ-PKG-04-01304 | PKG-04 | INV-PKG-04-010-01304 | 240.24 | 131997.95 | 6599.9 | Paid | 125398.05 | 2024-Q2
EXP-003019 | 2024-06-21 | BOQ-PKG-09-01029 | PKG-09 | INV-PKG-09-010-03019 | 203.39 | 87230.13 | 4361.51 | Paid | 82868.62 | 2024-Q2
EXP-004593 | 2024-06-21 | BOQ-PKG-03-00613 | PKG-03 | INV-PKG-03-009-04593 | 116.12 | 50193.9 | 2509.7 | Paid | 47684.2 | 2024-Q2
EXP-004914 | 2024-06-21 | BOQ-PKG-04-00934 | PKG-04 | INV-PKG-04-015-04914 | 386.49 | 136383.81 | 6819.19 | Approved Pending Payment | 129564.62 | 2024-Q2
EXP-005846 | 2024-06-21 | BOQ-PKG-06-01866 | PKG-06 | INV-PKG-06-002-05846 | 367.48 | 193937.85 | 9696.89 | Disputed | 184240.96 | 2024-Q2
EXP-005898 | 2024-06-21 | BOQ-PKG-08-01918 | PKG-08 | INV-PKG-08-019-05898 | 123.35 | 48597.77 | 2429.89 | Paid | 46167.88 | 2024-Q2
EXP-006033 | 2024-06-21 | BOQ-PKG-03-00063 | PKG-03 | INV-PKG-03-014-06033 | 92.96 | 103342.61 | 5167.13 | Paid | 98175.48 | 2024-Q2
EXP-006539 | 2024-06-21 | BOQ-PKG-09-00569 | PKG-09 | INV-PKG-09-030-06539 | 263.59 | 69626.25 | 3481.31 | Approved Pending Payment | 66144.94 | 2024-Q2
EXP-000136 | 2024-06-22 | BOQ-PKG-06-00136 | PKG-06 | INV-PKG-06-032-00136 | 377.22 | 123347.96 | 6167.4 | Approved Pending Payment | 117180.56 | 2024-Q2
EXP-000434 | 2024-06-22 | BOQ-PKG-04-00434 | PKG-04 | INV-PKG-04-015-00434 | 232.96 | 116062.65 | 5803.13 | Under Review | 110259.52 | 2024-Q2
EXP-001859 | 2024-06-22 | BOQ-PKG-09-01859 | PKG-09 | INV-PKG-09-005-01859 | 150.44 | 56581.88 | 2829.09 | Paid | 53752.79 | 2024-Q2
EXP-002142 | 2024-06-22 | BOQ-PKG-02-00152 | PKG-02 | INV-PKG-02-008-02142 | 158.72 | 171985.3 | 8599.26 | Paid | 163386.04 | 2024-Q2
EXP-004855 | 2024-06-22 | BOQ-PKG-05-00875 | PKG-05 | INV-PKG-05-026-04855 | 445.22 | 105288.59 | 5264.43 | Paid | 100024.16 | 2024-Q2
EXP-005491 | 2024-06-22 | BOQ-PKG-01-01511 | PKG-01 | INV-PKG-01-032-05491 | 224.53 | 32157.59 | 1607.88 | Paid | 30549.71 | 2024-Q2
EXP-005545 | 2024-06-22 | BOQ-PKG-05-01565 | PKG-05 | INV-PKG-05-016-05545 | 44.42 | 59792.94 | 2989.65 | Paid | 56803.29 | 2024-Q2
EXP-005571 | 2024-06-22 | BOQ-PKG-01-01591 | PKG-01 | INV-PKG-01-007-05571 | 126.76 | 147453.71 | 7372.69 | Paid | 140081.02 | 2024-Q2
EXP-000167 | 2024-06-23 | BOQ-PKG-07-00167 | PKG-07 | INV-PKG-07-028-00167 | 385 | 26431.85 | 1321.59 | Approved Pending Payment | 25110.26 | 2024-Q2
EXP-000347 | 2024-06-23 | BOQ-PKG-07-00347 | PKG-07 | INV-PKG-07-033-00347 | 435.91 | 112284.36 | 5614.22 | Paid | 106670.14 | 2024-Q2
EXP-000720 | 2024-06-23 | BOQ-PKG-10-00720 | PKG-10 | INV-PKG-10-021-00720 | 263.45 | 162456.84 | 8122.84 | Paid | 154334 | 2024-Q2
EXP-002239 | 2024-06-23 | BOQ-PKG-09-00249 | PKG-09 | INV-PKG-09-035-02239 | 53.31 | 161338.9 | 8066.94 | Under Review | 153271.96 | 2024-Q2
EXP-002787 | 2024-06-23 | BOQ-PKG-07-00797 | PKG-07 | INV-PKG-07-023-02787 | 13.26 | 142338.93 | 7116.95 | Paid | 135221.98 | 2024-Q2
EXP-002878 | 2024-06-23 | BOQ-PKG-08-00888 | PKG-08 | INV-PKG-08-009-02878 | 424.05 | 82597.96 | 4129.9 | Approved Pending Payment | 78468.06 | 2024-Q2
EXP-003481 | 2024-06-23 | BOQ-PKG-01-01491 | PKG-01 | INV-PKG-01-017-03481 | 339.36 | 39757 | 1987.85 | Paid | 37769.15 | 2024-Q2
EXP-004536 | 2024-06-23 | BOQ-PKG-06-00556 | PKG-06 | INV-PKG-06-022-04536 | 318.64 | 167292.97 | 8364.65 | Paid | 158928.32 | 2024-Q2
EXP-005149 | 2024-06-23 | BOQ-PKG-09-01169 | PKG-09 | INV-PKG-09-005-05149 | 62.56 | 124675.19 | 6233.76 | Under Review | 118441.43 | 2024-Q2
EXP-005583 | 2024-06-23 | BOQ-PKG-03-01603 | PKG-03 | INV-PKG-03-019-05583 | 261.99 | 108990.7 | 5449.54 | Under Review | 103541.16 | 2024-Q2
EXP-006165 | 2024-06-23 | BOQ-PKG-05-00195 | PKG-05 | INV-PKG-05-006-06165 | 302.82 | 94836.92 | 4741.85 | Disputed | 90095.07 | 2024-Q2
EXP-006377 | 2024-06-23 | BOQ-PKG-07-00407 | PKG-07 | INV-PKG-07-008-06377 | 25.23 | 65381.39 | 3269.07 | Paid | 62112.32 | 2024-Q2
EXP-006611 | 2024-06-23 | BOQ-PKG-01-00641 | PKG-01 | INV-PKG-01-032-06611 | 218.53 | 183400.59 | 9170.03 | Approved Pending Payment | 174230.56 | 2024-Q2
EXP-002108 | 2024-06-24 | BOQ-PKG-08-00118 | PKG-08 | INV-PKG-08-009-02108 | 225.24 | 115948.65 | 5797.43 | Paid | 110151.22 | 2024-Q2
EXP-002297 | 2024-06-24 | BOQ-PKG-07-00307 | PKG-07 | INV-PKG-07-023-02297 | 368.78 | 91313.82 | 4565.69 | Approved Pending Payment | 86748.13 | 2024-Q2
EXP-002998 | 2024-06-24 | BOQ-PKG-08-01008 | PKG-08 | INV-PKG-08-024-02998 | 14.8 | 63680.28 | 3184.01 | Paid | 60496.27 | 2024-Q2
EXP-004476 | 2024-06-24 | BOQ-PKG-06-00496 | PKG-06 | INV-PKG-06-032-04476 | 58.58 | 29850.13 | 1492.51 | Paid | 28357.62 | 2024-Q2
EXP-000553 | 2024-06-25 | BOQ-PKG-03-00553 | PKG-03 | INV-PKG-03-029-00553 | 55.39 | 134094.45 | 6704.72 | Paid | 127389.73 | 2024-Q2
EXP-000917 | 2024-06-25 | BOQ-PKG-07-00917 | PKG-07 | INV-PKG-07-008-00917 | 404.35 | 150828.49 | 7541.42 | Paid | 143287.07 | 2024-Q2
EXP-001093 | 2024-06-25 | BOQ-PKG-03-01093 | PKG-03 | INV-PKG-03-009-01093 | 51.49 | 67642.35 | 3382.12 | Paid | 64260.23 | 2024-Q2
EXP-001395 | 2024-06-25 | BOQ-PKG-05-01395 | PKG-05 | INV-PKG-05-031-01395 | 348.34 | 63495.96 | 3174.8 | Under Review | 60321.16 | 2024-Q2
EXP-003596 | 2024-06-25 | BOQ-PKG-06-01606 | PKG-06 | INV-PKG-06-027-03596 | 411.54 | 153565.62 | 7678.28 | Disputed | 145887.34 | 2024-Q2
EXP-004469 | 2024-06-25 | BOQ-PKG-09-00489 | PKG-09 | INV-PKG-09-025-04469 | 206.37 | 82116.32 | 4105.82 | Under Review | 78010.5 | 2024-Q2
EXP-004658 | 2024-06-25 | BOQ-PKG-08-00678 | PKG-08 | INV-PKG-08-004-04658 | 269.09 | 166823.36 | 8341.17 | Paid | 158482.19 | 2024-Q2
EXP-005359 | 2024-06-25 | BOQ-PKG-09-01379 | PKG-09 | INV-PKG-09-005-05359 | 304.45 | 91428.88 | 4571.44 | Paid | 86857.44 | 2024-Q2
EXP-005933 | 2024-06-25 | BOQ-PKG-03-01953 | PKG-03 | INV-PKG-03-019-05933 | 179.27 | 60727.01 | 3036.35 | Paid | 57690.66 | 2024-Q2
EXP-000113 | 2024-06-26 | BOQ-PKG-03-00113 | PKG-03 | INV-PKG-03-009-00113 | 235.54 | 62808.39 | 3140.42 | Paid | 59667.97 | 2024-Q2
EXP-000530 | 2024-06-26 | BOQ-PKG-10-00530 | PKG-10 | INV-PKG-10-006-00530 | 364.48 | 153977.48 | 7698.87 | Paid | 146278.61 | 2024-Q2
EXP-001146 | 2024-06-26 | BOQ-PKG-06-01146 | PKG-06 | INV-PKG-06-027-01146 | 6.17 | 106877.03 | 5343.85 | Paid | 101533.18 | 2024-Q2
EXP-001228 | 2024-06-26 | BOQ-PKG-08-01228 | PKG-08 | INV-PKG-08-004-01228 | 50.63 | 133919.84 | 6695.99 | Approved Pending Payment | 127223.85 | 2024-Q2
EXP-001285 | 2024-06-26 | BOQ-PKG-05-01285 | PKG-05 | INV-PKG-05-026-01285 | 129.03 | 52319.62 | 2615.98 | Disputed | 49703.64 | 2024-Q2
EXP-001697 | 2024-06-26 | BOQ-PKG-07-01697 | PKG-07 | INV-PKG-07-018-01697 | 344.19 | 213346.76 | 10667.34 | Paid | 202679.42 | 2024-Q2
EXP-002460 | 2024-06-26 | BOQ-PKG-10-00470 | PKG-10 | INV-PKG-10-011-02460 | 99.32 | 120151.83 | 6007.59 | Paid | 114144.24 | 2024-Q2
EXP-002855 | 2024-06-26 | BOQ-PKG-05-00865 | PKG-05 | INV-PKG-05-021-02855 | 34.92 | 148855.23 | 7442.76 | Approved Pending Payment | 141412.47 | 2024-Q2
EXP-003180 | 2024-06-26 | BOQ-PKG-10-01190 | PKG-10 | INV-PKG-10-031-03180 | 66.82 | 92298.42 | 4614.92 | Paid | 87683.5 | 2024-Q2
EXP-005658 | 2024-06-26 | BOQ-PKG-08-01678 | PKG-08 | INV-PKG-08-024-05658 | 374.76 | 139365.44 | 6968.27 | Paid | 132397.17 | 2024-Q2
EXP-006394 | 2024-06-26 | BOQ-PKG-04-00424 | PKG-04 | INV-PKG-04-025-06394 | 328.06 | 34379.24 | 1718.96 | Paid | 32660.28 | 2024-Q2
EXP-006506 | 2024-06-26 | BOQ-PKG-06-00536 | PKG-06 | INV-PKG-06-032-06506 | 154.32 | 150673.39 | 7533.67 | Under Review | 143139.72 | 2024-Q2
EXP-000588 | 2024-06-27 | BOQ-PKG-08-00588 | PKG-08 | INV-PKG-08-029-00588 | 173.82 | 195754.45 | 9787.72 | Paid | 185966.73 | 2024-Q2
EXP-001989 | 2024-06-27 | BOQ-PKG-09-01989 | PKG-09 | INV-PKG-09-030-01989 | 26.28 | 67999.54 | 3399.98 | Paid | 64599.56 | 2024-Q2
EXP-003128 | 2024-06-27 | BOQ-PKG-08-01138 | PKG-08 | INV-PKG-08-014-03128 | 274.6 | 79676.65 | 3983.83 | Approved Pending Payment | 75692.82 | 2024-Q2
EXP-004075 | 2024-06-27 | BOQ-PKG-05-00095 | PKG-05 | INV-PKG-05-016-04075 | 34.37 | 168501.94 | 8425.1 | Paid | 160076.84 | 2024-Q2
EXP-006053 | 2024-06-27 | BOQ-PKG-03-00083 | PKG-03 | INV-PKG-03-034-06053 | 180.11 | 94306.41 | 4715.32 | Disputed | 89591.09 | 2024-Q2
EXP-006287 | 2024-06-27 | BOQ-PKG-07-00317 | PKG-07 | INV-PKG-07-023-06287 | 191.92 | 109123.53 | 5456.18 | Paid | 103667.35 | 2024-Q2
EXP-006639 | 2024-06-27 | BOQ-PKG-09-00669 | PKG-09 | INV-PKG-09-025-06639 | 327.23 | 119960.64 | 5998.03 | Under Review | 113962.61 | 2024-Q2
EXP-006927 | 2024-06-27 | BOQ-PKG-07-00957 | PKG-07 | INV-PKG-07-033-06927 | 32.4 | 129788.47 | 6489.42 | Under Review | 123299.05 | 2024-Q2
EXP-000107 | 2024-06-28 | BOQ-PKG-07-00107 | PKG-07 | INV-PKG-07-003-00107 | 214.88 | 41410.83 | 2070.54 | Paid | 39340.29 | 2024-Q2
EXP-000847 | 2024-06-28 | BOQ-PKG-07-00847 | PKG-07 | INV-PKG-07-008-00847 | 343.54 | 27016.45 | 1350.82 | Paid | 25665.63 | 2024-Q2
EXP-001495 | 2024-06-28 | BOQ-PKG-05-01495 | PKG-05 | INV-PKG-05-026-01495 | 281.74 | 28374.76 | 1418.74 | Disputed | 26956.02 | 2024-Q2
EXP-003519 | 2024-06-28 | BOQ-PKG-09-01529 | PKG-09 | INV-PKG-09-020-03519 | 13.55 | 140578.36 | 7028.92 | Disputed | 133549.44 | 2024-Q2
EXP-004924 | 2024-06-28 | BOQ-PKG-04-00944 | PKG-04 | INV-PKG-04-025-04924 | 39.58 | 158983.06 | 7949.15 | Approved Pending Payment | 151033.91 | 2024-Q2
EXP-006563 | 2024-06-28 | BOQ-PKG-03-00593 | PKG-03 | INV-PKG-03-019-06563 | 52.16 | 67675.84 | 3383.79 | Paid | 64292.05 | 2024-Q2
EXP-007000 | 2024-06-28 | BOQ-PKG-10-01030 | PKG-10 | INV-PKG-10-001-07000 | 179.16 | 171009.09 | 8550.45 | Disputed | 162458.64 | 2024-Q2
EXP-001969 | 2024-06-29 | BOQ-PKG-09-01969 | PKG-09 | INV-PKG-09-010-01969 | 114.99 | 204090.96 | 10204.55 | Paid | 193886.41 | 2024-Q2
EXP-004793 | 2024-06-29 | BOQ-PKG-03-00813 | PKG-03 | INV-PKG-03-034-04793 | 272.5 | 154399 | 7719.95 | Paid | 146679.05 | 2024-Q2
EXP-005190 | 2024-06-29 | BOQ-PKG-10-01210 | PKG-10 | INV-PKG-10-011-05190 | 127.32 | 194631.31 | 9731.57 | Under Review | 184899.74 | 2024-Q2
EXP-006463 | 2024-06-29 | BOQ-PKG-03-00493 | PKG-03 | INV-PKG-03-024-06463 | 397.8 | 45410.88 | 2270.54 | Paid | 43140.34 | 2024-Q2
EXP-006791 | 2024-06-29 | BOQ-PKG-01-00821 | PKG-01 | INV-PKG-01-002-06791 | 412.71 | 194173.26 | 9708.66 | Approved Pending Payment | 184464.6 | 2024-Q2
EXP-000951 | 2024-06-30 | BOQ-PKG-01-00951 | PKG-01 | INV-PKG-01-007-00951 | 335.78 | 70747.2 | 3537.36 | Paid | 67209.84 | 2024-Q2
EXP-001884 | 2024-06-30 | BOQ-PKG-04-01884 | PKG-04 | INV-PKG-04-030-01884 | 249.18 | 109712.02 | 5485.6 | Paid | 104226.42 | 2024-Q2
EXP-002420 | 2024-06-30 | BOQ-PKG-10-00430 | PKG-10 | INV-PKG-10-006-02420 | 122.88 | 39034.34 | 1951.72 | Paid | 37082.62 | 2024-Q2
EXP-002941 | 2024-06-30 | BOQ-PKG-01-00951 | PKG-01 | INV-PKG-01-002-02941 | 326.14 | 134877.51 | 6743.88 | Paid | 128133.63 | 2024-Q2
EXP-003432 | 2024-06-30 | BOQ-PKG-02-01442 | PKG-02 | INV-PKG-02-003-03432 | 437.62 | 135165.53 | 6758.28 | Paid | 128407.25 | 2024-Q2
EXP-003988 | 2024-06-30 | BOQ-PKG-08-00008 | PKG-08 | INV-PKG-08-034-03988 | 247.4 | 124520.47 | 6226.02 | Paid | 118294.45 | 2024-Q2
EXP-004136 | 2024-06-30 | BOQ-PKG-06-00156 | PKG-06 | INV-PKG-06-007-04136 | 445.63 | 99458.37 | 4972.92 | Paid | 94485.45 | 2024-Q2
EXP-004900 | 2024-06-30 | BOQ-PKG-10-00920 | PKG-10 | INV-PKG-10-001-04900 | 211.87 | 146138.7 | 7306.94 | Paid | 138831.76 | 2024-Q2
EXP-006020 | 2024-06-30 | BOQ-PKG-10-00050 | PKG-10 | INV-PKG-10-001-06020 | 184.64 | 53104.92 | 2655.25 | Paid | 50449.67 | 2024-Q2
EXP-000039 | 2024-07-01 | BOQ-PKG-09-00039 | PKG-09 | INV-PKG-09-005-00039 | 444.36 | 107123.95 | 5356.2 | Under Review | 101767.75 | 2024-Q3
EXP-000068 | 2024-07-01 | BOQ-PKG-08-00068 | PKG-08 | INV-PKG-08-034-00068 | 326.32 | 31226.26 | 1561.31 | Paid | 29664.95 | 2024-Q3
EXP-001209 | 2024-07-01 | BOQ-PKG-09-01209 | PKG-09 | INV-PKG-09-020-01209 | 17.69 | 186253.94 | 9312.7 | Approved Pending Payment | 176941.24 | 2024-Q3
EXP-001565 | 2024-07-01 | BOQ-PKG-05-01565 | PKG-05 | INV-PKG-05-026-01565 | 166.81 | 97286.29 | 4864.31 | Disputed | 92421.98 | 2024-Q3
EXP-002343 | 2024-07-01 | BOQ-PKG-03-00353 | PKG-03 | INV-PKG-03-034-02343 | 308.59 | 118966.47 | 5948.32 | Paid | 113018.15 | 2024-Q3
EXP-002375 | 2024-07-01 | BOQ-PKG-05-00385 | PKG-05 | INV-PKG-05-031-02375 | 299.65 | 55119.47 | 2755.97 | Paid | 52363.5 | 2024-Q3
EXP-002509 | 2024-07-01 | BOQ-PKG-09-00519 | PKG-09 | INV-PKG-09-025-02509 | 355.27 | 180638.55 | 9031.93 | Paid | 171606.62 | 2024-Q3
EXP-002658 | 2024-07-01 | BOQ-PKG-08-00668 | PKG-08 | INV-PKG-08-034-02658 | 135.09 | 125082.37 | 6254.12 | Paid | 118828.25 | 2024-Q3
EXP-005015 | 2024-07-01 | BOQ-PKG-05-01035 | PKG-05 | INV-PKG-05-011-05015 | 135.54 | 155987.82 | 7799.39 | Approved Pending Payment | 148188.43 | 2024-Q3
EXP-000426 | 2024-07-02 | BOQ-PKG-06-00426 | PKG-06 | INV-PKG-06-007-00426 | 224.4 | 38302.08 | 1915.1 | Under Review | 36386.98 | 2024-Q3
EXP-003324 | 2024-07-02 | BOQ-PKG-04-01334 | PKG-04 | INV-PKG-04-035-03324 | 184.95 | 120573.92 | 6028.7 | Disputed | 114545.22 | 2024-Q3
EXP-003366 | 2024-07-02 | BOQ-PKG-06-01376 | PKG-06 | INV-PKG-06-007-03366 | 409 | 144600.66 | 7230.03 | Approved Pending Payment | 137370.63 | 2024-Q3
EXP-003711 | 2024-07-02 | BOQ-PKG-01-01721 | PKG-01 | INV-PKG-01-002-03711 | 266.26 | 201393.6 | 10069.68 | Paid | 191323.92 | 2024-Q3
EXP-005363 | 2024-07-02 | BOQ-PKG-03-01383 | PKG-03 | INV-PKG-03-009-05363 | 369.44 | 113786.6 | 5689.33 | Approved Pending Payment | 108097.27 | 2024-Q3
EXP-005661 | 2024-07-02 | BOQ-PKG-01-01681 | PKG-01 | INV-PKG-01-027-05661 | 152.51 | 204444.51 | 10222.23 | Paid | 194222.28 | 2024-Q3
EXP-006135 | 2024-07-02 | BOQ-PKG-05-00165 | PKG-05 | INV-PKG-05-011-06135 | 325.67 | 55055.44 | 2752.77 | Paid | 52302.67 | 2024-Q3
EXP-006717 | 2024-07-02 | BOQ-PKG-07-00747 | PKG-07 | INV-PKG-07-033-06717 | 140.74 | 144168.93 | 7208.45 | Under Review | 136960.48 | 2024-Q3
EXP-006879 | 2024-07-02 | BOQ-PKG-09-00909 | PKG-09 | INV-PKG-09-020-06879 | 207.99 | 69782.86 | 3489.14 | Paid | 66293.72 | 2024-Q3
EXP-001942 | 2024-07-03 | BOQ-PKG-02-01942 | PKG-02 | INV-PKG-02-018-01942 | 260.08 | 204234.03 | 10211.7 | Approved Pending Payment | 194022.33 | 2024-Q3
EXP-002500 | 2024-07-03 | BOQ-PKG-10-00510 | PKG-10 | INV-PKG-10-016-02500 | 41.58 | 84741.05 | 4237.05 | Paid | 80504 | 2024-Q3
EXP-003307 | 2024-07-03 | BOQ-PKG-07-01317 | PKG-07 | INV-PKG-07-018-03307 | 297.46 | 212107.44 | 10605.37 | Paid | 201502.07 | 2024-Q3
EXP-004520 | 2024-07-03 | BOQ-PKG-10-00540 | PKG-10 | INV-PKG-10-006-04520 | 411.77 | 86262.89 | 4313.14 | Paid | 81949.75 | 2024-Q3
EXP-006197 | 2024-07-03 | BOQ-PKG-07-00227 | PKG-07 | INV-PKG-07-003-06197 | 211.89 | 154599.77 | 7729.99 | Disputed | 146869.78 | 2024-Q3
EXP-006267 | 2024-07-03 | BOQ-PKG-07-00297 | PKG-07 | INV-PKG-07-003-06267 | 18.57 | 84894.49 | 4244.72 | Approved Pending Payment | 80649.77 | 2024-Q3
EXP-001515 | 2024-07-04 | BOQ-PKG-05-01515 | PKG-05 | INV-PKG-05-011-01515 | 327.24 | 178056.51 | 8902.83 | Paid | 169153.68 | 2024-Q3
EXP-002655 | 2024-07-04 | BOQ-PKG-05-00665 | PKG-05 | INV-PKG-05-031-02655 | 269.58 | 102253.52 | 5112.68 | Paid | 97140.84 | 2024-Q3
EXP-004474 | 2024-07-04 | BOQ-PKG-04-00494 | PKG-04 | INV-PKG-04-030-04474 | 92.24 | 199979.51 | 9998.98 | Paid | 189980.53 | 2024-Q3
EXP-004958 | 2024-07-04 | BOQ-PKG-08-00978 | PKG-08 | INV-PKG-08-024-04958 | 129.39 | 86428.57 | 4321.43 | Paid | 82107.14 | 2024-Q3
EXP-005361 | 2024-07-04 | BOQ-PKG-01-01381 | PKG-01 | INV-PKG-01-007-05361 | 343.42 | 56115.48 | 2805.77 | Paid | 53309.71 | 2024-Q3
EXP-005588 | 2024-07-04 | BOQ-PKG-08-01608 | PKG-08 | INV-PKG-08-024-05588 | 68.52 | 94276.35 | 4713.82 | Under Review | 89562.53 | 2024-Q3
EXP-006770 | 2024-07-04 | BOQ-PKG-10-00800 | PKG-10 | INV-PKG-10-016-06770 | 277.91 | 141376.75 | 7068.84 | Paid | 134307.91 | 2024-Q3
EXP-000306 | 2024-07-05 | BOQ-PKG-06-00306 | PKG-06 | INV-PKG-06-027-00306 | 229.34 | 82614.58 | 4130.73 | Paid | 78483.85 | 2024-Q3
EXP-000836 | 2024-07-05 | BOQ-PKG-06-00836 | PKG-06 | INV-PKG-06-032-00836 | 321.84 | 95080.82 | 4754.04 | Approved Pending Payment | 90326.78 | 2024-Q3
EXP-001931 | 2024-07-05 | BOQ-PKG-01-01931 | PKG-01 | INV-PKG-01-007-01931 | 58.57 | 51385.27 | 2569.26 | Paid | 48816.01 | 2024-Q3
EXP-002358 | 2024-07-05 | BOQ-PKG-08-00368 | PKG-08 | INV-PKG-08-014-02358 | 286.23 | 139465.53 | 6973.28 | Paid | 132492.25 | 2024-Q3
EXP-002830 | 2024-07-05 | BOQ-PKG-10-00840 | PKG-10 | INV-PKG-10-031-02830 | 310.56 | 209170.93 | 10458.55 | Approved Pending Payment | 198712.38 | 2024-Q3
EXP-005016 | 2024-07-05 | BOQ-PKG-06-01036 | PKG-06 | INV-PKG-06-012-05016 | 256.61 | 29104.67 | 1455.23 | Approved Pending Payment | 27649.44 | 2024-Q3
EXP-005440 | 2024-07-05 | BOQ-PKG-10-01460 | PKG-10 | INV-PKG-10-016-05440 | 221.99 | 118742.2 | 5937.11 | Approved Pending Payment | 112805.09 | 2024-Q3
EXP-005965 | 2024-07-05 | BOQ-PKG-05-01985 | PKG-05 | INV-PKG-05-016-05965 | 332.25 | 61656.76 | 3082.84 | Paid | 58573.92 | 2024-Q3
EXP-005997 | 2024-07-05 | BOQ-PKG-07-00027 | PKG-07 | INV-PKG-07-013-05997 | 172.49 | 178501.97 | 8925.1 | Under Review | 169576.87 | 2024-Q3
EXP-000620 | 2024-07-06 | BOQ-PKG-10-00620 | PKG-10 | INV-PKG-10-026-00620 | 260.42 | 143583.89 | 7179.19 | Approved Pending Payment | 136404.7 | 2024-Q3
EXP-001500 | 2024-07-06 | BOQ-PKG-10-01500 | PKG-10 | INV-PKG-10-031-01500 | 276.39 | 157192.59 | 7859.63 | Approved Pending Payment | 149332.96 | 2024-Q3
EXP-001871 | 2024-07-06 | BOQ-PKG-01-01871 | PKG-01 | INV-PKG-01-017-01871 | 143.5 | 122528.65 | 6126.43 | Paid | 116402.22 | 2024-Q3
EXP-004832 | 2024-07-06 | BOQ-PKG-02-00852 | PKG-02 | INV-PKG-02-003-04832 | 278.05 | 65952.66 | 3297.63 | Paid | 62655.03 | 2024-Q3
EXP-006543 | 2024-07-06 | BOQ-PKG-03-00573 | PKG-03 | INV-PKG-03-034-06543 | 155.59 | 165061.2 | 8253.06 | Paid | 156808.14 | 2024-Q3
EXP-000337 | 2024-07-07 | BOQ-PKG-07-00337 | PKG-07 | INV-PKG-07-023-00337 | 52.01 | 176790.86 | 8839.54 | Paid | 167951.32 | 2024-Q3
EXP-000646 | 2024-07-07 | BOQ-PKG-06-00646 | PKG-06 | INV-PKG-06-017-00646 | 117.48 | 98947.73 | 4947.39 | Approved Pending Payment | 94000.34 | 2024-Q3
EXP-001801 | 2024-07-07 | BOQ-PKG-01-01801 | PKG-01 | INV-PKG-01-017-01801 | 232.61 | 42713.55 | 2135.68 | Paid | 40577.87 | 2024-Q3
EXP-001992 | 2024-07-07 | BOQ-PKG-02-00002 | PKG-02 | INV-PKG-02-033-01992 | 307.19 | 165549 | 8277.45 | Under Review | 157271.55 | 2024-Q3
EXP-002119 | 2024-07-07 | BOQ-PKG-09-00129 | PKG-09 | INV-PKG-09-020-02119 | 423.93 | 126738.09 | 6336.9 | Paid | 120401.19 | 2024-Q3
EXP-004798 | 2024-07-07 | BOQ-PKG-08-00818 | PKG-08 | INV-PKG-08-004-04798 | 265.34 | 101363.4 | 5068.17 | Under Review | 96295.23 | 2024-Q3
EXP-005568 | 2024-07-07 | BOQ-PKG-08-01588 | PKG-08 | INV-PKG-08-004-05568 | 283.46 | 205461.81 | 10273.09 | Paid | 195188.72 | 2024-Q3
EXP-006756 | 2024-07-07 | BOQ-PKG-06-00786 | PKG-06 | INV-PKG-06-002-06756 | 211.86 | 87521.27 | 4376.06 | Paid | 83145.21 | 2024-Q3
EXP-001345 | 2024-07-08 | BOQ-PKG-05-01345 | PKG-05 | INV-PKG-05-016-01345 | 202.17 | 56957.26 | 2847.86 | Paid | 54109.4 | 2024-Q3
EXP-001990 | 2024-07-08 | BOQ-PKG-10-01990 | PKG-10 | INV-PKG-10-031-01990 | 22.33 | 31453.47 | 1572.67 | Paid | 29880.8 | 2024-Q3
EXP-002132 | 2024-07-08 | BOQ-PKG-02-00142 | PKG-02 | INV-PKG-02-033-02132 | 126.58 | 101865.73 | 5093.29 | Paid | 96772.44 | 2024-Q3
EXP-002896 | 2024-07-08 | BOQ-PKG-06-00906 | PKG-06 | INV-PKG-06-027-02896 | 105.29 | 147058.94 | 7352.95 | Paid | 139705.99 | 2024-Q3
EXP-003954 | 2024-07-08 | BOQ-PKG-04-01964 | PKG-04 | INV-PKG-04-035-03954 | 33.11 | 196230.86 | 9811.54 | Paid | 186419.32 | 2024-Q3
EXP-004607 | 2024-07-08 | BOQ-PKG-07-00627 | PKG-07 | INV-PKG-07-023-04607 | 142.18 | 115803.02 | 5790.15 | Under Review | 110012.87 | 2024-Q3
EXP-005133 | 2024-07-08 | BOQ-PKG-03-01153 | PKG-03 | INV-PKG-03-024-05133 | 409.42 | 103440.78 | 5172.04 | Paid | 98268.74 | 2024-Q3
EXP-000083 | 2024-07-09 | BOQ-PKG-03-00083 | PKG-03 | INV-PKG-03-014-00083 | 245.87 | 139331.52 | 6966.58 | Under Review | 132364.94 | 2024-Q3
EXP-000907 | 2024-07-09 | BOQ-PKG-07-00907 | PKG-07 | INV-PKG-07-033-00907 | 295 | 159301.26 | 7965.06 | Paid | 151336.2 | 2024-Q3
EXP-001200 | 2024-07-09 | BOQ-PKG-10-01200 | PKG-10 | INV-PKG-10-011-01200 | 220.98 | 185257.89 | 9262.89 | Paid | 175995 | 2024-Q3
EXP-001592 | 2024-07-09 | BOQ-PKG-02-01592 | PKG-02 | INV-PKG-02-018-01592 | 357.54 | 98386.72 | 4919.34 | Paid | 93467.38 | 2024-Q3
EXP-001952 | 2024-07-09 | BOQ-PKG-02-01952 | PKG-02 | INV-PKG-02-028-01952 | 409.74 | 173808.08 | 8690.4 | Under Review | 165117.68 | 2024-Q3
EXP-002922 | 2024-07-09 | BOQ-PKG-02-00932 | PKG-02 | INV-PKG-02-018-02922 | 325.03 | 151648.37 | 7582.42 | Paid | 144065.95 | 2024-Q3
EXP-003230 | 2024-07-09 | BOQ-PKG-10-01240 | PKG-10 | INV-PKG-10-011-03230 | 314.41 | 36504.16 | 1825.21 | Paid | 34678.95 | 2024-Q3
EXP-004268 | 2024-07-09 | BOQ-PKG-08-00288 | PKG-08 | INV-PKG-08-034-04268 | 61.49 | 70183.81 | 3509.19 | Paid | 66674.62 | 2024-Q3
EXP-004308 | 2024-07-09 | BOQ-PKG-08-00328 | PKG-08 | INV-PKG-08-004-04308 | 431.38 | 132881.55 | 6644.08 | Approved Pending Payment | 126237.47 | 2024-Q3
EXP-005586 | 2024-07-09 | BOQ-PKG-06-01606 | PKG-06 | INV-PKG-06-022-05586 | 424.2 | 109348.06 | 5467.4 | Paid | 103880.66 | 2024-Q3
EXP-006772 | 2024-07-09 | BOQ-PKG-02-00802 | PKG-02 | INV-PKG-02-018-06772 | 146.67 | 189145.67 | 9457.28 | Paid | 179688.39 | 2024-Q3
EXP-006913 | 2024-07-09 | BOQ-PKG-03-00943 | PKG-03 | INV-PKG-03-019-06913 | 27.16 | 175522.28 | 8776.11 | Paid | 166746.17 | 2024-Q3
EXP-000044 | 2024-07-10 | BOQ-PKG-04-00044 | PKG-04 | INV-PKG-04-010-00044 | 16.43 | 76721.06 | 3836.05 | Paid | 72885.01 | 2024-Q3
EXP-001113 | 2024-07-10 | BOQ-PKG-03-01113 | PKG-03 | INV-PKG-03-029-01113 | 158.95 | 88692.13 | 4434.61 | Paid | 84257.52 | 2024-Q3
EXP-001624 | 2024-07-10 | BOQ-PKG-04-01624 | PKG-04 | INV-PKG-04-015-01624 | 83.86 | 190498.5 | 9524.93 | Paid | 180973.57 | 2024-Q3
EXP-001925 | 2024-07-10 | BOQ-PKG-05-01925 | PKG-05 | INV-PKG-05-001-01925 | 93.29 | 112078.07 | 5603.9 | Paid | 106474.17 | 2024-Q3
EXP-002021 | 2024-07-10 | BOQ-PKG-01-00031 | PKG-01 | INV-PKG-01-027-02021 | 361.28 | 200860.96 | 10043.05 | Paid | 190817.91 | 2024-Q3
EXP-002251 | 2024-07-10 | BOQ-PKG-01-00261 | PKG-01 | INV-PKG-01-012-02251 | 280.75 | 194665.86 | 9733.29 | Paid | 184932.57 | 2024-Q3
EXP-002279 | 2024-07-10 | BOQ-PKG-09-00289 | PKG-09 | INV-PKG-09-005-02279 | 282.86 | 150634.97 | 7531.75 | Paid | 143103.22 | 2024-Q3
EXP-002471 | 2024-07-10 | BOQ-PKG-01-00481 | PKG-01 | INV-PKG-01-022-02471 | 288.44 | 168780.89 | 8439.04 | Paid | 160341.85 | 2024-Q3
EXP-002978 | 2024-07-10 | BOQ-PKG-08-00988 | PKG-08 | INV-PKG-08-004-02978 | 109.8 | 166518 | 8325.9 | Paid | 158192.1 | 2024-Q3
EXP-005424 | 2024-07-10 | BOQ-PKG-04-01444 | PKG-04 | INV-PKG-04-035-05424 | 440.72 | 95125.04 | 4756.25 | Paid | 90368.79 | 2024-Q3
EXP-005835 | 2024-07-10 | BOQ-PKG-05-01855 | PKG-05 | INV-PKG-05-026-05835 | 66.68 | 63162.91 | 3158.15 | Under Review | 60004.76 | 2024-Q3
EXP-001147 | 2024-07-11 | BOQ-PKG-07-01147 | PKG-07 | INV-PKG-07-028-01147 | 387.55 | 70519.41 | 3525.97 | Paid | 66993.44 | 2024-Q3
EXP-001289 | 2024-07-11 | BOQ-PKG-09-01289 | PKG-09 | INV-PKG-09-030-01289 | 204.46 | 134315.52 | 6715.78 | Approved Pending Payment | 127599.74 | 2024-Q3
EXP-002643 | 2024-07-11 | BOQ-PKG-03-00653 | PKG-03 | INV-PKG-03-019-02643 | 324.12 | 89450.34 | 4472.52 | Paid | 84977.82 | 2024-Q3
EXP-003018 | 2024-07-11 | BOQ-PKG-08-01028 | PKG-08 | INV-PKG-08-009-03018 | 34.62 | 58762.88 | 2938.14 | Paid | 55824.74 | 2024-Q3
EXP-003530 | 2024-07-11 | BOQ-PKG-10-01540 | PKG-10 | INV-PKG-10-031-03530 | 373.75 | 186340.04 | 9317 | Under Review | 177023.04 | 2024-Q3
EXP-004698 | 2024-07-11 | BOQ-PKG-08-00718 | PKG-08 | INV-PKG-08-009-04698 | 54.74 | 149364.81 | 7468.24 | Paid | 141896.57 | 2024-Q3
EXP-000513 | 2024-07-12 | BOQ-PKG-03-00513 | PKG-03 | INV-PKG-03-024-00513 | 363.21 | 200842.2 | 10042.11 | Paid | 190800.09 | 2024-Q3
EXP-001108 | 2024-07-12 | BOQ-PKG-08-01108 | PKG-08 | INV-PKG-08-024-01108 | 213.9 | 158796.08 | 7939.8 | Paid | 150856.28 | 2024-Q3
EXP-002254 | 2024-07-12 | BOQ-PKG-04-00264 | PKG-04 | INV-PKG-04-015-02254 | 364.57 | 74340.42 | 3717.02 | Paid | 70623.4 | 2024-Q3
EXP-003034 | 2024-07-12 | BOQ-PKG-04-01044 | PKG-04 | INV-PKG-04-025-03034 | 133.81 | 185270.18 | 9263.51 | Under Review | 176006.67 | 2024-Q3
EXP-004380 | 2024-07-12 | BOQ-PKG-10-00400 | PKG-10 | INV-PKG-10-006-04380 | 347.39 | 89044.73 | 4452.24 | Paid | 84592.49 | 2024-Q3
EXP-005415 | 2024-07-12 | BOQ-PKG-05-01435 | PKG-05 | INV-PKG-05-026-05415 | 160.03 | 197147.52 | 9857.38 | Paid | 187290.14 | 2024-Q3
EXP-005420 | 2024-07-12 | BOQ-PKG-10-01440 | PKG-10 | INV-PKG-10-031-05420 | 246.07 | 209081.18 | 10454.06 | Paid | 198627.12 | 2024-Q3
EXP-005715 | 2024-07-12 | BOQ-PKG-05-01735 | PKG-05 | INV-PKG-05-011-05715 | 372.07 | 89088.36 | 4454.42 | Paid | 84633.94 | 2024-Q3
EXP-003236 | 2024-07-13 | BOQ-PKG-06-01246 | PKG-06 | INV-PKG-06-017-03236 | 209.17 | 135776.06 | 6788.8 | Paid | 128987.26 | 2024-Q3
EXP-003444 | 2024-07-13 | BOQ-PKG-04-01454 | PKG-04 | INV-PKG-04-015-03444 | 392.93 | 168265.68 | 8413.28 | Paid | 159852.4 | 2024-Q3
EXP-004234 | 2024-07-13 | BOQ-PKG-04-00254 | PKG-04 | INV-PKG-04-035-04234 | 102.76 | 195847.4 | 9792.37 | Paid | 186055.03 | 2024-Q3
EXP-000496 | 2024-07-14 | BOQ-PKG-06-00496 | PKG-06 | INV-PKG-06-007-00496 | 278.87 | 96105.96 | 4805.3 | Paid | 91300.66 | 2024-Q3
EXP-000845 | 2024-07-14 | BOQ-PKG-05-00845 | PKG-05 | INV-PKG-05-006-00845 | 186.3 | 196965.48 | 9848.27 | Paid | 187117.21 | 2024-Q3
EXP-003412 | 2024-07-14 | BOQ-PKG-02-01422 | PKG-02 | INV-PKG-02-018-03412 | 231.19 | 63249.01 | 3162.45 | Paid | 60086.56 | 2024-Q3
EXP-003473 | 2024-07-14 | BOQ-PKG-03-01483 | PKG-03 | INV-PKG-03-009-03473 | 286.48 | 127890.86 | 6394.54 | Paid | 121496.32 | 2024-Q3
EXP-003601 | 2024-07-14 | BOQ-PKG-01-01611 | PKG-01 | INV-PKG-01-032-03601 | 192.14 | 135110.1 | 6755.51 | Paid | 128354.59 | 2024-Q3
EXP-003682 | 2024-07-14 | BOQ-PKG-02-01692 | PKG-02 | INV-PKG-02-008-03682 | 299.02 | 71660.6 | 3583.03 | Paid | 68077.57 | 2024-Q3
EXP-003870 | 2024-07-14 | BOQ-PKG-10-01880 | PKG-10 | INV-PKG-10-021-03870 | 368.88 | 148699.83 | 7434.99 | Paid | 141264.84 | 2024-Q3
EXP-005008 | 2024-07-14 | BOQ-PKG-08-01028 | PKG-08 | INV-PKG-08-004-05008 | 262.2 | 120752.49 | 6037.62 | Paid | 114714.87 | 2024-Q3
EXP-005971 | 2024-07-14 | BOQ-PKG-01-00001 | PKG-01 | INV-PKG-01-022-05971 | 253.52 | 115284.63 | 5764.23 | Paid | 109520.4 | 2024-Q3
EXP-000176 | 2024-07-15 | BOQ-PKG-06-00176 | PKG-06 | INV-PKG-06-002-00176 | 69.98 | 205598.67 | 10279.93 | Under Review | 195318.74 | 2024-Q3
EXP-000289 | 2024-07-15 | BOQ-PKG-09-00289 | PKG-09 | INV-PKG-09-010-00289 | 142.71 | 204530.31 | 10226.52 | Paid | 194303.79 | 2024-Q3
EXP-000713 | 2024-07-15 | BOQ-PKG-03-00713 | PKG-03 | INV-PKG-03-014-00713 | 32.24 | 139414.09 | 6970.7 | Paid | 132443.39 | 2024-Q3
EXP-000723 | 2024-07-15 | BOQ-PKG-03-00723 | PKG-03 | INV-PKG-03-024-00723 | 378.8 | 164213.16 | 8210.66 | Paid | 156002.5 | 2024-Q3
EXP-001392 | 2024-07-15 | BOQ-PKG-02-01392 | PKG-02 | INV-PKG-02-028-01392 | 407.47 | 58663.05 | 2933.15 | Paid | 55729.9 | 2024-Q3
EXP-001711 | 2024-07-15 | BOQ-PKG-01-01711 | PKG-01 | INV-PKG-01-032-01711 | 295.71 | 33467.03 | 1673.35 | Paid | 31793.68 | 2024-Q3
EXP-001823 | 2024-07-15 | BOQ-PKG-03-01823 | PKG-03 | INV-PKG-03-004-01823 | 163.46 | 53932.57 | 2696.63 | Under Review | 51235.94 | 2024-Q3
EXP-002851 | 2024-07-15 | BOQ-PKG-01-00861 | PKG-01 | INV-PKG-01-017-02851 | 267.56 | 160008.13 | 8000.41 | Paid | 152007.72 | 2024-Q3
EXP-002937 | 2024-07-15 | BOQ-PKG-07-00947 | PKG-07 | INV-PKG-07-033-02937 | 424.8 | 99111 | 4955.55 | Paid | 94155.45 | 2024-Q3
EXP-003293 | 2024-07-15 | BOQ-PKG-03-01303 | PKG-03 | INV-PKG-03-004-03293 | 124.14 | 77672.24 | 3883.61 | Paid | 73788.63 | 2024-Q3
EXP-004436 | 2024-07-15 | BOQ-PKG-06-00456 | PKG-06 | INV-PKG-06-027-04436 | 344.21 | 36708.71 | 1835.44 | Paid | 34873.27 | 2024-Q3
EXP-004517 | 2024-07-15 | BOQ-PKG-07-00537 | PKG-07 | INV-PKG-07-003-04517 | 193.05 | 144687.64 | 7234.38 | Paid | 137453.26 | 2024-Q3
EXP-004786 | 2024-07-15 | BOQ-PKG-06-00806 | PKG-06 | INV-PKG-06-027-04786 | 52.38 | 82094.17 | 4104.71 | Disputed | 77989.46 | 2024-Q3
EXP-005541 | 2024-07-15 | BOQ-PKG-01-01561 | PKG-01 | INV-PKG-01-012-05541 | 114.76 | 167821.74 | 8391.09 | Paid | 159430.65 | 2024-Q3
EXP-005970 | 2024-07-15 | BOQ-PKG-10-01990 | PKG-10 | INV-PKG-10-021-05970 | 285.59 | 102210.34 | 5110.52 | Paid | 97099.82 | 2024-Q3
EXP-006349 | 2024-07-15 | BOQ-PKG-09-00379 | PKG-09 | INV-PKG-09-015-06349 | 387.17 | 82204.83 | 4110.24 | Paid | 78094.59 | 2024-Q3
EXP-000259 | 2024-07-16 | BOQ-PKG-09-00259 | PKG-09 | INV-PKG-09-015-00259 | 62.44 | 81296.6 | 4064.83 | Paid | 77231.77 | 2024-Q3
EXP-000470 | 2024-07-16 | BOQ-PKG-10-00470 | PKG-10 | INV-PKG-10-016-00470 | 428.08 | 99985.2 | 4999.26 | Paid | 94985.94 | 2024-Q3
EXP-000574 | 2024-07-16 | BOQ-PKG-04-00574 | PKG-04 | INV-PKG-04-015-00574 | 190.25 | 108579.26 | 5428.96 | Paid | 103150.3 | 2024-Q3
EXP-001491 | 2024-07-16 | BOQ-PKG-01-01491 | PKG-01 | INV-PKG-01-022-01491 | 284.18 | 206230.8 | 10311.54 | Approved Pending Payment | 195919.26 | 2024-Q3
EXP-003120 | 2024-07-16 | BOQ-PKG-10-01130 | PKG-10 | INV-PKG-10-006-03120 | 255.24 | 37419.2 | 1870.96 | Paid | 35548.24 | 2024-Q3
EXP-003475 | 2024-07-16 | BOQ-PKG-05-01485 | PKG-05 | INV-PKG-05-011-03475 | 308.24 | 194517.71 | 9725.89 | Paid | 184791.82 | 2024-Q3
EXP-004344 | 2024-07-16 | BOQ-PKG-04-00364 | PKG-04 | INV-PKG-04-005-04344 | 314.06 | 125097.42 | 6254.87 | Approved Pending Payment | 118842.55 | 2024-Q3
EXP-006144 | 2024-07-16 | BOQ-PKG-04-00174 | PKG-04 | INV-PKG-04-020-06144 | 60.15 | 145740 | 7287 | Disputed | 138453 | 2024-Q3
EXP-006481 | 2024-07-16 | BOQ-PKG-01-00511 | PKG-01 | INV-PKG-01-007-06481 | 190.76 | 172951.9 | 8647.59 | Paid | 164304.31 | 2024-Q3
EXP-006668 | 2024-07-16 | BOQ-PKG-08-00698 | PKG-08 | INV-PKG-08-019-06668 | 337.6 | 47455.48 | 2372.77 | Approved Pending Payment | 45082.71 | 2024-Q3
EXP-000601 | 2024-07-17 | BOQ-PKG-01-00601 | PKG-01 | INV-PKG-01-007-00601 | 243.79 | 203687.96 | 10184.4 | Approved Pending Payment | 193503.56 | 2024-Q3
EXP-000670 | 2024-07-17 | BOQ-PKG-10-00670 | PKG-10 | INV-PKG-10-006-00670 | 100.48 | 157820.72 | 7891.04 | Paid | 149929.68 | 2024-Q3
EXP-001282 | 2024-07-17 | BOQ-PKG-02-01282 | PKG-02 | INV-PKG-02-023-01282 | 63.05 | 212041.08 | 10602.05 | Under Review | 201439.03 | 2024-Q3
EXP-001325 | 2024-07-17 | BOQ-PKG-05-01325 | PKG-05 | INV-PKG-05-031-01325 | 97.73 | 152159.81 | 7607.99 | Paid | 144551.82 | 2024-Q3
EXP-002179 | 2024-07-17 | BOQ-PKG-09-00189 | PKG-09 | INV-PKG-09-010-02179 | 189.92 | 97485.37 | 4874.27 | Approved Pending Payment | 92611.1 | 2024-Q3
EXP-004331 | 2024-07-17 | BOQ-PKG-01-00351 | PKG-01 | INV-PKG-01-027-04331 | 232.09 | 106203.87 | 5310.19 | Paid | 100893.68 | 2024-Q3
EXP-005534 | 2024-07-17 | BOQ-PKG-04-01554 | PKG-04 | INV-PKG-04-005-05534 | 192.76 | 156559.93 | 7828 | Paid | 148731.93 | 2024-Q3
EXP-005635 | 2024-07-17 | BOQ-PKG-05-01655 | PKG-05 | INV-PKG-05-001-05635 | 315.73 | 190282.5 | 9514.12 | Paid | 180768.38 | 2024-Q3
EXP-005857 | 2024-07-17 | BOQ-PKG-07-01877 | PKG-07 | INV-PKG-07-013-05857 | 413.51 | 62311.38 | 3115.57 | Paid | 59195.81 | 2024-Q3
EXP-005983 | 2024-07-17 | BOQ-PKG-03-00013 | PKG-03 | INV-PKG-03-034-05983 | 249 | 174513.11 | 8725.66 | Paid | 165787.45 | 2024-Q3
EXP-006901 | 2024-07-17 | BOQ-PKG-01-00931 | PKG-01 | INV-PKG-01-007-06901 | 107.36 | 168608.63 | 8430.43 | Approved Pending Payment | 160178.2 | 2024-Q3
EXP-001770 | 2024-07-18 | BOQ-PKG-10-01770 | PKG-10 | INV-PKG-10-021-01770 | 345.23 | 28049.46 | 1402.47 | Paid | 26646.99 | 2024-Q3
EXP-002000 | 2024-07-18 | BOQ-PKG-10-00010 | PKG-10 | INV-PKG-10-006-02000 | 271.86 | 82653.9 | 4132.7 | Paid | 78521.2 | 2024-Q3
EXP-003114 | 2024-07-18 | BOQ-PKG-04-01124 | PKG-04 | INV-PKG-04-035-03114 | 276.66 | 105472.93 | 5273.65 | Approved Pending Payment | 100199.28 | 2024-Q3
EXP-004283 | 2024-07-18 | BOQ-PKG-03-00303 | PKG-03 | INV-PKG-03-014-04283 | 151.6 | 109314.62 | 5465.73 | Paid | 103848.89 | 2024-Q3
EXP-004751 | 2024-07-18 | BOQ-PKG-01-00771 | PKG-01 | INV-PKG-01-027-04751 | 124.42 | 172540.31 | 8627.02 | Approved Pending Payment | 163913.29 | 2024-Q3
EXP-005403 | 2024-07-18 | BOQ-PKG-03-01423 | PKG-03 | INV-PKG-03-014-05403 | 437.43 | 180438.35 | 9021.92 | Under Review | 171416.43 | 2024-Q3
EXP-006024 | 2024-07-18 | BOQ-PKG-04-00054 | PKG-04 | INV-PKG-04-005-06024 | 423.05 | 176433.14 | 8821.66 | Paid | 167611.48 | 2024-Q3
EXP-006562 | 2024-07-18 | BOQ-PKG-02-00592 | PKG-02 | INV-PKG-02-018-06562 | 192.16 | 190182.75 | 9509.14 | Approved Pending Payment | 180673.61 | 2024-Q3
EXP-006748 | 2024-07-18 | BOQ-PKG-08-00778 | PKG-08 | INV-PKG-08-029-06748 | 219.05 | 60827.29 | 3041.36 | Paid | 57785.93 | 2024-Q3
EXP-000689 | 2024-07-19 | BOQ-PKG-09-00689 | PKG-09 | INV-PKG-09-025-00689 | 312.08 | 96186.88 | 4809.34 | Paid | 91377.54 | 2024-Q3
EXP-003167 | 2024-07-19 | BOQ-PKG-07-01177 | PKG-07 | INV-PKG-07-018-03167 | 448.11 | 188337.34 | 9416.87 | Paid | 178920.47 | 2024-Q3
EXP-005617 | 2024-07-19 | BOQ-PKG-07-01637 | PKG-07 | INV-PKG-07-018-05617 | 209.78 | 144450.5 | 7222.52 | Paid | 137227.98 | 2024-Q3
EXP-005881 | 2024-07-19 | BOQ-PKG-01-01901 | PKG-01 | INV-PKG-01-002-05881 | 85.63 | 41436.11 | 2071.81 | Paid | 39364.3 | 2024-Q3
EXP-006203 | 2024-07-19 | BOQ-PKG-03-00233 | PKG-03 | INV-PKG-03-009-06203 | 346.7 | 81679.36 | 4083.97 | Paid | 77595.39 | 2024-Q3
EXP-000215 | 2024-07-20 | BOQ-PKG-05-00215 | PKG-05 | INV-PKG-05-006-00215 | 363.3 | 56718.55 | 2835.93 | Paid | 53882.62 | 2024-Q3
EXP-000935 | 2024-07-20 | BOQ-PKG-05-00935 | PKG-05 | INV-PKG-05-026-00935 | 188.68 | 66903.15 | 3345.16 | Paid | 63557.99 | 2024-Q3
EXP-003959 | 2024-07-20 | BOQ-PKG-09-01969 | PKG-09 | INV-PKG-09-005-03959 | 151.69 | 136278.84 | 6813.94 | Paid | 129464.9 | 2024-Q3
EXP-006186 | 2024-07-20 | BOQ-PKG-06-00216 | PKG-06 | INV-PKG-06-027-06186 | 365.69 | 54062.06 | 2703.1 | Paid | 51358.96 | 2024-Q3
EXP-000125 | 2024-07-21 | BOQ-PKG-05-00125 | PKG-05 | INV-PKG-05-021-00125 | 353.61 | 191737.4 | 9586.87 | Approved Pending Payment | 182150.53 | 2024-Q3
EXP-000599 | 2024-07-21 | BOQ-PKG-09-00599 | PKG-09 | INV-PKG-09-005-00599 | 272.75 | 35028.4 | 1751.42 | Paid | 33276.98 | 2024-Q3
EXP-001132 | 2024-07-21 | BOQ-PKG-02-01132 | PKG-02 | INV-PKG-02-013-01132 | 421.68 | 27262.74 | 1363.14 | Paid | 25899.6 | 2024-Q3
EXP-002800 | 2024-07-21 | BOQ-PKG-10-00810 | PKG-10 | INV-PKG-10-001-02800 | 245.09 | 57826.63 | 2891.33 | Approved Pending Payment | 54935.3 | 2024-Q3
EXP-005766 | 2024-07-21 | BOQ-PKG-06-01786 | PKG-06 | INV-PKG-06-027-05766 | 154.3 | 168249.17 | 8412.46 | Paid | 159836.71 | 2024-Q3
EXP-005840 | 2024-07-21 | BOQ-PKG-10-01860 | PKG-10 | INV-PKG-10-031-05840 | 328.95 | 27524.74 | 1376.24 | Paid | 26148.5 | 2024-Q3
EXP-005896 | 2024-07-21 | BOQ-PKG-06-01916 | PKG-06 | INV-PKG-06-017-05896 | 54 | 178413.56 | 8920.68 | Paid | 169492.88 | 2024-Q3
EXP-000294 | 2024-07-22 | BOQ-PKG-04-00294 | PKG-04 | INV-PKG-04-015-00294 | 159.78 | 140233.49 | 7011.67 | Paid | 133221.82 | 2024-Q3
EXP-000891 | 2024-07-22 | BOQ-PKG-01-00891 | PKG-01 | INV-PKG-01-017-00891 | 266.53 | 36914.26 | 1845.71 | Disputed | 35068.55 | 2024-Q3
EXP-001040 | 2024-07-22 | BOQ-PKG-10-01040 | PKG-10 | INV-PKG-10-026-01040 | 108.18 | 173778.51 | 8688.93 | Paid | 165089.58 | 2024-Q3
EXP-001462 | 2024-07-22 | BOQ-PKG-02-01462 | PKG-02 | INV-PKG-02-028-01462 | 426.54 | 87440.09 | 4372 | Paid | 83068.09 | 2024-Q3
EXP-004051 | 2024-07-22 | BOQ-PKG-01-00071 | PKG-01 | INV-PKG-01-027-04051 | 182.9 | 53900.09 | 2695 | Paid | 51205.09 | 2024-Q3
EXP-004530 | 2024-07-22 | BOQ-PKG-10-00550 | PKG-10 | INV-PKG-10-016-04530 | 394.83 | 149771.63 | 7488.58 | Paid | 142283.05 | 2024-Q3
EXP-006799 | 2024-07-22 | BOQ-PKG-09-00829 | PKG-09 | INV-PKG-09-010-06799 | 158.76 | 173597.06 | 8679.85 | Approved Pending Payment | 164917.21 | 2024-Q3
EXP-000771 | 2024-07-23 | BOQ-PKG-01-00771 | PKG-01 | INV-PKG-01-002-00771 | 188.99 | 64279.77 | 3213.99 | Paid | 61065.78 | 2024-Q3
EXP-000801 | 2024-07-23 | BOQ-PKG-01-00801 | PKG-01 | INV-PKG-01-032-00801 | 98.9 | 149103.53 | 7455.18 | Paid | 141648.35 | 2024-Q3
EXP-004023 | 2024-07-23 | BOQ-PKG-03-00043 | PKG-03 | INV-PKG-03-034-04023 | 209.73 | 73191.49 | 3659.57 | Approved Pending Payment | 69531.92 | 2024-Q3
EXP-004789 | 2024-07-23 | BOQ-PKG-09-00809 | PKG-09 | INV-PKG-09-030-04789 | 311.42 | 181423.9 | 9071.2 | Disputed | 172352.7 | 2024-Q3
EXP-005005 | 2024-07-23 | BOQ-PKG-05-01025 | PKG-05 | INV-PKG-05-001-05005 | 41.2 | 85195.2 | 4259.76 | Paid | 80935.44 | 2024-Q3
EXP-005353 | 2024-07-23 | BOQ-PKG-03-01373 | PKG-03 | INV-PKG-03-034-05353 | 367.86 | 118973.43 | 5948.67 | Paid | 113024.76 | 2024-Q3
EXP-005652 | 2024-07-23 | BOQ-PKG-02-01672 | PKG-02 | INV-PKG-02-018-05652 | 53.25 | 63223.86 | 3161.19 | Approved Pending Payment | 60062.67 | 2024-Q3
EXP-006038 | 2024-07-23 | BOQ-PKG-08-00068 | PKG-08 | INV-PKG-08-019-06038 | 117.42 | 117175.39 | 5858.77 | Paid | 111316.62 | 2024-Q3
EXP-000505 | 2024-07-24 | BOQ-PKG-05-00505 | PKG-05 | INV-PKG-05-016-00505 | 40.63 | 108204.77 | 5410.24 | Paid | 102794.53 | 2024-Q3
EXP-000866 | 2024-07-24 | BOQ-PKG-06-00866 | PKG-06 | INV-PKG-06-027-00866 | 84.49 | 86443.54 | 4322.18 | Paid | 82121.36 | 2024-Q3
EXP-002480 | 2024-07-24 | BOQ-PKG-10-00490 | PKG-10 | INV-PKG-10-031-02480 | 73.83 | 114135.57 | 5706.78 | Under Review | 108428.79 | 2024-Q3
EXP-003213 | 2024-07-24 | BOQ-PKG-03-01223 | PKG-03 | INV-PKG-03-029-03213 | 339.66 | 153805.88 | 7690.29 | Paid | 146115.59 | 2024-Q3
EXP-005441 | 2024-07-24 | BOQ-PKG-01-01461 | PKG-01 | INV-PKG-01-017-05441 | 269.76 | 27567.03 | 1378.35 | Approved Pending Payment | 26188.68 | 2024-Q3
EXP-005757 | 2024-07-24 | BOQ-PKG-07-01777 | PKG-07 | INV-PKG-07-018-05757 | 276.25 | 41545.61 | 2077.28 | Paid | 39468.33 | 2024-Q3
EXP-006389 | 2024-07-24 | BOQ-PKG-09-00419 | PKG-09 | INV-PKG-09-020-06389 | 109.43 | 103021.71 | 5151.09 | Paid | 97870.62 | 2024-Q3
EXP-006882 | 2024-07-24 | BOQ-PKG-02-00912 | PKG-02 | INV-PKG-02-023-06882 | 5.26 | 202916.28 | 10145.81 | Paid | 192770.47 | 2024-Q3
EXP-000079 | 2024-07-25 | BOQ-PKG-09-00079 | PKG-09 | INV-PKG-09-010-00079 | 177.08 | 33219.79 | 1660.99 | Paid | 31558.8 | 2024-Q3
EXP-000851 | 2024-07-25 | BOQ-PKG-01-00851 | PKG-01 | INV-PKG-01-012-00851 | 206.08 | 173961.06 | 8698.05 | Paid | 165263.01 | 2024-Q3
EXP-000967 | 2024-07-25 | BOQ-PKG-07-00967 | PKG-07 | INV-PKG-07-023-00967 | 183.87 | 179658.85 | 8982.94 | Paid | 170675.91 | 2024-Q3
EXP-003452 | 2024-07-25 | BOQ-PKG-02-01462 | PKG-02 | INV-PKG-02-023-03452 | 311.95 | 25543.61 | 1277.18 | Paid | 24266.43 | 2024-Q3
EXP-004118 | 2024-07-25 | BOQ-PKG-08-00138 | PKG-08 | INV-PKG-08-024-04118 | 163.63 | 214710.73 | 10735.54 | Paid | 203975.19 | 2024-Q3
EXP-005929 | 2024-07-25 | BOQ-PKG-09-01949 | PKG-09 | INV-PKG-09-015-05929 | 127.7 | 24587.12 | 1229.36 | Paid | 23357.76 | 2024-Q3
EXP-006175 | 2024-07-25 | BOQ-PKG-05-00205 | PKG-05 | INV-PKG-05-016-06175 | 247.66 | 105347.81 | 5267.39 | Paid | 100080.42 | 2024-Q3
EXP-006920 | 2024-07-25 | BOQ-PKG-10-00950 | PKG-10 | INV-PKG-10-026-06920 | 68.94 | 141092.79 | 7054.64 | Paid | 134038.15 | 2024-Q3
EXP-000181 | 2024-07-26 | BOQ-PKG-01-00181 | PKG-01 | INV-PKG-01-007-00181 | 213.72 | 169136.53 | 8456.83 | Paid | 160679.7 | 2024-Q3
EXP-000257 | 2024-07-26 | BOQ-PKG-07-00257 | PKG-07 | INV-PKG-07-013-00257 | 372.78 | 123597.15 | 6179.86 | Disputed | 117417.29 | 2024-Q3
EXP-002060 | 2024-07-26 | BOQ-PKG-10-00070 | PKG-10 | INV-PKG-10-031-02060 | 88.24 | 117932.55 | 5896.63 | Paid | 112035.92 | 2024-Q3
EXP-002679 | 2024-07-26 | BOQ-PKG-09-00689 | PKG-09 | INV-PKG-09-020-02679 | 149.43 | 25628.39 | 1281.42 | Paid | 24346.97 | 2024-Q3
EXP-003144 | 2024-07-26 | BOQ-PKG-04-01154 | PKG-04 | INV-PKG-04-030-03144 | 292.68 | 149306.62 | 7465.33 | Paid | 141841.29 | 2024-Q3
EXP-004876 | 2024-07-26 | BOQ-PKG-06-00896 | PKG-06 | INV-PKG-06-012-04876 | 115.47 | 58158.36 | 2907.92 | Under Review | 55250.44 | 2024-Q3
EXP-006234 | 2024-07-26 | BOQ-PKG-04-00264 | PKG-04 | INV-PKG-04-005-06234 | 404.72 | 161230.35 | 8061.52 | Paid | 153168.83 | 2024-Q3
EXP-000381 | 2024-07-27 | BOQ-PKG-01-00381 | PKG-01 | INV-PKG-01-032-00381 | 283.93 | 94449 | 4722.45 | Paid | 89726.55 | 2024-Q3
EXP-001246 | 2024-07-27 | BOQ-PKG-06-01246 | PKG-06 | INV-PKG-06-022-01246 | 355.91 | 53117.88 | 2655.89 | Paid | 50461.99 | 2024-Q3
EXP-001825 | 2024-07-27 | BOQ-PKG-05-01825 | PKG-05 | INV-PKG-05-006-01825 | 139.13 | 62762.52 | 3138.13 | Paid | 59624.39 | 2024-Q3
EXP-001999 | 2024-07-27 | BOQ-PKG-09-00009 | PKG-09 | INV-PKG-09-005-01999 | 247.63 | 172009 | 8600.45 | Approved Pending Payment | 163408.55 | 2024-Q3
EXP-002382 | 2024-07-27 | BOQ-PKG-02-00392 | PKG-02 | INV-PKG-02-003-02382 | 310.98 | 89232.22 | 4461.61 | Under Review | 84770.61 | 2024-Q3
EXP-003125 | 2024-07-27 | BOQ-PKG-05-01135 | PKG-05 | INV-PKG-05-011-03125 | 31.04 | 127858.87 | 6392.94 | Disputed | 121465.93 | 2024-Q3
EXP-003906 | 2024-07-27 | BOQ-PKG-06-01916 | PKG-06 | INV-PKG-06-022-03906 | 438.57 | 154102.36 | 7705.12 | Paid | 146397.24 | 2024-Q3
EXP-004359 | 2024-07-27 | BOQ-PKG-09-00379 | PKG-09 | INV-PKG-09-020-04359 | 404.35 | 65239.48 | 3261.97 | Under Review | 61977.51 | 2024-Q3
EXP-006942 | 2024-07-27 | BOQ-PKG-02-00972 | PKG-02 | INV-PKG-02-013-06942 | 49.16 | 135158.5 | 6757.92 | Paid | 128400.58 | 2024-Q3
EXP-001682 | 2024-07-28 | BOQ-PKG-02-01682 | PKG-02 | INV-PKG-02-003-01682 | 341.29 | 112093.87 | 5604.69 | Paid | 106489.18 | 2024-Q3
EXP-002482 | 2024-07-28 | BOQ-PKG-02-00492 | PKG-02 | INV-PKG-02-033-02482 | 23.14 | 147646.25 | 7382.31 | Paid | 140263.94 | 2024-Q3
EXP-003049 | 2024-07-28 | BOQ-PKG-09-01059 | PKG-09 | INV-PKG-09-005-03049 | 446.42 | 170502.45 | 8525.12 | Paid | 161977.33 | 2024-Q3
EXP-005875 | 2024-07-28 | BOQ-PKG-05-01895 | PKG-05 | INV-PKG-05-031-05875 | 276.32 | 144735.56 | 7236.78 | Approved Pending Payment | 137498.78 | 2024-Q3
EXP-006768 | 2024-07-28 | BOQ-PKG-08-00798 | PKG-08 | INV-PKG-08-014-06768 | 315.22 | 25788.62 | 1289.43 | Paid | 24499.19 | 2024-Q3
EXP-002569 | 2024-07-29 | BOQ-PKG-09-00579 | PKG-09 | INV-PKG-09-015-02569 | 239.71 | 60185.53 | 3009.28 | Paid | 57176.25 | 2024-Q3
EXP-003548 | 2024-07-29 | BOQ-PKG-08-01558 | PKG-08 | INV-PKG-08-014-03548 | 132.32 | 115570.05 | 5778.5 | Paid | 109791.55 | 2024-Q3
EXP-004741 | 2024-07-29 | BOQ-PKG-01-00761 | PKG-01 | INV-PKG-01-017-04741 | 71.53 | 123000.53 | 6150.03 | Paid | 116850.5 | 2024-Q3
EXP-004754 | 2024-07-29 | BOQ-PKG-04-00774 | PKG-04 | INV-PKG-04-030-04754 | 69.64 | 184137.79 | 9206.89 | Paid | 174930.9 | 2024-Q3
EXP-005014 | 2024-07-29 | BOQ-PKG-04-01034 | PKG-04 | INV-PKG-04-010-05014 | 156.88 | 67269.31 | 3363.47 | Paid | 63905.84 | 2024-Q3
EXP-005336 | 2024-07-29 | BOQ-PKG-06-01356 | PKG-06 | INV-PKG-06-017-05336 | 188.12 | 62810.45 | 3140.52 | Paid | 59669.93 | 2024-Q3
EXP-001326 | 2024-07-30 | BOQ-PKG-06-01326 | PKG-06 | INV-PKG-06-032-01326 | 293.69 | 190228.46 | 9511.42 | Under Review | 180717.04 | 2024-Q3
EXP-001776 | 2024-07-30 | BOQ-PKG-06-01776 | PKG-06 | INV-PKG-06-027-01776 | 361.14 | 140191.26 | 7009.56 | Paid | 133181.7 | 2024-Q3
EXP-003288 | 2024-07-30 | BOQ-PKG-08-01298 | PKG-08 | INV-PKG-08-034-03288 | 358.3 | 207128.05 | 10356.4 | Paid | 196771.65 | 2024-Q3
EXP-004003 | 2024-07-30 | BOQ-PKG-03-00023 | PKG-03 | INV-PKG-03-014-04003 | 187.02 | 62630.19 | 3131.51 | Paid | 59498.68 | 2024-Q3
EXP-004224 | 2024-07-30 | BOQ-PKG-04-00244 | PKG-04 | INV-PKG-04-025-04224 | 226.79 | 194405.69 | 9720.28 | Approved Pending Payment | 184685.41 | 2024-Q3
EXP-005714 | 2024-07-30 | BOQ-PKG-04-01734 | PKG-04 | INV-PKG-04-010-05714 | 314.63 | 120988.16 | 6049.41 | Approved Pending Payment | 114938.75 | 2024-Q3
EXP-006295 | 2024-07-30 | BOQ-PKG-05-00325 | PKG-05 | INV-PKG-05-031-06295 | 325.04 | 134794.44 | 6739.72 | Paid | 128054.72 | 2024-Q3
EXP-000886 | 2024-07-31 | BOQ-PKG-06-00886 | PKG-06 | INV-PKG-06-012-00886 | 6.66 | 69082.3 | 3454.12 | Paid | 65628.18 | 2024-Q3
EXP-002008 | 2024-07-31 | BOQ-PKG-08-00018 | PKG-08 | INV-PKG-08-014-02008 | 425.2 | 28545.87 | 1427.29 | Paid | 27118.58 | 2024-Q3
EXP-002058 | 2024-07-31 | BOQ-PKG-08-00068 | PKG-08 | INV-PKG-08-029-02058 | 427.25 | 36386.92 | 1819.35 | Paid | 34567.57 | 2024-Q3
EXP-001069 | 2024-08-01 | BOQ-PKG-09-01069 | PKG-09 | INV-PKG-09-020-01069 | 398.68 | 138218.28 | 6910.91 | Paid | 131307.37 | 2024-Q3
EXP-001352 | 2024-08-01 | BOQ-PKG-02-01352 | PKG-02 | INV-PKG-02-023-01352 | 350.39 | 112282.01 | 5614.1 | Paid | 106667.91 | 2024-Q3
EXP-002326 | 2024-08-01 | BOQ-PKG-06-00336 | PKG-06 | INV-PKG-06-017-02326 | 353.84 | 154153.16 | 7707.66 | Paid | 146445.5 | 2024-Q3
EXP-002364 | 2024-08-01 | BOQ-PKG-04-00374 | PKG-04 | INV-PKG-04-020-02364 | 167.88 | 182878.33 | 9143.92 | Paid | 173734.41 | 2024-Q3
EXP-003592 | 2024-08-01 | BOQ-PKG-02-01602 | PKG-02 | INV-PKG-02-023-03592 | 222.88 | 41393.16 | 2069.66 | Approved Pending Payment | 39323.5 | 2024-Q3
EXP-003616 | 2024-08-01 | BOQ-PKG-06-01626 | PKG-06 | INV-PKG-06-012-03616 | 131.42 | 194679.03 | 9733.95 | Paid | 184945.08 | 2024-Q3
EXP-004288 | 2024-08-01 | BOQ-PKG-08-00308 | PKG-08 | INV-PKG-08-019-04288 | 190.35 | 198165.19 | 9908.26 | Under Review | 188256.93 | 2024-Q3
EXP-004851 | 2024-08-01 | BOQ-PKG-01-00871 | PKG-01 | INV-PKG-01-022-04851 | 245.52 | 108561.68 | 5428.08 | Approved Pending Payment | 103133.6 | 2024-Q3
EXP-005616 | 2024-08-01 | BOQ-PKG-06-01636 | PKG-06 | INV-PKG-06-017-05616 | 21.99 | 137645.34 | 6882.27 | Paid | 130763.07 | 2024-Q3
EXP-000379 | 2024-08-02 | BOQ-PKG-09-00379 | PKG-09 | INV-PKG-09-030-00379 | 110.34 | 144847.75 | 7242.39 | Paid | 137605.36 | 2024-Q3
EXP-001072 | 2024-08-02 | BOQ-PKG-02-01072 | PKG-02 | INV-PKG-02-023-01072 | 286.54 | 203112.86 | 10155.64 | Paid | 192957.22 | 2024-Q3
EXP-001676 | 2024-08-02 | BOQ-PKG-06-01676 | PKG-06 | INV-PKG-06-032-01676 | 365.96 | 163706.73 | 8185.34 | Paid | 155521.39 | 2024-Q3
EXP-001702 | 2024-08-02 | BOQ-PKG-02-01702 | PKG-02 | INV-PKG-02-023-01702 | 180.08 | 35142.35 | 1757.12 | Approved Pending Payment | 33385.23 | 2024-Q3
EXP-001948 | 2024-08-02 | BOQ-PKG-08-01948 | PKG-08 | INV-PKG-08-024-01948 | 252.82 | 168405.29 | 8420.26 | Paid | 159985.03 | 2024-Q3
EXP-002788 | 2024-08-02 | BOQ-PKG-08-00798 | PKG-08 | INV-PKG-08-024-02788 | 169.75 | 171777.99 | 8588.9 | Under Review | 163189.09 | 2024-Q3
EXP-004314 | 2024-08-02 | BOQ-PKG-04-00334 | PKG-04 | INV-PKG-04-010-04314 | 120.8 | 199625.07 | 9981.25 | Paid | 189643.82 | 2024-Q3
EXP-006017 | 2024-08-02 | BOQ-PKG-07-00047 | PKG-07 | INV-PKG-07-033-06017 | 345.31 | 128543.58 | 6427.18 | Paid | 122116.4 | 2024-Q3
EXP-006102 | 2024-08-02 | BOQ-PKG-02-00132 | PKG-02 | INV-PKG-02-013-06102 | 156.93 | 127630.67 | 6381.53 | Paid | 121249.14 | 2024-Q3
EXP-006305 | 2024-08-02 | BOQ-PKG-05-00335 | PKG-05 | INV-PKG-05-006-06305 | 39.5 | 206284.01 | 10314.2 | Paid | 195969.81 | 2024-Q3
EXP-006433 | 2024-08-02 | BOQ-PKG-03-00463 | PKG-03 | INV-PKG-03-029-06433 | 233.96 | 130408.99 | 6520.45 | Paid | 123888.54 | 2024-Q3
EXP-006458 | 2024-08-02 | BOQ-PKG-08-00488 | PKG-08 | INV-PKG-08-019-06458 | 86.82 | 158571.45 | 7928.57 | Paid | 150642.88 | 2024-Q3
EXP-000208 | 2024-08-03 | BOQ-PKG-08-00208 | PKG-08 | INV-PKG-08-034-00208 | 23.47 | 84464.97 | 4223.25 | Approved Pending Payment | 80241.72 | 2024-Q3
EXP-006439 | 2024-08-03 | BOQ-PKG-09-00469 | PKG-09 | INV-PKG-09-035-06439 | 173.32 | 211198.41 | 10559.92 | Paid | 200638.49 | 2024-Q3
EXP-002642 | 2024-08-04 | BOQ-PKG-02-00652 | PKG-02 | INV-PKG-02-018-02642 | 187.09 | 200940.46 | 10047.02 | Paid | 190893.44 | 2024-Q3
EXP-004311 | 2024-08-04 | BOQ-PKG-01-00331 | PKG-01 | INV-PKG-01-007-04311 | 274.61 | 92489.21 | 4624.46 | Paid | 87864.75 | 2024-Q3
EXP-004484 | 2024-08-04 | BOQ-PKG-04-00504 | PKG-04 | INV-PKG-04-005-04484 | 155.89 | 121036.79 | 6051.84 | Paid | 114984.95 | 2024-Q3
EXP-004711 | 2024-08-04 | BOQ-PKG-01-00731 | PKG-01 | INV-PKG-01-022-04711 | 273.77 | 199945.83 | 9997.29 | Under Review | 189948.54 | 2024-Q3
EXP-004728 | 2024-08-04 | BOQ-PKG-08-00748 | PKG-08 | INV-PKG-08-004-04728 | 88.35 | 87637.35 | 4381.87 | Paid | 83255.48 | 2024-Q3
EXP-004882 | 2024-08-04 | BOQ-PKG-02-00902 | PKG-02 | INV-PKG-02-018-04882 | 311.77 | 61568.31 | 3078.42 | Paid | 58489.89 | 2024-Q3
EXP-005849 | 2024-08-04 | BOQ-PKG-09-01869 | PKG-09 | INV-PKG-09-005-05849 | 365.44 | 62476.96 | 3123.85 | Paid | 59353.11 | 2024-Q3
EXP-006507 | 2024-08-04 | BOQ-PKG-07-00537 | PKG-07 | INV-PKG-07-033-06507 | 167.07 | 83756.29 | 4187.81 | Disputed | 79568.48 | 2024-Q3
EXP-006605 | 2024-08-04 | BOQ-PKG-05-00635 | PKG-05 | INV-PKG-05-026-06605 | 125.87 | 142218.33 | 7110.92 | Approved Pending Payment | 135107.41 | 2024-Q3
EXP-001158 | 2024-08-05 | BOQ-PKG-08-01158 | PKG-08 | INV-PKG-08-004-01158 | 287.15 | 172325.29 | 8616.26 | Paid | 163709.03 | 2024-Q3
EXP-001402 | 2024-08-05 | BOQ-PKG-02-01402 | PKG-02 | INV-PKG-02-003-01402 | 21.81 | 32895.39 | 1644.77 | Paid | 31250.62 | 2024-Q3
EXP-004066 | 2024-08-05 | BOQ-PKG-06-00086 | PKG-06 | INV-PKG-06-007-04066 | 46.92 | 125646.27 | 6282.31 | Paid | 119363.96 | 2024-Q3
EXP-004598 | 2024-08-05 | BOQ-PKG-08-00618 | PKG-08 | INV-PKG-08-014-04598 | 420.38 | 183976.15 | 9198.81 | Paid | 174777.34 | 2024-Q3
EXP-004659 | 2024-08-05 | BOQ-PKG-09-00679 | PKG-09 | INV-PKG-09-005-04659 | 308.67 | 200662.46 | 10033.12 | Paid | 190629.34 | 2024-Q3
EXP-006367 | 2024-08-05 | BOQ-PKG-07-00397 | PKG-07 | INV-PKG-07-033-06367 | 56.83 | 129372.25 | 6468.61 | Paid | 122903.64 | 2024-Q3
EXP-006474 | 2024-08-05 | BOQ-PKG-04-00504 | PKG-04 | INV-PKG-04-035-06474 | 324.12 | 80249.46 | 4012.47 | Paid | 76236.99 | 2024-Q3
EXP-006608 | 2024-08-05 | BOQ-PKG-08-00638 | PKG-08 | INV-PKG-08-029-06608 | 275.37 | 190443.84 | 9522.19 | Paid | 180921.65 | 2024-Q3
EXP-000671 | 2024-08-06 | BOQ-PKG-01-00671 | PKG-01 | INV-PKG-01-007-00671 | 388.42 | 200144.8 | 10007.24 | Paid | 190137.56 | 2024-Q3
EXP-001390 | 2024-08-06 | BOQ-PKG-10-01390 | PKG-10 | INV-PKG-10-026-01390 | 376.34 | 103029.24 | 5151.46 | Under Review | 97877.78 | 2024-Q3
EXP-001668 | 2024-08-06 | BOQ-PKG-08-01668 | PKG-08 | INV-PKG-08-024-01668 | 191.75 | 56796.96 | 2839.85 | Disputed | 53957.11 | 2024-Q3
EXP-001732 | 2024-08-06 | BOQ-PKG-02-01732 | PKG-02 | INV-PKG-02-018-01732 | 326.25 | 174089.2 | 8704.46 | Approved Pending Payment | 165384.74 | 2024-Q3
EXP-002558 | 2024-08-06 | BOQ-PKG-08-00568 | PKG-08 | INV-PKG-08-004-02558 | 239.68 | 70277.44 | 3513.87 | Paid | 66763.57 | 2024-Q3
EXP-003738 | 2024-08-06 | BOQ-PKG-08-01748 | PKG-08 | INV-PKG-08-029-03738 | 340.45 | 183647.44 | 9182.37 | Paid | 174465.07 | 2024-Q3
EXP-003904 | 2024-08-06 | BOQ-PKG-04-01914 | PKG-04 | INV-PKG-04-020-03904 | 322.89 | 126712.86 | 6335.64 | Paid | 120377.22 | 2024-Q3
EXP-004262 | 2024-08-06 | BOQ-PKG-02-00282 | PKG-02 | INV-PKG-02-028-04262 | 316.53 | 164995.53 | 8249.78 | Paid | 156745.75 | 2024-Q3
EXP-005369 | 2024-08-06 | BOQ-PKG-09-01389 | PKG-09 | INV-PKG-09-015-05369 | 301.52 | 59455.76 | 2972.79 | Paid | 56482.97 | 2024-Q3
EXP-005492 | 2024-08-06 | BOQ-PKG-02-01512 | PKG-02 | INV-PKG-02-033-05492 | 9.16 | 79074.6 | 3953.73 | Paid | 75120.87 | 2024-Q3
EXP-005979 | 2024-08-06 | BOQ-PKG-09-00009 | PKG-09 | INV-PKG-09-030-05979 | 121.81 | 132080.86 | 6604.04 | Paid | 125476.82 | 2024-Q3
EXP-006107 | 2024-08-06 | BOQ-PKG-07-00137 | PKG-07 | INV-PKG-07-018-06107 | 259.44 | 151331.88 | 7566.59 | Approved Pending Payment | 143765.29 | 2024-Q3
EXP-006475 | 2024-08-06 | BOQ-PKG-05-00505 | PKG-05 | INV-PKG-05-001-06475 | 125.59 | 142578.71 | 7128.94 | Approved Pending Payment | 135449.77 | 2024-Q3
EXP-000198 | 2024-08-07 | BOQ-PKG-08-00198 | PKG-08 | INV-PKG-08-024-00198 | 435.44 | 163098.45 | 8154.92 | Paid | 154943.53 | 2024-Q3
EXP-000686 | 2024-08-07 | BOQ-PKG-06-00686 | PKG-06 | INV-PKG-06-022-00686 | 302.98 | 199961.77 | 9998.09 | Paid | 189963.68 | 2024-Q3
EXP-004108 | 2024-08-07 | BOQ-PKG-08-00128 | PKG-08 | INV-PKG-08-014-04108 | 220.25 | 207938.69 | 10396.93 | Under Review | 197541.76 | 2024-Q3
EXP-004481 | 2024-08-07 | BOQ-PKG-01-00501 | PKG-01 | INV-PKG-01-002-04481 | 341.7 | 123188.53 | 6159.43 | Paid | 117029.1 | 2024-Q3
EXP-004649 | 2024-08-07 | BOQ-PKG-09-00669 | PKG-09 | INV-PKG-09-030-04649 | 227.29 | 136552.17 | 6827.61 | Paid | 129724.56 | 2024-Q3
EXP-004680 | 2024-08-07 | BOQ-PKG-10-00700 | PKG-10 | INV-PKG-10-026-04680 | 38.32 | 98929.29 | 4946.46 | Paid | 93982.83 | 2024-Q3
EXP-004790 | 2024-08-07 | BOQ-PKG-10-00810 | PKG-10 | INV-PKG-10-031-04790 | 190.43 | 97801.36 | 4890.07 | Paid | 92911.29 | 2024-Q3
EXP-004804 | 2024-08-07 | BOQ-PKG-04-00824 | PKG-04 | INV-PKG-04-010-04804 | 365.56 | 73954.52 | 3697.73 | Paid | 70256.79 | 2024-Q3
EXP-006134 | 2024-08-07 | BOQ-PKG-04-00164 | PKG-04 | INV-PKG-04-010-06134 | 358 | 76515.71 | 3825.79 | Paid | 72689.92 | 2024-Q3
EXP-006870 | 2024-08-07 | BOQ-PKG-10-00900 | PKG-10 | INV-PKG-10-011-06870 | 381.97 | 86743.85 | 4337.19 | Under Review | 82406.66 | 2024-Q3
EXP-000296 | 2024-08-08 | BOQ-PKG-06-00296 | PKG-06 | INV-PKG-06-017-00296 | 168.17 | 100544.01 | 5027.2 | Under Review | 95516.81 | 2024-Q3
EXP-001751 | 2024-08-08 | BOQ-PKG-01-01751 | PKG-01 | INV-PKG-01-002-01751 | 150.6 | 137662.83 | 6883.14 | Paid | 130779.69 | 2024-Q3
EXP-002956 | 2024-08-08 | BOQ-PKG-06-00966 | PKG-06 | INV-PKG-06-017-02956 | 104.54 | 75809.52 | 3790.48 | Paid | 72019.04 | 2024-Q3
EXP-003185 | 2024-08-08 | BOQ-PKG-05-01195 | PKG-05 | INV-PKG-05-001-03185 | 52.42 | 46640.34 | 2332.02 | Paid | 44308.32 | 2024-Q3
EXP-004008 | 2024-08-08 | BOQ-PKG-08-00028 | PKG-08 | INV-PKG-08-019-04008 | 86.55 | 164905.8 | 8245.29 | Paid | 156660.51 | 2024-Q3
EXP-004105 | 2024-08-08 | BOQ-PKG-05-00125 | PKG-05 | INV-PKG-05-011-04105 | 402.25 | 152869.16 | 7643.46 | Under Review | 145225.7 | 2024-Q3
EXP-004898 | 2024-08-08 | BOQ-PKG-08-00918 | PKG-08 | INV-PKG-08-034-04898 | 194.61 | 210665.61 | 10533.28 | Paid | 200132.33 | 2024-Q3
EXP-002135 | 2024-08-09 | BOQ-PKG-05-00145 | PKG-05 | INV-PKG-05-001-02135 | 246.37 | 94670.92 | 4733.55 | Paid | 89937.37 | 2024-Q3
EXP-003271 | 2024-08-09 | BOQ-PKG-01-01281 | PKG-01 | INV-PKG-01-017-03271 | 294.77 | 165000.79 | 8250.04 | Approved Pending Payment | 156750.75 | 2024-Q3
EXP-005334 | 2024-08-09 | BOQ-PKG-04-01354 | PKG-04 | INV-PKG-04-015-05334 | 105.89 | 101040.65 | 5052.03 | Paid | 95988.62 | 2024-Q3
EXP-006082 | 2024-08-09 | BOQ-PKG-02-00112 | PKG-02 | INV-PKG-02-028-06082 | 117.94 | 37172.13 | 1858.61 | Approved Pending Payment | 35313.52 | 2024-Q3
EXP-006100 | 2024-08-09 | BOQ-PKG-10-00130 | PKG-10 | INV-PKG-10-011-06100 | 296.43 | 31317.4 | 1565.87 | Paid | 29751.53 | 2024-Q3
EXP-001540 | 2024-08-10 | BOQ-PKG-10-01540 | PKG-10 | INV-PKG-10-001-01540 | 142.76 | 139489.07 | 6974.45 | Paid | 132514.62 | 2024-Q3
EXP-001864 | 2024-08-10 | BOQ-PKG-04-01864 | PKG-04 | INV-PKG-04-010-01864 | 437.19 | 157841.76 | 7892.09 | Paid | 149949.67 | 2024-Q3
EXP-002206 | 2024-08-10 | BOQ-PKG-06-00216 | PKG-06 | INV-PKG-06-002-02206 | 119.75 | 129545.61 | 6477.28 | Paid | 123068.33 | 2024-Q3
EXP-004416 | 2024-08-10 | BOQ-PKG-06-00436 | PKG-06 | INV-PKG-06-007-04416 | 36.4 | 92221.57 | 4611.08 | Paid | 87610.49 | 2024-Q3
EXP-004720 | 2024-08-10 | BOQ-PKG-10-00740 | PKG-10 | INV-PKG-10-031-04720 | 439.43 | 83628.53 | 4181.43 | Paid | 79447.1 | 2024-Q3
EXP-006269 | 2024-08-10 | BOQ-PKG-09-00299 | PKG-09 | INV-PKG-09-005-06269 | 171.42 | 142660.65 | 7133.03 | Paid | 135527.62 | 2024-Q3
EXP-006348 | 2024-08-10 | BOQ-PKG-08-00378 | PKG-08 | INV-PKG-08-014-06348 | 337.57 | 78048.71 | 3902.44 | Paid | 74146.27 | 2024-Q3
EXP-000899 | 2024-08-11 | BOQ-PKG-09-00899 | PKG-09 | INV-PKG-09-025-00899 | 130.46 | 104012.65 | 5200.63 | Under Review | 98812.02 | 2024-Q3
EXP-003247 | 2024-08-11 | BOQ-PKG-07-01257 | PKG-07 | INV-PKG-07-028-03247 | 26.07 | 68047.62 | 3402.38 | Approved Pending Payment | 64645.24 | 2024-Q3
EXP-004391 | 2024-08-11 | BOQ-PKG-01-00411 | PKG-01 | INV-PKG-01-017-04391 | 172.21 | 49038.28 | 2451.91 | Approved Pending Payment | 46586.37 | 2024-Q3
EXP-004524 | 2024-08-11 | BOQ-PKG-04-00544 | PKG-04 | INV-PKG-04-010-04524 | 223.9 | 105719.36 | 5285.97 | Paid | 100433.39 | 2024-Q3
EXP-005378 | 2024-08-11 | BOQ-PKG-08-01398 | PKG-08 | INV-PKG-08-024-05378 | 307.45 | 81956.69 | 4097.83 | Paid | 77858.86 | 2024-Q3
EXP-006194 | 2024-08-11 | BOQ-PKG-04-00224 | PKG-04 | INV-PKG-04-035-06194 | 186.49 | 106877.21 | 5343.86 | Paid | 101533.35 | 2024-Q3
EXP-001223 | 2024-08-12 | BOQ-PKG-03-01223 | PKG-03 | INV-PKG-03-034-01223 | 76.83 | 95932.11 | 4796.61 | Approved Pending Payment | 91135.5 | 2024-Q3
EXP-002406 | 2024-08-12 | BOQ-PKG-06-00416 | PKG-06 | INV-PKG-06-027-02406 | 215.34 | 35413.72 | 1770.69 | Paid | 33643.03 | 2024-Q3
EXP-002629 | 2024-08-12 | BOQ-PKG-09-00639 | PKG-09 | INV-PKG-09-005-02629 | 239.69 | 56954.46 | 2847.72 | Paid | 54106.74 | 2024-Q3
EXP-003747 | 2024-08-12 | BOQ-PKG-07-01757 | PKG-07 | INV-PKG-07-003-03747 | 249.22 | 199372.58 | 9968.63 | Paid | 189403.95 | 2024-Q3
EXP-004964 | 2024-08-12 | BOQ-PKG-04-00984 | PKG-04 | INV-PKG-04-030-04964 | 68.9 | 199299.12 | 9964.96 | Paid | 189334.16 | 2024-Q3
EXP-005427 | 2024-08-12 | BOQ-PKG-07-01447 | PKG-07 | INV-PKG-07-003-05427 | 388.43 | 136831.32 | 6841.57 | Paid | 129989.75 | 2024-Q3
EXP-005490 | 2024-08-12 | BOQ-PKG-10-01510 | PKG-10 | INV-PKG-10-031-05490 | 363.29 | 81583.78 | 4079.19 | Paid | 77504.59 | 2024-Q3
EXP-006554 | 2024-08-12 | BOQ-PKG-04-00584 | PKG-04 | INV-PKG-04-010-06554 | 93.28 | 186526.63 | 9326.33 | Disputed | 177200.3 | 2024-Q3
EXP-006744 | 2024-08-12 | BOQ-PKG-04-00774 | PKG-04 | INV-PKG-04-025-06744 | 360.41 | 196180.78 | 9809.04 | Disputed | 186371.74 | 2024-Q3
EXP-000767 | 2024-08-13 | BOQ-PKG-07-00767 | PKG-07 | INV-PKG-07-033-00767 | 30.15 | 43010.63 | 2150.53 | Paid | 40860.1 | 2024-Q3
EXP-001226 | 2024-08-13 | BOQ-PKG-06-01226 | PKG-06 | INV-PKG-06-002-01226 | 121.23 | 117827.36 | 5891.37 | Paid | 111935.99 | 2024-Q3
EXP-001827 | 2024-08-13 | BOQ-PKG-07-01827 | PKG-07 | INV-PKG-07-008-01827 | 238.91 | 40771.15 | 2038.56 | Paid | 38732.59 | 2024-Q3
EXP-001962 | 2024-08-13 | BOQ-PKG-02-01962 | PKG-02 | INV-PKG-02-003-01962 | 320.56 | 40515.67 | 2025.78 | Paid | 38489.89 | 2024-Q3
EXP-004028 | 2024-08-13 | BOQ-PKG-08-00048 | PKG-08 | INV-PKG-08-004-04028 | 98.83 | 132791.82 | 6639.59 | Paid | 126152.23 | 2024-Q3
EXP-004498 | 2024-08-13 | BOQ-PKG-08-00518 | PKG-08 | INV-PKG-08-019-04498 | 75.67 | 207110.77 | 10355.54 | Paid | 196755.23 | 2024-Q3
EXP-005201 | 2024-08-13 | BOQ-PKG-01-01221 | PKG-01 | INV-PKG-01-022-05201 | 177.6 | 187330.05 | 9366.5 | Paid | 177963.55 | 2024-Q3
EXP-002173 | 2024-08-14 | BOQ-PKG-03-00183 | PKG-03 | INV-PKG-03-004-02173 | 164.8 | 67367.78 | 3368.39 | Approved Pending Payment | 63999.39 | 2024-Q3
EXP-002617 | 2024-08-14 | BOQ-PKG-07-00627 | PKG-07 | INV-PKG-07-028-02617 | 304.78 | 184001.97 | 9200.1 | Approved Pending Payment | 174801.87 | 2024-Q3
EXP-003287 | 2024-08-14 | BOQ-PKG-07-01297 | PKG-07 | INV-PKG-07-033-03287 | 326.98 | 137440.26 | 6872.01 | Paid | 130568.25 | 2024-Q3
EXP-003811 | 2024-08-14 | BOQ-PKG-01-01821 | PKG-01 | INV-PKG-01-032-03811 | 126.02 | 50916.95 | 2545.85 | Paid | 48371.1 | 2024-Q3
EXP-004962 | 2024-08-14 | BOQ-PKG-02-00982 | PKG-02 | INV-PKG-02-028-04962 | 253.05 | 191415.65 | 9570.78 | Under Review | 181844.87 | 2024-Q3
EXP-005505 | 2024-08-14 | BOQ-PKG-05-01525 | PKG-05 | INV-PKG-05-011-05505 | 431.19 | 88280.09 | 4414 | Disputed | 83866.09 | 2024-Q3
EXP-005556 | 2024-08-14 | BOQ-PKG-06-01576 | PKG-06 | INV-PKG-06-027-05556 | 319.13 | 98350.49 | 4917.52 | Under Review | 93432.97 | 2024-Q3
EXP-006169 | 2024-08-14 | BOQ-PKG-09-00199 | PKG-09 | INV-PKG-09-010-06169 | 115.04 | 122443.8 | 6122.19 | Paid | 116321.61 | 2024-Q3
EXP-000281 | 2024-08-15 | BOQ-PKG-01-00281 | PKG-01 | INV-PKG-01-002-00281 | 229.5 | 69848.06 | 3492.4 | Paid | 66355.66 | 2024-Q3
EXP-001775 | 2024-08-15 | BOQ-PKG-05-01775 | PKG-05 | INV-PKG-05-026-01775 | 187.8 | 188060.42 | 9403.02 | Paid | 178657.4 | 2024-Q3
EXP-003844 | 2024-08-15 | BOQ-PKG-04-01854 | PKG-04 | INV-PKG-04-030-03844 | 161.91 | 161356.45 | 8067.82 | Paid | 153288.63 | 2024-Q3
EXP-004725 | 2024-08-15 | BOQ-PKG-05-00745 | PKG-05 | INV-PKG-05-001-04725 | 13.59 | 69312.86 | 3465.64 | Under Review | 65847.22 | 2024-Q3
EXP-005275 | 2024-08-15 | BOQ-PKG-05-01295 | PKG-05 | INV-PKG-05-026-05275 | 298.19 | 171651.55 | 8582.58 | Paid | 163068.97 | 2024-Q3
EXP-005351 | 2024-08-15 | BOQ-PKG-01-01371 | PKG-01 | INV-PKG-01-032-05351 | 40.12 | 160180.15 | 8009.01 | Approved Pending Payment | 152171.14 | 2024-Q3
EXP-006378 | 2024-08-15 | BOQ-PKG-08-00408 | PKG-08 | INV-PKG-08-009-06378 | 335.16 | 51592.78 | 2579.64 | Approved Pending Payment | 49013.14 | 2024-Q3
EXP-006482 | 2024-08-15 | BOQ-PKG-02-00512 | PKG-02 | INV-PKG-02-008-06482 | 250.6 | 70955.19 | 3547.76 | Paid | 67407.43 | 2024-Q3
EXP-006867 | 2024-08-15 | BOQ-PKG-07-00897 | PKG-07 | INV-PKG-07-008-06867 | 62.63 | 179603 | 8980.15 | Paid | 170622.85 | 2024-Q3
EXP-000509 | 2024-08-16 | BOQ-PKG-09-00509 | PKG-09 | INV-PKG-09-020-00509 | 99.25 | 167698.5 | 8384.93 | Paid | 159313.57 | 2024-Q3
EXP-001905 | 2024-08-16 | BOQ-PKG-05-01905 | PKG-05 | INV-PKG-05-016-01905 | 297.1 | 52699.93 | 2635 | Paid | 50064.93 | 2024-Q3
EXP-002223 | 2024-08-16 | BOQ-PKG-03-00233 | PKG-03 | INV-PKG-03-019-02223 | 289.56 | 108410.92 | 5420.55 | Paid | 102990.37 | 2024-Q3
EXP-004781 | 2024-08-16 | BOQ-PKG-01-00801 | PKG-01 | INV-PKG-01-022-04781 | 288.16 | 203429.72 | 10171.49 | Paid | 193258.23 | 2024-Q3
EXP-005115 | 2024-08-16 | BOQ-PKG-05-01135 | PKG-05 | INV-PKG-05-006-05115 | 271.13 | 49053.27 | 2452.66 | Paid | 46600.61 | 2024-Q3
EXP-006284 | 2024-08-16 | BOQ-PKG-04-00314 | PKG-04 | INV-PKG-04-020-06284 | 88.46 | 172241.63 | 8612.08 | Under Review | 163629.55 | 2024-Q3
EXP-006795 | 2024-08-16 | BOQ-PKG-05-00825 | PKG-05 | INV-PKG-05-006-06795 | 23.42 | 54365.81 | 2718.29 | Paid | 51647.52 | 2024-Q3
EXP-000575 | 2024-08-17 | BOQ-PKG-05-00575 | PKG-05 | INV-PKG-05-016-00575 | 419.51 | 197813.53 | 9890.68 | Paid | 187922.85 | 2024-Q3
EXP-001445 | 2024-08-17 | BOQ-PKG-05-01445 | PKG-05 | INV-PKG-05-011-01445 | 178.38 | 139914.23 | 6995.71 | Under Review | 132918.52 | 2024-Q3
EXP-002067 | 2024-08-17 | BOQ-PKG-07-00077 | PKG-07 | INV-PKG-07-003-02067 | 180.84 | 145299.49 | 7264.97 | Approved Pending Payment | 138034.52 | 2024-Q3
EXP-006074 | 2024-08-17 | BOQ-PKG-04-00104 | PKG-04 | INV-PKG-04-020-06074 | 96.18 | 155457.58 | 7772.88 | Paid | 147684.7 | 2024-Q3
EXP-006599 | 2024-08-17 | BOQ-PKG-09-00629 | PKG-09 | INV-PKG-09-020-06599 | 397.58 | 124296.35 | 6214.82 | Disputed | 118081.53 | 2024-Q3
EXP-000260 | 2024-08-18 | BOQ-PKG-10-00260 | PKG-10 | INV-PKG-10-016-00260 | 78.95 | 89027.86 | 4451.39 | Paid | 84576.47 | 2024-Q3
EXP-004500 | 2024-08-18 | BOQ-PKG-10-00520 | PKG-10 | INV-PKG-10-021-04500 | 291.46 | 196106.45 | 9805.32 | Approved Pending Payment | 186301.13 | 2024-Q3
EXP-006504 | 2024-08-18 | BOQ-PKG-04-00534 | PKG-04 | INV-PKG-04-030-06504 | 188.43 | 87878.02 | 4393.9 | Disputed | 83484.12 | 2024-Q3
EXP-001371 | 2024-08-19 | BOQ-PKG-01-01371 | PKG-01 | INV-PKG-01-007-01371 | 59.12 | 90029.04 | 4501.45 | Paid | 85527.59 | 2024-Q3
EXP-004821 | 2024-08-19 | BOQ-PKG-01-00841 | PKG-01 | INV-PKG-01-027-04821 | 287.98 | 77952.9 | 3897.64 | Paid | 74055.26 | 2024-Q3
EXP-005873 | 2024-08-19 | BOQ-PKG-03-01893 | PKG-03 | INV-PKG-03-029-05873 | 262.51 | 40101.19 | 2005.06 | Paid | 38096.13 | 2024-Q3
EXP-006961 | 2024-08-19 | BOQ-PKG-01-00991 | PKG-01 | INV-PKG-01-032-06961 | 415.77 | 83715.01 | 4185.75 | Paid | 79529.26 | 2024-Q3
EXP-000585 | 2024-08-20 | BOQ-PKG-05-00585 | PKG-05 | INV-PKG-05-026-00585 | 93.81 | 31340.38 | 1567.02 | Paid | 29773.36 | 2024-Q3
EXP-003261 | 2024-08-20 | BOQ-PKG-01-01271 | PKG-01 | INV-PKG-01-007-03261 | 407.69 | 140345.71 | 7017.29 | Paid | 133328.42 | 2024-Q3
EXP-004408 | 2024-08-20 | BOQ-PKG-08-00428 | PKG-08 | INV-PKG-08-034-04408 | 232.99 | 194294.56 | 9714.73 | Paid | 184579.83 | 2024-Q3
EXP-005775 | 2024-08-20 | BOQ-PKG-05-01795 | PKG-05 | INV-PKG-05-001-05775 | 110.92 | 89617.66 | 4480.88 | Approved Pending Payment | 85136.78 | 2024-Q3
EXP-001453 | 2024-08-21 | BOQ-PKG-03-01453 | PKG-03 | INV-PKG-03-019-01453 | 394.04 | 55542.97 | 2777.15 | Paid | 52765.82 | 2024-Q3
EXP-003282 | 2024-08-21 | BOQ-PKG-02-01292 | PKG-02 | INV-PKG-02-028-03282 | 414.55 | 135599.92 | 6780 | Paid | 128819.92 | 2024-Q3
EXP-003886 | 2024-08-21 | BOQ-PKG-06-01896 | PKG-06 | INV-PKG-06-002-03886 | 300.09 | 170361.08 | 8518.05 | Paid | 161843.03 | 2024-Q3
EXP-004081 | 2024-08-21 | BOQ-PKG-01-00101 | PKG-01 | INV-PKG-01-022-04081 | 386.88 | 111279.9 | 5564 | Approved Pending Payment | 105715.9 | 2024-Q3
EXP-004379 | 2024-08-21 | BOQ-PKG-09-00399 | PKG-09 | INV-PKG-09-005-04379 | 221.11 | 211714.15 | 10585.71 | Approved Pending Payment | 201128.44 | 2024-Q3
EXP-004573 | 2024-08-21 | BOQ-PKG-03-00593 | PKG-03 | INV-PKG-03-024-04573 | 82.86 | 188823.46 | 9441.17 | Approved Pending Payment | 179382.29 | 2024-Q3
EXP-005503 | 2024-08-21 | BOQ-PKG-03-01523 | PKG-03 | INV-PKG-03-009-05503 | 282.63 | 114863.82 | 5743.19 | Paid | 109120.63 | 2024-Q3
EXP-006733 | 2024-08-21 | BOQ-PKG-03-00763 | PKG-03 | INV-PKG-03-014-06733 | 301.34 | 119725.78 | 5986.29 | Paid | 113739.49 | 2024-Q3
EXP-006857 | 2024-08-21 | BOQ-PKG-07-00887 | PKG-07 | INV-PKG-07-033-06857 | 403.54 | 182034.6 | 9101.73 | Paid | 172932.87 | 2024-Q3
EXP-006201 | 2024-08-22 | BOQ-PKG-01-00231 | PKG-01 | INV-PKG-01-007-06201 | 103.79 | 153560.68 | 7678.03 | Paid | 145882.65 | 2024-Q3
EXP-006637 | 2024-08-22 | BOQ-PKG-07-00667 | PKG-07 | INV-PKG-07-023-06637 | 195.01 | 171959.7 | 8597.98 | Paid | 163361.72 | 2024-Q3
EXP-000343 | 2024-08-23 | BOQ-PKG-03-00343 | PKG-03 | INV-PKG-03-029-00343 | 74.76 | 152654.37 | 7632.72 | Approved Pending Payment | 145021.65 | 2024-Q3
EXP-000508 | 2024-08-23 | BOQ-PKG-08-00508 | PKG-08 | INV-PKG-08-019-00508 | 381.17 | 165722.09 | 8286.1 | Paid | 157435.99 | 2024-Q3
EXP-000641 | 2024-08-23 | BOQ-PKG-01-00641 | PKG-01 | INV-PKG-01-012-00641 | 187.25 | 173191.81 | 8659.59 | Paid | 164532.22 | 2024-Q3
EXP-001736 | 2024-08-23 | BOQ-PKG-06-01736 | PKG-06 | INV-PKG-06-022-01736 | 332.51 | 25480.3 | 1274.02 | Approved Pending Payment | 24206.28 | 2024-Q3
EXP-002318 | 2024-08-23 | BOQ-PKG-08-00328 | PKG-08 | INV-PKG-08-009-02318 | 234.17 | 81750.46 | 4087.52 | Paid | 77662.94 | 2024-Q3
EXP-004157 | 2024-08-23 | BOQ-PKG-07-00177 | PKG-07 | INV-PKG-07-028-04157 | 158.15 | 75794.9 | 3789.74 | Paid | 72005.16 | 2024-Q3
EXP-004294 | 2024-08-23 | BOQ-PKG-04-00314 | PKG-04 | INV-PKG-04-025-04294 | 369.04 | 150121.16 | 7506.06 | Disputed | 142615.1 | 2024-Q3
EXP-005437 | 2024-08-23 | BOQ-PKG-07-01457 | PKG-07 | INV-PKG-07-013-05437 | 292.76 | 185732.96 | 9286.65 | Approved Pending Payment | 176446.31 | 2024-Q3
EXP-006537 | 2024-08-23 | BOQ-PKG-07-00567 | PKG-07 | INV-PKG-07-028-06537 | 318.62 | 169168.12 | 8458.41 | Paid | 160709.71 | 2024-Q3
EXP-000672 | 2024-08-24 | BOQ-PKG-02-00672 | PKG-02 | INV-PKG-02-008-00672 | 27.15 | 74964.66 | 3748.23 | Paid | 71216.43 | 2024-Q3
EXP-001850 | 2024-08-24 | BOQ-PKG-10-01850 | PKG-10 | INV-PKG-10-031-01850 | 188.28 | 152818.12 | 7640.91 | Paid | 145177.21 | 2024-Q3
EXP-002470 | 2024-08-24 | BOQ-PKG-10-00480 | PKG-10 | INV-PKG-10-021-02470 | 92.92 | 25556.37 | 1277.82 | Under Review | 24278.55 | 2024-Q3
EXP-002771 | 2024-08-24 | BOQ-PKG-01-00781 | PKG-01 | INV-PKG-01-007-02771 | 86.73 | 25738.67 | 1286.93 | Paid | 24451.74 | 2024-Q3
EXP-002772 | 2024-08-24 | BOQ-PKG-02-00782 | PKG-02 | INV-PKG-02-008-02772 | 28.88 | 106434.64 | 5321.73 | Paid | 101112.91 | 2024-Q3
EXP-003242 | 2024-08-24 | BOQ-PKG-02-01252 | PKG-02 | INV-PKG-02-023-03242 | 91.21 | 66630.41 | 3331.52 | Paid | 63298.89 | 2024-Q3
EXP-004301 | 2024-08-24 | BOQ-PKG-01-00321 | PKG-01 | INV-PKG-01-032-04301 | 44.83 | 41809.03 | 2090.45 | Paid | 39718.58 | 2024-Q3
EXP-006783 | 2024-08-24 | BOQ-PKG-03-00813 | PKG-03 | INV-PKG-03-029-06783 | 54.27 | 203072.26 | 10153.61 | Paid | 192918.65 | 2024-Q3
EXP-000341 | 2024-08-25 | BOQ-PKG-01-00341 | PKG-01 | INV-PKG-01-027-00341 | 225 | 190350.98 | 9517.55 | Paid | 180833.43 | 2024-Q3
EXP-000412 | 2024-08-25 | BOQ-PKG-02-00412 | PKG-02 | INV-PKG-02-028-00412 | 322.58 | 181595.81 | 9079.79 | Under Review | 172516.02 | 2024-Q3
EXP-001853 | 2024-08-25 | BOQ-PKG-03-01853 | PKG-03 | INV-PKG-03-034-01853 | 49.65 | 52440.66 | 2622.03 | Approved Pending Payment | 49818.63 | 2024-Q3
EXP-001923 | 2024-08-25 | BOQ-PKG-03-01923 | PKG-03 | INV-PKG-03-034-01923 | 192.79 | 201600.86 | 10080.04 | Paid | 191520.82 | 2024-Q3
EXP-003358 | 2024-08-25 | BOQ-PKG-08-01368 | PKG-08 | INV-PKG-08-034-03358 | 419.46 | 179252.9 | 8962.64 | Paid | 170290.26 | 2024-Q3
EXP-003668 | 2024-08-25 | BOQ-PKG-08-01678 | PKG-08 | INV-PKG-08-029-03668 | 326.41 | 106407.81 | 5320.39 | Paid | 101087.42 | 2024-Q3
EXP-003694 | 2024-08-25 | BOQ-PKG-04-01704 | PKG-04 | INV-PKG-04-020-03694 | 83.05 | 159681.81 | 7984.09 | Approved Pending Payment | 151697.72 | 2024-Q3
EXP-003719 | 2024-08-25 | BOQ-PKG-09-01729 | PKG-09 | INV-PKG-09-010-03719 | 443 | 126782.5 | 6339.12 | Paid | 120443.38 | 2024-Q3
EXP-003728 | 2024-08-25 | BOQ-PKG-08-01738 | PKG-08 | INV-PKG-08-019-03728 | 394.34 | 53171.2 | 2658.56 | Paid | 50512.64 | 2024-Q3
EXP-000374 | 2024-08-26 | BOQ-PKG-04-00374 | PKG-04 | INV-PKG-04-025-00374 | 99.12 | 159089.6 | 7954.48 | Paid | 151135.12 | 2024-Q3
EXP-002620 | 2024-08-26 | BOQ-PKG-10-00630 | PKG-10 | INV-PKG-10-031-02620 | 68.8 | 95519.84 | 4775.99 | Under Review | 90743.85 | 2024-Q3
EXP-003957 | 2024-08-26 | BOQ-PKG-07-01967 | PKG-07 | INV-PKG-07-003-03957 | 123.22 | 205256.92 | 10262.85 | Paid | 194994.07 | 2024-Q3
EXP-005226 | 2024-08-26 | BOQ-PKG-06-01246 | PKG-06 | INV-PKG-06-012-05226 | 15.79 | 97979.23 | 4898.96 | Paid | 93080.27 | 2024-Q3
EXP-005694 | 2024-08-26 | BOQ-PKG-04-01714 | PKG-04 | INV-PKG-04-025-05694 | 123.28 | 64407.71 | 3220.39 | Approved Pending Payment | 61187.32 | 2024-Q3
EXP-005751 | 2024-08-26 | BOQ-PKG-01-01771 | PKG-01 | INV-PKG-01-012-05751 | 306.7 | 134278.39 | 6713.92 | Approved Pending Payment | 127564.47 | 2024-Q3
EXP-005841 | 2024-08-26 | BOQ-PKG-01-01861 | PKG-01 | INV-PKG-01-032-05841 | 124.38 | 53267.18 | 2663.36 | Paid | 50603.82 | 2024-Q3
EXP-006940 | 2024-08-26 | BOQ-PKG-10-00970 | PKG-10 | INV-PKG-10-011-06940 | 346.76 | 28026.31 | 1401.32 | Paid | 26624.99 | 2024-Q3
EXP-001497 | 2024-08-27 | BOQ-PKG-07-01497 | PKG-07 | INV-PKG-07-028-01497 | 41.13 | 139224.46 | 6961.22 | Paid | 132263.24 | 2024-Q3
EXP-001798 | 2024-08-27 | BOQ-PKG-08-01798 | PKG-08 | INV-PKG-08-014-01798 | 194.61 | 161904.95 | 8095.25 | Paid | 153809.7 | 2024-Q3
EXP-002869 | 2024-08-27 | BOQ-PKG-09-00879 | PKG-09 | INV-PKG-09-035-02869 | 313.14 | 166063.3 | 8303.16 | Paid | 157760.14 | 2024-Q3
EXP-003960 | 2024-08-27 | BOQ-PKG-10-01970 | PKG-10 | INV-PKG-10-006-03960 | 316.94 | 88501.59 | 4425.08 | Paid | 84076.51 | 2024-Q3
EXP-006545 | 2024-08-27 | BOQ-PKG-05-00575 | PKG-05 | INV-PKG-05-001-06545 | 203.32 | 168010.38 | 8400.52 | Paid | 159609.86 | 2024-Q3
EXP-006709 | 2024-08-27 | BOQ-PKG-09-00739 | PKG-09 | INV-PKG-09-025-06709 | 149.02 | 80304.98 | 4015.25 | Paid | 76289.73 | 2024-Q3
EXP-006933 | 2024-08-27 | BOQ-PKG-03-00963 | PKG-03 | INV-PKG-03-004-06933 | 57.12 | 118967.47 | 5948.37 | Paid | 113019.1 | 2024-Q3
EXP-003912 | 2024-08-28 | BOQ-PKG-02-01922 | PKG-02 | INV-PKG-02-028-03912 | 109.52 | 201785.48 | 10089.27 | Paid | 191696.21 | 2024-Q3
EXP-004219 | 2024-08-28 | BOQ-PKG-09-00239 | PKG-09 | INV-PKG-09-020-04219 | 90.97 | 197371.97 | 9868.6 | Approved Pending Payment | 187503.37 | 2024-Q3
EXP-005083 | 2024-08-28 | BOQ-PKG-03-01103 | PKG-03 | INV-PKG-03-009-05083 | 143.06 | 84943.86 | 4247.19 | Paid | 80696.67 | 2024-Q3
EXP-006622 | 2024-08-28 | BOQ-PKG-02-00652 | PKG-02 | INV-PKG-02-008-06622 | 81.47 | 32137.29 | 1606.86 | Paid | 30530.43 | 2024-Q3
EXP-003249 | 2024-08-29 | BOQ-PKG-09-01259 | PKG-09 | INV-PKG-09-030-03249 | 388.74 | 143520.29 | 7176.01 | Paid | 136344.28 | 2024-Q3
EXP-004445 | 2024-08-29 | BOQ-PKG-05-00465 | PKG-05 | INV-PKG-05-001-04445 | 233.37 | 163454.73 | 8172.74 | Paid | 155281.99 | 2024-Q3
EXP-004815 | 2024-08-29 | BOQ-PKG-05-00835 | PKG-05 | INV-PKG-05-021-04815 | 216.26 | 70493.69 | 3524.68 | Approved Pending Payment | 66969.01 | 2024-Q3
EXP-005362 | 2024-08-29 | BOQ-PKG-02-01382 | PKG-02 | INV-PKG-02-008-05362 | 81.46 | 203836.77 | 10191.84 | Under Review | 193644.93 | 2024-Q3
EXP-005678 | 2024-08-29 | BOQ-PKG-08-01698 | PKG-08 | INV-PKG-08-009-05678 | 224.78 | 128905.35 | 6445.27 | Under Review | 122460.08 | 2024-Q3
EXP-005838 | 2024-08-29 | BOQ-PKG-08-01858 | PKG-08 | INV-PKG-08-029-05838 | 60.17 | 203733.09 | 10186.65 | Paid | 193546.44 | 2024-Q3
EXP-006052 | 2024-08-29 | BOQ-PKG-02-00082 | PKG-02 | INV-PKG-02-033-06052 | 173.28 | 77848.02 | 3892.4 | Paid | 73955.62 | 2024-Q3
EXP-006742 | 2024-08-29 | BOQ-PKG-02-00772 | PKG-02 | INV-PKG-02-023-06742 | 188.78 | 134851.32 | 6742.57 | Paid | 128108.75 | 2024-Q3
EXP-000517 | 2024-08-30 | BOQ-PKG-07-00517 | PKG-07 | INV-PKG-07-028-00517 | 148.97 | 58608.74 | 2930.44 | Paid | 55678.3 | 2024-Q3
EXP-001730 | 2024-08-30 | BOQ-PKG-10-01730 | PKG-10 | INV-PKG-10-016-01730 | 164.65 | 195862.53 | 9793.13 | Approved Pending Payment | 186069.4 | 2024-Q3
EXP-002705 | 2024-08-30 | BOQ-PKG-05-00715 | PKG-05 | INV-PKG-05-011-02705 | 126.94 | 189357.63 | 9467.88 | Paid | 179889.75 | 2024-Q3
EXP-003031 | 2024-08-30 | BOQ-PKG-01-01041 | PKG-01 | INV-PKG-01-022-03031 | 288.93 | 95479.37 | 4773.97 | Paid | 90705.4 | 2024-Q3
EXP-003784 | 2024-08-30 | BOQ-PKG-04-01794 | PKG-04 | INV-PKG-04-005-03784 | 309.37 | 75977.4 | 3798.87 | Paid | 72178.53 | 2024-Q3
EXP-004622 | 2024-08-30 | BOQ-PKG-02-00642 | PKG-02 | INV-PKG-02-003-04622 | 349.81 | 46070.44 | 2303.52 | Under Review | 43766.92 | 2024-Q3
EXP-004864 | 2024-08-30 | BOQ-PKG-04-00884 | PKG-04 | INV-PKG-04-035-04864 | 117.9 | 92769.46 | 4638.47 | Paid | 88130.99 | 2024-Q3
EXP-005259 | 2024-08-30 | BOQ-PKG-09-01279 | PKG-09 | INV-PKG-09-010-05259 | 176.11 | 45080.28 | 2254.01 | Paid | 42826.27 | 2024-Q3
EXP-006404 | 2024-08-30 | BOQ-PKG-04-00434 | PKG-04 | INV-PKG-04-035-06404 | 20.17 | 156294.36 | 7814.72 | Paid | 148479.64 | 2024-Q3
EXP-001970 | 2024-08-31 | BOQ-PKG-10-01970 | PKG-10 | INV-PKG-10-011-01970 | 223.25 | 36399.78 | 1819.99 | Paid | 34579.79 | 2024-Q3
EXP-003096 | 2024-08-31 | BOQ-PKG-06-01106 | PKG-06 | INV-PKG-06-017-03096 | 40.11 | 27940.75 | 1397.04 | Paid | 26543.71 | 2024-Q3
EXP-005172 | 2024-08-31 | BOQ-PKG-02-01192 | PKG-02 | INV-PKG-02-028-05172 | 101.78 | 82689.33 | 4134.47 | Approved Pending Payment | 78554.86 | 2024-Q3
EXP-005634 | 2024-08-31 | BOQ-PKG-04-01654 | PKG-04 | INV-PKG-04-035-05634 | 446.66 | 27184.08 | 1359.2 | Approved Pending Payment | 25824.88 | 2024-Q3
EXP-001270 | 2024-09-01 | BOQ-PKG-10-01270 | PKG-10 | INV-PKG-10-011-01270 | 189.26 | 67345.48 | 3367.27 | Under Review | 63978.21 | 2024-Q3
EXP-003104 | 2024-09-01 | BOQ-PKG-04-01114 | PKG-04 | INV-PKG-04-025-03104 | 401.39 | 193459.7 | 9672.98 | Paid | 183786.72 | 2024-Q3
EXP-003254 | 2024-09-01 | BOQ-PKG-04-01264 | PKG-04 | INV-PKG-04-035-03254 | 238.96 | 69166.5 | 3458.32 | Paid | 65708.18 | 2024-Q3
EXP-003599 | 2024-09-01 | BOQ-PKG-09-01609 | PKG-09 | INV-PKG-09-030-03599 | 275.5 | 212870.05 | 10643.5 | Paid | 202226.55 | 2024-Q3
EXP-004254 | 2024-09-01 | BOQ-PKG-04-00274 | PKG-04 | INV-PKG-04-020-04254 | 172.66 | 122246.78 | 6112.34 | Paid | 116134.44 | 2024-Q3
EXP-000285 | 2024-09-02 | BOQ-PKG-05-00285 | PKG-05 | INV-PKG-05-006-00285 | 435.2 | 198824.29 | 9941.21 | Paid | 188883.08 | 2024-Q3
EXP-000355 | 2024-09-02 | BOQ-PKG-05-00355 | PKG-05 | INV-PKG-05-006-00355 | 360.36 | 44886.87 | 2244.34 | Under Review | 42642.53 | 2024-Q3
EXP-002155 | 2024-09-02 | BOQ-PKG-05-00165 | PKG-05 | INV-PKG-05-021-02155 | 93.36 | 122654.63 | 6132.73 | Paid | 116521.9 | 2024-Q3
EXP-002542 | 2024-09-02 | BOQ-PKG-02-00552 | PKG-02 | INV-PKG-02-023-02542 | 137.21 | 132169.4 | 6608.47 | Paid | 125560.93 | 2024-Q3
EXP-002687 | 2024-09-02 | BOQ-PKG-07-00697 | PKG-07 | INV-PKG-07-028-02687 | 160.35 | 53148.94 | 2657.45 | Paid | 50491.49 | 2024-Q3
EXP-003384 | 2024-09-02 | BOQ-PKG-04-01394 | PKG-04 | INV-PKG-04-025-03384 | 367.31 | 42753.77 | 2137.69 | Paid | 40616.08 | 2024-Q3
EXP-004090 | 2024-09-02 | BOQ-PKG-10-00110 | PKG-10 | INV-PKG-10-031-04090 | 89.33 | 188968.98 | 9448.45 | Paid | 179520.53 | 2024-Q3
EXP-004176 | 2024-09-02 | BOQ-PKG-06-00196 | PKG-06 | INV-PKG-06-012-04176 | 367.77 | 43740.71 | 2187.04 | Paid | 41553.67 | 2024-Q3
EXP-006649 | 2024-09-02 | BOQ-PKG-09-00679 | PKG-09 | INV-PKG-09-035-06649 | 206.35 | 153046.41 | 7652.32 | Paid | 145394.09 | 2024-Q3
EXP-006731 | 2024-09-02 | BOQ-PKG-01-00761 | PKG-01 | INV-PKG-01-012-06731 | 333.18 | 184321.98 | 9216.1 | Paid | 175105.88 | 2024-Q3
EXP-000788 | 2024-09-03 | BOQ-PKG-08-00788 | PKG-08 | INV-PKG-08-019-00788 | 307.86 | 45169.98 | 2258.5 | Paid | 42911.48 | 2024-Q3
EXP-001031 | 2024-09-03 | BOQ-PKG-01-01031 | PKG-01 | INV-PKG-01-017-01031 | 337.03 | 118983.44 | 5949.17 | Approved Pending Payment | 113034.27 | 2024-Q3
EXP-001698 | 2024-09-03 | BOQ-PKG-08-01698 | PKG-08 | INV-PKG-08-019-01698 | 101.86 | 49659.04 | 2482.95 | Paid | 47176.09 | 2024-Q3
EXP-003133 | 2024-09-03 | BOQ-PKG-03-01143 | PKG-03 | INV-PKG-03-019-03133 | 402.17 | 122877.56 | 6143.88 | Paid | 116733.68 | 2024-Q3
EXP-003686 | 2024-09-03 | BOQ-PKG-06-01696 | PKG-06 | INV-PKG-06-012-03686 | 294.33 | 123080.53 | 6154.03 | Paid | 116926.5 | 2024-Q3
EXP-004883 | 2024-09-03 | BOQ-PKG-03-00903 | PKG-03 | INV-PKG-03-019-04883 | 7.07 | 185366.61 | 9268.33 | Paid | 176098.28 | 2024-Q3
EXP-005350 | 2024-09-03 | BOQ-PKG-10-01370 | PKG-10 | INV-PKG-10-031-05350 | 299.62 | 40119.31 | 2005.97 | Paid | 38113.34 | 2024-Q3
EXP-006046 | 2024-09-03 | BOQ-PKG-06-00076 | PKG-06 | INV-PKG-06-027-06046 | 313.63 | 158448.44 | 7922.42 | Paid | 150526.02 | 2024-Q3
EXP-006503 | 2024-09-03 | BOQ-PKG-03-00533 | PKG-03 | INV-PKG-03-029-06503 | 307.45 | 189953.27 | 9497.66 | Paid | 180455.61 | 2024-Q3
EXP-006568 | 2024-09-03 | BOQ-PKG-08-00598 | PKG-08 | INV-PKG-08-024-06568 | 182.63 | 67870.76 | 3393.54 | Paid | 64477.22 | 2024-Q3
EXP-006691 | 2024-09-03 | BOQ-PKG-01-00721 | PKG-01 | INV-PKG-01-007-06691 | 285.91 | 73968.78 | 3698.44 | Paid | 70270.34 | 2024-Q3
EXP-000384 | 2024-09-04 | BOQ-PKG-04-00384 | PKG-04 | INV-PKG-04-035-00384 | 412.1 | 89628.64 | 4481.43 | Paid | 85147.21 | 2024-Q3
EXP-000669 | 2024-09-04 | BOQ-PKG-09-00669 | PKG-09 | INV-PKG-09-005-00669 | 241.78 | 115810.92 | 5790.55 | Paid | 110020.37 | 2024-Q3
EXP-002797 | 2024-09-04 | BOQ-PKG-07-00807 | PKG-07 | INV-PKG-07-033-02797 | 9.05 | 103775.7 | 5188.78 | Paid | 98586.92 | 2024-Q3
EXP-003311 | 2024-09-04 | BOQ-PKG-01-01321 | PKG-01 | INV-PKG-01-022-03311 | 263.99 | 99987.13 | 4999.36 | Paid | 94987.77 | 2024-Q3
EXP-005788 | 2024-09-04 | BOQ-PKG-08-01808 | PKG-08 | INV-PKG-08-014-05788 | 33.14 | 155132.96 | 7756.65 | Paid | 147376.31 | 2024-Q3
EXP-005897 | 2024-09-04 | BOQ-PKG-07-01917 | PKG-07 | INV-PKG-07-018-05897 | 259.83 | 187072.21 | 9353.61 | Paid | 177718.6 | 2024-Q3
EXP-006057 | 2024-09-04 | BOQ-PKG-07-00087 | PKG-07 | INV-PKG-07-003-06057 | 13.27 | 114899.71 | 5744.99 | Paid | 109154.72 | 2024-Q3
EXP-006610 | 2024-09-04 | BOQ-PKG-10-00640 | PKG-10 | INV-PKG-10-031-06610 | 167.99 | 45356.04 | 2267.8 | Paid | 43088.24 | 2024-Q3
EXP-000892 | 2024-09-05 | BOQ-PKG-02-00892 | PKG-02 | INV-PKG-02-018-00892 | 205.29 | 28379.66 | 1418.98 | Paid | 26960.68 | 2024-Q3
EXP-001080 | 2024-09-05 | BOQ-PKG-10-01080 | PKG-10 | INV-PKG-10-031-01080 | 314.42 | 103345.57 | 5167.28 | Paid | 98178.29 | 2024-Q3
EXP-001303 | 2024-09-05 | BOQ-PKG-03-01303 | PKG-03 | INV-PKG-03-009-01303 | 9.01 | 65976.12 | 3298.81 | Paid | 62677.31 | 2024-Q3
EXP-003192 | 2024-09-05 | BOQ-PKG-02-01202 | PKG-02 | INV-PKG-02-008-03192 | 323.56 | 173622.75 | 8681.14 | Paid | 164941.61 | 2024-Q3
EXP-005101 | 2024-09-05 | BOQ-PKG-01-01121 | PKG-01 | INV-PKG-01-027-05101 | 100.5 | 127859.63 | 6392.98 | Paid | 121466.65 | 2024-Q3
EXP-005455 | 2024-09-05 | BOQ-PKG-05-01475 | PKG-05 | INV-PKG-05-031-05455 | 79.86 | 148852.82 | 7442.64 | Paid | 141410.18 | 2024-Q3
EXP-000473 | 2024-09-06 | BOQ-PKG-03-00473 | PKG-03 | INV-PKG-03-019-00473 | 292.13 | 149180.08 | 7459 | Paid | 141721.08 | 2024-Q3
EXP-003643 | 2024-09-06 | BOQ-PKG-03-01653 | PKG-03 | INV-PKG-03-004-03643 | 87.32 | 65710.12 | 3285.51 | Paid | 62424.61 | 2024-Q3
EXP-005262 | 2024-09-06 | BOQ-PKG-02-01282 | PKG-02 | INV-PKG-02-013-05262 | 142.35 | 181669.29 | 9083.46 | Approved Pending Payment | 172585.83 | 2024-Q3
EXP-006465 | 2024-09-06 | BOQ-PKG-05-00495 | PKG-05 | INV-PKG-05-026-06465 | 418.92 | 59340.29 | 2967.01 | Disputed | 56373.28 | 2024-Q3
EXP-001448 | 2024-09-07 | BOQ-PKG-08-01448 | PKG-08 | INV-PKG-08-014-01448 | 197.34 | 147827.26 | 7391.36 | Paid | 140435.9 | 2024-Q3
EXP-001754 | 2024-09-07 | BOQ-PKG-04-01754 | PKG-04 | INV-PKG-04-005-01754 | 45.63 | 159808.32 | 7990.42 | Paid | 151817.9 | 2024-Q3
EXP-004375 | 2024-09-07 | BOQ-PKG-05-00395 | PKG-05 | INV-PKG-05-001-04375 | 221.12 | 127775.9 | 6388.8 | Paid | 121387.1 | 2024-Q3
EXP-000145 | 2024-09-08 | BOQ-PKG-05-00145 | PKG-05 | INV-PKG-05-006-00145 | 37.65 | 148858.92 | 7442.95 | Paid | 141415.97 | 2024-Q3
EXP-000512 | 2024-09-08 | BOQ-PKG-02-00512 | PKG-02 | INV-PKG-02-023-00512 | 302.85 | 189193.52 | 9459.68 | Paid | 179733.84 | 2024-Q3
EXP-000607 | 2024-09-08 | BOQ-PKG-07-00607 | PKG-07 | INV-PKG-07-013-00607 | 363.63 | 74315.96 | 3715.8 | Paid | 70600.16 | 2024-Q3
EXP-000820 | 2024-09-08 | BOQ-PKG-10-00820 | PKG-10 | INV-PKG-10-016-00820 | 276.24 | 131841.59 | 6592.08 | Paid | 125249.51 | 2024-Q3
EXP-003861 | 2024-09-08 | BOQ-PKG-01-01871 | PKG-01 | INV-PKG-01-012-03861 | 152.85 | 200130.03 | 10006.5 | Under Review | 190123.53 | 2024-Q3
EXP-004112 | 2024-09-08 | BOQ-PKG-02-00132 | PKG-02 | INV-PKG-02-018-04112 | 199.14 | 138038.74 | 6901.94 | Approved Pending Payment | 131136.8 | 2024-Q3
EXP-006317 | 2024-09-08 | BOQ-PKG-07-00347 | PKG-07 | INV-PKG-07-018-06317 | 21.85 | 181163.31 | 9058.17 | Paid | 172105.14 | 2024-Q3
EXP-001301 | 2024-09-09 | BOQ-PKG-01-01301 | PKG-01 | INV-PKG-01-007-01301 | 314.13 | 164259.45 | 8212.97 | Paid | 156046.48 | 2024-Q3
EXP-001963 | 2024-09-09 | BOQ-PKG-03-01963 | PKG-03 | INV-PKG-03-004-01963 | 117.51 | 144256.41 | 7212.82 | Under Review | 137043.59 | 2024-Q3
EXP-002286 | 2024-09-09 | BOQ-PKG-06-00296 | PKG-06 | INV-PKG-06-012-02286 | 331.58 | 75985.99 | 3799.3 | Paid | 72186.69 | 2024-Q3
EXP-002483 | 2024-09-09 | BOQ-PKG-03-00493 | PKG-03 | INV-PKG-03-034-02483 | 142.65 | 135541.34 | 6777.07 | Paid | 128764.27 | 2024-Q3
EXP-004163 | 2024-09-09 | BOQ-PKG-03-00183 | PKG-03 | INV-PKG-03-034-04163 | 100.56 | 160174.57 | 8008.73 | Paid | 152165.84 | 2024-Q3
EXP-006409 | 2024-09-09 | BOQ-PKG-09-00439 | PKG-09 | INV-PKG-09-005-06409 | 147.85 | 78409.67 | 3920.48 | Under Review | 74489.19 | 2024-Q3
EXP-006640 | 2024-09-09 | BOQ-PKG-10-00670 | PKG-10 | INV-PKG-10-026-06640 | 308.86 | 141274.78 | 7063.74 | Paid | 134211.04 | 2024-Q3
EXP-000908 | 2024-09-10 | BOQ-PKG-08-00908 | PKG-08 | INV-PKG-08-034-00908 | 430.38 | 195672.66 | 9783.63 | Approved Pending Payment | 185889.03 | 2024-Q3
EXP-001003 | 2024-09-10 | BOQ-PKG-03-01003 | PKG-03 | INV-PKG-03-024-01003 | 95.65 | 87331.02 | 4366.55 | Paid | 82964.47 | 2024-Q3
EXP-001437 | 2024-09-10 | BOQ-PKG-07-01437 | PKG-07 | INV-PKG-07-003-01437 | 149.51 | 183492.06 | 9174.6 | Paid | 174317.46 | 2024-Q3
EXP-001912 | 2024-09-10 | BOQ-PKG-02-01912 | PKG-02 | INV-PKG-02-023-01912 | 171.81 | 177834.87 | 8891.74 | Paid | 168943.13 | 2024-Q3
EXP-002336 | 2024-09-10 | BOQ-PKG-06-00346 | PKG-06 | INV-PKG-06-027-02336 | 180.91 | 203358.43 | 10167.92 | Paid | 193190.51 | 2024-Q3
EXP-002716 | 2024-09-10 | BOQ-PKG-06-00726 | PKG-06 | INV-PKG-06-022-02716 | 163.08 | 53470.99 | 2673.55 | Disputed | 50797.44 | 2024-Q3
EXP-002774 | 2024-09-10 | BOQ-PKG-04-00784 | PKG-04 | INV-PKG-04-010-02774 | 214.83 | 89003.17 | 4450.16 | Approved Pending Payment | 84553.01 | 2024-Q3
EXP-003808 | 2024-09-10 | BOQ-PKG-08-01818 | PKG-08 | INV-PKG-08-029-03808 | 354.27 | 102452.13 | 5122.61 | Paid | 97329.52 | 2024-Q3
EXP-004315 | 2024-09-10 | BOQ-PKG-05-00335 | PKG-05 | INV-PKG-05-011-04315 | 54.35 | 197644.67 | 9882.23 | Paid | 187762.44 | 2024-Q3
EXP-004564 | 2024-09-10 | BOQ-PKG-04-00584 | PKG-04 | INV-PKG-04-015-04564 | 209.35 | 46068.95 | 2303.45 | Paid | 43765.5 | 2024-Q3
EXP-005662 | 2024-09-10 | BOQ-PKG-02-01682 | PKG-02 | INV-PKG-02-028-05662 | 9.61 | 157035.36 | 7851.77 | Disputed | 149183.59 | 2024-Q3
EXP-006387 | 2024-09-10 | BOQ-PKG-07-00417 | PKG-07 | INV-PKG-07-018-06387 | 92.52 | 144399.78 | 7219.99 | Paid | 137179.79 | 2024-Q3
EXP-006658 | 2024-09-10 | BOQ-PKG-08-00688 | PKG-08 | INV-PKG-08-009-06658 | 298.89 | 44651.69 | 2232.58 | Paid | 42419.11 | 2024-Q3
EXP-000898 | 2024-09-11 | BOQ-PKG-08-00898 | PKG-08 | INV-PKG-08-024-00898 | 199.37 | 119117.15 | 5955.86 | Paid | 113161.29 | 2024-Q3
EXP-001163 | 2024-09-11 | BOQ-PKG-03-01163 | PKG-03 | INV-PKG-03-009-01163 | 235.24 | 26237.94 | 1311.9 | Paid | 24926.04 | 2024-Q3
EXP-001194 | 2024-09-11 | BOQ-PKG-04-01194 | PKG-04 | INV-PKG-04-005-01194 | 152.24 | 74378.36 | 3718.92 | Paid | 70659.44 | 2024-Q3
EXP-003649 | 2024-09-11 | BOQ-PKG-09-01659 | PKG-09 | INV-PKG-09-010-03649 | 335.27 | 34487.85 | 1724.39 | Paid | 32763.46 | 2024-Q3
EXP-004545 | 2024-09-11 | BOQ-PKG-05-00565 | PKG-05 | INV-PKG-05-031-04545 | 61.31 | 143774 | 7188.7 | Paid | 136585.3 | 2024-Q3
EXP-006227 | 2024-09-11 | BOQ-PKG-07-00257 | PKG-07 | INV-PKG-07-033-06227 | 65.27 | 112390.89 | 5619.54 | Paid | 106771.35 | 2024-Q3
EXP-000959 | 2024-09-12 | BOQ-PKG-09-00959 | PKG-09 | INV-PKG-09-015-00959 | 122.14 | 126907.02 | 6345.35 | Under Review | 120561.67 | 2024-Q3
EXP-001484 | 2024-09-12 | BOQ-PKG-04-01484 | PKG-04 | INV-PKG-04-015-01484 | 344.82 | 150277.69 | 7513.88 | Paid | 142763.81 | 2024-Q3
EXP-001968 | 2024-09-12 | BOQ-PKG-08-01968 | PKG-08 | INV-PKG-08-009-01968 | 120.25 | 116493.13 | 5824.66 | Paid | 110668.47 | 2024-Q3
EXP-004199 | 2024-09-12 | BOQ-PKG-09-00219 | PKG-09 | INV-PKG-09-035-04199 | 27.1 | 174019.74 | 8700.99 | Under Review | 165318.75 | 2024-Q3
EXP-000846 | 2024-09-13 | BOQ-PKG-06-00846 | PKG-06 | INV-PKG-06-007-00846 | 61.53 | 34335.58 | 1716.78 | Paid | 32618.8 | 2024-Q3
EXP-001985 | 2024-09-13 | BOQ-PKG-05-01985 | PKG-05 | INV-PKG-05-026-01985 | 367.06 | 143130.55 | 7156.53 | Paid | 135974.02 | 2024-Q3
EXP-002167 | 2024-09-13 | BOQ-PKG-07-00177 | PKG-07 | INV-PKG-07-033-02167 | 221.17 | 115124.31 | 5756.22 | Paid | 109368.09 | 2024-Q3
EXP-004135 | 2024-09-13 | BOQ-PKG-05-00155 | PKG-05 | INV-PKG-05-006-04135 | 84.15 | 56763.17 | 2838.16 | Paid | 53925.01 | 2024-Q3
EXP-006381 | 2024-09-13 | BOQ-PKG-01-00411 | PKG-01 | INV-PKG-01-012-06381 | 182.29 | 116495.13 | 5824.76 | Disputed | 110670.37 | 2024-Q3
EXP-006517 | 2024-09-13 | BOQ-PKG-07-00547 | PKG-07 | INV-PKG-07-008-06517 | 79.99 | 95396.26 | 4769.81 | Paid | 90626.45 | 2024-Q3
EXP-006602 | 2024-09-13 | BOQ-PKG-02-00632 | PKG-02 | INV-PKG-02-023-06602 | 427.13 | 136595.8 | 6829.79 | Paid | 129766.01 | 2024-Q3
EXP-000657 | 2024-09-14 | BOQ-PKG-07-00657 | PKG-07 | INV-PKG-07-028-00657 | 89.73 | 143194.34 | 7159.72 | Approved Pending Payment | 136034.62 | 2024-Q3
EXP-001096 | 2024-09-14 | BOQ-PKG-06-01096 | PKG-06 | INV-PKG-06-012-01096 | 174.19 | 188999.63 | 9449.98 | Paid | 179549.65 | 2024-Q3
EXP-000190 | 2024-09-15 | BOQ-PKG-10-00190 | PKG-10 | INV-PKG-10-016-00190 | 211.94 | 67584.22 | 3379.21 | Under Review | 64205.01 | 2024-Q3
EXP-001877 | 2024-09-15 | BOQ-PKG-07-01877 | PKG-07 | INV-PKG-07-023-01877 | 174.74 | 89533.97 | 4476.7 | Paid | 85057.27 | 2024-Q3
EXP-002187 | 2024-09-15 | BOQ-PKG-07-00197 | PKG-07 | INV-PKG-07-018-02187 | 247.03 | 163353.53 | 8167.68 | Paid | 155185.85 | 2024-Q3
EXP-004093 | 2024-09-15 | BOQ-PKG-03-00113 | PKG-03 | INV-PKG-03-034-04093 | 18.64 | 46060.07 | 2303 | Paid | 43757.07 | 2024-Q3
EXP-004264 | 2024-09-15 | BOQ-PKG-04-00284 | PKG-04 | INV-PKG-04-030-04264 | 368.48 | 62158.06 | 3107.9 | Paid | 59050.16 | 2024-Q3
EXP-004327 | 2024-09-15 | BOQ-PKG-07-00347 | PKG-07 | INV-PKG-07-023-04327 | 143.05 | 109008.67 | 5450.43 | Paid | 103558.24 | 2024-Q3
EXP-004734 | 2024-09-15 | BOQ-PKG-04-00754 | PKG-04 | INV-PKG-04-010-04734 | 177.37 | 33628.52 | 1681.43 | Approved Pending Payment | 31947.09 | 2024-Q3
EXP-000271 | 2024-09-16 | BOQ-PKG-01-00271 | PKG-01 | INV-PKG-01-027-00271 | 145.82 | 39556.08 | 1977.8 | Disputed | 37578.28 | 2024-Q3
EXP-000380 | 2024-09-16 | BOQ-PKG-10-00380 | PKG-10 | INV-PKG-10-031-00380 | 390.82 | 148292.78 | 7414.64 | Paid | 140878.14 | 2024-Q3
EXP-001217 | 2024-09-16 | BOQ-PKG-07-01217 | PKG-07 | INV-PKG-07-028-01217 | 21.8 | 130017.79 | 6500.89 | Paid | 123516.9 | 2024-Q3
EXP-004718 | 2024-09-16 | BOQ-PKG-08-00738 | PKG-08 | INV-PKG-08-029-04718 | 235.84 | 139254.55 | 6962.73 | Under Review | 132291.82 | 2024-Q3
EXP-006157 | 2024-09-16 | BOQ-PKG-07-00187 | PKG-07 | INV-PKG-07-033-06157 | 298.85 | 41493.33 | 2074.67 | Paid | 39418.66 | 2024-Q3
EXP-006300 | 2024-09-16 | BOQ-PKG-10-00330 | PKG-10 | INV-PKG-10-001-06300 | 122.64 | 199900.29 | 9995.01 | Paid | 189905.28 | 2024-Q3
EXP-006360 | 2024-09-16 | BOQ-PKG-10-00390 | PKG-10 | INV-PKG-10-026-06360 | 326.08 | 35983.19 | 1799.16 | Paid | 34184.03 | 2024-Q3
EXP-006521 | 2024-09-16 | BOQ-PKG-01-00551 | PKG-01 | INV-PKG-01-012-06521 | 224.24 | 201214.03 | 10060.7 | Under Review | 191153.33 | 2024-Q3
EXP-000008 | 2024-09-17 | BOQ-PKG-08-00008 | PKG-08 | INV-PKG-08-009-00008 | 399.31 | 188138.49 | 9406.92 | Paid | 178731.57 | 2024-Q3
EXP-002201 | 2024-09-17 | BOQ-PKG-01-00211 | PKG-01 | INV-PKG-01-032-02201 | 158.12 | 206813.83 | 10340.69 | Approved Pending Payment | 196473.14 | 2024-Q3
EXP-003375 | 2024-09-17 | BOQ-PKG-05-01385 | PKG-05 | INV-PKG-05-016-03375 | 276.87 | 32722.22 | 1636.11 | Under Review | 31086.11 | 2024-Q3
EXP-003774 | 2024-09-17 | BOQ-PKG-04-01784 | PKG-04 | INV-PKG-04-030-03774 | 382.99 | 59898.58 | 2994.93 | Paid | 56903.65 | 2024-Q3
EXP-004819 | 2024-09-17 | BOQ-PKG-09-00839 | PKG-09 | INV-PKG-09-025-04819 | 379.58 | 201885.9 | 10094.3 | Approved Pending Payment | 191791.6 | 2024-Q3
EXP-005882 | 2024-09-17 | BOQ-PKG-02-01902 | PKG-02 | INV-PKG-02-003-05882 | 382.65 | 168369.15 | 8418.46 | Paid | 159950.69 | 2024-Q3
EXP-006062 | 2024-09-17 | BOQ-PKG-02-00092 | PKG-02 | INV-PKG-02-008-06062 | 295.52 | 45344.92 | 2267.25 | Paid | 43077.67 | 2024-Q3
EXP-006089 | 2024-09-17 | BOQ-PKG-09-00119 | PKG-09 | INV-PKG-09-035-06089 | 407.49 | 82777.71 | 4138.89 | Paid | 78638.82 | 2024-Q3
EXP-006148 | 2024-09-17 | BOQ-PKG-08-00178 | PKG-08 | INV-PKG-08-024-06148 | 213.18 | 152099.63 | 7604.98 | Paid | 144494.65 | 2024-Q3
EXP-006313 | 2024-09-17 | BOQ-PKG-03-00343 | PKG-03 | INV-PKG-03-014-06313 | 83.34 | 63281.07 | 3164.05 | Paid | 60117.02 | 2024-Q3
EXP-000315 | 2024-09-18 | BOQ-PKG-05-00315 | PKG-05 | INV-PKG-05-001-00315 | 176.35 | 201733.34 | 10086.67 | Approved Pending Payment | 191646.67 | 2024-Q3
EXP-000790 | 2024-09-18 | BOQ-PKG-10-00790 | PKG-10 | INV-PKG-10-021-00790 | 384.74 | 189114.69 | 9455.73 | Paid | 179658.96 | 2024-Q3
EXP-003833 | 2024-09-18 | BOQ-PKG-03-01843 | PKG-03 | INV-PKG-03-019-03833 | 179.98 | 121853.12 | 6092.66 | Under Review | 115760.46 | 2024-Q3
EXP-005125 | 2024-09-18 | BOQ-PKG-05-01145 | PKG-05 | INV-PKG-05-016-05125 | 95.96 | 87335.01 | 4366.75 | Approved Pending Payment | 82968.26 | 2024-Q3
EXP-005818 | 2024-09-18 | BOQ-PKG-08-01838 | PKG-08 | INV-PKG-08-009-05818 | 284.18 | 135726.83 | 6786.34 | Paid | 128940.49 | 2024-Q3
EXP-005973 | 2024-09-18 | BOQ-PKG-03-00003 | PKG-03 | INV-PKG-03-024-05973 | 20.1 | 160596.07 | 8029.8 | Paid | 152566.27 | 2024-Q3
EXP-006214 | 2024-09-18 | BOQ-PKG-04-00244 | PKG-04 | INV-PKG-04-020-06214 | 222.85 | 34269.4 | 1713.47 | Paid | 32555.93 | 2024-Q3
EXP-006706 | 2024-09-18 | BOQ-PKG-06-00736 | PKG-06 | INV-PKG-06-022-06706 | 341.98 | 84806.86 | 4240.34 | Paid | 80566.52 | 2024-Q3
EXP-000103 | 2024-09-19 | BOQ-PKG-03-00103 | PKG-03 | INV-PKG-03-034-00103 | 314.25 | 132890.19 | 6644.51 | Approved Pending Payment | 126245.68 | 2024-Q3
EXP-003762 | 2024-09-19 | BOQ-PKG-02-01772 | PKG-02 | INV-PKG-02-018-03762 | 288.78 | 205095 | 10254.75 | Under Review | 194840.25 | 2024-Q3
EXP-004396 | 2024-09-19 | BOQ-PKG-06-00416 | PKG-06 | INV-PKG-06-022-04396 | 157.7 | 123404.49 | 6170.22 | Approved Pending Payment | 117234.27 | 2024-Q3
EXP-005647 | 2024-09-19 | BOQ-PKG-07-01667 | PKG-07 | INV-PKG-07-013-05647 | 343.84 | 118744.84 | 5937.24 | Paid | 112807.6 | 2024-Q3
EXP-006529 | 2024-09-19 | BOQ-PKG-09-00559 | PKG-09 | INV-PKG-09-020-06529 | 397.6 | 136246.83 | 6812.34 | Paid | 129434.49 | 2024-Q3
EXP-000410 | 2024-09-20 | BOQ-PKG-10-00410 | PKG-10 | INV-PKG-10-026-00410 | 394.27 | 48832.45 | 2441.62 | Paid | 46390.83 | 2024-Q3
EXP-001227 | 2024-09-20 | BOQ-PKG-07-01227 | PKG-07 | INV-PKG-07-003-01227 | 20.91 | 155366.2 | 7768.31 | Paid | 147597.89 | 2024-Q3
EXP-001461 | 2024-09-20 | BOQ-PKG-01-01461 | PKG-01 | INV-PKG-01-027-01461 | 114.16 | 196394.78 | 9819.74 | Under Review | 186575.04 | 2024-Q3
EXP-001835 | 2024-09-20 | BOQ-PKG-05-01835 | PKG-05 | INV-PKG-05-016-01835 | 25.13 | 24003.05 | 1200.15 | Paid | 22802.9 | 2024-Q3
EXP-003506 | 2024-09-20 | BOQ-PKG-06-01516 | PKG-06 | INV-PKG-06-007-03506 | 398.7 | 155037.49 | 7751.87 | Paid | 147285.62 | 2024-Q3
EXP-001518 | 2024-09-21 | BOQ-PKG-08-01518 | PKG-08 | INV-PKG-08-014-01518 | 6.75 | 112799.57 | 5639.98 | Approved Pending Payment | 107159.59 | 2024-Q3
EXP-001722 | 2024-09-21 | BOQ-PKG-02-01722 | PKG-02 | INV-PKG-02-008-01722 | 97.79 | 172636.02 | 8631.8 | Paid | 164004.22 | 2024-Q3
EXP-005138 | 2024-09-21 | BOQ-PKG-08-01158 | PKG-08 | INV-PKG-08-029-05138 | 237.02 | 211373.08 | 10568.65 | Paid | 200804.43 | 2024-Q3
EXP-006457 | 2024-09-21 | BOQ-PKG-07-00487 | PKG-07 | INV-PKG-07-018-06457 | 314.19 | 103086.49 | 5154.32 | Approved Pending Payment | 97932.17 | 2024-Q3
EXP-006498 | 2024-09-21 | BOQ-PKG-08-00528 | PKG-08 | INV-PKG-08-024-06498 | 114.06 | 64488.25 | 3224.41 | Approved Pending Payment | 61263.84 | 2024-Q3
EXP-006619 | 2024-09-21 | BOQ-PKG-09-00649 | PKG-09 | INV-PKG-09-005-06619 | 325.86 | 115047.32 | 5752.37 | Paid | 109294.95 | 2024-Q3
EXP-000363 | 2024-09-22 | BOQ-PKG-03-00363 | PKG-03 | INV-PKG-03-014-00363 | 299.97 | 210849.64 | 10542.48 | Paid | 200307.16 | 2024-Q3
EXP-000497 | 2024-09-22 | BOQ-PKG-07-00497 | PKG-07 | INV-PKG-07-008-00497 | 310.31 | 197435.05 | 9871.75 | Approved Pending Payment | 187563.3 | 2024-Q3
EXP-000997 | 2024-09-22 | BOQ-PKG-07-00997 | PKG-07 | INV-PKG-07-018-00997 | 236.18 | 103924.82 | 5196.24 | Paid | 98728.58 | 2024-Q3
EXP-001065 | 2024-09-22 | BOQ-PKG-05-01065 | PKG-05 | INV-PKG-05-016-01065 | 225.3 | 182069.72 | 9103.49 | Approved Pending Payment | 172966.23 | 2024-Q3
EXP-001067 | 2024-09-22 | BOQ-PKG-07-01067 | PKG-07 | INV-PKG-07-018-01067 | 160.69 | 154573.67 | 7728.68 | Paid | 146844.99 | 2024-Q3
EXP-001444 | 2024-09-22 | BOQ-PKG-04-01444 | PKG-04 | INV-PKG-04-010-01444 | 376.68 | 84930.07 | 4246.5 | Under Review | 80683.57 | 2024-Q3
EXP-003024 | 2024-09-22 | BOQ-PKG-04-01034 | PKG-04 | INV-PKG-04-015-03024 | 299.3 | 133252.4 | 6662.62 | Paid | 126589.78 | 2024-Q3
EXP-004438 | 2024-09-22 | BOQ-PKG-08-00458 | PKG-08 | INV-PKG-08-029-04438 | 416.91 | 77878.93 | 3893.95 | Paid | 73984.98 | 2024-Q3
EXP-006061 | 2024-09-22 | BOQ-PKG-01-00091 | PKG-01 | INV-PKG-01-007-06061 | 35.65 | 166012.97 | 8300.65 | Approved Pending Payment | 157712.32 | 2024-Q3
EXP-000346 | 2024-09-23 | BOQ-PKG-06-00346 | PKG-06 | INV-PKG-06-032-00346 | 403.64 | 43788.08 | 2189.4 | Under Review | 41598.68 | 2024-Q3
EXP-001737 | 2024-09-23 | BOQ-PKG-07-01737 | PKG-07 | INV-PKG-07-023-01737 | 273.46 | 150636.74 | 7531.84 | Paid | 143104.9 | 2024-Q3
EXP-001856 | 2024-09-23 | BOQ-PKG-06-01856 | PKG-06 | INV-PKG-06-002-01856 | 47.2 | 85480.23 | 4274.01 | Paid | 81206.22 | 2024-Q3
EXP-002190 | 2024-09-23 | BOQ-PKG-10-00200 | PKG-10 | INV-PKG-10-021-02190 | 421.43 | 106244.42 | 5312.22 | Paid | 100932.2 | 2024-Q3
EXP-002722 | 2024-09-23 | BOQ-PKG-02-00732 | PKG-02 | INV-PKG-02-028-02722 | 295.28 | 126928.97 | 6346.45 | Paid | 120582.52 | 2024-Q3
EXP-003036 | 2024-09-23 | BOQ-PKG-06-01046 | PKG-06 | INV-PKG-06-027-03036 | 136.95 | 59063.99 | 2953.2 | Paid | 56110.79 | 2024-Q3
EXP-003919 | 2024-09-23 | BOQ-PKG-09-01929 | PKG-09 | INV-PKG-09-035-03919 | 260.5 | 206019.37 | 10300.97 | Under Review | 195718.4 | 2024-Q3
EXP-004534 | 2024-09-23 | BOQ-PKG-04-00554 | PKG-04 | INV-PKG-04-020-04534 | 375.73 | 174716.71 | 8735.84 | Approved Pending Payment | 165980.87 | 2024-Q3
EXP-006079 | 2024-09-23 | BOQ-PKG-09-00109 | PKG-09 | INV-PKG-09-025-06079 | 281.68 | 70676.19 | 3533.81 | Paid | 67142.38 | 2024-Q3
EXP-002231 | 2024-09-24 | BOQ-PKG-01-00241 | PKG-01 | INV-PKG-01-027-02231 | 443.27 | 186898.46 | 9344.92 | Approved Pending Payment | 177553.54 | 2024-Q3
EXP-004945 | 2024-09-24 | BOQ-PKG-05-00965 | PKG-05 | INV-PKG-05-011-04945 | 14.97 | 173321.12 | 8666.06 | Paid | 164655.06 | 2024-Q3
EXP-005061 | 2024-09-24 | BOQ-PKG-01-01081 | PKG-01 | INV-PKG-01-022-05061 | 123.85 | 178016.49 | 8900.82 | Paid | 169115.67 | 2024-Q3
EXP-005517 | 2024-09-24 | BOQ-PKG-07-01537 | PKG-07 | INV-PKG-07-023-05517 | 26.79 | 41069.38 | 2053.47 | Under Review | 39015.91 | 2024-Q3
EXP-005543 | 2024-09-24 | BOQ-PKG-03-01563 | PKG-03 | INV-PKG-03-014-05543 | 179.9 | 80481.9 | 4024.1 | Paid | 76457.8 | 2024-Q3
EXP-006552 | 2024-09-24 | BOQ-PKG-02-00582 | PKG-02 | INV-PKG-02-008-06552 | 35.87 | 85648.17 | 4282.41 | Under Review | 81365.76 | 2024-Q3
EXP-000006 | 2024-09-25 | BOQ-PKG-06-00006 | PKG-06 | INV-PKG-06-007-00006 | 165.68 | 101611.65 | 5080.58 | Paid | 96531.07 | 2024-Q3
EXP-000325 | 2024-09-25 | BOQ-PKG-05-00325 | PKG-05 | INV-PKG-05-011-00325 | 145.47 | 47899.91 | 2395 | Paid | 45504.91 | 2024-Q3
EXP-000674 | 2024-09-25 | BOQ-PKG-04-00674 | PKG-04 | INV-PKG-04-010-00674 | 207.45 | 113649.18 | 5682.46 | Under Review | 107966.72 | 2024-Q3
EXP-001419 | 2024-09-25 | BOQ-PKG-09-01419 | PKG-09 | INV-PKG-09-020-01419 | 410.66 | 89397.07 | 4469.85 | Paid | 84927.22 | 2024-Q3
EXP-002419 | 2024-09-25 | BOQ-PKG-09-00429 | PKG-09 | INV-PKG-09-005-02419 | 259.5 | 210059.07 | 10502.95 | Under Review | 199556.12 | 2024-Q3
EXP-002875 | 2024-09-25 | BOQ-PKG-05-00885 | PKG-05 | INV-PKG-05-006-02875 | 400.58 | 173738.91 | 8686.95 | Paid | 165051.96 | 2024-Q3
EXP-003492 | 2024-09-25 | BOQ-PKG-02-01502 | PKG-02 | INV-PKG-02-028-03492 | 247.32 | 171654.31 | 8582.72 | Paid | 163071.59 | 2024-Q3
EXP-004856 | 2024-09-25 | BOQ-PKG-06-00876 | PKG-06 | INV-PKG-06-027-04856 | 232.36 | 86283.41 | 4314.17 | Paid | 81969.24 | 2024-Q3
EXP-000111 | 2024-09-26 | BOQ-PKG-01-00111 | PKG-01 | INV-PKG-01-007-00111 | 93.4 | 68966.93 | 3448.35 | Paid | 65518.58 | 2024-Q3
EXP-000493 | 2024-09-26 | BOQ-PKG-03-00493 | PKG-03 | INV-PKG-03-004-00493 | 14.36 | 153081.69 | 7654.08 | Paid | 145427.61 | 2024-Q3
EXP-003191 | 2024-09-26 | BOQ-PKG-01-01201 | PKG-01 | INV-PKG-01-007-03191 | 340.62 | 69795.06 | 3489.75 | Approved Pending Payment | 66305.31 | 2024-Q3
EXP-004369 | 2024-09-26 | BOQ-PKG-09-00389 | PKG-09 | INV-PKG-09-030-04369 | 225.05 | 148175.13 | 7408.76 | Paid | 140766.37 | 2024-Q3
EXP-005828 | 2024-09-26 | BOQ-PKG-08-01848 | PKG-08 | INV-PKG-08-019-05828 | 57.51 | 131073.88 | 6553.69 | Approved Pending Payment | 124520.19 | 2024-Q3
EXP-006809 | 2024-09-26 | BOQ-PKG-09-00839 | PKG-09 | INV-PKG-09-020-06809 | 211.43 | 93628.27 | 4681.41 | Paid | 88946.86 | 2024-Q3
EXP-000893 | 2024-09-27 | BOQ-PKG-03-00893 | PKG-03 | INV-PKG-03-019-00893 | 97.04 | 145093.3 | 7254.66 | Paid | 137838.64 | 2024-Q3
EXP-000921 | 2024-09-27 | BOQ-PKG-01-00921 | PKG-01 | INV-PKG-01-012-00921 | 346.95 | 185054.42 | 9252.72 | Paid | 175801.7 | 2024-Q3
EXP-001156 | 2024-09-27 | BOQ-PKG-06-01156 | PKG-06 | INV-PKG-06-002-01156 | 113.01 | 204139.27 | 10206.96 | Paid | 193932.31 | 2024-Q3
EXP-001727 | 2024-09-27 | BOQ-PKG-07-01727 | PKG-07 | INV-PKG-07-013-01727 | 20.57 | 71422.1 | 3571.11 | Under Review | 67850.99 | 2024-Q3
EXP-006805 | 2024-09-27 | BOQ-PKG-05-00835 | PKG-05 | INV-PKG-05-016-06805 | 300.34 | 91221.22 | 4561.06 | Paid | 86660.16 | 2024-Q3
EXP-006923 | 2024-09-27 | BOQ-PKG-03-00953 | PKG-03 | INV-PKG-03-029-06923 | 25.68 | 52251.03 | 2612.55 | Paid | 49638.48 | 2024-Q3
EXP-000141 | 2024-09-28 | BOQ-PKG-01-00141 | PKG-01 | INV-PKG-01-002-00141 | 115.71 | 196673.98 | 9833.7 | Approved Pending Payment | 186840.28 | 2024-Q3
EXP-001039 | 2024-09-28 | BOQ-PKG-09-01039 | PKG-09 | INV-PKG-09-025-01039 | 385.66 | 28898.31 | 1444.92 | Paid | 27453.39 | 2024-Q3
EXP-002723 | 2024-09-28 | BOQ-PKG-03-00733 | PKG-03 | INV-PKG-03-029-02723 | 358.7 | 64970.35 | 3248.52 | Approved Pending Payment | 61721.83 | 2024-Q3
EXP-003086 | 2024-09-28 | BOQ-PKG-06-01096 | PKG-06 | INV-PKG-06-007-03086 | 70.32 | 78465.52 | 3923.28 | Paid | 74542.24 | 2024-Q3
EXP-006334 | 2024-09-28 | BOQ-PKG-04-00364 | PKG-04 | INV-PKG-04-035-06334 | 175.15 | 134302.8 | 6715.14 | Paid | 127587.66 | 2024-Q3
EXP-000031 | 2024-09-29 | BOQ-PKG-01-00031 | PKG-01 | INV-PKG-01-032-00031 | 101.96 | 149055.23 | 7452.76 | Paid | 141602.47 | 2024-Q3
EXP-000524 | 2024-09-29 | BOQ-PKG-04-00524 | PKG-04 | INV-PKG-04-035-00524 | 57.29 | 73328.32 | 3666.42 | Paid | 69661.9 | 2024-Q3
EXP-000983 | 2024-09-29 | BOQ-PKG-03-00983 | PKG-03 | INV-PKG-03-004-00983 | 375.14 | 206903.89 | 10345.19 | Paid | 196558.7 | 2024-Q3
EXP-001009 | 2024-09-29 | BOQ-PKG-09-01009 | PKG-09 | INV-PKG-09-030-01009 | 392.84 | 112748.03 | 5637.4 | Paid | 107110.63 | 2024-Q3
EXP-001425 | 2024-09-29 | BOQ-PKG-05-01425 | PKG-05 | INV-PKG-05-026-01425 | 394.37 | 165271.89 | 8263.59 | Approved Pending Payment | 157008.3 | 2024-Q3
EXP-001953 | 2024-09-29 | BOQ-PKG-03-01953 | PKG-03 | INV-PKG-03-029-01953 | 40.99 | 148340.27 | 7417.01 | Paid | 140923.26 | 2024-Q3
EXP-002209 | 2024-09-29 | BOQ-PKG-09-00219 | PKG-09 | INV-PKG-09-005-02209 | 375.27 | 40416.43 | 2020.82 | Paid | 38395.61 | 2024-Q3
EXP-002806 | 2024-09-29 | BOQ-PKG-06-00816 | PKG-06 | INV-PKG-06-007-02806 | 157.22 | 198934.09 | 9946.7 | Paid | 188987.39 | 2024-Q3
EXP-003238 | 2024-09-29 | BOQ-PKG-08-01248 | PKG-08 | INV-PKG-08-019-03238 | 207.15 | 174041.5 | 8702.08 | Approved Pending Payment | 165339.42 | 2024-Q3
EXP-003341 | 2024-09-29 | BOQ-PKG-01-01351 | PKG-01 | INV-PKG-01-017-03341 | 183.33 | 113604.46 | 5680.22 | Paid | 107924.24 | 2024-Q3
EXP-003394 | 2024-09-29 | BOQ-PKG-04-01404 | PKG-04 | INV-PKG-04-035-03394 | 446.89 | 56836.68 | 2841.83 | Paid | 53994.85 | 2024-Q3
EXP-004143 | 2024-09-29 | BOQ-PKG-03-00163 | PKG-03 | INV-PKG-03-014-04143 | 269.09 | 74470.93 | 3723.55 | Paid | 70747.38 | 2024-Q3
EXP-005232 | 2024-09-29 | BOQ-PKG-02-01252 | PKG-02 | INV-PKG-02-018-05232 | 408.87 | 199107.73 | 9955.39 | Paid | 189152.34 | 2024-Q3
EXP-006903 | 2024-09-29 | BOQ-PKG-03-00933 | PKG-03 | INV-PKG-03-009-06903 | 125 | 160653.91 | 8032.7 | Approved Pending Payment | 152621.21 | 2024-Q3
EXP-000804 | 2024-09-30 | BOQ-PKG-04-00804 | PKG-04 | INV-PKG-04-035-00804 | 98.24 | 112438.75 | 5621.94 | Paid | 106816.81 | 2024-Q3
EXP-001411 | 2024-09-30 | BOQ-PKG-01-01411 | PKG-01 | INV-PKG-01-012-01411 | 6.09 | 103372.2 | 5168.61 | Approved Pending Payment | 98203.59 | 2024-Q3
EXP-001457 | 2024-09-30 | BOQ-PKG-07-01457 | PKG-07 | INV-PKG-07-023-01457 | 139.67 | 137596.2 | 6879.81 | Approved Pending Payment | 130716.39 | 2024-Q3
EXP-001623 | 2024-09-30 | BOQ-PKG-03-01623 | PKG-03 | INV-PKG-03-014-01623 | 113.81 | 50882.48 | 2544.12 | Paid | 48338.36 | 2024-Q3
EXP-001821 | 2024-09-30 | BOQ-PKG-01-01821 | PKG-01 | INV-PKG-01-002-01821 | 80.5 | 116111.97 | 5805.6 | Paid | 110306.37 | 2024-Q3
EXP-001997 | 2024-09-30 | BOQ-PKG-07-00007 | PKG-07 | INV-PKG-07-003-01997 | 261.94 | 191013.42 | 9550.67 | Approved Pending Payment | 181462.75 | 2024-Q3
EXP-002230 | 2024-09-30 | BOQ-PKG-10-00240 | PKG-10 | INV-PKG-10-026-02230 | 289.95 | 114498.41 | 5724.92 | Paid | 108773.49 | 2024-Q3
EXP-002370 | 2024-09-30 | BOQ-PKG-10-00380 | PKG-10 | INV-PKG-10-026-02370 | 137.49 | 126197.34 | 6309.87 | Paid | 119887.47 | 2024-Q3
EXP-003260 | 2024-09-30 | BOQ-PKG-10-01270 | PKG-10 | INV-PKG-10-006-03260 | 122.63 | 88983.78 | 4449.19 | Paid | 84534.59 | 2024-Q3
EXP-004032 | 2024-09-30 | BOQ-PKG-02-00052 | PKG-02 | INV-PKG-02-008-04032 | 259.02 | 137518.82 | 6875.94 | Paid | 130642.88 | 2024-Q3
EXP-004442 | 2024-09-30 | BOQ-PKG-02-00462 | PKG-02 | INV-PKG-02-033-04442 | 259.48 | 71014.82 | 3550.74 | Paid | 67464.08 | 2024-Q3
EXP-004489 | 2024-09-30 | BOQ-PKG-09-00509 | PKG-09 | INV-PKG-09-010-04489 | 119.13 | 71490.06 | 3574.5 | Approved Pending Payment | 67915.56 | 2024-Q3
EXP-005344 | 2024-09-30 | BOQ-PKG-04-01364 | PKG-04 | INV-PKG-04-025-05344 | 422.74 | 58248.75 | 2912.44 | Paid | 55336.31 | 2024-Q3
EXP-006540 | 2024-09-30 | BOQ-PKG-10-00570 | PKG-10 | INV-PKG-10-031-06540 | 7.72 | 172174.45 | 8608.72 | Paid | 163565.73 | 2024-Q3
EXP-006735 | 2024-09-30 | BOQ-PKG-05-00765 | PKG-05 | INV-PKG-05-016-06735 | 41.89 | 29190.24 | 1459.51 | Paid | 27730.73 | 2024-Q3
EXP-000334 | 2024-10-01 | BOQ-PKG-04-00334 | PKG-04 | INV-PKG-04-020-00334 | 16.84 | 162800.53 | 8140.03 | Paid | 154660.5 | 2024-Q4
EXP-000995 | 2024-10-01 | BOQ-PKG-05-00995 | PKG-05 | INV-PKG-05-016-00995 | 371.72 | 25058.18 | 1252.91 | Paid | 23805.27 | 2024-Q4
EXP-001121 | 2024-10-01 | BOQ-PKG-01-01121 | PKG-01 | INV-PKG-01-002-01121 | 248.69 | 49460.26 | 2473.01 | Under Review | 46987.25 | 2024-Q4
EXP-001220 | 2024-10-01 | BOQ-PKG-10-01220 | PKG-10 | INV-PKG-10-031-01220 | 95.18 | 102796.58 | 5139.83 | Disputed | 97656.75 | 2024-Q4
EXP-001666 | 2024-10-01 | BOQ-PKG-06-01666 | PKG-06 | INV-PKG-06-022-01666 | 229.78 | 197729.49 | 9886.47 | Paid | 187843.02 | 2024-Q4
EXP-003884 | 2024-10-01 | BOQ-PKG-04-01894 | PKG-04 | INV-PKG-04-035-03884 | 183.72 | 101027.52 | 5051.38 | Paid | 95976.14 | 2024-Q4
EXP-004908 | 2024-10-01 | BOQ-PKG-08-00928 | PKG-08 | INV-PKG-08-009-04908 | 111.34 | 115147.02 | 5757.35 | Paid | 109389.67 | 2024-Q4
EXP-006142 | 2024-10-01 | BOQ-PKG-02-00172 | PKG-02 | INV-PKG-02-018-06142 | 48.57 | 67094.62 | 3354.73 | Paid | 63739.89 | 2024-Q4
EXP-002977 | 2024-10-02 | BOQ-PKG-07-00987 | PKG-07 | INV-PKG-07-003-02977 | 262.82 | 33926.98 | 1696.35 | Approved Pending Payment | 32230.63 | 2024-Q4
EXP-003464 | 2024-10-02 | BOQ-PKG-04-01474 | PKG-04 | INV-PKG-04-035-03464 | 151.96 | 100775.61 | 5038.78 | Paid | 95736.83 | 2024-Q4
EXP-003618 | 2024-10-02 | BOQ-PKG-08-01628 | PKG-08 | INV-PKG-08-014-03618 | 356.11 | 189536.08 | 9476.8 | Paid | 180059.28 | 2024-Q4
EXP-004502 | 2024-10-02 | BOQ-PKG-02-00522 | PKG-02 | INV-PKG-02-023-04502 | 431.11 | 99288.05 | 4964.4 | Paid | 94323.65 | 2024-Q4
EXP-001519 | 2024-10-03 | BOQ-PKG-09-01519 | PKG-09 | INV-PKG-09-015-01519 | 202.42 | 39516.19 | 1975.81 | Approved Pending Payment | 37540.38 | 2024-Q4
EXP-003461 | 2024-10-03 | BOQ-PKG-01-01471 | PKG-01 | INV-PKG-01-032-03461 | 321.72 | 140849.01 | 7042.45 | Paid | 133806.56 | 2024-Q4
EXP-003942 | 2024-10-03 | BOQ-PKG-02-01952 | PKG-02 | INV-PKG-02-023-03942 | 27.3 | 108740.71 | 5437.04 | Paid | 103303.67 | 2024-Q4
EXP-004088 | 2024-10-03 | BOQ-PKG-08-00108 | PKG-08 | INV-PKG-08-029-04088 | 231.07 | 133733.75 | 6686.69 | Paid | 127047.06 | 2024-Q4
EXP-005010 | 2024-10-03 | BOQ-PKG-10-01030 | PKG-10 | INV-PKG-10-006-05010 | 393.29 | 150600.73 | 7530.04 | Paid | 143070.69 | 2024-Q4
EXP-005307 | 2024-10-03 | BOQ-PKG-07-01327 | PKG-07 | INV-PKG-07-023-05307 | 203.33 | 61264.67 | 3063.23 | Paid | 58201.44 | 2024-Q4
EXP-005374 | 2024-10-03 | BOQ-PKG-04-01394 | PKG-04 | INV-PKG-04-020-05374 | 261.14 | 44984.38 | 2249.22 | Paid | 42735.16 | 2024-Q4
EXP-005380 | 2024-10-03 | BOQ-PKG-10-01400 | PKG-10 | INV-PKG-10-026-05380 | 231.33 | 73216.12 | 3660.81 | Approved Pending Payment | 69555.31 | 2024-Q4
EXP-005831 | 2024-10-03 | BOQ-PKG-01-01851 | PKG-01 | INV-PKG-01-022-05831 | 285.4 | 25115.24 | 1255.76 | Paid | 23859.48 | 2024-Q4
EXP-000067 | 2024-10-04 | BOQ-PKG-07-00067 | PKG-07 | INV-PKG-07-033-00067 | 423.69 | 48540 | 2427 | Disputed | 46113 | 2024-Q4
EXP-000484 | 2024-10-04 | BOQ-PKG-04-00484 | PKG-04 | INV-PKG-04-030-00484 | 226.69 | 85067.32 | 4253.37 | Approved Pending Payment | 80813.95 | 2024-Q4
EXP-000738 | 2024-10-04 | BOQ-PKG-08-00738 | PKG-08 | INV-PKG-08-004-00738 | 291.05 | 157746.43 | 7887.32 | Paid | 149859.11 | 2024-Q4
EXP-001189 | 2024-10-04 | BOQ-PKG-09-01189 | PKG-09 | INV-PKG-09-035-01189 | 392.11 | 138110.82 | 6905.54 | Paid | 131205.28 | 2024-Q4
EXP-001615 | 2024-10-04 | BOQ-PKG-05-01615 | PKG-05 | INV-PKG-05-006-01615 | 151.77 | 148295.17 | 7414.76 | Approved Pending Payment | 140880.41 | 2024-Q4
EXP-001725 | 2024-10-04 | BOQ-PKG-05-01725 | PKG-05 | INV-PKG-05-011-01725 | 216.77 | 110856.95 | 5542.85 | Approved Pending Payment | 105314.1 | 2024-Q4
EXP-004173 | 2024-10-04 | BOQ-PKG-03-00193 | PKG-03 | INV-PKG-03-009-04173 | 112.75 | 188126.91 | 9406.35 | Paid | 178720.56 | 2024-Q4
EXP-005921 | 2024-10-04 | BOQ-PKG-01-01941 | PKG-01 | INV-PKG-01-007-05921 | 254.39 | 156427.19 | 7821.36 | Paid | 148605.83 | 2024-Q4
EXP-006677 | 2024-10-04 | BOQ-PKG-07-00707 | PKG-07 | INV-PKG-07-028-06677 | 151.71 | 175063.07 | 8753.15 | Under Review | 166309.92 | 2024-Q4
EXP-001641 | 2024-10-05 | BOQ-PKG-01-01641 | PKG-01 | INV-PKG-01-032-01641 | 401.19 | 125768.43 | 6288.42 | Paid | 119480.01 | 2024-Q4
EXP-001774 | 2024-10-05 | BOQ-PKG-04-01774 | PKG-04 | INV-PKG-04-025-01774 | 424.71 | 182844.31 | 9142.22 | Paid | 173702.09 | 2024-Q4
EXP-002733 | 2024-10-05 | BOQ-PKG-03-00743 | PKG-03 | INV-PKG-03-004-02733 | 237.58 | 85611.45 | 4280.57 | Under Review | 81330.88 | 2024-Q4
EXP-003377 | 2024-10-05 | BOQ-PKG-07-01387 | PKG-07 | INV-PKG-07-018-03377 | 203.84 | 107773.77 | 5388.69 | Paid | 102385.08 | 2024-Q4
EXP-003902 | 2024-10-05 | BOQ-PKG-02-01912 | PKG-02 | INV-PKG-02-018-03902 | 201.02 | 92254.82 | 4612.74 | Paid | 87642.08 | 2024-Q4
EXP-004218 | 2024-10-05 | BOQ-PKG-08-00238 | PKG-08 | INV-PKG-08-019-04218 | 177.93 | 198566.84 | 9928.34 | Paid | 188638.5 | 2024-Q4
EXP-004458 | 2024-10-05 | BOQ-PKG-08-00478 | PKG-08 | INV-PKG-08-014-04458 | 126.01 | 121132.43 | 6056.62 | Approved Pending Payment | 115075.81 | 2024-Q4
EXP-001543 | 2024-10-06 | BOQ-PKG-03-01543 | PKG-03 | INV-PKG-03-004-01543 | 258.98 | 173743.93 | 8687.2 | Paid | 165056.73 | 2024-Q4
EXP-003102 | 2024-10-06 | BOQ-PKG-02-01112 | PKG-02 | INV-PKG-02-023-03102 | 437.47 | 57367.62 | 2868.38 | Paid | 54499.24 | 2024-Q4
EXP-004292 | 2024-10-06 | BOQ-PKG-02-00312 | PKG-02 | INV-PKG-02-023-04292 | 101.8 | 70621.89 | 3531.09 | Paid | 67090.8 | 2024-Q4
EXP-000071 | 2024-10-07 | BOQ-PKG-01-00071 | PKG-01 | INV-PKG-01-002-00071 | 63.82 | 107260.02 | 5363 | Paid | 101897.02 | 2024-Q4
EXP-000092 | 2024-10-07 | BOQ-PKG-02-00092 | PKG-02 | INV-PKG-02-023-00092 | 160.72 | 176585.47 | 8829.27 | Paid | 167756.2 | 2024-Q4
EXP-000557 | 2024-10-07 | BOQ-PKG-07-00557 | PKG-07 | INV-PKG-07-033-00557 | 76.09 | 53652.02 | 2682.6 | Approved Pending Payment | 50969.42 | 2024-Q4
EXP-000828 | 2024-10-07 | BOQ-PKG-08-00828 | PKG-08 | INV-PKG-08-024-00828 | 330.34 | 67377.85 | 3368.89 | Paid | 64008.96 | 2024-Q4
EXP-003516 | 2024-10-07 | BOQ-PKG-06-01526 | PKG-06 | INV-PKG-06-017-03516 | 59.69 | 86349.99 | 4317.5 | Paid | 82032.49 | 2024-Q4
EXP-004453 | 2024-10-07 | BOQ-PKG-03-00473 | PKG-03 | INV-PKG-03-009-04453 | 276.48 | 31704.76 | 1585.24 | Paid | 30119.52 | 2024-Q4
EXP-004482 | 2024-10-07 | BOQ-PKG-02-00502 | PKG-02 | INV-PKG-02-003-04482 | 196.03 | 59087.01 | 2954.35 | Paid | 56132.66 | 2024-Q4
EXP-004569 | 2024-10-07 | BOQ-PKG-09-00589 | PKG-09 | INV-PKG-09-020-04569 | 232.47 | 187952.98 | 9397.65 | Approved Pending Payment | 178555.33 | 2024-Q4
EXP-004675 | 2024-10-07 | BOQ-PKG-05-00695 | PKG-05 | INV-PKG-05-021-04675 | 246.17 | 158956.94 | 7947.85 | Paid | 151009.09 | 2024-Q4
EXP-005665 | 2024-10-07 | BOQ-PKG-05-01685 | PKG-05 | INV-PKG-05-031-05665 | 9.56 | 197986.92 | 9899.35 | Paid | 188087.57 | 2024-Q4
EXP-006816 | 2024-10-07 | BOQ-PKG-06-00846 | PKG-06 | INV-PKG-06-027-06816 | 26.84 | 28726.61 | 1436.33 | Paid | 27290.28 | 2024-Q4
EXP-000263 | 2024-10-08 | BOQ-PKG-03-00263 | PKG-03 | INV-PKG-03-019-00263 | 87.01 | 30115.06 | 1505.75 | Approved Pending Payment | 28609.31 | 2024-Q4
EXP-002423 | 2024-10-08 | BOQ-PKG-03-00433 | PKG-03 | INV-PKG-03-009-02423 | 269.92 | 151512.3 | 7575.62 | Under Review | 143936.68 | 2024-Q4
EXP-002743 | 2024-10-08 | BOQ-PKG-03-00753 | PKG-03 | INV-PKG-03-014-02743 | 133.11 | 190982.54 | 9549.13 | Paid | 181433.41 | 2024-Q4
EXP-003098 | 2024-10-08 | BOQ-PKG-08-01108 | PKG-08 | INV-PKG-08-019-03098 | 398.85 | 97715.95 | 4885.8 | Paid | 92830.15 | 2024-Q4
EXP-003665 | 2024-10-08 | BOQ-PKG-05-01675 | PKG-05 | INV-PKG-05-026-03665 | 357.88 | 117293.12 | 5864.66 | Paid | 111428.46 | 2024-Q4
EXP-004973 | 2024-10-08 | BOQ-PKG-03-00993 | PKG-03 | INV-PKG-03-004-04973 | 289.42 | 62728.82 | 3136.44 | Paid | 59592.38 | 2024-Q4
EXP-005022 | 2024-10-08 | BOQ-PKG-02-01042 | PKG-02 | INV-PKG-02-018-05022 | 405.11 | 52979.87 | 2648.99 | Paid | 50330.88 | 2024-Q4
EXP-006443 | 2024-10-08 | BOQ-PKG-03-00473 | PKG-03 | INV-PKG-03-004-06443 | 197.26 | 128948.75 | 6447.44 | Approved Pending Payment | 122501.31 | 2024-Q4
EXP-000269 | 2024-10-09 | BOQ-PKG-09-00269 | PKG-09 | INV-PKG-09-025-00269 | 129.16 | 103439.61 | 5171.98 | Paid | 98267.63 | 2024-Q4
EXP-000631 | 2024-10-09 | BOQ-PKG-01-00631 | PKG-01 | INV-PKG-01-002-00631 | 210.09 | 145328.39 | 7266.42 | Paid | 138061.97 | 2024-Q4
EXP-001793 | 2024-10-09 | BOQ-PKG-03-01793 | PKG-03 | INV-PKG-03-009-01793 | 304.67 | 27911.44 | 1395.57 | Paid | 26515.87 | 2024-Q4
EXP-002440 | 2024-10-09 | BOQ-PKG-10-00450 | PKG-10 | INV-PKG-10-026-02440 | 261.04 | 108632.51 | 5431.63 | Paid | 103200.88 | 2024-Q4
EXP-002847 | 2024-10-09 | BOQ-PKG-07-00857 | PKG-07 | INV-PKG-07-013-02847 | 86.84 | 34199.69 | 1709.98 | Paid | 32489.71 | 2024-Q4
EXP-003275 | 2024-10-09 | BOQ-PKG-05-01285 | PKG-05 | INV-PKG-05-021-03275 | 160.85 | 75074 | 3753.7 | Under Review | 71320.3 | 2024-Q4
EXP-004679 | 2024-10-09 | BOQ-PKG-09-00699 | PKG-09 | INV-PKG-09-025-04679 | 267.1 | 50346.97 | 2517.35 | Paid | 47829.62 | 2024-Q4
EXP-005187 | 2024-10-09 | BOQ-PKG-07-01207 | PKG-07 | INV-PKG-07-008-05187 | 85.51 | 149536.88 | 7476.84 | Paid | 142060.04 | 2024-Q4
EXP-005717 | 2024-10-09 | BOQ-PKG-07-01737 | PKG-07 | INV-PKG-07-013-05717 | 444.78 | 205128.8 | 10256.44 | Disputed | 194872.36 | 2024-Q4
EXP-006408 | 2024-10-09 | BOQ-PKG-08-00438 | PKG-08 | INV-PKG-08-004-06408 | 434.42 | 144361.27 | 7218.06 | Paid | 137143.21 | 2024-Q4
EXP-000169 | 2024-10-10 | BOQ-PKG-09-00169 | PKG-09 | INV-PKG-09-030-00169 | 133.59 | 93549.89 | 4677.49 | Paid | 88872.4 | 2024-Q4
EXP-003246 | 2024-10-10 | BOQ-PKG-06-01256 | PKG-06 | INV-PKG-06-027-03246 | 353.44 | 150366.54 | 7518.33 | Paid | 142848.21 | 2024-Q4
EXP-004977 | 2024-10-10 | BOQ-PKG-07-00997 | PKG-07 | INV-PKG-07-008-04977 | 43.14 | 72978.08 | 3648.9 | Paid | 69329.18 | 2024-Q4
EXP-005077 | 2024-10-10 | BOQ-PKG-07-01097 | PKG-07 | INV-PKG-07-003-05077 | 259.03 | 36316.78 | 1815.84 | Paid | 34500.94 | 2024-Q4
EXP-005899 | 2024-10-10 | BOQ-PKG-09-01919 | PKG-09 | INV-PKG-09-020-05899 | 381.47 | 200983.75 | 10049.19 | Paid | 190934.56 | 2024-Q4
EXP-006189 | 2024-10-10 | BOQ-PKG-09-00219 | PKG-09 | INV-PKG-09-030-06189 | 239.97 | 146893.45 | 7344.67 | Paid | 139548.78 | 2024-Q4
EXP-006822 | 2024-10-10 | BOQ-PKG-02-00852 | PKG-02 | INV-PKG-02-033-06822 | 422.76 | 139874.49 | 6993.72 | Under Review | 132880.77 | 2024-Q4
EXP-002177 | 2024-10-11 | BOQ-PKG-07-00187 | PKG-07 | INV-PKG-07-008-02177 | 261.09 | 47646.42 | 2382.32 | Approved Pending Payment | 45264.1 | 2024-Q4
EXP-002762 | 2024-10-11 | BOQ-PKG-02-00772 | PKG-02 | INV-PKG-02-033-02762 | 54.78 | 138991.06 | 6949.55 | Paid | 132041.51 | 2024-Q4
EXP-003253 | 2024-10-11 | BOQ-PKG-03-01263 | PKG-03 | INV-PKG-03-034-03253 | 357.82 | 203376.4 | 10168.82 | Paid | 193207.58 | 2024-Q4
EXP-003695 | 2024-10-11 | BOQ-PKG-05-01705 | PKG-05 | INV-PKG-05-021-03695 | 191.88 | 98333.59 | 4916.68 | Approved Pending Payment | 93416.91 | 2024-Q4
EXP-006327 | 2024-10-11 | BOQ-PKG-07-00357 | PKG-07 | INV-PKG-07-028-06327 | 75.2 | 72410.76 | 3620.54 | Under Review | 68790.22 | 2024-Q4
EXP-000106 | 2024-10-12 | BOQ-PKG-06-00106 | PKG-06 | INV-PKG-06-002-00106 | 331.9 | 28597.33 | 1429.87 | Under Review | 27167.46 | 2024-Q4
EXP-000564 | 2024-10-12 | BOQ-PKG-04-00564 | PKG-04 | INV-PKG-04-005-00564 | 432.92 | 79756.75 | 3987.84 | Paid | 75768.91 | 2024-Q4
EXP-000691 | 2024-10-12 | BOQ-PKG-01-00691 | PKG-01 | INV-PKG-01-027-00691 | 209.75 | 58694.06 | 2934.7 | Paid | 55759.36 | 2024-Q4
EXP-001179 | 2024-10-12 | BOQ-PKG-09-01179 | PKG-09 | INV-PKG-09-025-01179 | 234.99 | 71449.27 | 3572.46 | Paid | 67876.81 | 2024-Q4
EXP-002585 | 2024-10-12 | BOQ-PKG-05-00595 | PKG-05 | INV-PKG-05-031-02585 | 74.89 | 106570.62 | 5328.53 | Paid | 101242.09 | 2024-Q4
EXP-002609 | 2024-10-12 | BOQ-PKG-09-00619 | PKG-09 | INV-PKG-09-020-02609 | 137.46 | 107309.67 | 5365.48 | Approved Pending Payment | 101944.19 | 2024-Q4
EXP-003270 | 2024-10-12 | BOQ-PKG-10-01280 | PKG-10 | INV-PKG-10-016-03270 | 59.47 | 166914.47 | 8345.72 | Paid | 158568.75 | 2024-Q4
EXP-004859 | 2024-10-12 | BOQ-PKG-09-00879 | PKG-09 | INV-PKG-09-030-04859 | 112.79 | 147561.2 | 7378.06 | Paid | 140183.14 | 2024-Q4
EXP-005423 | 2024-10-12 | BOQ-PKG-03-01443 | PKG-03 | INV-PKG-03-034-05423 | 358.41 | 134519.21 | 6725.96 | Approved Pending Payment | 127793.25 | 2024-Q4
EXP-005680 | 2024-10-12 | BOQ-PKG-10-01700 | PKG-10 | INV-PKG-10-011-05680 | 111.86 | 120459.17 | 6022.96 | Paid | 114436.21 | 2024-Q4
EXP-005768 | 2024-10-12 | BOQ-PKG-08-01788 | PKG-08 | INV-PKG-08-029-05768 | 65.94 | 55030 | 2751.5 | Paid | 52278.5 | 2024-Q4
EXP-000560 | 2024-10-13 | BOQ-PKG-10-00560 | PKG-10 | INV-PKG-10-001-00560 | 332.87 | 112757.89 | 5637.89 | Paid | 107120 | 2024-Q4
EXP-001007 | 2024-10-13 | BOQ-PKG-07-01007 | PKG-07 | INV-PKG-07-028-01007 | 168.3 | 38213.45 | 1910.67 | Paid | 36302.78 | 2024-Q4
EXP-001135 | 2024-10-13 | BOQ-PKG-05-01135 | PKG-05 | INV-PKG-05-016-01135 | 77.04 | 68965.17 | 3448.26 | Paid | 65516.91 | 2024-Q4
EXP-001767 | 2024-10-13 | BOQ-PKG-07-01767 | PKG-07 | INV-PKG-07-018-01767 | 268.66 | 76768.72 | 3838.44 | Paid | 72930.28 | 2024-Q4
EXP-003026 | 2024-10-13 | BOQ-PKG-06-01036 | PKG-06 | INV-PKG-06-017-03026 | 162.59 | 30442.23 | 1522.11 | Paid | 28920.12 | 2024-Q4
EXP-004737 | 2024-10-13 | BOQ-PKG-07-00757 | PKG-07 | INV-PKG-07-013-04737 | 318.63 | 91234.43 | 4561.72 | Paid | 86672.71 | 2024-Q4
EXP-005258 | 2024-10-13 | BOQ-PKG-08-01278 | PKG-08 | INV-PKG-08-009-05258 | 108.98 | 90714.78 | 4535.74 | Paid | 86179.04 | 2024-Q4
EXP-005439 | 2024-10-13 | BOQ-PKG-09-01459 | PKG-09 | INV-PKG-09-015-05439 | 442.31 | 150237.84 | 7511.89 | Paid | 142725.95 | 2024-Q4
EXP-005692 | 2024-10-13 | BOQ-PKG-02-01712 | PKG-02 | INV-PKG-02-023-05692 | 272.87 | 212833.96 | 10641.7 | Paid | 202192.26 | 2024-Q4
EXP-005722 | 2024-10-13 | BOQ-PKG-02-01742 | PKG-02 | INV-PKG-02-018-05722 | 345.12 | 204800.18 | 10240.01 | Paid | 194560.17 | 2024-Q4
EXP-006541 | 2024-10-13 | BOQ-PKG-01-00571 | PKG-01 | INV-PKG-01-032-06541 | 68.58 | 149442.86 | 7472.14 | Paid | 141970.72 | 2024-Q4
EXP-000555 | 2024-10-14 | BOQ-PKG-05-00555 | PKG-05 | INV-PKG-05-031-00555 | 253.26 | 78139.67 | 3906.98 | Paid | 74232.69 | 2024-Q4
EXP-000840 | 2024-10-14 | BOQ-PKG-10-00840 | PKG-10 | INV-PKG-10-001-00840 | 110.02 | 154560.77 | 7728.04 | Paid | 146832.73 | 2024-Q4
EXP-001575 | 2024-10-14 | BOQ-PKG-05-01575 | PKG-05 | INV-PKG-05-001-01575 | 400.74 | 192186.25 | 9609.31 | Paid | 182576.94 | 2024-Q4
EXP-002950 | 2024-10-14 | BOQ-PKG-10-00960 | PKG-10 | INV-PKG-10-011-02950 | 18.63 | 40594.49 | 2029.72 | Paid | 38564.77 | 2024-Q4
EXP-003008 | 2024-10-14 | BOQ-PKG-08-01018 | PKG-08 | INV-PKG-08-034-03008 | 9.1 | 66473.13 | 3323.66 | Paid | 63149.47 | 2024-Q4
EXP-004153 | 2024-10-14 | BOQ-PKG-03-00173 | PKG-03 | INV-PKG-03-024-04153 | 112.16 | 48845.13 | 2442.26 | Paid | 46402.87 | 2024-Q4
EXP-004808 | 2024-10-14 | BOQ-PKG-08-00828 | PKG-08 | INV-PKG-08-014-04808 | 207.55 | 168795.22 | 8439.76 | Paid | 160355.46 | 2024-Q4
EXP-004879 | 2024-10-14 | BOQ-PKG-09-00899 | PKG-09 | INV-PKG-09-015-04879 | 127.18 | 64600.24 | 3230.01 | Paid | 61370.23 | 2024-Q4
EXP-006601 | 2024-10-14 | BOQ-PKG-01-00631 | PKG-01 | INV-PKG-01-022-06601 | 449.67 | 39892.35 | 1994.62 | Paid | 37897.73 | 2024-Q4
EXP-001622 | 2024-10-15 | BOQ-PKG-02-01622 | PKG-02 | INV-PKG-02-013-01622 | 284.21 | 130790.44 | 6539.52 | Paid | 124250.92 | 2024-Q4
EXP-002322 | 2024-10-15 | BOQ-PKG-02-00332 | PKG-02 | INV-PKG-02-013-02322 | 97.51 | 94997.09 | 4749.85 | Paid | 90247.24 | 2024-Q4
EXP-004274 | 2024-10-15 | BOQ-PKG-04-00294 | PKG-04 | INV-PKG-04-005-04274 | 306.65 | 62303.31 | 3115.17 | Paid | 59188.14 | 2024-Q4
EXP-004613 | 2024-10-15 | BOQ-PKG-03-00633 | PKG-03 | INV-PKG-03-029-04613 | 99.97 | 125715.67 | 6285.78 | Approved Pending Payment | 119429.89 | 2024-Q4
EXP-005287 | 2024-10-15 | BOQ-PKG-07-01307 | PKG-07 | INV-PKG-07-003-05287 | 97.39 | 172370.63 | 8618.53 | Paid | 163752.1 | 2024-Q4
EXP-005729 | 2024-10-15 | BOQ-PKG-09-01749 | PKG-09 | INV-PKG-09-025-05729 | 369.39 | 79987.32 | 3999.37 | Under Review | 75987.95 | 2024-Q4
EXP-000295 | 2024-10-16 | BOQ-PKG-05-00295 | PKG-05 | INV-PKG-05-016-00295 | 111.24 | 63364.52 | 3168.23 | Paid | 60196.29 | 2024-Q4
EXP-000829 | 2024-10-16 | BOQ-PKG-09-00829 | PKG-09 | INV-PKG-09-025-00829 | 284.86 | 46515.89 | 2325.79 | Paid | 44190.1 | 2024-Q4
EXP-001570 | 2024-10-16 | BOQ-PKG-10-01570 | PKG-10 | INV-PKG-10-031-01570 | 156.17 | 193474.27 | 9673.71 | Paid | 183800.56 | 2024-Q4
EXP-003130 | 2024-10-16 | BOQ-PKG-10-01140 | PKG-10 | INV-PKG-10-016-03130 | 86.86 | 152006.5 | 7600.33 | Paid | 144406.17 | 2024-Q4
EXP-003309 | 2024-10-16 | BOQ-PKG-09-01319 | PKG-09 | INV-PKG-09-020-03309 | 347.7 | 49681.3 | 2484.07 | Approved Pending Payment | 47197.23 | 2024-Q4
EXP-001026 | 2024-10-17 | BOQ-PKG-06-01026 | PKG-06 | INV-PKG-06-012-01026 | 69.4 | 171593.8 | 8579.69 | Paid | 163014.11 | 2024-Q4
EXP-002324 | 2024-10-17 | BOQ-PKG-04-00334 | PKG-04 | INV-PKG-04-015-02324 | 62.64 | 184837.88 | 9241.89 | Paid | 175595.99 | 2024-Q4
EXP-002376 | 2024-10-17 | BOQ-PKG-06-00386 | PKG-06 | INV-PKG-06-032-02376 | 383.65 | 105454.97 | 5272.75 | Paid | 100182.22 | 2024-Q4
EXP-002491 | 2024-10-17 | BOQ-PKG-01-00501 | PKG-01 | INV-PKG-01-007-02491 | 323.38 | 171134.64 | 8556.73 | Paid | 162577.91 | 2024-Q4
EXP-002781 | 2024-10-17 | BOQ-PKG-01-00791 | PKG-01 | INV-PKG-01-017-02781 | 364.34 | 115213.33 | 5760.67 | Paid | 109452.66 | 2024-Q4
EXP-004531 | 2024-10-17 | BOQ-PKG-01-00551 | PKG-01 | INV-PKG-01-017-04531 | 68.76 | 143440.25 | 7172.01 | Under Review | 136268.24 | 2024-Q4
EXP-004670 | 2024-10-17 | BOQ-PKG-10-00690 | PKG-10 | INV-PKG-10-016-04670 | 227.53 | 171601.26 | 8580.06 | Disputed | 163021.2 | 2024-Q4
EXP-004952 | 2024-10-17 | BOQ-PKG-02-00972 | PKG-02 | INV-PKG-02-018-04952 | 302.49 | 174254.08 | 8712.7 | Paid | 165541.38 | 2024-Q4
EXP-005555 | 2024-10-17 | BOQ-PKG-05-01575 | PKG-05 | INV-PKG-05-026-05555 | 140.07 | 99240.54 | 4962.03 | Paid | 94278.51 | 2024-Q4
EXP-006217 | 2024-10-17 | BOQ-PKG-07-00247 | PKG-07 | INV-PKG-07-023-06217 | 351.63 | 168697.87 | 8434.89 | Paid | 160262.98 | 2024-Q4
EXP-002307 | 2024-10-18 | BOQ-PKG-07-00317 | PKG-07 | INV-PKG-07-033-02307 | 351.27 | 194210 | 9710.5 | Paid | 184499.5 | 2024-Q4
EXP-002461 | 2024-10-18 | BOQ-PKG-01-00471 | PKG-01 | INV-PKG-01-012-02461 | 357.23 | 174325.92 | 8716.3 | Paid | 165609.62 | 2024-Q4
EXP-003590 | 2024-10-18 | BOQ-PKG-10-01600 | PKG-10 | INV-PKG-10-021-03590 | 26.76 | 192237.6 | 9611.88 | Paid | 182625.72 | 2024-Q4
EXP-005274 | 2024-10-18 | BOQ-PKG-04-01294 | PKG-04 | INV-PKG-04-025-05274 | 163.17 | 121710.8 | 6085.54 | Paid | 115625.26 | 2024-Q4
EXP-005282 | 2024-10-18 | BOQ-PKG-02-01302 | PKG-02 | INV-PKG-02-033-05282 | 102.35 | 173705.54 | 8685.28 | Under Review | 165020.26 | 2024-Q4
EXP-006202 | 2024-10-18 | BOQ-PKG-02-00232 | PKG-02 | INV-PKG-02-008-06202 | 80.08 | 130866.52 | 6543.33 | Paid | 124323.19 | 2024-Q4
EXP-006827 | 2024-10-18 | BOQ-PKG-07-00857 | PKG-07 | INV-PKG-07-003-06827 | 205.64 | 72329.12 | 3616.46 | Under Review | 68712.66 | 2024-Q4
EXP-000029 | 2024-10-19 | BOQ-PKG-09-00029 | PKG-09 | INV-PKG-09-030-00029 | 238.83 | 159067.11 | 7953.36 | Approved Pending Payment | 151113.75 | 2024-Q4
EXP-001763 | 2024-10-19 | BOQ-PKG-03-01763 | PKG-03 | INV-PKG-03-014-01763 | 82.59 | 177860.37 | 8893.02 | Paid | 168967.35 | 2024-Q4
EXP-004178 | 2024-10-19 | BOQ-PKG-08-00198 | PKG-08 | INV-PKG-08-014-04178 | 258.44 | 202907.84 | 10145.39 | Disputed | 192762.45 | 2024-Q4
EXP-005080 | 2024-10-19 | BOQ-PKG-10-01100 | PKG-10 | INV-PKG-10-006-05080 | 106.74 | 140135.5 | 7006.78 | Under Review | 133128.72 | 2024-Q4
EXP-005235 | 2024-10-19 | BOQ-PKG-05-01255 | PKG-05 | INV-PKG-05-021-05235 | 120.09 | 176241.59 | 8812.08 | Approved Pending Payment | 167429.51 | 2024-Q4
EXP-000017 | 2024-10-20 | BOQ-PKG-07-00017 | PKG-07 | INV-PKG-07-018-00017 | 98.59 | 163612.85 | 8180.64 | Under Review | 155432.21 | 2024-Q4
EXP-001636 | 2024-10-20 | BOQ-PKG-06-01636 | PKG-06 | INV-PKG-06-027-01636 | 11.08 | 38109.27 | 1905.46 | Paid | 36203.81 | 2024-Q4
EXP-006126 | 2024-10-20 | BOQ-PKG-06-00156 | PKG-06 | INV-PKG-06-002-06126 | 227.66 | 155917.34 | 7795.87 | Paid | 148121.47 | 2024-Q4
EXP-006188 | 2024-10-20 | BOQ-PKG-08-00218 | PKG-08 | INV-PKG-08-029-06188 | 377.45 | 126843.3 | 6342.17 | Disputed | 120501.13 | 2024-Q4
EXP-006872 | 2024-10-20 | BOQ-PKG-02-00902 | PKG-02 | INV-PKG-02-013-06872 | 429.07 | 183804.79 | 9190.24 | Paid | 174614.55 | 2024-Q4
EXP-000345 | 2024-10-21 | BOQ-PKG-05-00345 | PKG-05 | INV-PKG-05-031-00345 | 162.77 | 126844.76 | 6342.24 | Under Review | 120502.52 | 2024-Q4
EXP-002599 | 2024-10-21 | BOQ-PKG-09-00609 | PKG-09 | INV-PKG-09-010-02599 | 361.87 | 159298.89 | 7964.94 | Paid | 151333.95 | 2024-Q4
EXP-004844 | 2024-10-21 | BOQ-PKG-04-00864 | PKG-04 | INV-PKG-04-015-04844 | 245.26 | 131872.06 | 6593.6 | Approved Pending Payment | 125278.46 | 2024-Q4
EXP-005612 | 2024-10-21 | BOQ-PKG-02-01632 | PKG-02 | INV-PKG-02-013-05612 | 123.28 | 145266.28 | 7263.31 | Paid | 138002.97 | 2024-Q4
EXP-000064 | 2024-10-22 | BOQ-PKG-04-00064 | PKG-04 | INV-PKG-04-030-00064 | 68.84 | 51939.32 | 2596.97 | Paid | 49342.35 | 2024-Q4
EXP-001092 | 2024-10-22 | BOQ-PKG-02-01092 | PKG-02 | INV-PKG-02-008-01092 | 327.88 | 64235.54 | 3211.78 | Paid | 61023.76 | 2024-Q4
EXP-001493 | 2024-10-22 | BOQ-PKG-03-01493 | PKG-03 | INV-PKG-03-024-01493 | 247.53 | 65453.11 | 3272.66 | Paid | 62180.45 | 2024-Q4
EXP-001561 | 2024-10-22 | BOQ-PKG-01-01561 | PKG-01 | INV-PKG-01-022-01561 | 254.92 | 160222.52 | 8011.13 | Paid | 152211.39 | 2024-Q4
EXP-001584 | 2024-10-22 | BOQ-PKG-04-01584 | PKG-04 | INV-PKG-04-010-01584 | 34.83 | 194051.93 | 9702.6 | Paid | 184349.33 | 2024-Q4
EXP-002026 | 2024-10-22 | BOQ-PKG-06-00036 | PKG-06 | INV-PKG-06-032-02026 | 255.43 | 72245 | 3612.25 | Paid | 68632.75 | 2024-Q4
EXP-002803 | 2024-10-22 | BOQ-PKG-03-00813 | PKG-03 | INV-PKG-03-004-02803 | 392.56 | 27456.2 | 1372.81 | Approved Pending Payment | 26083.39 | 2024-Q4
EXP-004522 | 2024-10-22 | BOQ-PKG-02-00542 | PKG-02 | INV-PKG-02-008-04522 | 314.04 | 182651.01 | 9132.55 | Paid | 173518.46 | 2024-Q4
EXP-005182 | 2024-10-22 | BOQ-PKG-02-01202 | PKG-02 | INV-PKG-02-003-05182 | 80.97 | 115279.49 | 5763.97 | Paid | 109515.52 | 2024-Q4
EXP-005296 | 2024-10-22 | BOQ-PKG-06-01316 | PKG-06 | INV-PKG-06-012-05296 | 160.06 | 125088 | 6254.4 | Approved Pending Payment | 118833.6 | 2024-Q4
EXP-006045 | 2024-10-22 | BOQ-PKG-05-00075 | PKG-05 | INV-PKG-05-026-06045 | 270.74 | 180121.36 | 9006.07 | Under Review | 171115.29 | 2024-Q4
EXP-006105 | 2024-10-22 | BOQ-PKG-05-00135 | PKG-05 | INV-PKG-05-016-06105 | 144.57 | 136022.84 | 6801.14 | Under Review | 129221.7 | 2024-Q4
EXP-006724 | 2024-10-22 | BOQ-PKG-04-00754 | PKG-04 | INV-PKG-04-005-06724 | 231.04 | 67114.49 | 3355.72 | Paid | 63758.77 | 2024-Q4
EXP-001342 | 2024-10-23 | BOQ-PKG-02-01342 | PKG-02 | INV-PKG-02-013-01342 | 207.88 | 38103.78 | 1905.19 | Paid | 36198.59 | 2024-Q4
EXP-003135 | 2024-10-23 | BOQ-PKG-05-01145 | PKG-05 | INV-PKG-05-021-03135 | 219.65 | 149904.45 | 7495.22 | Paid | 142409.23 | 2024-Q4
EXP-004691 | 2024-10-23 | BOQ-PKG-01-00711 | PKG-01 | INV-PKG-01-002-04691 | 294.3 | 50154.99 | 2507.75 | Paid | 47647.24 | 2024-Q4
EXP-004782 | 2024-10-23 | BOQ-PKG-02-00802 | PKG-02 | INV-PKG-02-023-04782 | 35.83 | 74845.61 | 3742.28 | Paid | 71103.33 | 2024-Q4
EXP-005992 | 2024-10-23 | BOQ-PKG-02-00022 | PKG-02 | INV-PKG-02-008-05992 | 177 | 193268.32 | 9663.42 | Under Review | 183604.9 | 2024-Q4
EXP-006890 | 2024-10-23 | BOQ-PKG-10-00920 | PKG-10 | INV-PKG-10-031-06890 | 423.43 | 207890.02 | 10394.5 | Paid | 197495.52 | 2024-Q4
EXP-000868 | 2024-10-24 | BOQ-PKG-08-00868 | PKG-08 | INV-PKG-08-029-00868 | 390.79 | 167941.83 | 8397.09 | Paid | 159544.74 | 2024-Q4
EXP-002258 | 2024-10-24 | BOQ-PKG-08-00268 | PKG-08 | INV-PKG-08-019-02258 | 86.26 | 136163.08 | 6808.15 | Paid | 129354.93 | 2024-Q4
EXP-002345 | 2024-10-24 | BOQ-PKG-05-00355 | PKG-05 | INV-PKG-05-001-02345 | 58.06 | 96612.33 | 4830.62 | Paid | 91781.71 | 2024-Q4
EXP-003974 | 2024-10-24 | BOQ-PKG-04-01984 | PKG-04 | INV-PKG-04-020-03974 | 140.77 | 179992.31 | 8999.62 | Paid | 170992.69 | 2024-Q4
EXP-004159 | 2024-10-24 | BOQ-PKG-09-00179 | PKG-09 | INV-PKG-09-030-04159 | 8.2 | 116925.13 | 5846.26 | Paid | 111078.87 | 2024-Q4
EXP-004796 | 2024-10-24 | BOQ-PKG-06-00816 | PKG-06 | INV-PKG-06-002-04796 | 263.28 | 74196.62 | 3709.83 | Paid | 70486.79 | 2024-Q4
EXP-005549 | 2024-10-24 | BOQ-PKG-09-01569 | PKG-09 | INV-PKG-09-020-05549 | 370.71 | 50006.85 | 2500.34 | Paid | 47506.51 | 2024-Q4
EXP-005668 | 2024-10-24 | BOQ-PKG-08-01688 | PKG-08 | INV-PKG-08-034-05668 | 64.6 | 108663.66 | 5433.18 | Paid | 103230.48 | 2024-Q4
EXP-000249 | 2024-10-25 | BOQ-PKG-09-00249 | PKG-09 | INV-PKG-09-005-00249 | 216.07 | 54679.88 | 2733.99 | Paid | 51945.89 | 2024-Q4
EXP-000365 | 2024-10-25 | BOQ-PKG-05-00365 | PKG-05 | INV-PKG-05-016-00365 | 49.57 | 76518.55 | 3825.93 | Paid | 72692.62 | 2024-Q4
EXP-003978 | 2024-10-25 | BOQ-PKG-08-01988 | PKG-08 | INV-PKG-08-024-03978 | 65.07 | 99540.5 | 4977.03 | Paid | 94563.47 | 2024-Q4
EXP-004643 | 2024-10-25 | BOQ-PKG-03-00663 | PKG-03 | INV-PKG-03-024-04643 | 177.38 | 196079.18 | 9803.96 | Paid | 186275.22 | 2024-Q4
EXP-005567 | 2024-10-25 | BOQ-PKG-07-01587 | PKG-07 | INV-PKG-07-003-05567 | 340.24 | 41956.16 | 2097.81 | Approved Pending Payment | 39858.35 | 2024-Q4
EXP-005984 | 2024-10-25 | BOQ-PKG-04-00014 | PKG-04 | INV-PKG-04-035-05984 | 371.26 | 165111.9 | 8255.59 | Paid | 156856.31 | 2024-Q4
EXP-006708 | 2024-10-25 | BOQ-PKG-08-00738 | PKG-08 | INV-PKG-08-024-06708 | 62.69 | 141243.66 | 7062.18 | Paid | 134181.48 | 2024-Q4
EXP-000236 | 2024-10-26 | BOQ-PKG-06-00236 | PKG-06 | INV-PKG-06-027-00236 | 86.9 | 164842.02 | 8242.1 | Paid | 156599.92 | 2024-Q4
EXP-001460 | 2024-10-26 | BOQ-PKG-10-01460 | PKG-10 | INV-PKG-10-026-01460 | 130.34 | 140149.54 | 7007.48 | Approved Pending Payment | 133142.06 | 2024-Q4
EXP-003408 | 2024-10-26 | BOQ-PKG-08-01418 | PKG-08 | INV-PKG-08-014-03408 | 283.89 | 147397.46 | 7369.87 | Under Review | 140027.59 | 2024-Q4
EXP-003494 | 2024-10-26 | BOQ-PKG-04-01504 | PKG-04 | INV-PKG-04-030-03494 | 407.58 | 42015.26 | 2100.76 | Paid | 39914.5 | 2024-Q4
EXP-005234 | 2024-10-26 | BOQ-PKG-04-01254 | PKG-04 | INV-PKG-04-020-05234 | 340.45 | 37803.54 | 1890.18 | Paid | 35913.36 | 2024-Q4
EXP-006192 | 2024-10-26 | BOQ-PKG-02-00222 | PKG-02 | INV-PKG-02-033-06192 | 435.83 | 182431.67 | 9121.58 | Paid | 173310.09 | 2024-Q4
EXP-006340 | 2024-10-26 | BOQ-PKG-10-00370 | PKG-10 | INV-PKG-10-006-06340 | 159.97 | 56701.25 | 2835.06 | Paid | 53866.19 | 2024-Q4
EXP-006588 | 2024-10-26 | BOQ-PKG-08-00618 | PKG-08 | INV-PKG-08-009-06588 | 126.21 | 93375.96 | 4668.8 | Disputed | 88707.16 | 2024-Q4
EXP-006631 | 2024-10-26 | BOQ-PKG-01-00661 | PKG-01 | INV-PKG-01-017-06631 | 240.7 | 138169.9 | 6908.5 | Paid | 131261.4 | 2024-Q4
EXP-000348 | 2024-10-27 | BOQ-PKG-08-00348 | PKG-08 | INV-PKG-08-034-00348 | 88.79 | 78077.67 | 3903.88 | Paid | 74173.79 | 2024-Q4
EXP-000970 | 2024-10-27 | BOQ-PKG-10-00970 | PKG-10 | INV-PKG-10-026-00970 | 294.38 | 84641.17 | 4232.06 | Paid | 80409.11 | 2024-Q4
EXP-002337 | 2024-10-27 | BOQ-PKG-07-00347 | PKG-07 | INV-PKG-07-028-02337 | 53.78 | 114310.26 | 5715.51 | Paid | 108594.75 | 2024-Q4
EXP-002505 | 2024-10-27 | BOQ-PKG-05-00515 | PKG-05 | INV-PKG-05-021-02505 | 322.71 | 137425.99 | 6871.3 | Paid | 130554.69 | 2024-Q4
EXP-002702 | 2024-10-27 | BOQ-PKG-02-00712 | PKG-02 | INV-PKG-02-008-02702 | 207.06 | 125529.22 | 6276.46 | Under Review | 119252.76 | 2024-Q4
EXP-004423 | 2024-10-27 | BOQ-PKG-03-00443 | PKG-03 | INV-PKG-03-014-04423 | 352.11 | 126403.06 | 6320.15 | Paid | 120082.91 | 2024-Q4
EXP-006591 | 2024-10-27 | BOQ-PKG-01-00621 | PKG-01 | INV-PKG-01-012-06591 | 400.47 | 166121.52 | 8306.08 | Under Review | 157815.44 | 2024-Q4
EXP-000211 | 2024-10-28 | BOQ-PKG-01-00211 | PKG-01 | INV-PKG-01-002-00211 | 241.95 | 130339.99 | 6517 | Paid | 123822.99 | 2024-Q4
EXP-002144 | 2024-10-28 | BOQ-PKG-04-00154 | PKG-04 | INV-PKG-04-010-02144 | 63.64 | 93226.74 | 4661.34 | Paid | 88565.4 | 2024-Q4
EXP-002735 | 2024-10-28 | BOQ-PKG-05-00745 | PKG-05 | INV-PKG-05-006-02735 | 111.24 | 133381.49 | 6669.07 | Paid | 126712.42 | 2024-Q4
EXP-003370 | 2024-10-28 | BOQ-PKG-10-01380 | PKG-10 | INV-PKG-10-011-03370 | 435.18 | 77095.61 | 3854.78 | Disputed | 73240.83 | 2024-Q4
EXP-003449 | 2024-10-28 | BOQ-PKG-09-01459 | PKG-09 | INV-PKG-09-020-03449 | 339.1 | 185403.21 | 9270.16 | Paid | 176133.05 | 2024-Q4
EXP-006947 | 2024-10-28 | BOQ-PKG-07-00977 | PKG-07 | INV-PKG-07-018-06947 | 77.12 | 195590.18 | 9779.51 | Paid | 185810.67 | 2024-Q4
EXP-000578 | 2024-10-29 | BOQ-PKG-08-00578 | PKG-08 | INV-PKG-08-019-00578 | 179.81 | 57832.14 | 2891.61 | Under Review | 54940.53 | 2024-Q4
EXP-000602 | 2024-10-29 | BOQ-PKG-02-00602 | PKG-02 | INV-PKG-02-008-00602 | 196.1 | 108823.08 | 5441.15 | Paid | 103381.93 | 2024-Q4
EXP-000775 | 2024-10-29 | BOQ-PKG-05-00775 | PKG-05 | INV-PKG-05-006-00775 | 315.61 | 168745.34 | 8437.27 | Paid | 160308.07 | 2024-Q4
EXP-001380 | 2024-10-29 | BOQ-PKG-10-01380 | PKG-10 | INV-PKG-10-016-01380 | 205.13 | 121536.02 | 6076.8 | Under Review | 115459.22 | 2024-Q4
EXP-003619 | 2024-10-29 | BOQ-PKG-09-01629 | PKG-09 | INV-PKG-09-015-03619 | 387.86 | 58634.69 | 2931.73 | Under Review | 55702.96 | 2024-Q4
EXP-004029 | 2024-10-29 | BOQ-PKG-09-00049 | PKG-09 | INV-PKG-09-005-04029 | 289.16 | 141670.84 | 7083.54 | Paid | 134587.3 | 2024-Q4
EXP-005525 | 2024-10-29 | BOQ-PKG-05-01545 | PKG-05 | INV-PKG-05-031-05525 | 46.53 | 83764.92 | 4188.25 | Under Review | 79576.67 | 2024-Q4
EXP-000245 | 2024-10-30 | BOQ-PKG-05-00245 | PKG-05 | INV-PKG-05-001-00245 | 442.41 | 146406.52 | 7320.33 | Disputed | 139086.19 | 2024-Q4
EXP-001811 | 2024-10-30 | BOQ-PKG-01-01811 | PKG-01 | INV-PKG-01-027-01811 | 165.23 | 99237.9 | 4961.9 | Paid | 94276 | 2024-Q4
EXP-004714 | 2024-10-30 | BOQ-PKG-04-00734 | PKG-04 | INV-PKG-04-025-04714 | 158.98 | 128844.57 | 6442.23 | Paid | 122402.34 | 2024-Q4
EXP-005693 | 2024-10-30 | BOQ-PKG-03-01713 | PKG-03 | INV-PKG-03-024-05693 | 21.05 | 100980.92 | 5049.05 | Under Review | 95931.87 | 2024-Q4
EXP-006654 | 2024-10-30 | BOQ-PKG-04-00684 | PKG-04 | INV-PKG-04-005-06654 | 291.33 | 139174.59 | 6958.73 | Approved Pending Payment | 132215.86 | 2024-Q4
EXP-001488 | 2024-10-31 | BOQ-PKG-08-01488 | PKG-08 | INV-PKG-08-019-01488 | 416.87 | 95986.8 | 4799.34 | Paid | 91187.46 | 2024-Q4
EXP-001560 | 2024-10-31 | BOQ-PKG-10-01560 | PKG-10 | INV-PKG-10-021-01560 | 61.7 | 129328.11 | 6466.41 | Paid | 122861.7 | 2024-Q4
EXP-001867 | 2024-10-31 | BOQ-PKG-07-01867 | PKG-07 | INV-PKG-07-013-01867 | 209.52 | 59397.84 | 2969.89 | Paid | 56427.95 | 2024-Q4
EXP-002983 | 2024-10-31 | BOQ-PKG-03-00993 | PKG-03 | INV-PKG-03-009-02983 | 211.18 | 117304.91 | 5865.25 | Paid | 111439.66 | 2024-Q4
EXP-004413 | 2024-10-31 | BOQ-PKG-03-00433 | PKG-03 | INV-PKG-03-004-04413 | 65.18 | 71782.92 | 3589.15 | Paid | 68193.77 | 2024-Q4
EXP-006326 | 2024-10-31 | BOQ-PKG-06-00356 | PKG-06 | INV-PKG-06-027-06326 | 81.72 | 73481.06 | 3674.05 | Approved Pending Payment | 69807.01 | 2024-Q4
EXP-006524 | 2024-10-31 | BOQ-PKG-04-00554 | PKG-04 | INV-PKG-04-015-06524 | 295.71 | 50860.96 | 2543.05 | Paid | 48317.91 | 2024-Q4
EXP-006858 | 2024-10-31 | BOQ-PKG-08-00888 | PKG-08 | INV-PKG-08-034-06858 | 305.2 | 194491.73 | 9724.59 | Paid | 184767.14 | 2024-Q4
EXP-002794 | 2024-11-01 | BOQ-PKG-04-00804 | PKG-04 | INV-PKG-04-030-02794 | 186.12 | 130355.99 | 6517.8 | Paid | 123838.19 | 2024-Q4
EXP-002870 | 2024-11-01 | BOQ-PKG-10-00880 | PKG-10 | INV-PKG-10-001-02870 | 271.12 | 54281.22 | 2714.06 | Paid | 51567.16 | 2024-Q4
EXP-000049 | 2024-11-02 | BOQ-PKG-09-00049 | PKG-09 | INV-PKG-09-015-00049 | 278.07 | 196244.37 | 9812.22 | Paid | 186432.15 | 2024-Q4
EXP-001505 | 2024-11-02 | BOQ-PKG-05-01505 | PKG-05 | INV-PKG-05-001-01505 | 398.6 | 148327.19 | 7416.36 | Paid | 140910.83 | 2024-Q4
EXP-002115 | 2024-11-02 | BOQ-PKG-05-00125 | PKG-05 | INV-PKG-05-016-02115 | 61.26 | 170550.56 | 8527.53 | Paid | 162023.03 | 2024-Q4
EXP-003632 | 2024-11-02 | BOQ-PKG-02-01642 | PKG-02 | INV-PKG-02-028-03632 | 98.48 | 56840.43 | 2842.02 | Under Review | 53998.41 | 2024-Q4
EXP-003639 | 2024-11-02 | BOQ-PKG-09-01649 | PKG-09 | INV-PKG-09-035-03639 | 222.73 | 63573.76 | 3178.69 | Approved Pending Payment | 60395.07 | 2024-Q4
EXP-003965 | 2024-11-02 | BOQ-PKG-05-01975 | PKG-05 | INV-PKG-05-011-03965 | 176.86 | 81633.24 | 4081.66 | Paid | 77551.58 | 2024-Q4
EXP-003992 | 2024-11-02 | BOQ-PKG-02-00012 | PKG-02 | INV-PKG-02-003-03992 | 260.12 | 98695.33 | 4934.77 | Paid | 93760.56 | 2024-Q4
EXP-004229 | 2024-11-02 | BOQ-PKG-09-00249 | PKG-09 | INV-PKG-09-030-04229 | 374.72 | 204292.51 | 10214.63 | Paid | 194077.88 | 2024-Q4
EXP-004352 | 2024-11-02 | BOQ-PKG-02-00372 | PKG-02 | INV-PKG-02-013-04352 | 295.25 | 52487.29 | 2624.36 | Approved Pending Payment | 49862.93 | 2024-Q4
EXP-004835 | 2024-11-02 | BOQ-PKG-05-00855 | PKG-05 | INV-PKG-05-006-04835 | 205.24 | 78391.96 | 3919.6 | Paid | 74472.36 | 2024-Q4
EXP-005472 | 2024-11-02 | BOQ-PKG-02-01492 | PKG-02 | INV-PKG-02-013-05472 | 104.08 | 115497.37 | 5774.87 | Paid | 109722.5 | 2024-Q4
EXP-005608 | 2024-11-02 | BOQ-PKG-08-01628 | PKG-08 | INV-PKG-08-009-05608 | 384.96 | 112718.24 | 5635.91 | Paid | 107082.33 | 2024-Q4
EXP-000344 | 2024-11-03 | BOQ-PKG-04-00344 | PKG-04 | INV-PKG-04-030-00344 | 204.35 | 103422.46 | 5171.12 | Paid | 98251.34 | 2024-Q4
EXP-000890 | 2024-11-03 | BOQ-PKG-10-00890 | PKG-10 | INV-PKG-10-016-00890 | 57.01 | 204891.62 | 10244.58 | Paid | 194647.04 | 2024-Q4
EXP-001882 | 2024-11-03 | BOQ-PKG-02-01882 | PKG-02 | INV-PKG-02-028-01882 | 275.27 | 59091.79 | 2954.59 | Paid | 56137.2 | 2024-Q4
EXP-002032 | 2024-11-03 | BOQ-PKG-02-00042 | PKG-02 | INV-PKG-02-003-02032 | 145.3 | 35759.1 | 1787.96 | Paid | 33971.14 | 2024-Q4
EXP-002328 | 2024-11-03 | BOQ-PKG-08-00338 | PKG-08 | INV-PKG-08-019-02328 | 248.11 | 161203.71 | 8060.19 | Paid | 153143.52 | 2024-Q4
EXP-003411 | 2024-11-03 | BOQ-PKG-01-01421 | PKG-01 | INV-PKG-01-017-03411 | 380.62 | 62073.71 | 3103.69 | Paid | 58970.02 | 2024-Q4
EXP-004306 | 2024-11-03 | BOQ-PKG-06-00326 | PKG-06 | INV-PKG-06-002-04306 | 336.44 | 31691.92 | 1584.6 | Approved Pending Payment | 30107.32 | 2024-Q4
EXP-004880 | 2024-11-03 | BOQ-PKG-10-00900 | PKG-10 | INV-PKG-10-016-04880 | 440.54 | 199246.16 | 9962.31 | Disputed | 189283.85 | 2024-Q4
EXP-004938 | 2024-11-03 | BOQ-PKG-08-00958 | PKG-08 | INV-PKG-08-004-04938 | 185.42 | 200012.83 | 10000.64 | Paid | 190012.19 | 2024-Q4
EXP-000235 | 2024-11-04 | BOQ-PKG-05-00235 | PKG-05 | INV-PKG-05-026-00235 | 94.8 | 197576.15 | 9878.81 | Paid | 187697.34 | 2024-Q4
EXP-001059 | 2024-11-04 | BOQ-PKG-09-01059 | PKG-09 | INV-PKG-09-010-01059 | 237.24 | 146482.36 | 7324.12 | Paid | 139158.24 | 2024-Q4
EXP-001436 | 2024-11-04 | BOQ-PKG-06-01436 | PKG-06 | INV-PKG-06-002-01436 | 424.66 | 58209.98 | 2910.5 | Paid | 55299.48 | 2024-Q4
EXP-001794 | 2024-11-04 | BOQ-PKG-04-01794 | PKG-04 | INV-PKG-04-010-01794 | 239.92 | 66188.52 | 3309.43 | Paid | 62879.09 | 2024-Q4
EXP-001977 | 2024-11-04 | BOQ-PKG-07-01977 | PKG-07 | INV-PKG-07-018-01977 | 137.22 | 83477.15 | 4173.86 | Approved Pending Payment | 79303.29 | 2024-Q4
EXP-003231 | 2024-11-04 | BOQ-PKG-01-01241 | PKG-01 | INV-PKG-01-012-03231 | 27.18 | 176594.93 | 8829.75 | Paid | 167765.18 | 2024-Q4
EXP-005225 | 2024-11-04 | BOQ-PKG-05-01245 | PKG-05 | INV-PKG-05-011-05225 | 88.33 | 44026.54 | 2201.33 | Approved Pending Payment | 41825.21 | 2024-Q4
EXP-006425 | 2024-11-04 | BOQ-PKG-05-00455 | PKG-05 | INV-PKG-05-021-06425 | 243.28 | 208905.81 | 10445.29 | Paid | 198460.52 | 2024-Q4
EXP-006842 | 2024-11-04 | BOQ-PKG-02-00872 | PKG-02 | INV-PKG-02-018-06842 | 75.8 | 164066.43 | 8203.32 | Paid | 155863.11 | 2024-Q4
EXP-002758 | 2024-11-05 | BOQ-PKG-08-00768 | PKG-08 | INV-PKG-08-029-02758 | 14.02 | 166086.36 | 8304.32 | Approved Pending Payment | 157782.04 | 2024-Q4
EXP-003443 | 2024-11-05 | BOQ-PKG-03-01453 | PKG-03 | INV-PKG-03-014-03443 | 165.4 | 112825.92 | 5641.3 | Approved Pending Payment | 107184.62 | 2024-Q4
EXP-004259 | 2024-11-05 | BOQ-PKG-09-00279 | PKG-09 | INV-PKG-09-025-04259 | 201.19 | 92212.9 | 4610.64 | Paid | 87602.26 | 2024-Q4
EXP-004803 | 2024-11-05 | BOQ-PKG-03-00823 | PKG-03 | INV-PKG-03-009-04803 | 261.04 | 62297.92 | 3114.9 | Approved Pending Payment | 59183.02 | 2024-Q4
EXP-005272 | 2024-11-05 | BOQ-PKG-02-01292 | PKG-02 | INV-PKG-02-023-05272 | 40.47 | 155727.85 | 7786.39 | Paid | 147941.46 | 2024-Q4
EXP-005339 | 2024-11-05 | BOQ-PKG-09-01359 | PKG-09 | INV-PKG-09-020-05339 | 261.16 | 28928.43 | 1446.42 | Paid | 27482.01 | 2024-Q4
EXP-005411 | 2024-11-05 | BOQ-PKG-01-01431 | PKG-01 | INV-PKG-01-022-05411 | 410.74 | 100156.72 | 5007.84 | Paid | 95148.88 | 2024-Q4
EXP-005706 | 2024-11-05 | BOQ-PKG-06-01726 | PKG-06 | INV-PKG-06-002-05706 | 44.46 | 166110.92 | 8305.55 | Paid | 157805.37 | 2024-Q4
EXP-000120 | 2024-11-06 | BOQ-PKG-10-00120 | PKG-10 | INV-PKG-10-016-00120 | 187.75 | 65444.32 | 3272.22 | Paid | 62172.1 | 2024-Q4
EXP-000323 | 2024-11-06 | BOQ-PKG-03-00323 | PKG-03 | INV-PKG-03-009-00323 | 238.77 | 37613.45 | 1880.67 | Paid | 35732.78 | 2024-Q4
EXP-003700 | 2024-11-06 | BOQ-PKG-10-01710 | PKG-10 | INV-PKG-10-026-03700 | 106.72 | 105801.27 | 5290.06 | Paid | 100511.21 | 2024-Q4
EXP-005957 | 2024-11-06 | BOQ-PKG-07-01977 | PKG-07 | INV-PKG-07-008-05957 | 109.03 | 104574.2 | 5228.71 | Paid | 99345.49 | 2024-Q4
EXP-006532 | 2024-11-06 | BOQ-PKG-02-00562 | PKG-02 | INV-PKG-02-023-06532 | 399.76 | 105744.4 | 5287.22 | Approved Pending Payment | 100457.18 | 2024-Q4
EXP-000727 | 2024-11-07 | BOQ-PKG-07-00727 | PKG-07 | INV-PKG-07-028-00727 | 84.58 | 190787.58 | 9539.38 | Paid | 181248.2 | 2024-Q4
EXP-000949 | 2024-11-07 | BOQ-PKG-09-00949 | PKG-09 | INV-PKG-09-005-00949 | 340.38 | 64458.86 | 3222.94 | Under Review | 61235.92 | 2024-Q4
EXP-001681 | 2024-11-07 | BOQ-PKG-01-01681 | PKG-01 | INV-PKG-01-002-01681 | 260.5 | 117338.75 | 5866.94 | Paid | 111471.81 | 2024-Q4
EXP-003505 | 2024-11-07 | BOQ-PKG-05-01515 | PKG-05 | INV-PKG-05-006-03505 | 62.92 | 171341.78 | 8567.09 | Approved Pending Payment | 162774.69 | 2024-Q4
EXP-003840 | 2024-11-07 | BOQ-PKG-10-01850 | PKG-10 | INV-PKG-10-026-03840 | 308.31 | 82257.25 | 4112.86 | Paid | 78144.39 | 2024-Q4
EXP-004943 | 2024-11-07 | BOQ-PKG-03-00963 | PKG-03 | INV-PKG-03-009-04943 | 99.51 | 46974.4 | 2348.72 | Paid | 44625.68 | 2024-Q4
EXP-005134 | 2024-11-07 | BOQ-PKG-04-01154 | PKG-04 | INV-PKG-04-025-05134 | 31.35 | 72011.27 | 3600.56 | Under Review | 68410.71 | 2024-Q4
EXP-000821 | 2024-11-08 | BOQ-PKG-01-00821 | PKG-01 | INV-PKG-01-017-00821 | 68.12 | 61883.7 | 3094.18 | Paid | 58789.52 | 2024-Q4
EXP-001424 | 2024-11-08 | BOQ-PKG-04-01424 | PKG-04 | INV-PKG-04-025-01424 | 316.58 | 181441.66 | 9072.08 | Disputed | 172369.58 | 2024-Q4
EXP-001470 | 2024-11-08 | BOQ-PKG-10-01470 | PKG-10 | INV-PKG-10-001-01470 | 201.95 | 46538.83 | 2326.94 | Paid | 44211.89 | 2024-Q4
EXP-002549 | 2024-11-08 | BOQ-PKG-09-00559 | PKG-09 | INV-PKG-09-030-02549 | 171.52 | 142693.31 | 7134.67 | Approved Pending Payment | 135558.64 | 2024-Q4
EXP-003381 | 2024-11-08 | BOQ-PKG-01-01391 | PKG-01 | INV-PKG-01-022-03381 | 284.64 | 166160.84 | 8308.04 | Under Review | 157852.8 | 2024-Q4
EXP-004142 | 2024-11-08 | BOQ-PKG-02-00162 | PKG-02 | INV-PKG-02-013-04142 | 206.29 | 186777.95 | 9338.9 | Approved Pending Payment | 177439.05 | 2024-Q4
EXP-004766 | 2024-11-08 | BOQ-PKG-06-00786 | PKG-06 | INV-PKG-06-007-04766 | 148.14 | 54643.62 | 2732.18 | Paid | 51911.44 | 2024-Q4
EXP-004886 | 2024-11-08 | BOQ-PKG-06-00906 | PKG-06 | INV-PKG-06-022-04886 | 412.32 | 31110.4 | 1555.52 | Approved Pending Payment | 29554.88 | 2024-Q4
EXP-006963 | 2024-11-08 | BOQ-PKG-03-00993 | PKG-03 | INV-PKG-03-034-06963 | 150.62 | 144231.91 | 7211.6 | Approved Pending Payment | 137020.31 | 2024-Q4
EXP-000052 | 2024-11-09 | BOQ-PKG-02-00052 | PKG-02 | INV-PKG-02-018-00052 | 30.31 | 169702.4 | 8485.12 | Paid | 161217.28 | 2024-Q4
EXP-001397 | 2024-11-09 | BOQ-PKG-07-01397 | PKG-07 | INV-PKG-07-033-01397 | 238.03 | 113251.6 | 5662.58 | Under Review | 107589.02 | 2024-Q4
EXP-001645 | 2024-11-09 | BOQ-PKG-05-01645 | PKG-05 | INV-PKG-05-001-01645 | 357.66 | 49288.51 | 2464.43 | Paid | 46824.08 | 2024-Q4
EXP-003528 | 2024-11-09 | BOQ-PKG-08-01538 | PKG-08 | INV-PKG-08-029-03528 | 163.07 | 31375.4 | 1568.77 | Paid | 29806.63 | 2024-Q4
EXP-004071 | 2024-11-09 | BOQ-PKG-01-00091 | PKG-01 | INV-PKG-01-012-04071 | 92.16 | 170745.39 | 8537.27 | Paid | 162208.12 | 2024-Q4
EXP-000183 | 2024-11-10 | BOQ-PKG-03-00183 | PKG-03 | INV-PKG-03-009-00183 | 29.8 | 134999.53 | 6749.98 | Paid | 128249.55 | 2024-Q4
EXP-000844 | 2024-11-10 | BOQ-PKG-04-00844 | PKG-04 | INV-PKG-04-005-00844 | 306.4 | 78477.92 | 3923.9 | Paid | 74554.02 | 2024-Q4
EXP-003168 | 2024-11-10 | BOQ-PKG-08-01178 | PKG-08 | INV-PKG-08-019-03168 | 350.1 | 195456.52 | 9772.83 | Approved Pending Payment | 185683.69 | 2024-Q4
EXP-005171 | 2024-11-10 | BOQ-PKG-01-01191 | PKG-01 | INV-PKG-01-027-05171 | 422.88 | 72423.9 | 3621.2 | Paid | 68802.7 | 2024-Q4
EXP-005474 | 2024-11-10 | BOQ-PKG-04-01494 | PKG-04 | INV-PKG-04-015-05474 | 65.69 | 84493.99 | 4224.7 | Approved Pending Payment | 80269.29 | 2024-Q4
EXP-006625 | 2024-11-10 | BOQ-PKG-05-00655 | PKG-05 | INV-PKG-05-011-06625 | 12.59 | 198184.7 | 9909.24 | Paid | 188275.46 | 2024-Q4
EXP-006642 | 2024-11-10 | BOQ-PKG-02-00672 | PKG-02 | INV-PKG-02-028-06642 | 345.8 | 82574.53 | 4128.73 | Paid | 78445.8 | 2024-Q4
EXP-000128 | 2024-11-11 | BOQ-PKG-08-00128 | PKG-08 | INV-PKG-08-024-00128 | 364.93 | 184502.58 | 9225.13 | Approved Pending Payment | 175277.45 | 2024-Q4
EXP-000876 | 2024-11-11 | BOQ-PKG-06-00876 | PKG-06 | INV-PKG-06-002-00876 | 130.46 | 118734.3 | 5936.72 | Paid | 112797.58 | 2024-Q4
EXP-001860 | 2024-11-11 | BOQ-PKG-10-01860 | PKG-10 | INV-PKG-10-006-01860 | 245.08 | 151998.68 | 7599.93 | Approved Pending Payment | 144398.75 | 2024-Q4
EXP-002604 | 2024-11-11 | BOQ-PKG-04-00614 | PKG-04 | INV-PKG-04-015-02604 | 243.55 | 149739.33 | 7486.97 | Paid | 142252.36 | 2024-Q4
EXP-002610 | 2024-11-11 | BOQ-PKG-10-00620 | PKG-10 | INV-PKG-10-021-02610 | 384.92 | 175995.87 | 8799.79 | Paid | 167196.08 | 2024-Q4
EXP-005907 | 2024-11-11 | BOQ-PKG-07-01927 | PKG-07 | INV-PKG-07-028-05907 | 46.07 | 105609.08 | 5280.45 | Paid | 100328.63 | 2024-Q4
EXP-000229 | 2024-11-12 | BOQ-PKG-09-00229 | PKG-09 | INV-PKG-09-020-00229 | 416.47 | 34396.53 | 1719.83 | Under Review | 32676.7 | 2024-Q4
EXP-001954 | 2024-11-12 | BOQ-PKG-04-01954 | PKG-04 | INV-PKG-04-030-01954 | 446.8 | 153322.43 | 7666.12 | Paid | 145656.31 | 2024-Q4
EXP-003302 | 2024-11-12 | BOQ-PKG-02-01312 | PKG-02 | INV-PKG-02-013-03302 | 155.79 | 167938.63 | 8396.93 | Paid | 159541.7 | 2024-Q4
EXP-004697 | 2024-11-12 | BOQ-PKG-07-00717 | PKG-07 | INV-PKG-07-008-04697 | 46.89 | 81818.03 | 4090.9 | Paid | 77727.13 | 2024-Q4
EXP-004730 | 2024-11-12 | BOQ-PKG-10-00750 | PKG-10 | INV-PKG-10-006-04730 | 191 | 150992.23 | 7549.61 | Paid | 143442.62 | 2024-Q4
EXP-004170 | 2024-11-13 | BOQ-PKG-10-00190 | PKG-10 | INV-PKG-10-006-04170 | 196.87 | 35014.51 | 1750.73 | Paid | 33263.78 | 2024-Q4
EXP-004839 | 2024-11-13 | BOQ-PKG-09-00859 | PKG-09 | INV-PKG-09-010-04839 | 68.36 | 208829.88 | 10441.49 | Paid | 198388.39 | 2024-Q4
EXP-004847 | 2024-11-13 | BOQ-PKG-07-00867 | PKG-07 | INV-PKG-07-018-04847 | 53.43 | 45426.24 | 2271.31 | Paid | 43154.93 | 2024-Q4
EXP-006158 | 2024-11-13 | BOQ-PKG-08-00188 | PKG-08 | INV-PKG-08-034-06158 | 18.84 | 139622.49 | 6981.12 | Approved Pending Payment | 132641.37 | 2024-Q4
EXP-006468 | 2024-11-13 | BOQ-PKG-08-00498 | PKG-08 | INV-PKG-08-029-06468 | 158.33 | 65384.84 | 3269.24 | Paid | 62115.6 | 2024-Q4
EXP-006614 | 2024-11-13 | BOQ-PKG-04-00644 | PKG-04 | INV-PKG-04-035-06614 | 145.27 | 45117.3 | 2255.87 | Paid | 42861.43 | 2024-Q4
EXP-000148 | 2024-11-14 | BOQ-PKG-08-00148 | PKG-08 | INV-PKG-08-009-00148 | 270.24 | 208789.44 | 10439.47 | Under Review | 198349.97 | 2024-Q4
EXP-000164 | 2024-11-14 | BOQ-PKG-04-00164 | PKG-04 | INV-PKG-04-025-00164 | 78.11 | 165131.9 | 8256.59 | Paid | 156875.31 | 2024-Q4
EXP-000591 | 2024-11-14 | BOQ-PKG-01-00591 | PKG-01 | INV-PKG-01-032-00591 | 46.62 | 100669.66 | 5033.48 | Under Review | 95636.18 | 2024-Q4
EXP-000659 | 2024-11-14 | BOQ-PKG-09-00659 | PKG-09 | INV-PKG-09-030-00659 | 433.94 | 138363.21 | 6918.16 | Paid | 131445.05 | 2024-Q4
EXP-002463 | 2024-11-14 | BOQ-PKG-03-00473 | PKG-03 | INV-PKG-03-014-02463 | 92.12 | 180490.88 | 9024.54 | Paid | 171466.34 | 2024-Q4
EXP-002846 | 2024-11-14 | BOQ-PKG-06-00856 | PKG-06 | INV-PKG-06-012-02846 | 259.48 | 159270.39 | 7963.52 | Approved Pending Payment | 151306.87 | 2024-Q4
EXP-002921 | 2024-11-14 | BOQ-PKG-01-00931 | PKG-01 | INV-PKG-01-017-02921 | 316.67 | 46339.15 | 2316.96 | Approved Pending Payment | 44022.19 | 2024-Q4
EXP-003797 | 2024-11-14 | BOQ-PKG-07-01807 | PKG-07 | INV-PKG-07-018-03797 | 433.02 | 137064.7 | 6853.24 | Paid | 130211.46 | 2024-Q4
EXP-003852 | 2024-11-14 | BOQ-PKG-02-01862 | PKG-02 | INV-PKG-02-003-03852 | 208.93 | 157782.49 | 7889.12 | Approved Pending Payment | 149893.37 | 2024-Q4
EXP-005569 | 2024-11-14 | BOQ-PKG-09-01589 | PKG-09 | INV-PKG-09-005-05569 | 371.44 | 91165.6 | 4558.28 | Approved Pending Payment | 86607.32 | 2024-Q4
EXP-006594 | 2024-11-14 | BOQ-PKG-04-00624 | PKG-04 | INV-PKG-04-015-06594 | 182.21 | 41744.79 | 2087.24 | Paid | 39657.55 | 2024-Q4
EXP-001322 | 2024-11-15 | BOQ-PKG-02-01322 | PKG-02 | INV-PKG-02-028-01322 | 38.38 | 195699.02 | 9784.95 | Paid | 185914.07 | 2024-Q4
EXP-001707 | 2024-11-15 | BOQ-PKG-07-01707 | PKG-07 | INV-PKG-07-028-01707 | 445.36 | 53448.27 | 2672.41 | Approved Pending Payment | 50775.86 | 2024-Q4
EXP-003199 | 2024-11-15 | BOQ-PKG-09-01209 | PKG-09 | INV-PKG-09-015-03199 | 367.74 | 130287.27 | 6514.36 | Approved Pending Payment | 123772.91 | 2024-Q4
EXP-003570 | 2024-11-15 | BOQ-PKG-10-01580 | PKG-10 | INV-PKG-10-001-03570 | 237.84 | 150245.03 | 7512.25 | Paid | 142732.78 | 2024-Q4
EXP-003571 | 2024-11-15 | BOQ-PKG-01-01581 | PKG-01 | INV-PKG-01-002-03571 | 142.23 | 95252.55 | 4762.63 | Approved Pending Payment | 90489.92 | 2024-Q4
EXP-003720 | 2024-11-15 | BOQ-PKG-10-01730 | PKG-10 | INV-PKG-10-011-03720 | 154.28 | 154082.19 | 7704.11 | Paid | 146378.08 | 2024-Q4
EXP-005162 | 2024-11-15 | BOQ-PKG-02-01182 | PKG-02 | INV-PKG-02-018-05162 | 281.17 | 184238.35 | 9211.92 | Paid | 175026.43 | 2024-Q4
EXP-005220 | 2024-11-15 | BOQ-PKG-10-01240 | PKG-10 | INV-PKG-10-006-05220 | 254.74 | 72018.51 | 3600.93 | Paid | 68417.58 | 2024-Q4
EXP-006429 | 2024-11-15 | BOQ-PKG-09-00459 | PKG-09 | INV-PKG-09-025-06429 | 72.74 | 212277.27 | 10613.86 | Paid | 201663.41 | 2024-Q4
EXP-000996 | 2024-11-16 | BOQ-PKG-06-00996 | PKG-06 | INV-PKG-06-017-00996 | 291.98 | 184484.84 | 9224.24 | Approved Pending Payment | 175260.6 | 2024-Q4
EXP-001109 | 2024-11-16 | BOQ-PKG-09-01109 | PKG-09 | INV-PKG-09-025-01109 | 276.63 | 201961.68 | 10098.08 | Paid | 191863.6 | 2024-Q4
EXP-001553 | 2024-11-16 | BOQ-PKG-03-01553 | PKG-03 | INV-PKG-03-014-01553 | 199.91 | 84434.37 | 4221.72 | Approved Pending Payment | 80212.65 | 2024-Q4
EXP-002093 | 2024-11-16 | BOQ-PKG-03-00103 | PKG-03 | INV-PKG-03-029-02093 | 193.87 | 52442.67 | 2622.13 | Paid | 49820.54 | 2024-Q4
EXP-002289 | 2024-11-16 | BOQ-PKG-09-00299 | PKG-09 | INV-PKG-09-015-02289 | 310.46 | 65296.12 | 3264.81 | Under Review | 62031.31 | 2024-Q4
EXP-002487 | 2024-11-16 | BOQ-PKG-07-00497 | PKG-07 | INV-PKG-07-003-02487 | 295.15 | 159566.94 | 7978.35 | Paid | 151588.59 | 2024-Q4
EXP-004385 | 2024-11-16 | BOQ-PKG-05-00405 | PKG-05 | INV-PKG-05-011-04385 | 158.73 | 175254.17 | 8762.71 | Paid | 166491.46 | 2024-Q4
EXP-004817 | 2024-11-16 | BOQ-PKG-07-00837 | PKG-07 | INV-PKG-07-023-04817 | 59.58 | 123120.22 | 6156.01 | Approved Pending Payment | 116964.21 | 2024-Q4
EXP-000912 | 2024-11-17 | BOQ-PKG-02-00912 | PKG-02 | INV-PKG-02-003-00912 | 65.63 | 189222.28 | 9461.11 | Under Review | 179761.17 | 2024-Q4
EXP-002028 | 2024-11-17 | BOQ-PKG-08-00038 | PKG-08 | INV-PKG-08-034-02028 | 161.43 | 37121.19 | 1856.06 | Paid | 35265.13 | 2024-Q4
EXP-002330 | 2024-11-17 | BOQ-PKG-10-00340 | PKG-10 | INV-PKG-10-021-02330 | 275.89 | 193176.94 | 9658.85 | Paid | 183518.09 | 2024-Q4
EXP-003267 | 2024-11-17 | BOQ-PKG-07-01277 | PKG-07 | INV-PKG-07-013-03267 | 117.35 | 78692.54 | 3934.63 | Paid | 74757.91 | 2024-Q4
EXP-003793 | 2024-11-17 | BOQ-PKG-03-01803 | PKG-03 | INV-PKG-03-014-03793 | 265.59 | 81097 | 4054.85 | Paid | 77042.15 | 2024-Q4
EXP-003814 | 2024-11-17 | BOQ-PKG-04-01824 | PKG-04 | INV-PKG-04-035-03814 | 217.96 | 118653.76 | 5932.69 | Under Review | 112721.07 | 2024-Q4
EXP-004337 | 2024-11-17 | BOQ-PKG-07-00357 | PKG-07 | INV-PKG-07-033-04337 | 51.08 | 173368.92 | 8668.45 | Disputed | 164700.47 | 2024-Q4
EXP-005113 | 2024-11-17 | BOQ-PKG-03-01133 | PKG-03 | INV-PKG-03-004-05113 | 188.77 | 189007.93 | 9450.4 | Paid | 179557.53 | 2024-Q4
EXP-005250 | 2024-11-17 | BOQ-PKG-10-01270 | PKG-10 | INV-PKG-10-001-05250 | 383.22 | 160605.3 | 8030.26 | Paid | 152575.04 | 2024-Q4
EXP-005888 | 2024-11-17 | BOQ-PKG-08-01908 | PKG-08 | INV-PKG-08-009-05888 | 229.23 | 208331.45 | 10416.57 | Paid | 197914.88 | 2024-Q4
EXP-000019 | 2024-11-18 | BOQ-PKG-09-00019 | PKG-09 | INV-PKG-09-020-00019 | 306.04 | 135979.74 | 6798.99 | Paid | 129180.75 | 2024-Q4
EXP-002073 | 2024-11-18 | BOQ-PKG-03-00083 | PKG-03 | INV-PKG-03-009-02073 | 86.39 | 52434.57 | 2621.73 | Disputed | 49812.84 | 2024-Q4
EXP-002385 | 2024-11-18 | BOQ-PKG-05-00395 | PKG-05 | INV-PKG-05-006-02385 | 108.59 | 71800.82 | 3590.04 | Paid | 68210.78 | 2024-Q4
EXP-002519 | 2024-11-18 | BOQ-PKG-09-00529 | PKG-09 | INV-PKG-09-035-02519 | 86.33 | 194868.77 | 9743.44 | Paid | 185125.33 | 2024-Q4
EXP-003380 | 2024-11-18 | BOQ-PKG-10-01390 | PKG-10 | INV-PKG-10-021-03380 | 419.87 | 83486.99 | 4174.35 | Paid | 79312.64 | 2024-Q4
EXP-003438 | 2024-11-18 | BOQ-PKG-08-01448 | PKG-08 | INV-PKG-08-009-03438 | 208.51 | 66045.69 | 3302.28 | Paid | 62743.41 | 2024-Q4
EXP-000682 | 2024-11-19 | BOQ-PKG-02-00682 | PKG-02 | INV-PKG-02-018-00682 | 47.16 | 202693.49 | 10134.67 | Paid | 192558.82 | 2024-Q4
EXP-000940 | 2024-11-19 | BOQ-PKG-10-00940 | PKG-10 | INV-PKG-10-031-00940 | 68.94 | 156904.28 | 7845.21 | Paid | 149059.07 | 2024-Q4
EXP-002379 | 2024-11-19 | BOQ-PKG-09-00389 | PKG-09 | INV-PKG-09-035-02379 | 20.61 | 145960.06 | 7298 | Paid | 138662.06 | 2024-Q4
EXP-002464 | 2024-11-19 | BOQ-PKG-04-00474 | PKG-04 | INV-PKG-04-015-02464 | 110.13 | 193584.04 | 9679.2 | Paid | 183904.84 | 2024-Q4
EXP-002848 | 2024-11-19 | BOQ-PKG-08-00858 | PKG-08 | INV-PKG-08-014-02848 | 278.04 | 32618.92 | 1630.95 | Paid | 30987.97 | 2024-Q4
EXP-005836 | 2024-11-19 | BOQ-PKG-06-01856 | PKG-06 | INV-PKG-06-027-05836 | 148.92 | 127819.04 | 6390.95 | Under Review | 121428.09 | 2024-Q4
EXP-000576 | 2024-11-20 | BOQ-PKG-06-00576 | PKG-06 | INV-PKG-06-017-00576 | 284.44 | 77735.37 | 3886.77 | Paid | 73848.6 | 2024-Q4
EXP-001056 | 2024-11-20 | BOQ-PKG-06-01056 | PKG-06 | INV-PKG-06-007-01056 | 112.78 | 56697.63 | 2834.88 | Paid | 53862.75 | 2024-Q4
EXP-002725 | 2024-11-20 | BOQ-PKG-05-00735 | PKG-05 | INV-PKG-05-031-02725 | 297.9 | 47145.77 | 2357.29 | Paid | 44788.48 | 2024-Q4
EXP-003620 | 2024-11-20 | BOQ-PKG-10-01630 | PKG-10 | INV-PKG-10-016-03620 | 189.45 | 110200.07 | 5510 | Paid | 104690.07 | 2024-Q4
EXP-004425 | 2024-11-20 | BOQ-PKG-05-00445 | PKG-05 | INV-PKG-05-016-04425 | 384.48 | 115574.19 | 5778.71 | Paid | 109795.48 | 2024-Q4
EXP-004857 | 2024-11-20 | BOQ-PKG-07-00877 | PKG-07 | INV-PKG-07-028-04857 | 36.29 | 185572.85 | 9278.64 | Approved Pending Payment | 176294.21 | 2024-Q4
EXP-005177 | 2024-11-20 | BOQ-PKG-07-01197 | PKG-07 | INV-PKG-07-033-05177 | 61.3 | 64841.94 | 3242.1 | Disputed | 61599.84 | 2024-Q4
EXP-005916 | 2024-11-20 | BOQ-PKG-06-01936 | PKG-06 | INV-PKG-06-002-05916 | 230.61 | 92094.67 | 4604.73 | Paid | 87489.94 | 2024-Q4
EXP-006129 | 2024-11-20 | BOQ-PKG-09-00159 | PKG-09 | INV-PKG-09-005-06129 | 216.39 | 160566.08 | 8028.3 | Paid | 152537.78 | 2024-Q4
EXP-006499 | 2024-11-20 | BOQ-PKG-09-00529 | PKG-09 | INV-PKG-09-025-06499 | 140.78 | 183290.96 | 9164.55 | Paid | 174126.41 | 2024-Q4
EXP-001187 | 2024-11-21 | BOQ-PKG-07-01187 | PKG-07 | INV-PKG-07-033-01187 | 409.14 | 42390.07 | 2119.5 | Paid | 40270.57 | 2024-Q4
EXP-002426 | 2024-11-21 | BOQ-PKG-06-00436 | PKG-06 | INV-PKG-06-012-02426 | 215.04 | 166912.5 | 8345.62 | Paid | 158566.88 | 2024-Q4
EXP-002821 | 2024-11-21 | BOQ-PKG-01-00831 | PKG-01 | INV-PKG-01-022-02821 | 213.16 | 156102.31 | 7805.12 | Approved Pending Payment | 148297.19 | 2024-Q4
EXP-003209 | 2024-11-21 | BOQ-PKG-09-01219 | PKG-09 | INV-PKG-09-025-03209 | 147.33 | 86048.28 | 4302.41 | Paid | 81745.87 | 2024-Q4
EXP-004204 | 2024-11-21 | BOQ-PKG-04-00224 | PKG-04 | INV-PKG-04-005-04204 | 328.5 | 198435.48 | 9921.77 | Under Review | 188513.71 | 2024-Q4
EXP-004448 | 2024-11-21 | BOQ-PKG-08-00468 | PKG-08 | INV-PKG-08-004-04448 | 164 | 86665.49 | 4333.27 | Paid | 82332.22 | 2024-Q4
EXP-000675 | 2024-11-22 | BOQ-PKG-05-00675 | PKG-05 | INV-PKG-05-011-00675 | 23.78 | 117008.08 | 5850.4 | Paid | 111157.68 | 2024-Q4
EXP-001048 | 2024-11-22 | BOQ-PKG-08-01048 | PKG-08 | INV-PKG-08-034-01048 | 243.91 | 199260.32 | 9963.02 | Paid | 189297.3 | 2024-Q4
EXP-002113 | 2024-11-22 | BOQ-PKG-03-00123 | PKG-03 | INV-PKG-03-014-02113 | 271.2 | 57230.17 | 2861.51 | Paid | 54368.66 | 2024-Q4
EXP-003147 | 2024-11-22 | BOQ-PKG-07-01157 | PKG-07 | INV-PKG-07-033-03147 | 59.03 | 106675.88 | 5333.79 | Paid | 101342.09 | 2024-Q4
EXP-003761 | 2024-11-22 | BOQ-PKG-01-01771 | PKG-01 | INV-PKG-01-017-03761 | 50.63 | 71267.74 | 3563.39 | Paid | 67704.35 | 2024-Q4
EXP-003896 | 2024-11-22 | BOQ-PKG-06-01906 | PKG-06 | INV-PKG-06-012-03896 | 315.53 | 173121.74 | 8656.09 | Approved Pending Payment | 164465.65 | 2024-Q4
EXP-004604 | 2024-11-22 | BOQ-PKG-04-00624 | PKG-04 | INV-PKG-04-020-04604 | 218.52 | 182227.12 | 9111.36 | Paid | 173115.76 | 2024-Q4
EXP-005094 | 2024-11-22 | BOQ-PKG-04-01114 | PKG-04 | INV-PKG-04-020-05094 | 416.34 | 191995.63 | 9599.78 | Paid | 182395.85 | 2024-Q4
EXP-006621 | 2024-11-22 | BOQ-PKG-01-00651 | PKG-01 | INV-PKG-01-007-06621 | 102.76 | 179294.66 | 8964.73 | Paid | 170329.93 | 2024-Q4
EXP-001130 | 2024-11-23 | BOQ-PKG-10-01130 | PKG-10 | INV-PKG-10-011-01130 | 269.93 | 180169.68 | 9008.48 | Paid | 171161.2 | 2024-Q4
EXP-002756 | 2024-11-23 | BOQ-PKG-06-00766 | PKG-06 | INV-PKG-06-027-02756 | 327.57 | 134090.17 | 6704.51 | Paid | 127385.66 | 2024-Q4
EXP-005128 | 2024-11-23 | BOQ-PKG-08-01148 | PKG-08 | INV-PKG-08-019-05128 | 125.02 | 125029.29 | 6251.46 | Paid | 118777.83 | 2024-Q4
EXP-005727 | 2024-11-23 | BOQ-PKG-07-01747 | PKG-07 | INV-PKG-07-023-05727 | 305.28 | 54482.89 | 2724.14 | Approved Pending Payment | 51758.75 | 2024-Q4
EXP-002402 | 2024-11-24 | BOQ-PKG-02-00412 | PKG-02 | INV-PKG-02-023-02402 | 441.1 | 85228.24 | 4261.41 | Paid | 80966.83 | 2024-Q4
EXP-004559 | 2024-11-24 | BOQ-PKG-09-00579 | PKG-09 | INV-PKG-09-010-04559 | 302.04 | 201395.1 | 10069.76 | Paid | 191325.34 | 2024-Q4
EXP-004816 | 2024-11-24 | BOQ-PKG-06-00836 | PKG-06 | INV-PKG-06-022-04816 | 273.34 | 172292.29 | 8614.61 | Paid | 163677.68 | 2024-Q4
EXP-005174 | 2024-11-24 | BOQ-PKG-04-01194 | PKG-04 | INV-PKG-04-030-05174 | 225.53 | 33521.35 | 1676.07 | Paid | 31845.28 | 2024-Q4
EXP-006372 | 2024-11-24 | BOQ-PKG-02-00402 | PKG-02 | INV-PKG-02-003-06372 | 411.32 | 44779.81 | 2238.99 | Paid | 42540.82 | 2024-Q4
EXP-000243 | 2024-11-25 | BOQ-PKG-03-00243 | PKG-03 | INV-PKG-03-034-00243 | 316.86 | 172442.96 | 8622.15 | Paid | 163820.81 | 2024-Q4
EXP-003343 | 2024-11-25 | BOQ-PKG-03-01353 | PKG-03 | INV-PKG-03-019-03343 | 426.57 | 188600.08 | 9430 | Paid | 179170.08 | 2024-Q4
EXP-004036 | 2024-11-25 | BOQ-PKG-06-00056 | PKG-06 | INV-PKG-06-012-04036 | 262.3 | 43699.07 | 2184.95 | Paid | 41514.12 | 2024-Q4
EXP-005547 | 2024-11-25 | BOQ-PKG-07-01567 | PKG-07 | INV-PKG-07-018-05547 | 403.28 | 28072.35 | 1403.62 | Paid | 26668.73 | 2024-Q4
EXP-004239 | 2024-11-26 | BOQ-PKG-09-00259 | PKG-09 | INV-PKG-09-005-04239 | 120.74 | 32680.16 | 1634.01 | Paid | 31046.15 | 2024-Q4
EXP-005977 | 2024-11-26 | BOQ-PKG-07-00007 | PKG-07 | INV-PKG-07-028-05977 | 259.79 | 81624.29 | 4081.21 | Paid | 77543.08 | 2024-Q4
EXP-000304 | 2024-11-27 | BOQ-PKG-04-00304 | PKG-04 | INV-PKG-04-025-00304 | 262.79 | 190956.05 | 9547.8 | Paid | 181408.25 | 2024-Q4
EXP-000515 | 2024-11-27 | BOQ-PKG-05-00515 | PKG-05 | INV-PKG-05-026-00515 | 237.21 | 128155.09 | 6407.75 | Approved Pending Payment | 121747.34 | 2024-Q4
EXP-001053 | 2024-11-27 | BOQ-PKG-03-01053 | PKG-03 | INV-PKG-03-004-01053 | 314.49 | 156847.6 | 7842.38 | Paid | 149005.22 | 2024-Q4
EXP-001777 | 2024-11-27 | BOQ-PKG-07-01777 | PKG-07 | INV-PKG-07-028-01777 | 432.13 | 120103.29 | 6005.16 | Paid | 114098.13 | 2024-Q4
EXP-002134 | 2024-11-27 | BOQ-PKG-04-00144 | PKG-04 | INV-PKG-04-035-02134 | 397.16 | 142252.37 | 7112.62 | Paid | 135139.75 | 2024-Q4
EXP-002636 | 2024-11-27 | BOQ-PKG-06-00646 | PKG-06 | INV-PKG-06-012-02636 | 375.04 | 140922.98 | 7046.15 | Paid | 133876.83 | 2024-Q4
EXP-002925 | 2024-11-27 | BOQ-PKG-05-00935 | PKG-05 | INV-PKG-05-021-02925 | 248.33 | 43540.59 | 2177.03 | Paid | 41363.56 | 2024-Q4
EXP-003333 | 2024-11-27 | BOQ-PKG-03-01343 | PKG-03 | INV-PKG-03-009-03333 | 161.17 | 32570.68 | 1628.53 | Paid | 30942.15 | 2024-Q4
EXP-005073 | 2024-11-27 | BOQ-PKG-03-01093 | PKG-03 | INV-PKG-03-034-05073 | 408.53 | 36572.71 | 1828.64 | Paid | 34744.07 | 2024-Q4
EXP-005240 | 2024-11-27 | BOQ-PKG-10-01260 | PKG-10 | INV-PKG-10-026-05240 | 99.53 | 140093.1 | 7004.66 | Paid | 133088.44 | 2024-Q4
EXP-005500 | 2024-11-27 | BOQ-PKG-10-01520 | PKG-10 | INV-PKG-10-006-05500 | 310.44 | 69666.64 | 3483.33 | Disputed | 66183.31 | 2024-Q4
EXP-005786 | 2024-11-27 | BOQ-PKG-06-01806 | PKG-06 | INV-PKG-06-012-05786 | 295.9 | 97074.48 | 4853.72 | Paid | 92220.76 | 2024-Q4
EXP-006003 | 2024-11-27 | BOQ-PKG-03-00033 | PKG-03 | INV-PKG-03-019-06003 | 173.01 | 161541.09 | 8077.05 | Paid | 153464.04 | 2024-Q4
EXP-006989 | 2024-11-27 | BOQ-PKG-09-01019 | PKG-09 | INV-PKG-09-025-06989 | 179.18 | 107040.07 | 5352 | Paid | 101688.07 | 2024-Q4
EXP-000621 | 2024-11-28 | BOQ-PKG-01-00621 | PKG-01 | INV-PKG-01-027-00621 | 345.47 | 104610.77 | 5230.54 | Paid | 99380.23 | 2024-Q4
EXP-000861 | 2024-11-28 | BOQ-PKG-01-00861 | PKG-01 | INV-PKG-01-022-00861 | 439.33 | 184541.51 | 9227.08 | Paid | 175314.43 | 2024-Q4
EXP-001544 | 2024-11-28 | BOQ-PKG-04-01544 | PKG-04 | INV-PKG-04-005-01544 | 211.6 | 203248.01 | 10162.4 | Paid | 193085.61 | 2024-Q4
EXP-002120 | 2024-11-28 | BOQ-PKG-10-00130 | PKG-10 | INV-PKG-10-021-02120 | 443.57 | 117954.41 | 5897.72 | Paid | 112056.69 | 2024-Q4
EXP-002169 | 2024-11-28 | BOQ-PKG-09-00179 | PKG-09 | INV-PKG-09-035-02169 | 5.59 | 80022.38 | 4001.12 | Paid | 76021.26 | 2024-Q4
EXP-004692 | 2024-11-28 | BOQ-PKG-02-00712 | PKG-02 | INV-PKG-02-003-04692 | 381.79 | 170418.06 | 8520.9 | Under Review | 161897.16 | 2024-Q4
EXP-005343 | 2024-11-28 | BOQ-PKG-03-01363 | PKG-03 | INV-PKG-03-024-05343 | 177.78 | 53675.09 | 2683.75 | Approved Pending Payment | 50991.34 | 2024-Q4
EXP-005372 | 2024-11-28 | BOQ-PKG-02-01392 | PKG-02 | INV-PKG-02-018-05372 | 365.67 | 180407.56 | 9020.38 | Paid | 171387.18 | 2024-Q4
EXP-005396 | 2024-11-28 | BOQ-PKG-06-01416 | PKG-06 | INV-PKG-06-007-05396 | 91.87 | 147154.68 | 7357.73 | Approved Pending Payment | 139796.95 | 2024-Q4
EXP-006828 | 2024-11-28 | BOQ-PKG-08-00858 | PKG-08 | INV-PKG-08-004-06828 | 354.56 | 138996.87 | 6949.84 | Approved Pending Payment | 132047.03 | 2024-Q4
EXP-006910 | 2024-11-28 | BOQ-PKG-10-00940 | PKG-10 | INV-PKG-10-016-06910 | 233.36 | 191451.19 | 9572.56 | Paid | 181878.63 | 2024-Q4
EXP-006971 | 2024-11-28 | BOQ-PKG-01-01001 | PKG-01 | INV-PKG-01-007-06971 | 206.16 | 85957.34 | 4297.87 | Paid | 81659.47 | 2024-Q4
EXP-000267 | 2024-11-29 | BOQ-PKG-07-00267 | PKG-07 | INV-PKG-07-023-00267 | 278.71 | 204132.76 | 10206.64 | Paid | 193926.12 | 2024-Q4
EXP-001060 | 2024-11-29 | BOQ-PKG-10-01060 | PKG-10 | INV-PKG-10-011-01060 | 134.18 | 120321.32 | 6016.07 | Paid | 114305.25 | 2024-Q4
EXP-001539 | 2024-11-29 | BOQ-PKG-09-01539 | PKG-09 | INV-PKG-09-035-01539 | 69.29 | 69578.21 | 3478.91 | Paid | 66099.3 | 2024-Q4
EXP-002516 | 2024-11-29 | BOQ-PKG-06-00526 | PKG-06 | INV-PKG-06-032-02516 | 289.69 | 126651.16 | 6332.56 | Paid | 120318.6 | 2024-Q4
EXP-002528 | 2024-11-29 | BOQ-PKG-08-00538 | PKG-08 | INV-PKG-08-009-02528 | 85.96 | 81439.91 | 4072 | Under Review | 77367.91 | 2024-Q4
EXP-002935 | 2024-11-29 | BOQ-PKG-05-00945 | PKG-05 | INV-PKG-05-031-02935 | 120.99 | 206922.07 | 10346.1 | Approved Pending Payment | 196575.97 | 2024-Q4
EXP-003097 | 2024-11-29 | BOQ-PKG-07-01107 | PKG-07 | INV-PKG-07-018-03097 | 348.96 | 159048.65 | 7952.43 | Approved Pending Payment | 151096.22 | 2024-Q4
EXP-003398 | 2024-11-29 | BOQ-PKG-08-01408 | PKG-08 | INV-PKG-08-004-03398 | 323.6 | 115229.57 | 5761.48 | Paid | 109468.09 | 2024-Q4
EXP-004831 | 2024-11-29 | BOQ-PKG-01-00851 | PKG-01 | INV-PKG-01-002-04831 | 157.23 | 117469.35 | 5873.47 | Paid | 111595.88 | 2024-Q4
EXP-006118 | 2024-11-29 | BOQ-PKG-08-00148 | PKG-08 | INV-PKG-08-029-06118 | 130.84 | 156206.3 | 7810.32 | Paid | 148395.98 | 2024-Q4
EXP-001120 | 2024-11-30 | BOQ-PKG-10-01120 | PKG-10 | INV-PKG-10-001-01120 | 324.48 | 156909.99 | 7845.5 | Paid | 149064.49 | 2024-Q4
EXP-002014 | 2024-11-30 | BOQ-PKG-04-00024 | PKG-04 | INV-PKG-04-020-02014 | 39.65 | 61654.32 | 3082.72 | Paid | 58571.6 | 2024-Q4
EXP-003478 | 2024-11-30 | BOQ-PKG-08-01488 | PKG-08 | INV-PKG-08-014-03478 | 248.84 | 170663.58 | 8533.18 | Paid | 162130.4 | 2024-Q4
EXP-006860 | 2024-11-30 | BOQ-PKG-10-00890 | PKG-10 | INV-PKG-10-001-06860 | 344.35 | 172009.71 | 8600.49 | Paid | 163409.22 | 2024-Q4
EXP-000532 | 2024-12-01 | BOQ-PKG-02-00532 | PKG-02 | INV-PKG-02-008-00532 | 408.56 | 129267.91 | 6463.4 | Paid | 122804.51 | 2024-Q4
EXP-001021 | 2024-12-01 | BOQ-PKG-01-01021 | PKG-01 | INV-PKG-01-007-01021 | 214.08 | 87412.06 | 4370.6 | Paid | 83041.46 | 2024-Q4
EXP-002455 | 2024-12-01 | BOQ-PKG-05-00465 | PKG-05 | INV-PKG-05-006-02455 | 188.24 | 41159.05 | 2057.95 | Paid | 39101.1 | 2024-Q4
EXP-004358 | 2024-12-01 | BOQ-PKG-08-00378 | PKG-08 | INV-PKG-08-019-04358 | 44.89 | 192372.61 | 9618.63 | Paid | 182753.98 | 2024-Q4
EXP-005098 | 2024-12-01 | BOQ-PKG-08-01118 | PKG-08 | INV-PKG-08-024-05098 | 72.08 | 144162.37 | 7208.12 | Paid | 136954.25 | 2024-Q4
EXP-005212 | 2024-12-01 | BOQ-PKG-02-01232 | PKG-02 | INV-PKG-02-033-05212 | 437.19 | 49276.8 | 2463.84 | Paid | 46812.96 | 2024-Q4
EXP-000127 | 2024-12-02 | BOQ-PKG-07-00127 | PKG-07 | INV-PKG-07-023-00127 | 32.78 | 111199.07 | 5559.95 | Paid | 105639.12 | 2024-Q4
EXP-003101 | 2024-12-02 | BOQ-PKG-01-01111 | PKG-01 | INV-PKG-01-022-03101 | 60.04 | 150117.28 | 7505.86 | Paid | 142611.42 | 2024-Q4
EXP-003189 | 2024-12-02 | BOQ-PKG-09-01199 | PKG-09 | INV-PKG-09-005-03189 | 162.89 | 134577.99 | 6728.9 | Paid | 127849.09 | 2024-Q4
EXP-004431 | 2024-12-02 | BOQ-PKG-01-00451 | PKG-01 | INV-PKG-01-022-04431 | 177.26 | 172499.36 | 8624.97 | Paid | 163874.39 | 2024-Q4
EXP-004795 | 2024-12-02 | BOQ-PKG-05-00815 | PKG-05 | INV-PKG-05-001-04795 | 237.53 | 117755.05 | 5887.75 | Approved Pending Payment | 111867.3 | 2024-Q4
EXP-000028 | 2024-12-03 | BOQ-PKG-08-00028 | PKG-08 | INV-PKG-08-029-00028 | 413.18 | 97063 | 4853.15 | Paid | 92209.85 | 2024-Q4
EXP-000317 | 2024-12-03 | BOQ-PKG-07-00317 | PKG-07 | INV-PKG-07-003-00317 | 448.96 | 71880.4 | 3594.02 | Under Review | 68286.38 | 2024-Q4
EXP-001006 | 2024-12-03 | BOQ-PKG-06-01006 | PKG-06 | INV-PKG-06-027-01006 | 139.02 | 131880.91 | 6594.05 | Paid | 125286.86 | 2024-Q4
EXP-001118 | 2024-12-03 | BOQ-PKG-08-01118 | PKG-08 | INV-PKG-08-034-01118 | 281.27 | 190240.47 | 9512.02 | Approved Pending Payment | 180728.45 | 2024-Q4
EXP-001364 | 2024-12-03 | BOQ-PKG-04-01364 | PKG-04 | INV-PKG-04-035-01364 | 186.78 | 90883.56 | 4544.18 | Paid | 86339.38 | 2024-Q4
EXP-001951 | 2024-12-03 | BOQ-PKG-01-01951 | PKG-01 | INV-PKG-01-027-01951 | 146.57 | 207119.12 | 10355.96 | Approved Pending Payment | 196763.16 | 2024-Q4
EXP-002098 | 2024-12-03 | BOQ-PKG-08-00108 | PKG-08 | INV-PKG-08-034-02098 | 143.83 | 194377.77 | 9718.89 | Paid | 184658.88 | 2024-Q4
EXP-002294 | 2024-12-03 | BOQ-PKG-04-00304 | PKG-04 | INV-PKG-04-020-02294 | 213.18 | 81684.87 | 4084.24 | Paid | 77600.63 | 2024-Q4
EXP-003409 | 2024-12-03 | BOQ-PKG-09-01419 | PKG-09 | INV-PKG-09-015-03409 | 322.36 | 119168.32 | 5958.42 | Approved Pending Payment | 113209.9 | 2024-Q4
EXP-005304 | 2024-12-03 | BOQ-PKG-04-01324 | PKG-04 | INV-PKG-04-020-05304 | 338.26 | 105495.54 | 5274.78 | Paid | 100220.76 | 2024-Q4
EXP-006351 | 2024-12-03 | BOQ-PKG-01-00381 | PKG-01 | INV-PKG-01-017-06351 | 115.44 | 134333.7 | 6716.69 | Approved Pending Payment | 127617.01 | 2024-Q4
EXP-000155 | 2024-12-04 | BOQ-PKG-05-00155 | PKG-05 | INV-PKG-05-016-00155 | 202.66 | 150182.55 | 7509.13 | Under Review | 142673.42 | 2024-Q4
EXP-000193 | 2024-12-04 | BOQ-PKG-03-00193 | PKG-03 | INV-PKG-03-019-00193 | 197.99 | 180404.54 | 9020.23 | Approved Pending Payment | 171384.31 | 2024-Q4
EXP-000394 | 2024-12-04 | BOQ-PKG-04-00394 | PKG-04 | INV-PKG-04-010-00394 | 155.64 | 25618.29 | 1280.91 | Approved Pending Payment | 24337.38 | 2024-Q4
EXP-002325 | 2024-12-04 | BOQ-PKG-05-00335 | PKG-05 | INV-PKG-05-016-02325 | 435.14 | 138056.06 | 6902.8 | Paid | 131153.26 | 2024-Q4
EXP-002833 | 2024-12-04 | BOQ-PKG-03-00843 | PKG-03 | INV-PKG-03-034-02833 | 142.64 | 157189.9 | 7859.5 | Paid | 149330.4 | 2024-Q4
EXP-004141 | 2024-12-04 | BOQ-PKG-01-00161 | PKG-01 | INV-PKG-01-012-04141 | 449.76 | 178965.44 | 8948.27 | Paid | 170017.17 | 2024-Q4
EXP-005366 | 2024-12-04 | BOQ-PKG-06-01386 | PKG-06 | INV-PKG-06-012-05366 | 284.85 | 26626.86 | 1331.34 | Paid | 25295.52 | 2024-Q4
EXP-006056 | 2024-12-04 | BOQ-PKG-06-00086 | PKG-06 | INV-PKG-06-002-06056 | 181.82 | 92922.32 | 4646.12 | Paid | 88276.2 | 2024-Q4
EXP-006375 | 2024-12-04 | BOQ-PKG-05-00405 | PKG-05 | INV-PKG-05-006-06375 | 330.55 | 205273.18 | 10263.66 | Under Review | 195009.52 | 2024-Q4
EXP-000033 | 2024-12-05 | BOQ-PKG-03-00033 | PKG-03 | INV-PKG-03-034-00033 | 64.89 | 42646.08 | 2132.3 | Under Review | 40513.78 | 2024-Q4
EXP-000701 | 2024-12-05 | BOQ-PKG-01-00701 | PKG-01 | INV-PKG-01-002-00701 | 66.52 | 105960.65 | 5298.03 | Paid | 100662.62 | 2024-Q4
EXP-000859 | 2024-12-05 | BOQ-PKG-09-00859 | PKG-09 | INV-PKG-09-020-00859 | 53.04 | 37198.59 | 1859.93 | Paid | 35338.66 | 2024-Q4
EXP-000971 | 2024-12-05 | BOQ-PKG-01-00971 | PKG-01 | INV-PKG-01-027-00971 | 187.76 | 158591.36 | 7929.57 | Under Review | 150661.79 | 2024-Q4
EXP-002499 | 2024-12-05 | BOQ-PKG-09-00509 | PKG-09 | INV-PKG-09-015-02499 | 257.51 | 76407.36 | 3820.37 | Approved Pending Payment | 72586.99 | 2024-Q4
EXP-003283 | 2024-12-05 | BOQ-PKG-03-01293 | PKG-03 | INV-PKG-03-029-03283 | 15.15 | 76890.47 | 3844.52 | Paid | 73045.95 | 2024-Q4
EXP-003542 | 2024-12-05 | BOQ-PKG-02-01552 | PKG-02 | INV-PKG-02-008-03542 | 108.99 | 206095.19 | 10304.76 | Paid | 195790.43 | 2024-Q4
EXP-005461 | 2024-12-05 | BOQ-PKG-01-01481 | PKG-01 | INV-PKG-01-002-05461 | 341.44 | 67310.61 | 3365.53 | Paid | 63945.08 | 2024-Q4
EXP-005877 | 2024-12-05 | BOQ-PKG-07-01897 | PKG-07 | INV-PKG-07-033-05877 | 436.17 | 131978.56 | 6598.93 | Paid | 125379.63 | 2024-Q4
EXP-006032 | 2024-12-05 | BOQ-PKG-02-00062 | PKG-02 | INV-PKG-02-013-06032 | 203.79 | 62362.66 | 3118.13 | Paid | 59244.53 | 2024-Q4
EXP-006685 | 2024-12-05 | BOQ-PKG-05-00715 | PKG-05 | INV-PKG-05-001-06685 | 36.52 | 64486.07 | 3224.3 | Paid | 61261.77 | 2024-Q4
EXP-005140 | 2024-12-06 | BOQ-PKG-10-01160 | PKG-10 | INV-PKG-10-031-05140 | 93.48 | 121805.35 | 6090.27 | Paid | 115715.08 | 2024-Q4
EXP-005188 | 2024-12-06 | BOQ-PKG-08-01208 | PKG-08 | INV-PKG-08-009-05188 | 347.53 | 48405.29 | 2420.26 | Paid | 45985.03 | 2024-Q4
EXP-005783 | 2024-12-06 | BOQ-PKG-03-01803 | PKG-03 | INV-PKG-03-009-05783 | 146.75 | 201225.2 | 10061.26 | Paid | 191163.94 | 2024-Q4
EXP-005937 | 2024-12-06 | BOQ-PKG-07-01957 | PKG-07 | INV-PKG-07-023-05937 | 273.34 | 169219.74 | 8460.99 | Paid | 160758.75 | 2024-Q4
EXP-006070 | 2024-12-06 | BOQ-PKG-10-00100 | PKG-10 | INV-PKG-10-016-06070 | 379.83 | 176881.33 | 8844.07 | Paid | 168037.26 | 2024-Q4
EXP-000149 | 2024-12-07 | BOQ-PKG-09-00149 | PKG-09 | INV-PKG-09-010-00149 | 29.36 | 61676.75 | 3083.84 | Paid | 58592.91 | 2024-Q4
EXP-001155 | 2024-12-07 | BOQ-PKG-05-01155 | PKG-05 | INV-PKG-05-001-01155 | 52.38 | 118207.9 | 5910.4 | Paid | 112297.5 | 2024-Q4
EXP-001212 | 2024-12-07 | BOQ-PKG-02-01212 | PKG-02 | INV-PKG-02-023-01212 | 402.67 | 78752.3 | 3937.62 | Paid | 74814.68 | 2024-Q4
EXP-001720 | 2024-12-07 | BOQ-PKG-10-01720 | PKG-10 | INV-PKG-10-006-01720 | 20.53 | 123970.01 | 6198.5 | Paid | 117771.51 | 2024-Q4
EXP-001886 | 2024-12-07 | BOQ-PKG-06-01886 | PKG-06 | INV-PKG-06-032-01886 | 293.82 | 184099.01 | 9204.95 | Approved Pending Payment | 174894.06 | 2024-Q4
EXP-005425 | 2024-12-07 | BOQ-PKG-05-01445 | PKG-05 | INV-PKG-05-001-05425 | 362.05 | 116620.72 | 5831.04 | Paid | 110789.68 | 2024-Q4
EXP-005755 | 2024-12-07 | BOQ-PKG-05-01775 | PKG-05 | INV-PKG-05-016-05755 | 364.22 | 195720.8 | 9786.04 | Approved Pending Payment | 185934.76 | 2024-Q4
EXP-000539 | 2024-12-08 | BOQ-PKG-09-00539 | PKG-09 | INV-PKG-09-015-00539 | 364.43 | 67541.37 | 3377.07 | Paid | 64164.3 | 2024-Q4
EXP-002527 | 2024-12-08 | BOQ-PKG-07-00537 | PKG-07 | INV-PKG-07-008-02527 | 239.02 | 64894.79 | 3244.74 | Paid | 61650.05 | 2024-Q4
EXP-005511 | 2024-12-08 | BOQ-PKG-01-01531 | PKG-01 | INV-PKG-01-017-05511 | 245.29 | 62742.59 | 3137.13 | Under Review | 59605.46 | 2024-Q4
EXP-006312 | 2024-12-08 | BOQ-PKG-02-00342 | PKG-02 | INV-PKG-02-013-06312 | 303.85 | 80558.68 | 4027.93 | Paid | 76530.75 | 2024-Q4
EXP-001416 | 2024-12-09 | BOQ-PKG-06-01416 | PKG-06 | INV-PKG-06-017-01416 | 271.72 | 193726.44 | 9686.32 | Paid | 184040.12 | 2024-Q4
EXP-001738 | 2024-12-09 | BOQ-PKG-08-01738 | PKG-08 | INV-PKG-08-024-01738 | 376.99 | 163231.01 | 8161.55 | Paid | 155069.46 | 2024-Q4
EXP-001915 | 2024-12-09 | BOQ-PKG-05-01915 | PKG-05 | INV-PKG-05-026-01915 | 244.52 | 171519.17 | 8575.96 | Approved Pending Payment | 162943.21 | 2024-Q4
EXP-003666 | 2024-12-09 | BOQ-PKG-06-01676 | PKG-06 | INV-PKG-06-027-03666 | 379.41 | 31664.11 | 1583.21 | Paid | 30080.9 | 2024-Q4
EXP-004364 | 2024-12-09 | BOQ-PKG-04-00384 | PKG-04 | INV-PKG-04-025-04364 | 331.42 | 79870.11 | 3993.51 | Approved Pending Payment | 75876.6 | 2024-Q4
EXP-005170 | 2024-12-09 | BOQ-PKG-10-01190 | PKG-10 | INV-PKG-10-026-05170 | 239.41 | 76979.63 | 3848.98 | Paid | 73130.65 | 2024-Q4
EXP-005308 | 2024-12-09 | BOQ-PKG-08-01328 | PKG-08 | INV-PKG-08-024-05308 | 246.58 | 195056.86 | 9752.84 | Paid | 185304.02 | 2024-Q4
EXP-005453 | 2024-12-09 | BOQ-PKG-03-01473 | PKG-03 | INV-PKG-03-029-05453 | 284.96 | 26147.41 | 1307.37 | Paid | 24840.04 | 2024-Q4
EXP-006297 | 2024-12-09 | BOQ-PKG-07-00327 | PKG-07 | INV-PKG-07-033-06297 | 223 | 210200.29 | 10510.01 | Approved Pending Payment | 199690.28 | 2024-Q4
EXP-006973 | 2024-12-09 | BOQ-PKG-03-01003 | PKG-03 | INV-PKG-03-009-06973 | 189.36 | 126944.87 | 6347.24 | Paid | 120597.63 | 2024-Q4
EXP-001011 | 2024-12-10 | BOQ-PKG-01-01011 | PKG-01 | INV-PKG-01-032-01011 | 321.04 | 94280.65 | 4714.03 | Paid | 89566.62 | 2024-Q4
EXP-001632 | 2024-12-10 | BOQ-PKG-02-01632 | PKG-02 | INV-PKG-02-023-01632 | 344.47 | 133174.51 | 6658.73 | Approved Pending Payment | 126515.78 | 2024-Q4
EXP-002010 | 2024-12-10 | BOQ-PKG-10-00020 | PKG-10 | INV-PKG-10-016-02010 | 297.54 | 25942.57 | 1297.13 | Paid | 24645.44 | 2024-Q4
EXP-002110 | 2024-12-10 | BOQ-PKG-10-00120 | PKG-10 | INV-PKG-10-011-02110 | 182.94 | 93638.7 | 4681.94 | Paid | 88956.76 | 2024-Q4
EXP-002939 | 2024-12-10 | BOQ-PKG-09-00949 | PKG-09 | INV-PKG-09-035-02939 | 446.11 | 111984.37 | 5599.22 | Paid | 106385.15 | 2024-Q4
EXP-003990 | 2024-12-10 | BOQ-PKG-10-00010 | PKG-10 | INV-PKG-10-001-03990 | 117.89 | 67199.95 | 3360 | Approved Pending Payment | 63839.95 | 2024-Q4
EXP-004041 | 2024-12-10 | BOQ-PKG-01-00061 | PKG-01 | INV-PKG-01-017-04041 | 289.61 | 103674.17 | 5183.71 | Paid | 98490.46 | 2024-Q4
EXP-006352 | 2024-12-10 | BOQ-PKG-02-00382 | PKG-02 | INV-PKG-02-018-06352 | 366.47 | 107276.95 | 5363.85 | Approved Pending Payment | 101913.1 | 2024-Q4
EXP-006660 | 2024-12-10 | BOQ-PKG-10-00690 | PKG-10 | INV-PKG-10-011-06660 | 421.75 | 28943.26 | 1447.16 | Paid | 27496.1 | 2024-Q4
EXP-001629 | 2024-12-11 | BOQ-PKG-09-01629 | PKG-09 | INV-PKG-09-020-01629 | 206.96 | 140038.12 | 7001.91 | Paid | 133036.21 | 2024-Q4
EXP-001700 | 2024-12-11 | BOQ-PKG-10-01700 | PKG-10 | INV-PKG-10-021-01700 | 99.62 | 92155.63 | 4607.78 | Paid | 87547.85 | 2024-Q4
EXP-002033 | 2024-12-11 | BOQ-PKG-03-00043 | PKG-03 | INV-PKG-03-004-02033 | 318.81 | 123969.54 | 6198.48 | Paid | 117771.06 | 2024-Q4
EXP-002263 | 2024-12-11 | BOQ-PKG-03-00273 | PKG-03 | INV-PKG-03-024-02263 | 375.68 | 156506.19 | 7825.31 | Paid | 148680.88 | 2024-Q4
EXP-003272 | 2024-12-11 | BOQ-PKG-02-01282 | PKG-02 | INV-PKG-02-018-03272 | 342.37 | 30356.51 | 1517.83 | Disputed | 28838.68 | 2024-Q4
EXP-003634 | 2024-12-11 | BOQ-PKG-04-01644 | PKG-04 | INV-PKG-04-030-03634 | 134.47 | 139182.02 | 6959.1 | Paid | 132222.92 | 2024-Q4
EXP-005124 | 2024-12-11 | BOQ-PKG-04-01144 | PKG-04 | INV-PKG-04-015-05124 | 62.56 | 51925.68 | 2596.28 | Paid | 49329.4 | 2024-Q4
EXP-005229 | 2024-12-11 | BOQ-PKG-09-01249 | PKG-09 | INV-PKG-09-015-05229 | 151.7 | 158378.99 | 7918.95 | Under Review | 150460.04 | 2024-Q4
EXP-005852 | 2024-12-11 | BOQ-PKG-02-01872 | PKG-02 | INV-PKG-02-008-05852 | 160.3 | 48834.73 | 2441.74 | Paid | 46392.99 | 2024-Q4
EXP-006488 | 2024-12-11 | BOQ-PKG-08-00518 | PKG-08 | INV-PKG-08-014-06488 | 63.67 | 187301.12 | 9365.06 | Paid | 177936.06 | 2024-Q4
EXP-000459 | 2024-12-12 | BOQ-PKG-09-00459 | PKG-09 | INV-PKG-09-005-00459 | 418.13 | 36330.79 | 1816.54 | Paid | 34514.25 | 2024-Q4
EXP-001196 | 2024-12-12 | BOQ-PKG-06-01196 | PKG-06 | INV-PKG-06-007-01196 | 335.1 | 167383.83 | 8369.19 | Paid | 159014.64 | 2024-Q4
EXP-003830 | 2024-12-12 | BOQ-PKG-10-01840 | PKG-10 | INV-PKG-10-016-03830 | 45.83 | 84806.67 | 4240.33 | Under Review | 80566.34 | 2024-Q4
EXP-004031 | 2024-12-12 | BOQ-PKG-01-00051 | PKG-01 | INV-PKG-01-007-04031 | 434.67 | 42663.22 | 2133.16 | Paid | 40530.06 | 2024-Q4
EXP-004068 | 2024-12-12 | BOQ-PKG-08-00088 | PKG-08 | INV-PKG-08-009-04068 | 292.55 | 44144.6 | 2207.23 | Paid | 41937.37 | 2024-Q4
EXP-004347 | 2024-12-12 | BOQ-PKG-07-00367 | PKG-07 | INV-PKG-07-008-04347 | 45.64 | 52357.67 | 2617.88 | Paid | 49739.79 | 2024-Q4
EXP-004858 | 2024-12-12 | BOQ-PKG-08-00878 | PKG-08 | INV-PKG-08-029-04858 | 216.11 | 79524.68 | 3976.23 | Approved Pending Payment | 75548.45 | 2024-Q4
EXP-005027 | 2024-12-12 | BOQ-PKG-07-01047 | PKG-07 | INV-PKG-07-023-05027 | 282.66 | 58200.04 | 2910 | Paid | 55290.04 | 2024-Q4
EXP-006853 | 2024-12-12 | BOQ-PKG-03-00883 | PKG-03 | INV-PKG-03-029-06853 | 44.51 | 65907.2 | 3295.36 | Approved Pending Payment | 62611.84 | 2024-Q4
EXP-001365 | 2024-12-13 | BOQ-PKG-05-01365 | PKG-05 | INV-PKG-05-001-01365 | 377.57 | 37670.87 | 1883.54 | Disputed | 35787.33 | 2024-Q4
EXP-002748 | 2024-12-13 | BOQ-PKG-08-00758 | PKG-08 | INV-PKG-08-019-02748 | 157.59 | 83222.05 | 4161.1 | Paid | 79060.95 | 2024-Q4
EXP-003117 | 2024-12-13 | BOQ-PKG-07-01127 | PKG-07 | INV-PKG-07-003-03117 | 57.8 | 50093.44 | 2504.67 | Paid | 47588.77 | 2024-Q4
EXP-003715 | 2024-12-13 | BOQ-PKG-05-01725 | PKG-05 | INV-PKG-05-006-03715 | 197.06 | 162697.47 | 8134.87 | Approved Pending Payment | 154562.6 | 2024-Q4
EXP-005050 | 2024-12-13 | BOQ-PKG-10-01070 | PKG-10 | INV-PKG-10-011-05050 | 244.2 | 158821.76 | 7941.09 | Approved Pending Payment | 150880.67 | 2024-Q4
EXP-006110 | 2024-12-13 | BOQ-PKG-10-00140 | PKG-10 | INV-PKG-10-021-06110 | 287.06 | 138855.3 | 6942.76 | Paid | 131912.54 | 2024-Q4
EXP-006445 | 2024-12-13 | BOQ-PKG-05-00475 | PKG-05 | INV-PKG-05-006-06445 | 339.08 | 133107.04 | 6655.35 | Paid | 126451.69 | 2024-Q4
EXP-006917 | 2024-12-13 | BOQ-PKG-07-00947 | PKG-07 | INV-PKG-07-023-06917 | 156.9 | 212503.89 | 10625.19 | Paid | 201878.7 | 2024-Q4
EXP-000192 | 2024-12-14 | BOQ-PKG-02-00192 | PKG-02 | INV-PKG-02-018-00192 | 409.75 | 132841.73 | 6642.09 | Approved Pending Payment | 126199.64 | 2024-Q4
EXP-000425 | 2024-12-14 | BOQ-PKG-05-00425 | PKG-05 | INV-PKG-05-006-00425 | 326.59 | 86197 | 4309.85 | Paid | 81887.15 | 2024-Q4
EXP-001771 | 2024-12-14 | BOQ-PKG-01-01771 | PKG-01 | INV-PKG-01-022-01771 | 82.22 | 93033.27 | 4651.66 | Paid | 88381.61 | 2024-Q4
EXP-005114 | 2024-12-14 | BOQ-PKG-04-01134 | PKG-04 | INV-PKG-04-005-05114 | 100.51 | 122158.33 | 6107.92 | Approved Pending Payment | 116050.41 | 2024-Q4
EXP-005622 | 2024-12-14 | BOQ-PKG-02-01642 | PKG-02 | INV-PKG-02-023-05622 | 273.61 | 166047.47 | 8302.37 | Paid | 157745.1 | 2024-Q4
EXP-005785 | 2024-12-14 | BOQ-PKG-05-01805 | PKG-05 | INV-PKG-05-011-05785 | 271.74 | 110881.05 | 5544.05 | Paid | 105337 | 2024-Q4
EXP-006453 | 2024-12-14 | BOQ-PKG-03-00483 | PKG-03 | INV-PKG-03-014-06453 | 292.02 | 190160.34 | 9508.02 | Paid | 180652.32 | 2024-Q4
EXP-000074 | 2024-12-15 | BOQ-PKG-04-00074 | PKG-04 | INV-PKG-04-005-00074 | 360.9 | 130759.68 | 6537.98 | Paid | 124221.7 | 2024-Q4
EXP-000811 | 2024-12-15 | BOQ-PKG-01-00811 | PKG-01 | INV-PKG-01-007-00811 | 290.78 | 67663.78 | 3383.19 | Approved Pending Payment | 64280.59 | 2024-Q4
EXP-002092 | 2024-12-15 | BOQ-PKG-02-00102 | PKG-02 | INV-PKG-02-028-02092 | 325.18 | 107778.55 | 5388.93 | Paid | 102389.62 | 2024-Q4
EXP-002114 | 2024-12-15 | BOQ-PKG-04-00124 | PKG-04 | INV-PKG-04-015-02114 | 238.57 | 136607.47 | 6830.37 | Paid | 129777.1 | 2024-Q4
EXP-002158 | 2024-12-15 | BOQ-PKG-08-00168 | PKG-08 | INV-PKG-08-024-02158 | 209.13 | 202323.56 | 10116.18 | Paid | 192207.38 | 2024-Q4
EXP-004169 | 2024-12-15 | BOQ-PKG-09-00189 | PKG-09 | INV-PKG-09-005-04169 | 50.74 | 123398.03 | 6169.9 | Paid | 117228.13 | 2024-Q4
EXP-004174 | 2024-12-15 | BOQ-PKG-04-00194 | PKG-04 | INV-PKG-04-010-04174 | 386.75 | 27908.5 | 1395.43 | Paid | 26513.07 | 2024-Q4
EXP-004618 | 2024-12-15 | BOQ-PKG-08-00638 | PKG-08 | INV-PKG-08-034-04618 | 278.14 | 117537.13 | 5876.86 | Paid | 111660.27 | 2024-Q4
EXP-006556 | 2024-12-15 | BOQ-PKG-06-00586 | PKG-06 | INV-PKG-06-012-06556 | 68.56 | 165248.24 | 8262.41 | Paid | 156985.83 | 2024-Q4
EXP-000769 | 2024-12-16 | BOQ-PKG-09-00769 | PKG-09 | INV-PKG-09-035-00769 | 174.61 | 102632.97 | 5131.65 | Paid | 97501.32 | 2024-Q4
EXP-001201 | 2024-12-16 | BOQ-PKG-01-01201 | PKG-01 | INV-PKG-01-012-01201 | 273.48 | 84830.49 | 4241.52 | Under Review | 80588.97 | 2024-Q4
EXP-002619 | 2024-12-16 | BOQ-PKG-09-00629 | PKG-09 | INV-PKG-09-030-02619 | 251.69 | 136901.11 | 6845.06 | Paid | 130056.05 | 2024-Q4
EXP-002783 | 2024-12-16 | BOQ-PKG-03-00793 | PKG-03 | INV-PKG-03-019-02783 | 313.95 | 201653.74 | 10082.69 | Paid | 191571.05 | 2024-Q4
EXP-002990 | 2024-12-16 | BOQ-PKG-10-01000 | PKG-10 | INV-PKG-10-016-02990 | 334.07 | 111926.7 | 5596.34 | Paid | 106330.36 | 2024-Q4
EXP-003561 | 2024-12-16 | BOQ-PKG-01-01571 | PKG-01 | INV-PKG-01-027-03561 | 413.61 | 217332.73 | 10866.64 | Approved Pending Payment | 206466.09 | 2024-Q4
EXP-004404 | 2024-12-16 | BOQ-PKG-04-00424 | PKG-04 | INV-PKG-04-030-04404 | 428.65 | 157546.31 | 7877.32 | Approved Pending Payment | 149668.99 | 2024-Q4
EXP-005310 | 2024-12-16 | BOQ-PKG-10-01330 | PKG-10 | INV-PKG-10-026-05310 | 142.94 | 95018.49 | 4750.92 | Paid | 90267.57 | 2024-Q4
EXP-006342 | 2024-12-16 | BOQ-PKG-02-00372 | PKG-02 | INV-PKG-02-008-06342 | 212.4 | 36200.14 | 1810.01 | Paid | 34390.13 | 2024-Q4
EXP-006635 | 2024-12-16 | BOQ-PKG-05-00665 | PKG-05 | INV-PKG-05-021-06635 | 172.29 | 169282.42 | 8464.12 | Paid | 160818.3 | 2024-Q4
EXP-006849 | 2024-12-16 | BOQ-PKG-09-00879 | PKG-09 | INV-PKG-09-025-06849 | 269.44 | 146797.75 | 7339.89 | Approved Pending Payment | 139457.86 | 2024-Q4
EXP-000561 | 2024-12-17 | BOQ-PKG-01-00561 | PKG-01 | INV-PKG-01-002-00561 | 219.45 | 116179.3 | 5808.96 | Approved Pending Payment | 110370.34 | 2024-Q4
EXP-001538 | 2024-12-17 | BOQ-PKG-08-01538 | PKG-08 | INV-PKG-08-034-01538 | 260.55 | 182124.23 | 9106.21 | Paid | 173018.02 | 2024-Q4
EXP-002122 | 2024-12-17 | BOQ-PKG-02-00132 | PKG-02 | INV-PKG-02-023-02122 | 442.23 | 58100.65 | 2905.03 | Paid | 55195.62 | 2024-Q4
EXP-004456 | 2024-12-17 | BOQ-PKG-06-00476 | PKG-06 | INV-PKG-06-012-04456 | 439.61 | 66087.87 | 3304.39 | Paid | 62783.48 | 2024-Q4
EXP-000518 | 2024-12-18 | BOQ-PKG-08-00518 | PKG-08 | INV-PKG-08-029-00518 | 315.17 | 127375.21 | 6368.76 | Paid | 121006.45 | 2024-Q4
EXP-002985 | 2024-12-18 | BOQ-PKG-05-00995 | PKG-05 | INV-PKG-05-011-02985 | 223.51 | 195762.5 | 9788.12 | Paid | 185974.38 | 2024-Q4
EXP-003559 | 2024-12-18 | BOQ-PKG-09-01569 | PKG-09 | INV-PKG-09-025-03559 | 443.58 | 155460.83 | 7773.04 | Paid | 147687.79 | 2024-Q4
EXP-003729 | 2024-12-18 | BOQ-PKG-09-01739 | PKG-09 | INV-PKG-09-020-03729 | 423.55 | 66648.6 | 3332.43 | Paid | 63316.17 | 2024-Q4
EXP-004002 | 2024-12-18 | BOQ-PKG-02-00022 | PKG-02 | INV-PKG-02-013-04002 | 122.23 | 136775.63 | 6838.78 | Paid | 129936.85 | 2024-Q4
EXP-005020 | 2024-12-18 | BOQ-PKG-10-01040 | PKG-10 | INV-PKG-10-016-05020 | 57.4 | 108928.17 | 5446.41 | Disputed | 103481.76 | 2024-Q4
EXP-006023 | 2024-12-18 | BOQ-PKG-03-00053 | PKG-03 | INV-PKG-03-004-06023 | 123.58 | 205722.12 | 10286.11 | Approved Pending Payment | 195436.01 | 2024-Q4
EXP-001329 | 2024-12-19 | BOQ-PKG-09-01329 | PKG-09 | INV-PKG-09-035-01329 | 134.38 | 143099.5 | 7154.98 | Disputed | 135944.52 | 2024-Q4
EXP-003056 | 2024-12-19 | BOQ-PKG-06-01066 | PKG-06 | INV-PKG-06-012-03056 | 386.64 | 30174.95 | 1508.75 | Paid | 28666.2 | 2024-Q4
EXP-004576 | 2024-12-19 | BOQ-PKG-06-00596 | PKG-06 | INV-PKG-06-027-04576 | 353.24 | 142174.55 | 7108.73 | Paid | 135065.82 | 2024-Q4
EXP-004963 | 2024-12-19 | BOQ-PKG-03-00983 | PKG-03 | INV-PKG-03-029-04963 | 314.34 | 146987.88 | 7349.39 | Paid | 139638.49 | 2024-Q4
EXP-005039 | 2024-12-19 | BOQ-PKG-09-01059 | PKG-09 | INV-PKG-09-035-05039 | 211.63 | 130579.48 | 6528.97 | Paid | 124050.51 | 2024-Q4
EXP-001790 | 2024-12-20 | BOQ-PKG-10-01790 | PKG-10 | INV-PKG-10-006-01790 | 201.04 | 122176.05 | 6108.8 | Approved Pending Payment | 116067.25 | 2024-Q4
EXP-001991 | 2024-12-20 | BOQ-PKG-01-00001 | PKG-01 | INV-PKG-01-032-01991 | 402.93 | 38437.8 | 1921.89 | Paid | 36515.91 | 2024-Q4
EXP-003126 | 2024-12-20 | BOQ-PKG-06-01136 | PKG-06 | INV-PKG-06-012-03126 | 403.88 | 96662.22 | 4833.11 | Paid | 91829.11 | 2024-Q4
EXP-003816 | 2024-12-20 | BOQ-PKG-06-01826 | PKG-06 | INV-PKG-06-002-03816 | 407.97 | 126957.7 | 6347.88 | Paid | 120609.82 | 2024-Q4
EXP-006373 | 2024-12-20 | BOQ-PKG-03-00403 | PKG-03 | INV-PKG-03-004-06373 | 40.22 | 131773.15 | 6588.66 | Paid | 125184.49 | 2024-Q4
EXP-006630 | 2024-12-20 | BOQ-PKG-10-00660 | PKG-10 | INV-PKG-10-016-06630 | 381.87 | 164134.84 | 8206.74 | Disputed | 155928.1 | 2024-Q4
EXP-000596 | 2024-12-21 | BOQ-PKG-06-00596 | PKG-06 | INV-PKG-06-002-00596 | 245.64 | 152785.08 | 7639.25 | Under Review | 145145.83 | 2024-Q4
EXP-001404 | 2024-12-21 | BOQ-PKG-04-01404 | PKG-04 | INV-PKG-04-005-01404 | 417.38 | 151449.07 | 7572.45 | Paid | 143876.62 | 2024-Q4
EXP-001535 | 2024-12-21 | BOQ-PKG-05-01535 | PKG-05 | INV-PKG-05-031-01535 | 263.29 | 36786.41 | 1839.32 | Under Review | 34947.09 | 2024-Q4
EXP-002945 | 2024-12-21 | BOQ-PKG-05-00955 | PKG-05 | INV-PKG-05-006-02945 | 381.91 | 86505.47 | 4325.27 | Paid | 82180.2 | 2024-Q4
EXP-004286 | 2024-12-21 | BOQ-PKG-06-00306 | PKG-06 | INV-PKG-06-017-04286 | 102.76 | 193675.74 | 9683.79 | Paid | 183991.95 | 2024-Q4
EXP-005072 | 2024-12-21 | BOQ-PKG-02-01092 | PKG-02 | INV-PKG-02-033-05072 | 89.87 | 95484.17 | 4774.21 | Approved Pending Payment | 90709.96 | 2024-Q4
EXP-005593 | 2024-12-21 | BOQ-PKG-03-01613 | PKG-03 | INV-PKG-03-029-05593 | 449.31 | 76683.3 | 3834.17 | Paid | 72849.13 | 2024-Q4
EXP-005667 | 2024-12-21 | BOQ-PKG-07-01687 | PKG-07 | INV-PKG-07-033-05667 | 385.16 | 189944.33 | 9497.22 | Paid | 180447.11 | 2024-Q4
EXP-001684 | 2024-12-22 | BOQ-PKG-04-01684 | PKG-04 | INV-PKG-04-005-01684 | 272.06 | 53261.24 | 2663.06 | Paid | 50598.18 | 2024-Q4
EXP-005106 | 2024-12-22 | BOQ-PKG-06-01126 | PKG-06 | INV-PKG-06-032-05106 | 216.33 | 189401.64 | 9470.08 | Paid | 179931.56 | 2024-Q4
EXP-005938 | 2024-12-22 | BOQ-PKG-08-01958 | PKG-08 | INV-PKG-08-024-05938 | 196.36 | 85392.95 | 4269.65 | Under Review | 81123.3 | 2024-Q4
EXP-006935 | 2024-12-22 | BOQ-PKG-05-00965 | PKG-05 | INV-PKG-05-006-06935 | 433.14 | 109965.3 | 5498.26 | Approved Pending Payment | 104467.04 | 2024-Q4
EXP-000370 | 2024-12-23 | BOQ-PKG-10-00370 | PKG-10 | INV-PKG-10-021-00370 | 288.6 | 36734.67 | 1836.73 | Paid | 34897.94 | 2024-Q4
EXP-000467 | 2024-12-23 | BOQ-PKG-07-00467 | PKG-07 | INV-PKG-07-013-00467 | 238.29 | 146476.72 | 7323.84 | Paid | 139152.88 | 2024-Q4
EXP-002398 | 2024-12-23 | BOQ-PKG-08-00408 | PKG-08 | INV-PKG-08-019-02398 | 247.47 | 113901.96 | 5695.1 | Paid | 108206.86 | 2024-Q4
EXP-002477 | 2024-12-23 | BOQ-PKG-07-00487 | PKG-07 | INV-PKG-07-028-02477 | 120.92 | 182246.3 | 9112.32 | Paid | 173133.98 | 2024-Q4
EXP-003051 | 2024-12-23 | BOQ-PKG-01-01061 | PKG-01 | INV-PKG-01-007-03051 | 87.93 | 86351.39 | 4317.57 | Approved Pending Payment | 82033.82 | 2024-Q4
EXP-003488 | 2024-12-23 | BOQ-PKG-08-01498 | PKG-08 | INV-PKG-08-024-03488 | 13.65 | 203889.35 | 10194.47 | Paid | 193694.88 | 2024-Q4
EXP-006176 | 2024-12-23 | BOQ-PKG-06-00206 | PKG-06 | INV-PKG-06-017-06176 | 301.77 | 128714 | 6435.7 | Paid | 122278.3 | 2024-Q4
EXP-000139 | 2024-12-24 | BOQ-PKG-09-00139 | PKG-09 | INV-PKG-09-035-00139 | 396.28 | 154537.19 | 7726.86 | Paid | 146810.33 | 2024-Q4
EXP-002352 | 2024-12-24 | BOQ-PKG-02-00362 | PKG-02 | INV-PKG-02-008-02352 | 119.4 | 162102.85 | 8105.14 | Paid | 153997.71 | 2024-Q4
EXP-002417 | 2024-12-24 | BOQ-PKG-07-00427 | PKG-07 | INV-PKG-07-003-02417 | 61.86 | 45814.72 | 2290.74 | Paid | 43523.98 | 2024-Q4
EXP-005243 | 2024-12-24 | BOQ-PKG-03-01263 | PKG-03 | INV-PKG-03-029-05243 | 90.35 | 146209.33 | 7310.47 | Paid | 138898.86 | 2024-Q4
EXP-005271 | 2024-12-24 | BOQ-PKG-01-01291 | PKG-01 | INV-PKG-01-022-05271 | 150.32 | 70673.12 | 3533.66 | Paid | 67139.46 | 2024-Q4
EXP-005954 | 2024-12-24 | BOQ-PKG-04-01974 | PKG-04 | INV-PKG-04-005-05954 | 331.82 | 88080.19 | 4404.01 | Paid | 83676.18 | 2024-Q4
EXP-000793 | 2024-12-25 | BOQ-PKG-03-00793 | PKG-03 | INV-PKG-03-024-00793 | 290.25 | 187153.88 | 9357.69 | Paid | 177796.19 | 2024-Q4
EXP-000806 | 2024-12-25 | BOQ-PKG-06-00806 | PKG-06 | INV-PKG-06-002-00806 | 341.66 | 73082.04 | 3654.1 | Paid | 69427.94 | 2024-Q4
EXP-000838 | 2024-12-25 | BOQ-PKG-08-00838 | PKG-08 | INV-PKG-08-034-00838 | 28.26 | 151177.02 | 7558.85 | Paid | 143618.17 | 2024-Q4
EXP-001292 | 2024-12-25 | BOQ-PKG-02-01292 | PKG-02 | INV-PKG-02-033-01292 | 132.78 | 117025.75 | 5851.29 | Paid | 111174.46 | 2024-Q4
EXP-001351 | 2024-12-25 | BOQ-PKG-01-01351 | PKG-01 | INV-PKG-01-022-01351 | 384.3 | 166625.33 | 8331.27 | Paid | 158294.06 | 2024-Q4
EXP-002867 | 2024-12-25 | BOQ-PKG-07-00877 | PKG-07 | INV-PKG-07-033-02867 | 387.29 | 108826.71 | 5441.34 | Under Review | 103385.37 | 2024-Q4
EXP-003327 | 2024-12-25 | BOQ-PKG-07-01337 | PKG-07 | INV-PKG-07-003-03327 | 227.8 | 194927.36 | 9746.37 | Paid | 185180.99 | 2024-Q4
EXP-005070 | 2024-12-25 | BOQ-PKG-10-01090 | PKG-10 | INV-PKG-10-031-05070 | 115.85 | 134818.43 | 6740.92 | Paid | 128077.51 | 2024-Q4
EXP-005643 | 2024-12-25 | BOQ-PKG-03-01663 | PKG-03 | INV-PKG-03-009-05643 | 47.15 | 109442.13 | 5472.11 | Paid | 103970.02 | 2024-Q4
EXP-006153 | 2024-12-25 | BOQ-PKG-03-00183 | PKG-03 | INV-PKG-03-029-06153 | 415.83 | 86266.45 | 4313.32 | Paid | 81953.13 | 2024-Q4
EXP-006675 | 2024-12-25 | BOQ-PKG-05-00705 | PKG-05 | INV-PKG-05-026-06675 | 219.7 | 186129.9 | 9306.5 | Approved Pending Payment | 176823.4 | 2024-Q4
EXP-000619 | 2024-12-26 | BOQ-PKG-09-00619 | PKG-09 | INV-PKG-09-025-00619 | 197.43 | 135615.02 | 6780.75 | Paid | 128834.27 | 2024-Q4
EXP-000985 | 2024-12-26 | BOQ-PKG-05-00985 | PKG-05 | INV-PKG-05-006-00985 | 411.1 | 173065.47 | 8653.27 | Paid | 164412.2 | 2024-Q4
EXP-001161 | 2024-12-26 | BOQ-PKG-01-01161 | PKG-01 | INV-PKG-01-007-01161 | 179.79 | 159098.32 | 7954.92 | Paid | 151143.4 | 2024-Q4
EXP-001279 | 2024-12-26 | BOQ-PKG-09-01279 | PKG-09 | INV-PKG-09-020-01279 | 407.49 | 117571.32 | 5878.57 | Disputed | 111692.75 | 2024-Q4
EXP-001490 | 2024-12-26 | BOQ-PKG-10-01490 | PKG-10 | INV-PKG-10-021-01490 | 49.59 | 143954.87 | 7197.74 | Paid | 136757.13 | 2024-Q4
EXP-001639 | 2024-12-26 | BOQ-PKG-09-01639 | PKG-09 | INV-PKG-09-030-01639 | 396.34 | 32459.81 | 1622.99 | Paid | 30836.82 | 2024-Q4
EXP-003875 | 2024-12-26 | BOQ-PKG-05-01885 | PKG-05 | INV-PKG-05-026-03875 | 254.51 | 104042.61 | 5202.13 | Paid | 98840.48 | 2024-Q4
EXP-004113 | 2024-12-26 | BOQ-PKG-03-00133 | PKG-03 | INV-PKG-03-019-04113 | 368.76 | 42824.15 | 2141.21 | Paid | 40682.94 | 2024-Q4
EXP-005215 | 2024-12-26 | BOQ-PKG-05-01235 | PKG-05 | INV-PKG-05-001-05215 | 442.31 | 136326.09 | 6816.3 | Paid | 129509.79 | 2024-Q4
EXP-006047 | 2024-12-26 | BOQ-PKG-07-00077 | PKG-07 | INV-PKG-07-028-06047 | 25.11 | 198944.38 | 9947.22 | Approved Pending Payment | 188997.16 | 2024-Q4
EXP-006473 | 2024-12-26 | BOQ-PKG-03-00503 | PKG-03 | INV-PKG-03-034-06473 | 184 | 28437.43 | 1421.87 | Paid | 27015.56 | 2024-Q4
EXP-006919 | 2024-12-26 | BOQ-PKG-09-00949 | PKG-09 | INV-PKG-09-025-06919 | 29.67 | 77185.04 | 3859.25 | Under Review | 73325.79 | 2024-Q4
EXP-006999 | 2024-12-26 | BOQ-PKG-09-01029 | PKG-09 | INV-PKG-09-035-06999 | 145.16 | 179494.59 | 8974.73 | Approved Pending Payment | 170519.86 | 2024-Q4
EXP-004107 | 2024-12-27 | BOQ-PKG-07-00127 | PKG-07 | INV-PKG-07-013-04107 | 295.42 | 79348.77 | 3967.44 | Paid | 75381.33 | 2024-Q4
EXP-004807 | 2024-12-27 | BOQ-PKG-07-00827 | PKG-07 | INV-PKG-07-013-04807 | 302.93 | 159263.86 | 7963.19 | Under Review | 151300.67 | 2024-Q4
EXP-005819 | 2024-12-27 | BOQ-PKG-09-01839 | PKG-09 | INV-PKG-09-010-05819 | 81.76 | 112050.83 | 5602.54 | Paid | 106448.29 | 2024-Q4
EXP-000719 | 2024-12-28 | BOQ-PKG-09-00719 | PKG-09 | INV-PKG-09-020-00719 | 246.32 | 52585.12 | 2629.26 | Paid | 49955.86 | 2024-Q4
EXP-001052 | 2024-12-28 | BOQ-PKG-02-01052 | PKG-02 | INV-PKG-02-003-01052 | 13.4 | 42695.13 | 2134.76 | Paid | 40560.37 | 2024-Q4
EXP-003248 | 2024-12-28 | BOQ-PKG-08-01258 | PKG-08 | INV-PKG-08-029-03248 | 340.81 | 108351.79 | 5417.59 | Disputed | 102934.2 | 2024-Q4
EXP-003932 | 2024-12-28 | BOQ-PKG-02-01942 | PKG-02 | INV-PKG-02-013-03932 | 441.14 | 122666.32 | 6133.32 | Paid | 116533 | 2024-Q4
EXP-004916 | 2024-12-28 | BOQ-PKG-06-00936 | PKG-06 | INV-PKG-06-017-04916 | 253.33 | 117946.21 | 5897.31 | Paid | 112048.9 | 2024-Q4
EXP-005038 | 2024-12-28 | BOQ-PKG-08-01058 | PKG-08 | INV-PKG-08-034-05038 | 45.11 | 168358.56 | 8417.93 | Paid | 159940.63 | 2024-Q4
EXP-005175 | 2024-12-28 | BOQ-PKG-05-01195 | PKG-05 | INV-PKG-05-031-05175 | 180.03 | 44961.51 | 2248.08 | Paid | 42713.43 | 2024-Q4
EXP-005858 | 2024-12-28 | BOQ-PKG-08-01878 | PKG-08 | INV-PKG-08-014-05858 | 207.67 | 180128.97 | 9006.45 | Paid | 171122.52 | 2024-Q4
EXP-006066 | 2024-12-28 | BOQ-PKG-06-00096 | PKG-06 | INV-PKG-06-012-06066 | 87.53 | 145116.54 | 7255.83 | Paid | 137860.71 | 2024-Q4
EXP-006088 | 2024-12-28 | BOQ-PKG-08-00118 | PKG-08 | INV-PKG-08-034-06088 | 192.1 | 84568.86 | 4228.44 | Paid | 80340.42 | 2024-Q4
EXP-006172 | 2024-12-28 | BOQ-PKG-02-00202 | PKG-02 | INV-PKG-02-013-06172 | 203.43 | 201058.68 | 10052.93 | Under Review | 191005.75 | 2024-Q4
EXP-006777 | 2024-12-28 | BOQ-PKG-07-00807 | PKG-07 | INV-PKG-07-023-06777 | 42.18 | 144302.65 | 7215.13 | Paid | 137087.52 | 2024-Q4
EXP-000690 | 2024-12-29 | BOQ-PKG-10-00690 | PKG-10 | INV-PKG-10-026-00690 | 49.78 | 82798.08 | 4139.9 | Paid | 78658.18 | 2024-Q4
EXP-002843 | 2024-12-29 | BOQ-PKG-03-00853 | PKG-03 | INV-PKG-03-009-02843 | 303.42 | 64679.97 | 3234 | Paid | 61445.97 | 2024-Q4
EXP-002849 | 2024-12-29 | BOQ-PKG-09-00859 | PKG-09 | INV-PKG-09-015-02849 | 303.74 | 184180.67 | 9209.03 | Paid | 174971.64 | 2024-Q4
EXP-004913 | 2024-12-29 | BOQ-PKG-03-00933 | PKG-03 | INV-PKG-03-014-04913 | 125.8 | 197738.77 | 9886.94 | Paid | 187851.83 | 2024-Q4
EXP-004953 | 2024-12-29 | BOQ-PKG-03-00973 | PKG-03 | INV-PKG-03-019-04953 | 230.07 | 144152.08 | 7207.6 | Paid | 136944.48 | 2024-Q4
EXP-006672 | 2024-12-29 | BOQ-PKG-02-00702 | PKG-02 | INV-PKG-02-023-06672 | 56.97 | 65797.7 | 3289.88 | Paid | 62507.82 | 2024-Q4
EXP-000143 | 2024-12-30 | BOQ-PKG-03-00143 | PKG-03 | INV-PKG-03-004-00143 | 163.95 | 88325.61 | 4416.28 | Paid | 83909.33 | 2024-Q4
EXP-000645 | 2024-12-30 | BOQ-PKG-05-00645 | PKG-05 | INV-PKG-05-016-00645 | 65.31 | 117065.8 | 5853.29 | Under Review | 111212.51 | 2024-Q4
EXP-000709 | 2024-12-30 | BOQ-PKG-09-00709 | PKG-09 | INV-PKG-09-010-00709 | 230.09 | 130863.78 | 6543.19 | Paid | 124320.59 | 2024-Q4
EXP-001298 | 2024-12-30 | BOQ-PKG-08-01298 | PKG-08 | INV-PKG-08-004-01298 | 193.66 | 93387.09 | 4669.35 | Paid | 88717.74 | 2024-Q4
EXP-002506 | 2024-12-30 | BOQ-PKG-06-00516 | PKG-06 | INV-PKG-06-022-02506 | 268.49 | 87430.43 | 4371.52 | Paid | 83058.91 | 2024-Q4
EXP-004220 | 2024-12-30 | BOQ-PKG-10-00240 | PKG-10 | INV-PKG-10-021-04220 | 443.62 | 91598.9 | 4579.94 | Paid | 87018.96 | 2024-Q4
EXP-002728 | 2024-12-31 | BOQ-PKG-08-00738 | PKG-08 | INV-PKG-08-034-02728 | 193.34 | 133784.97 | 6689.25 | Paid | 127095.72 | 2024-Q4
EXP-001658 | 2025-01-01 | BOQ-PKG-08-01658 | PKG-08 | INV-PKG-08-014-01658 | 22.53 | 92555.34 | 4627.77 | Paid | 87927.57 | 2025-Q1
EXP-002096 | 2025-01-01 | BOQ-PKG-06-00106 | PKG-06 | INV-PKG-06-032-02096 | 91.79 | 46135.41 | 2306.77 | Approved Pending Payment | 43828.64 | 2025-Q1
EXP-002359 | 2025-01-01 | BOQ-PKG-09-00369 | PKG-09 | INV-PKG-09-015-02359 | 48.03 | 68283.42 | 3414.17 | Disputed | 64869.25 | 2025-Q1
EXP-003040 | 2025-01-01 | BOQ-PKG-10-01050 | PKG-10 | INV-PKG-10-031-03040 | 237.4 | 34465.49 | 1723.27 | Paid | 32742.22 | 2025-Q1
EXP-003158 | 2025-01-01 | BOQ-PKG-08-01168 | PKG-08 | INV-PKG-08-009-03158 | 180.58 | 43543.93 | 2177.2 | Paid | 41366.73 | 2025-Q1
EXP-003642 | 2025-01-01 | BOQ-PKG-02-01652 | PKG-02 | INV-PKG-02-003-03642 | 186.27 | 108280.8 | 5414.04 | Paid | 102866.76 | 2025-Q1
EXP-003979 | 2025-01-01 | BOQ-PKG-09-01989 | PKG-09 | INV-PKG-09-025-03979 | 384.08 | 171145.38 | 8557.27 | Approved Pending Payment | 162588.11 | 2025-Q1
EXP-004099 | 2025-01-01 | BOQ-PKG-09-00119 | PKG-09 | INV-PKG-09-005-04099 | 394.72 | 176724.86 | 8836.24 | Under Review | 167888.62 | 2025-Q1
EXP-004180 | 2025-01-01 | BOQ-PKG-10-00200 | PKG-10 | INV-PKG-10-016-04180 | 441.67 | 43806.28 | 2190.31 | Paid | 41615.97 | 2025-Q1
EXP-000284 | 2025-01-02 | BOQ-PKG-04-00284 | PKG-04 | INV-PKG-04-005-00284 | 46.14 | 108528.71 | 5426.44 | Under Review | 103102.27 | 2025-Q1
EXP-002501 | 2025-01-02 | BOQ-PKG-01-00511 | PKG-01 | INV-PKG-01-017-02501 | 356.51 | 31111.77 | 1555.59 | Paid | 29556.18 | 2025-Q1
EXP-003400 | 2025-01-02 | BOQ-PKG-10-01410 | PKG-10 | INV-PKG-10-006-03400 | 50.45 | 188756.26 | 9437.81 | Paid | 179318.45 | 2025-Q1
EXP-003627 | 2025-01-02 | BOQ-PKG-07-01637 | PKG-07 | INV-PKG-07-023-03627 | 418.96 | 109061.79 | 5453.09 | Under Review | 103608.7 | 2025-Q1
EXP-003943 | 2025-01-02 | BOQ-PKG-03-01953 | PKG-03 | INV-PKG-03-024-03943 | 93.72 | 130331.91 | 6516.6 | Paid | 123815.31 | 2025-Q1
EXP-004516 | 2025-01-02 | BOQ-PKG-06-00536 | PKG-06 | INV-PKG-06-002-04516 | 391.31 | 155002.07 | 7750.1 | Paid | 147251.97 | 2025-Q1
EXP-000678 | 2025-01-03 | BOQ-PKG-08-00678 | PKG-08 | INV-PKG-08-014-00678 | 224.5 | 128851.85 | 6442.59 | Under Review | 122409.26 | 2025-Q1
EXP-001205 | 2025-01-03 | BOQ-PKG-05-01205 | PKG-05 | INV-PKG-05-016-01205 | 153.15 | 57305.11 | 2865.26 | Paid | 54439.85 | 2025-Q1
EXP-002834 | 2025-01-03 | BOQ-PKG-04-00844 | PKG-04 | INV-PKG-04-035-02834 | 326.05 | 85847.17 | 4292.36 | Paid | 81554.81 | 2025-Q1
EXP-004733 | 2025-01-03 | BOQ-PKG-03-00753 | PKG-03 | INV-PKG-03-009-04733 | 171.81 | 162606.87 | 8130.34 | Paid | 154476.53 | 2025-Q1
EXP-005055 | 2025-01-03 | BOQ-PKG-05-01075 | PKG-05 | INV-PKG-05-016-05055 | 408.89 | 29350.35 | 1467.52 | Under Review | 27882.83 | 2025-Q1
EXP-005266 | 2025-01-03 | BOQ-PKG-06-01286 | PKG-06 | INV-PKG-06-017-05266 | 164.38 | 208513.81 | 10425.69 | Paid | 198088.12 | 2025-Q1
EXP-006268 | 2025-01-03 | BOQ-PKG-08-00298 | PKG-08 | INV-PKG-08-004-06268 | 331.17 | 25944.56 | 1297.23 | Paid | 24647.33 | 2025-Q1
EXP-001381 | 2025-01-04 | BOQ-PKG-01-01381 | PKG-01 | INV-PKG-01-017-01381 | 40.95 | 97005.04 | 4850.25 | Paid | 92154.79 | 2025-Q1
EXP-003848 | 2025-01-04 | BOQ-PKG-08-01858 | PKG-08 | INV-PKG-08-034-03848 | 290.05 | 110435.37 | 5521.77 | Paid | 104913.6 | 2025-Q1
EXP-005021 | 2025-01-04 | BOQ-PKG-01-01041 | PKG-01 | INV-PKG-01-017-05021 | 246.51 | 180497.6 | 9024.88 | Paid | 171472.72 | 2025-Q1
EXP-005263 | 2025-01-04 | BOQ-PKG-03-01283 | PKG-03 | INV-PKG-03-014-05263 | 182.27 | 56942.68 | 2847.13 | Under Review | 54095.55 | 2025-Q1
EXP-005530 | 2025-01-04 | BOQ-PKG-10-01550 | PKG-10 | INV-PKG-10-001-05530 | 79.11 | 76155 | 3807.75 | Paid | 72347.25 | 2025-Q1
EXP-005958 | 2025-01-04 | BOQ-PKG-08-01978 | PKG-08 | INV-PKG-08-009-05958 | 159.08 | 70489.86 | 3524.49 | Paid | 66965.37 | 2025-Q1
EXP-006397 | 2025-01-04 | BOQ-PKG-07-00427 | PKG-07 | INV-PKG-07-028-06397 | 70.04 | 51909.72 | 2595.49 | Paid | 49314.23 | 2025-Q1
EXP-000360 | 2025-01-05 | BOQ-PKG-10-00360 | PKG-10 | INV-PKG-10-011-00360 | 283.91 | 52511.34 | 2625.57 | Paid | 49885.77 | 2025-Q1
EXP-001124 | 2025-01-05 | BOQ-PKG-04-01124 | PKG-04 | INV-PKG-04-005-01124 | 226.5 | 86222.4 | 4311.12 | Paid | 81911.28 | 2025-Q1
EXP-002908 | 2025-01-05 | BOQ-PKG-08-00918 | PKG-08 | INV-PKG-08-004-02908 | 324.2 | 95695.51 | 4784.78 | Paid | 90910.73 | 2025-Q1
EXP-003626 | 2025-01-05 | BOQ-PKG-06-01636 | PKG-06 | INV-PKG-06-022-03626 | 33.05 | 122898.01 | 6144.9 | Paid | 116753.11 | 2025-Q1
EXP-005419 | 2025-01-05 | BOQ-PKG-09-01439 | PKG-09 | INV-PKG-09-030-05419 | 183.5 | 53903.68 | 2695.18 | Paid | 51208.5 | 2025-Q1
EXP-000431 | 2025-01-06 | BOQ-PKG-01-00431 | PKG-01 | INV-PKG-01-012-00431 | 341.56 | 120572.15 | 6028.61 | Paid | 114543.54 | 2025-Q1
EXP-000606 | 2025-01-06 | BOQ-PKG-06-00606 | PKG-06 | INV-PKG-06-012-00606 | 242.43 | 23496.42 | 1174.82 | Paid | 22321.6 | 2025-Q1
EXP-001637 | 2025-01-06 | BOQ-PKG-07-01637 | PKG-07 | INV-PKG-07-028-01637 | 284.54 | 123458.03 | 6172.9 | Paid | 117285.13 | 2025-Q1
EXP-001904 | 2025-01-06 | BOQ-PKG-04-01904 | PKG-04 | INV-PKG-04-015-01904 | 417.84 | 41153.09 | 2057.65 | Paid | 39095.44 | 2025-Q1
EXP-005391 | 2025-01-06 | BOQ-PKG-01-01411 | PKG-01 | INV-PKG-01-002-05391 | 208.44 | 197386.85 | 9869.34 | Paid | 187517.51 | 2025-Q1
EXP-006254 | 2025-01-06 | BOQ-PKG-04-00284 | PKG-04 | INV-PKG-04-025-06254 | 74.37 | 180017.07 | 9000.85 | Paid | 171016.22 | 2025-Q1
EXP-000055 | 2025-01-07 | BOQ-PKG-05-00055 | PKG-05 | INV-PKG-05-021-00055 | 32.61 | 87330.59 | 4366.53 | Paid | 82964.06 | 2025-Q1
EXP-000162 | 2025-01-07 | BOQ-PKG-02-00162 | PKG-02 | INV-PKG-02-023-00162 | 394.78 | 192861.68 | 9643.08 | Paid | 183218.6 | 2025-Q1
EXP-000232 | 2025-01-07 | BOQ-PKG-02-00232 | PKG-02 | INV-PKG-02-023-00232 | 273.43 | 39378.12 | 1968.91 | Under Review | 37409.21 | 2025-Q1
EXP-000246 | 2025-01-07 | BOQ-PKG-06-00246 | PKG-06 | INV-PKG-06-002-00246 | 361.82 | 108111.13 | 5405.56 | Paid | 102705.57 | 2025-Q1
EXP-001986 | 2025-01-07 | BOQ-PKG-06-01986 | PKG-06 | INV-PKG-06-027-01986 | 415.22 | 31562.82 | 1578.14 | Paid | 29984.68 | 2025-Q1
EXP-003357 | 2025-01-07 | BOQ-PKG-07-01367 | PKG-07 | INV-PKG-07-033-03357 | 43.71 | 113830.91 | 5691.55 | Paid | 108139.36 | 2025-Q1
EXP-003673 | 2025-01-07 | BOQ-PKG-03-01683 | PKG-03 | INV-PKG-03-034-03673 | 180.56 | 111151.54 | 5557.58 | Paid | 105593.96 | 2025-Q1
EXP-004556 | 2025-01-07 | BOQ-PKG-06-00576 | PKG-06 | INV-PKG-06-007-04556 | 285.96 | 172863.1 | 8643.16 | Paid | 164219.94 | 2025-Q1
EXP-004707 | 2025-01-07 | BOQ-PKG-07-00727 | PKG-07 | INV-PKG-07-018-04707 | 161.93 | 90087.42 | 4504.37 | Paid | 85583.05 | 2025-Q1
EXP-004895 | 2025-01-07 | BOQ-PKG-05-00915 | PKG-05 | INV-PKG-05-031-04895 | 75.7 | 130272.44 | 6513.62 | Paid | 123758.82 | 2025-Q1
EXP-005837 | 2025-01-07 | BOQ-PKG-07-01857 | PKG-07 | INV-PKG-07-028-05837 | 223.25 | 126257.18 | 6312.86 | Paid | 119944.32 | 2025-Q1
EXP-005885 | 2025-01-07 | BOQ-PKG-05-01905 | PKG-05 | INV-PKG-05-006-05885 | 151.61 | 88140.78 | 4407.04 | Paid | 83733.74 | 2025-Q1
EXP-006216 | 2025-01-07 | BOQ-PKG-06-00246 | PKG-06 | INV-PKG-06-022-06216 | 98.48 | 39966.79 | 1998.34 | Paid | 37968.45 | 2025-Q1
EXP-006663 | 2025-01-07 | BOQ-PKG-03-00693 | PKG-03 | INV-PKG-03-014-06663 | 10.83 | 57657.16 | 2882.86 | Under Review | 54774.3 | 2025-Q1
EXP-006975 | 2025-01-07 | BOQ-PKG-05-01005 | PKG-05 | INV-PKG-05-011-06975 | 124.8 | 145526.08 | 7276.3 | Paid | 138249.78 | 2025-Q1
EXP-001893 | 2025-01-08 | BOQ-PKG-03-01893 | PKG-03 | INV-PKG-03-004-01893 | 337.75 | 198268.21 | 9913.41 | Paid | 188354.8 | 2025-Q1
EXP-002244 | 2025-01-08 | BOQ-PKG-04-00254 | PKG-04 | INV-PKG-04-005-02244 | 369.06 | 189845.68 | 9492.28 | Paid | 180353.4 | 2025-Q1
EXP-003344 | 2025-01-08 | BOQ-PKG-04-01354 | PKG-04 | INV-PKG-04-020-03344 | 129.98 | 153353.18 | 7667.66 | Paid | 145685.52 | 2025-Q1
EXP-003969 | 2025-01-08 | BOQ-PKG-09-01979 | PKG-09 | INV-PKG-09-015-03969 | 337.35 | 192890.65 | 9644.53 | Paid | 183246.12 | 2025-Q1
EXP-004009 | 2025-01-08 | BOQ-PKG-09-00029 | PKG-09 | INV-PKG-09-020-04009 | 179.66 | 188879.33 | 9443.97 | Paid | 179435.36 | 2025-Q1
EXP-005065 | 2025-01-08 | BOQ-PKG-05-01085 | PKG-05 | INV-PKG-05-026-05065 | 121.31 | 91318.94 | 4565.95 | Paid | 86752.99 | 2025-Q1
EXP-005314 | 2025-01-08 | BOQ-PKG-04-01334 | PKG-04 | INV-PKG-04-030-05314 | 117.47 | 187953.42 | 9397.67 | Under Review | 178555.75 | 2025-Q1
EXP-005405 | 2025-01-08 | BOQ-PKG-05-01425 | PKG-05 | INV-PKG-05-016-05405 | 23.67 | 167306.55 | 8365.33 | Approved Pending Payment | 158941.22 | 2025-Q1
EXP-000212 | 2025-01-09 | BOQ-PKG-02-00212 | PKG-02 | INV-PKG-02-003-00212 | 279.65 | 208670.24 | 10433.51 | Under Review | 198236.73 | 2025-Q1
EXP-002002 | 2025-01-09 | BOQ-PKG-02-00012 | PKG-02 | INV-PKG-02-008-02002 | 9.27 | 74640.93 | 3732.05 | Paid | 70908.88 | 2025-Q1
EXP-002523 | 2025-01-09 | BOQ-PKG-03-00533 | PKG-03 | INV-PKG-03-004-02523 | 363.35 | 145162.09 | 7258.1 | Paid | 137903.99 | 2025-Q1
EXP-002661 | 2025-01-09 | BOQ-PKG-01-00671 | PKG-01 | INV-PKG-01-002-02661 | 165.38 | 99313.8 | 4965.69 | Paid | 94348.11 | 2025-Q1
EXP-003078 | 2025-01-09 | BOQ-PKG-08-01088 | PKG-08 | INV-PKG-08-034-03078 | 431.36 | 36619.33 | 1830.97 | Paid | 34788.36 | 2025-Q1
EXP-004420 | 2025-01-09 | BOQ-PKG-10-00440 | PKG-10 | INV-PKG-10-011-04420 | 334.1 | 30066.06 | 1503.3 | Under Review | 28562.76 | 2025-Q1
EXP-005443 | 2025-01-09 | BOQ-PKG-03-01463 | PKG-03 | INV-PKG-03-019-05443 | 9.22 | 139911.49 | 6995.57 | Paid | 132915.92 | 2025-Q1
EXP-006012 | 2025-01-09 | BOQ-PKG-02-00042 | PKG-02 | INV-PKG-02-028-06012 | 46.04 | 128520.85 | 6426.04 | Paid | 122094.81 | 2025-Q1
EXP-006954 | 2025-01-09 | BOQ-PKG-04-00984 | PKG-04 | INV-PKG-04-025-06954 | 241.25 | 206716.07 | 10335.8 | Paid | 196380.27 | 2025-Q1
EXP-001278 | 2025-01-10 | BOQ-PKG-08-01278 | PKG-08 | INV-PKG-08-019-01278 | 369.25 | 93055.86 | 4652.79 | Paid | 88403.07 | 2025-Q1
EXP-003376 | 2025-01-10 | BOQ-PKG-06-01386 | PKG-06 | INV-PKG-06-017-03376 | 234.36 | 114289.9 | 5714.5 | Paid | 108575.4 | 2025-Q1
EXP-004196 | 2025-01-10 | BOQ-PKG-06-00216 | PKG-06 | INV-PKG-06-032-04196 | 302.05 | 207663.12 | 10383.16 | Approved Pending Payment | 197279.96 | 2025-Q1
EXP-004247 | 2025-01-10 | BOQ-PKG-07-00267 | PKG-07 | INV-PKG-07-013-04247 | 8.24 | 71782.16 | 3589.11 | Paid | 68193.05 | 2025-Q1
EXP-005553 | 2025-01-10 | BOQ-PKG-03-01573 | PKG-03 | INV-PKG-03-024-05553 | 89.7 | 117972.81 | 5898.64 | Paid | 112074.17 | 2025-Q1
EXP-001010 | 2025-01-11 | BOQ-PKG-10-01010 | PKG-10 | INV-PKG-10-031-01010 | 256.11 | 47086.56 | 2354.33 | Paid | 44732.23 | 2025-Q1
EXP-001532 | 2025-01-11 | BOQ-PKG-02-01532 | PKG-02 | INV-PKG-02-028-01532 | 278.1 | 140175.04 | 7008.75 | Paid | 133166.29 | 2025-Q1
EXP-002459 | 2025-01-11 | BOQ-PKG-09-00469 | PKG-09 | INV-PKG-09-010-02459 | 331.92 | 199156.01 | 9957.8 | Approved Pending Payment | 189198.21 | 2025-Q1
EXP-002648 | 2025-01-11 | BOQ-PKG-08-00658 | PKG-08 | INV-PKG-08-024-02648 | 63.96 | 186544.3 | 9327.22 | Paid | 177217.08 | 2025-Q1
EXP-004284 | 2025-01-11 | BOQ-PKG-04-00304 | PKG-04 | INV-PKG-04-015-04284 | 295.8 | 105819.73 | 5290.99 | Under Review | 100528.74 | 2025-Q1
EXP-005765 | 2025-01-11 | BOQ-PKG-05-01785 | PKG-05 | INV-PKG-05-026-05765 | 212.49 | 78860.24 | 3943.01 | Paid | 74917.23 | 2025-Q1
EXP-006250 | 2025-01-11 | BOQ-PKG-10-00280 | PKG-10 | INV-PKG-10-021-06250 | 418.62 | 153169.64 | 7658.48 | Approved Pending Payment | 145511.16 | 2025-Q1
EXP-006652 | 2025-01-11 | BOQ-PKG-02-00682 | PKG-02 | INV-PKG-02-003-06652 | 79.19 | 175990.87 | 8799.54 | Paid | 167191.33 | 2025-Q1
EXP-000179 | 2025-01-12 | BOQ-PKG-09-00179 | PKG-09 | INV-PKG-09-005-00179 | 63.86 | 59414.28 | 2970.71 | Paid | 56443.57 | 2025-Q1
EXP-000356 | 2025-01-12 | BOQ-PKG-06-00356 | PKG-06 | INV-PKG-06-007-00356 | 285.63 | 103742.32 | 5187.12 | Paid | 98555.2 | 2025-Q1
EXP-000614 | 2025-01-12 | BOQ-PKG-04-00614 | PKG-04 | INV-PKG-04-020-00614 | 329.64 | 27094.96 | 1354.75 | Paid | 25740.21 | 2025-Q1
EXP-001224 | 2025-01-12 | BOQ-PKG-04-01224 | PKG-04 | INV-PKG-04-035-01224 | 267.16 | 155309.5 | 7765.48 | Paid | 147544.02 | 2025-Q1
EXP-003746 | 2025-01-12 | BOQ-PKG-06-01756 | PKG-06 | INV-PKG-06-002-03746 | 252.98 | 90177.59 | 4508.88 | Paid | 85668.71 | 2025-Q1
EXP-004421 | 2025-01-12 | BOQ-PKG-01-00441 | PKG-01 | INV-PKG-01-012-04421 | 14.48 | 30043.67 | 1502.18 | Approved Pending Payment | 28541.49 | 2025-Q1
EXP-004969 | 2025-01-12 | BOQ-PKG-09-00989 | PKG-09 | INV-PKG-09-035-04969 | 411.57 | 68068.9 | 3403.44 | Paid | 64665.46 | 2025-Q1
EXP-005093 | 2025-01-12 | BOQ-PKG-03-01113 | PKG-03 | INV-PKG-03-019-05093 | 200.88 | 104184.43 | 5209.22 | Approved Pending Payment | 98975.21 | 2025-Q1
EXP-006420 | 2025-01-12 | BOQ-PKG-10-00450 | PKG-10 | INV-PKG-10-016-06420 | 114.23 | 85713.72 | 4285.69 | Paid | 81428.03 | 2025-Q1
EXP-000698 | 2025-01-13 | BOQ-PKG-08-00698 | PKG-08 | INV-PKG-08-034-00698 | 377.3 | 146748.51 | 7337.43 | Paid | 139411.08 | 2025-Q1
EXP-001259 | 2025-01-13 | BOQ-PKG-09-01259 | PKG-09 | INV-PKG-09-035-01259 | 197.39 | 200115.14 | 10005.76 | Under Review | 190109.38 | 2025-Q1
EXP-003095 | 2025-01-13 | BOQ-PKG-05-01105 | PKG-05 | INV-PKG-05-016-03095 | 282.35 | 105203.35 | 5260.17 | Paid | 99943.18 | 2025-Q1
EXP-004608 | 2025-01-13 | BOQ-PKG-08-00628 | PKG-08 | INV-PKG-08-024-04608 | 317.87 | 197832.27 | 9891.61 | Under Review | 187940.66 | 2025-Q1
EXP-004677 | 2025-01-13 | BOQ-PKG-07-00697 | PKG-07 | INV-PKG-07-023-04677 | 70.02 | 31367.11 | 1568.36 | Under Review | 29798.75 | 2025-Q1
EXP-004894 | 2025-01-13 | BOQ-PKG-04-00914 | PKG-04 | INV-PKG-04-030-04894 | 375.59 | 195863.88 | 9793.19 | Approved Pending Payment | 186070.69 | 2025-Q1
EXP-005130 | 2025-01-13 | BOQ-PKG-10-01150 | PKG-10 | INV-PKG-10-021-05130 | 192.35 | 170354.26 | 8517.71 | Under Review | 161836.55 | 2025-Q1
EXP-005548 | 2025-01-13 | BOQ-PKG-08-01568 | PKG-08 | INV-PKG-08-019-05548 | 191.97 | 78261.26 | 3913.06 | Paid | 74348.2 | 2025-Q1
EXP-000279 | 2025-01-14 | BOQ-PKG-09-00279 | PKG-09 | INV-PKG-09-035-00279 | 159.4 | 106869.11 | 5343.46 | Paid | 101525.65 | 2025-Q1
EXP-001525 | 2025-01-14 | BOQ-PKG-05-01525 | PKG-05 | INV-PKG-05-021-01525 | 377.23 | 206125.29 | 10306.26 | Paid | 195819.03 | 2025-Q1
EXP-002560 | 2025-01-14 | BOQ-PKG-10-00570 | PKG-10 | INV-PKG-10-006-02560 | 293.41 | 192263.32 | 9613.17 | Paid | 182650.15 | 2025-Q1
EXP-002669 | 2025-01-14 | BOQ-PKG-09-00679 | PKG-09 | INV-PKG-09-010-02669 | 6.58 | 133371.59 | 6668.58 | Paid | 126703.01 | 2025-Q1
EXP-003299 | 2025-01-14 | BOQ-PKG-09-01309 | PKG-09 | INV-PKG-09-010-03299 | 56.56 | 59168.66 | 2958.43 | Paid | 56210.23 | 2025-Q1
EXP-004760 | 2025-01-14 | BOQ-PKG-10-00780 | PKG-10 | INV-PKG-10-001-04760 | 76.76 | 178228.35 | 8911.42 | Paid | 169316.93 | 2025-Q1
EXP-005119 | 2025-01-14 | BOQ-PKG-09-01139 | PKG-09 | INV-PKG-09-010-05119 | 446.47 | 131407.87 | 6570.39 | Paid | 124837.48 | 2025-Q1
EXP-005448 | 2025-01-14 | BOQ-PKG-08-01468 | PKG-08 | INV-PKG-08-024-05448 | 187.37 | 82051.33 | 4102.57 | Paid | 77948.76 | 2025-Q1
EXP-006179 | 2025-01-14 | BOQ-PKG-09-00209 | PKG-09 | INV-PKG-09-020-06179 | 81.17 | 195216.51 | 9760.83 | Under Review | 185455.68 | 2025-Q1
EXP-006447 | 2025-01-14 | BOQ-PKG-07-00477 | PKG-07 | INV-PKG-07-008-06447 | 163.28 | 55351.74 | 2767.59 | Paid | 52584.15 | 2025-Q1
EXP-000255 | 2025-01-15 | BOQ-PKG-05-00255 | PKG-05 | INV-PKG-05-011-00255 | 435.18 | 149076.22 | 7453.81 | Under Review | 141622.41 | 2025-Q1
EXP-000288 | 2025-01-15 | BOQ-PKG-08-00288 | PKG-08 | INV-PKG-08-009-00288 | 162.3 | 82811.88 | 4140.59 | Paid | 78671.29 | 2025-Q1
EXP-002946 | 2025-01-15 | BOQ-PKG-06-00956 | PKG-06 | INV-PKG-06-007-02946 | 157.74 | 182875.83 | 9143.79 | Paid | 173732.04 | 2025-Q1
EXP-003210 | 2025-01-15 | BOQ-PKG-10-01220 | PKG-10 | INV-PKG-10-026-03210 | 71.34 | 27452.94 | 1372.65 | Paid | 26080.29 | 2025-Q1
EXP-004014 | 2025-01-15 | BOQ-PKG-04-00034 | PKG-04 | INV-PKG-04-025-04014 | 91.76 | 119003.25 | 5950.16 | Paid | 113053.09 | 2025-Q1
EXP-004620 | 2025-01-15 | BOQ-PKG-10-00640 | PKG-10 | INV-PKG-10-001-04620 | 283.05 | 29184.26 | 1459.21 | Paid | 27725.05 | 2025-Q1
EXP-005417 | 2025-01-15 | BOQ-PKG-07-01437 | PKG-07 | INV-PKG-07-028-05417 | 432.9 | 105438.4 | 5271.92 | Under Review | 100166.48 | 2025-Q1
EXP-005640 | 2025-01-15 | BOQ-PKG-10-01660 | PKG-10 | INV-PKG-10-006-05640 | 392.81 | 118427.41 | 5921.37 | Approved Pending Payment | 112506.04 | 2025-Q1
EXP-005974 | 2025-01-15 | BOQ-PKG-04-00004 | PKG-04 | INV-PKG-04-025-05974 | 75.64 | 44304.05 | 2215.2 | Disputed | 42088.85 | 2025-Q1
EXP-006593 | 2025-01-15 | BOQ-PKG-03-00623 | PKG-03 | INV-PKG-03-014-06593 | 435.02 | 43337.47 | 2166.87 | Paid | 41170.6 | 2025-Q1
EXP-003005 | 2025-01-16 | BOQ-PKG-05-01015 | PKG-05 | INV-PKG-05-031-03005 | 96.07 | 34883.85 | 1744.19 | Approved Pending Payment | 33139.66 | 2025-Q1
EXP-003795 | 2025-01-16 | BOQ-PKG-05-01805 | PKG-05 | INV-PKG-05-016-03795 | 243.43 | 143373.31 | 7168.67 | Paid | 136204.64 | 2025-Q1
EXP-004684 | 2025-01-16 | BOQ-PKG-04-00704 | PKG-04 | INV-PKG-04-030-04684 | 13.33 | 197325.34 | 9866.27 | Paid | 187459.07 | 2025-Q1
EXP-004919 | 2025-01-16 | BOQ-PKG-09-00939 | PKG-09 | INV-PKG-09-020-04919 | 331.58 | 140027.54 | 7001.38 | Paid | 133026.16 | 2025-Q1
EXP-005200 | 2025-01-16 | BOQ-PKG-10-01220 | PKG-10 | INV-PKG-10-021-05200 | 59.34 | 147905.97 | 7395.3 | Paid | 140510.67 | 2025-Q1
EXP-005370 | 2025-01-16 | BOQ-PKG-10-01390 | PKG-10 | INV-PKG-10-016-05370 | 138.6 | 200989.3 | 10049.46 | Paid | 190939.84 | 2025-Q1
EXP-005778 | 2025-01-16 | BOQ-PKG-08-01798 | PKG-08 | INV-PKG-08-004-05778 | 161.5 | 183062.11 | 9153.11 | Disputed | 173909 | 2025-Q1
EXP-006508 | 2025-01-16 | BOQ-PKG-08-00538 | PKG-08 | INV-PKG-08-034-06508 | 423.53 | 94599.12 | 4729.96 | Paid | 89869.16 | 2025-Q1
EXP-000241 | 2025-01-17 | BOQ-PKG-01-00241 | PKG-01 | INV-PKG-01-032-00241 | 374.16 | 50567.84 | 2528.39 | Approved Pending Payment | 48039.45 | 2025-Q1
EXP-000880 | 2025-01-17 | BOQ-PKG-10-00880 | PKG-10 | INV-PKG-10-006-00880 | 80.99 | 66682.86 | 3334.14 | Paid | 63348.72 | 2025-Q1
EXP-003482 | 2025-01-17 | BOQ-PKG-02-01492 | PKG-02 | INV-PKG-02-018-03482 | 380.83 | 24792.68 | 1239.63 | Paid | 23553.05 | 2025-Q1
EXP-003984 | 2025-01-17 | BOQ-PKG-04-00004 | PKG-04 | INV-PKG-04-030-03984 | 275.03 | 147495.7 | 7374.79 | Disputed | 140120.91 | 2025-Q1
EXP-004505 | 2025-01-17 | BOQ-PKG-05-00525 | PKG-05 | INV-PKG-05-026-04505 | 329.25 | 100650.04 | 5032.5 | Approved Pending Payment | 95617.54 | 2025-Q1
EXP-006161 | 2025-01-17 | BOQ-PKG-01-00191 | PKG-01 | INV-PKG-01-002-06161 | 405.9 | 84384.61 | 4219.23 | Paid | 80165.38 | 2025-Q1
EXP-006983 | 2025-01-17 | BOQ-PKG-03-01013 | PKG-03 | INV-PKG-03-019-06983 | 331.71 | 85213.71 | 4260.69 | Approved Pending Payment | 80953.02 | 2025-Q1
EXP-000038 | 2025-01-18 | BOQ-PKG-08-00038 | PKG-08 | INV-PKG-08-004-00038 | 111.93 | 41064.62 | 2053.23 | Paid | 39011.39 | 2025-Q1
EXP-002561 | 2025-01-18 | BOQ-PKG-01-00571 | PKG-01 | INV-PKG-01-007-02561 | 198.75 | 37667.67 | 1883.38 | Paid | 35784.29 | 2025-Q1
EXP-004644 | 2025-01-18 | BOQ-PKG-04-00664 | PKG-04 | INV-PKG-04-025-04644 | 349.5 | 47842.3 | 2392.12 | Paid | 45450.18 | 2025-Q1
EXP-004812 | 2025-01-18 | BOQ-PKG-02-00832 | PKG-02 | INV-PKG-02-018-04812 | 286.68 | 137008.83 | 6850.44 | Under Review | 130158.39 | 2025-Q1
EXP-005135 | 2025-01-18 | BOQ-PKG-05-01155 | PKG-05 | INV-PKG-05-026-05135 | 289.69 | 100111.62 | 5005.58 | Paid | 95106.04 | 2025-Q1
EXP-005651 | 2025-01-18 | BOQ-PKG-01-01671 | PKG-01 | INV-PKG-01-017-05651 | 169.17 | 144617.55 | 7230.88 | Paid | 137386.67 | 2025-Q1
EXP-005868 | 2025-01-18 | BOQ-PKG-08-01888 | PKG-08 | INV-PKG-08-024-05868 | 144.21 | 41856.65 | 2092.83 | Disputed | 39763.82 | 2025-Q1
EXP-006168 | 2025-01-18 | BOQ-PKG-08-00198 | PKG-08 | INV-PKG-08-009-06168 | 373.91 | 118733.26 | 5936.66 | Paid | 112796.6 | 2025-Q1
EXP-006470 | 2025-01-18 | BOQ-PKG-10-00500 | PKG-10 | INV-PKG-10-031-06470 | 53.96 | 211328.92 | 10566.45 | Disputed | 200762.47 | 2025-Q1
EXP-002478 | 2025-01-19 | BOQ-PKG-08-00488 | PKG-08 | INV-PKG-08-029-02478 | 296.26 | 71049.08 | 3552.45 | Paid | 67496.63 | 2025-Q1
EXP-003003 | 2025-01-19 | BOQ-PKG-03-01013 | PKG-03 | INV-PKG-03-029-03003 | 11.72 | 192062.3 | 9603.12 | Approved Pending Payment | 182459.18 | 2025-Q1
EXP-003967 | 2025-01-19 | BOQ-PKG-07-01977 | PKG-07 | INV-PKG-07-013-03967 | 234.61 | 120920.07 | 6046 | Paid | 114874.07 | 2025-Q1
EXP-004579 | 2025-01-19 | BOQ-PKG-09-00599 | PKG-09 | INV-PKG-09-030-04579 | 93.11 | 137070.98 | 6853.55 | Paid | 130217.43 | 2025-Q1
EXP-004845 | 2025-01-19 | BOQ-PKG-05-00865 | PKG-05 | INV-PKG-05-016-04845 | 234.78 | 26567.16 | 1328.36 | Paid | 25238.8 | 2025-Q1
EXP-005538 | 2025-01-19 | BOQ-PKG-08-01558 | PKG-08 | INV-PKG-08-009-05538 | 232.54 | 202528.9 | 10126.44 | Disputed | 192402.46 | 2025-Q1
EXP-005709 | 2025-01-19 | BOQ-PKG-09-01729 | PKG-09 | INV-PKG-09-005-05709 | 58.21 | 172935.38 | 8646.77 | Paid | 164288.61 | 2025-Q1
EXP-006138 | 2025-01-19 | BOQ-PKG-08-00168 | PKG-08 | INV-PKG-08-014-06138 | 162.93 | 161260.33 | 8063.02 | Under Review | 153197.31 | 2025-Q1
EXP-006206 | 2025-01-19 | BOQ-PKG-06-00236 | PKG-06 | INV-PKG-06-012-06206 | 377.77 | 198621.48 | 9931.07 | Paid | 188690.41 | 2025-Q1
EXP-001186 | 2025-01-20 | BOQ-PKG-06-01186 | PKG-06 | INV-PKG-06-032-01186 | 381 | 23359.77 | 1167.99 | Paid | 22191.78 | 2025-Q1
EXP-001399 | 2025-01-20 | BOQ-PKG-09-01399 | PKG-09 | INV-PKG-09-035-01399 | 426.22 | 70906.97 | 3545.35 | Approved Pending Payment | 67361.62 | 2025-Q1
EXP-001660 | 2025-01-20 | BOQ-PKG-10-01660 | PKG-10 | INV-PKG-10-016-01660 | 334.66 | 138071.36 | 6903.57 | Paid | 131167.79 | 2025-Q1
EXP-002104 | 2025-01-20 | BOQ-PKG-04-00114 | PKG-04 | INV-PKG-04-005-02104 | 345.91 | 105787.95 | 5289.4 | Paid | 100498.55 | 2025-Q1
EXP-002127 | 2025-01-20 | BOQ-PKG-07-00137 | PKG-07 | INV-PKG-07-028-02127 | 379.38 | 152707.28 | 7635.36 | Paid | 145071.92 | 2025-Q1
EXP-003332 | 2025-01-20 | BOQ-PKG-02-01342 | PKG-02 | INV-PKG-02-008-03332 | 437.23 | 92077.93 | 4603.9 | Paid | 87474.03 | 2025-Q1
EXP-004706 | 2025-01-20 | BOQ-PKG-06-00726 | PKG-06 | INV-PKG-06-017-04706 | 231.59 | 44273.88 | 2213.69 | Approved Pending Payment | 42060.19 | 2025-Q1
EXP-005642 | 2025-01-20 | BOQ-PKG-02-01662 | PKG-02 | INV-PKG-02-008-05642 | 211.1 | 193855.17 | 9692.76 | Paid | 184162.41 | 2025-Q1
EXP-005644 | 2025-01-20 | BOQ-PKG-04-01664 | PKG-04 | INV-PKG-04-010-05644 | 370.07 | 29008.07 | 1450.4 | Approved Pending Payment | 27557.67 | 2025-Q1
EXP-006180 | 2025-01-20 | BOQ-PKG-10-00210 | PKG-10 | INV-PKG-10-021-06180 | 30.36 | 43098.04 | 2154.9 | Paid | 40943.14 | 2025-Q1
EXP-000174 | 2025-01-21 | BOQ-PKG-04-00174 | PKG-04 | INV-PKG-04-035-00174 | 426.76 | 51339.39 | 2566.97 | Paid | 48772.42 | 2025-Q1
EXP-001422 | 2025-01-21 | BOQ-PKG-02-01422 | PKG-02 | INV-PKG-02-023-01422 | 407.69 | 127997.92 | 6399.9 | Paid | 121598.02 | 2025-Q1
EXP-002726 | 2025-01-21 | BOQ-PKG-06-00736 | PKG-06 | INV-PKG-06-032-02726 | 38.31 | 111962.33 | 5598.12 | Paid | 106364.21 | 2025-Q1
EXP-003175 | 2025-01-21 | BOQ-PKG-05-01185 | PKG-05 | INV-PKG-05-026-03175 | 112.26 | 36084.21 | 1804.21 | Paid | 34280 | 2025-Q1
EXP-003636 | 2025-01-21 | BOQ-PKG-06-01646 | PKG-06 | INV-PKG-06-032-03636 | 326.82 | 130677.82 | 6533.89 | Paid | 124143.93 | 2025-Q1
EXP-004987 | 2025-01-21 | BOQ-PKG-07-01007 | PKG-07 | INV-PKG-07-018-04987 | 19.48 | 93468.2 | 4673.41 | Paid | 88794.79 | 2025-Q1
EXP-005191 | 2025-01-21 | BOQ-PKG-01-01211 | PKG-01 | INV-PKG-01-012-05191 | 428.54 | 199258.89 | 9962.94 | Paid | 189295.95 | 2025-Q1
EXP-005606 | 2025-01-21 | BOQ-PKG-06-01626 | PKG-06 | INV-PKG-06-007-05606 | 255.62 | 161292.64 | 8064.63 | Under Review | 153228.01 | 2025-Q1
EXP-005744 | 2025-01-21 | BOQ-PKG-04-01764 | PKG-04 | INV-PKG-04-005-05744 | 34.83 | 129531.16 | 6476.56 | Paid | 123054.6 | 2025-Q1
EXP-006128 | 2025-01-21 | BOQ-PKG-08-00158 | PKG-08 | INV-PKG-08-004-06128 | 213.38 | 107258.74 | 5362.94 | Under Review | 101895.8 | 2025-Q1
EXP-000090 | 2025-01-22 | BOQ-PKG-10-00090 | PKG-10 | INV-PKG-10-021-00090 | 110.43 | 40985.22 | 2049.26 | Approved Pending Payment | 38935.96 | 2025-Q1
EXP-000142 | 2025-01-22 | BOQ-PKG-02-00142 | PKG-02 | INV-PKG-02-003-00142 | 66.97 | 26028.1 | 1301.4 | Disputed | 24726.7 | 2025-Q1
EXP-000205 | 2025-01-22 | BOQ-PKG-05-00205 | PKG-05 | INV-PKG-05-031-00205 | 215.68 | 181192.6 | 9059.63 | Under Review | 172132.97 | 2025-Q1
EXP-000919 | 2025-01-22 | BOQ-PKG-09-00919 | PKG-09 | INV-PKG-09-010-00919 | 177.56 | 76094.31 | 3804.72 | Under Review | 72289.59 | 2025-Q1
EXP-001475 | 2025-01-22 | BOQ-PKG-05-01475 | PKG-05 | INV-PKG-05-006-01475 | 6.95 | 75646.88 | 3782.34 | Approved Pending Payment | 71864.54 | 2025-Q1
EXP-002676 | 2025-01-22 | BOQ-PKG-06-00686 | PKG-06 | INV-PKG-06-017-02676 | 129.57 | 68062.45 | 3403.12 | Paid | 64659.33 | 2025-Q1
EXP-004572 | 2025-01-22 | BOQ-PKG-02-00592 | PKG-02 | INV-PKG-02-023-04572 | 77.01 | 107161.02 | 5358.05 | Approved Pending Payment | 101802.97 | 2025-Q1
EXP-000991 | 2025-01-23 | BOQ-PKG-01-00991 | PKG-01 | INV-PKG-01-012-00991 | 106.2 | 56660.14 | 2833.01 | Paid | 53827.13 | 2025-Q1
EXP-001350 | 2025-01-23 | BOQ-PKG-10-01350 | PKG-10 | INV-PKG-10-021-01350 | 170.75 | 106270.96 | 5313.55 | Paid | 100957.41 | 2025-Q1
EXP-001735 | 2025-01-23 | BOQ-PKG-05-01735 | PKG-05 | INV-PKG-05-021-01735 | 85.03 | 76897.44 | 3844.87 | Paid | 73052.57 | 2025-Q1
EXP-002890 | 2025-01-23 | BOQ-PKG-10-00900 | PKG-10 | INV-PKG-10-021-02890 | 271.33 | 92869.05 | 4643.45 | Paid | 88225.6 | 2025-Q1
EXP-003511 | 2025-01-23 | BOQ-PKG-01-01521 | PKG-01 | INV-PKG-01-012-03511 | 75.97 | 58680.58 | 2934.03 | Paid | 55746.55 | 2025-Q1
EXP-004368 | 2025-01-23 | BOQ-PKG-08-00388 | PKG-08 | INV-PKG-08-029-04368 | 320.81 | 52556.52 | 2627.83 | Paid | 49928.69 | 2025-Q1
EXP-004652 | 2025-01-23 | BOQ-PKG-02-00672 | PKG-02 | INV-PKG-02-033-04652 | 423.2 | 97816.65 | 4890.83 | Paid | 92925.82 | 2025-Q1
EXP-006869 | 2025-01-23 | BOQ-PKG-09-00899 | PKG-09 | INV-PKG-09-010-06869 | 349.27 | 181492.74 | 9074.64 | Paid | 172418.1 | 2025-Q1
EXP-000195 | 2025-01-24 | BOQ-PKG-05-00195 | PKG-05 | INV-PKG-05-021-00195 | 27.81 | 100319.86 | 5015.99 | Paid | 95303.87 | 2025-Q1
EXP-002493 | 2025-01-24 | BOQ-PKG-03-00503 | PKG-03 | INV-PKG-03-009-02493 | 118.39 | 54023.11 | 2701.16 | Paid | 51321.95 | 2025-Q1
EXP-003637 | 2025-01-24 | BOQ-PKG-07-01647 | PKG-07 | INV-PKG-07-033-03637 | 61.12 | 115417.8 | 5770.89 | Paid | 109646.91 | 2025-Q1
EXP-004637 | 2025-01-24 | BOQ-PKG-07-00657 | PKG-07 | INV-PKG-07-018-04637 | 300.92 | 79498.41 | 3974.92 | Approved Pending Payment | 75523.49 | 2025-Q1
EXP-004966 | 2025-01-24 | BOQ-PKG-06-00986 | PKG-06 | INV-PKG-06-032-04966 | 256.06 | 197913.05 | 9895.65 | Disputed | 188017.4 | 2025-Q1
EXP-005573 | 2025-01-24 | BOQ-PKG-03-01593 | PKG-03 | INV-PKG-03-009-05573 | 302.12 | 186137.63 | 9306.88 | Paid | 176830.75 | 2025-Q1
EXP-006286 | 2025-01-24 | BOQ-PKG-06-00316 | PKG-06 | INV-PKG-06-022-06286 | 221.35 | 201911.07 | 10095.55 | Paid | 191815.52 | 2025-Q1
EXP-006553 | 2025-01-24 | BOQ-PKG-03-00583 | PKG-03 | INV-PKG-03-009-06553 | 394.94 | 29615.8 | 1480.79 | Approved Pending Payment | 28135.01 | 2025-Q1
EXP-000098 | 2025-01-25 | BOQ-PKG-08-00098 | PKG-08 | INV-PKG-08-029-00098 | 64.19 | 55461.02 | 2773.05 | Under Review | 52687.97 | 2025-Q1
EXP-003871 | 2025-01-25 | BOQ-PKG-01-01881 | PKG-01 | INV-PKG-01-022-03871 | 312.17 | 162235.47 | 8111.77 | Disputed | 154123.7 | 2025-Q1
EXP-000816 | 2025-01-26 | BOQ-PKG-06-00816 | PKG-06 | INV-PKG-06-012-00816 | 154.66 | 67615.94 | 3380.8 | Paid | 64235.14 | 2025-Q1
EXP-002384 | 2025-01-26 | BOQ-PKG-04-00394 | PKG-04 | INV-PKG-04-005-02384 | 307.72 | 183423.67 | 9171.18 | Paid | 174252.49 | 2025-Q1
EXP-002901 | 2025-01-26 | BOQ-PKG-01-00911 | PKG-01 | INV-PKG-01-032-02901 | 445.86 | 192284.62 | 9614.23 | Paid | 182670.39 | 2025-Q1
EXP-002944 | 2025-01-26 | BOQ-PKG-04-00954 | PKG-04 | INV-PKG-04-005-02944 | 388.55 | 84096.12 | 4204.81 | Approved Pending Payment | 79891.31 | 2025-Q1
EXP-004828 | 2025-01-26 | BOQ-PKG-08-00848 | PKG-08 | INV-PKG-08-034-04828 | 124.38 | 201163.79 | 10058.19 | Paid | 191105.6 | 2025-Q1
EXP-006897 | 2025-01-26 | BOQ-PKG-07-00927 | PKG-07 | INV-PKG-07-003-06897 | 127.83 | 143409.44 | 7170.47 | Paid | 136238.97 | 2025-Q1
EXP-001473 | 2025-01-27 | BOQ-PKG-03-01473 | PKG-03 | INV-PKG-03-004-01473 | 80.6 | 98239.36 | 4911.97 | Paid | 93327.39 | 2025-Q1
EXP-001971 | 2025-01-27 | BOQ-PKG-01-01971 | PKG-01 | INV-PKG-01-012-01971 | 65.91 | 158202.2 | 7910.11 | Paid | 150292.09 | 2025-Q1
EXP-002427 | 2025-01-27 | BOQ-PKG-07-00437 | PKG-07 | INV-PKG-07-013-02427 | 107.32 | 90423.88 | 4521.19 | Approved Pending Payment | 85902.69 | 2025-Q1
EXP-002628 | 2025-01-27 | BOQ-PKG-08-00638 | PKG-08 | INV-PKG-08-004-02628 | 42.14 | 78483.63 | 3924.18 | Paid | 74559.45 | 2025-Q1
EXP-004874 | 2025-01-27 | BOQ-PKG-04-00894 | PKG-04 | INV-PKG-04-010-04874 | 122.3 | 185653.96 | 9282.7 | Paid | 176371.26 | 2025-Q1
EXP-004981 | 2025-01-27 | BOQ-PKG-01-01001 | PKG-01 | INV-PKG-01-012-04981 | 324.23 | 192620.59 | 9631.03 | Approved Pending Payment | 182989.56 | 2025-Q1
EXP-005040 | 2025-01-27 | BOQ-PKG-10-01060 | PKG-10 | INV-PKG-10-001-05040 | 62.89 | 38395.18 | 1919.76 | Paid | 36475.42 | 2025-Q1
EXP-005156 | 2025-01-27 | BOQ-PKG-06-01176 | PKG-06 | INV-PKG-06-012-05156 | 446.31 | 65198.09 | 3259.9 | Paid | 61938.19 | 2025-Q1
EXP-005242 | 2025-01-27 | BOQ-PKG-02-01262 | PKG-02 | INV-PKG-02-028-05242 | 31.61 | 92249.45 | 4612.47 | Paid | 87636.98 | 2025-Q1
EXP-001916 | 2025-01-28 | BOQ-PKG-06-01916 | PKG-06 | INV-PKG-06-027-01916 | 89.07 | 160341.6 | 8017.08 | Paid | 152324.52 | 2025-Q1
EXP-003732 | 2025-01-28 | BOQ-PKG-02-01742 | PKG-02 | INV-PKG-02-023-03732 | 336.95 | 48259 | 2412.95 | Paid | 45846.05 | 2025-Q1
EXP-004034 | 2025-01-28 | BOQ-PKG-04-00054 | PKG-04 | INV-PKG-04-010-04034 | 322.17 | 30954.57 | 1547.73 | Paid | 29406.84 | 2025-Q1
EXP-004460 | 2025-01-28 | BOQ-PKG-10-00480 | PKG-10 | INV-PKG-10-016-04460 | 326.21 | 205884.73 | 10294.24 | Paid | 195590.49 | 2025-Q1
EXP-005442 | 2025-01-28 | BOQ-PKG-02-01462 | PKG-02 | INV-PKG-02-018-05442 | 376.84 | 207929.51 | 10396.48 | Paid | 197533.03 | 2025-Q1
EXP-000397 | 2025-01-29 | BOQ-PKG-07-00397 | PKG-07 | INV-PKG-07-013-00397 | 426.48 | 101954.8 | 5097.74 | Paid | 96857.06 | 2025-Q1
EXP-001609 | 2025-01-29 | BOQ-PKG-09-01609 | PKG-09 | INV-PKG-09-035-01609 | 261.73 | 190379.92 | 9519 | Paid | 180860.92 | 2025-Q1
EXP-002094 | 2025-01-29 | BOQ-PKG-04-00104 | PKG-04 | INV-PKG-04-030-02094 | 402.85 | 117067.77 | 5853.39 | Under Review | 111214.38 | 2025-Q1
EXP-003012 | 2025-01-29 | BOQ-PKG-02-01022 | PKG-02 | INV-PKG-02-003-03012 | 319.19 | 133898.37 | 6694.92 | Paid | 127203.45 | 2025-Q1
EXP-005192 | 2025-01-29 | BOQ-PKG-02-01212 | PKG-02 | INV-PKG-02-013-05192 | 410.5 | 184565.83 | 9228.29 | Paid | 175337.54 | 2025-Q1
EXP-006086 | 2025-01-29 | BOQ-PKG-06-00116 | PKG-06 | INV-PKG-06-032-06086 | 185.19 | 163251.2 | 8162.56 | Paid | 155088.64 | 2025-Q1
EXP-006315 | 2025-01-29 | BOQ-PKG-05-00345 | PKG-05 | INV-PKG-05-016-06315 | 181.35 | 126728.04 | 6336.4 | Paid | 120391.64 | 2025-Q1
EXP-002246 | 2025-01-30 | BOQ-PKG-06-00256 | PKG-06 | INV-PKG-06-007-02246 | 359.03 | 161738.33 | 8086.92 | Paid | 153651.41 | 2025-Q1
EXP-002349 | 2025-01-30 | BOQ-PKG-09-00359 | PKG-09 | INV-PKG-09-005-02349 | 36.55 | 161624.1 | 8081.21 | Under Review | 153542.89 | 2025-Q1
EXP-004184 | 2025-01-30 | BOQ-PKG-04-00204 | PKG-04 | INV-PKG-04-020-04184 | 258.19 | 124459.8 | 6222.99 | Paid | 118236.81 | 2025-Q1
EXP-005859 | 2025-01-30 | BOQ-PKG-09-01879 | PKG-09 | INV-PKG-09-015-05859 | 29.74 | 155427.16 | 7771.36 | Approved Pending Payment | 147655.8 | 2025-Q1
EXP-006055 | 2025-01-30 | BOQ-PKG-05-00085 | PKG-05 | INV-PKG-05-001-06055 | 371.45 | 68608.32 | 3430.42 | Paid | 65177.9 | 2025-Q1
EXP-000041 | 2025-01-31 | BOQ-PKG-01-00041 | PKG-01 | INV-PKG-01-007-00041 | 304.27 | 149121.42 | 7456.07 | Paid | 141665.35 | 2025-Q1
EXP-000097 | 2025-01-31 | BOQ-PKG-07-00097 | PKG-07 | INV-PKG-07-028-00097 | 236.23 | 204001.04 | 10200.05 | Paid | 193800.99 | 2025-Q1
EXP-001119 | 2025-01-31 | BOQ-PKG-09-01119 | PKG-09 | INV-PKG-09-035-01119 | 50.57 | 34176.56 | 1708.83 | Paid | 32467.73 | 2025-Q1
EXP-001502 | 2025-01-31 | BOQ-PKG-02-01502 | PKG-02 | INV-PKG-02-033-01502 | 157.83 | 100811.58 | 5040.58 | Paid | 95771 | 2025-Q1
EXP-001548 | 2025-01-31 | BOQ-PKG-08-01548 | PKG-08 | INV-PKG-08-009-01548 | 38.8 | 150800.41 | 7540.02 | Paid | 143260.39 | 2025-Q1
EXP-002488 | 2025-01-31 | BOQ-PKG-08-00498 | PKG-08 | INV-PKG-08-004-02488 | 435.32 | 140552.69 | 7027.63 | Paid | 133525.06 | 2025-Q1
EXP-002525 | 2025-01-31 | BOQ-PKG-05-00535 | PKG-05 | INV-PKG-05-006-02525 | 326.54 | 157149.46 | 7857.47 | Paid | 149291.99 | 2025-Q1
EXP-003057 | 2025-01-31 | BOQ-PKG-07-01067 | PKG-07 | INV-PKG-07-013-03057 | 448.66 | 54742.05 | 2737.1 | Under Review | 52004.95 | 2025-Q1
EXP-003937 | 2025-01-31 | BOQ-PKG-07-01947 | PKG-07 | INV-PKG-07-018-03937 | 18.1 | 170691.95 | 8534.6 | Paid | 162157.35 | 2025-Q1
EXP-004291 | 2025-01-31 | BOQ-PKG-01-00311 | PKG-01 | INV-PKG-01-022-04291 | 16.37 | 112390.99 | 5619.55 | Approved Pending Payment | 106771.44 | 2025-Q1
EXP-006346 | 2025-01-31 | BOQ-PKG-06-00376 | PKG-06 | INV-PKG-06-012-06346 | 133 | 75782.76 | 3789.14 | Paid | 71993.62 | 2025-Q1
EXP-006786 | 2025-01-31 | BOQ-PKG-06-00816 | PKG-06 | INV-PKG-06-032-06786 | 415.45 | 34302.88 | 1715.14 | Paid | 32587.74 | 2025-Q1
EXP-000417 | 2025-02-01 | BOQ-PKG-07-00417 | PKG-07 | INV-PKG-07-033-00417 | 153.32 | 116446.61 | 5822.33 | Paid | 110624.28 | 2025-Q1
EXP-000964 | 2025-02-01 | BOQ-PKG-04-00964 | PKG-04 | INV-PKG-04-020-00964 | 65.95 | 115089.71 | 5754.49 | Paid | 109335.22 | 2025-Q1
EXP-001733 | 2025-02-01 | BOQ-PKG-03-01733 | PKG-03 | INV-PKG-03-019-01733 | 306.87 | 173004.18 | 8650.21 | Paid | 164353.97 | 2025-Q1
EXP-001819 | 2025-02-01 | BOQ-PKG-09-01819 | PKG-09 | INV-PKG-09-035-01819 | 388.76 | 57944.3 | 2897.22 | Under Review | 55047.08 | 2025-Q1
EXP-002353 | 2025-02-01 | BOQ-PKG-03-00363 | PKG-03 | INV-PKG-03-009-02353 | 322.13 | 197852.41 | 9892.62 | Paid | 187959.79 | 2025-Q1
EXP-001033 | 2025-02-02 | BOQ-PKG-03-01033 | PKG-03 | INV-PKG-03-019-01033 | 93.28 | 203670.59 | 10183.53 | Approved Pending Payment | 193487.06 | 2025-Q1
EXP-002102 | 2025-02-02 | BOQ-PKG-02-00112 | PKG-02 | INV-PKG-02-003-02102 | 22.77 | 175793.21 | 8789.66 | Paid | 167003.55 | 2025-Q1
EXP-002644 | 2025-02-02 | BOQ-PKG-04-00654 | PKG-04 | INV-PKG-04-020-02644 | 50.92 | 119575.1 | 5978.76 | Approved Pending Payment | 113596.34 | 2025-Q1
EXP-003259 | 2025-02-02 | BOQ-PKG-09-01269 | PKG-09 | INV-PKG-09-005-03259 | 371.08 | 139996.19 | 6999.81 | Approved Pending Payment | 132996.38 | 2025-Q1
EXP-003471 | 2025-02-02 | BOQ-PKG-01-01481 | PKG-01 | INV-PKG-01-007-03471 | 107.54 | 68238.11 | 3411.91 | Paid | 64826.2 | 2025-Q1
EXP-004628 | 2025-02-02 | BOQ-PKG-08-00648 | PKG-08 | INV-PKG-08-009-04628 | 387.52 | 199823.2 | 9991.16 | Approved Pending Payment | 189832.04 | 2025-Q1
EXP-006314 | 2025-02-02 | BOQ-PKG-04-00344 | PKG-04 | INV-PKG-04-015-06314 | 435.14 | 110938.07 | 5546.9 | Paid | 105391.17 | 2025-Q1
EXP-006538 | 2025-02-02 | BOQ-PKG-08-00568 | PKG-08 | INV-PKG-08-029-06538 | 47.74 | 207738.78 | 10386.94 | Paid | 197351.84 | 2025-Q1
EXP-006755 | 2025-02-02 | BOQ-PKG-05-00785 | PKG-05 | INV-PKG-05-001-06755 | 18.99 | 101447.24 | 5072.36 | Paid | 96374.88 | 2025-Q1
EXP-000276 | 2025-02-03 | BOQ-PKG-06-00276 | PKG-06 | INV-PKG-06-032-00276 | 80.28 | 212154.1 | 10607.71 | Paid | 201546.39 | 2025-Q1
EXP-000810 | 2025-02-03 | BOQ-PKG-10-00810 | PKG-10 | INV-PKG-10-006-00810 | 372.67 | 66566.51 | 3328.33 | Approved Pending Payment | 63238.18 | 2025-Q1
EXP-003289 | 2025-02-03 | BOQ-PKG-09-01299 | PKG-09 | INV-PKG-09-035-03289 | 364.74 | 135560.17 | 6778.01 | Under Review | 128782.16 | 2025-Q1
EXP-003372 | 2025-02-03 | BOQ-PKG-02-01382 | PKG-02 | INV-PKG-02-013-03372 | 153.85 | 89967.92 | 4498.4 | Paid | 85469.52 | 2025-Q1
EXP-004393 | 2025-02-03 | BOQ-PKG-03-00413 | PKG-03 | INV-PKG-03-019-04393 | 198.66 | 213078.94 | 10653.95 | Approved Pending Payment | 202424.99 | 2025-Q1
EXP-004657 | 2025-02-03 | BOQ-PKG-07-00677 | PKG-07 | INV-PKG-07-003-04657 | 57.98 | 164943.94 | 8247.2 | Paid | 156696.74 | 2025-Q1
EXP-005129 | 2025-02-03 | BOQ-PKG-09-01149 | PKG-09 | INV-PKG-09-020-05129 | 377.35 | 37804.46 | 1890.22 | Paid | 35914.24 | 2025-Q1
EXP-005513 | 2025-02-03 | BOQ-PKG-03-01533 | PKG-03 | INV-PKG-03-019-05513 | 92.46 | 144080.88 | 7204.04 | Paid | 136876.84 | 2025-Q1
EXP-005707 | 2025-02-03 | BOQ-PKG-07-01727 | PKG-07 | INV-PKG-07-003-05707 | 14.53 | 146119 | 7305.95 | Paid | 138813.05 | 2025-Q1
EXP-006801 | 2025-02-03 | BOQ-PKG-01-00831 | PKG-01 | INV-PKG-01-012-06801 | 280.99 | 97109.28 | 4855.46 | Paid | 92253.82 | 2025-Q1
EXP-006803 | 2025-02-03 | BOQ-PKG-03-00833 | PKG-03 | INV-PKG-03-014-06803 | 57.26 | 49518.81 | 2475.94 | Approved Pending Payment | 47042.87 | 2025-Q1
EXP-006830 | 2025-02-03 | BOQ-PKG-10-00860 | PKG-10 | INV-PKG-10-006-06830 | 69.89 | 54554.2 | 2727.71 | Approved Pending Payment | 51826.49 | 2025-Q1
EXP-000108 | 2025-02-04 | BOQ-PKG-08-00108 | PKG-08 | INV-PKG-08-004-00108 | 237.01 | 186787.44 | 9339.37 | Paid | 177448.07 | 2025-Q1
EXP-000387 | 2025-02-04 | BOQ-PKG-07-00387 | PKG-07 | INV-PKG-07-003-00387 | 417.33 | 155587.73 | 7779.39 | Paid | 147808.34 | 2025-Q1
EXP-001086 | 2025-02-04 | BOQ-PKG-06-01086 | PKG-06 | INV-PKG-06-002-01086 | 108.36 | 120871.23 | 6043.56 | Paid | 114827.67 | 2025-Q1
EXP-001174 | 2025-02-04 | BOQ-PKG-04-01174 | PKG-04 | INV-PKG-04-020-01174 | 382.35 | 93244.48 | 4662.22 | Paid | 88582.26 | 2025-Q1
EXP-001625 | 2025-02-04 | BOQ-PKG-05-01625 | PKG-05 | INV-PKG-05-016-01625 | 121.58 | 211628.32 | 10581.42 | Paid | 201046.9 | 2025-Q1
EXP-002116 | 2025-02-04 | BOQ-PKG-06-00126 | PKG-06 | INV-PKG-06-017-02116 | 226.86 | 125059.34 | 6252.97 | Paid | 118806.37 | 2025-Q1
EXP-003787 | 2025-02-04 | BOQ-PKG-07-01797 | PKG-07 | INV-PKG-07-008-03787 | 155.11 | 169342.18 | 8467.11 | Paid | 160875.07 | 2025-Q1
EXP-004629 | 2025-02-04 | BOQ-PKG-09-00649 | PKG-09 | INV-PKG-09-010-04629 | 75.71 | 88097.96 | 4404.9 | Paid | 83693.06 | 2025-Q1
EXP-004645 | 2025-02-04 | BOQ-PKG-05-00665 | PKG-05 | INV-PKG-05-026-04645 | 31.05 | 155629.75 | 7781.49 | Paid | 147848.26 | 2025-Q1
EXP-004709 | 2025-02-04 | BOQ-PKG-09-00729 | PKG-09 | INV-PKG-09-020-04709 | 400.34 | 64901.15 | 3245.06 | Paid | 61656.09 | 2025-Q1
EXP-006309 | 2025-02-04 | BOQ-PKG-09-00339 | PKG-09 | INV-PKG-09-010-06309 | 198.67 | 176847.8 | 8842.39 | Paid | 168005.41 | 2025-Q1
EXP-006335 | 2025-02-04 | BOQ-PKG-05-00365 | PKG-05 | INV-PKG-05-001-06335 | 242.38 | 116730.75 | 5836.54 | Paid | 110894.21 | 2025-Q1
EXP-000926 | 2025-02-05 | BOQ-PKG-06-00926 | PKG-06 | INV-PKG-06-017-00926 | 310.92 | 71366.37 | 3568.32 | Under Review | 67798.05 | 2025-Q1
EXP-001930 | 2025-02-05 | BOQ-PKG-10-01930 | PKG-10 | INV-PKG-10-006-01930 | 226.27 | 32456.73 | 1622.84 | Disputed | 30833.89 | 2025-Q1
EXP-002388 | 2025-02-05 | BOQ-PKG-08-00398 | PKG-08 | INV-PKG-08-009-02388 | 121.96 | 134754.23 | 6737.71 | Approved Pending Payment | 128016.52 | 2025-Q1
EXP-002857 | 2025-02-05 | BOQ-PKG-07-00867 | PKG-07 | INV-PKG-07-023-02857 | 139.21 | 40255.9 | 2012.8 | Paid | 38243.1 | 2025-Q1
EXP-003447 | 2025-02-05 | BOQ-PKG-07-01457 | PKG-07 | INV-PKG-07-018-03447 | 264.31 | 159538.39 | 7976.92 | Paid | 151561.47 | 2025-Q1
EXP-004407 | 2025-02-05 | BOQ-PKG-07-00427 | PKG-07 | INV-PKG-07-033-04407 | 379.22 | 51228.26 | 2561.41 | Paid | 48666.85 | 2025-Q1
EXP-004842 | 2025-02-05 | BOQ-PKG-02-00862 | PKG-02 | INV-PKG-02-013-04842 | 352.38 | 138327.72 | 6916.39 | Paid | 131411.33 | 2025-Q1
EXP-006357 | 2025-02-05 | BOQ-PKG-07-00387 | PKG-07 | INV-PKG-07-023-06357 | 197.75 | 90460.25 | 4523.01 | Paid | 85937.24 | 2025-Q1
EXP-000300 | 2025-02-06 | BOQ-PKG-10-00300 | PKG-10 | INV-PKG-10-021-00300 | 151.57 | 156598.87 | 7829.94 | Paid | 148768.93 | 2025-Q1
EXP-001171 | 2025-02-06 | BOQ-PKG-01-01171 | PKG-01 | INV-PKG-01-017-01171 | 403.46 | 56398.01 | 2819.9 | Paid | 53578.11 | 2025-Q1
EXP-001314 | 2025-02-06 | BOQ-PKG-04-01314 | PKG-04 | INV-PKG-04-020-01314 | 429.12 | 182566.76 | 9128.34 | Paid | 173438.42 | 2025-Q1
EXP-002147 | 2025-02-06 | BOQ-PKG-07-00157 | PKG-07 | INV-PKG-07-013-02147 | 28.4 | 124808.53 | 6240.43 | Paid | 118568.1 | 2025-Q1
EXP-002660 | 2025-02-06 | BOQ-PKG-10-00670 | PKG-10 | INV-PKG-10-001-02660 | 234.5 | 158400.85 | 7920.04 | Paid | 150480.81 | 2025-Q1
EXP-004123 | 2025-02-06 | BOQ-PKG-03-00143 | PKG-03 | INV-PKG-03-029-04123 | 279.7 | 196339.54 | 9816.98 | Paid | 186522.56 | 2025-Q1
EXP-004473 | 2025-02-06 | BOQ-PKG-03-00493 | PKG-03 | INV-PKG-03-029-04473 | 419.8 | 188133.23 | 9406.66 | Paid | 178726.57 | 2025-Q1
EXP-004491 | 2025-02-06 | BOQ-PKG-01-00511 | PKG-01 | INV-PKG-01-012-04491 | 48.67 | 71280.03 | 3564 | Under Review | 67716.03 | 2025-Q1
EXP-004694 | 2025-02-06 | BOQ-PKG-04-00714 | PKG-04 | INV-PKG-04-005-04694 | 406.57 | 76107.37 | 3805.37 | Paid | 72302 | 2025-Q1
EXP-006103 | 2025-02-06 | BOQ-PKG-03-00133 | PKG-03 | INV-PKG-03-014-06103 | 217.13 | 42301.71 | 2115.09 | Disputed | 40186.62 | 2025-Q1
EXP-006787 | 2025-02-06 | BOQ-PKG-07-00817 | PKG-07 | INV-PKG-07-033-06787 | 25.05 | 132952.17 | 6647.61 | Paid | 126304.56 | 2025-Q1
EXP-000522 | 2025-02-07 | BOQ-PKG-02-00522 | PKG-02 | INV-PKG-02-033-00522 | 214.46 | 32312.8 | 1615.64 | Approved Pending Payment | 30697.16 | 2025-Q1
EXP-001261 | 2025-02-07 | BOQ-PKG-01-01261 | PKG-01 | INV-PKG-01-002-01261 | 171.76 | 201814.49 | 10090.72 | Paid | 191723.77 | 2025-Q1
EXP-001321 | 2025-02-07 | BOQ-PKG-01-01321 | PKG-01 | INV-PKG-01-027-01321 | 445.91 | 112591.06 | 5629.55 | Paid | 106961.51 | 2025-Q1
EXP-001550 | 2025-02-07 | BOQ-PKG-10-01550 | PKG-10 | INV-PKG-10-011-01550 | 90.68 | 158299.65 | 7914.98 | Paid | 150384.67 | 2025-Q1
EXP-003308 | 2025-02-07 | BOQ-PKG-08-01318 | PKG-08 | INV-PKG-08-019-03308 | 144.1 | 201174.93 | 10058.75 | Paid | 191116.18 | 2025-Q1
EXP-004902 | 2025-02-07 | BOQ-PKG-02-00922 | PKG-02 | INV-PKG-02-003-04902 | 85.75 | 111776.06 | 5588.8 | Paid | 106187.26 | 2025-Q1
EXP-005466 | 2025-02-07 | BOQ-PKG-06-01486 | PKG-06 | INV-PKG-06-007-05466 | 146.34 | 106711.92 | 5335.6 | Paid | 101376.32 | 2025-Q1
EXP-005906 | 2025-02-07 | BOQ-PKG-06-01926 | PKG-06 | INV-PKG-06-027-05906 | 233.77 | 154004.31 | 7700.22 | Paid | 146304.09 | 2025-Q1
EXP-006722 | 2025-02-07 | BOQ-PKG-02-00752 | PKG-02 | INV-PKG-02-003-06722 | 221.57 | 172014.73 | 8600.74 | Paid | 163413.99 | 2025-Q1
EXP-006946 | 2025-02-07 | BOQ-PKG-06-00976 | PKG-06 | INV-PKG-06-017-06946 | 260.6 | 202268.98 | 10113.45 | Paid | 192155.53 | 2025-Q1
EXP-000009 | 2025-02-08 | BOQ-PKG-09-00009 | PKG-09 | INV-PKG-09-010-00009 | 112.04 | 153297.73 | 7664.89 | Paid | 145632.84 | 2025-Q1
EXP-000393 | 2025-02-08 | BOQ-PKG-03-00393 | PKG-03 | INV-PKG-03-009-00393 | 109.27 | 28427.08 | 1421.35 | Disputed | 27005.73 | 2025-Q1
EXP-000534 | 2025-02-08 | BOQ-PKG-04-00534 | PKG-04 | INV-PKG-04-010-00534 | 404.88 | 194062.32 | 9703.12 | Approved Pending Payment | 184359.2 | 2025-Q1
EXP-001034 | 2025-02-08 | BOQ-PKG-04-01034 | PKG-04 | INV-PKG-04-020-01034 | 163.03 | 99249.2 | 4962.46 | Paid | 94286.74 | 2025-Q1
EXP-001734 | 2025-02-08 | BOQ-PKG-04-01734 | PKG-04 | INV-PKG-04-020-01734 | 78.7 | 62980.31 | 3149.02 | Under Review | 59831.29 | 2025-Q1
EXP-001909 | 2025-02-08 | BOQ-PKG-09-01909 | PKG-09 | INV-PKG-09-020-01909 | 113.3 | 49403.17 | 2470.16 | Paid | 46933.01 | 2025-Q1
EXP-001924 | 2025-02-08 | BOQ-PKG-04-01924 | PKG-04 | INV-PKG-04-035-01924 | 251.98 | 66959.3 | 3347.96 | Under Review | 63611.34 | 2025-Q1
EXP-002753 | 2025-02-08 | BOQ-PKG-03-00763 | PKG-03 | INV-PKG-03-024-02753 | 15.27 | 152780.73 | 7639.04 | Paid | 145141.69 | 2025-Q1
EXP-002991 | 2025-02-08 | BOQ-PKG-01-01001 | PKG-01 | INV-PKG-01-017-02991 | 415.22 | 119130.65 | 5956.53 | Paid | 113174.12 | 2025-Q1
EXP-003429 | 2025-02-08 | BOQ-PKG-09-01439 | PKG-09 | INV-PKG-09-035-03429 | 109.28 | 122748.8 | 6137.44 | Approved Pending Payment | 116611.36 | 2025-Q1
EXP-004454 | 2025-02-08 | BOQ-PKG-04-00474 | PKG-04 | INV-PKG-04-010-04454 | 368.76 | 147818.39 | 7390.92 | Paid | 140427.47 | 2025-Q1
EXP-005614 | 2025-02-08 | BOQ-PKG-04-01634 | PKG-04 | INV-PKG-04-015-05614 | 321.08 | 198849.62 | 9942.48 | Paid | 188907.14 | 2025-Q1
EXP-005748 | 2025-02-08 | BOQ-PKG-08-01768 | PKG-08 | INV-PKG-08-009-05748 | 40.54 | 136972.61 | 6848.63 | Paid | 130123.98 | 2025-Q1
EXP-005750 | 2025-02-08 | BOQ-PKG-10-01770 | PKG-10 | INV-PKG-10-011-05750 | 270.42 | 131922.38 | 6596.12 | Paid | 125326.26 | 2025-Q1
EXP-006815 | 2025-02-08 | BOQ-PKG-05-00845 | PKG-05 | INV-PKG-05-026-06815 | 301.28 | 98101.15 | 4905.06 | Paid | 93196.09 | 2025-Q1
EXP-000531 | 2025-02-09 | BOQ-PKG-01-00531 | PKG-01 | INV-PKG-01-007-00531 | 66.59 | 148530.68 | 7426.53 | Paid | 141104.15 | 2025-Q1
EXP-001386 | 2025-02-09 | BOQ-PKG-06-01386 | PKG-06 | INV-PKG-06-022-01386 | 215.84 | 104049.62 | 5202.48 | Paid | 98847.14 | 2025-Q1
EXP-002715 | 2025-02-09 | BOQ-PKG-05-00725 | PKG-05 | INV-PKG-05-021-02715 | 52.98 | 99177.36 | 4958.87 | Under Review | 94218.49 | 2025-Q1
EXP-003684 | 2025-02-09 | BOQ-PKG-04-01694 | PKG-04 | INV-PKG-04-010-03684 | 401.2 | 26622.78 | 1331.14 | Paid | 25291.64 | 2025-Q1
EXP-004131 | 2025-02-09 | BOQ-PKG-01-00151 | PKG-01 | INV-PKG-01-002-04131 | 417.4 | 92662.68 | 4633.13 | Paid | 88029.55 | 2025-Q1
EXP-004841 | 2025-02-09 | BOQ-PKG-01-00861 | PKG-01 | INV-PKG-01-012-04841 | 405.25 | 186921.05 | 9346.05 | Paid | 177575 | 2025-Q1
EXP-005321 | 2025-02-09 | BOQ-PKG-01-01341 | PKG-01 | INV-PKG-01-002-05321 | 423.48 | 173193.61 | 8659.68 | Under Review | 164533.93 | 2025-Q1
EXP-001947 | 2025-02-10 | BOQ-PKG-07-01947 | PKG-07 | INV-PKG-07-023-01947 | 72.35 | 165519.2 | 8275.96 | Paid | 157243.24 | 2025-Q1
EXP-003153 | 2025-02-10 | BOQ-PKG-03-01163 | PKG-03 | INV-PKG-03-004-03153 | 171.3 | 123661.95 | 6183.1 | Under Review | 117478.85 | 2025-Q1
EXP-006716 | 2025-02-10 | BOQ-PKG-06-00746 | PKG-06 | INV-PKG-06-032-06716 | 136.33 | 36859.65 | 1842.98 | Paid | 35016.67 | 2025-Q1
EXP-001517 | 2025-02-11 | BOQ-PKG-07-01517 | PKG-07 | INV-PKG-07-013-01517 | 117.9 | 185342.04 | 9267.1 | Approved Pending Payment | 176074.94 | 2025-Q1
EXP-003207 | 2025-02-11 | BOQ-PKG-07-01217 | PKG-07 | INV-PKG-07-023-03207 | 19.62 | 48616.97 | 2430.85 | Paid | 46186.12 | 2025-Q1
EXP-004062 | 2025-02-11 | BOQ-PKG-02-00082 | PKG-02 | INV-PKG-02-003-04062 | 153.55 | 126529.14 | 6326.46 | Paid | 120202.68 | 2025-Q1
EXP-004237 | 2025-02-11 | BOQ-PKG-07-00257 | PKG-07 | INV-PKG-07-003-04237 | 307.71 | 95879.78 | 4793.99 | Paid | 91085.79 | 2025-Q1
EXP-004244 | 2025-02-11 | BOQ-PKG-04-00264 | PKG-04 | INV-PKG-04-010-04244 | 15.78 | 90832.16 | 4541.61 | Approved Pending Payment | 86290.55 | 2025-Q1
EXP-005167 | 2025-02-11 | BOQ-PKG-07-01187 | PKG-07 | INV-PKG-07-023-05167 | 100.74 | 188178.02 | 9408.9 | Paid | 178769.12 | 2025-Q1
EXP-005542 | 2025-02-11 | BOQ-PKG-02-01562 | PKG-02 | INV-PKG-02-013-05542 | 106.49 | 147897.24 | 7394.86 | Approved Pending Payment | 140502.38 | 2025-Q1
EXP-005611 | 2025-02-11 | BOQ-PKG-01-01631 | PKG-01 | INV-PKG-01-012-05611 | 436.62 | 140054.56 | 7002.73 | Approved Pending Payment | 133051.83 | 2025-Q1
EXP-006781 | 2025-02-11 | BOQ-PKG-01-00811 | PKG-01 | INV-PKG-01-027-06781 | 130.12 | 107954.72 | 5397.74 | Paid | 102556.98 | 2025-Q1
EXP-000548 | 2025-02-12 | BOQ-PKG-08-00548 | PKG-08 | INV-PKG-08-024-00548 | 44.76 | 103447.92 | 5172.4 | Paid | 98275.52 | 2025-Q1
EXP-002313 | 2025-02-12 | BOQ-PKG-03-00323 | PKG-03 | INV-PKG-03-004-02313 | 138.5 | 33630.72 | 1681.54 | Approved Pending Payment | 31949.18 | 2025-Q1
EXP-002465 | 2025-02-12 | BOQ-PKG-05-00475 | PKG-05 | INV-PKG-05-016-02465 | 285.8 | 94776.2 | 4738.81 | Paid | 90037.39 | 2025-Q1
EXP-003131 | 2025-02-12 | BOQ-PKG-01-01141 | PKG-01 | INV-PKG-01-017-03131 | 49.58 | 194181.77 | 9709.09 | Paid | 184472.68 | 2025-Q1
EXP-003889 | 2025-02-12 | BOQ-PKG-09-01899 | PKG-09 | INV-PKG-09-005-03889 | 37.03 | 105222.22 | 5261.11 | Approved Pending Payment | 99961.11 | 2025-Q1
EXP-005808 | 2025-02-12 | BOQ-PKG-08-01828 | PKG-08 | INV-PKG-08-034-05808 | 278.63 | 71664.21 | 3583.21 | Paid | 68081 | 2025-Q1
EXP-006427 | 2025-02-12 | BOQ-PKG-07-00457 | PKG-07 | INV-PKG-07-023-06427 | 411.61 | 144936.9 | 7246.84 | Paid | 137690.06 | 2025-Q1
EXP-006855 | 2025-02-12 | BOQ-PKG-05-00885 | PKG-05 | INV-PKG-05-031-06855 | 412.52 | 135837.48 | 6791.87 | Paid | 129045.61 | 2025-Q1
EXP-000587 | 2025-02-13 | BOQ-PKG-07-00587 | PKG-07 | INV-PKG-07-028-00587 | 440.14 | 60016.8 | 3000.84 | Paid | 57015.96 | 2025-Q1
EXP-003061 | 2025-02-13 | BOQ-PKG-01-01071 | PKG-01 | INV-PKG-01-017-03061 | 434.64 | 137258.18 | 6862.91 | Paid | 130395.27 | 2025-Q1
EXP-003623 | 2025-02-13 | BOQ-PKG-03-01633 | PKG-03 | INV-PKG-03-019-03623 | 356.22 | 101394.66 | 5069.73 | Under Review | 96324.93 | 2025-Q1
EXP-004164 | 2025-02-13 | BOQ-PKG-04-00184 | PKG-04 | INV-PKG-04-035-04164 | 400.93 | 210334.5 | 10516.72 | Under Review | 199817.78 | 2025-Q1
EXP-005920 | 2025-02-13 | BOQ-PKG-10-01940 | PKG-10 | INV-PKG-10-006-05920 | 308.08 | 137504.78 | 6875.24 | Paid | 130629.54 | 2025-Q1
EXP-000373 | 2025-02-14 | BOQ-PKG-03-00373 | PKG-03 | INV-PKG-03-024-00373 | 69.22 | 39838.62 | 1991.93 | Under Review | 37846.69 | 2025-Q1
EXP-001236 | 2025-02-14 | BOQ-PKG-06-01236 | PKG-06 | INV-PKG-06-012-01236 | 106.96 | 69328.98 | 3466.45 | Approved Pending Payment | 65862.53 | 2025-Q1
EXP-003156 | 2025-02-14 | BOQ-PKG-06-01166 | PKG-06 | INV-PKG-06-007-03156 | 99.36 | 122729.77 | 6136.49 | Paid | 116593.28 | 2025-Q1
EXP-003573 | 2025-02-14 | BOQ-PKG-03-01583 | PKG-03 | INV-PKG-03-004-03573 | 373.61 | 108986.01 | 5449.3 | Approved Pending Payment | 103536.71 | 2025-Q1
EXP-003651 | 2025-02-14 | BOQ-PKG-01-01661 | PKG-01 | INV-PKG-01-012-03651 | 165.56 | 59925.07 | 2996.25 | Paid | 56928.82 | 2025-Q1
EXP-004366 | 2025-02-14 | BOQ-PKG-06-00386 | PKG-06 | INV-PKG-06-027-04366 | 447.73 | 51877.9 | 2593.9 | Under Review | 49284 | 2025-Q1
EXP-006030 | 2025-02-14 | BOQ-PKG-10-00060 | PKG-10 | INV-PKG-10-011-06030 | 438.86 | 48139.39 | 2406.97 | Paid | 45732.42 | 2025-Q1
EXP-006078 | 2025-02-14 | BOQ-PKG-08-00108 | PKG-08 | INV-PKG-08-024-06078 | 120.54 | 47238.14 | 2361.91 | Under Review | 44876.23 | 2025-Q1
EXP-000409 | 2025-02-15 | BOQ-PKG-09-00409 | PKG-09 | INV-PKG-09-025-00409 | 384.71 | 178022.61 | 8901.13 | Paid | 169121.48 | 2025-Q1
EXP-000423 | 2025-02-15 | BOQ-PKG-03-00423 | PKG-03 | INV-PKG-03-004-00423 | 350.26 | 87618.44 | 4380.92 | Paid | 83237.52 | 2025-Q1
EXP-000536 | 2025-02-15 | BOQ-PKG-06-00536 | PKG-06 | INV-PKG-06-012-00536 | 116.78 | 81395.73 | 4069.79 | Paid | 77325.94 | 2025-Q1
EXP-000925 | 2025-02-15 | BOQ-PKG-05-00925 | PKG-05 | INV-PKG-05-016-00925 | 322.8 | 179743.43 | 8987.17 | Paid | 170756.26 | 2025-Q1
EXP-000927 | 2025-02-15 | BOQ-PKG-07-00927 | PKG-07 | INV-PKG-07-018-00927 | 410.4 | 202913.49 | 10145.67 | Paid | 192767.82 | 2025-Q1
EXP-001061 | 2025-02-15 | BOQ-PKG-01-01061 | PKG-01 | INV-PKG-01-012-01061 | 424.6 | 153534.37 | 7676.72 | Approved Pending Payment | 145857.65 | 2025-Q1
EXP-004210 | 2025-02-15 | BOQ-PKG-10-00230 | PKG-10 | INV-PKG-10-011-04210 | 203.11 | 187924.8 | 9396.24 | Paid | 178528.56 | 2025-Q1
EXP-004546 | 2025-02-15 | BOQ-PKG-06-00566 | PKG-06 | INV-PKG-06-032-04546 | 143.14 | 83067.29 | 4153.36 | Paid | 78913.93 | 2025-Q1
EXP-004897 | 2025-02-15 | BOQ-PKG-07-00917 | PKG-07 | INV-PKG-07-033-04897 | 185.54 | 38550.87 | 1927.54 | Under Review | 36623.33 | 2025-Q1
EXP-005104 | 2025-02-15 | BOQ-PKG-04-01124 | PKG-04 | INV-PKG-04-030-05104 | 132.64 | 87388.18 | 4369.41 | Paid | 83018.77 | 2025-Q1
EXP-005186 | 2025-02-15 | BOQ-PKG-06-01206 | PKG-06 | INV-PKG-06-007-05186 | 83.17 | 87532.99 | 4376.65 | Paid | 83156.34 | 2025-Q1
EXP-006410 | 2025-02-15 | BOQ-PKG-10-00440 | PKG-10 | INV-PKG-10-006-06410 | 433.59 | 129115.39 | 6455.77 | Paid | 122659.62 | 2025-Q1
EXP-006758 | 2025-02-15 | BOQ-PKG-08-00788 | PKG-08 | INV-PKG-08-004-06758 | 435.87 | 37218.9 | 1860.95 | Paid | 35357.95 | 2025-Q1
EXP-000147 | 2025-02-16 | BOQ-PKG-07-00147 | PKG-07 | INV-PKG-07-008-00147 | 208.82 | 73275.76 | 3663.79 | Paid | 69611.97 | 2025-Q1
EXP-001760 | 2025-02-16 | BOQ-PKG-10-01760 | PKG-10 | INV-PKG-10-011-01760 | 84.33 | 200578.5 | 10028.93 | Paid | 190549.57 | 2025-Q1
EXP-002011 | 2025-02-16 | BOQ-PKG-01-00021 | PKG-01 | INV-PKG-01-017-02011 | 367.58 | 185978.13 | 9298.91 | Paid | 176679.22 | 2025-Q1
EXP-003219 | 2025-02-16 | BOQ-PKG-09-01229 | PKG-09 | INV-PKG-09-035-03219 | 73.08 | 113254.04 | 5662.7 | Approved Pending Payment | 107591.34 | 2025-Q1
EXP-003754 | 2025-02-16 | BOQ-PKG-04-01764 | PKG-04 | INV-PKG-04-010-03754 | 399.75 | 69154.44 | 3457.72 | Paid | 65696.72 | 2025-Q1
EXP-004399 | 2025-02-16 | BOQ-PKG-09-00419 | PKG-09 | INV-PKG-09-025-04399 | 368.39 | 75505.45 | 3775.27 | Paid | 71730.18 | 2025-Q1
EXP-005317 | 2025-02-16 | BOQ-PKG-07-01337 | PKG-07 | INV-PKG-07-033-05317 | 51.12 | 109225.25 | 5461.26 | Paid | 103763.99 | 2025-Q1
EXP-006943 | 2025-02-16 | BOQ-PKG-03-00973 | PKG-03 | INV-PKG-03-014-06943 | 251.87 | 187977.54 | 9398.88 | Paid | 178578.66 | 2025-Q1
EXP-006960 | 2025-02-16 | BOQ-PKG-10-00990 | PKG-10 | INV-PKG-10-031-06960 | 358.47 | 116029.51 | 5801.48 | Paid | 110228.03 | 2025-Q1
EXP-000095 | 2025-02-17 | BOQ-PKG-05-00095 | PKG-05 | INV-PKG-05-026-00095 | 262.37 | 183670.65 | 9183.53 | Under Review | 174487.12 | 2025-Q1
EXP-002043 | 2025-02-17 | BOQ-PKG-03-00053 | PKG-03 | INV-PKG-03-014-02043 | 32.21 | 118131.63 | 5906.58 | Paid | 112225.05 | 2025-Q1
EXP-004282 | 2025-02-17 | BOQ-PKG-02-00302 | PKG-02 | INV-PKG-02-013-04282 | 294.99 | 116033.07 | 5801.65 | Approved Pending Payment | 110231.42 | 2025-Q1
EXP-004389 | 2025-02-17 | BOQ-PKG-09-00409 | PKG-09 | INV-PKG-09-015-04389 | 409.75 | 65529.55 | 3276.48 | Paid | 62253.07 | 2025-Q1
EXP-004609 | 2025-02-17 | BOQ-PKG-09-00629 | PKG-09 | INV-PKG-09-025-04609 | 330.93 | 77720.8 | 3886.04 | Paid | 73834.76 | 2025-Q1
EXP-000776 | 2025-02-18 | BOQ-PKG-06-00776 | PKG-06 | INV-PKG-06-007-00776 | 187.68 | 65221.06 | 3261.05 | Paid | 61960.01 | 2025-Q1
EXP-003705 | 2025-02-18 | BOQ-PKG-05-01715 | PKG-05 | INV-PKG-05-031-03705 | 53.74 | 72258.65 | 3612.93 | Paid | 68645.72 | 2025-Q1
EXP-004146 | 2025-02-18 | BOQ-PKG-06-00166 | PKG-06 | INV-PKG-06-017-04146 | 330.07 | 160789.87 | 8039.49 | Approved Pending Payment | 152750.38 | 2025-Q1
EXP-004470 | 2025-02-18 | BOQ-PKG-10-00490 | PKG-10 | INV-PKG-10-026-04470 | 155.89 | 133617.69 | 6680.88 | Paid | 126936.81 | 2025-Q1
EXP-005743 | 2025-02-18 | BOQ-PKG-03-01763 | PKG-03 | INV-PKG-03-004-05743 | 417.04 | 214634.69 | 10731.73 | Paid | 203902.96 | 2025-Q1
EXP-000146 | 2025-02-19 | BOQ-PKG-06-00146 | PKG-06 | INV-PKG-06-007-00146 | 354.35 | 61996.63 | 3099.83 | Paid | 58896.8 | 2025-Q1
EXP-001181 | 2025-02-19 | BOQ-PKG-01-01181 | PKG-01 | INV-PKG-01-027-01181 | 256.76 | 95320.72 | 4766.04 | Paid | 90554.68 | 2025-Q1
EXP-003088 | 2025-02-19 | BOQ-PKG-08-01098 | PKG-08 | INV-PKG-08-009-03088 | 131.48 | 187986.46 | 9399.32 | Paid | 178587.14 | 2025-Q1
EXP-003849 | 2025-02-19 | BOQ-PKG-09-01859 | PKG-09 | INV-PKG-09-035-03849 | 157.06 | 40606.55 | 2030.33 | Paid | 38576.22 | 2025-Q1
EXP-004273 | 2025-02-19 | BOQ-PKG-03-00293 | PKG-03 | INV-PKG-03-004-04273 | 364.8 | 97420.81 | 4871.04 | Paid | 92549.77 | 2025-Q1
EXP-005956 | 2025-02-19 | BOQ-PKG-06-01976 | PKG-06 | INV-PKG-06-007-05956 | 445.57 | 91916.61 | 4595.83 | Approved Pending Payment | 87320.78 | 2025-Q1
EXP-000191 | 2025-02-20 | BOQ-PKG-01-00191 | PKG-01 | INV-PKG-01-017-00191 | 157.25 | 202592.11 | 10129.61 | Paid | 192462.5 | 2025-Q1
EXP-000687 | 2025-02-20 | BOQ-PKG-07-00687 | PKG-07 | INV-PKG-07-023-00687 | 203.78 | 73208.1 | 3660.41 | Paid | 69547.69 | 2025-Q1
EXP-001450 | 2025-02-20 | BOQ-PKG-10-01450 | PKG-10 | INV-PKG-10-016-01450 | 317.67 | 196316.28 | 9815.81 | Paid | 186500.47 | 2025-Q1
EXP-001514 | 2025-02-20 | BOQ-PKG-04-01514 | PKG-04 | INV-PKG-04-010-01514 | 231.6 | 201146.88 | 10057.34 | Under Review | 191089.54 | 2025-Q1
EXP-002540 | 2025-02-20 | BOQ-PKG-10-00550 | PKG-10 | INV-PKG-10-021-02540 | 280.08 | 84484.25 | 4224.21 | Paid | 80260.04 | 2025-Q1
EXP-003250 | 2025-02-20 | BOQ-PKG-10-01260 | PKG-10 | INV-PKG-10-031-03250 | 106.49 | 37116.93 | 1855.85 | Disputed | 35261.08 | 2025-Q1
EXP-004342 | 2025-02-20 | BOQ-PKG-02-00362 | PKG-02 | INV-PKG-02-003-04342 | 296.66 | 72304.69 | 3615.23 | Paid | 68689.46 | 2025-Q1
EXP-005145 | 2025-02-20 | BOQ-PKG-05-01165 | PKG-05 | INV-PKG-05-001-05145 | 282.32 | 101590.29 | 5079.51 | Paid | 96510.78 | 2025-Q1
EXP-005431 | 2025-02-20 | BOQ-PKG-01-01451 | PKG-01 | INV-PKG-01-007-05431 | 432.49 | 66287.08 | 3314.35 | Paid | 62972.73 | 2025-Q1
EXP-005993 | 2025-02-20 | BOQ-PKG-03-00023 | PKG-03 | INV-PKG-03-009-05993 | 385.37 | 119561.56 | 5978.08 | Paid | 113583.48 | 2025-Q1
EXP-006152 | 2025-02-20 | BOQ-PKG-02-00182 | PKG-02 | INV-PKG-02-028-06152 | 8.02 | 49148.48 | 2457.42 | Paid | 46691.06 | 2025-Q1
EXP-006590 | 2025-02-20 | BOQ-PKG-10-00620 | PKG-10 | INV-PKG-10-011-06590 | 436.95 | 117576.76 | 5878.84 | Paid | 111697.92 | 2025-Q1
EXP-000488 | 2025-02-21 | BOQ-PKG-08-00488 | PKG-08 | INV-PKG-08-034-00488 | 176.57 | 198855.04 | 9942.75 | Paid | 188912.29 | 2025-Q1
EXP-000905 | 2025-02-21 | BOQ-PKG-05-00905 | PKG-05 | INV-PKG-05-031-00905 | 142.65 | 79159.27 | 3957.96 | Paid | 75201.31 | 2025-Q1
EXP-002004 | 2025-02-21 | BOQ-PKG-04-00014 | PKG-04 | INV-PKG-04-010-02004 | 412.48 | 115982.37 | 5799.12 | Approved Pending Payment | 110183.25 | 2025-Q1
EXP-004480 | 2025-02-21 | BOQ-PKG-10-00500 | PKG-10 | INV-PKG-10-001-04480 | 340.76 | 187607.1 | 9380.36 | Paid | 178226.74 | 2025-Q1
EXP-004965 | 2025-02-21 | BOQ-PKG-05-00985 | PKG-05 | INV-PKG-05-031-04965 | 165.21 | 173209.64 | 8660.48 | Under Review | 164549.16 | 2025-Q1
EXP-005095 | 2025-02-21 | BOQ-PKG-05-01115 | PKG-05 | INV-PKG-05-021-05095 | 267.84 | 74396.87 | 3719.84 | Paid | 70677.03 | 2025-Q1
EXP-005199 | 2025-02-21 | BOQ-PKG-09-01219 | PKG-09 | INV-PKG-09-020-05199 | 379.81 | 74306.05 | 3715.3 | Paid | 70590.75 | 2025-Q1
EXP-005994 | 2025-02-21 | BOQ-PKG-04-00024 | PKG-04 | INV-PKG-04-010-05994 | 120.66 | 76100.6 | 3805.03 | Paid | 72295.57 | 2025-Q1
EXP-006749 | 2025-02-21 | BOQ-PKG-09-00779 | PKG-09 | INV-PKG-09-030-06749 | 194.19 | 65128.4 | 3256.42 | Paid | 61871.98 | 2025-Q1
EXP-000239 | 2025-02-22 | BOQ-PKG-09-00239 | PKG-09 | INV-PKG-09-030-00239 | 256.61 | 26844.18 | 1342.21 | Paid | 25501.97 | 2025-Q1
EXP-001481 | 2025-02-22 | BOQ-PKG-01-01481 | PKG-01 | INV-PKG-01-012-01481 | 341.2 | 138934.8 | 6946.74 | Paid | 131988.06 | 2025-Q1
EXP-002893 | 2025-02-22 | BOQ-PKG-03-00903 | PKG-03 | INV-PKG-03-024-02893 | 73.47 | 202079.14 | 10103.96 | Paid | 191975.18 | 2025-Q1
EXP-003866 | 2025-02-22 | BOQ-PKG-06-01876 | PKG-06 | INV-PKG-06-017-03866 | 444.68 | 52449.31 | 2622.47 | Paid | 49826.84 | 2025-Q1
EXP-004829 | 2025-02-22 | BOQ-PKG-09-00849 | PKG-09 | INV-PKG-09-035-04829 | 381.05 | 154519.48 | 7725.97 | Paid | 146793.51 | 2025-Q1
EXP-006282 | 2025-02-22 | BOQ-PKG-02-00312 | PKG-02 | INV-PKG-02-018-06282 | 5.99 | 118204.73 | 5910.24 | Approved Pending Payment | 112294.49 | 2025-Q1
EXP-001355 | 2025-02-23 | BOQ-PKG-05-01355 | PKG-05 | INV-PKG-05-026-01355 | 274.76 | 129597.41 | 6479.87 | Paid | 123117.54 | 2025-Q1
EXP-001849 | 2025-02-23 | BOQ-PKG-09-01849 | PKG-09 | INV-PKG-09-030-01849 | 441.95 | 175603.13 | 8780.16 | Paid | 166822.97 | 2025-Q1
EXP-002582 | 2025-02-23 | BOQ-PKG-02-00592 | PKG-02 | INV-PKG-02-028-02582 | 437.86 | 126055.43 | 6302.77 | Paid | 119752.66 | 2025-Q1
EXP-003146 | 2025-02-23 | BOQ-PKG-06-01156 | PKG-06 | INV-PKG-06-032-03146 | 179.32 | 106949.91 | 5347.5 | Paid | 101602.41 | 2025-Q1
EXP-003218 | 2025-02-23 | BOQ-PKG-08-01228 | PKG-08 | INV-PKG-08-034-03218 | 135.57 | 142424.43 | 7121.22 | Paid | 135303.21 | 2025-Q1
EXP-003286 | 2025-02-23 | BOQ-PKG-06-01296 | PKG-06 | INV-PKG-06-032-03286 | 413.81 | 133686.19 | 6684.31 | Paid | 127001.88 | 2025-Q1
EXP-003940 | 2025-02-23 | BOQ-PKG-10-01950 | PKG-10 | INV-PKG-10-021-03940 | 132.6 | 116273.04 | 5813.65 | Paid | 110459.39 | 2025-Q1
EXP-004013 | 2025-02-23 | BOQ-PKG-03-00033 | PKG-03 | INV-PKG-03-024-04013 | 163.63 | 210795.03 | 10539.75 | Paid | 200255.28 | 2025-Q1
EXP-000014 | 2025-02-24 | BOQ-PKG-04-00014 | PKG-04 | INV-PKG-04-015-00014 | 151.98 | 132836.86 | 6641.84 | Paid | 126195.02 | 2025-Q1
EXP-000943 | 2025-02-24 | BOQ-PKG-03-00943 | PKG-03 | INV-PKG-03-034-00943 | 297.94 | 70396 | 3519.8 | Paid | 66876.2 | 2025-Q1
EXP-001312 | 2025-02-24 | BOQ-PKG-02-01312 | PKG-02 | INV-PKG-02-018-01312 | 152.13 | 41001.34 | 2050.07 | Paid | 38951.27 | 2025-Q1
EXP-001618 | 2025-02-24 | BOQ-PKG-08-01618 | PKG-08 | INV-PKG-08-009-01618 | 152.47 | 212276.56 | 10613.83 | Paid | 201662.73 | 2025-Q1
EXP-001663 | 2025-02-24 | BOQ-PKG-03-01663 | PKG-03 | INV-PKG-03-019-01663 | 187.6 | 207989.11 | 10399.46 | Paid | 197589.65 | 2025-Q1
EXP-001813 | 2025-02-24 | BOQ-PKG-03-01813 | PKG-03 | INV-PKG-03-029-01813 | 290.3 | 207354.55 | 10367.73 | Paid | 196986.82 | 2025-Q1
EXP-002076 | 2025-02-24 | BOQ-PKG-06-00086 | PKG-06 | INV-PKG-06-012-02076 | 442.55 | 87850.86 | 4392.54 | Approved Pending Payment | 83458.32 | 2025-Q1
EXP-002284 | 2025-02-24 | BOQ-PKG-04-00294 | PKG-04 | INV-PKG-04-010-02284 | 167.45 | 174123.44 | 8706.17 | Paid | 165417.27 | 2025-Q1
EXP-002329 | 2025-02-24 | BOQ-PKG-09-00339 | PKG-09 | INV-PKG-09-020-02329 | 379.95 | 177490.46 | 8874.52 | Paid | 168615.94 | 2025-Q1
EXP-002331 | 2025-02-24 | BOQ-PKG-01-00341 | PKG-01 | INV-PKG-01-022-02331 | 211.8 | 209349.21 | 10467.46 | Paid | 198881.75 | 2025-Q1
EXP-002639 | 2025-02-24 | BOQ-PKG-09-00649 | PKG-09 | INV-PKG-09-015-02639 | 111.08 | 24117.11 | 1205.86 | Paid | 22911.25 | 2025-Q1
EXP-003140 | 2025-02-24 | BOQ-PKG-10-01150 | PKG-10 | INV-PKG-10-026-03140 | 314.67 | 119563.88 | 5978.19 | Under Review | 113585.69 | 2025-Q1
EXP-004140 | 2025-02-24 | BOQ-PKG-10-00160 | PKG-10 | INV-PKG-10-011-04140 | 220.62 | 155453.12 | 7772.66 | Approved Pending Payment | 147680.46 | 2025-Q1
EXP-004433 | 2025-02-24 | BOQ-PKG-03-00453 | PKG-03 | INV-PKG-03-024-04433 | 111.16 | 170511.91 | 8525.6 | Paid | 161986.31 | 2025-Q1
EXP-004868 | 2025-02-24 | BOQ-PKG-08-00888 | PKG-08 | INV-PKG-08-004-04868 | 306.17 | 118115.81 | 5905.79 | Paid | 112210.02 | 2025-Q1
EXP-004934 | 2025-02-24 | BOQ-PKG-04-00954 | PKG-04 | INV-PKG-04-035-04934 | 378.86 | 125589.92 | 6279.5 | Paid | 119310.42 | 2025-Q1
EXP-005412 | 2025-02-24 | BOQ-PKG-02-01432 | PKG-02 | INV-PKG-02-023-05412 | 248.25 | 92466.17 | 4623.31 | Paid | 87842.86 | 2025-Q1
EXP-005854 | 2025-02-24 | BOQ-PKG-04-01874 | PKG-04 | INV-PKG-04-010-05854 | 433.99 | 149105.23 | 7455.26 | Paid | 141649.97 | 2025-Q1
EXP-001041 | 2025-02-25 | BOQ-PKG-01-01041 | PKG-01 | INV-PKG-01-027-01041 | 186.51 | 45836.31 | 2291.82 | Paid | 43544.49 | 2025-Q1
EXP-001918 | 2025-02-25 | BOQ-PKG-08-01918 | PKG-08 | INV-PKG-08-029-01918 | 105.91 | 112928.3 | 5646.42 | Approved Pending Payment | 107281.88 | 2025-Q1
EXP-005935 | 2025-02-25 | BOQ-PKG-05-01955 | PKG-05 | INV-PKG-05-021-05935 | 72.47 | 105793.36 | 5289.67 | Paid | 100503.69 | 2025-Q1
EXP-000110 | 2025-02-26 | BOQ-PKG-10-00110 | PKG-10 | INV-PKG-10-006-00110 | 338.69 | 195512.06 | 9775.6 | Paid | 185736.46 | 2025-Q1
EXP-001635 | 2025-02-26 | BOQ-PKG-05-01635 | PKG-05 | INV-PKG-05-026-01635 | 221.91 | 50384.1 | 2519.2 | Paid | 47864.9 | 2025-Q1
EXP-004555 | 2025-02-26 | BOQ-PKG-05-00575 | PKG-05 | INV-PKG-05-006-04555 | 246.06 | 87318.66 | 4365.93 | Paid | 82952.73 | 2025-Q1
EXP-004830 | 2025-02-26 | BOQ-PKG-10-00850 | PKG-10 | INV-PKG-10-001-04830 | 7.93 | 169568.76 | 8478.44 | Paid | 161090.32 | 2025-Q1
EXP-006694 | 2025-02-26 | BOQ-PKG-04-00724 | PKG-04 | INV-PKG-04-010-06694 | 360.26 | 85219.65 | 4260.98 | Paid | 80958.67 | 2025-Q1
EXP-000681 | 2025-02-27 | BOQ-PKG-01-00681 | PKG-01 | INV-PKG-01-017-00681 | 82.78 | 209238.87 | 10461.94 | Paid | 198776.93 | 2025-Q1
EXP-003094 | 2025-02-27 | BOQ-PKG-04-01104 | PKG-04 | INV-PKG-04-015-03094 | 418.02 | 118434.29 | 5921.71 | Paid | 112512.58 | 2025-Q1
EXP-003971 | 2025-02-27 | BOQ-PKG-01-01981 | PKG-01 | INV-PKG-01-017-03971 | 34.91 | 106083.71 | 5304.19 | Paid | 100779.52 | 2025-Q1
EXP-004006 | 2025-02-27 | BOQ-PKG-06-00026 | PKG-06 | INV-PKG-06-017-04006 | 278.08 | 106506.87 | 5325.34 | Paid | 101181.53 | 2025-Q1
EXP-004477 | 2025-02-27 | BOQ-PKG-07-00497 | PKG-07 | INV-PKG-07-033-04477 | 228.97 | 164034.7 | 8201.74 | Paid | 155832.96 | 2025-Q1
EXP-004683 | 2025-02-27 | BOQ-PKG-03-00703 | PKG-03 | INV-PKG-03-029-04683 | 393.38 | 186401.27 | 9320.06 | Paid | 177081.21 | 2025-Q1
EXP-006896 | 2025-02-27 | BOQ-PKG-06-00926 | PKG-06 | INV-PKG-06-002-06896 | 259.7 | 85226.57 | 4261.33 | Paid | 80965.24 | 2025-Q1
EXP-001306 | 2025-02-28 | BOQ-PKG-06-01306 | PKG-06 | INV-PKG-06-012-01306 | 206.58 | 121696.46 | 6084.82 | Paid | 115611.64 | 2025-Q1
EXP-001669 | 2025-02-28 | BOQ-PKG-09-01669 | PKG-09 | INV-PKG-09-025-01669 | 436.36 | 50480.77 | 2524.04 | Paid | 47956.73 | 2025-Q1
EXP-002057 | 2025-02-28 | BOQ-PKG-07-00067 | PKG-07 | INV-PKG-07-028-02057 | 373.6 | 115228.46 | 5761.42 | Approved Pending Payment | 109467.04 | 2025-Q1
EXP-002346 | 2025-02-28 | BOQ-PKG-06-00356 | PKG-06 | INV-PKG-06-002-02346 | 191.28 | 32432.69 | 1621.63 | Paid | 30811.06 | 2025-Q1
EXP-002836 | 2025-02-28 | BOQ-PKG-06-00846 | PKG-06 | INV-PKG-06-002-02836 | 322.68 | 26006.81 | 1300.34 | Approved Pending Payment | 24706.47 | 2025-Q1
EXP-003186 | 2025-02-28 | BOQ-PKG-06-01196 | PKG-06 | INV-PKG-06-002-03186 | 147.78 | 160381.31 | 8019.07 | Approved Pending Payment | 152362.24 | 2025-Q1
EXP-003667 | 2025-02-28 | BOQ-PKG-07-01677 | PKG-07 | INV-PKG-07-028-03667 | 284.48 | 46906.34 | 2345.32 | Disputed | 44561.02 | 2025-Q1
EXP-004044 | 2025-02-28 | BOQ-PKG-04-00064 | PKG-04 | INV-PKG-04-020-04044 | 301.1 | 118844.44 | 5942.22 | Under Review | 112902.22 | 2025-Q1
EXP-005047 | 2025-02-28 | BOQ-PKG-07-01067 | PKG-07 | INV-PKG-07-008-05047 | 431.39 | 197633.15 | 9881.66 | Paid | 187751.49 | 2025-Q1
EXP-005318 | 2025-02-28 | BOQ-PKG-08-01338 | PKG-08 | INV-PKG-08-034-05318 | 432.63 | 30071.83 | 1503.59 | Approved Pending Payment | 28568.24 | 2025-Q1
EXP-006388 | 2025-02-28 | BOQ-PKG-08-00418 | PKG-08 | INV-PKG-08-019-06388 | 56.39 | 52753.03 | 2637.65 | Paid | 50115.38 | 2025-Q1
EXP-001023 | 2025-03-01 | BOQ-PKG-03-01023 | PKG-03 | INV-PKG-03-009-01023 | 36.61 | 116851.7 | 5842.58 | Paid | 111009.12 | 2025-Q1
EXP-001465 | 2025-03-01 | BOQ-PKG-05-01465 | PKG-05 | INV-PKG-05-031-01465 | 92.96 | 122546.49 | 6127.32 | Paid | 116419.17 | 2025-Q1
EXP-001708 | 2025-03-01 | BOQ-PKG-08-01708 | PKG-08 | INV-PKG-08-029-01708 | 213.3 | 206884.95 | 10344.25 | Paid | 196540.7 | 2025-Q1
EXP-002042 | 2025-03-01 | BOQ-PKG-02-00052 | PKG-02 | INV-PKG-02-013-02042 | 209.22 | 201695.98 | 10084.8 | Paid | 191611.18 | 2025-Q1
EXP-002504 | 2025-03-01 | BOQ-PKG-04-00514 | PKG-04 | INV-PKG-04-020-02504 | 155.46 | 46084.14 | 2304.21 | Under Review | 43779.93 | 2025-Q1
EXP-002665 | 2025-03-01 | BOQ-PKG-05-00675 | PKG-05 | INV-PKG-05-006-02665 | 248.58 | 34385.44 | 1719.27 | Approved Pending Payment | 32666.17 | 2025-Q1
EXP-002752 | 2025-03-01 | BOQ-PKG-02-00762 | PKG-02 | INV-PKG-02-023-02752 | 307.35 | 106770.53 | 5338.53 | Paid | 101432 | 2025-Q1
EXP-003305 | 2025-03-01 | BOQ-PKG-05-01315 | PKG-05 | INV-PKG-05-016-03305 | 222.37 | 35943.3 | 1797.17 | Paid | 34146.13 | 2025-Q1
EXP-006343 | 2025-03-01 | BOQ-PKG-03-00373 | PKG-03 | INV-PKG-03-009-06343 | 193.06 | 142822.32 | 7141.12 | Paid | 135681.2 | 2025-Q1
EXP-006807 | 2025-03-01 | BOQ-PKG-07-00837 | PKG-07 | INV-PKG-07-018-06807 | 171.74 | 133546.38 | 6677.32 | Paid | 126869.06 | 2025-Q1
EXP-000580 | 2025-03-02 | BOQ-PKG-10-00580 | PKG-10 | INV-PKG-10-021-00580 | 90.81 | 60874.42 | 3043.72 | Paid | 57830.7 | 2025-Q1
EXP-000937 | 2025-03-02 | BOQ-PKG-07-00937 | PKG-07 | INV-PKG-07-028-00937 | 188.38 | 30581.89 | 1529.09 | Paid | 29052.8 | 2025-Q1
EXP-001274 | 2025-03-02 | BOQ-PKG-04-01274 | PKG-04 | INV-PKG-04-015-01274 | 222.2 | 197423.01 | 9871.15 | Paid | 187551.86 | 2025-Q1
EXP-002154 | 2025-03-02 | BOQ-PKG-04-00164 | PKG-04 | INV-PKG-04-020-02154 | 208.5 | 122888.1 | 6144.41 | Disputed | 116743.69 | 2025-Q1
EXP-002172 | 2025-03-02 | BOQ-PKG-02-00182 | PKG-02 | INV-PKG-02-003-02172 | 190.89 | 161652.55 | 8082.63 | Paid | 153569.92 | 2025-Q1
EXP-003790 | 2025-03-02 | BOQ-PKG-10-01800 | PKG-10 | INV-PKG-10-011-03790 | 80.32 | 118075.82 | 5903.79 | Paid | 112172.03 | 2025-Q1
EXP-003914 | 2025-03-02 | BOQ-PKG-04-01924 | PKG-04 | INV-PKG-04-030-03914 | 260.13 | 212318.44 | 10615.92 | Paid | 201702.52 | 2025-Q1
EXP-004307 | 2025-03-02 | BOQ-PKG-07-00327 | PKG-07 | INV-PKG-07-003-04307 | 156.83 | 139542.81 | 6977.14 | Paid | 132565.67 | 2025-Q1
EXP-004495 | 2025-03-02 | BOQ-PKG-05-00515 | PKG-05 | INV-PKG-05-016-04495 | 91.69 | 192163.91 | 9608.2 | Approved Pending Payment | 182555.71 | 2025-Q1
EXP-006204 | 2025-03-02 | BOQ-PKG-04-00234 | PKG-04 | INV-PKG-04-010-06204 | 211.29 | 127331.59 | 6366.58 | Under Review | 120965.01 | 2025-Q1
EXP-006962 | 2025-03-02 | BOQ-PKG-02-00992 | PKG-02 | INV-PKG-02-033-06962 | 407.19 | 207531.38 | 10376.57 | Paid | 197154.81 | 2025-Q1
EXP-000819 | 2025-03-03 | BOQ-PKG-09-00819 | PKG-09 | INV-PKG-09-015-00819 | 189.61 | 163086.51 | 8154.33 | Approved Pending Payment | 154932.18 | 2025-Q1
EXP-001300 | 2025-03-03 | BOQ-PKG-10-01300 | PKG-10 | INV-PKG-10-006-01300 | 136.12 | 33243.4 | 1662.17 | Paid | 31581.23 | 2025-Q1
EXP-001315 | 2025-03-03 | BOQ-PKG-05-01315 | PKG-05 | INV-PKG-05-021-01315 | 183.84 | 132289.94 | 6614.5 | Approved Pending Payment | 125675.44 | 2025-Q1
EXP-001780 | 2025-03-03 | BOQ-PKG-10-01780 | PKG-10 | INV-PKG-10-031-01780 | 282.35 | 148885.51 | 7444.28 | Paid | 141441.23 | 2025-Q1
EXP-003779 | 2025-03-03 | BOQ-PKG-09-01789 | PKG-09 | INV-PKG-09-035-03779 | 276.19 | 152458.18 | 7622.91 | Approved Pending Payment | 144835.27 | 2025-Q1
EXP-005207 | 2025-03-03 | BOQ-PKG-07-01227 | PKG-07 | INV-PKG-07-028-05207 | 403.55 | 204747.3 | 10237.36 | Paid | 194509.94 | 2025-Q1
EXP-005801 | 2025-03-03 | BOQ-PKG-01-01821 | PKG-01 | INV-PKG-01-027-05801 | 30.84 | 185988.01 | 9299.4 | Paid | 176688.61 | 2025-Q1
EXP-006090 | 2025-03-03 | BOQ-PKG-10-00120 | PKG-10 | INV-PKG-10-001-06090 | 109.99 | 167461.51 | 8373.08 | Paid | 159088.43 | 2025-Q1
EXP-006557 | 2025-03-03 | BOQ-PKG-07-00587 | PKG-07 | INV-PKG-07-013-06557 | 179.2 | 55460.61 | 2773.03 | Under Review | 52687.58 | 2025-Q1
EXP-006844 | 2025-03-03 | BOQ-PKG-04-00874 | PKG-04 | INV-PKG-04-020-06844 | 155.17 | 98384 | 4919.2 | Paid | 93464.8 | 2025-Q1
EXP-000600 | 2025-03-04 | BOQ-PKG-10-00600 | PKG-10 | INV-PKG-10-006-00600 | 338.16 | 182314.34 | 9115.72 | Paid | 173198.62 | 2025-Q1
EXP-001874 | 2025-03-04 | BOQ-PKG-04-01874 | PKG-04 | INV-PKG-04-020-01874 | 245.28 | 60498.9 | 3024.94 | Paid | 57473.96 | 2025-Q1
EXP-002362 | 2025-03-04 | BOQ-PKG-02-00372 | PKG-02 | INV-PKG-02-018-02362 | 116.49 | 85310.66 | 4265.53 | Under Review | 81045.13 | 2025-Q1
EXP-002393 | 2025-03-04 | BOQ-PKG-03-00403 | PKG-03 | INV-PKG-03-014-02393 | 126.84 | 130218.58 | 6510.93 | Paid | 123707.65 | 2025-Q1
EXP-003284 | 2025-03-04 | BOQ-PKG-04-01294 | PKG-04 | INV-PKG-04-030-03284 | 57.32 | 104467.95 | 5223.4 | Paid | 99244.55 | 2025-Q1
EXP-003582 | 2025-03-04 | BOQ-PKG-02-01592 | PKG-02 | INV-PKG-02-013-03582 | 296.37 | 159088.6 | 7954.43 | Paid | 151134.17 | 2025-Q1
EXP-004138 | 2025-03-04 | BOQ-PKG-08-00158 | PKG-08 | INV-PKG-08-009-04138 | 227.5 | 152557.03 | 7627.85 | Under Review | 144929.18 | 2025-Q1
EXP-004401 | 2025-03-04 | BOQ-PKG-01-00421 | PKG-01 | INV-PKG-01-027-04401 | 177.01 | 61943.8 | 3097.19 | Under Review | 58846.61 | 2025-Q1
EXP-006878 | 2025-03-04 | BOQ-PKG-08-00908 | PKG-08 | INV-PKG-08-019-06878 | 418.3 | 80998.79 | 4049.94 | Paid | 76948.85 | 2025-Q1
EXP-006921 | 2025-03-04 | BOQ-PKG-01-00951 | PKG-01 | INV-PKG-01-027-06921 | 212.89 | 165633.53 | 8281.68 | Paid | 157351.85 | 2025-Q1
EXP-003451 | 2025-03-05 | BOQ-PKG-01-01461 | PKG-01 | INV-PKG-01-022-03451 | 47.05 | 165975.1 | 8298.76 | Approved Pending Payment | 157676.34 | 2025-Q1
EXP-006252 | 2025-03-05 | BOQ-PKG-02-00282 | PKG-02 | INV-PKG-02-023-06252 | 341.33 | 52739.69 | 2636.98 | Approved Pending Payment | 50102.71 | 2025-Q1
EXP-000224 | 2025-03-06 | BOQ-PKG-04-00224 | PKG-04 | INV-PKG-04-015-00224 | 380.58 | 72485.19 | 3624.26 | Paid | 68860.93 | 2025-Q1
EXP-002986 | 2025-03-06 | BOQ-PKG-06-00996 | PKG-06 | INV-PKG-06-012-02986 | 370.19 | 169762.49 | 8488.12 | Paid | 161274.37 | 2025-Q1
EXP-003217 | 2025-03-06 | BOQ-PKG-07-01227 | PKG-07 | INV-PKG-07-033-03217 | 260.1 | 166642.17 | 8332.11 | Under Review | 158310.06 | 2025-Q1
EXP-003417 | 2025-03-06 | BOQ-PKG-07-01427 | PKG-07 | INV-PKG-07-023-03417 | 214.33 | 75264.1 | 3763.21 | Paid | 71500.89 | 2025-Q1
EXP-004465 | 2025-03-06 | BOQ-PKG-05-00485 | PKG-05 | INV-PKG-05-021-04465 | 387.7 | 27723.46 | 1386.17 | Paid | 26337.29 | 2025-Q1
EXP-004780 | 2025-03-06 | BOQ-PKG-10-00800 | PKG-10 | INV-PKG-10-021-04780 | 449.86 | 116792.71 | 5839.64 | Paid | 110953.07 | 2025-Q1
EXP-004885 | 2025-03-06 | BOQ-PKG-05-00905 | PKG-05 | INV-PKG-05-021-04885 | 255.68 | 77681.52 | 3884.08 | Paid | 73797.44 | 2025-Q1
EXP-002436 | 2025-03-07 | BOQ-PKG-06-00446 | PKG-06 | INV-PKG-06-022-02436 | 139.48 | 35775.15 | 1788.76 | Paid | 33986.39 | 2025-Q1
EXP-002457 | 2025-03-07 | BOQ-PKG-07-00467 | PKG-07 | INV-PKG-07-008-02457 | 355.12 | 197889.35 | 9894.47 | Paid | 187994.88 | 2025-Q1
EXP-002838 | 2025-03-07 | BOQ-PKG-08-00848 | PKG-08 | INV-PKG-08-004-02838 | 442.7 | 127159.51 | 6357.98 | Paid | 120801.53 | 2025-Q1
EXP-003588 | 2025-03-07 | BOQ-PKG-08-01598 | PKG-08 | INV-PKG-08-019-03588 | 330.42 | 200966.42 | 10048.32 | Paid | 190918.1 | 2025-Q1
EXP-004162 | 2025-03-07 | BOQ-PKG-02-00182 | PKG-02 | INV-PKG-02-033-04162 | 203.53 | 166779.34 | 8338.97 | Paid | 158440.37 | 2025-Q1
EXP-004376 | 2025-03-07 | BOQ-PKG-06-00396 | PKG-06 | INV-PKG-06-002-04376 | 243.06 | 100742.85 | 5037.14 | Approved Pending Payment | 95705.71 | 2025-Q1
EXP-004983 | 2025-03-07 | BOQ-PKG-03-01003 | PKG-03 | INV-PKG-03-014-04983 | 338.48 | 142540.62 | 7127.03 | Paid | 135413.59 | 2025-Q1
EXP-006887 | 2025-03-07 | BOQ-PKG-07-00917 | PKG-07 | INV-PKG-07-028-06887 | 7.37 | 114304.61 | 5715.23 | Paid | 108589.38 | 2025-Q1
EXP-001112 | 2025-03-08 | BOQ-PKG-02-01112 | PKG-02 | INV-PKG-02-028-01112 | 287.24 | 162387.33 | 8119.37 | Paid | 154267.96 | 2025-Q1
EXP-002454 | 2025-03-08 | BOQ-PKG-04-00464 | PKG-04 | INV-PKG-04-005-02454 | 178.6 | 151745.28 | 7587.26 | Paid | 144158.02 | 2025-Q1
EXP-004100 | 2025-03-08 | BOQ-PKG-10-00120 | PKG-10 | INV-PKG-10-006-04100 | 327.07 | 176010.05 | 8800.5 | Paid | 167209.55 | 2025-Q1
EXP-005520 | 2025-03-08 | BOQ-PKG-10-01540 | PKG-10 | INV-PKG-10-026-05520 | 429.06 | 109838.9 | 5491.94 | Approved Pending Payment | 104346.96 | 2025-Q1
EXP-000058 | 2025-03-09 | BOQ-PKG-08-00058 | PKG-08 | INV-PKG-08-024-00058 | 293.46 | 36280.45 | 1814.02 | Under Review | 34466.43 | 2025-Q1
EXP-002237 | 2025-03-09 | BOQ-PKG-07-00247 | PKG-07 | INV-PKG-07-033-02237 | 240.49 | 107782.24 | 5389.11 | Paid | 102393.13 | 2025-Q1
EXP-005795 | 2025-03-09 | BOQ-PKG-05-01815 | PKG-05 | INV-PKG-05-021-05795 | 369.09 | 194125.63 | 9706.28 | Paid | 184419.35 | 2025-Q1
EXP-006577 | 2025-03-09 | BOQ-PKG-07-00607 | PKG-07 | INV-PKG-07-033-06577 | 42.93 | 178870.89 | 8943.54 | Paid | 169927.35 | 2025-Q1
EXP-000004 | 2025-03-10 | BOQ-PKG-04-00004 | PKG-04 | INV-PKG-04-005-00004 | 153.81 | 97838 | 4891.9 | Paid | 92946.1 | 2025-Q1
EXP-000073 | 2025-03-10 | BOQ-PKG-03-00073 | PKG-03 | INV-PKG-03-004-00073 | 26.52 | 181660.65 | 9083.03 | Paid | 172577.62 | 2025-Q1
EXP-000378 | 2025-03-10 | BOQ-PKG-08-00378 | PKG-08 | INV-PKG-08-029-00378 | 330.84 | 69099.35 | 3454.97 | Paid | 65644.38 | 2025-Q1
EXP-000466 | 2025-03-10 | BOQ-PKG-06-00466 | PKG-06 | INV-PKG-06-012-00466 | 172.4 | 92712.61 | 4635.63 | Approved Pending Payment | 88076.98 | 2025-Q1
EXP-001129 | 2025-03-10 | BOQ-PKG-09-01129 | PKG-09 | INV-PKG-09-010-01129 | 36.82 | 98521.25 | 4926.06 | Paid | 93595.19 | 2025-Q1
EXP-001648 | 2025-03-10 | BOQ-PKG-08-01648 | PKG-08 | INV-PKG-08-004-01648 | 223.56 | 146641.04 | 7332.05 | Paid | 139308.99 | 2025-Q1
EXP-002168 | 2025-03-11 | BOQ-PKG-08-00178 | PKG-08 | INV-PKG-08-034-02168 | 203.79 | 88196.51 | 4409.83 | Paid | 83786.68 | 2025-Q1
EXP-003947 | 2025-03-11 | BOQ-PKG-07-01957 | PKG-07 | INV-PKG-07-028-03947 | 447.15 | 115613.03 | 5780.65 | Paid | 109832.38 | 2025-Q1
EXP-005596 | 2025-03-11 | BOQ-PKG-06-01616 | PKG-06 | INV-PKG-06-032-05596 | 224.76 | 187275.25 | 9363.76 | Paid | 177911.49 | 2025-Q1
EXP-001795 | 2025-03-12 | BOQ-PKG-05-01795 | PKG-05 | INV-PKG-05-011-01795 | 382.99 | 136663.44 | 6833.17 | Paid | 129830.27 | 2025-Q1
EXP-003006 | 2025-03-12 | BOQ-PKG-06-01016 | PKG-06 | INV-PKG-06-032-03006 | 328.15 | 147006.82 | 7350.34 | Paid | 139656.48 | 2025-Q1
EXP-004708 | 2025-03-12 | BOQ-PKG-08-00728 | PKG-08 | INV-PKG-08-019-04708 | 122.75 | 184784.67 | 9239.23 | Paid | 175545.44 | 2025-Q1
EXP-004809 | 2025-03-12 | BOQ-PKG-09-00829 | PKG-09 | INV-PKG-09-015-04809 | 405.27 | 90732.22 | 4536.61 | Under Review | 86195.61 | 2025-Q1
EXP-005926 | 2025-03-12 | BOQ-PKG-06-01946 | PKG-06 | INV-PKG-06-012-05926 | 280.74 | 178932.58 | 8946.63 | Paid | 169985.95 | 2025-Q1
EXP-006523 | 2025-03-12 | BOQ-PKG-03-00553 | PKG-03 | INV-PKG-03-014-06523 | 142.33 | 102778.78 | 5138.94 | Disputed | 97639.84 | 2025-Q1
EXP-006792 | 2025-03-12 | BOQ-PKG-02-00822 | PKG-02 | INV-PKG-02-003-06792 | 256 | 81424.07 | 4071.2 | Approved Pending Payment | 77352.87 | 2025-Q1
EXP-002577 | 2025-03-13 | BOQ-PKG-07-00587 | PKG-07 | INV-PKG-07-023-02577 | 143.88 | 73681.88 | 3684.09 | Paid | 69997.79 | 2025-Q1
EXP-006339 | 2025-03-13 | BOQ-PKG-09-00369 | PKG-09 | INV-PKG-09-005-06339 | 261.99 | 170337 | 8516.85 | Paid | 161820.15 | 2025-Q1
EXP-000200 | 2025-03-14 | BOQ-PKG-10-00200 | PKG-10 | INV-PKG-10-026-00200 | 59.94 | 59957.43 | 2997.87 | Paid | 56959.56 | 2025-Q1
EXP-000421 | 2025-03-14 | BOQ-PKG-01-00421 | PKG-01 | INV-PKG-01-002-00421 | 434.66 | 92605.57 | 4630.28 | Paid | 87975.29 | 2025-Q1
EXP-002663 | 2025-03-14 | BOQ-PKG-03-00673 | PKG-03 | INV-PKG-03-004-02663 | 365.35 | 71484.1 | 3574.21 | Paid | 67909.89 | 2025-Q1
EXP-004272 | 2025-03-14 | BOQ-PKG-02-00292 | PKG-02 | INV-PKG-02-003-04272 | 352.34 | 158412.69 | 7920.63 | Under Review | 150492.06 | 2025-Q1
EXP-004341 | 2025-03-14 | BOQ-PKG-01-00361 | PKG-01 | INV-PKG-01-002-04341 | 120.53 | 52304.53 | 2615.23 | Paid | 49689.3 | 2025-Q1
EXP-004745 | 2025-03-14 | BOQ-PKG-05-00765 | PKG-05 | INV-PKG-05-021-04745 | 437.79 | 172314.33 | 8615.72 | Approved Pending Payment | 163698.61 | 2025-Q1
EXP-004861 | 2025-03-14 | BOQ-PKG-01-00881 | PKG-01 | INV-PKG-01-032-04861 | 101.62 | 89863.11 | 4493.16 | Paid | 85369.95 | 2025-Q1
EXP-006400 | 2025-03-14 | BOQ-PKG-10-00430 | PKG-10 | INV-PKG-10-031-06400 | 24.65 | 32511.14 | 1625.56 | Approved Pending Payment | 30885.58 | 2025-Q1
EXP-000728 | 2025-03-15 | BOQ-PKG-08-00728 | PKG-08 | INV-PKG-08-029-00728 | 147.64 | 168943.65 | 8447.18 | Paid | 160496.47 | 2025-Q1
EXP-001400 | 2025-03-15 | BOQ-PKG-10-01400 | PKG-10 | INV-PKG-10-001-01400 | 422.2 | 160948.32 | 8047.42 | Paid | 152900.9 | 2025-Q1
EXP-003707 | 2025-03-15 | BOQ-PKG-07-01717 | PKG-07 | INV-PKG-07-033-03707 | 167.35 | 212900.98 | 10645.05 | Paid | 202255.93 | 2025-Q1
EXP-004989 | 2025-03-15 | BOQ-PKG-09-01009 | PKG-09 | INV-PKG-09-020-04989 | 274.65 | 128998.68 | 6449.93 | Approved Pending Payment | 122548.75 | 2025-Q1
EXP-005536 | 2025-03-15 | BOQ-PKG-06-01556 | PKG-06 | INV-PKG-06-007-05536 | 12.62 | 34173.31 | 1708.67 | Paid | 32464.64 | 2025-Q1
EXP-006689 | 2025-03-15 | BOQ-PKG-09-00719 | PKG-09 | INV-PKG-09-005-06689 | 406.34 | 59816.4 | 2990.82 | Paid | 56825.58 | 2025-Q1
EXP-006817 | 2025-03-15 | BOQ-PKG-07-00847 | PKG-07 | INV-PKG-07-028-06817 | 428.01 | 107557.42 | 5377.87 | Paid | 102179.55 | 2025-Q1
EXP-000225 | 2025-03-16 | BOQ-PKG-05-00225 | PKG-05 | INV-PKG-05-016-00225 | 262.04 | 128819.63 | 6440.98 | Paid | 122378.65 | 2025-Q1
EXP-000887 | 2025-03-16 | BOQ-PKG-07-00887 | PKG-07 | INV-PKG-07-013-00887 | 441.39 | 89003.12 | 4450.16 | Paid | 84552.96 | 2025-Q1
EXP-000934 | 2025-03-16 | BOQ-PKG-04-00934 | PKG-04 | INV-PKG-04-025-00934 | 200.85 | 41655.23 | 2082.76 | Paid | 39572.47 | 2025-Q1
EXP-000936 | 2025-03-16 | BOQ-PKG-06-00936 | PKG-06 | INV-PKG-06-027-00936 | 244.04 | 60269.94 | 3013.5 | Under Review | 57256.44 | 2025-Q1
EXP-001095 | 2025-03-16 | BOQ-PKG-05-01095 | PKG-05 | INV-PKG-05-011-01095 | 283.68 | 50018.02 | 2500.9 | Approved Pending Payment | 47517.12 | 2025-Q1
EXP-003501 | 2025-03-16 | BOQ-PKG-01-01511 | PKG-01 | INV-PKG-01-002-03501 | 93.09 | 40932.84 | 2046.64 | Under Review | 38886.2 | 2025-Q1
EXP-003767 | 2025-03-16 | BOQ-PKG-07-01777 | PKG-07 | INV-PKG-07-023-03767 | 77.77 | 41498.99 | 2074.95 | Paid | 39424.04 | 2025-Q1
EXP-004147 | 2025-03-16 | BOQ-PKG-07-00167 | PKG-07 | INV-PKG-07-018-04147 | 58.96 | 125960.8 | 6298.04 | Paid | 119662.76 | 2025-Q1
EXP-004324 | 2025-03-16 | BOQ-PKG-04-00344 | PKG-04 | INV-PKG-04-020-04324 | 71.61 | 177212.59 | 8860.63 | Paid | 168351.96 | 2025-Q1
EXP-000556 | 2025-03-17 | BOQ-PKG-06-00556 | PKG-06 | INV-PKG-06-032-00556 | 377.4 | 135910.33 | 6795.52 | Paid | 129114.81 | 2025-Q1
EXP-000716 | 2025-03-17 | BOQ-PKG-06-00716 | PKG-06 | INV-PKG-06-017-00716 | 88.94 | 119034.22 | 5951.71 | Approved Pending Payment | 113082.51 | 2025-Q1
EXP-000733 | 2025-03-17 | BOQ-PKG-03-00733 | PKG-03 | INV-PKG-03-034-00733 | 153.05 | 103807.22 | 5190.36 | Paid | 98616.86 | 2025-Q1
EXP-001203 | 2025-03-17 | BOQ-PKG-03-01203 | PKG-03 | INV-PKG-03-014-01203 | 149.68 | 114693.43 | 5734.67 | Paid | 108958.76 | 2025-Q1
EXP-001480 | 2025-03-17 | BOQ-PKG-10-01480 | PKG-10 | INV-PKG-10-011-01480 | 336.22 | 108756.82 | 5437.84 | Paid | 103318.98 | 2025-Q1
EXP-001644 | 2025-03-17 | BOQ-PKG-04-01644 | PKG-04 | INV-PKG-04-035-01644 | 363.53 | 53235.14 | 2661.76 | Paid | 50573.38 | 2025-Q1
EXP-001935 | 2025-03-17 | BOQ-PKG-05-01935 | PKG-05 | INV-PKG-05-011-01935 | 112.54 | 24315.97 | 1215.8 | Paid | 23100.17 | 2025-Q1
EXP-003060 | 2025-03-17 | BOQ-PKG-10-01070 | PKG-10 | INV-PKG-10-016-03060 | 415.01 | 123918.83 | 6195.94 | Paid | 117722.89 | 2025-Q1
EXP-003777 | 2025-03-17 | BOQ-PKG-07-01787 | PKG-07 | INV-PKG-07-033-03777 | 80.19 | 83566.25 | 4178.31 | Paid | 79387.94 | 2025-Q1
EXP-005483 | 2025-03-17 | BOQ-PKG-03-01503 | PKG-03 | INV-PKG-03-024-05483 | 65.91 | 154202.66 | 7710.13 | Paid | 146492.53 | 2025-Q1
EXP-005820 | 2025-03-17 | BOQ-PKG-10-01840 | PKG-10 | INV-PKG-10-011-05820 | 192.72 | 47065.02 | 2353.25 | Paid | 44711.77 | 2025-Q1
EXP-001142 | 2025-03-18 | BOQ-PKG-02-01142 | PKG-02 | INV-PKG-02-023-01142 | 132.06 | 78857.03 | 3942.85 | Approved Pending Payment | 74914.18 | 2025-Q1
EXP-001726 | 2025-03-18 | BOQ-PKG-06-01726 | PKG-06 | INV-PKG-06-012-01726 | 273.62 | 196625.54 | 9831.28 | Under Review | 186794.26 | 2025-Q1
EXP-002822 | 2025-03-18 | BOQ-PKG-02-00832 | PKG-02 | INV-PKG-02-023-02822 | 177.56 | 68020.8 | 3401.04 | Paid | 64619.76 | 2025-Q1
EXP-003367 | 2025-03-18 | BOQ-PKG-07-01377 | PKG-07 | INV-PKG-07-008-03367 | 253.6 | 24193.93 | 1209.7 | Paid | 22984.23 | 2025-Q1
EXP-003759 | 2025-03-18 | BOQ-PKG-09-01769 | PKG-09 | INV-PKG-09-015-03759 | 183.18 | 193134.14 | 9656.71 | Approved Pending Payment | 183477.43 | 2025-Q1
EXP-000909 | 2025-03-19 | BOQ-PKG-09-00909 | PKG-09 | INV-PKG-09-035-00909 | 193.85 | 52900.38 | 2645.02 | Paid | 50255.36 | 2025-Q1
EXP-001791 | 2025-03-19 | BOQ-PKG-01-01791 | PKG-01 | INV-PKG-01-007-01791 | 368.78 | 122026.2 | 6101.31 | Paid | 115924.89 | 2025-Q1
EXP-002171 | 2025-03-19 | BOQ-PKG-01-00181 | PKG-01 | INV-PKG-01-002-02171 | 236 | 174257.22 | 8712.86 | Paid | 165544.36 | 2025-Q1
EXP-002433 | 2025-03-19 | BOQ-PKG-03-00443 | PKG-03 | INV-PKG-03-019-02433 | 90.62 | 197824.65 | 9891.23 | Paid | 187933.42 | 2025-Q1
EXP-003885 | 2025-03-19 | BOQ-PKG-05-01895 | PKG-05 | INV-PKG-05-001-03885 | 232.3 | 126301.65 | 6315.08 | Paid | 119986.57 | 2025-Q1
EXP-004303 | 2025-03-19 | BOQ-PKG-03-00323 | PKG-03 | INV-PKG-03-034-04303 | 62.23 | 187220.66 | 9361.03 | Paid | 177859.63 | 2025-Q1
EXP-004446 | 2025-03-19 | BOQ-PKG-06-00466 | PKG-06 | INV-PKG-06-002-04446 | 276.62 | 173022.59 | 8651.13 | Paid | 164371.46 | 2025-Q1
EXP-004490 | 2025-03-19 | BOQ-PKG-10-00510 | PKG-10 | INV-PKG-10-011-04490 | 173.77 | 199541.5 | 9977.08 | Paid | 189564.42 | 2025-Q1
EXP-006167 | 2025-03-19 | BOQ-PKG-07-00197 | PKG-07 | INV-PKG-07-008-06167 | 173.02 | 82053.77 | 4102.69 | Approved Pending Payment | 77951.08 | 2025-Q1
EXP-000268 | 2025-03-20 | BOQ-PKG-08-00268 | PKG-08 | INV-PKG-08-024-00268 | 129.02 | 197292.15 | 9864.61 | Paid | 187427.54 | 2025-Q1
EXP-001598 | 2025-03-20 | BOQ-PKG-08-01598 | PKG-08 | INV-PKG-08-024-01598 | 395.6 | 41806.01 | 2090.3 | Approved Pending Payment | 39715.71 | 2025-Q1
EXP-002202 | 2025-03-20 | BOQ-PKG-02-00212 | PKG-02 | INV-PKG-02-033-02202 | 358.04 | 169725.04 | 8486.25 | Approved Pending Payment | 161238.79 | 2025-Q1
EXP-002592 | 2025-03-20 | BOQ-PKG-02-00602 | PKG-02 | INV-PKG-02-003-02592 | 114.99 | 74419.45 | 3720.97 | Paid | 70698.48 | 2025-Q1
EXP-003899 | 2025-03-20 | BOQ-PKG-09-01909 | PKG-09 | INV-PKG-09-015-03899 | 289.36 | 188133.3 | 9406.66 | Paid | 178726.64 | 2025-Q1
EXP-004126 | 2025-03-20 | BOQ-PKG-06-00146 | PKG-06 | INV-PKG-06-032-04126 | 207.8 | 120313.68 | 6015.68 | Under Review | 114298 | 2025-Q1
EXP-004335 | 2025-03-20 | BOQ-PKG-05-00355 | PKG-05 | INV-PKG-05-031-04335 | 354.3 | 42566.2 | 2128.31 | Paid | 40437.89 | 2025-Q1
EXP-000523 | 2025-03-21 | BOQ-PKG-03-00523 | PKG-03 | INV-PKG-03-034-00523 | 139.24 | 98293.57 | 4914.68 | Approved Pending Payment | 93378.89 | 2025-Q1
EXP-001057 | 2025-03-21 | BOQ-PKG-07-01057 | PKG-07 | INV-PKG-07-008-01057 | 230.58 | 153871.6 | 7693.58 | Approved Pending Payment | 146178.02 | 2025-Q1
EXP-001571 | 2025-03-21 | BOQ-PKG-01-01571 | PKG-01 | INV-PKG-01-032-01571 | 361.54 | 173538.87 | 8676.94 | Paid | 164861.93 | 2025-Q1
EXP-006050 | 2025-03-21 | BOQ-PKG-10-00080 | PKG-10 | INV-PKG-10-031-06050 | 372.98 | 103319.33 | 5165.97 | Paid | 98153.36 | 2025-Q1
EXP-000377 | 2025-03-22 | BOQ-PKG-07-00377 | PKG-07 | INV-PKG-07-028-00377 | 235.52 | 25177.56 | 1258.88 | Paid | 23918.68 | 2025-Q1
EXP-000761 | 2025-03-22 | BOQ-PKG-01-00761 | PKG-01 | INV-PKG-01-027-00761 | 18.72 | 180920.95 | 9046.05 | Under Review | 171874.9 | 2025-Q1
EXP-000772 | 2025-03-22 | BOQ-PKG-02-00772 | PKG-02 | INV-PKG-02-003-00772 | 274.54 | 151714.73 | 7585.74 | Under Review | 144128.99 | 2025-Q1
EXP-001139 | 2025-03-22 | BOQ-PKG-09-01139 | PKG-09 | INV-PKG-09-020-01139 | 315.64 | 93805.77 | 4690.29 | Paid | 89115.48 | 2025-Q1
EXP-002022 | 2025-03-22 | BOQ-PKG-02-00032 | PKG-02 | INV-PKG-02-028-02022 | 337.76 | 73638.3 | 3681.92 | Paid | 69956.38 | 2025-Q1
EXP-002163 | 2025-03-22 | BOQ-PKG-03-00173 | PKG-03 | INV-PKG-03-029-02163 | 166.68 | 143412.15 | 7170.61 | Paid | 136241.54 | 2025-Q1
EXP-003733 | 2025-03-22 | BOQ-PKG-03-01743 | PKG-03 | INV-PKG-03-024-03733 | 250.64 | 61014.37 | 3050.72 | Paid | 57963.65 | 2025-Q1
EXP-004053 | 2025-03-22 | BOQ-PKG-03-00073 | PKG-03 | INV-PKG-03-029-04053 | 213.39 | 98524.03 | 4926.2 | Paid | 93597.83 | 2025-Q1
EXP-004074 | 2025-03-22 | BOQ-PKG-04-00094 | PKG-04 | INV-PKG-04-015-04074 | 427.13 | 58202.52 | 2910.13 | Paid | 55292.39 | 2025-Q1
EXP-004377 | 2025-03-22 | BOQ-PKG-07-00397 | PKG-07 | INV-PKG-07-003-04377 | 5.09 | 186499.06 | 9324.95 | Paid | 177174.11 | 2025-Q1
EXP-004785 | 2025-03-22 | BOQ-PKG-05-00805 | PKG-05 | INV-PKG-05-026-04785 | 337.27 | 52783.43 | 2639.17 | Paid | 50144.26 | 2025-Q1
EXP-005084 | 2025-03-22 | BOQ-PKG-04-01104 | PKG-04 | INV-PKG-04-010-05084 | 195.27 | 37330.91 | 1866.55 | Paid | 35464.36 | 2025-Q1
EXP-005273 | 2025-03-22 | BOQ-PKG-03-01293 | PKG-03 | INV-PKG-03-024-05273 | 401.21 | 132514.68 | 6625.73 | Paid | 125888.95 | 2025-Q1
EXP-006407 | 2025-03-22 | BOQ-PKG-07-00437 | PKG-07 | INV-PKG-07-003-06407 | 295.49 | 94482.91 | 4724.15 | Under Review | 89758.76 | 2025-Q1
EXP-000647 | 2025-03-23 | BOQ-PKG-07-00647 | PKG-07 | INV-PKG-07-018-00647 | 80.99 | 73881.63 | 3694.08 | Paid | 70187.55 | 2025-Q1
EXP-002355 | 2025-03-23 | BOQ-PKG-05-00365 | PKG-05 | INV-PKG-05-011-02355 | 372.5 | 81646.43 | 4082.32 | Under Review | 77564.11 | 2025-Q1
EXP-003709 | 2025-03-23 | BOQ-PKG-09-01719 | PKG-09 | INV-PKG-09-035-03709 | 52.84 | 74385.23 | 3719.26 | Approved Pending Payment | 70665.97 | 2025-Q1
EXP-004007 | 2025-03-23 | BOQ-PKG-07-00027 | PKG-07 | INV-PKG-07-018-04007 | 369.18 | 27291.89 | 1364.59 | Under Review | 25927.3 | 2025-Q1
EXP-004888 | 2025-03-23 | BOQ-PKG-08-00908 | PKG-08 | INV-PKG-08-024-04888 | 137.23 | 51098.82 | 2554.94 | Paid | 48543.88 | 2025-Q1
EXP-005017 | 2025-03-23 | BOQ-PKG-07-01037 | PKG-07 | INV-PKG-07-013-05017 | 71.72 | 103317.94 | 5165.9 | Paid | 98152.04 | 2025-Q1
EXP-005735 | 2025-03-23 | BOQ-PKG-05-01755 | PKG-05 | INV-PKG-05-031-05735 | 223.77 | 113908.29 | 5695.41 | Paid | 108212.88 | 2025-Q1
EXP-000422 | 2025-03-24 | BOQ-PKG-02-00422 | PKG-02 | INV-PKG-02-003-00422 | 342.99 | 63421.02 | 3171.05 | Paid | 60249.97 | 2025-Q1
EXP-002252 | 2025-03-24 | BOQ-PKG-02-00262 | PKG-02 | INV-PKG-02-013-02252 | 172.23 | 131160.23 | 6558.01 | Paid | 124602.22 | 2025-Q1
EXP-002621 | 2025-03-24 | BOQ-PKG-01-00631 | PKG-01 | INV-PKG-01-032-02621 | 291.06 | 44543.68 | 2227.18 | Paid | 42316.5 | 2025-Q1
EXP-002732 | 2025-03-24 | BOQ-PKG-02-00742 | PKG-02 | INV-PKG-02-003-02732 | 12.26 | 56386.68 | 2819.33 | Approved Pending Payment | 53567.35 | 2025-Q1
EXP-002989 | 2025-03-24 | BOQ-PKG-09-00999 | PKG-09 | INV-PKG-09-015-02989 | 35.26 | 146007.58 | 7300.38 | Paid | 138707.2 | 2025-Q1
EXP-003090 | 2025-03-24 | BOQ-PKG-10-01100 | PKG-10 | INV-PKG-10-011-03090 | 8.61 | 105604.58 | 5280.23 | Paid | 100324.35 | 2025-Q1
EXP-004058 | 2025-03-24 | BOQ-PKG-08-00078 | PKG-08 | INV-PKG-08-034-04058 | 444.54 | 131043.5 | 6552.18 | Paid | 124491.32 | 2025-Q1
EXP-002766 | 2025-03-25 | BOQ-PKG-06-00776 | PKG-06 | INV-PKG-06-002-02766 | 97.69 | 153309.4 | 7665.47 | Paid | 145643.93 | 2025-Q1
EXP-003604 | 2025-03-25 | BOQ-PKG-04-01614 | PKG-04 | INV-PKG-04-035-03604 | 310.46 | 166020.98 | 8301.05 | Paid | 157719.93 | 2025-Q1
EXP-003681 | 2025-03-25 | BOQ-PKG-01-01691 | PKG-01 | INV-PKG-01-007-03681 | 200.82 | 58716.51 | 2935.83 | Paid | 55780.68 | 2025-Q1
EXP-005315 | 2025-03-25 | BOQ-PKG-05-01335 | PKG-05 | INV-PKG-05-031-05315 | 446.72 | 127201.35 | 6360.07 | Paid | 120841.28 | 2025-Q1
EXP-005637 | 2025-03-25 | BOQ-PKG-07-01657 | PKG-07 | INV-PKG-07-003-05637 | 257.3 | 101883.53 | 5094.18 | Under Review | 96789.35 | 2025-Q1
EXP-005790 | 2025-03-25 | BOQ-PKG-10-01810 | PKG-10 | INV-PKG-10-016-05790 | 398.93 | 59431.18 | 2971.56 | Disputed | 56459.62 | 2025-Q1
EXP-006984 | 2025-03-25 | BOQ-PKG-04-01014 | PKG-04 | INV-PKG-04-020-06984 | 39.17 | 172595.82 | 8629.79 | Paid | 163966.03 | 2025-Q1
EXP-000551 | 2025-03-26 | BOQ-PKG-01-00551 | PKG-01 | INV-PKG-01-027-00551 | 104.5 | 195812.33 | 9790.62 | Paid | 186021.71 | 2025-Q1
EXP-001296 | 2025-03-26 | BOQ-PKG-06-01296 | PKG-06 | INV-PKG-06-002-01296 | 117.05 | 89582.98 | 4479.15 | Paid | 85103.83 | 2025-Q1
EXP-001888 | 2025-03-26 | BOQ-PKG-08-01888 | PKG-08 | INV-PKG-08-034-01888 | 39.56 | 209160.64 | 10458.03 | Approved Pending Payment | 198702.61 | 2025-Q1
EXP-002411 | 2025-03-26 | BOQ-PKG-01-00421 | PKG-01 | INV-PKG-01-032-02411 | 98.53 | 184327.23 | 9216.36 | Approved Pending Payment | 175110.87 | 2025-Q1
EXP-003552 | 2025-03-26 | BOQ-PKG-02-01562 | PKG-02 | INV-PKG-02-018-03552 | 152.48 | 143606.38 | 7180.32 | Paid | 136426.06 | 2025-Q1
EXP-003617 | 2025-03-26 | BOQ-PKG-07-01627 | PKG-07 | INV-PKG-07-013-03617 | 173.4 | 66583.61 | 3329.18 | Paid | 63254.43 | 2025-Q1
EXP-005733 | 2025-03-26 | BOQ-PKG-03-01753 | PKG-03 | INV-PKG-03-029-05733 | 8.72 | 143631.91 | 7181.6 | Paid | 136450.31 | 2025-Q1
EXP-006485 | 2025-03-26 | BOQ-PKG-05-00515 | PKG-05 | INV-PKG-05-011-06485 | 41.46 | 26927.19 | 1346.36 | Paid | 25580.83 | 2025-Q1
EXP-006657 | 2025-03-26 | BOQ-PKG-07-00687 | PKG-07 | INV-PKG-07-008-06657 | 377.67 | 83149.58 | 4157.48 | Paid | 78992.1 | 2025-Q1
EXP-006810 | 2025-03-26 | BOQ-PKG-10-00840 | PKG-10 | INV-PKG-10-021-06810 | 282.75 | 69381.3 | 3469.07 | Approved Pending Payment | 65912.23 | 2025-Q1
EXP-000293 | 2025-03-27 | BOQ-PKG-03-00293 | PKG-03 | INV-PKG-03-014-00293 | 101.83 | 50652.4 | 2532.62 | Paid | 48119.78 | 2025-Q1
EXP-000583 | 2025-03-27 | BOQ-PKG-03-00583 | PKG-03 | INV-PKG-03-024-00583 | 405.84 | 195779.18 | 9788.96 | Paid | 185990.22 | 2025-Q1
EXP-001110 | 2025-03-27 | BOQ-PKG-10-01110 | PKG-10 | INV-PKG-10-026-01110 | 401.42 | 43166.84 | 2158.34 | Under Review | 41008.5 | 2025-Q1
EXP-002333 | 2025-03-27 | BOQ-PKG-03-00343 | PKG-03 | INV-PKG-03-024-02333 | 196 | 188309.08 | 9415.45 | Paid | 178893.63 | 2025-Q1
EXP-004417 | 2025-03-27 | BOQ-PKG-07-00437 | PKG-07 | INV-PKG-07-008-04417 | 295.62 | 150130.62 | 7506.53 | Approved Pending Payment | 142624.09 | 2025-Q1
EXP-006320 | 2025-03-27 | BOQ-PKG-10-00350 | PKG-10 | INV-PKG-10-021-06320 | 429.81 | 78903.79 | 3945.19 | Paid | 74958.6 | 2025-Q1
EXP-006497 | 2025-03-27 | BOQ-PKG-07-00527 | PKG-07 | INV-PKG-07-023-06497 | 54.32 | 56253.75 | 2812.69 | Paid | 53441.06 | 2025-Q1
EXP-002801 | 2025-03-28 | BOQ-PKG-01-00811 | PKG-01 | INV-PKG-01-002-02801 | 71.17 | 155182.18 | 7759.11 | Approved Pending Payment | 147423.07 | 2025-Q1
EXP-002902 | 2025-03-28 | BOQ-PKG-02-00912 | PKG-02 | INV-PKG-02-033-02902 | 87.28 | 82761.18 | 4138.06 | Paid | 78623.12 | 2025-Q1
EXP-004111 | 2025-03-28 | BOQ-PKG-01-00131 | PKG-01 | INV-PKG-01-017-04111 | 385.47 | 112162.35 | 5608.12 | Paid | 106554.23 | 2025-Q1
EXP-004988 | 2025-03-28 | BOQ-PKG-08-01008 | PKG-08 | INV-PKG-08-019-04988 | 125.97 | 72543.48 | 3627.17 | Paid | 68916.31 | 2025-Q1
EXP-005746 | 2025-03-28 | BOQ-PKG-06-01766 | PKG-06 | INV-PKG-06-007-05746 | 428.2 | 169591.15 | 8479.56 | Paid | 161111.59 | 2025-Q1
EXP-005753 | 2025-03-28 | BOQ-PKG-03-01773 | PKG-03 | INV-PKG-03-014-05753 | 91.47 | 193157.91 | 9657.9 | Paid | 183500.01 | 2025-Q1
EXP-000872 | 2025-03-29 | BOQ-PKG-02-00872 | PKG-02 | INV-PKG-02-033-00872 | 423.73 | 114413.27 | 5720.66 | Approved Pending Payment | 108692.61 | 2025-Q1
EXP-000993 | 2025-03-29 | BOQ-PKG-03-00993 | PKG-03 | INV-PKG-03-014-00993 | 178.58 | 191404.48 | 9570.22 | Paid | 181834.26 | 2025-Q1
EXP-001848 | 2025-03-29 | BOQ-PKG-08-01848 | PKG-08 | INV-PKG-08-029-01848 | 144.5 | 152056.07 | 7602.8 | Paid | 144453.27 | 2025-Q1
EXP-002078 | 2025-03-29 | BOQ-PKG-08-00088 | PKG-08 | INV-PKG-08-014-02078 | 445.22 | 173698.7 | 8684.94 | Approved Pending Payment | 165013.76 | 2025-Q1
EXP-004583 | 2025-03-29 | BOQ-PKG-03-00603 | PKG-03 | INV-PKG-03-034-04583 | 409.78 | 104643.13 | 5232.16 | Paid | 99410.97 | 2025-Q1
EXP-004639 | 2025-03-29 | BOQ-PKG-09-00659 | PKG-09 | INV-PKG-09-020-04639 | 228.79 | 63883.07 | 3194.15 | Approved Pending Payment | 60688.92 | 2025-Q1
EXP-005864 | 2025-03-29 | BOQ-PKG-04-01884 | PKG-04 | INV-PKG-04-020-05864 | 95.89 | 54223.82 | 2711.19 | Paid | 51512.63 | 2025-Q1
EXP-005996 | 2025-03-29 | BOQ-PKG-06-00026 | PKG-06 | INV-PKG-06-012-05996 | 78.03 | 98895.45 | 4944.77 | Paid | 93950.68 | 2025-Q1
EXP-006461 | 2025-03-29 | BOQ-PKG-01-00491 | PKG-01 | INV-PKG-01-022-06461 | 191.27 | 25452.75 | 1272.64 | Paid | 24180.11 | 2025-Q1
EXP-000455 | 2025-03-30 | BOQ-PKG-05-00455 | PKG-05 | INV-PKG-05-001-00455 | 82.42 | 83666.52 | 4183.33 | Paid | 79483.19 | 2025-Q1
EXP-001106 | 2025-03-30 | BOQ-PKG-06-01106 | PKG-06 | INV-PKG-06-022-01106 | 44.39 | 135361.83 | 6768.09 | Paid | 128593.74 | 2025-Q1
EXP-001542 | 2025-03-30 | BOQ-PKG-02-01542 | PKG-02 | INV-PKG-02-003-01542 | 31.16 | 157954.29 | 7897.71 | Paid | 150056.58 | 2025-Q1
EXP-001619 | 2025-03-30 | BOQ-PKG-09-01619 | PKG-09 | INV-PKG-09-010-01619 | 189.71 | 53632.23 | 2681.61 | Paid | 50950.62 | 2025-Q1
EXP-003028 | 2025-03-30 | BOQ-PKG-08-01038 | PKG-08 | INV-PKG-08-019-03028 | 127.81 | 57810.26 | 2890.51 | Approved Pending Payment | 54919.75 | 2025-Q1
EXP-004617 | 2025-03-30 | BOQ-PKG-07-00637 | PKG-07 | INV-PKG-07-033-04617 | 322.39 | 93232.02 | 4661.6 | Paid | 88570.42 | 2025-Q1
EXP-005761 | 2025-03-30 | BOQ-PKG-01-01781 | PKG-01 | INV-PKG-01-022-05761 | 290.39 | 94592.28 | 4729.61 | Approved Pending Payment | 89862.67 | 2025-Q1
EXP-001018 | 2025-03-31 | BOQ-PKG-08-01018 | PKG-08 | INV-PKG-08-004-01018 | 117.76 | 113884.46 | 5694.22 | Paid | 108190.24 | 2025-Q1
EXP-001099 | 2025-03-31 | BOQ-PKG-09-01099 | PKG-09 | INV-PKG-09-015-01099 | 312 | 184653.32 | 9232.67 | Under Review | 175420.65 | 2025-Q1
EXP-001104 | 2025-03-31 | BOQ-PKG-04-01104 | PKG-04 | INV-PKG-04-020-01104 | 225.42 | 107500.34 | 5375.02 | Paid | 102125.32 | 2025-Q1
EXP-001160 | 2025-03-31 | BOQ-PKG-10-01160 | PKG-10 | INV-PKG-10-006-01160 | 244.2 | 208088.64 | 10404.43 | Paid | 197684.21 | 2025-Q1
EXP-001949 | 2025-03-31 | BOQ-PKG-09-01949 | PKG-09 | INV-PKG-09-025-01949 | 337.91 | 63891.81 | 3194.59 | Under Review | 60697.22 | 2025-Q1
EXP-002987 | 2025-03-31 | BOQ-PKG-07-00997 | PKG-07 | INV-PKG-07-013-02987 | 255.85 | 213004.66 | 10650.23 | Paid | 202354.43 | 2025-Q1
EXP-005213 | 2025-03-31 | BOQ-PKG-03-01233 | PKG-03 | INV-PKG-03-034-05213 | 41.94 | 117950.11 | 5897.51 | Paid | 112052.6 | 2025-Q1
EXP-006687 | 2025-03-31 | BOQ-PKG-07-00717 | PKG-07 | INV-PKG-07-003-06687 | 179.86 | 213252.5 | 10662.62 | Paid | 202589.88 | 2025-Q1
EXP-000024 | 2025-04-01 | BOQ-PKG-04-00024 | PKG-04 | INV-PKG-04-025-00024 | 11.09 | 38432.27 | 1921.61 | Paid | 36510.66 | 2025-Q2
EXP-002225 | 2025-04-01 | BOQ-PKG-05-00235 | PKG-05 | INV-PKG-05-021-02225 | 30.67 | 59020.14 | 2951.01 | Under Review | 56069.13 | 2025-Q2
EXP-003678 | 2025-04-01 | BOQ-PKG-08-01688 | PKG-08 | INV-PKG-08-004-03678 | 274.4 | 42767.63 | 2138.38 | Paid | 40629.25 | 2025-Q2
EXP-004277 | 2025-04-01 | BOQ-PKG-07-00297 | PKG-07 | INV-PKG-07-008-04277 | 301.59 | 98091.04 | 4904.55 | Approved Pending Payment | 93186.49 | 2025-Q2
EXP-006520 | 2025-04-01 | BOQ-PKG-10-00550 | PKG-10 | INV-PKG-10-011-06520 | 145.29 | 89877.25 | 4493.86 | Under Review | 85383.39 | 2025-Q2
EXP-000433 | 2025-04-02 | BOQ-PKG-03-00433 | PKG-03 | INV-PKG-03-014-00433 | 165.94 | 45478.06 | 2273.9 | Approved Pending Payment | 43204.16 | 2025-Q2
EXP-003751 | 2025-04-02 | BOQ-PKG-01-01761 | PKG-01 | INV-PKG-01-007-03751 | 74.39 | 107944.72 | 5397.24 | Approved Pending Payment | 102547.48 | 2025-Q2
EXP-004922 | 2025-04-02 | BOQ-PKG-02-00942 | PKG-02 | INV-PKG-02-023-04922 | 292.98 | 112246.42 | 5612.32 | Paid | 106634.1 | 2025-Q2
EXP-005110 | 2025-04-02 | BOQ-PKG-10-01130 | PKG-10 | INV-PKG-10-001-05110 | 441.23 | 131857 | 6592.85 | Approved Pending Payment | 125264.15 | 2025-Q2
EXP-005203 | 2025-04-02 | BOQ-PKG-03-01223 | PKG-03 | INV-PKG-03-024-05203 | 350.8 | 51908.35 | 2595.42 | Paid | 49312.93 | 2025-Q2
EXP-006519 | 2025-04-02 | BOQ-PKG-09-00549 | PKG-09 | INV-PKG-09-010-06519 | 118.43 | 168381.24 | 8419.06 | Paid | 159962.18 | 2025-Q2
EXP-001752 | 2025-04-03 | BOQ-PKG-02-01752 | PKG-02 | INV-PKG-02-003-01752 | 108.71 | 138281.18 | 6914.06 | Approved Pending Payment | 131367.12 | 2025-Q2
EXP-002045 | 2025-04-03 | BOQ-PKG-05-00055 | PKG-05 | INV-PKG-05-016-02045 | 400.3 | 171172.26 | 8558.61 | Approved Pending Payment | 162613.65 | 2025-Q2
EXP-002106 | 2025-04-03 | BOQ-PKG-06-00116 | PKG-06 | INV-PKG-06-007-02106 | 398.95 | 94548.67 | 4727.43 | Paid | 89821.24 | 2025-Q2
EXP-002730 | 2025-04-03 | BOQ-PKG-10-00740 | PKG-10 | INV-PKG-10-001-02730 | 292.01 | 129022.49 | 6451.12 | Under Review | 122571.37 | 2025-Q2
EXP-004514 | 2025-04-03 | BOQ-PKG-04-00534 | PKG-04 | INV-PKG-04-035-04514 | 417.85 | 171931.79 | 8596.59 | Paid | 163335.2 | 2025-Q2
EXP-005001 | 2025-04-03 | BOQ-PKG-01-01021 | PKG-01 | INV-PKG-01-032-05001 | 35.28 | 60629.45 | 3031.47 | Approved Pending Payment | 57597.98 | 2025-Q2
EXP-006945 | 2025-04-03 | BOQ-PKG-05-00975 | PKG-05 | INV-PKG-05-016-06945 | 385.44 | 53590.71 | 2679.54 | Paid | 50911.17 | 2025-Q2
EXP-001913 | 2025-04-04 | BOQ-PKG-03-01913 | PKG-03 | INV-PKG-03-024-01913 | 393.85 | 34801.69 | 1740.08 | Paid | 33061.61 | 2025-Q2
EXP-006380 | 2025-04-04 | BOQ-PKG-10-00410 | PKG-10 | INV-PKG-10-011-06380 | 283.97 | 211313.92 | 10565.7 | Under Review | 200748.22 | 2025-Q2
EXP-006997 | 2025-04-04 | BOQ-PKG-07-01027 | PKG-07 | INV-PKG-07-033-06997 | 227.79 | 77584.16 | 3879.21 | Paid | 73704.95 | 2025-Q2
EXP-000922 | 2025-04-05 | BOQ-PKG-02-00922 | PKG-02 | INV-PKG-02-013-00922 | 393.74 | 166532.03 | 8326.6 | Paid | 158205.43 | 2025-Q2
EXP-001337 | 2025-04-05 | BOQ-PKG-07-01337 | PKG-07 | INV-PKG-07-008-01337 | 26.35 | 187805.35 | 9390.27 | Paid | 178415.08 | 2025-Q2
EXP-003669 | 2025-04-05 | BOQ-PKG-09-01679 | PKG-09 | INV-PKG-09-030-03669 | 441.14 | 61045.58 | 3052.28 | Paid | 57993.3 | 2025-Q2
EXP-004149 | 2025-04-05 | BOQ-PKG-09-00169 | PKG-09 | INV-PKG-09-020-04149 | 134.7 | 112257.83 | 5612.89 | Under Review | 106644.94 | 2025-Q2
EXP-005700 | 2025-04-05 | BOQ-PKG-10-01720 | PKG-10 | INV-PKG-10-031-05700 | 148.71 | 102597.52 | 5129.88 | Paid | 97467.64 | 2025-Q2
EXP-002596 | 2025-04-06 | BOQ-PKG-06-00606 | PKG-06 | INV-PKG-06-007-02596 | 77.42 | 63551.13 | 3177.56 | Under Review | 60373.57 | 2025-Q2
EXP-004293 | 2025-04-06 | BOQ-PKG-03-00313 | PKG-03 | INV-PKG-03-024-04293 | 154.92 | 92878 | 4643.9 | Disputed | 88234.1 | 2025-Q2
EXP-004371 | 2025-04-06 | BOQ-PKG-01-00391 | PKG-01 | INV-PKG-01-032-04371 | 305.89 | 191820.27 | 9591.01 | Paid | 182229.26 | 2025-Q2
EXP-004791 | 2025-04-06 | BOQ-PKG-01-00811 | PKG-01 | INV-PKG-01-032-04791 | 88.32 | 124659.24 | 6232.96 | Paid | 118426.28 | 2025-Q2
EXP-004974 | 2025-04-06 | BOQ-PKG-04-00994 | PKG-04 | INV-PKG-04-005-04974 | 412.45 | 95076.81 | 4753.84 | Paid | 90322.97 | 2025-Q2
EXP-005376 | 2025-04-06 | BOQ-PKG-06-01396 | PKG-06 | INV-PKG-06-022-05376 | 238.13 | 63351.62 | 3167.58 | Paid | 60184.04 | 2025-Q2
EXP-006369 | 2025-04-06 | BOQ-PKG-09-00399 | PKG-09 | INV-PKG-09-035-06369 | 124.2 | 72915.52 | 3645.78 | Paid | 69269.74 | 2025-Q2
EXP-000962 | 2025-04-07 | BOQ-PKG-02-00962 | PKG-02 | INV-PKG-02-018-00962 | 225.64 | 155468.01 | 7773.4 | Paid | 147694.61 | 2025-Q2
EXP-001359 | 2025-04-07 | BOQ-PKG-09-01359 | PKG-09 | INV-PKG-09-030-01359 | 315.75 | 102467.47 | 5123.37 | Paid | 97344.1 | 2025-Q2
EXP-006535 | 2025-04-07 | BOQ-PKG-05-00565 | PKG-05 | INV-PKG-05-026-06535 | 404.98 | 169398.81 | 8469.94 | Paid | 160928.87 | 2025-Q2
EXP-000652 | 2025-04-08 | BOQ-PKG-02-00652 | PKG-02 | INV-PKG-02-023-00652 | 277.86 | 188514.24 | 9425.71 | Paid | 179088.53 | 2025-Q2
EXP-001523 | 2025-04-08 | BOQ-PKG-03-01523 | PKG-03 | INV-PKG-03-019-01523 | 405.39 | 85305.88 | 4265.29 | Under Review | 81040.59 | 2025-Q2
EXP-002038 | 2025-04-08 | BOQ-PKG-08-00048 | PKG-08 | INV-PKG-08-009-02038 | 143.26 | 181639.81 | 9081.99 | Paid | 172557.82 | 2025-Q2
EXP-002961 | 2025-04-08 | BOQ-PKG-01-00971 | PKG-01 | INV-PKG-01-022-02961 | 90.65 | 43368.38 | 2168.42 | Under Review | 41199.96 | 2025-Q2
EXP-003124 | 2025-04-08 | BOQ-PKG-04-01134 | PKG-04 | INV-PKG-04-010-03124 | 449.06 | 106259.62 | 5312.98 | Paid | 100946.64 | 2025-Q2
EXP-003909 | 2025-04-08 | BOQ-PKG-09-01919 | PKG-09 | INV-PKG-09-025-03909 | 386.54 | 190778.72 | 9538.94 | Paid | 181239.78 | 2025-Q2
EXP-004485 | 2025-04-08 | BOQ-PKG-05-00505 | PKG-05 | INV-PKG-05-006-04485 | 202.2 | 116368.23 | 5818.41 | Paid | 110549.82 | 2025-Q2
EXP-004767 | 2025-04-08 | BOQ-PKG-07-00787 | PKG-07 | INV-PKG-07-008-04767 | 347.02 | 189571.39 | 9478.57 | Paid | 180092.82 | 2025-Q2
EXP-003606 | 2025-04-09 | BOQ-PKG-06-01616 | PKG-06 | INV-PKG-06-002-03606 | 291.87 | 194280.61 | 9714.03 | Approved Pending Payment | 184566.58 | 2025-Q2
EXP-004328 | 2025-04-09 | BOQ-PKG-08-00348 | PKG-08 | INV-PKG-08-024-04328 | 53.09 | 47377.96 | 2368.9 | Approved Pending Payment | 45009.06 | 2025-Q2
EXP-000199 | 2025-04-10 | BOQ-PKG-09-00199 | PKG-09 | INV-PKG-09-025-00199 | 404.59 | 123951.08 | 6197.55 | Paid | 117753.53 | 2025-Q2
EXP-000592 | 2025-04-10 | BOQ-PKG-02-00592 | PKG-02 | INV-PKG-02-033-00592 | 146.18 | 166989.21 | 8349.46 | Paid | 158639.75 | 2025-Q2
EXP-001028 | 2025-04-10 | BOQ-PKG-08-01028 | PKG-08 | INV-PKG-08-014-01028 | 273.25 | 215167.88 | 10758.39 | Under Review | 204409.49 | 2025-Q2
EXP-003493 | 2025-04-10 | BOQ-PKG-03-01503 | PKG-03 | INV-PKG-03-029-03493 | 35.72 | 155097.77 | 7754.89 | Paid | 147342.88 | 2025-Q2
EXP-003796 | 2025-04-10 | BOQ-PKG-06-01806 | PKG-06 | INV-PKG-06-017-03796 | 100.62 | 74361.81 | 3718.09 | Paid | 70643.72 | 2025-Q2
EXP-004538 | 2025-04-10 | BOQ-PKG-08-00558 | PKG-08 | INV-PKG-08-024-04538 | 401.45 | 144384.33 | 7219.22 | Paid | 137165.11 | 2025-Q2
EXP-004806 | 2025-04-10 | BOQ-PKG-06-00826 | PKG-06 | INV-PKG-06-012-04806 | 184.68 | 197987.19 | 9899.36 | Paid | 188087.83 | 2025-Q2
EXP-005210 | 2025-04-10 | BOQ-PKG-10-01230 | PKG-10 | INV-PKG-10-031-05210 | 100.23 | 165955.29 | 8297.76 | Paid | 157657.53 | 2025-Q2
EXP-005928 | 2025-04-10 | BOQ-PKG-08-01948 | PKG-08 | INV-PKG-08-014-05928 | 242.07 | 64816.94 | 3240.85 | Paid | 61576.09 | 2025-Q2
EXP-000640 | 2025-04-11 | BOQ-PKG-10-00640 | PKG-10 | INV-PKG-10-011-00640 | 446.3 | 163983.44 | 8199.17 | Paid | 155784.27 | 2025-Q2
EXP-000867 | 2025-04-11 | BOQ-PKG-07-00867 | PKG-07 | INV-PKG-07-028-00867 | 125.45 | 29625.93 | 1481.3 | Paid | 28144.63 | 2025-Q2
EXP-001051 | 2025-04-11 | BOQ-PKG-01-01051 | PKG-01 | INV-PKG-01-002-01051 | 59.55 | 196485.39 | 9824.27 | Approved Pending Payment | 186661.12 | 2025-Q2
EXP-001341 | 2025-04-11 | BOQ-PKG-01-01341 | PKG-01 | INV-PKG-01-012-01341 | 429.68 | 71393.41 | 3569.67 | Paid | 67823.74 | 2025-Q2
EXP-002809 | 2025-04-11 | BOQ-PKG-09-00819 | PKG-09 | INV-PKG-09-010-02809 | 125.08 | 163118.26 | 8155.91 | Paid | 154962.35 | 2025-Q2
EXP-003069 | 2025-04-11 | BOQ-PKG-09-01079 | PKG-09 | INV-PKG-09-025-03069 | 433.89 | 94171.92 | 4708.6 | Paid | 89463.32 | 2025-Q2
EXP-003910 | 2025-04-11 | BOQ-PKG-10-01920 | PKG-10 | INV-PKG-10-026-03910 | 266.71 | 102048.91 | 5102.45 | Paid | 96946.46 | 2025-Q2
EXP-005784 | 2025-04-11 | BOQ-PKG-04-01804 | PKG-04 | INV-PKG-04-010-05784 | 146.61 | 214264.05 | 10713.2 | Paid | 203550.85 | 2025-Q2
EXP-000324 | 2025-04-12 | BOQ-PKG-04-00324 | PKG-04 | INV-PKG-04-010-00324 | 163.1 | 153294.52 | 7664.73 | Paid | 145629.79 | 2025-Q2
EXP-001216 | 2025-04-12 | BOQ-PKG-06-01216 | PKG-06 | INV-PKG-06-027-01216 | 204.19 | 169028.98 | 8451.45 | Paid | 160577.53 | 2025-Q2
EXP-002296 | 2025-04-12 | BOQ-PKG-06-00306 | PKG-06 | INV-PKG-06-022-02296 | 390.55 | 28403.02 | 1420.15 | Paid | 26982.87 | 2025-Q2
EXP-002432 | 2025-04-12 | BOQ-PKG-02-00442 | PKG-02 | INV-PKG-02-018-02432 | 197.04 | 148602.09 | 7430.1 | Paid | 141171.99 | 2025-Q2
EXP-003539 | 2025-04-12 | BOQ-PKG-09-01549 | PKG-09 | INV-PKG-09-005-03539 | 274.06 | 149417.08 | 7470.85 | Paid | 141946.23 | 2025-Q2
EXP-004497 | 2025-04-12 | BOQ-PKG-07-00517 | PKG-07 | INV-PKG-07-018-04497 | 6.9 | 203686.44 | 10184.32 | Paid | 193502.12 | 2025-Q2
EXP-005674 | 2025-04-12 | BOQ-PKG-04-01694 | PKG-04 | INV-PKG-04-005-05674 | 41.26 | 51316.36 | 2565.82 | Paid | 48750.54 | 2025-Q2
EXP-005682 | 2025-04-12 | BOQ-PKG-02-01702 | PKG-02 | INV-PKG-02-013-05682 | 439.91 | 89694.27 | 4484.71 | Paid | 85209.56 | 2025-Q2
EXP-006226 | 2025-04-12 | BOQ-PKG-06-00256 | PKG-06 | INV-PKG-06-032-06226 | 448.42 | 165995.58 | 8299.78 | Paid | 157695.8 | 2025-Q2
EXP-006331 | 2025-04-12 | BOQ-PKG-01-00361 | PKG-01 | INV-PKG-01-032-06331 | 108.46 | 133395.12 | 6669.76 | Paid | 126725.36 | 2025-Q2
EXP-006487 | 2025-04-12 | BOQ-PKG-07-00517 | PKG-07 | INV-PKG-07-013-06487 | 85.61 | 74044.06 | 3702.2 | Paid | 70341.86 | 2025-Q2
EXP-000046 | 2025-04-13 | BOQ-PKG-06-00046 | PKG-06 | INV-PKG-06-012-00046 | 265.58 | 120965.05 | 6048.25 | Paid | 114916.8 | 2025-Q2
EXP-004630 | 2025-04-13 | BOQ-PKG-10-00650 | PKG-10 | INV-PKG-10-011-04630 | 256.6 | 141350.51 | 7067.53 | Paid | 134282.98 | 2025-Q2
EXP-005544 | 2025-04-13 | BOQ-PKG-04-01564 | PKG-04 | INV-PKG-04-015-05544 | 153.83 | 182701.25 | 9135.06 | Approved Pending Payment | 173566.19 | 2025-Q2
EXP-005598 | 2025-04-13 | BOQ-PKG-08-01618 | PKG-08 | INV-PKG-08-034-05598 | 332.8 | 194024.23 | 9701.21 | Paid | 184323.02 | 2025-Q2
EXP-006866 | 2025-04-13 | BOQ-PKG-06-00896 | PKG-06 | INV-PKG-06-007-06866 | 364.71 | 133306.38 | 6665.32 | Paid | 126641.06 | 2025-Q2
EXP-000697 | 2025-04-14 | BOQ-PKG-07-00697 | PKG-07 | INV-PKG-07-033-00697 | 168.44 | 192550.98 | 9627.55 | Paid | 182923.43 | 2025-Q2
EXP-002802 | 2025-04-14 | BOQ-PKG-02-00812 | PKG-02 | INV-PKG-02-003-02802 | 206.92 | 185899.77 | 9294.99 | Paid | 176604.78 | 2025-Q2
EXP-004231 | 2025-04-14 | BOQ-PKG-01-00251 | PKG-01 | INV-PKG-01-032-04231 | 426.1 | 130354.69 | 6517.73 | Paid | 123836.96 | 2025-Q2
EXP-005685 | 2025-04-14 | BOQ-PKG-05-01705 | PKG-05 | INV-PKG-05-016-05685 | 335.24 | 62795.89 | 3139.79 | Paid | 59656.1 | 2025-Q2
EXP-000256 | 2025-04-15 | BOQ-PKG-06-00256 | PKG-06 | INV-PKG-06-012-00256 | 35.6 | 125755.29 | 6287.76 | Under Review | 119467.53 | 2025-Q2
EXP-001260 | 2025-04-15 | BOQ-PKG-10-01260 | PKG-10 | INV-PKG-10-001-01260 | 282.57 | 176987.23 | 8849.36 | Paid | 168137.87 | 2025-Q2
EXP-002751 | 2025-04-15 | BOQ-PKG-01-00761 | PKG-01 | INV-PKG-01-022-02751 | 271.54 | 57524.65 | 2876.23 | Paid | 54648.42 | 2025-Q2
EXP-004575 | 2025-04-15 | BOQ-PKG-05-00595 | PKG-05 | INV-PKG-05-026-04575 | 137.82 | 103137.89 | 5156.89 | Paid | 97981 | 2025-Q2
EXP-006702 | 2025-04-15 | BOQ-PKG-02-00732 | PKG-02 | INV-PKG-02-018-06702 | 65.05 | 164319.79 | 8215.99 | Disputed | 156103.8 | 2025-Q2
EXP-000630 | 2025-04-16 | BOQ-PKG-10-00630 | PKG-10 | INV-PKG-10-001-00630 | 36.36 | 74827.46 | 3741.37 | Under Review | 71086.09 | 2025-Q2
EXP-001176 | 2025-04-16 | BOQ-PKG-06-01176 | PKG-06 | INV-PKG-06-022-01176 | 39.94 | 126905.7 | 6345.28 | Paid | 120560.42 | 2025-Q2
EXP-001482 | 2025-04-16 | BOQ-PKG-02-01482 | PKG-02 | INV-PKG-02-013-01482 | 24.76 | 183356.92 | 9167.85 | Paid | 174189.07 | 2025-Q2
EXP-002121 | 2025-04-16 | BOQ-PKG-01-00131 | PKG-01 | INV-PKG-01-022-02121 | 23.9 | 109598.06 | 5479.9 | Approved Pending Payment | 104118.16 | 2025-Q2
EXP-002692 | 2025-04-16 | BOQ-PKG-02-00702 | PKG-02 | INV-PKG-02-033-02692 | 185.75 | 136461.58 | 6823.08 | Under Review | 129638.5 | 2025-Q2
EXP-003052 | 2025-04-16 | BOQ-PKG-02-01062 | PKG-02 | INV-PKG-02-008-03052 | 238.89 | 51500.68 | 2575.03 | Under Review | 48925.65 | 2025-Q2
EXP-003119 | 2025-04-16 | BOQ-PKG-09-01129 | PKG-09 | INV-PKG-09-005-03119 | 440.19 | 181291.36 | 9064.57 | Approved Pending Payment | 172226.79 | 2025-Q2
EXP-003647 | 2025-04-16 | BOQ-PKG-07-01657 | PKG-07 | INV-PKG-07-008-03647 | 144.96 | 50609.37 | 2530.47 | Under Review | 48078.9 | 2025-Q2
EXP-004392 | 2025-04-16 | BOQ-PKG-02-00412 | PKG-02 | INV-PKG-02-018-04392 | 114.39 | 140294.09 | 7014.7 | Paid | 133279.39 | 2025-Q2
EXP-005322 | 2025-04-16 | BOQ-PKG-02-01342 | PKG-02 | INV-PKG-02-003-05322 | 340.85 | 152515.95 | 7625.8 | Approved Pending Payment | 144890.15 | 2025-Q2
EXP-005579 | 2025-04-16 | BOQ-PKG-09-01599 | PKG-09 | INV-PKG-09-015-05579 | 370.3 | 175351.47 | 8767.57 | Paid | 166583.9 | 2025-Q2
EXP-000569 | 2025-04-17 | BOQ-PKG-09-00569 | PKG-09 | INV-PKG-09-010-00569 | 236.54 | 213544.42 | 10677.22 | Paid | 202867.2 | 2025-Q2
EXP-000639 | 2025-04-17 | BOQ-PKG-09-00639 | PKG-09 | INV-PKG-09-010-00639 | 399.64 | 96429.78 | 4821.49 | Paid | 91608.29 | 2025-Q2
EXP-000988 | 2025-04-17 | BOQ-PKG-08-00988 | PKG-08 | INV-PKG-08-009-00988 | 233.77 | 177968.98 | 8898.45 | Paid | 169070.53 | 2025-Q2
EXP-001929 | 2025-04-17 | BOQ-PKG-09-01929 | PKG-09 | INV-PKG-09-005-01929 | 137.7 | 183183.73 | 9159.19 | Paid | 174024.54 | 2025-Q2
EXP-002484 | 2025-04-17 | BOQ-PKG-04-00494 | PKG-04 | INV-PKG-04-035-02484 | 209.36 | 198458.45 | 9922.92 | Under Review | 188535.53 | 2025-Q2
EXP-003508 | 2025-04-17 | BOQ-PKG-08-01518 | PKG-08 | INV-PKG-08-009-03508 | 93.4 | 48711.12 | 2435.56 | Under Review | 46275.56 | 2025-Q2
EXP-005325 | 2025-04-17 | BOQ-PKG-05-01345 | PKG-05 | INV-PKG-05-006-05325 | 411.6 | 169735.73 | 8486.79 | Paid | 161248.94 | 2025-Q2
EXP-006028 | 2025-04-17 | BOQ-PKG-08-00058 | PKG-08 | INV-PKG-08-009-06028 | 426.02 | 77497.4 | 3874.87 | Under Review | 73622.53 | 2025-Q2
EXP-006040 | 2025-04-17 | BOQ-PKG-10-00070 | PKG-10 | INV-PKG-10-021-06040 | 313.57 | 64335.03 | 3216.75 | Paid | 61118.28 | 2025-Q2
EXP-006476 | 2025-04-17 | BOQ-PKG-06-00506 | PKG-06 | INV-PKG-06-002-06476 | 207.16 | 166889.11 | 8344.46 | Paid | 158544.65 | 2025-Q2
EXP-000080 | 2025-04-18 | BOQ-PKG-10-00080 | PKG-10 | INV-PKG-10-011-00080 | 175.34 | 175598.91 | 8779.95 | Paid | 166818.96 | 2025-Q2
EXP-000100 | 2025-04-18 | BOQ-PKG-10-00100 | PKG-10 | INV-PKG-10-031-00100 | 191.18 | 91411.92 | 4570.6 | Paid | 86841.32 | 2025-Q2
EXP-000157 | 2025-04-18 | BOQ-PKG-07-00157 | PKG-07 | INV-PKG-07-018-00157 | 444.17 | 161579.38 | 8078.97 | Paid | 153500.41 | 2025-Q2
EXP-001133 | 2025-04-18 | BOQ-PKG-03-01133 | PKG-03 | INV-PKG-03-014-01133 | 227.97 | 81575.78 | 4078.79 | Paid | 77496.99 | 2025-Q2
EXP-006075 | 2025-04-18 | BOQ-PKG-05-00105 | PKG-05 | INV-PKG-05-021-06075 | 209.5 | 147077.03 | 7353.85 | Paid | 139723.18 | 2025-Q2
EXP-006471 | 2025-04-18 | BOQ-PKG-01-00501 | PKG-01 | INV-PKG-01-032-06471 | 180.86 | 72744.97 | 3637.25 | Paid | 69107.72 | 2025-Q2
EXP-006638 | 2025-04-18 | BOQ-PKG-08-00668 | PKG-08 | INV-PKG-08-024-06638 | 448.5 | 92323.37 | 4616.17 | Paid | 87707.2 | 2025-Q2
EXP-004950 | 2025-04-19 | BOQ-PKG-10-00970 | PKG-10 | INV-PKG-10-016-04950 | 324.08 | 90469.3 | 4523.46 | Approved Pending Payment | 85945.84 | 2025-Q2
EXP-005902 | 2025-04-19 | BOQ-PKG-02-01922 | PKG-02 | INV-PKG-02-023-05902 | 377.84 | 81917.97 | 4095.9 | Paid | 77822.07 | 2025-Q2
EXP-006402 | 2025-04-19 | BOQ-PKG-02-00432 | PKG-02 | INV-PKG-02-033-06402 | 288.87 | 203624.68 | 10181.23 | Paid | 193443.45 | 2025-Q2
EXP-000382 | 2025-04-20 | BOQ-PKG-02-00382 | PKG-02 | INV-PKG-02-033-00382 | 256.8 | 199704.57 | 9985.23 | Paid | 189719.34 | 2025-Q2
EXP-001650 | 2025-04-20 | BOQ-PKG-10-01650 | PKG-10 | INV-PKG-10-006-01650 | 154.29 | 39468.71 | 1973.44 | Paid | 37495.27 | 2025-Q2
EXP-001981 | 2025-04-20 | BOQ-PKG-01-01981 | PKG-01 | INV-PKG-01-022-01981 | 212.45 | 141617.39 | 7080.87 | Paid | 134536.52 | 2025-Q2
EXP-002193 | 2025-04-20 | BOQ-PKG-03-00203 | PKG-03 | INV-PKG-03-024-02193 | 94.48 | 46596.41 | 2329.82 | Paid | 44266.59 | 2025-Q2
EXP-002260 | 2025-04-20 | BOQ-PKG-10-00270 | PKG-10 | INV-PKG-10-021-02260 | 186.15 | 143769.42 | 7188.47 | Disputed | 136580.95 | 2025-Q2
EXP-002850 | 2025-04-20 | BOQ-PKG-10-00860 | PKG-10 | INV-PKG-10-016-02850 | 331.6 | 172205.5 | 8610.28 | Paid | 163595.22 | 2025-Q2
EXP-003864 | 2025-04-20 | BOQ-PKG-04-01874 | PKG-04 | INV-PKG-04-015-03864 | 289.66 | 24020.47 | 1201.02 | Paid | 22819.45 | 2025-Q2
EXP-004746 | 2025-04-20 | BOQ-PKG-06-00766 | PKG-06 | INV-PKG-06-022-04746 | 88.24 | 154974.08 | 7748.7 | Paid | 147225.38 | 2025-Q2
EXP-005392 | 2025-04-20 | BOQ-PKG-02-01412 | PKG-02 | INV-PKG-02-003-05392 | 5.65 | 188604.14 | 9430.21 | Paid | 179173.93 | 2025-Q2
EXP-006025 | 2025-04-20 | BOQ-PKG-05-00055 | PKG-05 | INV-PKG-05-006-06025 | 269.04 | 176082.8 | 8804.14 | Paid | 167278.66 | 2025-Q2
EXP-006592 | 2025-04-20 | BOQ-PKG-02-00622 | PKG-02 | INV-PKG-02-013-06592 | 257.1 | 96186.2 | 4809.31 | Paid | 91376.89 | 2025-Q2
EXP-001715 | 2025-04-21 | BOQ-PKG-05-01715 | PKG-05 | INV-PKG-05-001-01715 | 64.83 | 78965.1 | 3948.26 | Paid | 75016.84 | 2025-Q2
EXP-005375 | 2025-04-21 | BOQ-PKG-05-01395 | PKG-05 | INV-PKG-05-021-05375 | 5.03 | 182538.98 | 9126.95 | Approved Pending Payment | 173412.03 | 2025-Q2
EXP-005565 | 2025-04-21 | BOQ-PKG-05-01585 | PKG-05 | INV-PKG-05-001-05565 | 200.25 | 98938.86 | 4946.94 | Paid | 93991.92 | 2025-Q2
EXP-006068 | 2025-04-21 | BOQ-PKG-08-00098 | PKG-08 | INV-PKG-08-014-06068 | 82.88 | 42242.07 | 2112.1 | Paid | 40129.97 | 2025-Q2
EXP-001661 | 2025-04-22 | BOQ-PKG-01-01661 | PKG-01 | INV-PKG-01-017-01661 | 445.49 | 63468.56 | 3173.43 | Paid | 60295.13 | 2025-Q2
EXP-001745 | 2025-04-22 | BOQ-PKG-05-01745 | PKG-05 | INV-PKG-05-031-01745 | 120.21 | 167677.65 | 8383.88 | Paid | 159293.77 | 2025-Q2
EXP-002588 | 2025-04-22 | BOQ-PKG-08-00598 | PKG-08 | INV-PKG-08-034-02588 | 205.53 | 88908.11 | 4445.41 | Approved Pending Payment | 84462.7 | 2025-Q2
EXP-003998 | 2025-04-22 | BOQ-PKG-08-00018 | PKG-08 | INV-PKG-08-009-03998 | 105.12 | 32067.11 | 1603.36 | Paid | 30463.75 | 2025-Q2
EXP-004669 | 2025-04-22 | BOQ-PKG-09-00689 | PKG-09 | INV-PKG-09-015-04669 | 68.25 | 186695.55 | 9334.78 | Paid | 177360.77 | 2025-Q2
EXP-005018 | 2025-04-22 | BOQ-PKG-08-01038 | PKG-08 | INV-PKG-08-014-05018 | 160.55 | 199855.43 | 9992.77 | Approved Pending Payment | 189862.66 | 2025-Q2
EXP-005255 | 2025-04-22 | BOQ-PKG-05-01275 | PKG-05 | INV-PKG-05-006-05255 | 48.94 | 151183.68 | 7559.18 | Under Review | 143624.5 | 2025-Q2
EXP-005620 | 2025-04-22 | BOQ-PKG-10-01640 | PKG-10 | INV-PKG-10-021-05620 | 182.97 | 185071.27 | 9253.56 | Paid | 175817.71 | 2025-Q2
EXP-000438 | 2025-04-23 | BOQ-PKG-08-00438 | PKG-08 | INV-PKG-08-019-00438 | 186.3 | 200902.37 | 10045.12 | Paid | 190857.25 | 2025-Q2
EXP-000731 | 2025-04-23 | BOQ-PKG-01-00731 | PKG-01 | INV-PKG-01-032-00731 | 273.43 | 87937.02 | 4396.85 | Paid | 83540.17 | 2025-Q2
EXP-000762 | 2025-04-23 | BOQ-PKG-02-00762 | PKG-02 | INV-PKG-02-028-00762 | 157.16 | 189180.2 | 9459.01 | Paid | 179721.19 | 2025-Q2
EXP-004612 | 2025-04-23 | BOQ-PKG-02-00632 | PKG-02 | INV-PKG-02-028-04612 | 201.99 | 63269.35 | 3163.47 | Disputed | 60105.88 | 2025-Q2
EXP-006363 | 2025-04-23 | BOQ-PKG-03-00393 | PKG-03 | INV-PKG-03-029-06363 | 182.42 | 84659.6 | 4232.98 | Paid | 80426.62 | 2025-Q2
EXP-000088 | 2025-04-24 | BOQ-PKG-08-00088 | PKG-08 | INV-PKG-08-019-00088 | 189.87 | 28053.06 | 1402.65 | Paid | 26650.41 | 2025-Q2
EXP-001731 | 2025-04-24 | BOQ-PKG-01-01731 | PKG-01 | INV-PKG-01-017-01731 | 17.84 | 36030.31 | 1801.52 | Paid | 34228.79 | 2025-Q2
EXP-001943 | 2025-04-24 | BOQ-PKG-03-01943 | PKG-03 | INV-PKG-03-019-01943 | 22.71 | 162082.83 | 8104.14 | Paid | 153978.69 | 2025-Q2
EXP-001958 | 2025-04-24 | BOQ-PKG-08-01958 | PKG-08 | INV-PKG-08-034-01958 | 43.53 | 137281.71 | 6864.09 | Paid | 130417.62 | 2025-Q2
EXP-002409 | 2025-04-24 | BOQ-PKG-09-00419 | PKG-09 | INV-PKG-09-030-02409 | 314.89 | 44353.21 | 2217.66 | Approved Pending Payment | 42135.55 | 2025-Q2
EXP-002887 | 2025-04-24 | BOQ-PKG-07-00897 | PKG-07 | INV-PKG-07-018-02887 | 435.39 | 208936.34 | 10446.82 | Under Review | 198489.52 | 2025-Q2
EXP-002934 | 2025-04-24 | BOQ-PKG-04-00944 | PKG-04 | INV-PKG-04-030-02934 | 114.64 | 115335.91 | 5766.8 | Paid | 109569.11 | 2025-Q2
EXP-003740 | 2025-04-24 | BOQ-PKG-10-01750 | PKG-10 | INV-PKG-10-031-03740 | 163.05 | 77133.72 | 3856.69 | Approved Pending Payment | 73277.03 | 2025-Q2
EXP-006163 | 2025-04-24 | BOQ-PKG-03-00193 | PKG-03 | INV-PKG-03-004-06163 | 241.03 | 147002.45 | 7350.12 | Paid | 139652.33 | 2025-Q2
EXP-000502 | 2025-04-25 | BOQ-PKG-02-00502 | PKG-02 | INV-PKG-02-013-00502 | 427.97 | 94996 | 4749.8 | Paid | 90246.2 | 2025-Q2
EXP-000882 | 2025-04-25 | BOQ-PKG-02-00882 | PKG-02 | INV-PKG-02-008-00882 | 439.11 | 86799.33 | 4339.97 | Paid | 82459.36 | 2025-Q2
EXP-001581 | 2025-04-25 | BOQ-PKG-01-01581 | PKG-01 | INV-PKG-01-007-01581 | 101.43 | 53449.07 | 2672.45 | Paid | 50776.62 | 2025-Q2
EXP-002224 | 2025-04-25 | BOQ-PKG-04-00234 | PKG-04 | INV-PKG-04-020-02224 | 140.05 | 130024.91 | 6501.25 | Paid | 123523.66 | 2025-Q2
EXP-002315 | 2025-04-25 | BOQ-PKG-05-00325 | PKG-05 | INV-PKG-05-006-02315 | 141.54 | 41497.69 | 2074.88 | Paid | 39422.81 | 2025-Q2
EXP-002737 | 2025-04-25 | BOQ-PKG-07-00747 | PKG-07 | INV-PKG-07-008-02737 | 204.4 | 213566 | 10678.3 | Paid | 202887.7 | 2025-Q2
EXP-002988 | 2025-04-25 | BOQ-PKG-08-00998 | PKG-08 | INV-PKG-08-014-02988 | 162.75 | 175656.23 | 8782.81 | Disputed | 166873.42 | 2025-Q2
EXP-005904 | 2025-04-25 | BOQ-PKG-04-01924 | PKG-04 | INV-PKG-04-025-05904 | 419.81 | 42541.72 | 2127.09 | Paid | 40414.63 | 2025-Q2
EXP-006036 | 2025-04-25 | BOQ-PKG-06-00066 | PKG-06 | INV-PKG-06-017-06036 | 269.57 | 124425.21 | 6221.26 | Paid | 118203.95 | 2025-Q2
EXP-006196 | 2025-04-25 | BOQ-PKG-06-00226 | PKG-06 | INV-PKG-06-002-06196 | 57.03 | 77115.44 | 3855.77 | Approved Pending Payment | 73259.67 | 2025-Q2
EXP-002659 | 2025-04-26 | BOQ-PKG-09-00669 | PKG-09 | INV-PKG-09-035-02659 | 386.08 | 120313.73 | 6015.69 | Paid | 114298.04 | 2025-Q2
EXP-003944 | 2025-04-26 | BOQ-PKG-04-01954 | PKG-04 | INV-PKG-04-025-03944 | 350.73 | 166593.18 | 8329.66 | Paid | 158263.52 | 2025-Q2
EXP-000416 | 2025-04-27 | BOQ-PKG-06-00416 | PKG-06 | INV-PKG-06-032-00416 | 215 | 118621.93 | 5931.1 | Approved Pending Payment | 112690.83 | 2025-Q2
EXP-000610 | 2025-04-27 | BOQ-PKG-10-00610 | PKG-10 | INV-PKG-10-016-00610 | 22.83 | 205826.88 | 10291.34 | Paid | 195535.54 | 2025-Q2
EXP-001280 | 2025-04-27 | BOQ-PKG-10-01280 | PKG-10 | INV-PKG-10-021-01280 | 84.39 | 122679.03 | 6133.95 | Approved Pending Payment | 116545.08 | 2025-Q2
EXP-003220 | 2025-04-27 | BOQ-PKG-10-01230 | PKG-10 | INV-PKG-10-001-03220 | 78.53 | 103637.99 | 5181.9 | Paid | 98456.09 | 2025-Q2
EXP-003939 | 2025-04-27 | BOQ-PKG-09-01949 | PKG-09 | INV-PKG-09-020-03939 | 353.03 | 159515.76 | 7975.79 | Paid | 151539.97 | 2025-Q2
EXP-005381 | 2025-04-27 | BOQ-PKG-01-01401 | PKG-01 | INV-PKG-01-027-05381 | 434.63 | 124331 | 6216.55 | Paid | 118114.45 | 2025-Q2
EXP-005485 | 2025-04-27 | BOQ-PKG-05-01505 | PKG-05 | INV-PKG-05-026-05485 | 10.35 | 202281.33 | 10114.07 | Approved Pending Payment | 192167.26 | 2025-Q2
EXP-001308 | 2025-04-28 | BOQ-PKG-08-01308 | PKG-08 | INV-PKG-08-014-01308 | 281.02 | 127904.58 | 6395.23 | Paid | 121509.35 | 2025-Q2
EXP-001369 | 2025-04-28 | BOQ-PKG-09-01369 | PKG-09 | INV-PKG-09-005-01369 | 29.57 | 196298.2 | 9814.91 | Paid | 186483.29 | 2025-Q2
EXP-002365 | 2025-04-28 | BOQ-PKG-05-00375 | PKG-05 | INV-PKG-05-021-02365 | 128 | 129633.17 | 6481.66 | Paid | 123151.51 | 2025-Q2
EXP-003059 | 2025-04-28 | BOQ-PKG-09-01069 | PKG-09 | INV-PKG-09-015-03059 | 446.16 | 31455.9 | 1572.8 | Paid | 29883.1 | 2025-Q2
EXP-004188 | 2025-04-28 | BOQ-PKG-08-00208 | PKG-08 | INV-PKG-08-024-04188 | 279.89 | 191655.18 | 9582.76 | Paid | 182072.42 | 2025-Q2
EXP-004245 | 2025-04-28 | BOQ-PKG-05-00265 | PKG-05 | INV-PKG-05-011-04245 | 215.3 | 129234.45 | 6461.72 | Paid | 122772.73 | 2025-Q2
EXP-001242 | 2025-04-29 | BOQ-PKG-02-01242 | PKG-02 | INV-PKG-02-018-01242 | 382.86 | 182423.24 | 9121.16 | Paid | 173302.08 | 2025-Q2
EXP-001907 | 2025-04-29 | BOQ-PKG-07-01907 | PKG-07 | INV-PKG-07-018-01907 | 425.85 | 166471.88 | 8323.59 | Paid | 158148.29 | 2025-Q2
EXP-002831 | 2025-04-29 | BOQ-PKG-01-00841 | PKG-01 | INV-PKG-01-032-02831 | 197.21 | 100583.11 | 5029.16 | Paid | 95553.95 | 2025-Q2
EXP-003116 | 2025-04-29 | BOQ-PKG-06-01126 | PKG-06 | INV-PKG-06-002-03116 | 313.93 | 37583.4 | 1879.17 | Paid | 35704.23 | 2025-Q2
EXP-003926 | 2025-04-29 | BOQ-PKG-06-01936 | PKG-06 | INV-PKG-06-007-03926 | 429.01 | 143027.98 | 7151.4 | Paid | 135876.58 | 2025-Q2
EXP-004351 | 2025-04-29 | BOQ-PKG-01-00371 | PKG-01 | INV-PKG-01-012-04351 | 285.89 | 86147.05 | 4307.35 | Paid | 81839.7 | 2025-Q2
EXP-004907 | 2025-04-29 | BOQ-PKG-07-00927 | PKG-07 | INV-PKG-07-008-04907 | 177.89 | 199396.4 | 9969.82 | Paid | 189426.58 | 2025-Q2
EXP-005059 | 2025-04-29 | BOQ-PKG-09-01079 | PKG-09 | INV-PKG-09-020-05059 | 195.99 | 26237.46 | 1311.87 | Paid | 24925.59 | 2025-Q2
EXP-005082 | 2025-04-29 | BOQ-PKG-02-01102 | PKG-02 | INV-PKG-02-008-05082 | 154.24 | 158015.17 | 7900.76 | Under Review | 150114.41 | 2025-Q2
EXP-005324 | 2025-04-29 | BOQ-PKG-04-01344 | PKG-04 | INV-PKG-04-005-05324 | 263.47 | 175716.37 | 8785.82 | Paid | 166930.55 | 2025-Q2
EXP-000447 | 2025-04-30 | BOQ-PKG-07-00447 | PKG-07 | INV-PKG-07-028-00447 | 59.88 | 97648.28 | 4882.41 | Approved Pending Payment | 92765.87 | 2025-Q2
EXP-005036 | 2025-04-30 | BOQ-PKG-06-01056 | PKG-06 | INV-PKG-06-032-05036 | 134.53 | 190830.17 | 9541.51 | Paid | 181288.66 | 2025-Q2
EXP-005316 | 2025-04-30 | BOQ-PKG-06-01336 | PKG-06 | INV-PKG-06-032-05316 | 333.17 | 165544.98 | 8277.25 | Paid | 157267.73 | 2025-Q2
EXP-005447 | 2025-04-30 | BOQ-PKG-07-01467 | PKG-07 | INV-PKG-07-023-05447 | 99.7 | 145080.5 | 7254.02 | Paid | 137826.48 | 2025-Q2
EXP-005657 | 2025-04-30 | BOQ-PKG-07-01677 | PKG-07 | INV-PKG-07-023-05657 | 56.22 | 41133.25 | 2056.66 | Paid | 39076.59 | 2025-Q2
EXP-005918 | 2025-04-30 | BOQ-PKG-08-01938 | PKG-08 | INV-PKG-08-004-05918 | 364.37 | 34358.44 | 1717.92 | Paid | 32640.52 | 2025-Q2
EXP-000700 | 2025-05-01 | BOQ-PKG-10-00700 | PKG-10 | INV-PKG-10-001-00700 | 302 | 27086.99 | 1354.35 | Paid | 25732.64 | 2025-Q2
EXP-000809 | 2025-05-01 | BOQ-PKG-09-00809 | PKG-09 | INV-PKG-09-005-00809 | 379.6 | 172343.28 | 8617.16 | Paid | 163726.12 | 2025-Q2
EXP-003723 | 2025-05-01 | BOQ-PKG-03-01733 | PKG-03 | INV-PKG-03-014-03723 | 448.25 | 112853.75 | 5642.69 | Paid | 107211.06 | 2025-Q2
EXP-001148 | 2025-05-02 | BOQ-PKG-08-01148 | PKG-08 | INV-PKG-08-029-01148 | 100.71 | 72764.75 | 3638.24 | Paid | 69126.51 | 2025-Q2
EXP-002139 | 2025-05-02 | BOQ-PKG-09-00149 | PKG-09 | INV-PKG-09-005-02139 | 394.67 | 45217.79 | 2260.89 | Paid | 42956.9 | 2025-Q2
EXP-002303 | 2025-05-02 | BOQ-PKG-03-00313 | PKG-03 | INV-PKG-03-029-02303 | 89.85 | 126213.5 | 6310.68 | Paid | 119902.82 | 2025-Q2
EXP-003151 | 2025-05-02 | BOQ-PKG-01-01161 | PKG-01 | INV-PKG-01-002-03151 | 213.17 | 116234.22 | 5811.71 | Paid | 110422.51 | 2025-Q2
EXP-003169 | 2025-05-02 | BOQ-PKG-09-01179 | PKG-09 | INV-PKG-09-020-03169 | 181.48 | 199314.9 | 9965.75 | Paid | 189349.15 | 2025-Q2
EXP-003329 | 2025-05-02 | BOQ-PKG-09-01339 | PKG-09 | INV-PKG-09-005-03329 | 398.43 | 138772.25 | 6938.61 | Paid | 131833.64 | 2025-Q2
EXP-003459 | 2025-05-02 | BOQ-PKG-09-01469 | PKG-09 | INV-PKG-09-030-03459 | 88.36 | 143281.53 | 7164.08 | Paid | 136117.45 | 2025-Q2
EXP-004132 | 2025-05-02 | BOQ-PKG-02-00152 | PKG-02 | INV-PKG-02-003-04132 | 87.39 | 113976.07 | 5698.8 | Under Review | 108277.27 | 2025-Q2
EXP-000827 | 2025-05-03 | BOQ-PKG-07-00827 | PKG-07 | INV-PKG-07-023-00827 | 140.82 | 208380.16 | 10419.01 | Paid | 197961.15 | 2025-Q2
EXP-000885 | 2025-05-03 | BOQ-PKG-05-00885 | PKG-05 | INV-PKG-05-011-00885 | 419.53 | 133252.48 | 6662.62 | Paid | 126589.86 | 2025-Q2
EXP-001788 | 2025-05-03 | BOQ-PKG-08-01788 | PKG-08 | INV-PKG-08-004-01788 | 177.47 | 133591.9 | 6679.6 | Paid | 126912.3 | 2025-Q2
EXP-002205 | 2025-05-03 | BOQ-PKG-05-00215 | PKG-05 | INV-PKG-05-001-02205 | 337.3 | 124784.11 | 6239.21 | Paid | 118544.9 | 2025-Q2
EXP-003152 | 2025-05-03 | BOQ-PKG-02-01162 | PKG-02 | INV-PKG-02-003-03152 | 240.19 | 155657.54 | 7782.88 | Paid | 147874.66 | 2025-Q2
EXP-004533 | 2025-05-03 | BOQ-PKG-03-00553 | PKG-03 | INV-PKG-03-019-04533 | 273.49 | 209417.92 | 10470.9 | Paid | 198947.02 | 2025-Q2
EXP-004837 | 2025-05-03 | BOQ-PKG-07-00857 | PKG-07 | INV-PKG-07-008-04837 | 362.23 | 74659 | 3732.95 | Approved Pending Payment | 70926.05 | 2025-Q2
EXP-005638 | 2025-05-03 | BOQ-PKG-08-01658 | PKG-08 | INV-PKG-08-004-05638 | 117.66 | 163498.18 | 8174.91 | Approved Pending Payment | 155323.27 | 2025-Q2
EXP-005861 | 2025-05-03 | BOQ-PKG-01-01881 | PKG-01 | INV-PKG-01-017-05861 | 447.3 | 155680.95 | 7784.05 | Paid | 147896.9 | 2025-Q2
EXP-000119 | 2025-05-04 | BOQ-PKG-09-00119 | PKG-09 | INV-PKG-09-015-00119 | 305.33 | 69960.2 | 3498.01 | Approved Pending Payment | 66462.19 | 2025-Q2
EXP-000458 | 2025-05-04 | BOQ-PKG-08-00458 | PKG-08 | INV-PKG-08-004-00458 | 441.73 | 41469.24 | 2073.46 | Paid | 39395.78 | 2025-Q2
EXP-001375 | 2025-05-04 | BOQ-PKG-05-01375 | PKG-05 | INV-PKG-05-011-01375 | 171.86 | 144030.86 | 7201.54 | Paid | 136829.32 | 2025-Q2
EXP-002059 | 2025-05-04 | BOQ-PKG-09-00069 | PKG-09 | INV-PKG-09-030-02059 | 192.95 | 55398.7 | 2769.94 | Paid | 52628.76 | 2025-Q2
EXP-002453 | 2025-05-04 | BOQ-PKG-03-00463 | PKG-03 | INV-PKG-03-004-02453 | 273.94 | 78580.47 | 3929.02 | Paid | 74651.45 | 2025-Q2
EXP-003027 | 2025-05-04 | BOQ-PKG-07-01037 | PKG-07 | INV-PKG-07-018-03027 | 175.75 | 123474.91 | 6173.75 | Paid | 117301.16 | 2025-Q2
EXP-004252 | 2025-05-04 | BOQ-PKG-02-00272 | PKG-02 | INV-PKG-02-018-04252 | 287.69 | 136433.49 | 6821.67 | Paid | 129611.82 | 2025-Q2
EXP-004528 | 2025-05-04 | BOQ-PKG-08-00548 | PKG-08 | INV-PKG-08-014-04528 | 322.66 | 34566.31 | 1728.32 | Paid | 32837.99 | 2025-Q2
EXP-004940 | 2025-05-04 | BOQ-PKG-10-00960 | PKG-10 | INV-PKG-10-006-04940 | 234.86 | 31816.36 | 1590.82 | Paid | 30225.54 | 2025-Q2
EXP-005053 | 2025-05-04 | BOQ-PKG-03-01073 | PKG-03 | INV-PKG-03-014-05053 | 71.77 | 164057.57 | 8202.88 | Paid | 155854.69 | 2025-Q2
EXP-005395 | 2025-05-04 | BOQ-PKG-05-01415 | PKG-05 | INV-PKG-05-006-05395 | 180.68 | 125924.76 | 6296.24 | Paid | 119628.52 | 2025-Q2
EXP-001103 | 2025-05-05 | BOQ-PKG-03-01103 | PKG-03 | INV-PKG-03-019-01103 | 24.31 | 86766.1 | 4338.3 | Paid | 82427.8 | 2025-Q2
EXP-002662 | 2025-05-05 | BOQ-PKG-02-00672 | PKG-02 | INV-PKG-02-003-02662 | 282.64 | 68440.8 | 3422.04 | Paid | 65018.76 | 2025-Q2
EXP-002721 | 2025-05-05 | BOQ-PKG-01-00731 | PKG-01 | INV-PKG-01-027-02721 | 169.16 | 44451.7 | 2222.58 | Paid | 42229.12 | 2025-Q2
EXP-002999 | 2025-05-05 | BOQ-PKG-09-01009 | PKG-09 | INV-PKG-09-025-02999 | 115.22 | 154295.47 | 7714.77 | Paid | 146580.7 | 2025-Q2
EXP-003996 | 2025-05-05 | BOQ-PKG-06-00016 | PKG-06 | INV-PKG-06-007-03996 | 276.57 | 59399.58 | 2969.98 | Paid | 56429.6 | 2025-Q2
EXP-004432 | 2025-05-05 | BOQ-PKG-02-00452 | PKG-02 | INV-PKG-02-023-04432 | 292.55 | 138177.14 | 6908.86 | Paid | 131268.28 | 2025-Q2
EXP-005570 | 2025-05-05 | BOQ-PKG-10-01590 | PKG-10 | INV-PKG-10-006-05570 | 353.53 | 83212.45 | 4160.62 | Paid | 79051.83 | 2025-Q2
EXP-000579 | 2025-05-06 | BOQ-PKG-09-00579 | PKG-09 | INV-PKG-09-020-00579 | 41.9 | 137951.14 | 6897.56 | Approved Pending Payment | 131053.58 | 2025-Q2
EXP-001611 | 2025-05-06 | BOQ-PKG-01-01611 | PKG-01 | INV-PKG-01-002-01611 | 155.71 | 165849.34 | 8292.47 | Under Review | 157556.87 | 2025-Q2
EXP-002468 | 2025-05-06 | BOQ-PKG-08-00478 | PKG-08 | INV-PKG-08-019-02468 | 196.22 | 156828.56 | 7841.43 | Paid | 148987.13 | 2025-Q2
EXP-003142 | 2025-05-06 | BOQ-PKG-02-01152 | PKG-02 | INV-PKG-02-028-03142 | 208.03 | 103170.41 | 5158.52 | Paid | 98011.89 | 2025-Q2
EXP-004318 | 2025-05-06 | BOQ-PKG-08-00338 | PKG-08 | INV-PKG-08-014-04318 | 130.94 | 105802.23 | 5290.11 | Approved Pending Payment | 100512.12 | 2025-Q2
EXP-005650 | 2025-05-06 | BOQ-PKG-10-01670 | PKG-10 | INV-PKG-10-016-05650 | 239.93 | 68163.55 | 3408.18 | Paid | 64755.37 | 2025-Q2
EXP-006277 | 2025-05-06 | BOQ-PKG-07-00307 | PKG-07 | INV-PKG-07-013-06277 | 415.46 | 108902.38 | 5445.12 | Paid | 103457.26 | 2025-Q2
EXP-006426 | 2025-05-06 | BOQ-PKG-06-00456 | PKG-06 | INV-PKG-06-022-06426 | 362.42 | 71855.74 | 3592.79 | Approved Pending Payment | 68262.95 | 2025-Q2
EXP-006705 | 2025-05-06 | BOQ-PKG-05-00735 | PKG-05 | INV-PKG-05-021-06705 | 216.23 | 80570.33 | 4028.52 | Paid | 76541.81 | 2025-Q2
EXP-000662 | 2025-05-07 | BOQ-PKG-02-00662 | PKG-02 | INV-PKG-02-033-00662 | 247.47 | 79571.93 | 3978.6 | Approved Pending Payment | 75593.33 | 2025-Q2
EXP-000759 | 2025-05-07 | BOQ-PKG-09-00759 | PKG-09 | INV-PKG-09-025-00759 | 320.4 | 69450.01 | 3472.5 | Paid | 65977.51 | 2025-Q2
EXP-001799 | 2025-05-07 | BOQ-PKG-09-01799 | PKG-09 | INV-PKG-09-015-01799 | 417.17 | 173670.64 | 8683.53 | Disputed | 164987.11 | 2025-Q2
EXP-002197 | 2025-05-07 | BOQ-PKG-07-00207 | PKG-07 | INV-PKG-07-028-02197 | 347.09 | 181958.21 | 9097.91 | Paid | 172860.3 | 2025-Q2
EXP-002581 | 2025-05-07 | BOQ-PKG-01-00591 | PKG-01 | INV-PKG-01-027-02581 | 366.54 | 163971.2 | 8198.56 | Paid | 155772.64 | 2025-Q2
EXP-002953 | 2025-05-07 | BOQ-PKG-03-00963 | PKG-03 | INV-PKG-03-014-02953 | 151.34 | 153424.58 | 7671.23 | Paid | 145753.35 | 2025-Q2
EXP-003465 | 2025-05-07 | BOQ-PKG-05-01475 | PKG-05 | INV-PKG-05-001-03465 | 367.46 | 181041.99 | 9052.1 | Paid | 171989.89 | 2025-Q2
EXP-003727 | 2025-05-07 | BOQ-PKG-07-01737 | PKG-07 | INV-PKG-07-018-03727 | 321.44 | 161926.99 | 8096.35 | Paid | 153830.64 | 2025-Q2
EXP-004121 | 2025-05-07 | BOQ-PKG-01-00141 | PKG-01 | INV-PKG-01-027-04121 | 31.55 | 100241.78 | 5012.09 | Paid | 95229.69 | 2025-Q2
EXP-005723 | 2025-05-07 | BOQ-PKG-03-01743 | PKG-03 | INV-PKG-03-019-05723 | 46.33 | 198827.51 | 9941.38 | Paid | 188886.13 | 2025-Q2
EXP-000222 | 2025-05-08 | BOQ-PKG-02-00222 | PKG-02 | INV-PKG-02-013-00222 | 347.09 | 35717.29 | 1785.86 | Paid | 33931.43 | 2025-Q2
EXP-000946 | 2025-05-08 | BOQ-PKG-06-00946 | PKG-06 | INV-PKG-06-002-00946 | 336.1 | 113903.6 | 5695.18 | Approved Pending Payment | 108208.42 | 2025-Q2
EXP-000954 | 2025-05-08 | BOQ-PKG-04-00954 | PKG-04 | INV-PKG-04-010-00954 | 71.55 | 42048.15 | 2102.41 | Paid | 39945.74 | 2025-Q2
EXP-001078 | 2025-05-08 | BOQ-PKG-08-01078 | PKG-08 | INV-PKG-08-029-01078 | 241.44 | 178328.4 | 8916.42 | Paid | 169411.98 | 2025-Q2
EXP-001297 | 2025-05-08 | BOQ-PKG-07-01297 | PKG-07 | INV-PKG-07-003-01297 | 238.74 | 212434.03 | 10621.7 | Paid | 201812.33 | 2025-Q2
EXP-003730 | 2025-05-08 | BOQ-PKG-10-01740 | PKG-10 | INV-PKG-10-021-03730 | 290.56 | 86314.76 | 4315.74 | Paid | 81999.02 | 2025-Q2
EXP-005488 | 2025-05-08 | BOQ-PKG-08-01508 | PKG-08 | INV-PKG-08-029-05488 | 203.99 | 170430.52 | 8521.53 | Paid | 161908.99 | 2025-Q2
EXP-006259 | 2025-05-08 | BOQ-PKG-09-00289 | PKG-09 | INV-PKG-09-030-06259 | 119.56 | 66464.29 | 3323.21 | Paid | 63141.08 | 2025-Q2
EXP-000298 | 2025-05-09 | BOQ-PKG-08-00298 | PKG-08 | INV-PKG-08-019-00298 | 351.09 | 189172.81 | 9458.64 | Paid | 179714.17 | 2025-Q2
EXP-000977 | 2025-05-09 | BOQ-PKG-07-00977 | PKG-07 | INV-PKG-07-033-00977 | 368.61 | 186371.38 | 9318.57 | Paid | 177052.81 | 2025-Q2
EXP-001370 | 2025-05-09 | BOQ-PKG-10-01370 | PKG-10 | INV-PKG-10-006-01370 | 16.41 | 202017.5 | 10100.88 | Paid | 191916.62 | 2025-Q2
EXP-002146 | 2025-05-09 | BOQ-PKG-06-00156 | PKG-06 | INV-PKG-06-012-02146 | 246.95 | 109973.59 | 5498.68 | Paid | 104474.91 | 2025-Q2
EXP-002410 | 2025-05-09 | BOQ-PKG-10-00420 | PKG-10 | INV-PKG-10-031-02410 | 317.7 | 160027.53 | 8001.38 | Under Review | 152026.15 | 2025-Q2
EXP-002635 | 2025-05-09 | BOQ-PKG-05-00645 | PKG-05 | INV-PKG-05-011-02635 | 207.8 | 211950.59 | 10597.53 | Approved Pending Payment | 201353.06 | 2025-Q2
EXP-002827 | 2025-05-09 | BOQ-PKG-07-00837 | PKG-07 | INV-PKG-07-028-02827 | 42.92 | 32673.77 | 1633.69 | Paid | 31040.08 | 2025-Q2
EXP-002940 | 2025-05-09 | BOQ-PKG-10-00950 | PKG-10 | INV-PKG-10-001-02940 | 434.88 | 203649.39 | 10182.47 | Approved Pending Payment | 193466.92 | 2025-Q2
EXP-003550 | 2025-05-09 | BOQ-PKG-10-01560 | PKG-10 | INV-PKG-10-016-03550 | 291.89 | 196928.6 | 9846.43 | Paid | 187082.17 | 2025-Q2
EXP-006140 | 2025-05-09 | BOQ-PKG-10-00170 | PKG-10 | INV-PKG-10-016-06140 | 222.19 | 90722.78 | 4536.14 | Paid | 86186.64 | 2025-Q2
EXP-006298 | 2025-05-09 | BOQ-PKG-08-00328 | PKG-08 | INV-PKG-08-034-06298 | 239.13 | 63162.47 | 3158.12 | Paid | 60004.35 | 2025-Q2
EXP-006483 | 2025-05-09 | BOQ-PKG-03-00513 | PKG-03 | INV-PKG-03-009-06483 | 128.55 | 206800.03 | 10340 | Approved Pending Payment | 196460.03 | 2025-Q2
EXP-006548 | 2025-05-09 | BOQ-PKG-08-00578 | PKG-08 | INV-PKG-08-004-06548 | 391.89 | 206927.19 | 10346.36 | Paid | 196580.83 | 2025-Q2
EXP-006734 | 2025-05-09 | BOQ-PKG-04-00764 | PKG-04 | INV-PKG-04-015-06734 | 120.49 | 198756.38 | 9937.82 | Paid | 188818.56 | 2025-Q2
EXP-000848 | 2025-05-10 | BOQ-PKG-08-00848 | PKG-08 | INV-PKG-08-009-00848 | 255.46 | 81123.98 | 4056.2 | Approved Pending Payment | 77067.78 | 2025-Q2
EXP-002741 | 2025-05-10 | BOQ-PKG-01-00751 | PKG-01 | INV-PKG-01-012-02741 | 349.13 | 151042.91 | 7552.15 | Paid | 143490.76 | 2025-Q2
EXP-003021 | 2025-05-10 | BOQ-PKG-01-01031 | PKG-01 | INV-PKG-01-012-03021 | 346.05 | 65812.17 | 3290.61 | Under Review | 62521.56 | 2025-Q2
EXP-003500 | 2025-05-10 | BOQ-PKG-10-01510 | PKG-10 | INV-PKG-10-001-03500 | 146.65 | 69168.43 | 3458.42 | Paid | 65710.01 | 2025-Q2
EXP-005480 | 2025-05-10 | BOQ-PKG-10-01500 | PKG-10 | INV-PKG-10-021-05480 | 398.69 | 31128.88 | 1556.44 | Paid | 29572.44 | 2025-Q2
EXP-005749 | 2025-05-10 | BOQ-PKG-09-01769 | PKG-09 | INV-PKG-09-010-05749 | 224.68 | 36938.36 | 1846.92 | Paid | 35091.44 | 2025-Q2
EXP-006008 | 2025-05-10 | BOQ-PKG-08-00038 | PKG-08 | INV-PKG-08-024-06008 | 388.1 | 186758.33 | 9337.92 | Approved Pending Payment | 177420.41 | 2025-Q2
EXP-006684 | 2025-05-10 | BOQ-PKG-04-00714 | PKG-04 | INV-PKG-04-035-06684 | 186.78 | 191390.54 | 9569.53 | Paid | 181821.01 | 2025-Q2
EXP-001141 | 2025-05-11 | BOQ-PKG-01-01141 | PKG-01 | INV-PKG-01-022-01141 | 15.67 | 84447.35 | 4222.37 | Paid | 80224.98 | 2025-Q2
EXP-001492 | 2025-05-11 | BOQ-PKG-02-01492 | PKG-02 | INV-PKG-02-023-01492 | 225.65 | 203696.82 | 10184.84 | Approved Pending Payment | 193511.98 | 2025-Q2
EXP-001556 | 2025-05-11 | BOQ-PKG-06-01556 | PKG-06 | INV-PKG-06-017-01556 | 365.54 | 186408.34 | 9320.42 | Paid | 177087.92 | 2025-Q2
EXP-002811 | 2025-05-11 | BOQ-PKG-01-00821 | PKG-01 | INV-PKG-01-012-02811 | 283.51 | 151738.31 | 7586.92 | Approved Pending Payment | 144151.39 | 2025-Q2
EXP-003908 | 2025-05-11 | BOQ-PKG-08-01918 | PKG-08 | INV-PKG-08-024-03908 | 265.73 | 69203.66 | 3460.18 | Under Review | 65743.48 | 2025-Q2
EXP-004165 | 2025-05-11 | BOQ-PKG-05-00185 | PKG-05 | INV-PKG-05-001-04165 | 420.91 | 186108.16 | 9305.41 | Paid | 176802.75 | 2025-Q2
EXP-005067 | 2025-05-11 | BOQ-PKG-07-01087 | PKG-07 | INV-PKG-07-028-05067 | 293.67 | 127998.93 | 6399.95 | Paid | 121598.98 | 2025-Q2
EXP-005675 | 2025-05-11 | BOQ-PKG-05-01695 | PKG-05 | INV-PKG-05-006-05675 | 346.15 | 159908.87 | 7995.44 | Paid | 151913.43 | 2025-Q2
EXP-003633 | 2025-05-12 | BOQ-PKG-03-01643 | PKG-03 | INV-PKG-03-029-03633 | 137.6 | 55042.2 | 2752.11 | Disputed | 52290.09 | 2025-Q2
EXP-003953 | 2025-05-12 | BOQ-PKG-03-01963 | PKG-03 | INV-PKG-03-034-03953 | 128.58 | 78754.69 | 3937.73 | Paid | 74816.96 | 2025-Q2
EXP-004899 | 2025-05-12 | BOQ-PKG-09-00919 | PKG-09 | INV-PKG-09-035-04899 | 329.89 | 157489.48 | 7874.47 | Paid | 149615.01 | 2025-Q2
EXP-004912 | 2025-05-12 | BOQ-PKG-02-00932 | PKG-02 | INV-PKG-02-013-04912 | 255.37 | 153732.67 | 7686.63 | Paid | 146046.04 | 2025-Q2
EXP-005787 | 2025-05-12 | BOQ-PKG-07-01807 | PKG-07 | INV-PKG-07-013-05787 | 318.61 | 106697.97 | 5334.9 | Paid | 101363.07 | 2025-Q2
EXP-005805 | 2025-05-12 | BOQ-PKG-05-01825 | PKG-05 | INV-PKG-05-031-05805 | 141.25 | 193683.88 | 9684.19 | Paid | 183999.69 | 2025-Q2
EXP-006819 | 2025-05-12 | BOQ-PKG-09-00849 | PKG-09 | INV-PKG-09-030-06819 | 103.94 | 116548.82 | 5827.44 | Paid | 110721.38 | 2025-Q2
EXP-001123 | 2025-05-13 | BOQ-PKG-03-01123 | PKG-03 | INV-PKG-03-004-01123 | 61.89 | 160608.81 | 8030.44 | Paid | 152578.37 | 2025-Q2
EXP-001316 | 2025-05-13 | BOQ-PKG-06-01316 | PKG-06 | INV-PKG-06-022-01316 | 51.65 | 181446.6 | 9072.33 | Disputed | 172374.27 | 2025-Q2
EXP-001452 | 2025-05-13 | BOQ-PKG-02-01452 | PKG-02 | INV-PKG-02-018-01452 | 240.45 | 186984.69 | 9349.23 | Paid | 177635.46 | 2025-Q2
EXP-001616 | 2025-05-13 | BOQ-PKG-06-01616 | PKG-06 | INV-PKG-06-007-01616 | 365.82 | 102435.97 | 5121.8 | Paid | 97314.17 | 2025-Q2
EXP-002613 | 2025-05-13 | BOQ-PKG-03-00623 | PKG-03 | INV-PKG-03-024-02613 | 237.8 | 65229.49 | 3261.47 | Paid | 61968.02 | 2025-Q2
EXP-005026 | 2025-05-13 | BOQ-PKG-06-01046 | PKG-06 | INV-PKG-06-022-05026 | 275.14 | 164632.77 | 8231.64 | Paid | 156401.13 | 2025-Q2
EXP-000137 | 2025-05-14 | BOQ-PKG-07-00137 | PKG-07 | INV-PKG-07-033-00137 | 273.92 | 112825.02 | 5641.25 | Approved Pending Payment | 107183.77 | 2025-Q2
EXP-000282 | 2025-05-14 | BOQ-PKG-02-00282 | PKG-02 | INV-PKG-02-003-00282 | 203.26 | 205623 | 10281.15 | Under Review | 195341.85 | 2025-Q2
EXP-001328 | 2025-05-14 | BOQ-PKG-08-01328 | PKG-08 | INV-PKG-08-034-01328 | 418.44 | 181821.16 | 9091.06 | Paid | 172730.1 | 2025-Q2
EXP-002536 | 2025-05-14 | BOQ-PKG-06-00546 | PKG-06 | INV-PKG-06-017-02536 | 256.53 | 24487.23 | 1224.36 | Paid | 23262.87 | 2025-Q2
EXP-002912 | 2025-05-14 | BOQ-PKG-02-00922 | PKG-02 | INV-PKG-02-008-02912 | 76.36 | 187847.95 | 9392.4 | Approved Pending Payment | 178455.55 | 2025-Q2
EXP-003859 | 2025-05-14 | BOQ-PKG-09-01869 | PKG-09 | INV-PKG-09-010-03859 | 30.92 | 132138.55 | 6606.93 | Paid | 125531.62 | 2025-Q2
EXP-004848 | 2025-05-14 | BOQ-PKG-08-00868 | PKG-08 | INV-PKG-08-019-04848 | 100.11 | 117497.36 | 5874.87 | Paid | 111622.49 | 2025-Q2
EXP-000258 | 2025-05-15 | BOQ-PKG-08-00258 | PKG-08 | INV-PKG-08-014-00258 | 134.44 | 114709.32 | 5735.47 | Paid | 108973.85 | 2025-Q2
EXP-001063 | 2025-05-15 | BOQ-PKG-03-01063 | PKG-03 | INV-PKG-03-014-01063 | 249.23 | 125084.1 | 6254.21 | Under Review | 118829.89 | 2025-Q2
EXP-001195 | 2025-05-15 | BOQ-PKG-05-01195 | PKG-05 | INV-PKG-05-006-01195 | 304.36 | 94345.27 | 4717.26 | Paid | 89628.01 | 2025-Q2
EXP-001251 | 2025-05-15 | BOQ-PKG-01-01251 | PKG-01 | INV-PKG-01-027-01251 | 152.12 | 184226.32 | 9211.32 | Approved Pending Payment | 175015 | 2025-Q2
EXP-002965 | 2025-05-15 | BOQ-PKG-05-00975 | PKG-05 | INV-PKG-05-026-02965 | 374.69 | 103085.21 | 5154.26 | Paid | 97930.95 | 2025-Q2
EXP-003112 | 2025-05-15 | BOQ-PKG-02-01122 | PKG-02 | INV-PKG-02-033-03112 | 219.36 | 161396.34 | 8069.82 | Paid | 153326.52 | 2025-Q2
EXP-005330 | 2025-05-15 | BOQ-PKG-10-01350 | PKG-10 | INV-PKG-10-011-05330 | 273.76 | 87562.66 | 4378.13 | Paid | 83184.53 | 2025-Q2
EXP-000415 | 2025-05-16 | BOQ-PKG-05-00415 | PKG-05 | INV-PKG-05-031-00415 | 427.87 | 122929.98 | 6146.5 | Approved Pending Payment | 116783.48 | 2025-Q2
EXP-000914 | 2025-05-16 | BOQ-PKG-04-00914 | PKG-04 | INV-PKG-04-005-00914 | 362.36 | 92881.54 | 4644.08 | Paid | 88237.46 | 2025-Q2
EXP-001407 | 2025-05-16 | BOQ-PKG-07-01407 | PKG-07 | INV-PKG-07-008-01407 | 305.71 | 199307.35 | 9965.37 | Under Review | 189341.98 | 2025-Q2
EXP-001933 | 2025-05-16 | BOQ-PKG-03-01933 | PKG-03 | INV-PKG-03-009-01933 | 216.66 | 145035.27 | 7251.76 | Paid | 137783.51 | 2025-Q2
EXP-004285 | 2025-05-16 | BOQ-PKG-05-00305 | PKG-05 | INV-PKG-05-016-04285 | 291.92 | 35305.64 | 1765.28 | Paid | 33540.36 | 2025-Q2
EXP-000037 | 2025-05-17 | BOQ-PKG-07-00037 | PKG-07 | INV-PKG-07-003-00037 | 42.85 | 125230.44 | 6261.52 | Paid | 118968.92 | 2025-Q2
EXP-001385 | 2025-05-17 | BOQ-PKG-05-01385 | PKG-05 | INV-PKG-05-021-01385 | 267 | 173513.55 | 8675.68 | Paid | 164837.87 | 2025-Q2
EXP-003093 | 2025-05-17 | BOQ-PKG-03-01103 | PKG-03 | INV-PKG-03-014-03093 | 263.59 | 53170.3 | 2658.52 | Paid | 50511.78 | 2025-Q2
EXP-004735 | 2025-05-17 | BOQ-PKG-05-00755 | PKG-05 | INV-PKG-05-011-04735 | 36.99 | 107855.39 | 5392.77 | Paid | 102462.62 | 2025-Q2
EXP-006385 | 2025-05-17 | BOQ-PKG-05-00415 | PKG-05 | INV-PKG-05-016-06385 | 102.1 | 111594.25 | 5579.71 | Under Review | 106014.54 | 2025-Q2
EXP-000881 | 2025-05-18 | BOQ-PKG-01-00881 | PKG-01 | INV-PKG-01-007-00881 | 80.95 | 151789.26 | 7589.46 | Paid | 144199.8 | 2025-Q2
EXP-001004 | 2025-05-18 | BOQ-PKG-04-01004 | PKG-04 | INV-PKG-04-025-01004 | 78.59 | 200147.26 | 10007.36 | Under Review | 190139.9 | 2025-Q2
EXP-001568 | 2025-05-18 | BOQ-PKG-08-01568 | PKG-08 | INV-PKG-08-029-01568 | 258.52 | 66624.6 | 3331.23 | Paid | 63293.37 | 2025-Q2
EXP-002532 | 2025-05-18 | BOQ-PKG-02-00542 | PKG-02 | INV-PKG-02-013-02532 | 372.97 | 37693.83 | 1884.69 | Approved Pending Payment | 35809.14 | 2025-Q2
EXP-002704 | 2025-05-18 | BOQ-PKG-04-00714 | PKG-04 | INV-PKG-04-010-02704 | 218.57 | 136624.06 | 6831.2 | Under Review | 129792.86 | 2025-Q2
EXP-005086 | 2025-05-18 | BOQ-PKG-06-01106 | PKG-06 | INV-PKG-06-012-05086 | 132.05 | 206395.73 | 10319.79 | Paid | 196075.94 | 2025-Q2
EXP-005479 | 2025-05-18 | BOQ-PKG-09-01499 | PKG-09 | INV-PKG-09-020-05479 | 383.89 | 56646.7 | 2832.34 | Paid | 53814.36 | 2025-Q2
EXP-005999 | 2025-05-18 | BOQ-PKG-09-00029 | PKG-09 | INV-PKG-09-015-05999 | 64.68 | 45565.65 | 2278.28 | Approved Pending Payment | 43287.37 | 2025-Q2
EXP-006576 | 2025-05-18 | BOQ-PKG-06-00606 | PKG-06 | INV-PKG-06-032-06576 | 274.71 | 111154.33 | 5557.72 | Paid | 105596.61 | 2025-Q2
EXP-000768 | 2025-05-19 | BOQ-PKG-08-00768 | PKG-08 | INV-PKG-08-034-00768 | 117.8 | 205892.62 | 10294.63 | Paid | 195597.99 | 2025-Q2
EXP-001105 | 2025-05-19 | BOQ-PKG-05-01105 | PKG-05 | INV-PKG-05-021-01105 | 332.53 | 132205.61 | 6610.28 | Paid | 125595.33 | 2025-Q2
EXP-001865 | 2025-05-19 | BOQ-PKG-05-01865 | PKG-05 | INV-PKG-05-011-01865 | 99.98 | 127355.42 | 6367.77 | Paid | 120987.65 | 2025-Q2
EXP-002130 | 2025-05-19 | BOQ-PKG-10-00140 | PKG-10 | INV-PKG-10-031-02130 | 153.08 | 76518.66 | 3825.93 | Paid | 72692.73 | 2025-Q2
EXP-002514 | 2025-05-19 | BOQ-PKG-04-00524 | PKG-04 | INV-PKG-04-030-02514 | 446.38 | 34112.08 | 1705.6 | Paid | 32406.48 | 2025-Q2
EXP-002611 | 2025-05-19 | BOQ-PKG-01-00621 | PKG-01 | INV-PKG-01-022-02611 | 202.95 | 89589.16 | 4479.46 | Paid | 85109.7 | 2025-Q2
EXP-004624 | 2025-05-19 | BOQ-PKG-04-00644 | PKG-04 | INV-PKG-04-005-04624 | 202.69 | 84179.8 | 4208.99 | Paid | 79970.81 | 2025-Q2
EXP-004703 | 2025-05-19 | BOQ-PKG-03-00723 | PKG-03 | INV-PKG-03-014-04703 | 396.8 | 66655.98 | 3332.8 | Paid | 63323.18 | 2025-Q2
EXP-006436 | 2025-05-19 | BOQ-PKG-06-00466 | PKG-06 | INV-PKG-06-032-06436 | 105.1 | 120093.11 | 6004.66 | Paid | 114088.45 | 2025-Q2
EXP-006814 | 2025-05-19 | BOQ-PKG-04-00844 | PKG-04 | INV-PKG-04-025-06814 | 399.25 | 192207.91 | 9610.4 | Paid | 182597.51 | 2025-Q2
EXP-002553 | 2025-05-20 | BOQ-PKG-03-00563 | PKG-03 | INV-PKG-03-034-02553 | 407.76 | 176920.74 | 8846.04 | Paid | 168074.7 | 2025-Q2
EXP-002899 | 2025-05-20 | BOQ-PKG-09-00909 | PKG-09 | INV-PKG-09-030-02899 | 380.3 | 104843.74 | 5242.19 | Under Review | 99601.55 | 2025-Q2
EXP-005946 | 2025-05-20 | BOQ-PKG-06-01966 | PKG-06 | INV-PKG-06-032-05946 | 75.93 | 195983.23 | 9799.16 | Under Review | 186184.07 | 2025-Q2
EXP-006574 | 2025-05-20 | BOQ-PKG-04-00604 | PKG-04 | INV-PKG-04-030-06574 | 146.62 | 33271.71 | 1663.59 | Paid | 31608.12 | 2025-Q2
EXP-000220 | 2025-05-21 | BOQ-PKG-10-00220 | PKG-10 | INV-PKG-10-011-00220 | 278.31 | 68027.46 | 3401.37 | Paid | 64626.09 | 2025-Q2
EXP-000305 | 2025-05-21 | BOQ-PKG-05-00305 | PKG-05 | INV-PKG-05-026-00305 | 27.77 | 67372.87 | 3368.64 | Paid | 64004.23 | 2025-Q2
EXP-001239 | 2025-05-21 | BOQ-PKG-09-01239 | PKG-09 | INV-PKG-09-015-01239 | 67.26 | 117331.4 | 5866.57 | Paid | 111464.83 | 2025-Q2
EXP-002713 | 2025-05-21 | BOQ-PKG-03-00723 | PKG-03 | INV-PKG-03-019-02713 | 351.7 | 133866.43 | 6693.32 | Paid | 127173.11 | 2025-Q2
EXP-003817 | 2025-05-21 | BOQ-PKG-07-01827 | PKG-07 | INV-PKG-07-003-03817 | 248.72 | 87259.23 | 4362.96 | Paid | 82896.27 | 2025-Q2
EXP-004550 | 2025-05-21 | BOQ-PKG-10-00570 | PKG-10 | INV-PKG-10-001-04550 | 206.6 | 157870.56 | 7893.53 | Disputed | 149977.03 | 2025-Q2
EXP-006511 | 2025-05-21 | BOQ-PKG-01-00541 | PKG-01 | INV-PKG-01-002-06511 | 83.63 | 35039.48 | 1751.97 | Paid | 33287.51 | 2025-Q2
EXP-006727 | 2025-05-21 | BOQ-PKG-07-00757 | PKG-07 | INV-PKG-07-008-06727 | 183.57 | 186857.23 | 9342.86 | Paid | 177514.37 | 2025-Q2
EXP-005618 | 2025-05-22 | BOQ-PKG-08-01638 | PKG-08 | INV-PKG-08-019-05618 | 369.33 | 30156.25 | 1507.81 | Paid | 28648.44 | 2025-Q2
EXP-005774 | 2025-05-22 | BOQ-PKG-04-01794 | PKG-04 | INV-PKG-04-035-05774 | 240.86 | 153789.35 | 7689.47 | Paid | 146099.88 | 2025-Q2
EXP-001077 | 2025-05-23 | BOQ-PKG-07-01077 | PKG-07 | INV-PKG-07-028-01077 | 374.46 | 99766.53 | 4988.33 | Paid | 94778.2 | 2025-Q2
EXP-002344 | 2025-05-23 | BOQ-PKG-04-00354 | PKG-04 | INV-PKG-04-035-02344 | 384.3 | 157533.53 | 7876.68 | Paid | 149656.85 | 2025-Q2
EXP-003160 | 2025-05-23 | BOQ-PKG-10-01170 | PKG-10 | INV-PKG-10-011-03160 | 178.34 | 119092.56 | 5954.63 | Paid | 113137.93 | 2025-Q2
EXP-003560 | 2025-05-23 | BOQ-PKG-10-01570 | PKG-10 | INV-PKG-10-026-03560 | 442.85 | 118574.7 | 5928.74 | Paid | 112645.96 | 2025-Q2
EXP-004471 | 2025-05-23 | BOQ-PKG-01-00491 | PKG-01 | INV-PKG-01-027-04471 | 187.13 | 76253.75 | 3812.69 | Paid | 72441.06 | 2025-Q2
EXP-005127 | 2025-05-23 | BOQ-PKG-07-01147 | PKG-07 | INV-PKG-07-018-05127 | 232.1 | 144065.23 | 7203.26 | Paid | 136861.97 | 2025-Q2
EXP-001245 | 2025-05-24 | BOQ-PKG-05-01245 | PKG-05 | INV-PKG-05-021-01245 | 81.58 | 79833.14 | 3991.66 | Paid | 75841.48 | 2025-Q2
EXP-001828 | 2025-05-24 | BOQ-PKG-08-01828 | PKG-08 | INV-PKG-08-009-01828 | 152.25 | 129718.95 | 6485.95 | Paid | 123233 | 2025-Q2
EXP-003195 | 2025-05-24 | BOQ-PKG-05-01205 | PKG-05 | INV-PKG-05-011-03195 | 429 | 137824.79 | 6891.24 | Paid | 130933.55 | 2025-Q2
EXP-003197 | 2025-05-24 | BOQ-PKG-07-01207 | PKG-07 | INV-PKG-07-013-03197 | 91.37 | 157492.86 | 7874.64 | Paid | 149618.22 | 2025-Q2
EXP-006264 | 2025-05-24 | BOQ-PKG-04-00294 | PKG-04 | INV-PKG-04-035-06264 | 407.48 | 187716.38 | 9385.82 | Paid | 178330.56 | 2025-Q2
EXP-006966 | 2025-05-24 | BOQ-PKG-06-00996 | PKG-06 | INV-PKG-06-002-06966 | 163.53 | 183200.43 | 9160.02 | Paid | 174040.41 | 2025-Q2
EXP-001263 | 2025-05-25 | BOQ-PKG-03-01263 | PKG-03 | INV-PKG-03-004-01263 | 8.21 | 84202.66 | 4210.13 | Paid | 79992.53 | 2025-Q2
EXP-002220 | 2025-05-25 | BOQ-PKG-10-00230 | PKG-10 | INV-PKG-10-016-02220 | 24.23 | 84973.54 | 4248.68 | Paid | 80724.86 | 2025-Q2
EXP-002474 | 2025-05-25 | BOQ-PKG-04-00484 | PKG-04 | INV-PKG-04-025-02474 | 165.19 | 27063.44 | 1353.17 | Paid | 25710.27 | 2025-Q2
EXP-003035 | 2025-05-25 | BOQ-PKG-05-01045 | PKG-05 | INV-PKG-05-026-03035 | 323.43 | 43716.06 | 2185.8 | Under Review | 41530.26 | 2025-Q2
EXP-003342 | 2025-05-25 | BOQ-PKG-02-01352 | PKG-02 | INV-PKG-02-018-03342 | 231.51 | 85117.9 | 4255.89 | Paid | 80862.01 | 2025-Q2
EXP-004039 | 2025-05-25 | BOQ-PKG-09-00059 | PKG-09 | INV-PKG-09-015-04039 | 235.94 | 95856.58 | 4792.83 | Paid | 91063.75 | 2025-Q2
EXP-006414 | 2025-05-25 | BOQ-PKG-04-00444 | PKG-04 | INV-PKG-04-010-06414 | 141.98 | 31680.51 | 1584.03 | Approved Pending Payment | 30096.48 | 2025-Q2
EXP-006820 | 2025-05-25 | BOQ-PKG-10-00850 | PKG-10 | INV-PKG-10-031-06820 | 106.64 | 142035.16 | 7101.76 | Paid | 134933.4 | 2025-Q2
EXP-002100 | 2025-05-26 | BOQ-PKG-10-00110 | PKG-10 | INV-PKG-10-001-02100 | 412.09 | 201847.86 | 10092.39 | Paid | 191755.47 | 2025-Q2
EXP-002111 | 2025-05-26 | BOQ-PKG-01-00121 | PKG-01 | INV-PKG-01-012-02111 | 442.19 | 35103.24 | 1755.16 | Approved Pending Payment | 33348.08 | 2025-Q2
EXP-002646 | 2025-05-26 | BOQ-PKG-06-00656 | PKG-06 | INV-PKG-06-022-02646 | 233.95 | 113435.56 | 5671.78 | Approved Pending Payment | 107763.78 | 2025-Q2
EXP-003297 | 2025-05-26 | BOQ-PKG-07-01307 | PKG-07 | INV-PKG-07-008-03297 | 62.14 | 87944.66 | 4397.23 | Disputed | 83547.43 | 2025-Q2
EXP-003805 | 2025-05-26 | BOQ-PKG-05-01815 | PKG-05 | INV-PKG-05-026-03805 | 86.96 | 76551.56 | 3827.58 | Approved Pending Payment | 72723.98 | 2025-Q2
EXP-004719 | 2025-05-26 | BOQ-PKG-09-00739 | PKG-09 | INV-PKG-09-030-04719 | 20.94 | 65330.93 | 3266.55 | Paid | 62064.38 | 2025-Q2
EXP-004905 | 2025-05-26 | BOQ-PKG-05-00925 | PKG-05 | INV-PKG-05-006-04905 | 305.38 | 46580.55 | 2329.03 | Paid | 44251.52 | 2025-Q2
EXP-005803 | 2025-05-26 | BOQ-PKG-03-01823 | PKG-03 | INV-PKG-03-029-05803 | 356.26 | 102169.53 | 5108.48 | Paid | 97061.05 | 2025-Q2
EXP-002141 | 2025-05-27 | BOQ-PKG-01-00151 | PKG-01 | INV-PKG-01-007-02141 | 14.9 | 152940.56 | 7647.03 | Approved Pending Payment | 145293.53 | 2025-Q2
EXP-002554 | 2025-05-27 | BOQ-PKG-04-00564 | PKG-04 | INV-PKG-04-035-02554 | 379.9 | 45721.67 | 2286.08 | Paid | 43435.59 | 2025-Q2
EXP-003222 | 2025-05-27 | BOQ-PKG-02-01232 | PKG-02 | INV-PKG-02-003-03222 | 97.96 | 36467.87 | 1823.39 | Paid | 34644.48 | 2025-Q2
EXP-003365 | 2025-05-27 | BOQ-PKG-05-01375 | PKG-05 | INV-PKG-05-006-03365 | 401.24 | 24110.25 | 1205.51 | Paid | 22904.74 | 2025-Q2
EXP-004309 | 2025-05-27 | BOQ-PKG-09-00329 | PKG-09 | INV-PKG-09-005-04309 | 112.54 | 62032.33 | 3101.62 | Approved Pending Payment | 58930.71 | 2025-Q2
EXP-004503 | 2025-05-27 | BOQ-PKG-03-00523 | PKG-03 | INV-PKG-03-024-04503 | 175.05 | 38535.69 | 1926.78 | Under Review | 36608.91 | 2025-Q2
EXP-004820 | 2025-05-27 | BOQ-PKG-10-00840 | PKG-10 | INV-PKG-10-026-04820 | 35.91 | 82085.7 | 4104.28 | Disputed | 77981.42 | 2025-Q2
EXP-006149 | 2025-05-27 | BOQ-PKG-09-00179 | PKG-09 | INV-PKG-09-025-06149 | 78.42 | 139601.18 | 6980.06 | Approved Pending Payment | 132621.12 | 2025-Q2
EXP-006162 | 2025-05-27 | BOQ-PKG-02-00192 | PKG-02 | INV-PKG-02-003-06162 | 58.33 | 69313.88 | 3465.69 | Paid | 65848.19 | 2025-Q2
EXP-004242 | 2025-05-28 | BOQ-PKG-02-00262 | PKG-02 | INV-PKG-02-008-04242 | 305.76 | 157863.86 | 7893.19 | Paid | 149970.67 | 2025-Q2
EXP-000440 | 2025-05-29 | BOQ-PKG-10-00440 | PKG-10 | INV-PKG-10-021-00440 | 254.91 | 54508.51 | 2725.43 | Paid | 51783.08 | 2025-Q2
EXP-000989 | 2025-05-29 | BOQ-PKG-09-00989 | PKG-09 | INV-PKG-09-010-00989 | 22 | 142372.46 | 7118.62 | Paid | 135253.84 | 2025-Q2
EXP-002084 | 2025-05-29 | BOQ-PKG-04-00094 | PKG-04 | INV-PKG-04-020-02084 | 417.39 | 30479.44 | 1523.97 | Paid | 28955.47 | 2025-Q2
EXP-002317 | 2025-05-29 | BOQ-PKG-07-00327 | PKG-07 | INV-PKG-07-008-02317 | 102.64 | 169064.6 | 8453.23 | Paid | 160611.37 | 2025-Q2
EXP-005268 | 2025-05-29 | BOQ-PKG-08-01288 | PKG-08 | INV-PKG-08-019-05268 | 119.36 | 80982.08 | 4049.1 | Under Review | 76932.98 | 2025-Q2
EXP-005577 | 2025-05-29 | BOQ-PKG-07-01597 | PKG-07 | INV-PKG-07-013-05577 | 49.45 | 106466.35 | 5323.32 | Paid | 101143.03 | 2025-Q2
EXP-005726 | 2025-05-29 | BOQ-PKG-06-01746 | PKG-06 | INV-PKG-06-022-05726 | 319.1 | 93831.09 | 4691.55 | Disputed | 89139.54 | 2025-Q2
EXP-000210 | 2025-05-30 | BOQ-PKG-10-00210 | PKG-10 | INV-PKG-10-001-00210 | 120.21 | 34399.48 | 1719.97 | Paid | 32679.51 | 2025-Q2
EXP-000751 | 2025-05-30 | BOQ-PKG-01-00751 | PKG-01 | INV-PKG-01-017-00751 | 67.8 | 24670 | 1233.5 | Paid | 23436.5 | 2025-Q2
EXP-002430 | 2025-05-30 | BOQ-PKG-10-00440 | PKG-10 | INV-PKG-10-016-02430 | 400.48 | 98033.7 | 4901.69 | Paid | 93132.01 | 2025-Q2
EXP-002696 | 2025-05-30 | BOQ-PKG-06-00706 | PKG-06 | INV-PKG-06-002-02696 | 426.25 | 93679.42 | 4683.97 | Paid | 88995.45 | 2025-Q2
EXP-004054 | 2025-05-30 | BOQ-PKG-04-00074 | PKG-04 | INV-PKG-04-030-04054 | 239.97 | 164325.5 | 8216.28 | Paid | 156109.22 | 2025-Q2
EXP-004257 | 2025-05-30 | BOQ-PKG-07-00277 | PKG-07 | INV-PKG-07-023-04257 | 135.38 | 73393.65 | 3669.68 | Paid | 69723.97 | 2025-Q2
EXP-004749 | 2025-05-30 | BOQ-PKG-09-00769 | PKG-09 | INV-PKG-09-025-04749 | 280.95 | 97676.85 | 4883.84 | Approved Pending Payment | 92793.01 | 2025-Q2
EXP-005189 | 2025-05-30 | BOQ-PKG-09-01209 | PKG-09 | INV-PKG-09-010-05189 | 149.02 | 176793.14 | 8839.66 | Approved Pending Payment | 167953.48 | 2025-Q2
EXP-005991 | 2025-05-30 | BOQ-PKG-01-00021 | PKG-01 | INV-PKG-01-007-05991 | 122.36 | 200715.09 | 10035.75 | Paid | 190679.34 | 2025-Q2
EXP-006154 | 2025-05-30 | BOQ-PKG-04-00184 | PKG-04 | INV-PKG-04-030-06154 | 217.53 | 89652.97 | 4482.65 | Paid | 85170.32 | 2025-Q2
EXP-006723 | 2025-05-30 | BOQ-PKG-03-00753 | PKG-03 | INV-PKG-03-004-06723 | 293.11 | 88551.91 | 4427.6 | Under Review | 84124.31 | 2025-Q2
EXP-003479 | 2025-05-31 | BOQ-PKG-09-01489 | PKG-09 | INV-PKG-09-015-03479 | 378.86 | 35461.11 | 1773.06 | Paid | 33688.05 | 2025-Q2
EXP-004304 | 2025-05-31 | BOQ-PKG-04-00324 | PKG-04 | INV-PKG-04-035-04304 | 293.07 | 77165.82 | 3858.29 | Paid | 73307.53 | 2025-Q2
EXP-004799 | 2025-05-31 | BOQ-PKG-09-00819 | PKG-09 | INV-PKG-09-005-04799 | 355.38 | 169975.8 | 8498.79 | Paid | 161477.01 | 2025-Q2
EXP-006155 | 2025-05-31 | BOQ-PKG-05-00185 | PKG-05 | INV-PKG-05-031-06155 | 297.13 | 37375.47 | 1868.77 | Paid | 35506.7 | 2025-Q2
EXP-006746 | 2025-05-31 | BOQ-PKG-06-00776 | PKG-06 | INV-PKG-06-027-06746 | 294.68 | 154557.45 | 7727.87 | Paid | 146829.58 | 2025-Q2
EXP-000796 | 2025-06-01 | BOQ-PKG-06-00796 | PKG-06 | INV-PKG-06-027-00796 | 302.86 | 174294.24 | 8714.71 | Paid | 165579.53 | 2025-Q2
EXP-003182 | 2025-06-01 | BOQ-PKG-02-01192 | PKG-02 | INV-PKG-02-033-03182 | 442.2 | 164507.66 | 8225.38 | Approved Pending Payment | 156282.28 | 2025-Q2
EXP-005664 | 2025-06-01 | BOQ-PKG-04-01684 | PKG-04 | INV-PKG-04-030-05664 | 252.42 | 105469.49 | 5273.47 | Paid | 100196.02 | 2025-Q2
EXP-006401 | 2025-06-01 | BOQ-PKG-01-00431 | PKG-01 | INV-PKG-01-032-06401 | 238.83 | 161708.66 | 8085.43 | Approved Pending Payment | 153623.23 | 2025-Q2
EXP-000597 | 2025-06-02 | BOQ-PKG-07-00597 | PKG-07 | INV-PKG-07-003-00597 | 182.88 | 204254.49 | 10212.72 | Paid | 194041.77 | 2025-Q2
EXP-001420 | 2025-06-02 | BOQ-PKG-10-01420 | PKG-10 | INV-PKG-10-021-01420 | 186.66 | 72899.52 | 3644.98 | Approved Pending Payment | 69254.54 | 2025-Q2
EXP-001716 | 2025-06-02 | BOQ-PKG-06-01716 | PKG-06 | INV-PKG-06-002-01716 | 308.92 | 147215.98 | 7360.8 | Paid | 139855.18 | 2025-Q2
EXP-003187 | 2025-06-02 | BOQ-PKG-07-01197 | PKG-07 | INV-PKG-07-003-03187 | 50.59 | 154778.84 | 7738.94 | Paid | 147039.9 | 2025-Q2
EXP-003470 | 2025-06-02 | BOQ-PKG-10-01480 | PKG-10 | INV-PKG-10-006-03470 | 436.15 | 192745.99 | 9637.3 | Under Review | 183108.69 | 2025-Q2
EXP-003485 | 2025-06-02 | BOQ-PKG-05-01495 | PKG-05 | INV-PKG-05-021-03485 | 330.11 | 41642.25 | 2082.11 | Paid | 39560.14 | 2025-Q2
EXP-003923 | 2025-06-02 | BOQ-PKG-03-01933 | PKG-03 | INV-PKG-03-004-03923 | 315.34 | 84441.93 | 4222.1 | Paid | 80219.83 | 2025-Q2
EXP-004151 | 2025-06-02 | BOQ-PKG-01-00171 | PKG-01 | INV-PKG-01-022-04151 | 24.4 | 113704.67 | 5685.23 | Approved Pending Payment | 108019.44 | 2025-Q2
EXP-004929 | 2025-06-02 | BOQ-PKG-09-00949 | PKG-09 | INV-PKG-09-030-04929 | 218.85 | 173551.88 | 8677.59 | Approved Pending Payment | 164874.29 | 2025-Q2
EXP-005516 | 2025-06-02 | BOQ-PKG-06-01536 | PKG-06 | INV-PKG-06-022-05516 | 295.39 | 33254.66 | 1662.73 | Paid | 31591.93 | 2025-Q2
EXP-005624 | 2025-06-02 | BOQ-PKG-04-01644 | PKG-04 | INV-PKG-04-025-05624 | 86.52 | 46968.07 | 2348.4 | Paid | 44619.67 | 2025-Q2
EXP-006536 | 2025-06-02 | BOQ-PKG-06-00566 | PKG-06 | INV-PKG-06-027-06536 | 146.77 | 116659.05 | 5832.95 | Paid | 110826.1 | 2025-Q2
EXP-001268 | 2025-06-03 | BOQ-PKG-08-01268 | PKG-08 | INV-PKG-08-009-01268 | 217.66 | 66724.18 | 3336.21 | Paid | 63387.97 | 2025-Q2
EXP-001839 | 2025-06-03 | BOQ-PKG-09-01839 | PKG-09 | INV-PKG-09-020-01839 | 198.24 | 98833.77 | 4941.69 | Paid | 93892.08 | 2025-Q2
EXP-001863 | 2025-06-03 | BOQ-PKG-03-01863 | PKG-03 | INV-PKG-03-009-01863 | 55.84 | 121553.15 | 6077.66 | Paid | 115475.49 | 2025-Q2
EXP-002133 | 2025-06-03 | BOQ-PKG-03-00143 | PKG-03 | INV-PKG-03-034-02133 | 346.94 | 166981.39 | 8349.07 | Approved Pending Payment | 158632.32 | 2025-Q2
EXP-003581 | 2025-06-03 | BOQ-PKG-01-01591 | PKG-01 | INV-PKG-01-012-03581 | 257.55 | 198131.16 | 9906.56 | Paid | 188224.6 | 2025-Q2
EXP-003691 | 2025-06-03 | BOQ-PKG-01-01701 | PKG-01 | INV-PKG-01-017-03691 | 234.75 | 27092.99 | 1354.65 | Paid | 25738.34 | 2025-Q2
EXP-005822 | 2025-06-03 | BOQ-PKG-02-01842 | PKG-02 | INV-PKG-02-013-05822 | 282.12 | 101597.02 | 5079.85 | Paid | 96517.17 | 2025-Q2
EXP-005968 | 2025-06-03 | BOQ-PKG-08-01988 | PKG-08 | INV-PKG-08-019-05968 | 35.46 | 128146.56 | 6407.33 | Paid | 121739.23 | 2025-Q2
EXP-006338 | 2025-06-03 | BOQ-PKG-08-00368 | PKG-08 | INV-PKG-08-004-06338 | 140.13 | 97646.39 | 4882.32 | Paid | 92764.07 | 2025-Q2
EXP-006589 | 2025-06-03 | BOQ-PKG-09-00619 | PKG-09 | INV-PKG-09-010-06589 | 349.2 | 73474.16 | 3673.71 | Paid | 69800.45 | 2025-Q2
EXP-000525 | 2025-06-04 | BOQ-PKG-05-00525 | PKG-05 | INV-PKG-05-001-00525 | 270.4 | 94499.37 | 4724.97 | Paid | 89774.4 | 2025-Q2
EXP-001405 | 2025-06-04 | BOQ-PKG-05-01405 | PKG-05 | INV-PKG-05-006-01405 | 66.36 | 132381.13 | 6619.06 | Paid | 125762.07 | 2025-Q2
EXP-001555 | 2025-06-04 | BOQ-PKG-05-01555 | PKG-05 | INV-PKG-05-016-01555 | 386.81 | 157900.44 | 7895.02 | Paid | 150005.42 | 2025-Q2
EXP-002782 | 2025-06-04 | BOQ-PKG-02-00792 | PKG-02 | INV-PKG-02-018-02782 | 146.5 | 124914.07 | 6245.7 | Approved Pending Payment | 118668.37 | 2025-Q2
EXP-002824 | 2025-06-04 | BOQ-PKG-04-00834 | PKG-04 | INV-PKG-04-025-02824 | 20.8 | 197926.6 | 9896.33 | Paid | 188030.27 | 2025-Q2
EXP-005826 | 2025-06-04 | BOQ-PKG-06-01846 | PKG-06 | INV-PKG-06-017-05826 | 20.69 | 174348.78 | 8717.44 | Under Review | 165631.34 | 2025-Q2
EXP-006005 | 2025-06-04 | BOQ-PKG-05-00035 | PKG-05 | INV-PKG-05-021-06005 | 243.86 | 169903.81 | 8495.19 | Paid | 161408.62 | 2025-Q2
EXP-000835 | 2025-06-05 | BOQ-PKG-05-00835 | PKG-05 | INV-PKG-05-031-00835 | 371.59 | 44695.26 | 2234.76 | Approved Pending Payment | 42460.5 | 2025-Q2
EXP-001309 | 2025-06-05 | BOQ-PKG-09-01309 | PKG-09 | INV-PKG-09-015-01309 | 307.11 | 186049.71 | 9302.49 | Paid | 176747.22 | 2025-Q2
EXP-001438 | 2025-06-05 | BOQ-PKG-08-01438 | PKG-08 | INV-PKG-08-004-01438 | 32.45 | 62843.09 | 3142.15 | Paid | 59700.94 | 2025-Q2
EXP-002213 | 2025-06-05 | BOQ-PKG-03-00223 | PKG-03 | INV-PKG-03-009-02213 | 13.99 | 54144.03 | 2707.2 | Paid | 51436.83 | 2025-Q2
EXP-003352 | 2025-06-05 | BOQ-PKG-02-01362 | PKG-02 | INV-PKG-02-028-03352 | 206.39 | 30220.67 | 1511.03 | Paid | 28709.64 | 2025-Q2
EXP-004010 | 2025-06-05 | BOQ-PKG-10-00030 | PKG-10 | INV-PKG-10-021-04010 | 429.51 | 44044.11 | 2202.21 | Disputed | 41841.9 | 2025-Q2
EXP-004235 | 2025-06-05 | BOQ-PKG-05-00255 | PKG-05 | INV-PKG-05-001-04235 | 240.21 | 187914.04 | 9395.7 | Paid | 178518.34 | 2025-Q2
EXP-004724 | 2025-06-05 | BOQ-PKG-04-00744 | PKG-04 | INV-PKG-04-035-04724 | 37.9 | 187610.58 | 9380.53 | Paid | 178230.05 | 2025-Q2
EXP-006982 | 2025-06-05 | BOQ-PKG-02-01012 | PKG-02 | INV-PKG-02-018-06982 | 448.74 | 185228.15 | 9261.41 | Paid | 175966.74 | 2025-Q2
EXP-000266 | 2025-06-06 | BOQ-PKG-06-00266 | PKG-06 | INV-PKG-06-022-00266 | 217.26 | 99539.32 | 4976.97 | Under Review | 94562.35 | 2025-Q2
EXP-002693 | 2025-06-06 | BOQ-PKG-03-00703 | PKG-03 | INV-PKG-03-034-02693 | 313.71 | 186030.5 | 9301.52 | Paid | 176728.98 | 2025-Q2
EXP-003080 | 2025-06-06 | BOQ-PKG-10-01090 | PKG-10 | INV-PKG-10-001-03080 | 350.93 | 130211.47 | 6510.57 | Approved Pending Payment | 123700.9 | 2025-Q2
EXP-003323 | 2025-06-06 | BOQ-PKG-03-01333 | PKG-03 | INV-PKG-03-034-03323 | 388.06 | 117167.88 | 5858.39 | Paid | 111309.49 | 2025-Q2
EXP-003436 | 2025-06-06 | BOQ-PKG-06-01446 | PKG-06 | INV-PKG-06-007-03436 | 255.32 | 160679.13 | 8033.96 | Paid | 152645.17 | 2025-Q2
EXP-004215 | 2025-06-06 | BOQ-PKG-05-00235 | PKG-05 | INV-PKG-05-016-04215 | 270.21 | 110110.59 | 5505.53 | Under Review | 104605.06 | 2025-Q2
EXP-004339 | 2025-06-06 | BOQ-PKG-09-00359 | PKG-09 | INV-PKG-09-035-04339 | 18.87 | 151925.93 | 7596.3 | Approved Pending Payment | 144329.63 | 2025-Q2
EXP-005978 | 2025-06-06 | BOQ-PKG-08-00008 | PKG-08 | INV-PKG-08-029-05978 | 15.31 | 173382.56 | 8669.13 | Paid | 164713.43 | 2025-Q2
EXP-000695 | 2025-06-07 | BOQ-PKG-05-00695 | PKG-05 | INV-PKG-05-031-00695 | 199.53 | 74555.31 | 3727.77 | Under Review | 70827.54 | 2025-Q2
EXP-001327 | 2025-06-07 | BOQ-PKG-07-01327 | PKG-07 | INV-PKG-07-033-01327 | 339.58 | 49494.02 | 2474.7 | Paid | 47019.32 | 2025-Q2
EXP-003194 | 2025-06-07 | BOQ-PKG-04-01204 | PKG-04 | INV-PKG-04-010-03194 | 129.39 | 54307.6 | 2715.38 | Paid | 51592.22 | 2025-Q2
EXP-003290 | 2025-06-07 | BOQ-PKG-10-01300 | PKG-10 | INV-PKG-10-001-03290 | 234.15 | 30710.95 | 1535.55 | Paid | 29175.4 | 2025-Q2
EXP-006406 | 2025-06-07 | BOQ-PKG-06-00436 | PKG-06 | INV-PKG-06-002-06406 | 364.34 | 182440.03 | 9122 | Paid | 173318.03 | 2025-Q2
EXP-000274 | 2025-06-08 | BOQ-PKG-04-00274 | PKG-04 | INV-PKG-04-030-00274 | 11.32 | 71758.15 | 3587.91 | Paid | 68170.24 | 2025-Q2
EXP-001837 | 2025-06-08 | BOQ-PKG-07-01837 | PKG-07 | INV-PKG-07-018-01837 | 268.93 | 121475.09 | 6073.75 | Paid | 115401.34 | 2025-Q2
EXP-002444 | 2025-06-08 | BOQ-PKG-04-00454 | PKG-04 | INV-PKG-04-030-02444 | 321 | 34787.82 | 1739.39 | Approved Pending Payment | 33048.43 | 2025-Q2
EXP-003758 | 2025-06-08 | BOQ-PKG-08-01768 | PKG-08 | INV-PKG-08-014-03758 | 8.08 | 26092.41 | 1304.62 | Paid | 24787.79 | 2025-Q2
EXP-004203 | 2025-06-08 | BOQ-PKG-03-00223 | PKG-03 | INV-PKG-03-004-04203 | 100.65 | 190186.17 | 9509.31 | Paid | 180676.86 | 2025-Q2
EXP-004211 | 2025-06-08 | BOQ-PKG-01-00231 | PKG-01 | INV-PKG-01-012-04211 | 315.74 | 146586.75 | 7329.34 | Approved Pending Payment | 139257.41 | 2025-Q2
EXP-004346 | 2025-06-08 | BOQ-PKG-06-00366 | PKG-06 | INV-PKG-06-007-04346 | 277.54 | 51516.78 | 2575.84 | Paid | 48940.94 | 2025-Q2
EXP-006967 | 2025-06-08 | BOQ-PKG-07-00997 | PKG-07 | INV-PKG-07-003-06967 | 251.86 | 145719.6 | 7285.98 | Paid | 138433.62 | 2025-Q2
EXP-002138 | 2025-06-09 | BOQ-PKG-08-00148 | PKG-08 | INV-PKG-08-004-02138 | 69.92 | 128678.32 | 6433.92 | Paid | 122244.4 | 2025-Q2
EXP-003415 | 2025-06-09 | BOQ-PKG-05-01425 | PKG-05 | INV-PKG-05-021-03415 | 102.01 | 127763.31 | 6388.17 | Paid | 121375.14 | 2025-Q2
EXP-003799 | 2025-06-09 | BOQ-PKG-09-01809 | PKG-09 | INV-PKG-09-020-03799 | 380.41 | 35483.99 | 1774.2 | Paid | 33709.79 | 2025-Q2
EXP-004941 | 2025-06-09 | BOQ-PKG-01-00961 | PKG-01 | INV-PKG-01-007-04941 | 181.08 | 102672.02 | 5133.6 | Paid | 97538.42 | 2025-Q2
EXP-005827 | 2025-06-09 | BOQ-PKG-07-01847 | PKG-07 | INV-PKG-07-018-05827 | 79.97 | 112474.99 | 5623.75 | Paid | 106851.24 | 2025-Q2
EXP-000494 | 2025-06-10 | BOQ-PKG-04-00494 | PKG-04 | INV-PKG-04-005-00494 | 436.12 | 110437.49 | 5521.87 | Paid | 104915.62 | 2025-Q2
EXP-002050 | 2025-06-10 | BOQ-PKG-10-00060 | PKG-10 | INV-PKG-10-021-02050 | 235.39 | 24577.65 | 1228.88 | Paid | 23348.77 | 2025-Q2
EXP-002248 | 2025-06-10 | BOQ-PKG-08-00258 | PKG-08 | INV-PKG-08-009-02248 | 388.01 | 41305.32 | 2065.27 | Paid | 39240.05 | 2025-Q2
EXP-003149 | 2025-06-10 | BOQ-PKG-09-01159 | PKG-09 | INV-PKG-09-035-03149 | 128.69 | 115518.33 | 5775.92 | Paid | 109742.41 | 2025-Q2
EXP-003564 | 2025-06-10 | BOQ-PKG-04-01574 | PKG-04 | INV-PKG-04-030-03564 | 19.08 | 200133.31 | 10006.67 | Paid | 190126.64 | 2025-Q2
EXP-003931 | 2025-06-10 | BOQ-PKG-01-01941 | PKG-01 | INV-PKG-01-012-03931 | 72.03 | 110436.25 | 5521.81 | Under Review | 104914.44 | 2025-Q2
EXP-005817 | 2025-06-10 | BOQ-PKG-07-01837 | PKG-07 | INV-PKG-07-008-05817 | 195.97 | 146906.37 | 7345.32 | Under Review | 139561.05 | 2025-Q2
EXP-000063 | 2025-06-11 | BOQ-PKG-03-00063 | PKG-03 | INV-PKG-03-029-00063 | 40.28 | 133730.49 | 6686.52 | Paid | 127043.97 | 2025-Q2
EXP-002565 | 2025-06-11 | BOQ-PKG-05-00575 | PKG-05 | INV-PKG-05-011-02565 | 316.48 | 182633.23 | 9131.66 | Under Review | 173501.57 | 2025-Q2
EXP-002938 | 2025-06-11 | BOQ-PKG-08-00948 | PKG-08 | INV-PKG-08-034-02938 | 276.99 | 218045.55 | 10902.28 | Disputed | 207143.27 | 2025-Q2
EXP-003880 | 2025-06-11 | BOQ-PKG-10-01890 | PKG-10 | INV-PKG-10-031-03880 | 40.87 | 168216.16 | 8410.81 | Paid | 159805.35 | 2025-Q2
EXP-003925 | 2025-06-11 | BOQ-PKG-05-01935 | PKG-05 | INV-PKG-05-006-03925 | 135.76 | 77688.87 | 3884.44 | Paid | 73804.43 | 2025-Q2
EXP-004642 | 2025-06-11 | BOQ-PKG-02-00662 | PKG-02 | INV-PKG-02-023-04642 | 128.5 | 194041.88 | 9702.09 | Under Review | 184339.79 | 2025-Q2
EXP-005046 | 2025-06-11 | BOQ-PKG-06-01066 | PKG-06 | INV-PKG-06-007-05046 | 135.19 | 146599.17 | 7329.96 | Paid | 139269.21 | 2025-Q2
EXP-006655 | 2025-06-11 | BOQ-PKG-05-00685 | PKG-05 | INV-PKG-05-006-06655 | 417.77 | 138294.68 | 6914.73 | Approved Pending Payment | 131379.95 | 2025-Q2
EXP-000644 | 2025-06-12 | BOQ-PKG-04-00644 | PKG-04 | INV-PKG-04-015-00644 | 63.33 | 172644.99 | 8632.25 | Under Review | 164012.74 | 2025-Q2
EXP-000918 | 2025-06-12 | BOQ-PKG-08-00918 | PKG-08 | INV-PKG-08-009-00918 | 413.97 | 191182.4 | 9559.12 | Paid | 181623.28 | 2025-Q2
EXP-002437 | 2025-06-12 | BOQ-PKG-07-00447 | PKG-07 | INV-PKG-07-023-02437 | 272.74 | 136360.56 | 6818.03 | Paid | 129542.53 | 2025-Q2
EXP-003766 | 2025-06-12 | BOQ-PKG-06-01776 | PKG-06 | INV-PKG-06-022-03766 | 228.92 | 77014.38 | 3850.72 | Approved Pending Payment | 73163.66 | 2025-Q2
EXP-004370 | 2025-06-12 | BOQ-PKG-10-00390 | PKG-10 | INV-PKG-10-031-04370 | 103.03 | 161995.61 | 8099.78 | Paid | 153895.83 | 2025-Q2
EXP-005578 | 2025-06-12 | BOQ-PKG-08-01598 | PKG-08 | INV-PKG-08-014-05578 | 220.2 | 110251.47 | 5512.57 | Approved Pending Payment | 104738.9 | 2025-Q2
EXP-000705 | 2025-06-13 | BOQ-PKG-05-00705 | PKG-05 | INV-PKG-05-006-00705 | 375.64 | 45921.72 | 2296.09 | Paid | 43625.63 | 2025-Q2
EXP-000924 | 2025-06-13 | BOQ-PKG-04-00924 | PKG-04 | INV-PKG-04-015-00924 | 240.69 | 89013.37 | 4450.67 | Paid | 84562.7 | 2025-Q2
EXP-004910 | 2025-06-13 | BOQ-PKG-10-00930 | PKG-10 | INV-PKG-10-011-04910 | 93.52 | 39880.15 | 1994.01 | Paid | 37886.14 | 2025-Q2
EXP-004927 | 2025-06-13 | BOQ-PKG-07-00947 | PKG-07 | INV-PKG-07-028-04927 | 363.64 | 77842.79 | 3892.14 | Paid | 73950.65 | 2025-Q2
EXP-005360 | 2025-06-13 | BOQ-PKG-10-01380 | PKG-10 | INV-PKG-10-006-05360 | 68.16 | 160767.7 | 8038.39 | Paid | 152729.31 | 2025-Q2
EXP-005463 | 2025-06-13 | BOQ-PKG-03-01483 | PKG-03 | INV-PKG-03-004-05463 | 389.19 | 208480.86 | 10424.04 | Paid | 198056.82 | 2025-Q2
EXP-005595 | 2025-06-13 | BOQ-PKG-05-01615 | PKG-05 | INV-PKG-05-031-05595 | 59.87 | 108718.33 | 5435.92 | Paid | 103282.41 | 2025-Q2
EXP-006788 | 2025-06-13 | BOQ-PKG-08-00818 | PKG-08 | INV-PKG-08-034-06788 | 182.19 | 155670.44 | 7783.52 | Paid | 147886.92 | 2025-Q2
EXP-006928 | 2025-06-13 | BOQ-PKG-08-00958 | PKG-08 | INV-PKG-08-034-06928 | 120.97 | 36098.57 | 1804.93 | Paid | 34293.64 | 2025-Q2
EXP-006976 | 2025-06-13 | BOQ-PKG-06-01006 | PKG-06 | INV-PKG-06-012-06976 | 302.74 | 28664.53 | 1433.23 | Paid | 27231.3 | 2025-Q2
EXP-000688 | 2025-06-14 | BOQ-PKG-08-00688 | PKG-08 | INV-PKG-08-024-00688 | 140.62 | 56005.95 | 2800.3 | Paid | 53205.65 | 2025-Q2
EXP-000780 | 2025-06-14 | BOQ-PKG-10-00780 | PKG-10 | INV-PKG-10-011-00780 | 295.93 | 97313.98 | 4865.7 | Paid | 92448.28 | 2025-Q2
EXP-001035 | 2025-06-14 | BOQ-PKG-05-01035 | PKG-05 | INV-PKG-05-021-01035 | 226.23 | 49088.6 | 2454.43 | Paid | 46634.17 | 2025-Q2
EXP-001612 | 2025-06-14 | BOQ-PKG-02-01612 | PKG-02 | INV-PKG-02-003-01612 | 111.03 | 183666.5 | 9183.33 | Paid | 174483.17 | 2025-Q2
EXP-004802 | 2025-06-14 | BOQ-PKG-02-00822 | PKG-02 | INV-PKG-02-008-04802 | 256.96 | 177515.15 | 8875.76 | Approved Pending Payment | 168639.39 | 2025-Q2
EXP-004824 | 2025-06-14 | BOQ-PKG-04-00844 | PKG-04 | INV-PKG-04-030-04824 | 127.01 | 65790.19 | 3289.51 | Paid | 62500.68 | 2025-Q2
EXP-005382 | 2025-06-14 | BOQ-PKG-02-01402 | PKG-02 | INV-PKG-02-028-05382 | 387.89 | 187286.25 | 9364.31 | Paid | 177921.94 | 2025-Q2
EXP-006383 | 2025-06-14 | BOQ-PKG-03-00413 | PKG-03 | INV-PKG-03-014-06383 | 283.21 | 199690.48 | 9984.52 | Paid | 189705.96 | 2025-Q2
EXP-000166 | 2025-06-15 | BOQ-PKG-06-00166 | PKG-06 | INV-PKG-06-027-00166 | 39.65 | 198321.35 | 9916.07 | Approved Pending Payment | 188405.28 | 2025-Q2
EXP-001107 | 2025-06-15 | BOQ-PKG-07-01107 | PKG-07 | INV-PKG-07-023-01107 | 241.88 | 38695.28 | 1934.76 | Paid | 36760.52 | 2025-Q2
EXP-002408 | 2025-06-15 | BOQ-PKG-08-00418 | PKG-08 | INV-PKG-08-029-02408 | 444.36 | 178457.27 | 8922.86 | Disputed | 169534.41 | 2025-Q2
EXP-003549 | 2025-06-15 | BOQ-PKG-09-01559 | PKG-09 | INV-PKG-09-015-03549 | 152.53 | 57846.11 | 2892.31 | Paid | 54953.8 | 2025-Q2
EXP-004437 | 2025-06-15 | BOQ-PKG-07-00457 | PKG-07 | INV-PKG-07-028-04437 | 164.12 | 152475.14 | 7623.76 | Paid | 144851.38 | 2025-Q2
EXP-004946 | 2025-06-15 | BOQ-PKG-06-00966 | PKG-06 | INV-PKG-06-012-04946 | 84.38 | 183515.6 | 9175.78 | Approved Pending Payment | 174339.82 | 2025-Q2
EXP-005772 | 2025-06-15 | BOQ-PKG-02-01792 | PKG-02 | INV-PKG-02-033-05772 | 160.04 | 149309.99 | 7465.5 | Paid | 141844.49 | 2025-Q2
EXP-005986 | 2025-06-15 | BOQ-PKG-06-00016 | PKG-06 | INV-PKG-06-002-05986 | 140.54 | 152977.93 | 7648.9 | Paid | 145329.03 | 2025-Q2
EXP-006566 | 2025-06-15 | BOQ-PKG-06-00596 | PKG-06 | INV-PKG-06-022-06566 | 44.52 | 146513.67 | 7325.68 | Paid | 139187.99 | 2025-Q2
EXP-006587 | 2025-06-15 | BOQ-PKG-07-00617 | PKG-07 | INV-PKG-07-008-06587 | 418.62 | 136187.75 | 6809.39 | Approved Pending Payment | 129378.36 | 2025-Q2
EXP-000197 | 2025-06-16 | BOQ-PKG-07-00197 | PKG-07 | INV-PKG-07-023-00197 | 95.81 | 79968.47 | 3998.42 | Paid | 75970.05 | 2025-Q2
EXP-000311 | 2025-06-16 | BOQ-PKG-01-00311 | PKG-01 | INV-PKG-01-032-00311 | 64.37 | 156613.24 | 7830.66 | Paid | 148782.58 | 2025-Q2
EXP-001250 | 2025-06-16 | BOQ-PKG-10-01250 | PKG-10 | INV-PKG-10-026-01250 | 319.52 | 167401.93 | 8370.1 | Paid | 159031.83 | 2025-Q2
EXP-001253 | 2025-06-16 | BOQ-PKG-03-01253 | PKG-03 | INV-PKG-03-029-01253 | 100.23 | 111118.81 | 5555.94 | Paid | 105562.87 | 2025-Q2
EXP-001758 | 2025-06-16 | BOQ-PKG-08-01758 | PKG-08 | INV-PKG-08-009-01758 | 284.3 | 195435.26 | 9771.76 | Paid | 185663.5 | 2025-Q2
EXP-002019 | 2025-06-16 | BOQ-PKG-09-00029 | PKG-09 | INV-PKG-09-025-02019 | 85.03 | 91801.33 | 4590.07 | Paid | 87211.26 | 2025-Q2
EXP-002394 | 2025-06-16 | BOQ-PKG-04-00404 | PKG-04 | INV-PKG-04-015-02394 | 110.7 | 150638.67 | 7531.93 | Approved Pending Payment | 143106.74 | 2025-Q2
EXP-002907 | 2025-06-16 | BOQ-PKG-07-00917 | PKG-07 | INV-PKG-07-003-02907 | 210.58 | 198242.61 | 9912.13 | Approved Pending Payment | 188330.48 | 2025-Q2
EXP-004069 | 2025-06-16 | BOQ-PKG-09-00089 | PKG-09 | INV-PKG-09-010-04069 | 196.44 | 52035.3 | 2601.77 | Approved Pending Payment | 49433.53 | 2025-Q2
EXP-004702 | 2025-06-16 | BOQ-PKG-02-00722 | PKG-02 | INV-PKG-02-013-04702 | 263.43 | 173672.51 | 8683.63 | Paid | 164988.88 | 2025-Q2
EXP-005299 | 2025-06-16 | BOQ-PKG-09-01319 | PKG-09 | INV-PKG-09-015-05299 | 147.44 | 81933.46 | 4096.67 | Paid | 77836.79 | 2025-Q2
EXP-006528 | 2025-06-16 | BOQ-PKG-08-00558 | PKG-08 | INV-PKG-08-019-06528 | 443.8 | 192584.71 | 9629.24 | Paid | 182955.47 | 2025-Q2
EXP-001504 | 2025-06-17 | BOQ-PKG-04-01504 | PKG-04 | INV-PKG-04-035-01504 | 28.74 | 96594.65 | 4829.73 | Disputed | 91764.92 | 2025-Q2
EXP-002508 | 2025-06-17 | BOQ-PKG-08-00518 | PKG-08 | INV-PKG-08-024-02508 | 218.95 | 199954.68 | 9997.73 | Paid | 189956.95 | 2025-Q2
EXP-002813 | 2025-06-17 | BOQ-PKG-03-00823 | PKG-03 | INV-PKG-03-014-02813 | 397.33 | 104053.2 | 5202.66 | Approved Pending Payment | 98850.54 | 2025-Q2
EXP-003778 | 2025-06-17 | BOQ-PKG-08-01788 | PKG-08 | INV-PKG-08-034-03778 | 344.82 | 134742.29 | 6737.11 | Paid | 128005.18 | 2025-Q2
EXP-005590 | 2025-06-17 | BOQ-PKG-10-01610 | PKG-10 | INV-PKG-10-026-05590 | 349.03 | 204456.25 | 10222.81 | Paid | 194233.44 | 2025-Q2
EXP-005712 | 2025-06-17 | BOQ-PKG-02-01732 | PKG-02 | INV-PKG-02-008-05712 | 242.2 | 33259.16 | 1662.96 | Under Review | 31596.2 | 2025-Q2
EXP-000852 | 2025-06-18 | BOQ-PKG-02-00852 | PKG-02 | INV-PKG-02-013-00852 | 317.72 | 173684.12 | 8684.21 | Paid | 164999.91 | 2025-Q2
EXP-002412 | 2025-06-18 | BOQ-PKG-02-00422 | PKG-02 | INV-PKG-02-033-02412 | 174.93 | 176310.43 | 8815.52 | Paid | 167494.91 | 2025-Q2
EXP-003585 | 2025-06-18 | BOQ-PKG-05-01595 | PKG-05 | INV-PKG-05-016-03585 | 100.87 | 183764.41 | 9188.22 | Paid | 174576.19 | 2025-Q2
EXP-005459 | 2025-06-18 | BOQ-PKG-09-01479 | PKG-09 | INV-PKG-09-035-05459 | 145.13 | 118976.3 | 5948.82 | Approved Pending Payment | 113027.48 | 2025-Q2
EXP-005934 | 2025-06-18 | BOQ-PKG-04-01954 | PKG-04 | INV-PKG-04-020-05934 | 315.68 | 146456.3 | 7322.82 | Paid | 139133.48 | 2025-Q2
EXP-006353 | 2025-06-18 | BOQ-PKG-03-00383 | PKG-03 | INV-PKG-03-019-06353 | 273.1 | 199900.76 | 9995.04 | Paid | 189905.72 | 2025-Q2
EXP-000763 | 2025-06-19 | BOQ-PKG-03-00763 | PKG-03 | INV-PKG-03-029-00763 | 102.6 | 105256.71 | 5262.84 | Approved Pending Payment | 99993.87 | 2025-Q2
EXP-002637 | 2025-06-19 | BOQ-PKG-07-00647 | PKG-07 | INV-PKG-07-013-02637 | 287.15 | 138284.43 | 6914.22 | Under Review | 131370.21 | 2025-Q2
EXP-003107 | 2025-06-19 | BOQ-PKG-07-01117 | PKG-07 | INV-PKG-07-028-03107 | 124.83 | 211999.21 | 10599.96 | Paid | 201399.25 | 2025-Q2
EXP-004984 | 2025-06-19 | BOQ-PKG-04-01004 | PKG-04 | INV-PKG-04-015-04984 | 127.7 | 141265.12 | 7063.26 | Paid | 134201.86 | 2025-Q2
EXP-005486 | 2025-06-19 | BOQ-PKG-06-01506 | PKG-06 | INV-PKG-06-027-05486 | 50.26 | 144282.61 | 7214.13 | Paid | 137068.48 | 2025-Q2
EXP-006027 | 2025-06-19 | BOQ-PKG-07-00057 | PKG-07 | INV-PKG-07-008-06027 | 368.65 | 170372.71 | 8518.64 | Paid | 161854.07 | 2025-Q2
EXP-006432 | 2025-06-19 | BOQ-PKG-02-00462 | PKG-02 | INV-PKG-02-028-06432 | 421.33 | 181577.81 | 9078.89 | Paid | 172498.92 | 2025-Q2
EXP-006697 | 2025-06-19 | BOQ-PKG-07-00727 | PKG-07 | INV-PKG-07-013-06697 | 168.12 | 183063.16 | 9153.16 | Paid | 173910 | 2025-Q2
EXP-000456 | 2025-06-20 | BOQ-PKG-06-00456 | PKG-06 | INV-PKG-06-002-00456 | 280.71 | 151713.21 | 7585.66 | Paid | 144127.55 | 2025-Q2
EXP-001908 | 2025-06-20 | BOQ-PKG-08-01908 | PKG-08 | INV-PKG-08-019-01908 | 212.81 | 193429.47 | 9671.47 | Paid | 183758 | 2025-Q2
EXP-002943 | 2025-06-20 | BOQ-PKG-03-00953 | PKG-03 | INV-PKG-03-004-02943 | 319.38 | 151968.27 | 7598.41 | Paid | 144369.86 | 2025-Q2
EXP-003658 | 2025-06-20 | BOQ-PKG-08-01668 | PKG-08 | INV-PKG-08-019-03658 | 294.6 | 174863.7 | 8743.19 | Paid | 166120.51 | 2025-Q2
EXP-003832 | 2025-06-20 | BOQ-PKG-02-01842 | PKG-02 | INV-PKG-02-018-03832 | 86.21 | 179430.08 | 8971.5 | Under Review | 170458.58 | 2025-Q2
EXP-004190 | 2025-06-20 | BOQ-PKG-10-00210 | PKG-10 | INV-PKG-10-026-04190 | 142.55 | 118499.46 | 5924.97 | Paid | 112574.49 | 2025-Q2
EXP-000609 | 2025-06-21 | BOQ-PKG-09-00609 | PKG-09 | INV-PKG-09-015-00609 | 368.47 | 207761.33 | 10388.07 | Paid | 197373.26 | 2025-Q2
EXP-000850 | 2025-06-21 | BOQ-PKG-10-00850 | PKG-10 | INV-PKG-10-011-00850 | 165 | 47758.23 | 2387.91 | Paid | 45370.32 | 2025-Q2
EXP-002932 | 2025-06-21 | BOQ-PKG-02-00942 | PKG-02 | INV-PKG-02-028-02932 | 284.2 | 116686.49 | 5834.32 | Approved Pending Payment | 110852.17 | 2025-Q2
EXP-003066 | 2025-06-21 | BOQ-PKG-06-01076 | PKG-06 | INV-PKG-06-022-03066 | 144.28 | 55593.12 | 2779.66 | Paid | 52813.46 | 2025-Q2
EXP-003406 | 2025-06-21 | BOQ-PKG-06-01416 | PKG-06 | INV-PKG-06-012-03406 | 426.45 | 36539.45 | 1826.97 | Paid | 34712.48 | 2025-Q2
EXP-003416 | 2025-06-21 | BOQ-PKG-06-01426 | PKG-06 | INV-PKG-06-022-03416 | 432.25 | 130482.81 | 6524.14 | Paid | 123958.67 | 2025-Q2
EXP-006823 | 2025-06-21 | BOQ-PKG-03-00853 | PKG-03 | INV-PKG-03-034-06823 | 388.67 | 126050.97 | 6302.55 | Paid | 119748.42 | 2025-Q2
EXP-000656 | 2025-06-22 | BOQ-PKG-06-00656 | PKG-06 | INV-PKG-06-027-00656 | 27.48 | 32685.27 | 1634.26 | Paid | 31051.01 | 2025-Q2
EXP-001032 | 2025-06-22 | BOQ-PKG-02-01032 | PKG-02 | INV-PKG-02-018-01032 | 299.13 | 84103.62 | 4205.18 | Paid | 79898.44 | 2025-Q2
EXP-001144 | 2025-06-22 | BOQ-PKG-04-01144 | PKG-04 | INV-PKG-04-025-01144 | 107.77 | 163166.52 | 8158.33 | Approved Pending Payment | 155008.19 | 2025-Q2
EXP-001529 | 2025-06-22 | BOQ-PKG-09-01529 | PKG-09 | INV-PKG-09-025-01529 | 126.95 | 34836.8 | 1741.84 | Paid | 33094.96 | 2025-Q2
EXP-002526 | 2025-06-22 | BOQ-PKG-06-00536 | PKG-06 | INV-PKG-06-007-02526 | 272.79 | 205472.99 | 10273.65 | Paid | 195199.34 | 2025-Q2
EXP-002862 | 2025-06-22 | BOQ-PKG-02-00872 | PKG-02 | INV-PKG-02-028-02862 | 25.82 | 211145.37 | 10557.27 | Paid | 200588.1 | 2025-Q2
EXP-003347 | 2025-06-22 | BOQ-PKG-07-01357 | PKG-07 | INV-PKG-07-023-03347 | 118.65 | 105407.7 | 5270.38 | Paid | 100137.32 | 2025-Q2
EXP-003467 | 2025-06-22 | BOQ-PKG-07-01477 | PKG-07 | INV-PKG-07-003-03467 | 394.36 | 210472.63 | 10523.63 | Paid | 199949 | 2025-Q2
EXP-004261 | 2025-06-22 | BOQ-PKG-01-00281 | PKG-01 | INV-PKG-01-027-04261 | 151.45 | 110088.04 | 5504.4 | Paid | 104583.64 | 2025-Q2
EXP-005514 | 2025-06-22 | BOQ-PKG-04-01534 | PKG-04 | INV-PKG-04-020-05514 | 150.9 | 193034.56 | 9651.73 | Paid | 183382.83 | 2025-Q2
EXP-000219 | 2025-06-23 | BOQ-PKG-09-00219 | PKG-09 | INV-PKG-09-010-00219 | 334.6 | 110778.16 | 5538.91 | Disputed | 105239.25 | 2025-Q2
EXP-001237 | 2025-06-23 | BOQ-PKG-07-01237 | PKG-07 | INV-PKG-07-013-01237 | 279.17 | 111545.38 | 5577.27 | Under Review | 105968.11 | 2025-Q2
EXP-001269 | 2025-06-23 | BOQ-PKG-09-01269 | PKG-09 | INV-PKG-09-010-01269 | 117.69 | 194892.31 | 9744.62 | Paid | 185147.69 | 2025-Q2
EXP-001787 | 2025-06-23 | BOQ-PKG-07-01787 | PKG-07 | INV-PKG-07-003-01787 | 435.6 | 203625.16 | 10181.26 | Approved Pending Payment | 193443.9 | 2025-Q2
EXP-002270 | 2025-06-23 | BOQ-PKG-10-00280 | PKG-10 | INV-PKG-10-031-02270 | 291.71 | 57489.9 | 2874.5 | Paid | 54615.4 | 2025-Q2
EXP-004047 | 2025-06-23 | BOQ-PKG-07-00067 | PKG-07 | INV-PKG-07-023-04047 | 394.13 | 156189.47 | 7809.47 | Under Review | 148380 | 2025-Q2
EXP-005066 | 2025-06-23 | BOQ-PKG-06-01086 | PKG-06 | INV-PKG-06-027-05066 | 111.2 | 146518.01 | 7325.9 | Paid | 139192.11 | 2025-Q2
EXP-005814 | 2025-06-23 | BOQ-PKG-04-01834 | PKG-04 | INV-PKG-04-005-05814 | 327.74 | 82007.4 | 4100.37 | Paid | 77907.03 | 2025-Q2
EXP-000511 | 2025-06-24 | BOQ-PKG-01-00511 | PKG-01 | INV-PKG-01-022-00511 | 406.23 | 189299.32 | 9464.97 | Paid | 179834.35 | 2025-Q2
EXP-000749 | 2025-06-24 | BOQ-PKG-09-00749 | PKG-09 | INV-PKG-09-015-00749 | 419.22 | 25421.09 | 1271.05 | Under Review | 24150.04 | 2025-Q2
EXP-001000 | 2025-06-24 | BOQ-PKG-10-01000 | PKG-10 | INV-PKG-10-021-01000 | 151.29 | 160235.86 | 8011.79 | Paid | 152224.07 | 2025-Q2
EXP-001440 | 2025-06-24 | BOQ-PKG-10-01440 | PKG-10 | INV-PKG-10-006-01440 | 272.1 | 208647.47 | 10432.37 | Paid | 198215.1 | 2025-Q2
EXP-001455 | 2025-06-24 | BOQ-PKG-05-01455 | PKG-05 | INV-PKG-05-021-01455 | 324.45 | 197449.59 | 9872.48 | Paid | 187577.11 | 2025-Q2
EXP-002087 | 2025-06-24 | BOQ-PKG-07-00097 | PKG-07 | INV-PKG-07-023-02087 | 360.92 | 134953.04 | 6747.65 | Paid | 128205.39 | 2025-Q2
EXP-004663 | 2025-06-24 | BOQ-PKG-03-00683 | PKG-03 | INV-PKG-03-009-04663 | 371.81 | 211753.19 | 10587.66 | Paid | 201165.53 | 2025-Q2
EXP-006683 | 2025-06-24 | BOQ-PKG-03-00713 | PKG-03 | INV-PKG-03-034-06683 | 338.27 | 25762.29 | 1288.11 | Approved Pending Payment | 24474.18 | 2025-Q2
EXP-001331 | 2025-06-25 | BOQ-PKG-01-01331 | PKG-01 | INV-PKG-01-002-01331 | 335.39 | 64322 | 3216.1 | Paid | 61105.9 | 2025-Q2
EXP-001347 | 2025-06-25 | BOQ-PKG-07-01347 | PKG-07 | INV-PKG-07-018-01347 | 132.81 | 203575.01 | 10178.75 | Disputed | 193396.26 | 2025-Q2
EXP-002397 | 2025-06-25 | BOQ-PKG-07-00407 | PKG-07 | INV-PKG-07-018-02397 | 357.15 | 128668.63 | 6433.43 | Paid | 122235.2 | 2025-Q2
EXP-002452 | 2025-06-25 | BOQ-PKG-02-00462 | PKG-02 | INV-PKG-02-003-02452 | 53.42 | 197238.35 | 9861.92 | Approved Pending Payment | 187376.43 | 2025-Q2
EXP-002710 | 2025-06-25 | BOQ-PKG-10-00720 | PKG-10 | INV-PKG-10-016-02710 | 326.39 | 198516.65 | 9925.83 | Paid | 188590.82 | 2025-Q2
EXP-004633 | 2025-06-25 | BOQ-PKG-03-00653 | PKG-03 | INV-PKG-03-014-04633 | 58.65 | 108457.52 | 5422.88 | Paid | 103034.64 | 2025-Q2
EXP-005498 | 2025-06-25 | BOQ-PKG-08-01518 | PKG-08 | INV-PKG-08-004-05498 | 424.9 | 193424.58 | 9671.23 | Paid | 183753.35 | 2025-Q2
EXP-006620 | 2025-06-25 | BOQ-PKG-10-00650 | PKG-10 | INV-PKG-10-006-06620 | 54.42 | 172346.22 | 8617.31 | Paid | 163728.91 | 2025-Q2
EXP-001376 | 2025-06-26 | BOQ-PKG-06-01376 | PKG-06 | INV-PKG-06-012-01376 | 320.38 | 50243.81 | 2512.19 | Paid | 47731.62 | 2025-Q2
EXP-002421 | 2025-06-26 | BOQ-PKG-01-00431 | PKG-01 | INV-PKG-01-007-02421 | 115.3 | 72059.13 | 3602.96 | Approved Pending Payment | 68456.17 | 2025-Q2
EXP-003280 | 2025-06-26 | BOQ-PKG-10-01290 | PKG-10 | INV-PKG-10-026-03280 | 263.85 | 181059.36 | 9052.97 | Approved Pending Payment | 172006.39 | 2025-Q2
EXP-006419 | 2025-06-26 | BOQ-PKG-09-00449 | PKG-09 | INV-PKG-09-015-06419 | 74.27 | 133252.27 | 6662.61 | Paid | 126589.66 | 2025-Q2
EXP-000082 | 2025-06-27 | BOQ-PKG-02-00082 | PKG-02 | INV-PKG-02-013-00082 | 432.11 | 31989.42 | 1599.47 | Paid | 30389.95 | 2025-Q2
EXP-001927 | 2025-06-27 | BOQ-PKG-07-01927 | PKG-07 | INV-PKG-07-003-01927 | 400.42 | 82384.38 | 4119.22 | Paid | 78265.16 | 2025-Q2
EXP-002166 | 2025-06-27 | BOQ-PKG-06-00176 | PKG-06 | INV-PKG-06-032-02166 | 134.18 | 180951.02 | 9047.55 | Disputed | 171903.47 | 2025-Q2
EXP-003477 | 2025-06-27 | BOQ-PKG-07-01487 | PKG-07 | INV-PKG-07-013-03477 | 152.34 | 86714.95 | 4335.75 | Paid | 82379.2 | 2025-Q2
EXP-004191 | 2025-06-27 | BOQ-PKG-01-00211 | PKG-01 | INV-PKG-01-027-04191 | 341.45 | 73025.27 | 3651.26 | Paid | 69374.01 | 2025-Q2
EXP-004212 | 2025-06-27 | BOQ-PKG-02-00232 | PKG-02 | INV-PKG-02-013-04212 | 100.53 | 109759.12 | 5487.96 | Approved Pending Payment | 104271.16 | 2025-Q2
EXP-006895 | 2025-06-27 | BOQ-PKG-05-00925 | PKG-05 | INV-PKG-05-001-06895 | 160.54 | 143284.25 | 7164.21 | Approved Pending Payment | 136120.04 | 2025-Q2
EXP-000938 | 2025-06-28 | BOQ-PKG-08-00938 | PKG-08 | INV-PKG-08-029-00938 | 319.63 | 55967.85 | 2798.39 | Approved Pending Payment | 53169.46 | 2025-Q2
EXP-001202 | 2025-06-28 | BOQ-PKG-02-01202 | PKG-02 | INV-PKG-02-013-01202 | 149.54 | 75840.16 | 3792.01 | Approved Pending Payment | 72048.15 | 2025-Q2
EXP-001765 | 2025-06-28 | BOQ-PKG-05-01765 | PKG-05 | INV-PKG-05-016-01765 | 30.83 | 148546.62 | 7427.33 | Approved Pending Payment | 141119.29 | 2025-Q2
EXP-001940 | 2025-06-28 | BOQ-PKG-10-01940 | PKG-10 | INV-PKG-10-016-01940 | 171.1 | 189174.93 | 9458.75 | Paid | 179716.18 | 2025-Q2
EXP-002200 | 2025-06-28 | BOQ-PKG-10-00210 | PKG-10 | INV-PKG-10-031-02200 | 247.33 | 63209.78 | 3160.49 | Approved Pending Payment | 60049.29 | 2025-Q2
EXP-003562 | 2025-06-28 | BOQ-PKG-02-01572 | PKG-02 | INV-PKG-02-028-03562 | 267.86 | 126594.38 | 6329.72 | Paid | 120264.66 | 2025-Q2
EXP-004955 | 2025-06-28 | BOQ-PKG-05-00975 | PKG-05 | INV-PKG-05-021-04955 | 138.71 | 208620.37 | 10431.02 | Paid | 198189.35 | 2025-Q2
EXP-004992 | 2025-06-28 | BOQ-PKG-02-01012 | PKG-02 | INV-PKG-02-023-04992 | 220.69 | 103166.55 | 5158.33 | Paid | 98008.22 | 2025-Q2
EXP-005604 | 2025-06-28 | BOQ-PKG-04-01624 | PKG-04 | INV-PKG-04-005-05604 | 378.48 | 161412.25 | 8070.61 | Paid | 153341.64 | 2025-Q2
EXP-000231 | 2025-06-29 | BOQ-PKG-01-00231 | PKG-01 | INV-PKG-01-022-00231 | 234.06 | 40917.99 | 2045.9 | Disputed | 38872.09 | 2025-Q2
EXP-000643 | 2025-06-29 | BOQ-PKG-03-00643 | PKG-03 | INV-PKG-03-014-00643 | 221.45 | 115218.46 | 5760.92 | Approved Pending Payment | 109457.54 | 2025-Q2
EXP-002443 | 2025-06-29 | BOQ-PKG-03-00453 | PKG-03 | INV-PKG-03-029-02443 | 25.37 | 199922.65 | 9996.13 | Disputed | 189926.52 | 2025-Q2
EXP-003661 | 2025-06-29 | BOQ-PKG-01-01671 | PKG-01 | INV-PKG-01-022-03661 | 190.05 | 189535 | 9476.75 | Approved Pending Payment | 180058.25 | 2025-Q2
EXP-004354 | 2025-06-29 | BOQ-PKG-04-00374 | PKG-04 | INV-PKG-04-015-04354 | 47.89 | 179520.11 | 8976.01 | Paid | 170544.1 | 2025-Q2
EXP-005869 | 2025-06-29 | BOQ-PKG-09-01889 | PKG-09 | INV-PKG-09-025-05869 | 247.64 | 30575.4 | 1528.77 | Paid | 29046.63 | 2025-Q2
EXP-006496 | 2025-06-29 | BOQ-PKG-06-00526 | PKG-06 | INV-PKG-06-022-06496 | 100.37 | 124636.4 | 6231.82 | Paid | 118404.58 | 2025-Q2
EXP-006704 | 2025-06-29 | BOQ-PKG-04-00734 | PKG-04 | INV-PKG-04-020-06704 | 128.36 | 92629.41 | 4631.47 | Approved Pending Payment | 87997.94 | 2025-Q2
EXP-006753 | 2025-06-29 | BOQ-PKG-03-00783 | PKG-03 | INV-PKG-03-034-06753 | 396.53 | 105288.5 | 5264.42 | Paid | 100024.08 | 2025-Q2
EXP-001137 | 2025-06-30 | BOQ-PKG-07-01137 | PKG-07 | INV-PKG-07-018-01137 | 118.48 | 70325.83 | 3516.29 | Paid | 66809.54 | 2025-Q2
EXP-001749 | 2025-06-30 | BOQ-PKG-09-01749 | PKG-09 | INV-PKG-09-035-01749 | 42.68 | 198822.47 | 9941.12 | Paid | 188881.35 | 2025-Q2
EXP-002844 | 2025-06-30 | BOQ-PKG-04-00854 | PKG-04 | INV-PKG-04-010-02844 | 347.08 | 167642.49 | 8382.12 | Paid | 159260.37 | 2025-Q2
EXP-003515 | 2025-06-30 | BOQ-PKG-05-01525 | PKG-05 | INV-PKG-05-016-03515 | 163.17 | 127678.38 | 6383.92 | Paid | 121294.46 | 2025-Q2
EXP-004626 | 2025-06-30 | BOQ-PKG-06-00646 | PKG-06 | INV-PKG-06-007-04626 | 230.46 | 148222.95 | 7411.15 | Paid | 140811.8 | 2025-Q2
EXP-004673 | 2025-06-30 | BOQ-PKG-03-00693 | PKG-03 | INV-PKG-03-019-04673 | 88.67 | 118665.4 | 5933.27 | Paid | 112732.13 | 2025-Q2
EXP-005217 | 2025-06-30 | BOQ-PKG-07-01237 | PKG-07 | INV-PKG-07-003-05217 | 33.4 | 148132.61 | 7406.63 | Approved Pending Payment | 140725.98 | 2025-Q2
EXP-005302 | 2025-06-30 | BOQ-PKG-02-01322 | PKG-02 | INV-PKG-02-018-05302 | 322.47 | 144603.28 | 7230.16 | Paid | 137373.12 | 2025-Q2
EXP-006251 | 2025-06-30 | BOQ-PKG-01-00281 | PKG-01 | INV-PKG-01-022-06251 | 75.83 | 83918.19 | 4195.91 | Paid | 79722.28 | 2025-Q2
EXP-006831 | 2025-06-30 | BOQ-PKG-01-00861 | PKG-01 | INV-PKG-01-007-06831 | 136.33 | 200007.77 | 10000.39 | Approved Pending Payment | 190007.38 | 2025-Q2
EXP-002618 | 2025-07-01 | BOQ-PKG-08-00628 | PKG-08 | INV-PKG-08-029-02618 | 248.01 | 206706.54 | 10335.33 | Approved Pending Payment | 196371.21 | 2025-Q3
EXP-002709 | 2025-07-01 | BOQ-PKG-09-00719 | PKG-09 | INV-PKG-09-015-02709 | 270.26 | 103150.02 | 5157.5 | Paid | 97992.52 | 2025-Q3
EXP-003315 | 2025-07-01 | BOQ-PKG-05-01325 | PKG-05 | INV-PKG-05-026-03315 | 219.53 | 32471.64 | 1623.58 | Paid | 30848.06 | 2025-Q3
EXP-003595 | 2025-07-01 | BOQ-PKG-05-01605 | PKG-05 | INV-PKG-05-026-03595 | 386.26 | 142176.96 | 7108.85 | Paid | 135068.11 | 2025-Q3
EXP-004265 | 2025-07-01 | BOQ-PKG-05-00285 | PKG-05 | INV-PKG-05-031-04265 | 210.09 | 187716.61 | 9385.83 | Approved Pending Payment | 178330.78 | 2025-Q3
EXP-004998 | 2025-07-01 | BOQ-PKG-08-01018 | PKG-08 | INV-PKG-08-029-04998 | 280.68 | 203779.03 | 10188.95 | Under Review | 193590.08 | 2025-Q3
EXP-005914 | 2025-07-01 | BOQ-PKG-04-01934 | PKG-04 | INV-PKG-04-035-05914 | 272.66 | 123862.71 | 6193.14 | Approved Pending Payment | 117669.57 | 2025-Q3
EXP-000492 | 2025-07-02 | BOQ-PKG-02-00492 | PKG-02 | INV-PKG-02-003-00492 | 250.95 | 44032.89 | 2201.64 | Paid | 41831.25 | 2025-Q3
EXP-000519 | 2025-07-02 | BOQ-PKG-09-00519 | PKG-09 | INV-PKG-09-030-00519 | 7.61 | 39748.89 | 1987.44 | Paid | 37761.45 | 2025-Q3
EXP-001136 | 2025-07-02 | BOQ-PKG-06-01136 | PKG-06 | INV-PKG-06-017-01136 | 425.5 | 61123.85 | 3056.19 | Approved Pending Payment | 58067.66 | 2025-Q3
EXP-003699 | 2025-07-02 | BOQ-PKG-09-01709 | PKG-09 | INV-PKG-09-025-03699 | 343.87 | 187162.3 | 9358.12 | Approved Pending Payment | 177804.18 | 2025-Q3
EXP-004223 | 2025-07-02 | BOQ-PKG-03-00243 | PKG-03 | INV-PKG-03-024-04223 | 401.07 | 88270.75 | 4413.54 | Paid | 83857.21 | 2025-Q3
EXP-000027 | 2025-07-03 | BOQ-PKG-07-00027 | PKG-07 | INV-PKG-07-028-00027 | 227.62 | 35709.04 | 1785.45 | Paid | 33923.59 | 2025-Q3
EXP-000552 | 2025-07-03 | BOQ-PKG-02-00552 | PKG-02 | INV-PKG-02-028-00552 | 424.98 | 24146.98 | 1207.35 | Under Review | 22939.63 | 2025-Q3
EXP-002327 | 2025-07-03 | BOQ-PKG-07-00337 | PKG-07 | INV-PKG-07-018-02327 | 332.39 | 73492.89 | 3674.64 | Under Review | 69818.25 | 2025-Q3
EXP-004057 | 2025-07-03 | BOQ-PKG-07-00077 | PKG-07 | INV-PKG-07-033-04057 | 151.88 | 105095.51 | 5254.78 | Under Review | 99840.73 | 2025-Q3
EXP-005799 | 2025-07-03 | BOQ-PKG-09-01819 | PKG-09 | INV-PKG-09-025-05799 | 239.56 | 83646.66 | 4182.33 | Paid | 79464.33 | 2025-Q3
EXP-000116 | 2025-07-04 | BOQ-PKG-06-00116 | PKG-06 | INV-PKG-06-012-00116 | 300.05 | 155825 | 7791.25 | Disputed | 148033.75 | 2025-Q3
EXP-001516 | 2025-07-04 | BOQ-PKG-06-01516 | PKG-06 | INV-PKG-06-012-01516 | 388.11 | 172102.19 | 8605.11 | Approved Pending Payment | 163497.08 | 2025-Q3
EXP-002290 | 2025-07-04 | BOQ-PKG-10-00300 | PKG-10 | INV-PKG-10-016-02290 | 277.09 | 37858.94 | 1892.95 | Paid | 35965.99 | 2025-Q3
EXP-003670 | 2025-07-04 | BOQ-PKG-10-01680 | PKG-10 | INV-PKG-10-031-03670 | 278.73 | 113257.59 | 5662.88 | Under Review | 107594.71 | 2025-Q3
EXP-006015 | 2025-07-04 | BOQ-PKG-05-00045 | PKG-05 | INV-PKG-05-031-06015 | 422.21 | 140095.4 | 7004.77 | Approved Pending Payment | 133090.63 | 2025-Q3
EXP-006692 | 2025-07-04 | BOQ-PKG-02-00722 | PKG-02 | INV-PKG-02-008-06692 | 206.4 | 110227.1 | 5511.36 | Paid | 104715.74 | 2025-Q3
EXP-001198 | 2025-07-05 | BOQ-PKG-08-01198 | PKG-08 | INV-PKG-08-009-01198 | 323.4 | 45274.73 | 2263.74 | Paid | 43010.99 | 2025-Q3
EXP-001472 | 2025-07-05 | BOQ-PKG-02-01472 | PKG-02 | INV-PKG-02-003-01472 | 144.13 | 58825.58 | 2941.28 | Paid | 55884.3 | 2025-Q3
EXP-001807 | 2025-07-05 | BOQ-PKG-07-01807 | PKG-07 | INV-PKG-07-023-01807 | 288.6 | 157948.92 | 7897.45 | Under Review | 150051.47 | 2025-Q3
EXP-002295 | 2025-07-05 | BOQ-PKG-05-00305 | PKG-05 | INV-PKG-05-021-02295 | 110.88 | 208546.25 | 10427.31 | Paid | 198118.94 | 2025-Q3
EXP-002372 | 2025-07-05 | BOQ-PKG-02-00382 | PKG-02 | INV-PKG-02-028-02372 | 406.21 | 120474.59 | 6023.73 | Under Review | 114450.86 | 2025-Q3
EXP-002677 | 2025-07-05 | BOQ-PKG-07-00687 | PKG-07 | INV-PKG-07-018-02677 | 105.55 | 190628.39 | 9531.42 | Approved Pending Payment | 181096.97 | 2025-Q3
EXP-003281 | 2025-07-05 | BOQ-PKG-01-01291 | PKG-01 | INV-PKG-01-027-03281 | 138.74 | 78181.49 | 3909.07 | Paid | 74272.42 | 2025-Q3
EXP-003608 | 2025-07-05 | BOQ-PKG-08-01618 | PKG-08 | INV-PKG-08-004-03608 | 359.76 | 109547.47 | 5477.37 | Paid | 104070.1 | 2025-Q3
EXP-005584 | 2025-07-05 | BOQ-PKG-04-01604 | PKG-04 | INV-PKG-04-020-05584 | 291.74 | 48589.47 | 2429.47 | Under Review | 46160 | 2025-Q3
EXP-006597 | 2025-07-05 | BOQ-PKG-07-00627 | PKG-07 | INV-PKG-07-018-06597 | 265.33 | 63787.11 | 3189.36 | Approved Pending Payment | 60597.75 | 2025-Q3
EXP-001410 | 2025-07-06 | BOQ-PKG-10-01410 | PKG-10 | INV-PKG-10-011-01410 | 71.48 | 114429.58 | 5721.48 | Paid | 108708.1 | 2025-Q3
EXP-001880 | 2025-07-06 | BOQ-PKG-10-01880 | PKG-10 | INV-PKG-10-026-01880 | 405.21 | 207194.07 | 10359.7 | Approved Pending Payment | 196834.37 | 2025-Q3
EXP-002645 | 2025-07-06 | BOQ-PKG-05-00655 | PKG-05 | INV-PKG-05-021-02645 | 327.17 | 101132.17 | 5056.61 | Paid | 96075.56 | 2025-Q3
EXP-003878 | 2025-07-06 | BOQ-PKG-08-01888 | PKG-08 | INV-PKG-08-029-03878 | 110.4 | 25621.51 | 1281.08 | Paid | 24340.43 | 2025-Q3
EXP-003950 | 2025-07-06 | BOQ-PKG-10-01960 | PKG-10 | INV-PKG-10-031-03950 | 181.92 | 37354.46 | 1867.72 | Paid | 35486.74 | 2025-Q3
EXP-005886 | 2025-07-06 | BOQ-PKG-06-01906 | PKG-06 | INV-PKG-06-007-05886 | 40.13 | 212355.98 | 10617.8 | Under Review | 201738.18 | 2025-Q3
EXP-005924 | 2025-07-06 | BOQ-PKG-04-01944 | PKG-04 | INV-PKG-04-010-05924 | 271.38 | 50815.57 | 2540.78 | Under Review | 48274.79 | 2025-Q3
EXP-000773 | 2025-07-07 | BOQ-PKG-03-00773 | PKG-03 | INV-PKG-03-004-00773 | 200.58 | 36391.23 | 1819.56 | Approved Pending Payment | 34571.67 | 2025-Q3
EXP-001959 | 2025-07-07 | BOQ-PKG-09-01959 | PKG-09 | INV-PKG-09-035-01959 | 367.32 | 171351.38 | 8567.57 | Under Review | 162783.81 | 2025-Q3
EXP-002740 | 2025-07-07 | BOQ-PKG-10-00750 | PKG-10 | INV-PKG-10-011-02740 | 308.69 | 40277.51 | 2013.88 | Paid | 38263.63 | 2025-Q3
EXP-003087 | 2025-07-07 | BOQ-PKG-07-01097 | PKG-07 | INV-PKG-07-008-03087 | 28.79 | 117882.56 | 5894.13 | Paid | 111988.43 | 2025-Q3
EXP-004557 | 2025-07-07 | BOQ-PKG-07-00577 | PKG-07 | INV-PKG-07-008-04557 | 205.1 | 192061.58 | 9603.08 | Paid | 182458.5 | 2025-Q3
EXP-005507 | 2025-07-07 | BOQ-PKG-07-01527 | PKG-07 | INV-PKG-07-013-05507 | 243.01 | 99944.5 | 4997.23 | Paid | 94947.27 | 2025-Q3
EXP-005551 | 2025-07-07 | BOQ-PKG-01-01571 | PKG-01 | INV-PKG-01-022-05551 | 258.33 | 96854.66 | 4842.73 | Approved Pending Payment | 92011.93 | 2025-Q3
EXP-006356 | 2025-07-07 | BOQ-PKG-06-00386 | PKG-06 | INV-PKG-06-022-06356 | 351.03 | 157951.35 | 7897.57 | Paid | 150053.78 | 2025-Q3
EXP-006438 | 2025-07-07 | BOQ-PKG-08-00468 | PKG-08 | INV-PKG-08-034-06438 | 370.54 | 31159.94 | 1558 | Paid | 29601.94 | 2025-Q3
EXP-000462 | 2025-07-08 | BOQ-PKG-02-00462 | PKG-02 | INV-PKG-02-008-00462 | 391.14 | 108442.58 | 5422.13 | Paid | 103020.45 | 2025-Q3
EXP-002229 | 2025-07-08 | BOQ-PKG-09-00239 | PKG-09 | INV-PKG-09-025-02229 | 20.88 | 120846.36 | 6042.32 | Paid | 114804.04 | 2025-Q3
EXP-003274 | 2025-07-08 | BOQ-PKG-04-01284 | PKG-04 | INV-PKG-04-020-03274 | 176.37 | 46567.7 | 2328.38 | Paid | 44239.32 | 2025-Q3
EXP-003568 | 2025-07-08 | BOQ-PKG-08-01578 | PKG-08 | INV-PKG-08-034-03568 | 48.18 | 140307.54 | 7015.38 | Under Review | 133292.16 | 2025-Q3
EXP-003980 | 2025-07-08 | BOQ-PKG-10-01990 | PKG-10 | INV-PKG-10-026-03980 | 156.67 | 161759.39 | 8087.97 | Paid | 153671.42 | 2025-Q3
EXP-005659 | 2025-07-08 | BOQ-PKG-09-01679 | PKG-09 | INV-PKG-09-025-05659 | 272.79 | 200202.17 | 10010.11 | Paid | 190192.06 | 2025-Q3
EXP-006700 | 2025-07-08 | BOQ-PKG-10-00730 | PKG-10 | INV-PKG-10-016-06700 | 377.09 | 115103.2 | 5755.16 | Paid | 109348.04 | 2025-Q3
EXP-000661 | 2025-07-09 | BOQ-PKG-01-00661 | PKG-01 | INV-PKG-01-032-00661 | 28.84 | 50652.02 | 2532.6 | Paid | 48119.42 | 2025-Q3
EXP-004043 | 2025-07-09 | BOQ-PKG-03-00063 | PKG-03 | INV-PKG-03-019-04043 | 319.86 | 100769.06 | 5038.45 | Disputed | 95730.61 | 2025-Q3
EXP-004125 | 2025-07-09 | BOQ-PKG-05-00145 | PKG-05 | INV-PKG-05-031-04125 | 224 | 124220.44 | 6211.02 | Under Review | 118009.42 | 2025-Q3
EXP-005944 | 2025-07-09 | BOQ-PKG-04-01964 | PKG-04 | INV-PKG-04-030-05944 | 289.17 | 88381.14 | 4419.06 | Paid | 83962.08 | 2025-Q3
EXP-006209 | 2025-07-09 | BOQ-PKG-09-00239 | PKG-09 | INV-PKG-09-015-06209 | 297.15 | 45421.79 | 2271.09 | Paid | 43150.7 | 2025-Q3
EXP-000545 | 2025-07-10 | BOQ-PKG-05-00545 | PKG-05 | INV-PKG-05-021-00545 | 336.7 | 93230.38 | 4661.52 | Paid | 88568.86 | 2025-Q3
EXP-002157 | 2025-07-10 | BOQ-PKG-07-00167 | PKG-07 | INV-PKG-07-023-02157 | 398.47 | 26982.29 | 1349.11 | Under Review | 25633.18 | 2025-Q3
EXP-002195 | 2025-07-10 | BOQ-PKG-05-00205 | PKG-05 | INV-PKG-05-026-02195 | 71.74 | 168068.64 | 8403.43 | Paid | 159665.21 | 2025-Q3
EXP-002889 | 2025-07-10 | BOQ-PKG-09-00899 | PKG-09 | INV-PKG-09-020-02889 | 42.9 | 137459.33 | 6872.97 | Paid | 130586.36 | 2025-Q3
EXP-004994 | 2025-07-10 | BOQ-PKG-04-01014 | PKG-04 | INV-PKG-04-025-04994 | 253.87 | 78703.68 | 3935.18 | Under Review | 74768.5 | 2025-Q3
EXP-005732 | 2025-07-10 | BOQ-PKG-02-01752 | PKG-02 | INV-PKG-02-028-05732 | 235.25 | 154496.56 | 7724.83 | Under Review | 146771.73 | 2025-Q3
EXP-000005 | 2025-07-11 | BOQ-PKG-05-00005 | PKG-05 | INV-PKG-05-006-00005 | 363.42 | 161372.39 | 8068.62 | Paid | 153303.77 | 2025-Q3
EXP-000537 | 2025-07-11 | BOQ-PKG-07-00537 | PKG-07 | INV-PKG-07-013-00537 | 201.62 | 90386.03 | 4519.3 | Under Review | 85866.73 | 2025-Q3
EXP-000889 | 2025-07-11 | BOQ-PKG-09-00889 | PKG-09 | INV-PKG-09-015-00889 | 117.87 | 63974.34 | 3198.72 | Paid | 60775.62 | 2025-Q3
EXP-001299 | 2025-07-11 | BOQ-PKG-09-01299 | PKG-09 | INV-PKG-09-005-01299 | 384.59 | 169389.74 | 8469.49 | Paid | 160920.25 | 2025-Q3
EXP-001333 | 2025-07-11 | BOQ-PKG-03-01333 | PKG-03 | INV-PKG-03-004-01333 | 402.96 | 116590.92 | 5829.55 | Paid | 110761.37 | 2025-Q3
EXP-003660 | 2025-07-11 | BOQ-PKG-10-01670 | PKG-10 | INV-PKG-10-021-03660 | 137.44 | 213086.93 | 10654.35 | Paid | 202432.58 | 2025-Q3
EXP-004687 | 2025-07-11 | BOQ-PKG-07-00707 | PKG-07 | INV-PKG-07-033-04687 | 23.96 | 138046.1 | 6902.3 | Approved Pending Payment | 131143.8 | 2025-Q3
EXP-005088 | 2025-07-11 | BOQ-PKG-08-01108 | PKG-08 | INV-PKG-08-014-05088 | 132.5 | 169237.51 | 8461.88 | Paid | 160775.63 | 2025-Q3
EXP-005666 | 2025-07-11 | BOQ-PKG-06-01686 | PKG-06 | INV-PKG-06-032-05666 | 311.74 | 205399.12 | 10269.96 | Paid | 195129.16 | 2025-Q3
EXP-005830 | 2025-07-11 | BOQ-PKG-10-01850 | PKG-10 | INV-PKG-10-021-05830 | 367.67 | 127973.52 | 6398.68 | Approved Pending Payment | 121574.84 | 2025-Q3
EXP-006518 | 2025-07-11 | BOQ-PKG-08-00548 | PKG-08 | INV-PKG-08-009-06518 | 11.83 | 196737.48 | 9836.87 | Approved Pending Payment | 186900.61 | 2025-Q3
EXP-000333 | 2025-07-12 | BOQ-PKG-03-00333 | PKG-03 | INV-PKG-03-019-00333 | 369.68 | 83943.13 | 4197.16 | Paid | 79745.97 | 2025-Q3
EXP-000973 | 2025-07-12 | BOQ-PKG-03-00973 | PKG-03 | INV-PKG-03-029-00973 | 384.87 | 71145.38 | 3557.27 | Paid | 67588.11 | 2025-Q3
EXP-001164 | 2025-07-12 | BOQ-PKG-04-01164 | PKG-04 | INV-PKG-04-010-01164 | 416.96 | 143466.99 | 7173.35 | Under Review | 136293.64 | 2025-Q3
EXP-002614 | 2025-07-12 | BOQ-PKG-04-00624 | PKG-04 | INV-PKG-04-025-02614 | 258.99 | 195027.06 | 9751.35 | Paid | 185275.71 | 2025-Q3
EXP-002615 | 2025-07-12 | BOQ-PKG-05-00625 | PKG-05 | INV-PKG-05-026-02615 | 45.64 | 59711.66 | 2985.58 | Paid | 56726.08 | 2025-Q3
EXP-004048 | 2025-07-12 | BOQ-PKG-08-00068 | PKG-08 | INV-PKG-08-024-04048 | 274.84 | 57043.45 | 2852.17 | Under Review | 54191.28 | 2025-Q3
EXP-004975 | 2025-07-12 | BOQ-PKG-05-00995 | PKG-05 | INV-PKG-05-006-04975 | 154.19 | 87401.51 | 4370.08 | Paid | 83031.43 | 2025-Q3
EXP-005349 | 2025-07-12 | BOQ-PKG-09-01369 | PKG-09 | INV-PKG-09-030-05349 | 103.79 | 105565.89 | 5278.29 | Approved Pending Payment | 100287.6 | 2025-Q3
EXP-005770 | 2025-07-12 | BOQ-PKG-10-01790 | PKG-10 | INV-PKG-10-031-05770 | 277.62 | 108244.26 | 5412.21 | Paid | 102832.05 | 2025-Q3
EXP-001413 | 2025-07-13 | BOQ-PKG-03-01413 | PKG-03 | INV-PKG-03-014-01413 | 314.56 | 199788.33 | 9989.42 | Paid | 189798.91 | 2025-Q3
EXP-002530 | 2025-07-13 | BOQ-PKG-10-00540 | PKG-10 | INV-PKG-10-011-02530 | 223.85 | 161689.54 | 8084.48 | Paid | 153605.06 | 2025-Q3
EXP-002630 | 2025-07-13 | BOQ-PKG-10-00640 | PKG-10 | INV-PKG-10-006-02630 | 70.59 | 83944.58 | 4197.23 | Approved Pending Payment | 79747.35 | 2025-Q3
EXP-003203 | 2025-07-13 | BOQ-PKG-03-01213 | PKG-03 | INV-PKG-03-019-03203 | 342.9 | 40627.84 | 2031.39 | Under Review | 38596.45 | 2025-Q3
EXP-003834 | 2025-07-13 | BOQ-PKG-04-01844 | PKG-04 | INV-PKG-04-020-03834 | 103.69 | 102946.91 | 5147.35 | Paid | 97799.56 | 2025-Q3
EXP-004201 | 2025-07-13 | BOQ-PKG-01-00221 | PKG-01 | INV-PKG-01-002-04201 | 132.74 | 147746.21 | 7387.31 | Paid | 140358.9 | 2025-Q3
EXP-000020 | 2025-07-14 | BOQ-PKG-10-00020 | PKG-10 | INV-PKG-10-021-00020 | 195.93 | 77043.14 | 3852.16 | Paid | 73190.98 | 2025-Q3
EXP-000123 | 2025-07-14 | BOQ-PKG-03-00123 | PKG-03 | INV-PKG-03-019-00123 | 97.03 | 116387.99 | 5819.4 | Paid | 110568.59 | 2025-Q3
EXP-000233 | 2025-07-14 | BOQ-PKG-03-00233 | PKG-03 | INV-PKG-03-024-00233 | 61.12 | 135317.58 | 6765.88 | Paid | 128551.7 | 2025-Q3
EXP-001956 | 2025-07-14 | BOQ-PKG-06-01956 | PKG-06 | INV-PKG-06-032-01956 | 151.01 | 172721.72 | 8636.09 | Paid | 164085.63 | 2025-Q3
EXP-002320 | 2025-07-14 | BOQ-PKG-10-00330 | PKG-10 | INV-PKG-10-011-02320 | 211.18 | 150597.04 | 7529.85 | Approved Pending Payment | 143067.19 | 2025-Q3
EXP-003318 | 2025-07-14 | BOQ-PKG-08-01328 | PKG-08 | INV-PKG-08-029-03318 | 307.88 | 86408.98 | 4320.45 | Paid | 82088.53 | 2025-Q3
EXP-005379 | 2025-07-14 | BOQ-PKG-09-01399 | PKG-09 | INV-PKG-09-025-05379 | 157.25 | 153055.35 | 7652.77 | Paid | 145402.58 | 2025-Q3
EXP-000290 | 2025-07-15 | BOQ-PKG-10-00290 | PKG-10 | INV-PKG-10-011-00290 | 442.59 | 70027.93 | 3501.4 | Paid | 66526.53 | 2025-Q3
EXP-001025 | 2025-07-15 | BOQ-PKG-05-01025 | PKG-05 | INV-PKG-05-011-01025 | 357.44 | 85921.51 | 4296.08 | Paid | 81625.43 | 2025-Q3
EXP-002373 | 2025-07-15 | BOQ-PKG-03-00383 | PKG-03 | INV-PKG-03-029-02373 | 420.58 | 83375.43 | 4168.77 | Paid | 79206.66 | 2025-Q3
EXP-002900 | 2025-07-15 | BOQ-PKG-10-00910 | PKG-10 | INV-PKG-10-031-02900 | 256.96 | 73453.96 | 3672.7 | Paid | 69781.26 | 2025-Q3
EXP-005731 | 2025-07-15 | BOQ-PKG-01-01751 | PKG-01 | INV-PKG-01-027-05731 | 149.98 | 127979.85 | 6398.99 | Paid | 121580.86 | 2025-Q3
EXP-006242 | 2025-07-15 | BOQ-PKG-02-00272 | PKG-02 | INV-PKG-02-013-06242 | 69.42 | 171299.78 | 8564.99 | Approved Pending Payment | 162734.79 | 2025-Q3
EXP-000740 | 2025-07-16 | BOQ-PKG-10-00740 | PKG-10 | INV-PKG-10-006-00740 | 338.45 | 197241.28 | 9862.06 | Paid | 187379.22 | 2025-Q3
EXP-000785 | 2025-07-16 | BOQ-PKG-05-00785 | PKG-05 | INV-PKG-05-016-00785 | 103.41 | 75946.99 | 3797.35 | Paid | 72149.64 | 2025-Q3
EXP-001368 | 2025-07-16 | BOQ-PKG-08-01368 | PKG-08 | INV-PKG-08-004-01368 | 400.93 | 151078.96 | 7553.95 | Paid | 143525.01 | 2025-Q3
EXP-003224 | 2025-07-16 | BOQ-PKG-04-01234 | PKG-04 | INV-PKG-04-005-03224 | 192.59 | 140189.54 | 7009.48 | Paid | 133180.06 | 2025-Q3
EXP-003894 | 2025-07-16 | BOQ-PKG-04-01904 | PKG-04 | INV-PKG-04-010-03894 | 235.62 | 102276.63 | 5113.83 | Paid | 97162.8 | 2025-Q3
EXP-005297 | 2025-07-16 | BOQ-PKG-07-01317 | PKG-07 | INV-PKG-07-013-05297 | 77.45 | 51832.55 | 2591.63 | Approved Pending Payment | 49240.92 | 2025-Q3
EXP-005625 | 2025-07-16 | BOQ-PKG-05-01645 | PKG-05 | INV-PKG-05-026-05625 | 292.34 | 117643.75 | 5882.19 | Paid | 111761.56 | 2025-Q3
EXP-005800 | 2025-07-16 | BOQ-PKG-10-01820 | PKG-10 | INV-PKG-10-026-05800 | 113.81 | 197078.87 | 9853.94 | Paid | 187224.93 | 2025-Q3
EXP-006080 | 2025-07-16 | BOQ-PKG-10-00110 | PKG-10 | INV-PKG-10-026-06080 | 71.72 | 25434.96 | 1271.75 | Paid | 24163.21 | 2025-Q3
EXP-000270 | 2025-07-17 | BOQ-PKG-10-00270 | PKG-10 | INV-PKG-10-026-00270 | 41.74 | 52538.57 | 2626.93 | Paid | 49911.64 | 2025-Q3
EXP-000451 | 2025-07-17 | BOQ-PKG-01-00451 | PKG-01 | INV-PKG-01-032-00451 | 410.55 | 124146.68 | 6207.33 | Paid | 117939.35 | 2025-Q3
EXP-001275 | 2025-07-17 | BOQ-PKG-05-01275 | PKG-05 | INV-PKG-05-016-01275 | 311.71 | 44998 | 2249.9 | Paid | 42748.1 | 2025-Q3
EXP-002551 | 2025-07-17 | BOQ-PKG-01-00561 | PKG-01 | INV-PKG-01-032-02551 | 28.4 | 72383.8 | 3619.19 | Approved Pending Payment | 68764.61 | 2025-Q3
EXP-002780 | 2025-07-17 | BOQ-PKG-10-00790 | PKG-10 | INV-PKG-10-016-02780 | 110.68 | 72837.69 | 3641.88 | Paid | 69195.81 | 2025-Q3
EXP-003162 | 2025-07-17 | BOQ-PKG-02-01172 | PKG-02 | INV-PKG-02-013-03162 | 194.82 | 38587.6 | 1929.38 | Paid | 36658.22 | 2025-Q3
EXP-004055 | 2025-07-17 | BOQ-PKG-05-00075 | PKG-05 | INV-PKG-05-031-04055 | 433.02 | 98888.06 | 4944.4 | Approved Pending Payment | 93943.66 | 2025-Q3
EXP-004487 | 2025-07-17 | BOQ-PKG-07-00507 | PKG-07 | INV-PKG-07-008-04487 | 16.96 | 202882.3 | 10144.12 | Paid | 192738.18 | 2025-Q3
EXP-004543 | 2025-07-17 | BOQ-PKG-03-00563 | PKG-03 | INV-PKG-03-029-04543 | 21.58 | 174979.83 | 8748.99 | Paid | 166230.84 | 2025-Q3
EXP-005185 | 2025-07-17 | BOQ-PKG-05-01205 | PKG-05 | INV-PKG-05-006-05185 | 293.78 | 165752.63 | 8287.63 | Approved Pending Payment | 157465 | 2025-Q3
EXP-005470 | 2025-07-17 | BOQ-PKG-10-01490 | PKG-10 | INV-PKG-10-011-05470 | 168.88 | 37200.26 | 1860.01 | Paid | 35340.25 | 2025-Q3
EXP-000435 | 2025-07-18 | BOQ-PKG-05-00435 | PKG-05 | INV-PKG-05-016-00435 | 245.4 | 32192.18 | 1609.61 | Paid | 30582.57 | 2025-Q3
EXP-000604 | 2025-07-18 | BOQ-PKG-04-00604 | PKG-04 | INV-PKG-04-010-00604 | 301.83 | 191792.67 | 9589.63 | Paid | 182203.04 | 2025-Q3
EXP-001140 | 2025-07-18 | BOQ-PKG-10-01140 | PKG-10 | INV-PKG-10-021-01140 | 426.88 | 36795.46 | 1839.77 | Paid | 34955.69 | 2025-Q3
EXP-001354 | 2025-07-18 | BOQ-PKG-04-01354 | PKG-04 | INV-PKG-04-025-01354 | 395.33 | 185244.17 | 9262.21 | Paid | 175981.96 | 2025-Q3
EXP-003725 | 2025-07-18 | BOQ-PKG-05-01735 | PKG-05 | INV-PKG-05-016-03725 | 448.54 | 77504.62 | 3875.23 | Paid | 73629.39 | 2025-Q3
EXP-004279 | 2025-07-18 | BOQ-PKG-09-00299 | PKG-09 | INV-PKG-09-010-04279 | 356.33 | 102039.08 | 5101.95 | Paid | 96937.13 | 2025-Q3
EXP-004560 | 2025-07-18 | BOQ-PKG-10-00580 | PKG-10 | INV-PKG-10-011-04560 | 246.14 | 184321.17 | 9216.06 | Paid | 175105.11 | 2025-Q3
EXP-005109 | 2025-07-18 | BOQ-PKG-09-01129 | PKG-09 | INV-PKG-09-035-05109 | 298.31 | 187102.06 | 9355.1 | Paid | 177746.96 | 2025-Q3
EXP-006918 | 2025-07-18 | BOQ-PKG-08-00948 | PKG-08 | INV-PKG-08-024-06918 | 280.98 | 27588.17 | 1379.41 | Paid | 26208.76 | 2025-Q3
EXP-000069 | 2025-07-19 | BOQ-PKG-09-00069 | PKG-09 | INV-PKG-09-035-00069 | 421.49 | 149235.93 | 7461.8 | Approved Pending Payment | 141774.13 | 2025-Q3
EXP-001252 | 2025-07-19 | BOQ-PKG-02-01252 | PKG-02 | INV-PKG-02-028-01252 | 349.03 | 88285.56 | 4414.28 | Paid | 83871.28 | 2025-Q3
EXP-001621 | 2025-07-19 | BOQ-PKG-01-01621 | PKG-01 | INV-PKG-01-012-01621 | 283.39 | 32834.05 | 1641.7 | Paid | 31192.35 | 2025-Q3
EXP-001712 | 2025-07-19 | BOQ-PKG-02-01712 | PKG-02 | INV-PKG-02-033-01712 | 299.49 | 155542.15 | 7777.11 | Paid | 147765.04 | 2025-Q3
EXP-002964 | 2025-07-19 | BOQ-PKG-04-00974 | PKG-04 | INV-PKG-04-025-02964 | 312.91 | 195701.5 | 9785.08 | Disputed | 185916.42 | 2025-Q3
EXP-003418 | 2025-07-19 | BOQ-PKG-08-01428 | PKG-08 | INV-PKG-08-024-03418 | 288.21 | 88333.37 | 4416.67 | Paid | 83916.7 | 2025-Q3
EXP-003697 | 2025-07-19 | BOQ-PKG-07-01707 | PKG-07 | INV-PKG-07-023-03697 | 370.43 | 173515 | 8675.75 | Disputed | 164839.25 | 2025-Q3
EXP-003862 | 2025-07-19 | BOQ-PKG-02-01872 | PKG-02 | INV-PKG-02-013-03862 | 59.87 | 115097.17 | 5754.86 | Paid | 109342.31 | 2025-Q3
EXP-000060 | 2025-07-20 | BOQ-PKG-10-00060 | PKG-10 | INV-PKG-10-026-00060 | 183.65 | 84517.22 | 4225.86 | Paid | 80291.36 | 2025-Q3
EXP-000254 | 2025-07-20 | BOQ-PKG-04-00254 | PKG-04 | INV-PKG-04-010-00254 | 360.02 | 184699.66 | 9234.98 | Paid | 175464.68 | 2025-Q3
EXP-001898 | 2025-07-20 | BOQ-PKG-08-01898 | PKG-08 | INV-PKG-08-009-01898 | 240.81 | 177651.91 | 8882.6 | Paid | 168769.31 | 2025-Q3
EXP-002485 | 2025-07-20 | BOQ-PKG-05-00495 | PKG-05 | INV-PKG-05-001-02485 | 359.1 | 103920.06 | 5196 | Under Review | 98724.06 | 2025-Q3
EXP-002529 | 2025-07-20 | BOQ-PKG-09-00539 | PKG-09 | INV-PKG-09-010-02529 | 367.57 | 106190.93 | 5309.55 | Paid | 100881.38 | 2025-Q3
EXP-004567 | 2025-07-20 | BOQ-PKG-07-00587 | PKG-07 | INV-PKG-07-018-04567 | 95.84 | 166648.54 | 8332.43 | Approved Pending Payment | 158316.11 | 2025-Q3
EXP-005290 | 2025-07-20 | BOQ-PKG-10-01310 | PKG-10 | INV-PKG-10-006-05290 | 433.53 | 175192.05 | 8759.6 | Paid | 166432.45 | 2025-Q3
EXP-000478 | 2025-07-21 | BOQ-PKG-08-00478 | PKG-08 | INV-PKG-08-024-00478 | 163.76 | 54624.76 | 2731.24 | Approved Pending Payment | 51893.52 | 2025-Q3
EXP-001809 | 2025-07-21 | BOQ-PKG-09-01809 | PKG-09 | INV-PKG-09-025-01809 | 390.76 | 204702.68 | 10235.13 | Paid | 194467.55 | 2025-Q3
EXP-002214 | 2025-07-21 | BOQ-PKG-04-00224 | PKG-04 | INV-PKG-04-010-02214 | 68.77 | 105884.64 | 5294.23 | Paid | 100590.41 | 2025-Q3
EXP-002651 | 2025-07-21 | BOQ-PKG-01-00661 | PKG-01 | INV-PKG-01-027-02651 | 277.22 | 163270.22 | 8163.51 | Approved Pending Payment | 155106.71 | 2025-Q3
EXP-005144 | 2025-07-21 | BOQ-PKG-04-01164 | PKG-04 | INV-PKG-04-035-05144 | 379.77 | 81699.77 | 4084.99 | Paid | 77614.78 | 2025-Q3
EXP-002563 | 2025-07-22 | BOQ-PKG-03-00573 | PKG-03 | INV-PKG-03-009-02563 | 23.95 | 208210.08 | 10410.5 | Paid | 197799.58 | 2025-Q3
EXP-002667 | 2025-07-22 | BOQ-PKG-07-00677 | PKG-07 | INV-PKG-07-008-02667 | 269.98 | 169120.13 | 8456.01 | Paid | 160664.12 | 2025-Q3
EXP-004137 | 2025-07-22 | BOQ-PKG-07-00157 | PKG-07 | INV-PKG-07-008-04137 | 440.69 | 135326 | 6766.3 | Paid | 128559.7 | 2025-Q3
EXP-004551 | 2025-07-22 | BOQ-PKG-01-00571 | PKG-01 | INV-PKG-01-002-04551 | 212.36 | 128316.21 | 6415.81 | Paid | 121900.4 | 2025-Q3
EXP-006183 | 2025-07-22 | BOQ-PKG-03-00213 | PKG-03 | INV-PKG-03-024-06183 | 153.39 | 195587.62 | 9779.38 | Paid | 185808.24 | 2025-Q3
EXP-006682 | 2025-07-22 | BOQ-PKG-02-00712 | PKG-02 | INV-PKG-02-033-06682 | 135.4 | 199130.33 | 9956.52 | Paid | 189173.81 | 2025-Q3
EXP-006955 | 2025-07-22 | BOQ-PKG-05-00985 | PKG-05 | INV-PKG-05-026-06955 | 437.01 | 172077.35 | 8603.87 | Approved Pending Payment | 163473.48 | 2025-Q3
EXP-000981 | 2025-07-23 | BOQ-PKG-01-00981 | PKG-01 | INV-PKG-01-002-00981 | 202.1 | 29890.22 | 1494.51 | Approved Pending Payment | 28395.71 | 2025-Q3
EXP-004035 | 2025-07-23 | BOQ-PKG-05-00055 | PKG-05 | INV-PKG-05-011-04035 | 113.07 | 55379.74 | 2768.99 | Approved Pending Payment | 52610.75 | 2025-Q3
EXP-004128 | 2025-07-23 | BOQ-PKG-08-00148 | PKG-08 | INV-PKG-08-034-04128 | 84.09 | 29826.05 | 1491.3 | Paid | 28334.75 | 2025-Q3
EXP-004510 | 2025-07-23 | BOQ-PKG-10-00530 | PKG-10 | INV-PKG-10-031-04510 | 410.76 | 187918.5 | 9395.93 | Paid | 178522.57 | 2025-Q3
EXP-005329 | 2025-07-23 | BOQ-PKG-09-01349 | PKG-09 | INV-PKG-09-010-05329 | 72.34 | 184344.89 | 9217.24 | Paid | 175127.65 | 2025-Q3
EXP-006729 | 2025-07-23 | BOQ-PKG-09-00759 | PKG-09 | INV-PKG-09-010-06729 | 309.59 | 73621.26 | 3681.06 | Paid | 69940.2 | 2025-Q3
EXP-000913 | 2025-07-24 | BOQ-PKG-03-00913 | PKG-03 | INV-PKG-03-004-00913 | 305.02 | 176273.57 | 8813.68 | Paid | 167459.89 | 2025-Q3
EXP-000942 | 2025-07-24 | BOQ-PKG-02-00942 | PKG-02 | INV-PKG-02-033-00942 | 145.47 | 39298.46 | 1964.92 | Paid | 37333.54 | 2025-Q3
EXP-003587 | 2025-07-24 | BOQ-PKG-07-01597 | PKG-07 | INV-PKG-07-018-03587 | 117.82 | 170479.31 | 8523.97 | Paid | 161955.34 | 2025-Q3
EXP-003677 | 2025-07-24 | BOQ-PKG-07-01687 | PKG-07 | INV-PKG-07-003-03677 | 351.83 | 199747.88 | 9987.39 | Paid | 189760.49 | 2025-Q3
EXP-004586 | 2025-07-24 | BOQ-PKG-06-00606 | PKG-06 | INV-PKG-06-002-04586 | 155.34 | 100072.38 | 5003.62 | Under Review | 95068.76 | 2025-Q3
EXP-006715 | 2025-07-24 | BOQ-PKG-05-00745 | PKG-05 | INV-PKG-05-031-06715 | 316.2 | 159717.55 | 7985.88 | Paid | 151731.67 | 2025-Q3
EXP-001816 | 2025-07-25 | BOQ-PKG-06-01816 | PKG-06 | INV-PKG-06-032-01816 | 127.18 | 30756.19 | 1537.81 | Paid | 29218.38 | 2025-Q3
EXP-003972 | 2025-07-25 | BOQ-PKG-02-01982 | PKG-02 | INV-PKG-02-018-03972 | 142.78 | 155740.64 | 7787.03 | Paid | 147953.61 | 2025-Q3
EXP-004117 | 2025-07-25 | BOQ-PKG-07-00137 | PKG-07 | INV-PKG-07-023-04117 | 393.82 | 82880.62 | 4144.03 | Under Review | 78736.59 | 2025-Q3
EXP-004155 | 2025-07-25 | BOQ-PKG-05-00175 | PKG-05 | INV-PKG-05-026-04155 | 140.26 | 92755.64 | 4637.78 | Approved Pending Payment | 88117.86 | 2025-Q3
EXP-004208 | 2025-07-25 | BOQ-PKG-08-00228 | PKG-08 | INV-PKG-08-009-04208 | 399.85 | 126240.29 | 6312.01 | Approved Pending Payment | 119928.28 | 2025-Q3
EXP-005941 | 2025-07-25 | BOQ-PKG-01-01961 | PKG-01 | INV-PKG-01-027-05941 | 60.12 | 52940.53 | 2647.03 | Approved Pending Payment | 50293.5 | 2025-Q3
EXP-005981 | 2025-07-25 | BOQ-PKG-01-00011 | PKG-01 | INV-PKG-01-032-05981 | 13.69 | 61081.89 | 3054.09 | Paid | 58027.8 | 2025-Q3
EXP-006796 | 2025-07-25 | BOQ-PKG-06-00826 | PKG-06 | INV-PKG-06-007-06796 | 24.88 | 40785.36 | 2039.27 | Approved Pending Payment | 38746.09 | 2025-Q3
EXP-000112 | 2025-07-26 | BOQ-PKG-02-00112 | PKG-02 | INV-PKG-02-008-00112 | 194.79 | 134293.66 | 6714.68 | Paid | 127578.98 | 2025-Q3
EXP-001197 | 2025-07-26 | BOQ-PKG-07-01197 | PKG-07 | INV-PKG-07-008-01197 | 258.96 | 114803.74 | 5740.19 | Paid | 109063.55 | 2025-Q3
EXP-001463 | 2025-07-26 | BOQ-PKG-03-01463 | PKG-03 | INV-PKG-03-029-01463 | 146.48 | 129645.91 | 6482.3 | Paid | 123163.61 | 2025-Q3
EXP-002479 | 2025-07-26 | BOQ-PKG-09-00489 | PKG-09 | INV-PKG-09-030-02479 | 341.55 | 100476.39 | 5023.82 | Paid | 95452.57 | 2025-Q3
EXP-002539 | 2025-07-26 | BOQ-PKG-09-00549 | PKG-09 | INV-PKG-09-020-02539 | 143.29 | 214593.97 | 10729.7 | Paid | 203864.27 | 2025-Q3
EXP-003228 | 2025-07-26 | BOQ-PKG-08-01238 | PKG-08 | INV-PKG-08-009-03228 | 152.28 | 106572.4 | 5328.62 | Paid | 101243.78 | 2025-Q3
EXP-003749 | 2025-07-26 | BOQ-PKG-09-01759 | PKG-09 | INV-PKG-09-005-03749 | 262.28 | 123817.95 | 6190.9 | Paid | 117627.05 | 2025-Q3
EXP-004872 | 2025-07-26 | BOQ-PKG-02-00892 | PKG-02 | INV-PKG-02-008-04872 | 230.34 | 151318.72 | 7565.94 | Paid | 143752.78 | 2025-Q3
EXP-005003 | 2025-07-26 | BOQ-PKG-03-01023 | PKG-03 | INV-PKG-03-034-05003 | 433.06 | 41994.11 | 2099.71 | Paid | 39894.4 | 2025-Q3
EXP-006794 | 2025-07-26 | BOQ-PKG-04-00824 | PKG-04 | INV-PKG-04-005-06794 | 114.86 | 180270.39 | 9013.52 | Paid | 171256.87 | 2025-Q3
EXP-006840 | 2025-07-26 | BOQ-PKG-10-00870 | PKG-10 | INV-PKG-10-016-06840 | 407.23 | 146248.67 | 7312.43 | Paid | 138936.24 | 2025-Q3
EXP-001221 | 2025-07-27 | BOQ-PKG-01-01221 | PKG-01 | INV-PKG-01-032-01221 | 252.84 | 146348.73 | 7317.44 | Paid | 139031.29 | 2025-Q3
EXP-001346 | 2025-07-27 | BOQ-PKG-06-01346 | PKG-06 | INV-PKG-06-017-01346 | 283.78 | 125984.08 | 6299.2 | Paid | 119684.88 | 2025-Q3
EXP-001602 | 2025-07-27 | BOQ-PKG-02-01602 | PKG-02 | INV-PKG-02-028-01602 | 127.68 | 57873.19 | 2893.66 | Under Review | 54979.53 | 2025-Q3
EXP-002374 | 2025-07-27 | BOQ-PKG-04-00384 | PKG-04 | INV-PKG-04-030-02374 | 326.26 | 163745.08 | 8187.25 | Paid | 155557.83 | 2025-Q3
EXP-002562 | 2025-07-27 | BOQ-PKG-02-00572 | PKG-02 | INV-PKG-02-008-02562 | 166.45 | 142512.86 | 7125.64 | Under Review | 135387.22 | 2025-Q3
EXP-003081 | 2025-07-27 | BOQ-PKG-01-01091 | PKG-01 | INV-PKG-01-002-03081 | 10.66 | 192973.2 | 9648.66 | Under Review | 183324.54 | 2025-Q3
EXP-003132 | 2025-07-27 | BOQ-PKG-02-01142 | PKG-02 | INV-PKG-02-018-03132 | 90.79 | 48325.73 | 2416.29 | Paid | 45909.44 | 2025-Q3
EXP-003696 | 2025-07-27 | BOQ-PKG-06-01706 | PKG-06 | INV-PKG-06-022-03696 | 127.36 | 201462.34 | 10073.12 | Disputed | 191389.22 | 2025-Q3
EXP-003851 | 2025-07-27 | BOQ-PKG-01-01861 | PKG-01 | INV-PKG-01-002-03851 | 88.05 | 115833.38 | 5791.67 | Approved Pending Payment | 110041.71 | 2025-Q3
EXP-005948 | 2025-07-27 | BOQ-PKG-08-01968 | PKG-08 | INV-PKG-08-034-05948 | 353.07 | 64382.87 | 3219.14 | Paid | 61163.73 | 2025-Q3
EXP-001486 | 2025-07-28 | BOQ-PKG-06-01486 | PKG-06 | INV-PKG-06-017-01486 | 90.39 | 132499.37 | 6624.97 | Paid | 125874.4 | 2025-Q3
EXP-004935 | 2025-07-28 | BOQ-PKG-05-00955 | PKG-05 | INV-PKG-05-001-04935 | 249.88 | 139939.91 | 6997 | Under Review | 132942.91 | 2025-Q3
EXP-005389 | 2025-07-28 | BOQ-PKG-09-01409 | PKG-09 | INV-PKG-09-035-05389 | 321.27 | 124793.49 | 6239.67 | Approved Pending Payment | 118553.82 | 2025-Q3
EXP-006113 | 2025-07-28 | BOQ-PKG-03-00143 | PKG-03 | INV-PKG-03-024-06113 | 177.8 | 200584 | 10029.2 | Paid | 190554.8 | 2025-Q3
EXP-006207 | 2025-07-28 | BOQ-PKG-07-00237 | PKG-07 | INV-PKG-07-013-06207 | 92.72 | 196047.83 | 9802.39 | Paid | 186245.44 | 2025-Q3
EXP-006240 | 2025-07-28 | BOQ-PKG-10-00270 | PKG-10 | INV-PKG-10-011-06240 | 399.1 | 139976.7 | 6998.84 | Under Review | 132977.86 | 2025-Q3
EXP-006462 | 2025-07-28 | BOQ-PKG-02-00492 | PKG-02 | INV-PKG-02-023-06462 | 261.11 | 44020.08 | 2201 | Approved Pending Payment | 41819.08 | 2025-Q3
EXP-001743 | 2025-07-29 | BOQ-PKG-03-01743 | PKG-03 | INV-PKG-03-029-01743 | 331.66 | 123037.97 | 6151.9 | Approved Pending Payment | 116886.07 | 2025-Q3
EXP-002466 | 2025-07-29 | BOQ-PKG-06-00476 | PKG-06 | INV-PKG-06-017-02466 | 135.62 | 51289.25 | 2564.46 | Paid | 48724.79 | 2025-Q3
EXP-002571 | 2025-07-29 | BOQ-PKG-01-00581 | PKG-01 | INV-PKG-01-017-02571 | 17.9 | 134467.36 | 6723.37 | Approved Pending Payment | 127743.99 | 2025-Q3
EXP-002701 | 2025-07-29 | BOQ-PKG-01-00711 | PKG-01 | INV-PKG-01-007-02701 | 402.04 | 150387.12 | 7519.36 | Under Review | 142867.76 | 2025-Q3
EXP-005676 | 2025-07-29 | BOQ-PKG-06-01696 | PKG-06 | INV-PKG-06-007-05676 | 335.03 | 51245.93 | 2562.3 | Under Review | 48683.63 | 2025-Q3
EXP-006223 | 2025-07-29 | BOQ-PKG-03-00253 | PKG-03 | INV-PKG-03-029-06223 | 28.11 | 163376 | 8168.8 | Approved Pending Payment | 155207.2 | 2025-Q3
EXP-000501 | 2025-07-30 | BOQ-PKG-01-00501 | PKG-01 | INV-PKG-01-012-00501 | 219.71 | 134800.34 | 6740.02 | Paid | 128060.32 | 2025-Q3
EXP-000624 | 2025-07-30 | BOQ-PKG-04-00624 | PKG-04 | INV-PKG-04-030-00624 | 376.83 | 31427.56 | 1571.38 | Under Review | 29856.18 | 2025-Q3
EXP-001710 | 2025-07-30 | BOQ-PKG-10-01710 | PKG-10 | INV-PKG-10-031-01710 | 10.63 | 24381.95 | 1219.1 | Paid | 23162.85 | 2025-Q3
EXP-003721 | 2025-07-30 | BOQ-PKG-01-01731 | PKG-01 | INV-PKG-01-012-03721 | 347.12 | 41695.73 | 2084.79 | Paid | 39610.94 | 2025-Q3
EXP-003975 | 2025-07-30 | BOQ-PKG-05-01985 | PKG-05 | INV-PKG-05-021-03975 | 66.83 | 115819.25 | 5790.96 | Paid | 110028.29 | 2025-Q3
EXP-006686 | 2025-07-30 | BOQ-PKG-06-00716 | PKG-06 | INV-PKG-06-002-06686 | 430.8 | 170306.93 | 8515.35 | Paid | 161791.58 | 2025-Q3
EXP-000413 | 2025-07-31 | BOQ-PKG-03-00413 | PKG-03 | INV-PKG-03-029-00413 | 61.56 | 101008.45 | 5050.42 | Paid | 95958.03 | 2025-Q3
EXP-000441 | 2025-07-31 | BOQ-PKG-01-00441 | PKG-01 | INV-PKG-01-022-00441 | 98.5 | 47339.39 | 2366.97 | Paid | 44972.42 | 2025-Q3
EXP-001643 | 2025-07-31 | BOQ-PKG-03-01643 | PKG-03 | INV-PKG-03-034-01643 | 108.86 | 201071.16 | 10053.56 | Paid | 191017.6 | 2025-Q3
EXP-002853 | 2025-07-31 | BOQ-PKG-03-00863 | PKG-03 | INV-PKG-03-019-02853 | 164.49 | 26917.72 | 1345.89 | Paid | 25571.83 | 2025-Q3
EXP-003190 | 2025-07-31 | BOQ-PKG-10-01200 | PKG-10 | INV-PKG-10-006-03190 | 429 | 75207.34 | 3760.37 | Under Review | 71446.97 | 2025-Q3
EXP-004033 | 2025-07-31 | BOQ-PKG-03-00053 | PKG-03 | INV-PKG-03-009-04033 | 411 | 106029.66 | 5301.48 | Paid | 100728.18 | 2025-Q3
EXP-004475 | 2025-07-31 | BOQ-PKG-05-00495 | PKG-05 | INV-PKG-05-031-04475 | 256.08 | 97856.78 | 4892.84 | Under Review | 92963.94 | 2025-Q3
EXP-004763 | 2025-07-31 | BOQ-PKG-03-00783 | PKG-03 | INV-PKG-03-004-04763 | 405.03 | 59007.92 | 2950.4 | Paid | 56057.52 | 2025-Q3
EXP-006738 | 2025-07-31 | BOQ-PKG-08-00768 | PKG-08 | INV-PKG-08-019-06738 | 50.35 | 36519.25 | 1825.96 | Paid | 34693.29 | 2025-Q3
EXP-000990 | 2025-08-01 | BOQ-PKG-10-00990 | PKG-10 | INV-PKG-10-011-00990 | 269.16 | 52982.74 | 2649.14 | Disputed | 50333.6 | 2025-Q3
EXP-000062 | 2025-08-02 | BOQ-PKG-02-00062 | PKG-02 | INV-PKG-02-028-00062 | 393 | 130073.56 | 6503.68 | Approved Pending Payment | 123569.88 | 2025-Q3
EXP-000372 | 2025-08-02 | BOQ-PKG-02-00372 | PKG-02 | INV-PKG-02-023-00372 | 399.53 | 101488.06 | 5074.4 | Paid | 96413.66 | 2025-Q3
EXP-002959 | 2025-08-02 | BOQ-PKG-09-00969 | PKG-09 | INV-PKG-09-020-02959 | 354.09 | 164725.2 | 8236.26 | Paid | 156488.94 | 2025-Q3
EXP-002963 | 2025-08-02 | BOQ-PKG-03-00973 | PKG-03 | INV-PKG-03-024-02963 | 350.87 | 167345.71 | 8367.29 | Paid | 158978.42 | 2025-Q3
EXP-003084 | 2025-08-02 | BOQ-PKG-04-01094 | PKG-04 | INV-PKG-04-005-03084 | 354.71 | 165566.68 | 8278.33 | Paid | 157288.35 | 2025-Q3
EXP-006616 | 2025-08-02 | BOQ-PKG-06-00646 | PKG-06 | INV-PKG-06-002-06616 | 400.05 | 121141.17 | 6057.06 | Paid | 115084.11 | 2025-Q3
EXP-006829 | 2025-08-02 | BOQ-PKG-09-00859 | PKG-09 | INV-PKG-09-005-06829 | 8.84 | 37497.55 | 1874.88 | Paid | 35622.67 | 2025-Q3
EXP-001656 | 2025-08-03 | BOQ-PKG-06-01656 | PKG-06 | INV-PKG-06-012-01656 | 144.97 | 129041.58 | 6452.08 | Approved Pending Payment | 122589.5 | 2025-Q3
EXP-001786 | 2025-08-03 | BOQ-PKG-06-01786 | PKG-06 | INV-PKG-06-002-01786 | 260.62 | 179698.81 | 8984.94 | Under Review | 170713.87 | 2025-Q3
EXP-003030 | 2025-08-03 | BOQ-PKG-10-01040 | PKG-10 | INV-PKG-10-021-03030 | 418.52 | 111130.05 | 5556.5 | Paid | 105573.55 | 2025-Q3
EXP-003624 | 2025-08-03 | BOQ-PKG-04-01634 | PKG-04 | INV-PKG-04-020-03624 | 268.22 | 140350.92 | 7017.55 | Paid | 133333.37 | 2025-Q3
EXP-004863 | 2025-08-03 | BOQ-PKG-03-00883 | PKG-03 | INV-PKG-03-034-04863 | 128.33 | 163683.71 | 8184.19 | Paid | 155499.52 | 2025-Q3
EXP-006422 | 2025-08-03 | BOQ-PKG-02-00452 | PKG-02 | INV-PKG-02-018-06422 | 99.06 | 25996.66 | 1299.83 | Disputed | 24696.83 | 2025-Q3
EXP-000326 | 2025-08-04 | BOQ-PKG-06-00326 | PKG-06 | INV-PKG-06-012-00326 | 392.01 | 189507.49 | 9475.37 | Paid | 180032.12 | 2025-Q3
EXP-003115 | 2025-08-04 | BOQ-PKG-05-01125 | PKG-05 | INV-PKG-05-001-03115 | 9.78 | 187390.55 | 9369.53 | Under Review | 178021.02 | 2025-Q3
EXP-003579 | 2025-08-04 | BOQ-PKG-09-01589 | PKG-09 | INV-PKG-09-010-03579 | 313.44 | 107889.83 | 5394.49 | Paid | 102495.34 | 2025-Q3
EXP-003841 | 2025-08-04 | BOQ-PKG-01-01851 | PKG-01 | INV-PKG-01-027-03841 | 190.05 | 52815.29 | 2640.76 | Paid | 50174.53 | 2025-Q3
EXP-004103 | 2025-08-04 | BOQ-PKG-03-00123 | PKG-03 | INV-PKG-03-009-04103 | 8.15 | 29473.05 | 1473.65 | Paid | 27999.4 | 2025-Q3
EXP-004580 | 2025-08-04 | BOQ-PKG-10-00600 | PKG-10 | INV-PKG-10-031-04580 | 291.21 | 138010.01 | 6900.5 | Paid | 131109.51 | 2025-Q3
EXP-006676 | 2025-08-04 | BOQ-PKG-06-00706 | PKG-06 | INV-PKG-06-027-06676 | 217.25 | 78875.65 | 3943.78 | Approved Pending Payment | 74931.87 | 2025-Q3
EXP-006880 | 2025-08-04 | BOQ-PKG-10-00910 | PKG-10 | INV-PKG-10-021-06880 | 273.88 | 36926 | 1846.3 | Paid | 35079.7 | 2025-Q3
EXP-003565 | 2025-08-05 | BOQ-PKG-05-01575 | PKG-05 | INV-PKG-05-031-03565 | 196.25 | 114179.89 | 5708.99 | Paid | 108470.9 | 2025-Q3
EXP-004561 | 2025-08-05 | BOQ-PKG-01-00581 | PKG-01 | INV-PKG-01-012-04561 | 238.37 | 152492.03 | 7624.6 | Paid | 144867.43 | 2025-Q3
EXP-004849 | 2025-08-05 | BOQ-PKG-09-00869 | PKG-09 | INV-PKG-09-020-04849 | 32.59 | 96867.09 | 4843.35 | Paid | 92023.74 | 2025-Q3
EXP-004878 | 2025-08-05 | BOQ-PKG-08-00898 | PKG-08 | INV-PKG-08-014-04878 | 230.99 | 109238.77 | 5461.94 | Paid | 103776.83 | 2025-Q3
EXP-000105 | 2025-08-06 | BOQ-PKG-05-00105 | PKG-05 | INV-PKG-05-001-00105 | 233.6 | 74739.67 | 3736.98 | Paid | 71002.69 | 2025-Q3
EXP-000754 | 2025-08-06 | BOQ-PKG-04-00754 | PKG-04 | INV-PKG-04-020-00754 | 81.22 | 159899.85 | 7994.99 | Paid | 151904.86 | 2025-Q3
EXP-000953 | 2025-08-06 | BOQ-PKG-03-00953 | PKG-03 | INV-PKG-03-009-00953 | 191.35 | 100914.5 | 5045.73 | Paid | 95868.77 | 2025-Q3
EXP-004995 | 2025-08-06 | BOQ-PKG-05-01015 | PKG-05 | INV-PKG-05-026-04995 | 315.5 | 112792.95 | 5639.65 | Paid | 107153.3 | 2025-Q3
EXP-006324 | 2025-08-06 | BOQ-PKG-04-00354 | PKG-04 | INV-PKG-04-025-06324 | 165.89 | 155828.03 | 7791.4 | Under Review | 148036.63 | 2025-Q3
EXP-006674 | 2025-08-06 | BOQ-PKG-04-00704 | PKG-04 | INV-PKG-04-025-06674 | 360.57 | 212059.77 | 10602.99 | Paid | 201456.78 | 2025-Q3
EXP-000481 | 2025-08-07 | BOQ-PKG-01-00481 | PKG-01 | INV-PKG-01-027-00481 | 240.87 | 28557.59 | 1427.88 | Paid | 27129.71 | 2025-Q3
EXP-000618 | 2025-08-07 | BOQ-PKG-08-00618 | PKG-08 | INV-PKG-08-024-00618 | 20.26 | 113680.46 | 5684.02 | Paid | 107996.44 | 2025-Q3
EXP-002744 | 2025-08-07 | BOQ-PKG-04-00754 | PKG-04 | INV-PKG-04-015-02744 | 60.54 | 174589.13 | 8729.46 | Under Review | 165859.67 | 2025-Q3
EXP-004464 | 2025-08-07 | BOQ-PKG-04-00484 | PKG-04 | INV-PKG-04-020-04464 | 260.63 | 39745.71 | 1987.29 | Paid | 37758.42 | 2025-Q3
EXP-004980 | 2025-08-07 | BOQ-PKG-10-01000 | PKG-10 | INV-PKG-10-011-04980 | 230.58 | 152710.6 | 7635.53 | Paid | 145075.07 | 2025-Q3
EXP-006329 | 2025-08-07 | BOQ-PKG-09-00359 | PKG-09 | INV-PKG-09-030-06329 | 412.62 | 114262.84 | 5713.14 | Paid | 108549.7 | 2025-Q3
EXP-006365 | 2025-08-07 | BOQ-PKG-05-00395 | PKG-05 | INV-PKG-05-031-06365 | 67.92 | 46291.43 | 2314.57 | Approved Pending Payment | 43976.86 | 2025-Q3
EXP-001633 | 2025-08-08 | BOQ-PKG-03-01633 | PKG-03 | INV-PKG-03-024-01633 | 432.58 | 145276.7 | 7263.84 | Paid | 138012.86 | 2025-Q3
EXP-001818 | 2025-08-08 | BOQ-PKG-08-01818 | PKG-08 | INV-PKG-08-034-01818 | 276.44 | 132761.69 | 6638.08 | Paid | 126123.61 | 2025-Q3
EXP-002718 | 2025-08-08 | BOQ-PKG-08-00728 | PKG-08 | INV-PKG-08-024-02718 | 299.36 | 196021.89 | 9801.09 | Approved Pending Payment | 186220.8 | 2025-Q3
EXP-003234 | 2025-08-08 | BOQ-PKG-04-01244 | PKG-04 | INV-PKG-04-015-03234 | 416.55 | 66573.23 | 3328.66 | Under Review | 63244.57 | 2025-Q3
EXP-003924 | 2025-08-08 | BOQ-PKG-04-01934 | PKG-04 | INV-PKG-04-005-03924 | 7.6 | 40824.64 | 2041.23 | Paid | 38783.41 | 2025-Q3
EXP-004877 | 2025-08-08 | BOQ-PKG-07-00897 | PKG-07 | INV-PKG-07-013-04877 | 288.84 | 197856.46 | 9892.82 | Paid | 187963.64 | 2025-Q3
EXP-005096 | 2025-08-08 | BOQ-PKG-06-01116 | PKG-06 | INV-PKG-06-022-05096 | 79.38 | 191750.48 | 9587.52 | Paid | 182162.96 | 2025-Q3
EXP-005499 | 2025-08-08 | BOQ-PKG-09-01519 | PKG-09 | INV-PKG-09-005-05499 | 305.33 | 119939.85 | 5996.99 | Paid | 113942.86 | 2025-Q3
EXP-006939 | 2025-08-08 | BOQ-PKG-09-00969 | PKG-09 | INV-PKG-09-010-06939 | 313.04 | 130158.9 | 6507.94 | Paid | 123650.96 | 2025-Q3
EXP-000214 | 2025-08-09 | BOQ-PKG-04-00214 | PKG-04 | INV-PKG-04-005-00214 | 222.95 | 121053.85 | 6052.69 | Paid | 115001.16 | 2025-Q3
EXP-001469 | 2025-08-09 | BOQ-PKG-09-01469 | PKG-09 | INV-PKG-09-035-01469 | 262.69 | 64849 | 3242.45 | Under Review | 61606.55 | 2025-Q3
EXP-003693 | 2025-08-09 | BOQ-PKG-03-01703 | PKG-03 | INV-PKG-03-019-03693 | 206.64 | 66717.67 | 3335.88 | Under Review | 63381.79 | 2025-Q3
EXP-003788 | 2025-08-09 | BOQ-PKG-08-01798 | PKG-08 | INV-PKG-08-009-03788 | 439.16 | 197906.5 | 9895.33 | Approved Pending Payment | 188011.17 | 2025-Q3
EXP-004615 | 2025-08-09 | BOQ-PKG-05-00635 | PKG-05 | INV-PKG-05-031-04615 | 28.28 | 94728.02 | 4736.4 | Approved Pending Payment | 89991.62 | 2025-Q3
EXP-000277 | 2025-08-10 | BOQ-PKG-07-00277 | PKG-07 | INV-PKG-07-033-00277 | 106.13 | 127385.49 | 6369.27 | Paid | 121016.22 | 2025-Q3
EXP-000503 | 2025-08-10 | BOQ-PKG-03-00503 | PKG-03 | INV-PKG-03-014-00503 | 138.02 | 98416.63 | 4920.83 | Disputed | 93495.8 | 2025-Q3
EXP-000753 | 2025-08-10 | BOQ-PKG-03-00753 | PKG-03 | INV-PKG-03-019-00753 | 77.95 | 158837.12 | 7941.86 | Paid | 150895.26 | 2025-Q3
EXP-001501 | 2025-08-10 | BOQ-PKG-01-01501 | PKG-01 | INV-PKG-01-032-01501 | 178.16 | 128826.26 | 6441.31 | Paid | 122384.95 | 2025-Q3
EXP-002884 | 2025-08-10 | BOQ-PKG-04-00894 | PKG-04 | INV-PKG-04-015-02884 | 172.08 | 92181.37 | 4609.07 | Paid | 87572.3 | 2025-Q3
EXP-003523 | 2025-08-10 | BOQ-PKG-03-01533 | PKG-03 | INV-PKG-03-024-03523 | 30.15 | 138272.5 | 6913.62 | Paid | 131358.88 | 2025-Q3
EXP-004319 | 2025-08-10 | BOQ-PKG-09-00339 | PKG-09 | INV-PKG-09-015-04319 | 295.87 | 62391.55 | 3119.58 | Paid | 59271.97 | 2025-Q3
EXP-005529 | 2025-08-10 | BOQ-PKG-09-01549 | PKG-09 | INV-PKG-09-035-05529 | 445.94 | 127563.61 | 6378.18 | Under Review | 121185.43 | 2025-Q3
EXP-005952 | 2025-08-10 | BOQ-PKG-02-01972 | PKG-02 | INV-PKG-02-003-05952 | 158.97 | 26408.62 | 1320.43 | Under Review | 25088.19 | 2025-Q3
EXP-006374 | 2025-08-10 | BOQ-PKG-04-00404 | PKG-04 | INV-PKG-04-005-06374 | 330.97 | 205104.01 | 10255.2 | Paid | 194848.81 | 2025-Q3
EXP-000076 | 2025-08-11 | BOQ-PKG-06-00076 | PKG-06 | INV-PKG-06-007-00076 | 103.12 | 141543.8 | 7077.19 | Paid | 134466.61 | 2025-Q3
EXP-000826 | 2025-08-11 | BOQ-PKG-06-00826 | PKG-06 | INV-PKG-06-022-00826 | 93.35 | 118536.06 | 5926.8 | Approved Pending Payment | 112609.26 | 2025-Q3
EXP-000930 | 2025-08-11 | BOQ-PKG-10-00930 | PKG-10 | INV-PKG-10-021-00930 | 128.28 | 181809.29 | 9090.46 | Paid | 172718.83 | 2025-Q3
EXP-001152 | 2025-08-11 | BOQ-PKG-02-01152 | PKG-02 | INV-PKG-02-033-01152 | 310.43 | 26961.3 | 1348.06 | Paid | 25613.24 | 2025-Q3
EXP-004654 | 2025-08-11 | BOQ-PKG-04-00674 | PKG-04 | INV-PKG-04-035-04654 | 449.74 | 49493.95 | 2474.7 | Approved Pending Payment | 47019.25 | 2025-Q3
EXP-004850 | 2025-08-11 | BOQ-PKG-10-00870 | PKG-10 | INV-PKG-10-021-04850 | 266.9 | 137910.98 | 6895.55 | Paid | 131015.43 | 2025-Q3
EXP-004931 | 2025-08-11 | BOQ-PKG-01-00951 | PKG-01 | INV-PKG-01-032-04931 | 197.8 | 92466.71 | 4623.34 | Paid | 87843.37 | 2025-Q3
EXP-005566 | 2025-08-11 | BOQ-PKG-06-01586 | PKG-06 | INV-PKG-06-002-05566 | 212.56 | 188619.94 | 9431 | Paid | 179188.94 | 2025-Q3
EXP-005793 | 2025-08-11 | BOQ-PKG-03-01813 | PKG-03 | INV-PKG-03-019-05793 | 276.21 | 174137.73 | 8706.89 | Paid | 165430.84 | 2025-Q3
EXP-000883 | 2025-08-12 | BOQ-PKG-03-00883 | PKG-03 | INV-PKG-03-009-00883 | 44.89 | 206468.61 | 10323.43 | Approved Pending Payment | 196145.18 | 2025-Q3
EXP-000944 | 2025-08-12 | BOQ-PKG-04-00944 | PKG-04 | INV-PKG-04-035-00944 | 433.48 | 133696.5 | 6684.83 | Paid | 127011.67 | 2025-Q3
EXP-002301 | 2025-08-12 | BOQ-PKG-01-00311 | PKG-01 | INV-PKG-01-027-02301 | 99.15 | 141008.12 | 7050.41 | Approved Pending Payment | 133957.71 | 2025-Q3
EXP-002654 | 2025-08-12 | BOQ-PKG-04-00664 | PKG-04 | INV-PKG-04-030-02654 | 9.35 | 173861.62 | 8693.08 | Disputed | 165168.54 | 2025-Q3
EXP-002928 | 2025-08-12 | BOQ-PKG-08-00938 | PKG-08 | INV-PKG-08-024-02928 | 225.06 | 192532.09 | 9626.6 | Paid | 182905.49 | 2025-Q3
EXP-006076 | 2025-08-12 | BOQ-PKG-06-00106 | PKG-06 | INV-PKG-06-022-06076 | 336.75 | 189077.97 | 9453.9 | Paid | 179624.07 | 2025-Q3
EXP-006440 | 2025-08-12 | BOQ-PKG-10-00470 | PKG-10 | INV-PKG-10-001-06440 | 114.76 | 142271.7 | 7113.59 | Paid | 135158.11 | 2025-Q3
EXP-000291 | 2025-08-13 | BOQ-PKG-01-00291 | PKG-01 | INV-PKG-01-012-00291 | 44.42 | 145185.55 | 7259.28 | Paid | 137926.27 | 2025-Q3
EXP-000454 | 2025-08-13 | BOQ-PKG-04-00454 | PKG-04 | INV-PKG-04-035-00454 | 79.22 | 175805.59 | 8790.28 | Paid | 167015.31 | 2025-Q3
EXP-002180 | 2025-08-13 | BOQ-PKG-10-00190 | PKG-10 | INV-PKG-10-011-02180 | 15.1 | 200655.97 | 10032.8 | Paid | 190623.17 | 2025-Q3
EXP-005340 | 2025-08-13 | BOQ-PKG-10-01360 | PKG-10 | INV-PKG-10-021-05340 | 443.4 | 119888.13 | 5994.41 | Paid | 113893.72 | 2025-Q3
EXP-005959 | 2025-08-13 | BOQ-PKG-09-01979 | PKG-09 | INV-PKG-09-010-05959 | 229.43 | 63310.39 | 3165.52 | Paid | 60144.87 | 2025-Q3
EXP-006906 | 2025-08-13 | BOQ-PKG-06-00936 | PKG-06 | INV-PKG-06-012-06906 | 275.66 | 202869.56 | 10143.48 | Paid | 192726.08 | 2025-Q3
EXP-000248 | 2025-08-14 | BOQ-PKG-08-00248 | PKG-08 | INV-PKG-08-004-00248 | 202.84 | 159088.32 | 7954.42 | Paid | 151133.9 | 2025-Q3
EXP-001443 | 2025-08-14 | BOQ-PKG-03-01443 | PKG-03 | INV-PKG-03-009-01443 | 73.29 | 63135.51 | 3156.78 | Paid | 59978.73 | 2025-Q3
EXP-002597 | 2025-08-14 | BOQ-PKG-07-00607 | PKG-07 | INV-PKG-07-008-02597 | 345.95 | 164146.48 | 8207.32 | Approved Pending Payment | 155939.16 | 2025-Q3
EXP-002929 | 2025-08-14 | BOQ-PKG-09-00939 | PKG-09 | INV-PKG-09-025-02929 | 282.69 | 105810.86 | 5290.54 | Under Review | 100520.32 | 2025-Q3
EXP-003269 | 2025-08-14 | BOQ-PKG-09-01279 | PKG-09 | INV-PKG-09-015-03269 | 227.85 | 98278.69 | 4913.93 | Paid | 93364.76 | 2025-Q3
EXP-004492 | 2025-08-14 | BOQ-PKG-02-00512 | PKG-02 | INV-PKG-02-013-04492 | 367.68 | 122263.85 | 6113.19 | Paid | 116150.66 | 2025-Q3
EXP-005012 | 2025-08-14 | BOQ-PKG-02-01032 | PKG-02 | INV-PKG-02-008-05012 | 248.06 | 60705.75 | 3035.29 | Paid | 57670.46 | 2025-Q3
EXP-005202 | 2025-08-14 | BOQ-PKG-02-01222 | PKG-02 | INV-PKG-02-023-05202 | 284.75 | 40738.36 | 2036.92 | Paid | 38701.44 | 2025-Q3
EXP-005802 | 2025-08-14 | BOQ-PKG-02-01822 | PKG-02 | INV-PKG-02-028-05802 | 265.1 | 119047.98 | 5952.4 | Paid | 113095.58 | 2025-Q3
EXP-006275 | 2025-08-14 | BOQ-PKG-05-00305 | PKG-05 | INV-PKG-05-011-06275 | 91.49 | 156996.33 | 7849.82 | Approved Pending Payment | 149146.51 | 2025-Q3
EXP-001536 | 2025-08-15 | BOQ-PKG-06-01536 | PKG-06 | INV-PKG-06-032-01536 | 427.88 | 208304.65 | 10415.23 | Paid | 197889.42 | 2025-Q3
EXP-002403 | 2025-08-15 | BOQ-PKG-03-00413 | PKG-03 | INV-PKG-03-024-02403 | 180.1 | 205227.92 | 10261.4 | Under Review | 194966.52 | 2025-Q3
EXP-002664 | 2025-08-15 | BOQ-PKG-04-00674 | PKG-04 | INV-PKG-04-005-02664 | 394.4 | 177995.23 | 8899.76 | Approved Pending Payment | 169095.47 | 2025-Q3
EXP-002698 | 2025-08-15 | BOQ-PKG-08-00708 | PKG-08 | INV-PKG-08-004-02698 | 192.73 | 28554.79 | 1427.74 | Paid | 27127.05 | 2025-Q3
EXP-003320 | 2025-08-15 | BOQ-PKG-10-01330 | PKG-10 | INV-PKG-10-031-03320 | 353.4 | 149525.91 | 7476.3 | Paid | 142049.61 | 2025-Q3
EXP-004381 | 2025-08-15 | BOQ-PKG-01-00401 | PKG-01 | INV-PKG-01-007-04381 | 328.3 | 142499.2 | 7124.96 | Paid | 135374.24 | 2025-Q3
EXP-005256 | 2025-08-15 | BOQ-PKG-06-01276 | PKG-06 | INV-PKG-06-007-05256 | 260.41 | 105921.71 | 5296.09 | Under Review | 100625.62 | 2025-Q3
EXP-006205 | 2025-08-15 | BOQ-PKG-05-00235 | PKG-05 | INV-PKG-05-011-06205 | 22.31 | 133810.56 | 6690.53 | Paid | 127120.03 | 2025-Q3
EXP-006710 | 2025-08-15 | BOQ-PKG-10-00740 | PKG-10 | INV-PKG-10-026-06710 | 27.85 | 122218.75 | 6110.94 | Paid | 116107.81 | 2025-Q3
EXP-000104 | 2025-08-16 | BOQ-PKG-04-00104 | PKG-04 | INV-PKG-04-035-00104 | 222.24 | 47891.89 | 2394.59 | Paid | 45497.3 | 2025-Q3
EXP-000230 | 2025-08-16 | BOQ-PKG-10-00230 | PKG-10 | INV-PKG-10-021-00230 | 248.15 | 69701.56 | 3485.08 | Approved Pending Payment | 66216.48 | 2025-Q3
EXP-000955 | 2025-08-16 | BOQ-PKG-05-00955 | PKG-05 | INV-PKG-05-011-00955 | 92.43 | 69070.27 | 3453.51 | Under Review | 65616.76 | 2025-Q3
EXP-003292 | 2025-08-16 | BOQ-PKG-02-01302 | PKG-02 | INV-PKG-02-003-03292 | 136.96 | 174936.54 | 8746.83 | Paid | 166189.71 | 2025-Q3
EXP-003520 | 2025-08-16 | BOQ-PKG-10-01530 | PKG-10 | INV-PKG-10-021-03520 | 214.33 | 104819.01 | 5240.95 | Paid | 99578.06 | 2025-Q3
EXP-004154 | 2025-08-16 | BOQ-PKG-04-00174 | PKG-04 | INV-PKG-04-025-04154 | 23.17 | 168216.18 | 8410.81 | Disputed | 159805.37 | 2025-Q3
EXP-005062 | 2025-08-16 | BOQ-PKG-02-01082 | PKG-02 | INV-PKG-02-023-05062 | 368.59 | 91936.96 | 4596.85 | Paid | 87340.11 | 2025-Q3
EXP-002583 | 2025-08-17 | BOQ-PKG-03-00593 | PKG-03 | INV-PKG-03-029-02583 | 237.66 | 26030.81 | 1301.54 | Paid | 24729.27 | 2025-Q3
EXP-004046 | 2025-08-17 | BOQ-PKG-06-00066 | PKG-06 | INV-PKG-06-022-04046 | 52.5 | 124279.66 | 6213.98 | Paid | 118065.68 | 2025-Q3
EXP-000648 | 2025-08-18 | BOQ-PKG-08-00648 | PKG-08 | INV-PKG-08-019-00648 | 256.76 | 162777.17 | 8138.86 | Under Review | 154638.31 | 2025-Q3
EXP-001222 | 2025-08-18 | BOQ-PKG-02-01222 | PKG-02 | INV-PKG-02-033-01222 | 323.7 | 103800.4 | 5190.02 | Paid | 98610.38 | 2025-Q3
EXP-004411 | 2025-08-18 | BOQ-PKG-01-00431 | PKG-01 | INV-PKG-01-002-04411 | 394.88 | 118412.08 | 5920.6 | Paid | 112491.48 | 2025-Q3
EXP-005430 | 2025-08-18 | BOQ-PKG-10-01450 | PKG-10 | INV-PKG-10-006-05430 | 310.96 | 30584.44 | 1529.22 | Under Review | 29055.22 | 2025-Q3
EXP-000710 | 2025-08-19 | BOQ-PKG-10-00710 | PKG-10 | INV-PKG-10-011-00710 | 265.49 | 127572.79 | 6378.64 | Paid | 121194.15 | 2025-Q3
EXP-001631 | 2025-08-19 | BOQ-PKG-01-01631 | PKG-01 | INV-PKG-01-022-01631 | 126.28 | 72855.03 | 3642.75 | Paid | 69212.28 | 2025-Q3
EXP-001671 | 2025-08-19 | BOQ-PKG-01-01671 | PKG-01 | INV-PKG-01-027-01671 | 443.61 | 195440 | 9772 | Paid | 185668 | 2025-Q3
EXP-001934 | 2025-08-19 | BOQ-PKG-04-01934 | PKG-04 | INV-PKG-04-010-01934 | 325.04 | 144179.56 | 7208.98 | Paid | 136970.58 | 2025-Q3
EXP-002149 | 2025-08-19 | BOQ-PKG-09-00159 | PKG-09 | INV-PKG-09-015-02149 | 47.58 | 88382.46 | 4419.12 | Under Review | 83963.34 | 2025-Q3
EXP-002873 | 2025-08-19 | BOQ-PKG-03-00883 | PKG-03 | INV-PKG-03-004-02873 | 213.34 | 178870.65 | 8943.53 | Paid | 169927.12 | 2025-Q3
EXP-003237 | 2025-08-19 | BOQ-PKG-07-01247 | PKG-07 | INV-PKG-07-018-03237 | 425.85 | 153242.39 | 7662.12 | Paid | 145580.27 | 2025-Q3
EXP-004646 | 2025-08-19 | BOQ-PKG-06-00666 | PKG-06 | INV-PKG-06-027-04646 | 414.35 | 44984.67 | 2249.23 | Approved Pending Payment | 42735.44 | 2025-Q3
EXP-006970 | 2025-08-19 | BOQ-PKG-10-01000 | PKG-10 | INV-PKG-10-006-06970 | 242.56 | 137885.15 | 6894.26 | Paid | 130990.89 | 2025-Q3
EXP-000757 | 2025-08-20 | BOQ-PKG-07-00757 | PKG-07 | INV-PKG-07-023-00757 | 44.03 | 98663.87 | 4933.19 | Paid | 93730.68 | 2025-Q3
EXP-000774 | 2025-08-20 | BOQ-PKG-04-00774 | PKG-04 | INV-PKG-04-005-00774 | 375.31 | 112703.69 | 5635.18 | Paid | 107068.51 | 2025-Q3
EXP-001638 | 2025-08-20 | BOQ-PKG-08-01638 | PKG-08 | INV-PKG-08-029-01638 | 388.08 | 165260.23 | 8263.01 | Paid | 156997.22 | 2025-Q3
EXP-001667 | 2025-08-20 | BOQ-PKG-07-01667 | PKG-07 | INV-PKG-07-023-01667 | 307.46 | 88209.6 | 4410.48 | Paid | 83799.12 | 2025-Q3
EXP-003388 | 2025-08-20 | BOQ-PKG-08-01398 | PKG-08 | INV-PKG-08-029-03388 | 311.91 | 159039.91 | 7952 | Paid | 151087.91 | 2025-Q3
EXP-004025 | 2025-08-20 | BOQ-PKG-05-00045 | PKG-05 | INV-PKG-05-001-04025 | 281.48 | 32902.55 | 1645.13 | Paid | 31257.42 | 2025-Q3
EXP-005879 | 2025-08-20 | BOQ-PKG-09-01899 | PKG-09 | INV-PKG-09-035-05879 | 365.58 | 161257.43 | 8062.87 | Paid | 153194.56 | 2025-Q3
EXP-001651 | 2025-08-21 | BOQ-PKG-01-01651 | PKG-01 | INV-PKG-01-007-01651 | 439.85 | 43712.86 | 2185.64 | Paid | 41527.22 | 2025-Q3
EXP-001744 | 2025-08-21 | BOQ-PKG-04-01744 | PKG-04 | INV-PKG-04-030-01744 | 72.1 | 186166.25 | 9308.31 | Paid | 176857.94 | 2025-Q3
EXP-002291 | 2025-08-21 | BOQ-PKG-01-00301 | PKG-01 | INV-PKG-01-017-02291 | 440.7 | 137503.66 | 6875.18 | Paid | 130628.48 | 2025-Q3
EXP-003256 | 2025-08-21 | BOQ-PKG-06-01266 | PKG-06 | INV-PKG-06-002-03256 | 36.28 | 202138.36 | 10106.92 | Paid | 192031.44 | 2025-Q3
EXP-003821 | 2025-08-21 | BOQ-PKG-01-01831 | PKG-01 | INV-PKG-01-007-03821 | 356.2 | 199201.49 | 9960.07 | Paid | 189241.42 | 2025-Q3
EXP-004091 | 2025-08-21 | BOQ-PKG-01-00111 | PKG-01 | INV-PKG-01-032-04091 | 204.16 | 53694.06 | 2684.7 | Paid | 51009.36 | 2025-Q3
EXP-005161 | 2025-08-21 | BOQ-PKG-01-01181 | PKG-01 | INV-PKG-01-017-05161 | 435.39 | 47174.3 | 2358.72 | Paid | 44815.58 | 2025-Q3
EXP-000237 | 2025-08-22 | BOQ-PKG-07-00237 | PKG-07 | INV-PKG-07-028-00237 | 22.95 | 84628.62 | 4231.43 | Paid | 80397.19 | 2025-Q3
EXP-002339 | 2025-08-22 | BOQ-PKG-09-00349 | PKG-09 | INV-PKG-09-030-02339 | 309.84 | 62385.63 | 3119.28 | Under Review | 59266.35 | 2025-Q3
EXP-004547 | 2025-08-22 | BOQ-PKG-07-00567 | PKG-07 | INV-PKG-07-033-04547 | 422.08 | 120342.55 | 6017.13 | Paid | 114325.42 | 2025-Q3
EXP-006798 | 2025-08-22 | BOQ-PKG-08-00828 | PKG-08 | INV-PKG-08-009-06798 | 224.09 | 199962.04 | 9998.1 | Under Review | 189963.94 | 2025-Q3
EXP-001647 | 2025-08-23 | BOQ-PKG-07-01647 | PKG-07 | INV-PKG-07-003-01647 | 231.51 | 216994.89 | 10849.74 | Paid | 206145.15 | 2025-Q3
EXP-003518 | 2025-08-23 | BOQ-PKG-08-01528 | PKG-08 | INV-PKG-08-019-03518 | 275.33 | 63648.93 | 3182.45 | Under Review | 60466.48 | 2025-Q3
EXP-005922 | 2025-08-23 | BOQ-PKG-02-01942 | PKG-02 | INV-PKG-02-008-05922 | 136.44 | 202196.21 | 10109.81 | Paid | 192086.4 | 2025-Q3
EXP-006253 | 2025-08-23 | BOQ-PKG-03-00283 | PKG-03 | INV-PKG-03-024-06253 | 83.58 | 176645.91 | 8832.3 | Paid | 167813.61 | 2025-Q3
EXP-006510 | 2025-08-23 | BOQ-PKG-10-00540 | PKG-10 | INV-PKG-10-001-06510 | 64.15 | 38368.43 | 1918.42 | Paid | 36450.01 | 2025-Q3
EXP-000469 | 2025-08-24 | BOQ-PKG-09-00469 | PKG-09 | INV-PKG-09-015-00469 | 231.73 | 124450.19 | 6222.51 | Paid | 118227.68 | 2025-Q3
EXP-002970 | 2025-08-24 | BOQ-PKG-10-00980 | PKG-10 | INV-PKG-10-031-02970 | 318.98 | 183975.03 | 9198.75 | Paid | 174776.28 | 2025-Q3
EXP-003032 | 2025-08-24 | BOQ-PKG-02-01042 | PKG-02 | INV-PKG-02-023-03032 | 127.71 | 34534.61 | 1726.73 | Under Review | 32807.88 | 2025-Q3
EXP-003842 | 2025-08-24 | BOQ-PKG-02-01852 | PKG-02 | INV-PKG-02-028-03842 | 382.64 | 26882.51 | 1344.13 | Paid | 25538.38 | 2025-Q3
EXP-003981 | 2025-08-24 | BOQ-PKG-01-00001 | PKG-01 | INV-PKG-01-027-03981 | 308.93 | 98504.64 | 4925.23 | Paid | 93579.41 | 2025-Q3
EXP-005910 | 2025-08-24 | BOQ-PKG-10-01930 | PKG-10 | INV-PKG-10-031-05910 | 257.38 | 170512.92 | 8525.65 | Paid | 161987.27 | 2025-Q3
EXP-001214 | 2025-08-25 | BOQ-PKG-04-01214 | PKG-04 | INV-PKG-04-025-01214 | 108.3 | 24599.28 | 1229.96 | Disputed | 23369.32 | 2025-Q3
EXP-005679 | 2025-08-25 | BOQ-PKG-09-01699 | PKG-09 | INV-PKG-09-010-05679 | 270.78 | 210365.36 | 10518.27 | Under Review | 199847.09 | 2025-Q3
EXP-002967 | 2025-08-26 | BOQ-PKG-07-00977 | PKG-07 | INV-PKG-07-028-02967 | 432.07 | 68646.92 | 3432.35 | Paid | 65214.57 | 2025-Q3
EXP-003335 | 2025-08-26 | BOQ-PKG-05-01345 | PKG-05 | INV-PKG-05-011-03335 | 292.02 | 91695.11 | 4584.76 | Approved Pending Payment | 87110.35 | 2025-Q3
EXP-003706 | 2025-08-26 | BOQ-PKG-06-01716 | PKG-06 | INV-PKG-06-032-03706 | 301.35 | 165693.11 | 8284.66 | Paid | 157408.45 | 2025-Q3
EXP-003869 | 2025-08-26 | BOQ-PKG-09-01879 | PKG-09 | INV-PKG-09-020-03869 | 187.52 | 51847.23 | 2592.36 | Paid | 49254.87 | 2025-Q3
EXP-003997 | 2025-08-26 | BOQ-PKG-07-00017 | PKG-07 | INV-PKG-07-008-03997 | 111.62 | 102659.98 | 5133 | Under Review | 97526.98 | 2025-Q3
EXP-004826 | 2025-08-26 | BOQ-PKG-06-00846 | PKG-06 | INV-PKG-06-032-04826 | 199.24 | 97662.52 | 4883.13 | Paid | 92779.39 | 2025-Q3
EXP-001878 | 2025-08-27 | BOQ-PKG-08-01878 | PKG-08 | INV-PKG-08-024-01878 | 78.1 | 186343.73 | 9317.19 | Paid | 177026.54 | 2025-Q3
EXP-002580 | 2025-08-27 | BOQ-PKG-10-00590 | PKG-10 | INV-PKG-10-026-02580 | 45.66 | 102475.45 | 5123.77 | Paid | 97351.68 | 2025-Q3
EXP-002591 | 2025-08-27 | BOQ-PKG-01-00601 | PKG-01 | INV-PKG-01-002-02591 | 145.15 | 52559.63 | 2627.98 | Paid | 49931.65 | 2025-Q3
EXP-002804 | 2025-08-27 | BOQ-PKG-04-00814 | PKG-04 | INV-PKG-04-005-02804 | 343.44 | 161831.36 | 8091.57 | Approved Pending Payment | 153739.79 | 2025-Q3
EXP-006888 | 2025-08-27 | BOQ-PKG-08-00918 | PKG-08 | INV-PKG-08-029-06888 | 295.38 | 53169.55 | 2658.48 | Disputed | 50511.07 | 2025-Q3
EXP-000386 | 2025-08-28 | BOQ-PKG-06-00386 | PKG-06 | INV-PKG-06-002-00386 | 203.86 | 165492.41 | 8274.62 | Paid | 157217.79 | 2025-Q3
EXP-000396 | 2025-08-28 | BOQ-PKG-06-00396 | PKG-06 | INV-PKG-06-012-00396 | 142.47 | 94743.4 | 4737.17 | Approved Pending Payment | 90006.23 | 2025-Q3
EXP-000411 | 2025-08-28 | BOQ-PKG-01-00411 | PKG-01 | INV-PKG-01-027-00411 | 163.45 | 167665.62 | 8383.28 | Paid | 159282.34 | 2025-Q3
EXP-001393 | 2025-08-28 | BOQ-PKG-03-01393 | PKG-03 | INV-PKG-03-029-01393 | 299.45 | 80856.63 | 4042.83 | Paid | 76813.8 | 2025-Q3
EXP-002285 | 2025-08-28 | BOQ-PKG-05-00295 | PKG-05 | INV-PKG-05-011-02285 | 73.04 | 177341.28 | 8867.06 | Under Review | 168474.22 | 2025-Q3
EXP-002826 | 2025-08-28 | BOQ-PKG-06-00836 | PKG-06 | INV-PKG-06-027-02826 | 54.77 | 81908.67 | 4095.43 | Paid | 77813.24 | 2025-Q3
EXP-003296 | 2025-08-28 | BOQ-PKG-06-01306 | PKG-06 | INV-PKG-06-007-03296 | 70.47 | 124340.73 | 6217.04 | Paid | 118123.69 | 2025-Q3
EXP-004187 | 2025-08-28 | BOQ-PKG-07-00207 | PKG-07 | INV-PKG-07-023-04187 | 56.36 | 46095.99 | 2304.8 | Paid | 43791.19 | 2025-Q3
EXP-005670 | 2025-08-28 | BOQ-PKG-10-01690 | PKG-10 | INV-PKG-10-001-05670 | 274.37 | 39550.89 | 1977.54 | Paid | 37573.35 | 2025-Q3
EXP-001102 | 2025-08-29 | BOQ-PKG-02-01102 | PKG-02 | INV-PKG-02-018-01102 | 7.51 | 56883.96 | 2844.2 | Paid | 54039.76 | 2025-Q3
EXP-001613 | 2025-08-29 | BOQ-PKG-03-01613 | PKG-03 | INV-PKG-03-004-01613 | 164.18 | 180934.29 | 9046.71 | Approved Pending Payment | 171887.58 | 2025-Q3
EXP-002936 | 2025-08-29 | BOQ-PKG-06-00946 | PKG-06 | INV-PKG-06-032-02936 | 378.43 | 166964.48 | 8348.22 | Disputed | 158616.26 | 2025-Q3
EXP-003622 | 2025-08-29 | BOQ-PKG-02-01632 | PKG-02 | INV-PKG-02-018-03622 | 203.87 | 193815.2 | 9690.76 | Paid | 184124.44 | 2025-Q3
EXP-004419 | 2025-08-29 | BOQ-PKG-09-00439 | PKG-09 | INV-PKG-09-010-04419 | 439.95 | 42471.81 | 2123.59 | Disputed | 40348.22 | 2025-Q3
EXP-004759 | 2025-08-29 | BOQ-PKG-09-00779 | PKG-09 | INV-PKG-09-035-04759 | 234 | 107817.34 | 5390.87 | Paid | 102426.47 | 2025-Q3
EXP-004870 | 2025-08-29 | BOQ-PKG-10-00890 | PKG-10 | INV-PKG-10-006-04870 | 426.17 | 42787.26 | 2139.36 | Paid | 40647.9 | 2025-Q3
EXP-005267 | 2025-08-29 | BOQ-PKG-07-01287 | PKG-07 | INV-PKG-07-018-05267 | 361.84 | 37278.11 | 1863.91 | Paid | 35414.2 | 2025-Q3
EXP-005293 | 2025-08-29 | BOQ-PKG-03-01313 | PKG-03 | INV-PKG-03-009-05293 | 344.61 | 25526.87 | 1276.34 | Paid | 24250.53 | 2025-Q3
EXP-005641 | 2025-08-29 | BOQ-PKG-01-01661 | PKG-01 | INV-PKG-01-007-05641 | 360.82 | 140344.89 | 7017.24 | Paid | 133327.65 | 2025-Q3
EXP-006187 | 2025-08-29 | BOQ-PKG-07-00217 | PKG-07 | INV-PKG-07-028-06187 | 213.49 | 143293.42 | 7164.67 | Paid | 136128.75 | 2025-Q3
EXP-000758 | 2025-08-30 | BOQ-PKG-08-00758 | PKG-08 | INV-PKG-08-024-00758 | 130.73 | 91579.85 | 4578.99 | Paid | 87000.86 | 2025-Q3
EXP-001608 | 2025-08-30 | BOQ-PKG-08-01608 | PKG-08 | INV-PKG-08-034-01608 | 37.34 | 175569.08 | 8778.45 | Paid | 166790.63 | 2025-Q3
EXP-001972 | 2025-08-30 | BOQ-PKG-02-01972 | PKG-02 | INV-PKG-02-013-01972 | 433.52 | 178683.89 | 8934.19 | Approved Pending Payment | 169749.7 | 2025-Q3
EXP-004496 | 2025-08-30 | BOQ-PKG-06-00516 | PKG-06 | INV-PKG-06-017-04496 | 44.04 | 84795.45 | 4239.77 | Paid | 80555.68 | 2025-Q3
EXP-004933 | 2025-08-30 | BOQ-PKG-03-00953 | PKG-03 | INV-PKG-03-034-04933 | 391.34 | 178764.66 | 8938.23 | Approved Pending Payment | 169826.43 | 2025-Q3
EXP-005762 | 2025-08-30 | BOQ-PKG-02-01782 | PKG-02 | INV-PKG-02-023-05762 | 233.98 | 80873.01 | 4043.65 | Under Review | 76829.36 | 2025-Q3
EXP-005995 | 2025-08-30 | BOQ-PKG-05-00025 | PKG-05 | INV-PKG-05-011-05995 | 177.02 | 162923.44 | 8146.17 | Paid | 154777.27 | 2025-Q3
EXP-006072 | 2025-08-30 | BOQ-PKG-02-00102 | PKG-02 | INV-PKG-02-018-06072 | 80.74 | 186467.95 | 9323.4 | Under Review | 177144.55 | 2025-Q3
EXP-000177 | 2025-08-31 | BOQ-PKG-07-00177 | PKG-07 | INV-PKG-07-003-00177 | 364.68 | 36350.98 | 1817.55 | Paid | 34533.43 | 2025-Q3
EXP-001820 | 2025-08-31 | BOQ-PKG-10-01820 | PKG-10 | INV-PKG-10-001-01820 | 368.55 | 149845.59 | 7492.28 | Under Review | 142353.31 | 2025-Q3
EXP-005501 | 2025-08-31 | BOQ-PKG-01-01521 | PKG-01 | INV-PKG-01-007-05501 | 427.33 | 161621.35 | 8081.07 | Paid | 153540.28 | 2025-Q3
EXP-000986 | 2025-09-01 | BOQ-PKG-06-00986 | PKG-06 | INV-PKG-06-007-00986 | 288.91 | 141922.42 | 7096.12 | Disputed | 134826.3 | 2025-Q3
EXP-004635 | 2025-09-01 | BOQ-PKG-05-00655 | PKG-05 | INV-PKG-05-016-04635 | 36.08 | 49124.17 | 2456.21 | Paid | 46667.96 | 2025-Q3
EXP-005408 | 2025-09-01 | BOQ-PKG-08-01428 | PKG-08 | INV-PKG-08-019-05408 | 63.62 | 103146.45 | 5157.32 | Approved Pending Payment | 97989.13 | 2025-Q3
EXP-005917 | 2025-09-01 | BOQ-PKG-07-01937 | PKG-07 | INV-PKG-07-003-05917 | 400.31 | 143785.85 | 7189.29 | Paid | 136596.56 | 2025-Q3
EXP-006087 | 2025-09-01 | BOQ-PKG-07-00117 | PKG-07 | INV-PKG-07-033-06087 | 259.43 | 54146.01 | 2707.3 | Paid | 51438.71 | 2025-Q3
EXP-000450 | 2025-09-02 | BOQ-PKG-10-00450 | PKG-10 | INV-PKG-10-031-00450 | 59.01 | 212597.24 | 10629.86 | Paid | 201967.38 | 2025-Q3
EXP-001508 | 2025-09-02 | BOQ-PKG-08-01508 | PKG-08 | INV-PKG-08-004-01508 | 172.16 | 51099.44 | 2554.97 | Approved Pending Payment | 48544.47 | 2025-Q3
EXP-002088 | 2025-09-02 | BOQ-PKG-08-00098 | PKG-08 | INV-PKG-08-024-02088 | 331.68 | 145003.16 | 7250.16 | Paid | 137753 | 2025-Q3
EXP-002876 | 2025-09-02 | BOQ-PKG-06-00886 | PKG-06 | INV-PKG-06-007-02876 | 69.36 | 114838.96 | 5741.95 | Paid | 109097.01 | 2025-Q3
EXP-004409 | 2025-09-02 | BOQ-PKG-09-00429 | PKG-09 | INV-PKG-09-035-04409 | 268.53 | 28041.26 | 1402.06 | Paid | 26639.2 | 2025-Q3
EXP-004801 | 2025-09-02 | BOQ-PKG-01-00821 | PKG-01 | INV-PKG-01-007-04801 | 174.4 | 169150.74 | 8457.54 | Paid | 160693.2 | 2025-Q3
EXP-005708 | 2025-09-02 | BOQ-PKG-08-01728 | PKG-08 | INV-PKG-08-004-05708 | 294.81 | 173747.32 | 8687.37 | Paid | 165059.95 | 2025-Q3
EXP-005807 | 2025-09-02 | BOQ-PKG-07-01827 | PKG-07 | INV-PKG-07-033-05807 | 412.63 | 109508.69 | 5475.43 | Paid | 104033.26 | 2025-Q3
EXP-006797 | 2025-09-02 | BOQ-PKG-07-00827 | PKG-07 | INV-PKG-07-008-06797 | 51.6 | 195854.08 | 9792.7 | Paid | 186061.38 | 2025-Q3
EXP-000482 | 2025-09-03 | BOQ-PKG-02-00482 | PKG-02 | INV-PKG-02-028-00482 | 252.98 | 159792.02 | 7989.6 | Paid | 151802.42 | 2025-Q3
EXP-002467 | 2025-09-03 | BOQ-PKG-07-00477 | PKG-07 | INV-PKG-07-018-02467 | 411.97 | 30077.37 | 1503.87 | Paid | 28573.5 | 2025-Q3
EXP-003138 | 2025-09-03 | BOQ-PKG-08-01148 | PKG-08 | INV-PKG-08-024-03138 | 217.02 | 46035.15 | 2301.76 | Approved Pending Payment | 43733.39 | 2025-Q3
EXP-003391 | 2025-09-03 | BOQ-PKG-01-01401 | PKG-01 | INV-PKG-01-032-03391 | 264.97 | 144702.63 | 7235.13 | Paid | 137467.5 | 2025-Q3
EXP-004956 | 2025-09-03 | BOQ-PKG-06-00976 | PKG-06 | INV-PKG-06-022-04956 | 113.69 | 116030.97 | 5801.55 | Paid | 110229.42 | 2025-Q3
EXP-005913 | 2025-09-03 | BOQ-PKG-03-01933 | PKG-03 | INV-PKG-03-034-05913 | 90.76 | 36729.7 | 1836.48 | Paid | 34893.22 | 2025-Q3
EXP-001243 | 2025-09-04 | BOQ-PKG-03-01243 | PKG-03 | INV-PKG-03-019-01243 | 139.05 | 28239.14 | 1411.96 | Paid | 26827.18 | 2025-Q3
EXP-001319 | 2025-09-04 | BOQ-PKG-09-01319 | PKG-09 | INV-PKG-09-025-01319 | 381.21 | 78447.97 | 3922.4 | Under Review | 74525.57 | 2025-Q3
EXP-003017 | 2025-09-04 | BOQ-PKG-07-01027 | PKG-07 | INV-PKG-07-008-03017 | 380.22 | 190874.17 | 9543.71 | Paid | 181330.46 | 2025-Q3
EXP-003635 | 2025-09-04 | BOQ-PKG-05-01645 | PKG-05 | INV-PKG-05-031-03635 | 323.86 | 197958.26 | 9897.91 | Disputed | 188060.35 | 2025-Q3
EXP-004161 | 2025-09-04 | BOQ-PKG-01-00181 | PKG-01 | INV-PKG-01-032-04161 | 270.53 | 144766.85 | 7238.34 | Paid | 137528.51 | 2025-Q3
EXP-006321 | 2025-09-04 | BOQ-PKG-01-00351 | PKG-01 | INV-PKG-01-022-06321 | 91.26 | 74508 | 3725.4 | Approved Pending Payment | 70782.6 | 2025-Q3
EXP-000025 | 2025-09-05 | BOQ-PKG-05-00025 | PKG-05 | INV-PKG-05-026-00025 | 194.75 | 123064.79 | 6153.24 | Paid | 116911.55 | 2025-Q3
EXP-000228 | 2025-09-05 | BOQ-PKG-08-00228 | PKG-08 | INV-PKG-08-019-00228 | 207.76 | 116236.69 | 5811.83 | Paid | 110424.86 | 2025-Q3
EXP-000385 | 2025-09-05 | BOQ-PKG-05-00385 | PKG-05 | INV-PKG-05-001-00385 | 246.61 | 47626.67 | 2381.33 | Paid | 45245.34 | 2025-Q3
EXP-001358 | 2025-09-05 | BOQ-PKG-08-01358 | PKG-08 | INV-PKG-08-029-01358 | 266.46 | 89825.85 | 4491.29 | Paid | 85334.56 | 2025-Q3
EXP-004227 | 2025-09-05 | BOQ-PKG-07-00247 | PKG-07 | INV-PKG-07-028-04227 | 216.33 | 89611.09 | 4480.55 | Paid | 85130.54 | 2025-Q3
EXP-005908 | 2025-09-05 | BOQ-PKG-08-01928 | PKG-08 | INV-PKG-08-029-05908 | 402.33 | 85100.62 | 4255.03 | Under Review | 80845.59 | 2025-Q3
EXP-006031 | 2025-09-05 | BOQ-PKG-01-00061 | PKG-01 | INV-PKG-01-012-06031 | 186.23 | 43529.24 | 2176.46 | Paid | 41352.78 | 2025-Q3
EXP-000042 | 2025-09-06 | BOQ-PKG-02-00042 | PKG-02 | INV-PKG-02-008-00042 | 62.11 | 133948.39 | 6697.42 | Paid | 127250.97 | 2025-Q3
EXP-000817 | 2025-09-06 | BOQ-PKG-07-00817 | PKG-07 | INV-PKG-07-013-00817 | 119.42 | 195862.08 | 9793.1 | Disputed | 186068.98 | 2025-Q3
EXP-002020 | 2025-09-06 | BOQ-PKG-10-00030 | PKG-10 | INV-PKG-10-026-02020 | 268.86 | 45847.29 | 2292.36 | Paid | 43554.93 | 2025-Q3
EXP-002510 | 2025-09-06 | BOQ-PKG-10-00520 | PKG-10 | INV-PKG-10-026-02510 | 200.41 | 146310.29 | 7315.51 | Disputed | 138994.78 | 2025-Q3
EXP-004414 | 2025-09-06 | BOQ-PKG-04-00434 | PKG-04 | INV-PKG-04-005-04414 | 243.66 | 123961.95 | 6198.1 | Paid | 117763.85 | 2025-Q3
EXP-005211 | 2025-09-06 | BOQ-PKG-01-01231 | PKG-01 | INV-PKG-01-032-05211 | 45.25 | 207430.27 | 10371.51 | Disputed | 197058.76 | 2025-Q3
EXP-005866 | 2025-09-06 | BOQ-PKG-06-01886 | PKG-06 | INV-PKG-06-022-05866 | 415.46 | 122862.59 | 6143.13 | Paid | 116719.46 | 2025-Q3
EXP-006241 | 2025-09-06 | BOQ-PKG-01-00271 | PKG-01 | INV-PKG-01-012-06241 | 102.44 | 93542.57 | 4677.13 | Approved Pending Payment | 88865.44 | 2025-Q3
EXP-006417 | 2025-09-06 | BOQ-PKG-07-00447 | PKG-07 | INV-PKG-07-013-06417 | 290.95 | 165299.12 | 8264.96 | Paid | 157034.16 | 2025-Q3
EXP-000359 | 2025-09-07 | BOQ-PKG-09-00359 | PKG-09 | INV-PKG-09-010-00359 | 325.87 | 73187.5 | 3659.38 | Paid | 69528.12 | 2025-Q3
EXP-002578 | 2025-09-07 | BOQ-PKG-08-00588 | PKG-08 | INV-PKG-08-024-02578 | 366.85 | 77627.04 | 3881.35 | Paid | 73745.69 | 2025-Q3
EXP-002926 | 2025-09-07 | BOQ-PKG-06-00936 | PKG-06 | INV-PKG-06-022-02926 | 376.13 | 57772.27 | 2888.61 | Paid | 54883.66 | 2025-Q3
EXP-004441 | 2025-09-07 | BOQ-PKG-01-00461 | PKG-01 | INV-PKG-01-032-04441 | 272.01 | 156406.84 | 7820.34 | Approved Pending Payment | 148586.5 | 2025-Q3
EXP-004797 | 2025-09-07 | BOQ-PKG-07-00817 | PKG-07 | INV-PKG-07-003-04797 | 194.39 | 25950.89 | 1297.54 | Paid | 24653.35 | 2025-Q3
EXP-005043 | 2025-09-07 | BOQ-PKG-03-01063 | PKG-03 | INV-PKG-03-004-05043 | 185.17 | 113324.94 | 5666.25 | Paid | 107658.69 | 2025-Q3
EXP-006664 | 2025-09-07 | BOQ-PKG-04-00694 | PKG-04 | INV-PKG-04-015-06664 | 300.54 | 43881.72 | 2194.09 | Paid | 41687.63 | 2025-Q3
EXP-000752 | 2025-09-08 | BOQ-PKG-02-00752 | PKG-02 | INV-PKG-02-018-00752 | 412 | 63709.64 | 3185.48 | Paid | 60524.16 | 2025-Q3
EXP-001558 | 2025-09-08 | BOQ-PKG-08-01558 | PKG-08 | INV-PKG-08-019-01558 | 119.36 | 32389 | 1619.45 | Paid | 30769.55 | 2025-Q3
EXP-001866 | 2025-09-08 | BOQ-PKG-06-01866 | PKG-06 | INV-PKG-06-012-01866 | 245.76 | 203736.55 | 10186.83 | Paid | 193549.72 | 2025-Q3
EXP-002556 | 2025-09-08 | BOQ-PKG-06-00566 | PKG-06 | INV-PKG-06-002-02556 | 195.13 | 192149.97 | 9607.5 | Paid | 182542.47 | 2025-Q3
EXP-004030 | 2025-09-08 | BOQ-PKG-10-00050 | PKG-10 | INV-PKG-10-006-04030 | 196.42 | 27494.24 | 1374.71 | Disputed | 26119.53 | 2025-Q3
EXP-004387 | 2025-09-08 | BOQ-PKG-07-00407 | PKG-07 | INV-PKG-07-013-04387 | 74.53 | 60006.95 | 3000.35 | Disputed | 57006.6 | 2025-Q3
EXP-004634 | 2025-09-08 | BOQ-PKG-04-00654 | PKG-04 | INV-PKG-04-015-04634 | 431.01 | 150085.07 | 7504.25 | Paid | 142580.82 | 2025-Q3
EXP-000178 | 2025-09-09 | BOQ-PKG-08-00178 | PKG-08 | INV-PKG-08-004-00178 | 163.4 | 52055.96 | 2602.8 | Approved Pending Payment | 49453.16 | 2025-Q3
EXP-001826 | 2025-09-09 | BOQ-PKG-06-01826 | PKG-06 | INV-PKG-06-007-01826 | 177.31 | 200789.48 | 10039.47 | Paid | 190750.01 | 2025-Q3
EXP-003022 | 2025-09-09 | BOQ-PKG-02-01032 | PKG-02 | INV-PKG-02-013-03022 | 52.12 | 195478.39 | 9773.92 | Approved Pending Payment | 185704.47 | 2025-Q3
EXP-003652 | 2025-09-09 | BOQ-PKG-02-01662 | PKG-02 | INV-PKG-02-013-03652 | 401.11 | 198674.35 | 9933.72 | Paid | 188740.63 | 2025-Q3
EXP-004313 | 2025-09-09 | BOQ-PKG-03-00333 | PKG-03 | INV-PKG-03-009-04313 | 312.17 | 147206.92 | 7360.35 | Paid | 139846.57 | 2025-Q3
EXP-005214 | 2025-09-09 | BOQ-PKG-04-01234 | PKG-04 | INV-PKG-04-035-05214 | 77.58 | 168136.04 | 8406.8 | Under Review | 159729.24 | 2025-Q3
EXP-006219 | 2025-09-09 | BOQ-PKG-09-00249 | PKG-09 | INV-PKG-09-025-06219 | 215.87 | 116698.27 | 5834.91 | Paid | 110863.36 | 2025-Q3
EXP-006584 | 2025-09-09 | BOQ-PKG-04-00614 | PKG-04 | INV-PKG-04-005-06584 | 311.87 | 171860.37 | 8593.02 | Paid | 163267.35 | 2025-Q3
EXP-006629 | 2025-09-09 | BOQ-PKG-09-00659 | PKG-09 | INV-PKG-09-015-06629 | 321.28 | 189079.78 | 9453.99 | Paid | 179625.79 | 2025-Q3
EXP-001169 | 2025-09-10 | BOQ-PKG-09-01169 | PKG-09 | INV-PKG-09-015-01169 | 339.32 | 147066.87 | 7353.34 | Paid | 139713.53 | 2025-Q3
EXP-001546 | 2025-09-10 | BOQ-PKG-06-01546 | PKG-06 | INV-PKG-06-007-01546 | 427.53 | 207987.6 | 10399.38 | Paid | 197588.22 | 2025-Q3
EXP-002034 | 2025-09-10 | BOQ-PKG-04-00044 | PKG-04 | INV-PKG-04-005-02034 | 298.7 | 75697.7 | 3784.88 | Paid | 71912.82 | 2025-Q3
EXP-002865 | 2025-09-10 | BOQ-PKG-05-00875 | PKG-05 | INV-PKG-05-031-02865 | 88.45 | 57434.36 | 2871.72 | Paid | 54562.64 | 2025-Q3
EXP-002997 | 2025-09-10 | BOQ-PKG-07-01007 | PKG-07 | INV-PKG-07-023-02997 | 67.77 | 141726.37 | 7086.32 | Paid | 134640.05 | 2025-Q3
EXP-006636 | 2025-09-10 | BOQ-PKG-06-00666 | PKG-06 | INV-PKG-06-022-06636 | 331.29 | 27306.94 | 1365.35 | Paid | 25941.59 | 2025-Q3
EXP-002245 | 2025-09-11 | BOQ-PKG-05-00255 | PKG-05 | INV-PKG-05-006-02245 | 237.21 | 102451.99 | 5122.6 | Paid | 97329.39 | 2025-Q3
EXP-003845 | 2025-09-11 | BOQ-PKG-05-01855 | PKG-05 | INV-PKG-05-031-03845 | 217.3 | 195157.73 | 9757.89 | Approved Pending Payment | 185399.84 | 2025-Q3
EXP-004056 | 2025-09-11 | BOQ-PKG-06-00076 | PKG-06 | INV-PKG-06-032-04056 | 296.26 | 41144.26 | 2057.21 | Paid | 39087.05 | 2025-Q3
EXP-005326 | 2025-09-11 | BOQ-PKG-06-01346 | PKG-06 | INV-PKG-06-007-05326 | 376.35 | 147222.58 | 7361.13 | Paid | 139861.45 | 2025-Q3
EXP-005691 | 2025-09-11 | BOQ-PKG-01-01711 | PKG-01 | INV-PKG-01-022-05691 | 267.82 | 136513.3 | 6825.66 | Paid | 129687.64 | 2025-Q3
EXP-005791 | 2025-09-11 | BOQ-PKG-01-01811 | PKG-01 | INV-PKG-01-017-05791 | 200.78 | 161702.46 | 8085.12 | Paid | 153617.34 | 2025-Q3
EXP-006586 | 2025-09-11 | BOQ-PKG-06-00616 | PKG-06 | INV-PKG-06-007-06586 | 130.4 | 135503.97 | 6775.2 | Paid | 128728.77 | 2025-Q3
EXP-001808 | 2025-09-12 | BOQ-PKG-08-01808 | PKG-08 | INV-PKG-08-024-01808 | 381.94 | 123936.7 | 6196.84 | Disputed | 117739.86 | 2025-Q3
EXP-002298 | 2025-09-12 | BOQ-PKG-08-00308 | PKG-08 | INV-PKG-08-024-02298 | 404.73 | 144214.62 | 7210.73 | Approved Pending Payment | 137003.89 | 2025-Q3
EXP-005205 | 2025-09-12 | BOQ-PKG-05-01225 | PKG-05 | INV-PKG-05-026-05205 | 209.39 | 199530.48 | 9976.52 | Paid | 189553.96 | 2025-Q3
EXP-006707 | 2025-09-12 | BOQ-PKG-07-00737 | PKG-07 | INV-PKG-07-023-06707 | 367.22 | 207468.67 | 10373.43 | Paid | 197095.24 | 2025-Q3
EXP-000693 | 2025-09-13 | BOQ-PKG-03-00693 | PKG-03 | INV-PKG-03-029-00693 | 38.44 | 49550.3 | 2477.52 | Paid | 47072.78 | 2025-Q3
EXP-002035 | 2025-09-13 | BOQ-PKG-05-00045 | PKG-05 | INV-PKG-05-006-02035 | 393.43 | 97796.72 | 4889.84 | Approved Pending Payment | 92906.88 | 2025-Q3
EXP-002414 | 2025-09-13 | BOQ-PKG-04-00424 | PKG-04 | INV-PKG-04-035-02414 | 415.38 | 52537.1 | 2626.86 | Approved Pending Payment | 49910.24 | 2025-Q3
EXP-003474 | 2025-09-13 | BOQ-PKG-04-01484 | PKG-04 | INV-PKG-04-010-03474 | 374.12 | 215864.66 | 10793.23 | Paid | 205071.43 | 2025-Q3
EXP-003480 | 2025-09-13 | BOQ-PKG-10-01490 | PKG-10 | INV-PKG-10-016-03480 | 99.08 | 164947.75 | 8247.39 | Under Review | 156700.36 | 2025-Q3
EXP-006698 | 2025-09-13 | BOQ-PKG-08-00728 | PKG-08 | INV-PKG-08-014-06698 | 23.97 | 97003.23 | 4850.16 | Paid | 92153.07 | 2025-Q3
EXP-002717 | 2025-09-14 | BOQ-PKG-07-00727 | PKG-07 | INV-PKG-07-023-02717 | 279.6 | 123177.98 | 6158.9 | Approved Pending Payment | 117019.08 | 2025-Q3
EXP-002757 | 2025-09-14 | BOQ-PKG-07-00767 | PKG-07 | INV-PKG-07-028-02757 | 366.97 | 89854.61 | 4492.73 | Paid | 85361.88 | 2025-Q3
EXP-003313 | 2025-09-14 | BOQ-PKG-03-01323 | PKG-03 | INV-PKG-03-024-03313 | 32.89 | 196435.5 | 9821.78 | Paid | 186613.72 | 2025-Q3
EXP-005711 | 2025-09-14 | BOQ-PKG-01-01731 | PKG-01 | INV-PKG-01-007-05711 | 44.94 | 113986.13 | 5699.31 | Paid | 108286.82 | 2025-Q3
EXP-001427 | 2025-09-15 | BOQ-PKG-07-01427 | PKG-07 | INV-PKG-07-028-01427 | 98.22 | 29459.11 | 1472.96 | Paid | 27986.15 | 2025-Q3
EXP-003407 | 2025-09-15 | BOQ-PKG-07-01417 | PKG-07 | INV-PKG-07-013-03407 | 182.55 | 172107.47 | 8605.37 | Paid | 163502.1 | 2025-Q3
EXP-003640 | 2025-09-15 | BOQ-PKG-10-01650 | PKG-10 | INV-PKG-10-001-03640 | 156.63 | 33744.64 | 1687.23 | Paid | 32057.41 | 2025-Q3
EXP-004757 | 2025-09-15 | BOQ-PKG-07-00777 | PKG-07 | INV-PKG-07-033-04757 | 188.11 | 86523.47 | 4326.17 | Approved Pending Payment | 82197.3 | 2025-Q3
EXP-004775 | 2025-09-15 | BOQ-PKG-05-00795 | PKG-05 | INV-PKG-05-016-04775 | 217.43 | 153167.21 | 7658.36 | Disputed | 145508.85 | 2025-Q3
EXP-005295 | 2025-09-15 | BOQ-PKG-05-01315 | PKG-05 | INV-PKG-05-011-05295 | 368.3 | 80752.92 | 4037.65 | Paid | 76715.27 | 2025-Q3
EXP-006495 | 2025-09-15 | BOQ-PKG-05-00525 | PKG-05 | INV-PKG-05-021-06495 | 353.09 | 39828.46 | 1991.42 | Approved Pending Payment | 37837.04 | 2025-Q3
EXP-006862 | 2025-09-15 | BOQ-PKG-02-00892 | PKG-02 | INV-PKG-02-003-06862 | 161.49 | 56529.08 | 2826.45 | Disputed | 53702.63 | 2025-Q3
EXP-000180 | 2025-09-16 | BOQ-PKG-10-00180 | PKG-10 | INV-PKG-10-006-00180 | 272.42 | 152246.75 | 7612.34 | Approved Pending Payment | 144634.41 | 2025-Q3
EXP-002046 | 2025-09-16 | BOQ-PKG-06-00056 | PKG-06 | INV-PKG-06-017-02046 | 208.82 | 191569.66 | 9578.48 | Paid | 181991.18 | 2025-Q3
EXP-003037 | 2025-09-16 | BOQ-PKG-07-01047 | PKG-07 | INV-PKG-07-028-03037 | 207.64 | 123564.23 | 6178.21 | Approved Pending Payment | 117386.02 | 2025-Q3
EXP-004443 | 2025-09-16 | BOQ-PKG-03-00463 | PKG-03 | INV-PKG-03-034-04443 | 358.37 | 194577.78 | 9728.89 | Paid | 184848.89 | 2025-Q3
EXP-004738 | 2025-09-16 | BOQ-PKG-08-00758 | PKG-08 | INV-PKG-08-014-04738 | 28.08 | 73141.76 | 3657.09 | Paid | 69484.67 | 2025-Q3
EXP-006069 | 2025-09-16 | BOQ-PKG-09-00099 | PKG-09 | INV-PKG-09-015-06069 | 5.56 | 159312.91 | 7965.65 | Paid | 151347.26 | 2025-Q3
EXP-006272 | 2025-09-16 | BOQ-PKG-02-00302 | PKG-02 | INV-PKG-02-008-06272 | 234.69 | 122585.99 | 6129.3 | Paid | 116456.69 | 2025-Q3
EXP-000350 | 2025-09-17 | BOQ-PKG-10-00350 | PKG-10 | INV-PKG-10-001-00350 | 92.75 | 41062.27 | 2053.11 | Under Review | 39009.16 | 2025-Q3
EXP-000992 | 2025-09-17 | BOQ-PKG-02-00992 | PKG-02 | INV-PKG-02-013-00992 | 44.16 | 189116.89 | 9455.84 | Paid | 179661.05 | 2025-Q3
EXP-002711 | 2025-09-17 | BOQ-PKG-01-00721 | PKG-01 | INV-PKG-01-017-02711 | 180.44 | 114895.63 | 5744.78 | Under Review | 109150.85 | 2025-Q3
EXP-006751 | 2025-09-17 | BOQ-PKG-01-00781 | PKG-01 | INV-PKG-01-032-06751 | 61.68 | 109112.59 | 5455.63 | Approved Pending Payment | 103656.96 | 2025-Q3
EXP-006825 | 2025-09-17 | BOQ-PKG-05-00855 | PKG-05 | INV-PKG-05-001-06825 | 159.82 | 54407.03 | 2720.35 | Paid | 51686.68 | 2025-Q3
EXP-000124 | 2025-09-18 | BOQ-PKG-04-00124 | PKG-04 | INV-PKG-04-020-00124 | 336.62 | 66797.69 | 3339.88 | Paid | 63457.81 | 2025-Q3
EXP-000401 | 2025-09-18 | BOQ-PKG-01-00401 | PKG-01 | INV-PKG-01-017-00401 | 12.55 | 195999.66 | 9799.98 | Paid | 186199.68 | 2025-Q3
EXP-001367 | 2025-09-18 | BOQ-PKG-07-01367 | PKG-07 | INV-PKG-07-003-01367 | 342.09 | 47165.35 | 2358.27 | Paid | 44807.08 | 2025-Q3
EXP-001814 | 2025-09-18 | BOQ-PKG-04-01814 | PKG-04 | INV-PKG-04-030-01814 | 83.8 | 133442.25 | 6672.11 | Paid | 126770.14 | 2025-Q3
EXP-002793 | 2025-09-18 | BOQ-PKG-03-00803 | PKG-03 | INV-PKG-03-029-02793 | 170.45 | 140153.31 | 7007.67 | Paid | 133145.64 | 2025-Q3
EXP-003020 | 2025-09-18 | BOQ-PKG-10-01030 | PKG-10 | INV-PKG-10-011-03020 | 422.05 | 42693.56 | 2134.68 | Approved Pending Payment | 40558.88 | 2025-Q3
EXP-003949 | 2025-09-18 | BOQ-PKG-09-01959 | PKG-09 | INV-PKG-09-030-03949 | 85.43 | 74186.99 | 3709.35 | Paid | 70477.64 | 2025-Q3
EXP-001175 | 2025-09-19 | BOQ-PKG-05-01175 | PKG-05 | INV-PKG-05-021-01175 | 437.94 | 34542.99 | 1727.15 | Under Review | 32815.84 | 2025-Q3
EXP-002211 | 2025-09-19 | BOQ-PKG-01-00221 | PKG-01 | INV-PKG-01-007-02211 | 426.65 | 32681.23 | 1634.06 | Paid | 31047.17 | 2025-Q3
EXP-002425 | 2025-09-19 | BOQ-PKG-05-00435 | PKG-05 | INV-PKG-05-011-02425 | 24.92 | 120434.89 | 6021.74 | Approved Pending Payment | 114413.15 | 2025-Q3
EXP-002448 | 2025-09-19 | BOQ-PKG-08-00458 | PKG-08 | INV-PKG-08-034-02448 | 63.32 | 163685.62 | 8184.28 | Approved Pending Payment | 155501.34 | 2025-Q3
EXP-002805 | 2025-09-19 | BOQ-PKG-05-00815 | PKG-05 | INV-PKG-05-006-02805 | 184.08 | 113950.96 | 5697.55 | Under Review | 108253.41 | 2025-Q3
EXP-004986 | 2025-09-19 | BOQ-PKG-06-01006 | PKG-06 | INV-PKG-06-017-04986 | 434.56 | 182533.87 | 9126.69 | Paid | 173407.18 | 2025-Q3
EXP-005982 | 2025-09-19 | BOQ-PKG-02-00012 | PKG-02 | INV-PKG-02-033-05982 | 76.09 | 84966.82 | 4248.34 | Approved Pending Payment | 80718.48 | 2025-Q3
EXP-001356 | 2025-09-20 | BOQ-PKG-06-01356 | PKG-06 | INV-PKG-06-027-01356 | 86.28 | 162001.76 | 8100.09 | Paid | 153901.67 | 2025-Q3
EXP-002462 | 2025-09-20 | BOQ-PKG-02-00472 | PKG-02 | INV-PKG-02-013-02462 | 446.79 | 135085.63 | 6754.28 | Paid | 128331.35 | 2025-Q3
EXP-004552 | 2025-09-20 | BOQ-PKG-02-00572 | PKG-02 | INV-PKG-02-003-04552 | 437.29 | 138092.5 | 6904.62 | Paid | 131187.88 | 2025-Q3
EXP-004747 | 2025-09-20 | BOQ-PKG-07-00767 | PKG-07 | INV-PKG-07-023-04747 | 287.57 | 50238.64 | 2511.93 | Paid | 47726.71 | 2025-Q3
EXP-005152 | 2025-09-20 | BOQ-PKG-02-01172 | PKG-02 | INV-PKG-02-008-05152 | 50.09 | 112664.59 | 5633.23 | Paid | 107031.36 | 2025-Q3
EXP-005695 | 2025-09-20 | BOQ-PKG-05-01715 | PKG-05 | INV-PKG-05-026-05695 | 354.74 | 130276.68 | 6513.83 | Paid | 123762.85 | 2025-Q3
EXP-005845 | 2025-09-20 | BOQ-PKG-05-01865 | PKG-05 | INV-PKG-05-001-05845 | 43.15 | 128856.53 | 6442.83 | Paid | 122413.7 | 2025-Q3
EXP-005969 | 2025-09-20 | BOQ-PKG-09-01989 | PKG-09 | INV-PKG-09-020-05969 | 291.95 | 151794.84 | 7589.74 | Paid | 144205.1 | 2025-Q3
EXP-006137 | 2025-09-20 | BOQ-PKG-07-00167 | PKG-07 | INV-PKG-07-013-06137 | 23 | 90772.24 | 4538.61 | Paid | 86233.63 | 2025-Q3
EXP-006364 | 2025-09-20 | BOQ-PKG-04-00394 | PKG-04 | INV-PKG-04-030-06364 | 371.23 | 197067.36 | 9853.37 | Paid | 187213.99 | 2025-Q3
EXP-000405 | 2025-09-21 | BOQ-PKG-05-00405 | PKG-05 | INV-PKG-05-021-00405 | 81.71 | 188479.79 | 9423.99 | Paid | 179055.8 | 2025-Q3
EXP-000789 | 2025-09-21 | BOQ-PKG-09-00789 | PKG-09 | INV-PKG-09-020-00789 | 321.87 | 55370.99 | 2768.55 | Under Review | 52602.44 | 2025-Q3
EXP-002360 | 2025-09-21 | BOQ-PKG-10-00370 | PKG-10 | INV-PKG-10-016-02360 | 412.99 | 138682.19 | 6934.11 | Disputed | 131748.08 | 2025-Q3
EXP-002502 | 2025-09-21 | BOQ-PKG-02-00512 | PKG-02 | INV-PKG-02-018-02502 | 434.99 | 123778.02 | 6188.9 | Paid | 117589.12 | 2025-Q3
EXP-002879 | 2025-09-21 | BOQ-PKG-09-00889 | PKG-09 | INV-PKG-09-010-02879 | 321.03 | 147673.91 | 7383.7 | Paid | 140290.21 | 2025-Q3
EXP-004429 | 2025-09-21 | BOQ-PKG-09-00449 | PKG-09 | INV-PKG-09-020-04429 | 164.54 | 127127.44 | 6356.37 | Paid | 120771.07 | 2025-Q3
EXP-005927 | 2025-09-21 | BOQ-PKG-07-01947 | PKG-07 | INV-PKG-07-013-05927 | 203.29 | 106399.8 | 5319.99 | Disputed | 101079.81 | 2025-Q3
EXP-006243 | 2025-09-21 | BOQ-PKG-03-00273 | PKG-03 | INV-PKG-03-014-06243 | 122.56 | 61751.09 | 3087.55 | Paid | 58663.54 | 2025-Q3
EXP-000059 | 2025-09-22 | BOQ-PKG-09-00059 | PKG-09 | INV-PKG-09-025-00059 | 429.78 | 52119.44 | 2605.97 | Paid | 49513.47 | 2025-Q3
EXP-001634 | 2025-09-22 | BOQ-PKG-04-01634 | PKG-04 | INV-PKG-04-025-01634 | 17.58 | 25945.75 | 1297.29 | Paid | 24648.46 | 2025-Q3
EXP-001728 | 2025-09-22 | BOQ-PKG-08-01728 | PKG-08 | INV-PKG-08-014-01728 | 41.36 | 47887.04 | 2394.35 | Paid | 45492.69 | 2025-Q3
EXP-002533 | 2025-09-22 | BOQ-PKG-03-00543 | PKG-03 | INV-PKG-03-014-02533 | 134.03 | 181676.65 | 9083.83 | Paid | 172592.82 | 2025-Q3
EXP-002600 | 2025-09-22 | BOQ-PKG-10-00610 | PKG-10 | INV-PKG-10-011-02600 | 113.69 | 186604.22 | 9330.21 | Paid | 177274.01 | 2025-Q3
EXP-004127 | 2025-09-22 | BOQ-PKG-07-00147 | PKG-07 | INV-PKG-07-033-04127 | 128.47 | 124409.61 | 6220.48 | Paid | 118189.13 | 2025-Q3
EXP-004761 | 2025-09-22 | BOQ-PKG-01-00781 | PKG-01 | INV-PKG-01-002-04761 | 194.16 | 181189.97 | 9059.5 | Paid | 172130.47 | 2025-Q3
EXP-005810 | 2025-09-22 | BOQ-PKG-10-01830 | PKG-10 | INV-PKG-10-001-05810 | 344.23 | 108796.89 | 5439.84 | Under Review | 103357.05 | 2025-Q3
EXP-000034 | 2025-09-23 | BOQ-PKG-04-00034 | PKG-04 | INV-PKG-04-035-00034 | 51.03 | 100776.35 | 5038.82 | Approved Pending Payment | 95737.53 | 2025-Q3
EXP-000683 | 2025-09-23 | BOQ-PKG-03-00683 | PKG-03 | INV-PKG-03-019-00683 | 15.99 | 175725.04 | 8786.25 | Paid | 166938.79 | 2025-Q3
EXP-003074 | 2025-09-23 | BOQ-PKG-04-01084 | PKG-04 | INV-PKG-04-030-03074 | 93.84 | 134697.12 | 6734.86 | Disputed | 127962.26 | 2025-Q3
EXP-003702 | 2025-09-23 | BOQ-PKG-02-01712 | PKG-02 | INV-PKG-02-028-03702 | 423.72 | 160779.02 | 8038.95 | Under Review | 152740.07 | 2025-Q3
EXP-004305 | 2025-09-23 | BOQ-PKG-05-00325 | PKG-05 | INV-PKG-05-001-04305 | 192.27 | 199939 | 9996.95 | Paid | 189942.05 | 2025-Q3
EXP-005383 | 2025-09-23 | BOQ-PKG-03-01403 | PKG-03 | INV-PKG-03-029-05383 | 344.15 | 100605.52 | 5030.28 | Paid | 95575.24 | 2025-Q3
EXP-005582 | 2025-09-23 | BOQ-PKG-02-01602 | PKG-02 | INV-PKG-02-018-05582 | 33.35 | 83738.38 | 4186.92 | Paid | 79551.46 | 2025-Q3
EXP-006279 | 2025-09-23 | BOQ-PKG-09-00309 | PKG-09 | INV-PKG-09-015-06279 | 333.79 | 138765.16 | 6938.26 | Paid | 131826.9 | 2025-Q3
EXP-006467 | 2025-09-23 | BOQ-PKG-07-00497 | PKG-07 | INV-PKG-07-028-06467 | 337.12 | 155302.91 | 7765.15 | Paid | 147537.76 | 2025-Q3
EXP-000730 | 2025-09-24 | BOQ-PKG-10-00730 | PKG-10 | INV-PKG-10-031-00730 | 400.91 | 109508.47 | 5475.42 | Approved Pending Payment | 104033.05 | 2025-Q3
EXP-002204 | 2025-09-24 | BOQ-PKG-04-00214 | PKG-04 | INV-PKG-04-035-02204 | 84.12 | 33984.72 | 1699.24 | Paid | 32285.48 | 2025-Q3
EXP-002962 | 2025-09-24 | BOQ-PKG-02-00972 | PKG-02 | INV-PKG-02-023-02962 | 69.15 | 206098.85 | 10304.94 | Paid | 195793.91 | 2025-Q3
EXP-003780 | 2025-09-24 | BOQ-PKG-10-01790 | PKG-10 | INV-PKG-10-001-03780 | 46.93 | 156467.01 | 7823.35 | Disputed | 148643.66 | 2025-Q3
EXP-006221 | 2025-09-24 | BOQ-PKG-01-00251 | PKG-01 | INV-PKG-01-027-06221 | 91.82 | 158734.52 | 7936.73 | Paid | 150797.79 | 2025-Q3
EXP-006222 | 2025-09-24 | BOQ-PKG-02-00252 | PKG-02 | INV-PKG-02-028-06222 | 432.84 | 61861.81 | 3093.09 | Paid | 58768.72 | 2025-Q3
EXP-006665 | 2025-09-24 | BOQ-PKG-05-00695 | PKG-05 | INV-PKG-05-016-06665 | 150.15 | 131720.09 | 6586 | Paid | 125134.09 | 2025-Q3
EXP-000361 | 2025-09-25 | BOQ-PKG-01-00361 | PKG-01 | INV-PKG-01-012-00361 | 185.31 | 131068.35 | 6553.42 | Paid | 124514.93 | 2025-Q3
EXP-003002 | 2025-09-25 | BOQ-PKG-02-01012 | PKG-02 | INV-PKG-02-028-03002 | 387.86 | 49852.23 | 2492.61 | Paid | 47359.62 | 2025-Q3
EXP-003577 | 2025-09-25 | BOQ-PKG-07-01587 | PKG-07 | INV-PKG-07-008-03577 | 276.21 | 124230.04 | 6211.5 | Paid | 118018.54 | 2025-Q3
EXP-004729 | 2025-09-25 | BOQ-PKG-09-00749 | PKG-09 | INV-PKG-09-005-04729 | 293.32 | 37043.64 | 1852.18 | Paid | 35191.46 | 2025-Q3
EXP-006043 | 2025-09-25 | BOQ-PKG-03-00073 | PKG-03 | INV-PKG-03-024-06043 | 393.18 | 40488.54 | 2024.43 | Paid | 38464.11 | 2025-Q3
EXP-006728 | 2025-09-25 | BOQ-PKG-08-00758 | PKG-08 | INV-PKG-08-009-06728 | 275.8 | 73644.64 | 3682.23 | Paid | 69962.41 | 2025-Q3
EXP-000460 | 2025-09-26 | BOQ-PKG-10-00460 | PKG-10 | INV-PKG-10-006-00460 | 118.77 | 94483.44 | 4724.17 | Paid | 89759.27 | 2025-Q3
EXP-001330 | 2025-09-26 | BOQ-PKG-10-01330 | PKG-10 | INV-PKG-10-001-01330 | 377.98 | 119212.07 | 5960.6 | Paid | 113251.47 | 2025-Q3
EXP-002015 | 2025-09-26 | BOQ-PKG-05-00025 | PKG-05 | INV-PKG-05-021-02015 | 176.06 | 150568.22 | 7528.41 | Paid | 143039.81 | 2025-Q3
EXP-002066 | 2025-09-26 | BOQ-PKG-06-00076 | PKG-06 | INV-PKG-06-002-02066 | 69.91 | 57166.23 | 2858.31 | Paid | 54307.92 | 2025-Q3
EXP-003586 | 2025-09-26 | BOQ-PKG-06-01596 | PKG-06 | INV-PKG-06-017-03586 | 147.33 | 68484.26 | 3424.21 | Approved Pending Payment | 65060.05 | 2025-Q3
EXP-003768 | 2025-09-26 | BOQ-PKG-08-01778 | PKG-08 | INV-PKG-08-024-03768 | 214.63 | 50757.21 | 2537.86 | Under Review | 48219.35 | 2025-Q3
EXP-001218 | 2025-09-27 | BOQ-PKG-08-01218 | PKG-08 | INV-PKG-08-029-01218 | 308.14 | 164420.27 | 8221.01 | Under Review | 156199.26 | 2025-Q3
EXP-001605 | 2025-09-27 | BOQ-PKG-05-01605 | PKG-05 | INV-PKG-05-031-01605 | 40.61 | 70666.59 | 3533.33 | Paid | 67133.26 | 2025-Q3
EXP-002866 | 2025-09-27 | BOQ-PKG-06-00876 | PKG-06 | INV-PKG-06-032-02866 | 229.31 | 159483.77 | 7974.19 | Paid | 151509.58 | 2025-Q3
EXP-005069 | 2025-09-27 | BOQ-PKG-09-01089 | PKG-09 | INV-PKG-09-030-05069 | 342.85 | 46839.08 | 2341.95 | Paid | 44497.13 | 2025-Q3
EXP-005445 | 2025-09-27 | BOQ-PKG-05-01465 | PKG-05 | INV-PKG-05-021-05445 | 133.93 | 215622.12 | 10781.11 | Paid | 204841.01 | 2025-Q3
EXP-005780 | 2025-09-27 | BOQ-PKG-10-01800 | PKG-10 | INV-PKG-10-006-05780 | 397.47 | 48520.25 | 2426.01 | Paid | 46094.24 | 2025-Q3
EXP-000541 | 2025-09-28 | BOQ-PKG-01-00541 | PKG-01 | INV-PKG-01-017-00541 | 108.77 | 182564.96 | 9128.25 | Paid | 173436.71 | 2025-Q3
EXP-000803 | 2025-09-28 | BOQ-PKG-03-00803 | PKG-03 | INV-PKG-03-034-00803 | 106.65 | 74009.74 | 3700.49 | Paid | 70309.25 | 2025-Q3
EXP-001687 | 2025-09-28 | BOQ-PKG-07-01687 | PKG-07 | INV-PKG-07-008-01687 | 396.65 | 66249.02 | 3312.45 | Paid | 62936.57 | 2025-Q3
EXP-001829 | 2025-09-28 | BOQ-PKG-09-01829 | PKG-09 | INV-PKG-09-010-01829 | 24.31 | 36485.79 | 1824.29 | Paid | 34661.5 | 2025-Q3
EXP-002282 | 2025-09-28 | BOQ-PKG-02-00292 | PKG-02 | INV-PKG-02-008-02282 | 107.99 | 70755.7 | 3537.78 | Under Review | 67217.92 | 2025-Q3
EXP-004012 | 2025-09-28 | BOQ-PKG-02-00032 | PKG-02 | INV-PKG-02-023-04012 | 39.49 | 34732.01 | 1736.6 | Under Review | 32995.41 | 2025-Q3
EXP-004925 | 2025-09-28 | BOQ-PKG-05-00945 | PKG-05 | INV-PKG-05-026-04925 | 67.91 | 40992.99 | 2049.65 | Approved Pending Payment | 38943.34 | 2025-Q3
EXP-005689 | 2025-09-28 | BOQ-PKG-09-01709 | PKG-09 | INV-PKG-09-020-05689 | 125.21 | 92561.76 | 4628.09 | Paid | 87933.67 | 2025-Q3
EXP-001675 | 2025-09-29 | BOQ-PKG-05-01675 | PKG-05 | INV-PKG-05-031-01675 | 385.44 | 70153.33 | 3507.67 | Paid | 66645.66 | 2025-Q3
EXP-001772 | 2025-09-29 | BOQ-PKG-02-01772 | PKG-02 | INV-PKG-02-023-01772 | 413.89 | 96354.34 | 4817.72 | Paid | 91536.62 | 2025-Q3
EXP-002280 | 2025-09-29 | BOQ-PKG-10-00290 | PKG-10 | INV-PKG-10-006-02280 | 379.71 | 162525.74 | 8126.29 | Paid | 154399.45 | 2025-Q3
EXP-002323 | 2025-09-29 | BOQ-PKG-03-00333 | PKG-03 | INV-PKG-03-014-02323 | 276.56 | 158159.25 | 7907.96 | Paid | 150251.29 | 2025-Q3
EXP-003826 | 2025-09-29 | BOQ-PKG-06-01836 | PKG-06 | INV-PKG-06-012-03826 | 373.62 | 174708.17 | 8735.41 | Paid | 165972.76 | 2025-Q3
EXP-006907 | 2025-09-29 | BOQ-PKG-07-00937 | PKG-07 | INV-PKG-07-013-06907 | 145.28 | 91292.01 | 4564.6 | Paid | 86727.41 | 2025-Q3
EXP-002401 | 2025-09-30 | BOQ-PKG-01-00411 | PKG-01 | INV-PKG-01-022-02401 | 392.21 | 192710.19 | 9635.51 | Paid | 183074.68 | 2025-Q3
EXP-003916 | 2025-09-30 | BOQ-PKG-06-01926 | PKG-06 | INV-PKG-06-032-03916 | 232.3 | 66582.47 | 3329.12 | Paid | 63253.35 | 2025-Q3
EXP-005390 | 2025-09-30 | BOQ-PKG-10-01410 | PKG-10 | INV-PKG-10-001-05390 | 449 | 111559.85 | 5577.99 | Approved Pending Payment | 105981.86 | 2025-Q3
EXP-005966 | 2025-09-30 | BOQ-PKG-06-01986 | PKG-06 | INV-PKG-06-017-05966 | 245.5 | 104394.52 | 5219.73 | Paid | 99174.79 | 2025-Q3
EXP-006156 | 2025-09-30 | BOQ-PKG-06-00186 | PKG-06 | INV-PKG-06-032-06156 | 348.55 | 185562.87 | 9278.14 | Approved Pending Payment | 176284.73 | 2025-Q3
EXP-006701 | 2025-09-30 | BOQ-PKG-01-00731 | PKG-01 | INV-PKG-01-017-06701 | 339.15 | 151560.96 | 7578.05 | Paid | 143982.91 | 2025-Q3
EXP-006833 | 2025-09-30 | BOQ-PKG-03-00863 | PKG-03 | INV-PKG-03-009-06833 | 72.74 | 163504 | 8175.2 | Approved Pending Payment | 155328.8 | 2025-Q3
EXP-000056 | 2025-10-01 | BOQ-PKG-06-00056 | PKG-06 | INV-PKG-06-022-00056 | 449 | 107050.76 | 5352.54 | Paid | 101698.22 | 2025-Q4
EXP-000216 | 2025-10-01 | BOQ-PKG-06-00216 | PKG-06 | INV-PKG-06-007-00216 | 199.78 | 75955.48 | 3797.77 | Paid | 72157.71 | 2025-Q4
EXP-000499 | 2025-10-01 | BOQ-PKG-09-00499 | PKG-09 | INV-PKG-09-010-00499 | 371.63 | 150157.7 | 7507.89 | Paid | 142649.81 | 2025-Q4
EXP-003644 | 2025-10-01 | BOQ-PKG-04-01654 | PKG-04 | INV-PKG-04-005-03644 | 56.59 | 97205.1 | 4860.26 | Paid | 92344.84 | 2025-Q4
EXP-005435 | 2025-10-01 | BOQ-PKG-05-01455 | PKG-05 | INV-PKG-05-011-05435 | 18.28 | 111985.39 | 5599.27 | Paid | 106386.12 | 2025-Q4
EXP-005901 | 2025-10-01 | BOQ-PKG-01-01921 | PKG-01 | INV-PKG-01-022-05901 | 23.07 | 26074.38 | 1303.72 | Paid | 24770.66 | 2025-Q4
EXP-006256 | 2025-10-01 | BOQ-PKG-06-00286 | PKG-06 | INV-PKG-06-027-06256 | 287.08 | 61558.61 | 3077.93 | Paid | 58480.68 | 2025-Q4
EXP-001673 | 2025-10-02 | BOQ-PKG-03-01673 | PKG-03 | INV-PKG-03-029-01673 | 148.99 | 88755.77 | 4437.79 | Paid | 84317.98 | 2025-Q4
EXP-001783 | 2025-10-02 | BOQ-PKG-03-01783 | PKG-03 | INV-PKG-03-034-01783 | 235.35 | 57255.36 | 2862.77 | Paid | 54392.59 | 2025-Q4
EXP-002674 | 2025-10-02 | BOQ-PKG-04-00684 | PKG-04 | INV-PKG-04-015-02674 | 200.7 | 155754.46 | 7787.72 | Paid | 147966.74 | 2025-Q4
EXP-002854 | 2025-10-02 | BOQ-PKG-04-00864 | PKG-04 | INV-PKG-04-020-02854 | 48.84 | 124789.65 | 6239.48 | Paid | 118550.17 | 2025-Q4
EXP-002864 | 2025-10-02 | BOQ-PKG-04-00874 | PKG-04 | INV-PKG-04-030-02864 | 31.37 | 197141.03 | 9857.05 | Approved Pending Payment | 187283.98 | 2025-Q4
EXP-003379 | 2025-10-02 | BOQ-PKG-09-01389 | PKG-09 | INV-PKG-09-020-03379 | 255.7 | 37181.31 | 1859.07 | Paid | 35322.24 | 2025-Q4
EXP-003472 | 2025-10-02 | BOQ-PKG-02-01482 | PKG-02 | INV-PKG-02-008-03472 | 310.3 | 27123.69 | 1356.18 | Paid | 25767.51 | 2025-Q4
EXP-004553 | 2025-10-02 | BOQ-PKG-03-00573 | PKG-03 | INV-PKG-03-004-04553 | 11.16 | 113309.33 | 5665.47 | Paid | 107643.86 | 2025-Q4
EXP-005089 | 2025-10-02 | BOQ-PKG-09-01109 | PKG-09 | INV-PKG-09-015-05089 | 409.03 | 67961.32 | 3398.07 | Paid | 64563.25 | 2025-Q4
EXP-005454 | 2025-10-02 | BOQ-PKG-04-01474 | PKG-04 | INV-PKG-04-030-05454 | 323.52 | 54276.37 | 2713.82 | Paid | 51562.55 | 2025-Q4
EXP-006442 | 2025-10-02 | BOQ-PKG-02-00472 | PKG-02 | INV-PKG-02-003-06442 | 439.98 | 180851.42 | 9042.57 | Approved Pending Payment | 171808.85 | 2025-Q4
EXP-006454 | 2025-10-02 | BOQ-PKG-04-00484 | PKG-04 | INV-PKG-04-015-06454 | 250.26 | 81175.39 | 4058.77 | Paid | 77116.62 | 2025-Q4
EXP-006526 | 2025-10-02 | BOQ-PKG-06-00556 | PKG-06 | INV-PKG-06-017-06526 | 351.36 | 37892.37 | 1894.62 | Under Review | 35997.75 | 2025-Q4
EXP-006624 | 2025-10-02 | BOQ-PKG-04-00654 | PKG-04 | INV-PKG-04-010-06624 | 293.45 | 74404.47 | 3720.22 | Under Review | 70684.25 | 2025-Q4
EXP-006986 | 2025-10-02 | BOQ-PKG-06-01016 | PKG-06 | INV-PKG-06-022-06986 | 278.17 | 119952.07 | 5997.6 | Paid | 113954.47 | 2025-Q4
EXP-000822 | 2025-10-03 | BOQ-PKG-02-00822 | PKG-02 | INV-PKG-02-018-00822 | 428.02 | 154557.3 | 7727.86 | Under Review | 146829.44 | 2025-Q4
EXP-001403 | 2025-10-03 | BOQ-PKG-03-01403 | PKG-03 | INV-PKG-03-004-01403 | 278.52 | 182215.25 | 9110.76 | Under Review | 173104.49 | 2025-Q4
EXP-005064 | 2025-10-03 | BOQ-PKG-04-01084 | PKG-04 | INV-PKG-04-025-05064 | 189.47 | 25995.82 | 1299.79 | Paid | 24696.03 | 2025-Q4
EXP-005328 | 2025-10-03 | BOQ-PKG-08-01348 | PKG-08 | INV-PKG-08-009-05328 | 283.04 | 80439.54 | 4021.98 | Paid | 76417.56 | 2025-Q4
EXP-005653 | 2025-10-03 | BOQ-PKG-03-01673 | PKG-03 | INV-PKG-03-019-05653 | 216.46 | 34940.32 | 1747.02 | Paid | 33193.3 | 2025-Q4
EXP-006570 | 2025-10-03 | BOQ-PKG-10-00600 | PKG-10 | INV-PKG-10-026-06570 | 419.11 | 37598.09 | 1879.9 | Approved Pending Payment | 35718.19 | 2025-Q4
EXP-000998 | 2025-10-04 | BOQ-PKG-08-00998 | PKG-08 | INV-PKG-08-019-00998 | 268.4 | 162312.11 | 8115.61 | Paid | 154196.5 | 2025-Q4
EXP-002492 | 2025-10-04 | BOQ-PKG-02-00502 | PKG-02 | INV-PKG-02-008-02492 | 314.54 | 157625.6 | 7881.28 | Paid | 149744.32 | 2025-Q4
EXP-002512 | 2025-10-04 | BOQ-PKG-02-00522 | PKG-02 | INV-PKG-02-028-02512 | 287 | 96227.77 | 4811.39 | Approved Pending Payment | 91416.38 | 2025-Q4
EXP-002584 | 2025-10-04 | BOQ-PKG-04-00594 | PKG-04 | INV-PKG-04-030-02584 | 35.61 | 94659.57 | 4732.98 | Under Review | 89926.59 | 2025-Q4
EXP-002589 | 2025-10-04 | BOQ-PKG-09-00599 | PKG-09 | INV-PKG-09-035-02589 | 77.47 | 163908.5 | 8195.43 | Paid | 155713.07 | 2025-Q4
EXP-003853 | 2025-10-04 | BOQ-PKG-03-01863 | PKG-03 | INV-PKG-03-004-03853 | 187.69 | 122356.87 | 6117.84 | Paid | 116239.03 | 2025-Q4
EXP-004603 | 2025-10-04 | BOQ-PKG-03-00623 | PKG-03 | INV-PKG-03-019-04603 | 18.58 | 187474.41 | 9373.72 | Paid | 178100.69 | 2025-Q4
EXP-005032 | 2025-10-04 | BOQ-PKG-02-01052 | PKG-02 | INV-PKG-02-028-05032 | 372.67 | 62285.93 | 3114.3 | Paid | 59171.63 | 2025-Q4
EXP-005071 | 2025-10-04 | BOQ-PKG-01-01091 | PKG-01 | INV-PKG-01-032-05071 | 164.17 | 94795.64 | 4739.78 | Paid | 90055.86 | 2025-Q4
EXP-002029 | 2025-10-05 | BOQ-PKG-09-00039 | PKG-09 | INV-PKG-09-035-02029 | 170.2 | 142928.01 | 7146.4 | Paid | 135781.61 | 2025-Q4
EXP-003603 | 2025-10-05 | BOQ-PKG-03-01613 | PKG-03 | INV-PKG-03-034-03603 | 175.12 | 100076.52 | 5003.83 | Paid | 95072.69 | 2025-Q4
EXP-004970 | 2025-10-05 | BOQ-PKG-10-00990 | PKG-10 | INV-PKG-10-001-04970 | 256.23 | 190325.22 | 9516.26 | Paid | 180808.96 | 2025-Q4
EXP-005120 | 2025-10-05 | BOQ-PKG-10-01140 | PKG-10 | INV-PKG-10-011-05120 | 430.71 | 129294.32 | 6464.72 | Paid | 122829.6 | 2025-Q4
EXP-005438 | 2025-10-05 | BOQ-PKG-08-01458 | PKG-08 | INV-PKG-08-014-05438 | 20.05 | 94039.78 | 4701.99 | Approved Pending Payment | 89337.79 | 2025-Q4
EXP-005804 | 2025-10-05 | BOQ-PKG-04-01824 | PKG-04 | INV-PKG-04-030-05804 | 193.39 | 47992.83 | 2399.64 | Paid | 45593.19 | 2025-Q4
EXP-006651 | 2025-10-05 | BOQ-PKG-01-00681 | PKG-01 | INV-PKG-01-002-06651 | 231.38 | 85314.9 | 4265.74 | Approved Pending Payment | 81049.16 | 2025-Q4
EXP-000026 | 2025-10-06 | BOQ-PKG-06-00026 | PKG-06 | INV-PKG-06-027-00026 | 434.56 | 34370.76 | 1718.54 | Paid | 32652.22 | 2025-Q4
EXP-000479 | 2025-10-06 | BOQ-PKG-09-00479 | PKG-09 | INV-PKG-09-025-00479 | 155.57 | 205024.07 | 10251.2 | Paid | 194772.87 | 2025-Q4
EXP-001522 | 2025-10-06 | BOQ-PKG-02-01522 | PKG-02 | INV-PKG-02-018-01522 | 189.32 | 32975.46 | 1648.77 | Paid | 31326.69 | 2025-Q4
EXP-002544 | 2025-10-06 | BOQ-PKG-04-00554 | PKG-04 | INV-PKG-04-025-02544 | 309.03 | 115338.81 | 5766.94 | Paid | 109571.87 | 2025-Q4
EXP-002652 | 2025-10-06 | BOQ-PKG-02-00662 | PKG-02 | INV-PKG-02-028-02652 | 101.04 | 101563.58 | 5078.18 | Under Review | 96485.4 | 2025-Q4
EXP-002807 | 2025-10-06 | BOQ-PKG-07-00817 | PKG-07 | INV-PKG-07-008-02807 | 445.89 | 181106.81 | 9055.34 | Paid | 172051.47 | 2025-Q4
EXP-003312 | 2025-10-06 | BOQ-PKG-02-01322 | PKG-02 | INV-PKG-02-023-03312 | 36.56 | 82935.33 | 4146.77 | Approved Pending Payment | 78788.56 | 2025-Q4
EXP-004382 | 2025-10-06 | BOQ-PKG-02-00402 | PKG-02 | INV-PKG-02-008-04382 | 136.72 | 79966.26 | 3998.31 | Paid | 75967.95 | 2025-Q4
EXP-005352 | 2025-10-06 | BOQ-PKG-02-01372 | PKG-02 | INV-PKG-02-033-05352 | 329.76 | 79817.59 | 3990.88 | Paid | 75826.71 | 2025-Q4
EXP-000251 | 2025-10-07 | BOQ-PKG-01-00251 | PKG-01 | INV-PKG-01-007-00251 | 191.6 | 153758.49 | 7687.92 | Paid | 146070.57 | 2025-Q4
EXP-005081 | 2025-10-07 | BOQ-PKG-01-01101 | PKG-01 | INV-PKG-01-007-05081 | 321.28 | 205458.82 | 10272.94 | Paid | 195185.88 | 2025-Q4
EXP-005158 | 2025-10-07 | BOQ-PKG-08-01178 | PKG-08 | INV-PKG-08-014-05158 | 255.1 | 159640.6 | 7982.03 | Paid | 151658.57 | 2025-Q4
EXP-006035 | 2025-10-07 | BOQ-PKG-05-00065 | PKG-05 | INV-PKG-05-016-06035 | 79.77 | 171806.49 | 8590.32 | Paid | 163216.17 | 2025-Q4
EXP-006477 | 2025-10-07 | BOQ-PKG-07-00507 | PKG-07 | INV-PKG-07-003-06477 | 187.23 | 153519.32 | 7675.97 | Paid | 145843.35 | 2025-Q4
EXP-003791 | 2025-10-08 | BOQ-PKG-01-01801 | PKG-01 | INV-PKG-01-012-03791 | 34.57 | 193943.59 | 9697.18 | Paid | 184246.41 | 2025-Q4
EXP-004582 | 2025-10-08 | BOQ-PKG-02-00602 | PKG-02 | INV-PKG-02-033-04582 | 111.43 | 135978.5 | 6798.92 | Paid | 129179.58 | 2025-Q4
EXP-005111 | 2025-10-08 | BOQ-PKG-01-01131 | PKG-01 | INV-PKG-01-002-05111 | 160.47 | 81664.96 | 4083.25 | Paid | 77581.71 | 2025-Q4
EXP-005527 | 2025-10-08 | BOQ-PKG-07-01547 | PKG-07 | INV-PKG-07-033-05527 | 164.45 | 27603.5 | 1380.18 | Paid | 26223.32 | 2025-Q4
EXP-000078 | 2025-10-09 | BOQ-PKG-08-00078 | PKG-08 | INV-PKG-08-009-00078 | 40.65 | 103626.92 | 5181.35 | Paid | 98445.57 | 2025-Q4
EXP-000209 | 2025-10-09 | BOQ-PKG-09-00209 | PKG-09 | INV-PKG-09-035-00209 | 198.75 | 205364.16 | 10268.21 | Under Review | 195095.95 | 2025-Q4
EXP-000611 | 2025-10-09 | BOQ-PKG-01-00611 | PKG-01 | INV-PKG-01-017-00611 | 131.51 | 134215.65 | 6710.78 | Paid | 127504.87 | 2025-Q4
EXP-001753 | 2025-10-09 | BOQ-PKG-03-01753 | PKG-03 | INV-PKG-03-004-01753 | 264.31 | 112219.02 | 5610.95 | Under Review | 106608.07 | 2025-Q4
EXP-002984 | 2025-10-09 | BOQ-PKG-04-00994 | PKG-04 | INV-PKG-04-010-02984 | 292.06 | 127835.84 | 6391.79 | Paid | 121444.05 | 2025-Q4
EXP-005004 | 2025-10-09 | BOQ-PKG-04-01024 | PKG-04 | INV-PKG-04-035-05004 | 116.48 | 170651.1 | 8532.56 | Under Review | 162118.54 | 2025-Q4
EXP-005283 | 2025-10-09 | BOQ-PKG-03-01303 | PKG-03 | INV-PKG-03-034-05283 | 404.22 | 129280.55 | 6464.03 | Paid | 122816.52 | 2025-Q4
EXP-000725 | 2025-10-10 | BOQ-PKG-05-00725 | PKG-05 | INV-PKG-05-026-00725 | 83.62 | 136459.56 | 6822.98 | Paid | 129636.58 | 2025-Q4
EXP-001655 | 2025-10-10 | BOQ-PKG-05-01655 | PKG-05 | INV-PKG-05-011-01655 | 351.46 | 169316.31 | 8465.82 | Approved Pending Payment | 160850.49 | 2025-Q4
EXP-001831 | 2025-10-10 | BOQ-PKG-01-01831 | PKG-01 | INV-PKG-01-012-01831 | 86.2 | 137522.71 | 6876.14 | Paid | 130646.57 | 2025-Q4
EXP-002816 | 2025-10-10 | BOQ-PKG-06-00826 | PKG-06 | INV-PKG-06-017-02816 | 400.64 | 102689.2 | 5134.46 | Paid | 97554.74 | 2025-Q4
EXP-003918 | 2025-10-10 | BOQ-PKG-08-01928 | PKG-08 | INV-PKG-08-034-03918 | 435.16 | 98171.48 | 4908.57 | Paid | 93262.91 | 2025-Q4
EXP-004072 | 2025-10-10 | BOQ-PKG-02-00092 | PKG-02 | INV-PKG-02-013-04072 | 110.36 | 108074.56 | 5403.73 | Paid | 102670.83 | 2025-Q4
EXP-005932 | 2025-10-10 | BOQ-PKG-02-01952 | PKG-02 | INV-PKG-02-018-05932 | 230.73 | 186161.83 | 9308.09 | Approved Pending Payment | 176853.74 | 2025-Q4
EXP-006571 | 2025-10-10 | BOQ-PKG-01-00601 | PKG-01 | INV-PKG-01-027-06571 | 105.8 | 55595.05 | 2779.75 | Under Review | 52815.3 | 2025-Q4
EXP-000854 | 2025-10-11 | BOQ-PKG-04-00854 | PKG-04 | INV-PKG-04-015-00854 | 101.18 | 138606.15 | 6930.31 | Approved Pending Payment | 131675.84 | 2025-Q4
EXP-002257 | 2025-10-11 | BOQ-PKG-07-00267 | PKG-07 | INV-PKG-07-018-02257 | 375.36 | 130728.58 | 6536.43 | Paid | 124192.15 | 2025-Q4
EXP-003563 | 2025-10-11 | BOQ-PKG-03-01573 | PKG-03 | INV-PKG-03-029-03563 | 59.12 | 75481.77 | 3774.09 | Under Review | 71707.68 | 2025-Q4
EXP-003722 | 2025-10-11 | BOQ-PKG-02-01732 | PKG-02 | INV-PKG-02-013-03722 | 150.76 | 98261.49 | 4913.07 | Disputed | 93348.42 | 2025-Q4
EXP-004909 | 2025-10-11 | BOQ-PKG-09-00929 | PKG-09 | INV-PKG-09-010-04909 | 350.9 | 152923.07 | 7646.15 | Paid | 145276.92 | 2025-Q4
EXP-005654 | 2025-10-11 | BOQ-PKG-04-01674 | PKG-04 | INV-PKG-04-020-05654 | 411.24 | 150815.25 | 7540.76 | Paid | 143274.49 | 2025-Q4
EXP-006081 | 2025-10-11 | BOQ-PKG-01-00111 | PKG-01 | INV-PKG-01-027-06081 | 95.17 | 186519.53 | 9325.98 | Paid | 177193.55 | 2025-Q4
EXP-000726 | 2025-10-12 | BOQ-PKG-06-00726 | PKG-06 | INV-PKG-06-027-00726 | 88.62 | 138793.5 | 6939.68 | Paid | 131853.82 | 2025-Q4
EXP-001978 | 2025-10-12 | BOQ-PKG-08-01978 | PKG-08 | INV-PKG-08-019-01978 | 360.44 | 72609.23 | 3630.46 | Paid | 68978.77 | 2025-Q4
EXP-002221 | 2025-10-12 | BOQ-PKG-01-00231 | PKG-01 | INV-PKG-01-017-02221 | 214.1 | 92731.88 | 4636.59 | Paid | 88095.29 | 2025-Q4
EXP-002489 | 2025-10-12 | BOQ-PKG-09-00499 | PKG-09 | INV-PKG-09-005-02489 | 119.72 | 70872.44 | 3543.62 | Paid | 67328.82 | 2025-Q4
EXP-002579 | 2025-10-12 | BOQ-PKG-09-00589 | PKG-09 | INV-PKG-09-025-02579 | 406 | 27659.04 | 1382.95 | Paid | 26276.09 | 2025-Q4
EXP-002634 | 2025-10-12 | BOQ-PKG-04-00644 | PKG-04 | INV-PKG-04-010-02634 | 331.16 | 66977.47 | 3348.87 | Paid | 63628.6 | 2025-Q4
EXP-003503 | 2025-10-12 | BOQ-PKG-03-01513 | PKG-03 | INV-PKG-03-004-03503 | 351.82 | 165109.89 | 8255.49 | Approved Pending Payment | 156854.4 | 2025-Q4
EXP-003825 | 2025-10-12 | BOQ-PKG-05-01835 | PKG-05 | INV-PKG-05-011-03825 | 118.2 | 159859.81 | 7992.99 | Paid | 151866.82 | 2025-Q4
EXP-003934 | 2025-10-12 | BOQ-PKG-04-01944 | PKG-04 | INV-PKG-04-015-03934 | 343.1 | 46060.04 | 2303 | Paid | 43757.04 | 2025-Q4
EXP-004067 | 2025-10-12 | BOQ-PKG-07-00087 | PKG-07 | INV-PKG-07-008-04067 | 222.93 | 103812.86 | 5190.64 | Paid | 98622.22 | 2025-Q4
EXP-004840 | 2025-10-12 | BOQ-PKG-10-00860 | PKG-10 | INV-PKG-10-011-04840 | 379.53 | 65915.56 | 3295.78 | Paid | 62619.78 | 2025-Q4
EXP-005602 | 2025-10-12 | BOQ-PKG-02-01622 | PKG-02 | INV-PKG-02-003-05602 | 445.29 | 177565.37 | 8878.27 | Paid | 168687.1 | 2025-Q4
EXP-000011 | 2025-10-13 | BOQ-PKG-01-00011 | PKG-01 | INV-PKG-01-012-00011 | 125.44 | 40612.86 | 2030.64 | Paid | 38582.22 | 2025-Q4
EXP-001434 | 2025-10-13 | BOQ-PKG-04-01434 | PKG-04 | INV-PKG-04-035-01434 | 213.83 | 91199.33 | 4559.97 | Approved Pending Payment | 86639.36 | 2025-Q4
EXP-002314 | 2025-10-13 | BOQ-PKG-04-00324 | PKG-04 | INV-PKG-04-005-02314 | 291.42 | 66844.4 | 3342.22 | Approved Pending Payment | 63502.18 | 2025-Q4
EXP-002837 | 2025-10-13 | BOQ-PKG-07-00847 | PKG-07 | INV-PKG-07-003-02837 | 330.62 | 179406.57 | 8970.33 | Paid | 170436.24 | 2025-Q4
EXP-002860 | 2025-10-13 | BOQ-PKG-10-00870 | PKG-10 | INV-PKG-10-026-02860 | 71.32 | 85393.15 | 4269.66 | Paid | 81123.49 | 2025-Q4
EXP-003423 | 2025-10-13 | BOQ-PKG-03-01433 | PKG-03 | INV-PKG-03-029-03423 | 91.54 | 61143.04 | 3057.15 | Under Review | 58085.89 | 2025-Q4
EXP-003753 | 2025-10-13 | BOQ-PKG-03-01763 | PKG-03 | INV-PKG-03-009-03753 | 49.03 | 149221.77 | 7461.09 | Paid | 141760.68 | 2025-Q4
EXP-006127 | 2025-10-13 | BOQ-PKG-07-00157 | PKG-07 | INV-PKG-07-003-06127 | 142.96 | 151521.67 | 7576.08 | Approved Pending Payment | 143945.59 | 2025-Q4
EXP-000721 | 2025-10-14 | BOQ-PKG-01-00721 | PKG-01 | INV-PKG-01-022-00721 | 180.48 | 23457.98 | 1172.9 | Paid | 22285.08 | 2025-Q4
EXP-001134 | 2025-10-14 | BOQ-PKG-04-01134 | PKG-04 | INV-PKG-04-015-01134 | 353.17 | 123901.03 | 6195.05 | Paid | 117705.98 | 2025-Q4
EXP-002686 | 2025-10-14 | BOQ-PKG-06-00696 | PKG-06 | INV-PKG-06-027-02686 | 134.9 | 111848.36 | 5592.42 | Paid | 106255.94 | 2025-Q4
EXP-003170 | 2025-10-14 | BOQ-PKG-10-01180 | PKG-10 | INV-PKG-10-021-03170 | 121.25 | 87442.73 | 4372.14 | Paid | 83070.59 | 2025-Q4
EXP-004535 | 2025-10-14 | BOQ-PKG-05-00555 | PKG-05 | INV-PKG-05-021-04535 | 215.72 | 63425.42 | 3171.27 | Paid | 60254.15 | 2025-Q4
EXP-005737 | 2025-10-14 | BOQ-PKG-07-01757 | PKG-07 | INV-PKG-07-033-05737 | 146.05 | 66156.02 | 3307.8 | Paid | 62848.22 | 2025-Q4
EXP-005738 | 2025-10-14 | BOQ-PKG-08-01758 | PKG-08 | INV-PKG-08-034-05738 | 292.1 | 181041.89 | 9052.09 | Paid | 171989.8 | 2025-Q4
EXP-000895 | 2025-10-15 | BOQ-PKG-05-00895 | PKG-05 | INV-PKG-05-021-00895 | 56.18 | 152965.63 | 7648.28 | Under Review | 145317.35 | 2025-Q4
EXP-001182 | 2025-10-15 | BOQ-PKG-02-01182 | PKG-02 | INV-PKG-02-028-01182 | 401.62 | 169725.73 | 8486.29 | Paid | 161239.44 | 2025-Q4
EXP-002242 | 2025-10-15 | BOQ-PKG-02-00252 | PKG-02 | INV-PKG-02-003-02242 | 193.54 | 116648.09 | 5832.4 | Paid | 110815.69 | 2025-Q4
EXP-006826 | 2025-10-15 | BOQ-PKG-06-00856 | PKG-06 | INV-PKG-06-002-06826 | 366.29 | 71776.14 | 3588.81 | Paid | 68187.33 | 2025-Q4
EXP-006985 | 2025-10-15 | BOQ-PKG-05-01015 | PKG-05 | INV-PKG-05-021-06985 | 229.89 | 149179.64 | 7458.98 | Paid | 141720.66 | 2025-Q4
EXP-000679 | 2025-10-16 | BOQ-PKG-09-00679 | PKG-09 | INV-PKG-09-015-00679 | 286.8 | 42861.6 | 2143.08 | Paid | 40718.52 | 2025-Q4
EXP-000931 | 2025-10-16 | BOQ-PKG-01-00931 | PKG-01 | INV-PKG-01-022-00931 | 103.56 | 30218.6 | 1510.93 | Paid | 28707.67 | 2025-Q4
EXP-001073 | 2025-10-16 | BOQ-PKG-03-01073 | PKG-03 | INV-PKG-03-024-01073 | 245.97 | 185135.41 | 9256.77 | Paid | 175878.64 | 2025-Q4
EXP-001583 | 2025-10-16 | BOQ-PKG-03-01583 | PKG-03 | INV-PKG-03-009-01583 | 29.76 | 47075.59 | 2353.78 | Paid | 44721.81 | 2025-Q4
EXP-001812 | 2025-10-16 | BOQ-PKG-02-01812 | PKG-02 | INV-PKG-02-028-01812 | 244.11 | 107990.12 | 5399.51 | Approved Pending Payment | 102590.61 | 2025-Q4
EXP-001854 | 2025-10-16 | BOQ-PKG-04-01854 | PKG-04 | INV-PKG-04-035-01854 | 154.55 | 55988.93 | 2799.45 | Paid | 53189.48 | 2025-Q4
EXP-002814 | 2025-10-16 | BOQ-PKG-04-00824 | PKG-04 | INV-PKG-04-015-02814 | 382.92 | 47975.39 | 2398.77 | Under Review | 45576.62 | 2025-Q4
EXP-003819 | 2025-10-16 | BOQ-PKG-09-01829 | PKG-09 | INV-PKG-09-005-03819 | 179.09 | 100628.32 | 5031.42 | Paid | 95596.9 | 2025-Q4
EXP-003892 | 2025-10-16 | BOQ-PKG-02-01902 | PKG-02 | INV-PKG-02-008-03892 | 64.37 | 81880.33 | 4094.02 | Paid | 77786.31 | 2025-Q4
EXP-005153 | 2025-10-16 | BOQ-PKG-03-01173 | PKG-03 | INV-PKG-03-009-05153 | 368.24 | 153370.16 | 7668.51 | Approved Pending Payment | 145701.65 | 2025-Q4
EXP-006022 | 2025-10-16 | BOQ-PKG-02-00052 | PKG-02 | INV-PKG-02-003-06022 | 341.94 | 83399.33 | 4169.97 | Paid | 79229.36 | 2025-Q4
EXP-000053 | 2025-10-17 | BOQ-PKG-03-00053 | PKG-03 | INV-PKG-03-019-00053 | 181.19 | 164546.89 | 8227.34 | Paid | 156319.55 | 2025-Q4
EXP-000722 | 2025-10-17 | BOQ-PKG-02-00722 | PKG-02 | INV-PKG-02-023-00722 | 190.76 | 160639.02 | 8031.95 | Paid | 152607.07 | 2025-Q4
EXP-001847 | 2025-10-17 | BOQ-PKG-07-01847 | PKG-07 | INV-PKG-07-028-01847 | 80.75 | 61352.08 | 3067.6 | Paid | 58284.48 | 2025-Q4
EXP-003703 | 2025-10-17 | BOQ-PKG-03-01713 | PKG-03 | INV-PKG-03-029-03703 | 134.12 | 189948.65 | 9497.43 | Paid | 180451.22 | 2025-Q4
EXP-004752 | 2025-10-17 | BOQ-PKG-02-00772 | PKG-02 | INV-PKG-02-028-04752 | 150.27 | 125438.04 | 6271.9 | Paid | 119166.14 | 2025-Q4
EXP-005560 | 2025-10-17 | BOQ-PKG-10-01580 | PKG-10 | INV-PKG-10-031-05560 | 47.42 | 59612.36 | 2980.62 | Paid | 56631.74 | 2025-Q4
EXP-006393 | 2025-10-17 | BOQ-PKG-03-00423 | PKG-03 | INV-PKG-03-024-06393 | 57.75 | 150052.82 | 7502.64 | Paid | 142550.18 | 2025-Q4
EXP-000030 | 2025-10-18 | BOQ-PKG-10-00030 | PKG-10 | INV-PKG-10-031-00030 | 307.44 | 197346.03 | 9867.3 | Paid | 187478.73 | 2025-Q4
EXP-003294 | 2025-10-18 | BOQ-PKG-04-01304 | PKG-04 | INV-PKG-04-005-03294 | 45.55 | 51457.57 | 2572.88 | Under Review | 48884.69 | 2025-Q4
EXP-006171 | 2025-10-18 | BOQ-PKG-01-00201 | PKG-01 | INV-PKG-01-012-06171 | 235.81 | 189619.91 | 9481 | Paid | 180138.91 | 2025-Q4
EXP-006612 | 2025-10-18 | BOQ-PKG-02-00642 | PKG-02 | INV-PKG-02-033-06612 | 289.21 | 174797.78 | 8739.89 | Under Review | 166057.89 | 2025-Q4
EXP-006905 | 2025-10-18 | BOQ-PKG-05-00935 | PKG-05 | INV-PKG-05-011-06905 | 25.97 | 146864.4 | 7343.22 | Disputed | 139521.18 | 2025-Q4
EXP-000091 | 2025-10-19 | BOQ-PKG-01-00091 | PKG-01 | INV-PKG-01-022-00091 | 248.38 | 116369.94 | 5818.5 | Paid | 110551.44 | 2025-Q4
EXP-003010 | 2025-10-19 | BOQ-PKG-10-01020 | PKG-10 | INV-PKG-10-001-03010 | 96.09 | 135345.1 | 6767.26 | Paid | 128577.84 | 2025-Q4
EXP-004424 | 2025-10-19 | BOQ-PKG-04-00444 | PKG-04 | INV-PKG-04-015-04424 | 231.85 | 198413.35 | 9920.67 | Paid | 188492.68 | 2025-Q4
EXP-005893 | 2025-10-19 | BOQ-PKG-03-01913 | PKG-03 | INV-PKG-03-014-05893 | 237.15 | 45820.2 | 2291.01 | Paid | 43529.19 | 2025-Q4
EXP-006262 | 2025-10-19 | BOQ-PKG-02-00292 | PKG-02 | INV-PKG-02-033-06262 | 94.23 | 36167.85 | 1808.39 | Paid | 34359.46 | 2025-Q4
EXP-000702 | 2025-10-20 | BOQ-PKG-02-00702 | PKG-02 | INV-PKG-02-003-00702 | 192.3 | 205028.24 | 10251.41 | Approved Pending Payment | 194776.83 | 2025-Q4
EXP-000744 | 2025-10-20 | BOQ-PKG-04-00744 | PKG-04 | INV-PKG-04-010-00744 | 189.42 | 150816.24 | 7540.81 | Paid | 143275.43 | 2025-Q4
EXP-001249 | 2025-10-20 | BOQ-PKG-09-01249 | PKG-09 | INV-PKG-09-025-01249 | 327.67 | 200290.06 | 10014.5 | Paid | 190275.56 | 2025-Q4
EXP-001349 | 2025-10-20 | BOQ-PKG-09-01349 | PKG-09 | INV-PKG-09-020-01349 | 107.83 | 122588.95 | 6129.45 | Paid | 116459.5 | 2025-Q4
EXP-001914 | 2025-10-20 | BOQ-PKG-04-01914 | PKG-04 | INV-PKG-04-025-01914 | 264.24 | 130758.31 | 6537.92 | Paid | 124220.39 | 2025-Q4
EXP-002574 | 2025-10-20 | BOQ-PKG-04-00584 | PKG-04 | INV-PKG-04-020-02574 | 363.85 | 145642.07 | 7282.1 | Paid | 138359.97 | 2025-Q4
EXP-002914 | 2025-10-20 | BOQ-PKG-04-00924 | PKG-04 | INV-PKG-04-010-02914 | 211.21 | 108594.4 | 5429.72 | Paid | 103164.68 | 2025-Q4
EXP-004275 | 2025-10-20 | BOQ-PKG-05-00295 | PKG-05 | INV-PKG-05-006-04275 | 400.78 | 153736.43 | 7686.82 | Paid | 146049.61 | 2025-Q4
EXP-005117 | 2025-10-20 | BOQ-PKG-07-01137 | PKG-07 | INV-PKG-07-008-05117 | 123.29 | 176777.15 | 8838.86 | Under Review | 167938.29 | 2025-Q4
EXP-005975 | 2025-10-20 | BOQ-PKG-05-00005 | PKG-05 | INV-PKG-05-026-05975 | 443.24 | 108318.21 | 5415.91 | Paid | 102902.3 | 2025-Q4
EXP-000916 | 2025-10-21 | BOQ-PKG-06-00916 | PKG-06 | INV-PKG-06-007-00916 | 34.86 | 137661.89 | 6883.09 | Approved Pending Payment | 130778.8 | 2025-Q4
EXP-001241 | 2025-10-21 | BOQ-PKG-01-01241 | PKG-01 | INV-PKG-01-017-01241 | 214.37 | 95426.74 | 4771.34 | Paid | 90655.4 | 2025-Q4
EXP-002368 | 2025-10-21 | BOQ-PKG-08-00378 | PKG-08 | INV-PKG-08-024-02368 | 322.27 | 191809.47 | 9590.47 | Paid | 182219 | 2025-Q4
EXP-002784 | 2025-10-21 | BOQ-PKG-04-00794 | PKG-04 | INV-PKG-04-020-02784 | 51.68 | 187015.15 | 9350.76 | Paid | 177664.39 | 2025-Q4
EXP-002993 | 2025-10-21 | BOQ-PKG-03-01003 | PKG-03 | INV-PKG-03-019-02993 | 47.35 | 104086.56 | 5204.33 | Paid | 98882.23 | 2025-Q4
EXP-003930 | 2025-10-21 | BOQ-PKG-10-01940 | PKG-10 | INV-PKG-10-011-03930 | 317.72 | 203373.91 | 10168.7 | Paid | 193205.21 | 2025-Q4
EXP-004198 | 2025-10-21 | BOQ-PKG-08-00218 | PKG-08 | INV-PKG-08-034-04198 | 106.53 | 71663.41 | 3583.17 | Paid | 68080.24 | 2025-Q4
EXP-006096 | 2025-10-21 | BOQ-PKG-06-00126 | PKG-06 | INV-PKG-06-007-06096 | 308.42 | 139917.05 | 6995.85 | Paid | 132921.2 | 2025-Q4
EXP-006988 | 2025-10-21 | BOQ-PKG-08-01018 | PKG-08 | INV-PKG-08-024-06988 | 222.71 | 93106.12 | 4655.31 | Paid | 88450.81 | 2025-Q4
EXP-001394 | 2025-10-22 | BOQ-PKG-04-01394 | PKG-04 | INV-PKG-04-030-01394 | 30.87 | 193124.39 | 9656.22 | Disputed | 183468.17 | 2025-Q4
EXP-001761 | 2025-10-22 | BOQ-PKG-01-01761 | PKG-01 | INV-PKG-01-012-01761 | 404.29 | 48397.72 | 2419.89 | Paid | 45977.83 | 2025-Q4
EXP-002236 | 2025-10-22 | BOQ-PKG-06-00246 | PKG-06 | INV-PKG-06-032-02236 | 115.12 | 133469.83 | 6673.49 | Paid | 126796.34 | 2025-Q4
EXP-003701 | 2025-10-22 | BOQ-PKG-01-01711 | PKG-01 | INV-PKG-01-027-03701 | 180.37 | 166223.87 | 8311.19 | Paid | 157912.68 | 2025-Q4
EXP-004640 | 2025-10-22 | BOQ-PKG-10-00660 | PKG-10 | INV-PKG-10-021-04640 | 427.72 | 74510.08 | 3725.5 | Approved Pending Payment | 70784.58 | 2025-Q4
EXP-005173 | 2025-10-22 | BOQ-PKG-03-01193 | PKG-03 | INV-PKG-03-029-05173 | 208.41 | 116575.7 | 5828.78 | Paid | 110746.92 | 2025-Q4
EXP-005615 | 2025-10-22 | BOQ-PKG-05-01635 | PKG-05 | INV-PKG-05-016-05615 | 189.08 | 142027.89 | 7101.39 | Paid | 134926.5 | 2025-Q4
EXP-006146 | 2025-10-22 | BOQ-PKG-06-00176 | PKG-06 | INV-PKG-06-022-06146 | 133.58 | 37833.37 | 1891.67 | Paid | 35941.7 | 2025-Q4
EXP-006229 | 2025-10-22 | BOQ-PKG-09-00259 | PKG-09 | INV-PKG-09-035-06229 | 245.89 | 142271.76 | 7113.59 | Paid | 135158.17 | 2025-Q4
EXP-006893 | 2025-10-22 | BOQ-PKG-03-00923 | PKG-03 | INV-PKG-03-034-06893 | 109.86 | 72063.76 | 3603.19 | Paid | 68460.57 | 2025-Q4
EXP-006958 | 2025-10-22 | BOQ-PKG-08-00988 | PKG-08 | INV-PKG-08-029-06958 | 205.6 | 181197.85 | 9059.89 | Under Review | 172137.96 | 2025-Q4
EXP-001257 | 2025-10-23 | BOQ-PKG-07-01257 | PKG-07 | INV-PKG-07-033-01257 | 307.65 | 154020.85 | 7701.04 | Approved Pending Payment | 146319.81 | 2025-Q4
EXP-001640 | 2025-10-23 | BOQ-PKG-10-01640 | PKG-10 | INV-PKG-10-031-01640 | 21.91 | 136834.04 | 6841.7 | Paid | 129992.34 | 2025-Q4
EXP-001869 | 2025-10-23 | BOQ-PKG-09-01869 | PKG-09 | INV-PKG-09-015-01869 | 155.87 | 130088.74 | 6504.44 | Paid | 123584.3 | 2025-Q4
EXP-002567 | 2025-10-23 | BOQ-PKG-07-00577 | PKG-07 | INV-PKG-07-013-02567 | 310.59 | 191151.32 | 9557.57 | Paid | 181593.75 | 2025-Q4
EXP-002706 | 2025-10-23 | BOQ-PKG-06-00716 | PKG-06 | INV-PKG-06-012-02706 | 229.97 | 149623.12 | 7481.16 | Approved Pending Payment | 142141.96 | 2025-Q4
EXP-002905 | 2025-10-23 | BOQ-PKG-05-00915 | PKG-05 | INV-PKG-05-001-02905 | 170.84 | 159665.48 | 7983.27 | Paid | 151682.21 | 2025-Q4
EXP-005168 | 2025-10-23 | BOQ-PKG-08-01188 | PKG-08 | INV-PKG-08-024-05168 | 87.04 | 94399.62 | 4719.98 | Paid | 89679.64 | 2025-Q4
EXP-006049 | 2025-10-23 | BOQ-PKG-09-00079 | PKG-09 | INV-PKG-09-030-06049 | 351.94 | 97589.07 | 4879.45 | Approved Pending Payment | 92709.62 | 2025-Q4
EXP-000130 | 2025-10-24 | BOQ-PKG-10-00130 | PKG-10 | INV-PKG-10-026-00130 | 152.57 | 118742 | 5937.1 | Paid | 112804.9 | 2025-Q4
EXP-000352 | 2025-10-24 | BOQ-PKG-02-00352 | PKG-02 | INV-PKG-02-003-00352 | 284.79 | 70963.53 | 3548.18 | Paid | 67415.35 | 2025-Q4
EXP-001683 | 2025-10-24 | BOQ-PKG-03-01683 | PKG-03 | INV-PKG-03-004-01683 | 423.62 | 152112.09 | 7605.6 | Approved Pending Payment | 144506.49 | 2025-Q4
EXP-003108 | 2025-10-24 | BOQ-PKG-08-01118 | PKG-08 | INV-PKG-08-029-03108 | 381.14 | 25179.38 | 1258.97 | Paid | 23920.41 | 2025-Q4
EXP-004312 | 2025-10-24 | BOQ-PKG-02-00332 | PKG-02 | INV-PKG-02-008-04312 | 307.72 | 142882.3 | 7144.12 | Paid | 135738.18 | 2025-Q4
EXP-004739 | 2025-10-24 | BOQ-PKG-09-00759 | PKG-09 | INV-PKG-09-015-04739 | 372.49 | 159397.69 | 7969.88 | Under Review | 151427.81 | 2025-Q4
EXP-005603 | 2025-10-24 | BOQ-PKG-03-01623 | PKG-03 | INV-PKG-03-004-05603 | 267.65 | 139705.81 | 6985.29 | Paid | 132720.52 | 2025-Q4
EXP-005704 | 2025-10-24 | BOQ-PKG-04-01724 | PKG-04 | INV-PKG-04-035-05704 | 128.91 | 34653.66 | 1732.68 | Paid | 32920.98 | 2025-Q4
EXP-005713 | 2025-10-24 | BOQ-PKG-03-01733 | PKG-03 | INV-PKG-03-009-05713 | 49.06 | 61189.24 | 3059.46 | Paid | 58129.78 | 2025-Q4
EXP-006002 | 2025-10-24 | BOQ-PKG-02-00032 | PKG-02 | INV-PKG-02-018-06002 | 229.45 | 195186.34 | 9759.32 | Approved Pending Payment | 185427.02 | 2025-Q4
EXP-006938 | 2025-10-24 | BOQ-PKG-08-00968 | PKG-08 | INV-PKG-08-009-06938 | 171.61 | 190552.07 | 9527.6 | Paid | 181024.47 | 2025-Q4
EXP-006996 | 2025-10-24 | BOQ-PKG-06-01026 | PKG-06 | INV-PKG-06-032-06996 | 149.82 | 188043.67 | 9402.18 | Approved Pending Payment | 178641.49 | 2025-Q4
EXP-000485 | 2025-10-25 | BOQ-PKG-05-00485 | PKG-05 | INV-PKG-05-031-00485 | 397.69 | 63746.88 | 3187.34 | Paid | 60559.54 | 2025-Q4
EXP-001097 | 2025-10-25 | BOQ-PKG-07-01097 | PKG-07 | INV-PKG-07-013-01097 | 13.76 | 161127.14 | 8056.36 | Approved Pending Payment | 153070.78 | 2025-Q4
EXP-002442 | 2025-10-25 | BOQ-PKG-02-00452 | PKG-02 | INV-PKG-02-028-02442 | 143.94 | 196355.18 | 9817.76 | Paid | 186537.42 | 2025-Q4
EXP-002490 | 2025-10-25 | BOQ-PKG-10-00500 | PKG-10 | INV-PKG-10-006-02490 | 124.9 | 135130.57 | 6756.53 | Paid | 128374.04 | 2025-Q4
EXP-003053 | 2025-10-25 | BOQ-PKG-03-01063 | PKG-03 | INV-PKG-03-009-03053 | 12.85 | 125473.23 | 6273.66 | Disputed | 119199.57 | 2025-Q4
EXP-004110 | 2025-10-25 | BOQ-PKG-10-00130 | PKG-10 | INV-PKG-10-016-04110 | 99.06 | 30488.94 | 1524.45 | Disputed | 28964.49 | 2025-Q4
EXP-005045 | 2025-10-25 | BOQ-PKG-05-01065 | PKG-05 | INV-PKG-05-006-05045 | 361.18 | 57593.5 | 2879.68 | Paid | 54713.82 | 2025-Q4
EXP-005097 | 2025-10-25 | BOQ-PKG-07-01117 | PKG-07 | INV-PKG-07-023-05097 | 55.13 | 108479.24 | 5423.96 | Paid | 103055.28 | 2025-Q4
EXP-005683 | 2025-10-25 | BOQ-PKG-03-01703 | PKG-03 | INV-PKG-03-014-05683 | 207.13 | 181466.18 | 9073.31 | Approved Pending Payment | 172392.87 | 2025-Q4
EXP-006648 | 2025-10-25 | BOQ-PKG-08-00678 | PKG-08 | INV-PKG-08-034-06648 | 78.69 | 120851.31 | 6042.57 | Paid | 114808.74 | 2025-Q4
EXP-000086 | 2025-10-26 | BOQ-PKG-06-00086 | PKG-06 | INV-PKG-06-017-00086 | 427.3 | 50087.88 | 2504.39 | Paid | 47583.49 | 2025-Q4
EXP-000404 | 2025-10-26 | BOQ-PKG-04-00404 | PKG-04 | INV-PKG-04-020-00404 | 228.93 | 166608.18 | 8330.41 | Paid | 158277.77 | 2025-Q4
EXP-002183 | 2025-10-26 | BOQ-PKG-03-00193 | PKG-03 | INV-PKG-03-014-02183 | 213.21 | 42215.54 | 2110.78 | Paid | 40104.76 | 2025-Q4
EXP-003136 | 2025-10-26 | BOQ-PKG-06-01146 | PKG-06 | INV-PKG-06-022-03136 | 204.69 | 190431.19 | 9521.56 | Paid | 180909.63 | 2025-Q4
EXP-003145 | 2025-10-26 | BOQ-PKG-05-01155 | PKG-05 | INV-PKG-05-031-03145 | 212.64 | 87616.87 | 4380.84 | Disputed | 83236.03 | 2025-Q4
EXP-004865 | 2025-10-26 | BOQ-PKG-05-00885 | PKG-05 | INV-PKG-05-001-04865 | 374.73 | 84239.43 | 4211.97 | Approved Pending Payment | 80027.46 | 2025-Q4
EXP-001509 | 2025-10-27 | BOQ-PKG-09-01509 | PKG-09 | INV-PKG-09-005-01509 | 12.96 | 62142.18 | 3107.11 | Paid | 59035.07 | 2025-Q4
EXP-002598 | 2025-10-27 | BOQ-PKG-08-00608 | PKG-08 | INV-PKG-08-009-02598 | 242.63 | 69482.7 | 3474.14 | Paid | 66008.56 | 2025-Q4
EXP-003961 | 2025-10-27 | BOQ-PKG-01-01971 | PKG-01 | INV-PKG-01-007-03961 | 111.23 | 183147.12 | 9157.36 | Paid | 173989.76 | 2025-Q4
EXP-004005 | 2025-10-27 | BOQ-PKG-05-00025 | PKG-05 | INV-PKG-05-016-04005 | 213.07 | 35464.34 | 1773.22 | Disputed | 33691.12 | 2025-Q4
EXP-004504 | 2025-10-27 | BOQ-PKG-04-00524 | PKG-04 | INV-PKG-04-025-04504 | 174.77 | 48969.6 | 2448.48 | Under Review | 46521.12 | 2025-Q4
EXP-005871 | 2025-10-27 | BOQ-PKG-01-01891 | PKG-01 | INV-PKG-01-027-05871 | 311.06 | 165024.03 | 8251.2 | Under Review | 156772.83 | 2025-Q4
EXP-006514 | 2025-10-27 | BOQ-PKG-04-00544 | PKG-04 | INV-PKG-04-005-06514 | 385.6 | 160903.8 | 8045.19 | Paid | 152858.61 | 2025-Q4
EXP-000299 | 2025-10-28 | BOQ-PKG-09-00299 | PKG-09 | INV-PKG-09-020-00299 | 144.21 | 35866.8 | 1793.34 | Paid | 34073.46 | 2025-Q4
EXP-001085 | 2025-10-28 | BOQ-PKG-05-01085 | PKG-05 | INV-PKG-05-001-01085 | 135.83 | 126473.1 | 6323.66 | Paid | 120149.44 | 2025-Q4
EXP-003425 | 2025-10-28 | BOQ-PKG-05-01435 | PKG-05 | INV-PKG-05-031-03425 | 31.02 | 102766.49 | 5138.32 | Paid | 97628.17 | 2025-Q4
EXP-003434 | 2025-10-28 | BOQ-PKG-04-01444 | PKG-04 | INV-PKG-04-005-03434 | 180.11 | 174692.39 | 8734.62 | Paid | 165957.77 | 2025-Q4
EXP-003958 | 2025-10-28 | BOQ-PKG-08-01968 | PKG-08 | INV-PKG-08-004-03958 | 387.41 | 99036.13 | 4951.81 | Paid | 94084.32 | 2025-Q4
EXP-004367 | 2025-10-28 | BOQ-PKG-07-00387 | PKG-07 | INV-PKG-07-028-04367 | 397.01 | 85186.34 | 4259.32 | Approved Pending Payment | 80927.02 | 2025-Q4
EXP-005006 | 2025-10-28 | BOQ-PKG-06-01026 | PKG-06 | INV-PKG-06-002-05006 | 223.46 | 145722.82 | 7286.14 | Paid | 138436.68 | 2025-Q4
EXP-005990 | 2025-10-28 | BOQ-PKG-10-00020 | PKG-10 | INV-PKG-10-006-05990 | 415.82 | 166773.22 | 8338.66 | Paid | 158434.56 | 2025-Q4
EXP-006232 | 2025-10-28 | BOQ-PKG-02-00262 | PKG-02 | INV-PKG-02-003-06232 | 433.53 | 78713.62 | 3935.68 | Approved Pending Payment | 74777.94 | 2025-Q4
EXP-006355 | 2025-10-28 | BOQ-PKG-05-00385 | PKG-05 | INV-PKG-05-021-06355 | 196.16 | 144605.1 | 7230.26 | Paid | 137374.84 | 2025-Q4
EXP-006926 | 2025-10-28 | BOQ-PKG-06-00956 | PKG-06 | INV-PKG-06-032-06926 | 337.39 | 80758.01 | 4037.9 | Paid | 76720.11 | 2025-Q4
EXP-000287 | 2025-10-29 | BOQ-PKG-07-00287 | PKG-07 | INV-PKG-07-008-00287 | 126.7 | 155776.54 | 7788.83 | Paid | 147987.71 | 2025-Q4
EXP-001154 | 2025-10-29 | BOQ-PKG-04-01154 | PKG-04 | INV-PKG-04-035-01154 | 357.64 | 78268.16 | 3913.41 | Under Review | 74354.75 | 2025-Q4
EXP-005075 | 2025-10-29 | BOQ-PKG-05-01095 | PKG-05 | INV-PKG-05-001-05075 | 341.81 | 63219.92 | 3161 | Paid | 60058.92 | 2025-Q4
EXP-005745 | 2025-10-29 | BOQ-PKG-05-01765 | PKG-05 | INV-PKG-05-006-05745 | 211.32 | 163051.87 | 8152.59 | Paid | 154899.28 | 2025-Q4
EXP-006266 | 2025-10-29 | BOQ-PKG-06-00296 | PKG-06 | INV-PKG-06-002-06266 | 445.21 | 143167.61 | 7158.38 | Paid | 136009.23 | 2025-Q4
EXP-006567 | 2025-10-29 | BOQ-PKG-07-00597 | PKG-07 | INV-PKG-07-023-06567 | 93.88 | 170557.48 | 8527.87 | Paid | 162029.61 | 2025-Q4
EXP-000734 | 2025-10-30 | BOQ-PKG-04-00734 | PKG-04 | INV-PKG-04-035-00734 | 233.98 | 60442.41 | 3022.12 | Paid | 57420.29 | 2025-Q4
EXP-000894 | 2025-10-30 | BOQ-PKG-04-00894 | PKG-04 | INV-PKG-04-020-00894 | 256.46 | 178741.3 | 8937.06 | Approved Pending Payment | 169804.24 | 2025-Q4
EXP-001806 | 2025-10-30 | BOQ-PKG-06-01806 | PKG-06 | INV-PKG-06-022-01806 | 441.34 | 198807.81 | 9940.39 | Paid | 188867.42 | 2025-Q4
EXP-002062 | 2025-10-30 | BOQ-PKG-02-00072 | PKG-02 | INV-PKG-02-033-02062 | 36.02 | 188497 | 9424.85 | Paid | 179072.15 | 2025-Q4
EXP-002418 | 2025-10-30 | BOQ-PKG-08-00428 | PKG-08 | INV-PKG-08-004-02418 | 37.93 | 59920.53 | 2996.03 | Paid | 56924.5 | 2025-Q4
EXP-005196 | 2025-10-30 | BOQ-PKG-06-01216 | PKG-06 | INV-PKG-06-017-05196 | 14.73 | 189653.96 | 9482.7 | Paid | 180171.26 | 2025-Q4
EXP-005734 | 2025-10-30 | BOQ-PKG-04-01754 | PKG-04 | INV-PKG-04-030-05734 | 148.99 | 52388.53 | 2619.43 | Paid | 49769.1 | 2025-Q4
EXP-006083 | 2025-10-30 | BOQ-PKG-03-00113 | PKG-03 | INV-PKG-03-029-06083 | 394.49 | 43364.71 | 2168.24 | Paid | 41196.47 | 2025-Q4
EXP-006412 | 2025-10-30 | BOQ-PKG-02-00442 | PKG-02 | INV-PKG-02-008-06412 | 234.21 | 83257.98 | 4162.9 | Under Review | 79095.08 | 2025-Q4
EXP-000982 | 2025-10-31 | BOQ-PKG-02-00982 | PKG-02 | INV-PKG-02-003-00982 | 327.57 | 152000.27 | 7600.01 | Paid | 144400.26 | 2025-Q4
EXP-001591 | 2025-10-31 | BOQ-PKG-01-01591 | PKG-01 | INV-PKG-01-017-01591 | 256.68 | 37390.17 | 1869.51 | Paid | 35520.66 | 2025-Q4
EXP-003368 | 2025-10-31 | BOQ-PKG-08-01378 | PKG-08 | INV-PKG-08-009-03368 | 218.17 | 80077.13 | 4003.86 | Paid | 76073.27 | 2025-Q4
EXP-005413 | 2025-10-31 | BOQ-PKG-03-01433 | PKG-03 | INV-PKG-03-024-05413 | 107.81 | 207540.96 | 10377.05 | Paid | 197163.91 | 2025-Q4
EXP-005451 | 2025-10-31 | BOQ-PKG-01-01471 | PKG-01 | INV-PKG-01-027-05451 | 273.1 | 52000.29 | 2600.01 | Paid | 49400.28 | 2025-Q4
EXP-006423 | 2025-10-31 | BOQ-PKG-03-00453 | PKG-03 | INV-PKG-03-019-06423 | 386.7 | 49258.74 | 2462.94 | Paid | 46795.8 | 2025-Q4
EXP-006671 | 2025-10-31 | BOQ-PKG-01-00701 | PKG-01 | INV-PKG-01-022-06671 | 144.06 | 161961.81 | 8098.09 | Paid | 153863.72 | 2025-Q4
EXP-003985 | 2025-11-01 | BOQ-PKG-05-00005 | PKG-05 | INV-PKG-05-031-03985 | 419.53 | 44378.14 | 2218.91 | Paid | 42159.23 | 2025-Q4
EXP-004774 | 2025-11-01 | BOQ-PKG-04-00794 | PKG-04 | INV-PKG-04-015-04774 | 14.55 | 52944.74 | 2647.24 | Paid | 50297.5 | 2025-Q4
EXP-006150 | 2025-11-01 | BOQ-PKG-10-00180 | PKG-10 | INV-PKG-10-026-06150 | 54.6 | 117021.93 | 5851.1 | Paid | 111170.83 | 2025-Q4
EXP-000021 | 2025-11-02 | BOQ-PKG-01-00021 | PKG-01 | INV-PKG-01-022-00021 | 108.83 | 143417.37 | 7170.87 | Paid | 136246.5 | 2025-Q4
EXP-000354 | 2025-11-02 | BOQ-PKG-04-00354 | PKG-04 | INV-PKG-04-005-00354 | 305.06 | 214777.49 | 10738.87 | Paid | 204038.62 | 2025-Q4
EXP-001401 | 2025-11-02 | BOQ-PKG-01-01401 | PKG-01 | INV-PKG-01-002-01401 | 268.52 | 185893.87 | 9294.69 | Paid | 176599.18 | 2025-Q4
EXP-002218 | 2025-11-02 | BOQ-PKG-08-00228 | PKG-08 | INV-PKG-08-014-02218 | 17.92 | 135357.69 | 6767.88 | Under Review | 128589.81 | 2025-Q4
EXP-004722 | 2025-11-02 | BOQ-PKG-02-00742 | PKG-02 | INV-PKG-02-033-04722 | 369.44 | 167583.33 | 8379.17 | Under Review | 159204.16 | 2025-Q4
EXP-005754 | 2025-11-02 | BOQ-PKG-04-01774 | PKG-04 | INV-PKG-04-015-05754 | 113.87 | 198026.48 | 9901.32 | Paid | 188125.16 | 2025-Q4
EXP-005759 | 2025-11-02 | BOQ-PKG-09-01779 | PKG-09 | INV-PKG-09-020-05759 | 296.51 | 45119.14 | 2255.96 | Under Review | 42863.18 | 2025-Q4
EXP-005909 | 2025-11-02 | BOQ-PKG-09-01929 | PKG-09 | INV-PKG-09-030-05909 | 51.9 | 101502.6 | 5075.13 | Paid | 96427.47 | 2025-Q4
EXP-006371 | 2025-11-02 | BOQ-PKG-01-00401 | PKG-01 | INV-PKG-01-002-06371 | 267.8 | 168812.74 | 8440.64 | Under Review | 160372.1 | 2025-Q4
EXP-002839 | 2025-11-03 | BOQ-PKG-09-00849 | PKG-09 | INV-PKG-09-005-02839 | 416.51 | 55432.03 | 2771.6 | Under Review | 52660.43 | 2025-Q4
EXP-003504 | 2025-11-03 | BOQ-PKG-04-01514 | PKG-04 | INV-PKG-04-005-03504 | 121.48 | 191668.43 | 9583.42 | Under Review | 182085.01 | 2025-Q4
EXP-003781 | 2025-11-03 | BOQ-PKG-01-01791 | PKG-01 | INV-PKG-01-002-03781 | 310.64 | 123519.58 | 6175.98 | Disputed | 117343.6 | 2025-Q4
EXP-006549 | 2025-11-03 | BOQ-PKG-09-00579 | PKG-09 | INV-PKG-09-005-06549 | 154.62 | 137896.86 | 6894.84 | Paid | 131002.02 | 2025-Q4
EXP-006987 | 2025-11-03 | BOQ-PKG-07-01017 | PKG-07 | INV-PKG-07-023-06987 | 194.34 | 101792.96 | 5089.65 | Paid | 96703.31 | 2025-Q4
EXP-001293 | 2025-11-04 | BOQ-PKG-03-01293 | PKG-03 | INV-PKG-03-034-01293 | 343.01 | 189985.71 | 9499.29 | Paid | 180486.42 | 2025-Q4
EXP-001382 | 2025-11-04 | BOQ-PKG-02-01382 | PKG-02 | INV-PKG-02-018-01382 | 29.69 | 78991.8 | 3949.59 | Paid | 75042.21 | 2025-Q4
EXP-001557 | 2025-11-04 | BOQ-PKG-07-01557 | PKG-07 | INV-PKG-07-018-01557 | 54.75 | 126935.16 | 6346.76 | Paid | 120588.4 | 2025-Q4
EXP-001901 | 2025-11-04 | BOQ-PKG-01-01901 | PKG-01 | INV-PKG-01-012-01901 | 8.6 | 134659.27 | 6732.96 | Approved Pending Payment | 127926.31 | 2025-Q4
EXP-005980 | 2025-11-04 | BOQ-PKG-10-00010 | PKG-10 | INV-PKG-10-031-05980 | 400.62 | 31854.43 | 1592.72 | Paid | 30261.71 | 2025-Q4
EXP-006290 | 2025-11-04 | BOQ-PKG-10-00320 | PKG-10 | INV-PKG-10-026-06290 | 174.92 | 66187.12 | 3309.36 | Paid | 62877.76 | 2025-Q4
EXP-000978 | 2025-11-05 | BOQ-PKG-08-00978 | PKG-08 | INV-PKG-08-034-00978 | 191.01 | 131046.77 | 6552.34 | Paid | 124494.43 | 2025-Q4
EXP-001071 | 2025-11-05 | BOQ-PKG-01-01071 | PKG-01 | INV-PKG-01-022-01071 | 345.77 | 108117.98 | 5405.9 | Paid | 102712.08 | 2025-Q4
EXP-004361 | 2025-11-05 | BOQ-PKG-01-00381 | PKG-01 | INV-PKG-01-022-04361 | 118.16 | 29015.43 | 1450.77 | Paid | 27564.66 | 2025-Q4
EXP-004667 | 2025-11-05 | BOQ-PKG-07-00687 | PKG-07 | INV-PKG-07-013-04667 | 15.86 | 47237.61 | 2361.88 | Paid | 44875.73 | 2025-Q4
EXP-004758 | 2025-11-05 | BOQ-PKG-08-00778 | PKG-08 | INV-PKG-08-034-04758 | 165.52 | 80616.41 | 4030.82 | Paid | 76585.59 | 2025-Q4
EXP-005633 | 2025-11-05 | BOQ-PKG-03-01653 | PKG-03 | INV-PKG-03-034-05633 | 365.61 | 77531.57 | 3876.58 | Approved Pending Payment | 73654.99 | 2025-Q4
EXP-005889 | 2025-11-05 | BOQ-PKG-09-01909 | PKG-09 | INV-PKG-09-010-05889 | 85.43 | 198558.51 | 9927.93 | Paid | 188630.58 | 2025-Q4
EXP-006361 | 2025-11-05 | BOQ-PKG-01-00391 | PKG-01 | INV-PKG-01-027-06361 | 241.89 | 194999.68 | 9749.98 | Paid | 185249.7 | 2025-Q4
EXP-001002 | 2025-11-06 | BOQ-PKG-02-01002 | PKG-02 | INV-PKG-02-023-01002 | 172.34 | 204914.37 | 10245.72 | Paid | 194668.65 | 2025-Q4
EXP-001168 | 2025-11-06 | BOQ-PKG-08-01168 | PKG-08 | INV-PKG-08-014-01168 | 270.23 | 108730.17 | 5436.51 | Paid | 103293.66 | 2025-Q4
EXP-001984 | 2025-11-06 | BOQ-PKG-04-01984 | PKG-04 | INV-PKG-04-025-01984 | 270.55 | 48554.27 | 2427.71 | Paid | 46126.56 | 2025-Q4
EXP-003154 | 2025-11-06 | BOQ-PKG-04-01164 | PKG-04 | INV-PKG-04-005-03154 | 404.9 | 162110.07 | 8105.5 | Paid | 154004.57 | 2025-Q4
EXP-003221 | 2025-11-06 | BOQ-PKG-01-01231 | PKG-01 | INV-PKG-01-002-03221 | 230.71 | 70576.94 | 3528.85 | Paid | 67048.09 | 2025-Q4
EXP-003229 | 2025-11-06 | BOQ-PKG-09-01239 | PKG-09 | INV-PKG-09-010-03229 | 429.18 | 204642.93 | 10232.15 | Paid | 194410.78 | 2025-Q4
EXP-000443 | 2025-11-07 | BOQ-PKG-03-00443 | PKG-03 | INV-PKG-03-024-00443 | 291.05 | 175914.32 | 8795.72 | Paid | 167118.6 | 2025-Q4
EXP-003403 | 2025-11-07 | BOQ-PKG-03-01413 | PKG-03 | INV-PKG-03-009-03403 | 20.17 | 160264.04 | 8013.2 | Paid | 152250.84 | 2025-Q4
EXP-003756 | 2025-11-07 | BOQ-PKG-06-01766 | PKG-06 | INV-PKG-06-012-03756 | 339.22 | 199428.37 | 9971.42 | Paid | 189456.95 | 2025-Q4
EXP-005988 | 2025-11-07 | BOQ-PKG-08-00018 | PKG-08 | INV-PKG-08-004-05988 | 393.58 | 83963.01 | 4198.15 | Paid | 79764.86 | 2025-Q4
EXP-002521 | 2025-11-08 | BOQ-PKG-01-00531 | PKG-01 | INV-PKG-01-002-02521 | 246.61 | 152104.12 | 7605.21 | Paid | 144498.91 | 2025-Q4
EXP-004160 | 2025-11-08 | BOQ-PKG-10-00180 | PKG-10 | INV-PKG-10-031-04160 | 330.86 | 111479.23 | 5573.96 | Paid | 105905.27 | 2025-Q4
EXP-001127 | 2025-11-09 | BOQ-PKG-07-01127 | PKG-07 | INV-PKG-07-008-01127 | 114.59 | 186646.04 | 9332.3 | Disputed | 177313.74 | 2025-Q4
EXP-001255 | 2025-11-09 | BOQ-PKG-05-01255 | PKG-05 | INV-PKG-05-031-01255 | 117.55 | 31257.5 | 1562.88 | Under Review | 29694.62 | 2025-Q4
EXP-002025 | 2025-11-09 | BOQ-PKG-05-00035 | PKG-05 | INV-PKG-05-031-02025 | 332.13 | 76957.7 | 3847.88 | Approved Pending Payment | 73109.82 | 2025-Q4
EXP-002633 | 2025-11-09 | BOQ-PKG-03-00643 | PKG-03 | INV-PKG-03-009-02633 | 431.56 | 136747.87 | 6837.39 | Approved Pending Payment | 129910.48 | 2025-Q4
EXP-003458 | 2025-11-09 | BOQ-PKG-08-01468 | PKG-08 | INV-PKG-08-029-03458 | 44.1 | 162792.04 | 8139.6 | Paid | 154652.44 | 2025-Q4
EXP-004664 | 2025-11-09 | BOQ-PKG-04-00684 | PKG-04 | INV-PKG-04-010-04664 | 319.07 | 158920.71 | 7946.04 | Paid | 150974.67 | 2025-Q4
EXP-005585 | 2025-11-09 | BOQ-PKG-05-01605 | PKG-05 | INV-PKG-05-021-05585 | 89.3 | 134843.69 | 6742.18 | Paid | 128101.51 | 2025-Q4
EXP-005681 | 2025-11-09 | BOQ-PKG-01-01701 | PKG-01 | INV-PKG-01-012-05681 | 18.19 | 152374.03 | 7618.7 | Paid | 144755.33 | 2025-Q4
EXP-006306 | 2025-11-09 | BOQ-PKG-06-00336 | PKG-06 | INV-PKG-06-007-06306 | 370.65 | 34791.88 | 1739.59 | Paid | 33052.29 | 2025-Q4
EXP-001324 | 2025-11-10 | BOQ-PKG-04-01324 | PKG-04 | INV-PKG-04-030-01324 | 248.74 | 133339.19 | 6666.96 | Paid | 126672.23 | 2025-Q4
EXP-003150 | 2025-11-10 | BOQ-PKG-10-01160 | PKG-10 | INV-PKG-10-001-03150 | 61.29 | 34556.51 | 1727.83 | Paid | 32828.68 | 2025-Q4
EXP-003527 | 2025-11-10 | BOQ-PKG-07-01537 | PKG-07 | INV-PKG-07-028-03527 | 412.32 | 41465.4 | 2073.27 | Approved Pending Payment | 39392.13 | 2025-Q4
EXP-004098 | 2025-11-10 | BOQ-PKG-08-00118 | PKG-08 | INV-PKG-08-004-04098 | 264.69 | 39649.9 | 1982.5 | Paid | 37667.4 | 2025-Q4
EXP-005206 | 2025-11-10 | BOQ-PKG-06-01226 | PKG-06 | INV-PKG-06-027-05206 | 372.38 | 101387.11 | 5069.36 | Paid | 96317.75 | 2025-Q4
EXP-005331 | 2025-11-10 | BOQ-PKG-01-01351 | PKG-01 | INV-PKG-01-012-05331 | 287.98 | 46252.09 | 2312.6 | Paid | 43939.49 | 2025-Q4
EXP-006484 | 2025-11-10 | BOQ-PKG-04-00514 | PKG-04 | INV-PKG-04-010-06484 | 223.3 | 68593.57 | 3429.68 | Paid | 65163.89 | 2025-Q4
EXP-000051 | 2025-11-11 | BOQ-PKG-01-00051 | PKG-01 | INV-PKG-01-017-00051 | 252.63 | 93825.3 | 4691.27 | Paid | 89134.03 | 2025-Q4
EXP-000712 | 2025-11-11 | BOQ-PKG-02-00712 | PKG-02 | INV-PKG-02-013-00712 | 356.12 | 88800.85 | 4440.04 | Paid | 84360.81 | 2025-Q4
EXP-002049 | 2025-11-11 | BOQ-PKG-09-00059 | PKG-09 | INV-PKG-09-020-02049 | 443.95 | 106523.84 | 5326.19 | Paid | 101197.65 | 2025-Q4
EXP-003326 | 2025-11-11 | BOQ-PKG-06-01336 | PKG-06 | INV-PKG-06-002-03326 | 12.35 | 52549.27 | 2627.46 | Paid | 49921.81 | 2025-Q4
EXP-005475 | 2025-11-11 | BOQ-PKG-05-01495 | PKG-05 | INV-PKG-05-016-05475 | 429.94 | 161625.4 | 8081.27 | Paid | 153544.13 | 2025-Q4
EXP-006964 | 2025-11-11 | BOQ-PKG-04-00994 | PKG-04 | INV-PKG-04-035-06964 | 116.83 | 175004.63 | 8750.23 | Paid | 166254.4 | 2025-Q4
EXP-000428 | 2025-11-12 | BOQ-PKG-08-00428 | PKG-08 | INV-PKG-08-009-00428 | 298.21 | 204780.21 | 10239.01 | Paid | 194541.2 | 2025-Q4
EXP-001409 | 2025-11-12 | BOQ-PKG-09-01409 | PKG-09 | INV-PKG-09-010-01409 | 23.69 | 193026.94 | 9651.35 | Paid | 183375.59 | 2025-Q4
EXP-002920 | 2025-11-12 | BOQ-PKG-10-00930 | PKG-10 | INV-PKG-10-016-02920 | 313.05 | 106561.15 | 5328.06 | Paid | 101233.09 | 2025-Q4
EXP-003435 | 2025-11-12 | BOQ-PKG-05-01445 | PKG-05 | INV-PKG-05-006-03435 | 418.17 | 154233.18 | 7711.66 | Paid | 146521.52 | 2025-Q4
EXP-003888 | 2025-11-12 | BOQ-PKG-08-01898 | PKG-08 | INV-PKG-08-004-03888 | 385.04 | 202750.62 | 10137.53 | Paid | 192613.09 | 2025-Q4
EXP-004338 | 2025-11-12 | BOQ-PKG-08-00358 | PKG-08 | INV-PKG-08-034-04338 | 82.18 | 112527.97 | 5626.4 | Paid | 106901.57 | 2025-Q4
EXP-004563 | 2025-11-12 | BOQ-PKG-03-00583 | PKG-03 | INV-PKG-03-014-04563 | 294.61 | 41183.51 | 2059.18 | Paid | 39124.33 | 2025-Q4
EXP-006560 | 2025-11-12 | BOQ-PKG-10-00590 | PKG-10 | INV-PKG-10-016-06560 | 352.09 | 175767.13 | 8788.36 | Paid | 166978.77 | 2025-Q4
EXP-006811 | 2025-11-12 | BOQ-PKG-01-00841 | PKG-01 | INV-PKG-01-022-06811 | 348.63 | 45942.23 | 2297.11 | Paid | 43645.12 | 2025-Q4
EXP-000445 | 2025-11-13 | BOQ-PKG-05-00445 | PKG-05 | INV-PKG-05-026-00445 | 184.12 | 198023.98 | 9901.2 | Paid | 188122.78 | 2025-Q4
EXP-000884 | 2025-11-13 | BOQ-PKG-04-00884 | PKG-04 | INV-PKG-04-010-00884 | 267.43 | 110971.88 | 5548.59 | Under Review | 105423.29 | 2025-Q4
EXP-001489 | 2025-11-13 | BOQ-PKG-09-01489 | PKG-09 | INV-PKG-09-020-01489 | 120.75 | 200273.83 | 10013.69 | Approved Pending Payment | 190260.14 | 2025-Q4
EXP-002685 | 2025-11-13 | BOQ-PKG-05-00695 | PKG-05 | INV-PKG-05-026-02685 | 340.25 | 36966.15 | 1848.31 | Approved Pending Payment | 35117.84 | 2025-Q4
EXP-006013 | 2025-11-13 | BOQ-PKG-03-00043 | PKG-03 | INV-PKG-03-029-06013 | 329.53 | 179540.17 | 8977.01 | Disputed | 170563.16 | 2025-Q4
EXP-006841 | 2025-11-13 | BOQ-PKG-01-00871 | PKG-01 | INV-PKG-01-017-06841 | 16.78 | 158689.73 | 7934.49 | Paid | 150755.24 | 2025-Q4
EXP-000677 | 2025-11-14 | BOQ-PKG-07-00677 | PKG-07 | INV-PKG-07-013-00677 | 206.96 | 128295.92 | 6414.8 | Paid | 121881.12 | 2025-Q4
EXP-000900 | 2025-11-14 | BOQ-PKG-10-00900 | PKG-10 | INV-PKG-10-026-00900 | 42.91 | 147066.9 | 7353.34 | Under Review | 139713.56 | 2025-Q4
EXP-001318 | 2025-11-14 | BOQ-PKG-08-01318 | PKG-08 | INV-PKG-08-024-01318 | 383.38 | 108507.86 | 5425.39 | Paid | 103082.47 | 2025-Q4
EXP-002235 | 2025-11-14 | BOQ-PKG-05-00245 | PKG-05 | INV-PKG-05-031-02235 | 383.61 | 197555.76 | 9877.79 | Paid | 187677.97 | 2025-Q4
EXP-003179 | 2025-11-14 | BOQ-PKG-09-01189 | PKG-09 | INV-PKG-09-030-03179 | 41.66 | 89874.46 | 4493.72 | Paid | 85380.74 | 2025-Q4
EXP-004542 | 2025-11-14 | BOQ-PKG-02-00562 | PKG-02 | INV-PKG-02-028-04542 | 446.65 | 95877.6 | 4793.88 | Approved Pending Payment | 91083.72 | 2025-Q4
EXP-004592 | 2025-11-14 | BOQ-PKG-02-00612 | PKG-02 | INV-PKG-02-008-04592 | 332.35 | 175562.93 | 8778.15 | Approved Pending Payment | 166784.78 | 2025-Q4
EXP-006333 | 2025-11-14 | BOQ-PKG-03-00363 | PKG-03 | INV-PKG-03-034-06333 | 352.6 | 149289.68 | 7464.48 | Paid | 141825.2 | 2025-Q4
EXP-001699 | 2025-11-15 | BOQ-PKG-09-01699 | PKG-09 | INV-PKG-09-020-01699 | 307.69 | 77476.14 | 3873.81 | Paid | 73602.33 | 2025-Q4
EXP-002273 | 2025-11-15 | BOQ-PKG-03-00283 | PKG-03 | INV-PKG-03-034-02273 | 180.18 | 71936.45 | 3596.82 | Paid | 68339.63 | 2025-Q4
EXP-003541 | 2025-11-15 | BOQ-PKG-01-01551 | PKG-01 | INV-PKG-01-007-03541 | 369.77 | 141702.42 | 7085.12 | Paid | 134617.3 | 2025-Q4
EXP-004122 | 2025-11-15 | BOQ-PKG-02-00142 | PKG-02 | INV-PKG-02-028-04122 | 139.55 | 32468.17 | 1623.41 | Approved Pending Payment | 30844.76 | 2025-Q4
EXP-004270 | 2025-11-15 | BOQ-PKG-10-00290 | PKG-10 | INV-PKG-10-001-04270 | 26.02 | 37649.27 | 1882.46 | Paid | 35766.81 | 2025-Q4
EXP-005179 | 2025-11-15 | BOQ-PKG-09-01199 | PKG-09 | INV-PKG-09-035-05179 | 63.56 | 107894.97 | 5394.75 | Paid | 102500.22 | 2025-Q4
EXP-005509 | 2025-11-15 | BOQ-PKG-09-01529 | PKG-09 | INV-PKG-09-015-05509 | 187.8 | 156616.66 | 7830.83 | Paid | 148785.83 | 2025-Q4
EXP-000520 | 2025-11-16 | BOQ-PKG-10-00520 | PKG-10 | INV-PKG-10-031-00520 | 414.42 | 73721.99 | 3686.1 | Paid | 70035.89 | 2025-Q4
EXP-001796 | 2025-11-16 | BOQ-PKG-06-01796 | PKG-06 | INV-PKG-06-012-01796 | 438.1 | 188344.06 | 9417.2 | Disputed | 178926.86 | 2025-Q4
EXP-001996 | 2025-11-16 | BOQ-PKG-06-00006 | PKG-06 | INV-PKG-06-002-01996 | 40.49 | 100117.61 | 5005.88 | Paid | 95111.73 | 2025-Q4
EXP-003223 | 2025-11-16 | BOQ-PKG-03-01233 | PKG-03 | INV-PKG-03-004-03223 | 336.41 | 158693.04 | 7934.65 | Paid | 150758.39 | 2025-Q4
EXP-003413 | 2025-11-16 | BOQ-PKG-03-01423 | PKG-03 | INV-PKG-03-019-03413 | 262.42 | 216230.51 | 10811.53 | Under Review | 205418.98 | 2025-Q4
EXP-004253 | 2025-11-16 | BOQ-PKG-03-00273 | PKG-03 | INV-PKG-03-019-04253 | 437.54 | 54920.52 | 2746.03 | Paid | 52174.49 | 2025-Q4
EXP-004600 | 2025-11-16 | BOQ-PKG-10-00620 | PKG-10 | INV-PKG-10-016-04600 | 319.48 | 201625.06 | 10081.25 | Under Review | 191543.81 | 2025-Q4
EXP-005821 | 2025-11-16 | BOQ-PKG-01-01841 | PKG-01 | INV-PKG-01-012-05821 | 423.83 | 38979.6 | 1948.98 | Paid | 37030.62 | 2025-Q4
EXP-000694 | 2025-11-17 | BOQ-PKG-04-00694 | PKG-04 | INV-PKG-04-030-00694 | 253.05 | 72587.4 | 3629.37 | Paid | 68958.03 | 2025-Q4
EXP-002724 | 2025-11-17 | BOQ-PKG-04-00734 | PKG-04 | INV-PKG-04-030-02724 | 86.27 | 46851.84 | 2342.59 | Approved Pending Payment | 44509.25 | 2025-Q4
EXP-002759 | 2025-11-17 | BOQ-PKG-09-00769 | PKG-09 | INV-PKG-09-030-02759 | 373.79 | 75367.58 | 3768.38 | Disputed | 71599.2 | 2025-Q4
EXP-003013 | 2025-11-17 | BOQ-PKG-03-01023 | PKG-03 | INV-PKG-03-004-03013 | 152 | 57636.27 | 2881.81 | Paid | 54754.46 | 2025-Q4
EXP-004156 | 2025-11-17 | BOQ-PKG-06-00176 | PKG-06 | INV-PKG-06-027-04156 | 94.29 | 51755.86 | 2587.79 | Under Review | 49168.07 | 2025-Q4
EXP-004783 | 2025-11-17 | BOQ-PKG-03-00803 | PKG-03 | INV-PKG-03-024-04783 | 339.28 | 34612.93 | 1730.65 | Paid | 32882.28 | 2025-Q4
EXP-000138 | 2025-11-18 | BOQ-PKG-08-00138 | PKG-08 | INV-PKG-08-034-00138 | 51.9 | 182980.68 | 9149.03 | Paid | 173831.65 | 2025-Q4
EXP-000968 | 2025-11-18 | BOQ-PKG-08-00968 | PKG-08 | INV-PKG-08-024-00968 | 265.85 | 91186.09 | 4559.3 | Paid | 86626.79 | 2025-Q4
EXP-001552 | 2025-11-18 | BOQ-PKG-02-01552 | PKG-02 | INV-PKG-02-013-01552 | 282.43 | 146672.98 | 7333.65 | Paid | 139339.33 | 2025-Q4
EXP-001800 | 2025-11-18 | BOQ-PKG-10-01800 | PKG-10 | INV-PKG-10-016-01800 | 32.79 | 29710.2 | 1485.51 | Approved Pending Payment | 28224.69 | 2025-Q4
EXP-002736 | 2025-11-18 | BOQ-PKG-06-00746 | PKG-06 | INV-PKG-06-007-02736 | 32.33 | 189098.5 | 9454.93 | Under Review | 179643.57 | 2025-Q4
EXP-004693 | 2025-11-18 | BOQ-PKG-03-00713 | PKG-03 | INV-PKG-03-004-04693 | 236.12 | 210020.33 | 10501.02 | Paid | 199519.31 | 2025-Q4
EXP-005936 | 2025-11-18 | BOQ-PKG-06-01956 | PKG-06 | INV-PKG-06-022-05936 | 142.4 | 146049.05 | 7302.45 | Under Review | 138746.6 | 2025-Q4
EXP-000262 | 2025-11-19 | BOQ-PKG-02-00262 | PKG-02 | INV-PKG-02-018-00262 | 442.75 | 32253.71 | 1612.69 | Approved Pending Payment | 30641.02 | 2025-Q4
EXP-000316 | 2025-11-19 | BOQ-PKG-06-00316 | PKG-06 | INV-PKG-06-002-00316 | 55.06 | 158500.78 | 7925.04 | Paid | 150575.74 | 2025-Q4
EXP-000853 | 2025-11-19 | BOQ-PKG-03-00853 | PKG-03 | INV-PKG-03-014-00853 | 306.42 | 28301.3 | 1415.06 | Paid | 26886.24 | 2025-Q4
EXP-001551 | 2025-11-19 | BOQ-PKG-01-01551 | PKG-01 | INV-PKG-01-012-01551 | 97.93 | 81058.22 | 4052.91 | Paid | 77005.31 | 2025-Q4
EXP-003387 | 2025-11-19 | BOQ-PKG-07-01397 | PKG-07 | INV-PKG-07-028-03387 | 446.77 | 155386.25 | 7769.31 | Paid | 147616.94 | 2025-Q4
EXP-004976 | 2025-11-19 | BOQ-PKG-06-00996 | PKG-06 | INV-PKG-06-007-04976 | 294.85 | 105386.21 | 5269.31 | Paid | 100116.9 | 2025-Q4
EXP-002233 | 2025-11-20 | BOQ-PKG-03-00243 | PKG-03 | INV-PKG-03-029-02233 | 441.82 | 155781.96 | 7789.1 | Paid | 147992.86 | 2025-Q4
EXP-003704 | 2025-11-20 | BOQ-PKG-04-01714 | PKG-04 | INV-PKG-04-030-03704 | 391.12 | 213406.68 | 10670.33 | Paid | 202736.35 | 2025-Q4
EXP-005269 | 2025-11-20 | BOQ-PKG-09-01289 | PKG-09 | INV-PKG-09-020-05269 | 421.9 | 141480.73 | 7074.04 | Paid | 134406.69 | 2025-Q4
EXP-001271 | 2025-11-21 | BOQ-PKG-01-01271 | PKG-01 | INV-PKG-01-012-01271 | 263.08 | 41171.76 | 2058.59 | Paid | 39113.17 | 2025-Q4
EXP-003306 | 2025-11-21 | BOQ-PKG-06-01316 | PKG-06 | INV-PKG-06-017-03306 | 292.32 | 57172.6 | 2858.63 | Paid | 54313.97 | 2025-Q4
EXP-003319 | 2025-11-21 | BOQ-PKG-09-01329 | PKG-09 | INV-PKG-09-030-03319 | 76.93 | 26568.18 | 1328.41 | Under Review | 25239.77 | 2025-Q4
EXP-003612 | 2025-11-21 | BOQ-PKG-02-01622 | PKG-02 | INV-PKG-02-008-03612 | 237.2 | 53605.25 | 2680.26 | Paid | 50924.99 | 2025-Q4
EXP-004097 | 2025-11-21 | BOQ-PKG-07-00117 | PKG-07 | INV-PKG-07-003-04097 | 284.83 | 87983.7 | 4399.19 | Paid | 83584.51 | 2025-Q4
EXP-000516 | 2025-11-22 | BOQ-PKG-06-00516 | PKG-06 | INV-PKG-06-027-00516 | 168 | 34496.67 | 1724.83 | Under Review | 32771.84 | 2025-Q4
EXP-001414 | 2025-11-22 | BOQ-PKG-04-01414 | PKG-04 | INV-PKG-04-015-01414 | 22.92 | 95381.07 | 4769.05 | Paid | 90612.02 | 2025-Q4
EXP-001779 | 2025-11-22 | BOQ-PKG-09-01779 | PKG-09 | INV-PKG-09-030-01779 | 397.48 | 90138.98 | 4506.95 | Under Review | 85632.03 | 2025-Q4
EXP-002948 | 2025-11-22 | BOQ-PKG-08-00958 | PKG-08 | INV-PKG-08-009-02948 | 243.3 | 26480.25 | 1324.01 | Under Review | 25156.24 | 2025-Q4
EXP-003043 | 2025-11-22 | BOQ-PKG-03-01053 | PKG-03 | INV-PKG-03-034-03043 | 443.5 | 122766.58 | 6138.33 | Paid | 116628.25 | 2025-Q4
EXP-004181 | 2025-11-22 | BOQ-PKG-01-00201 | PKG-01 | INV-PKG-01-017-04181 | 92.75 | 47518.08 | 2375.9 | Approved Pending Payment | 45142.18 | 2025-Q4
EXP-004700 | 2025-11-22 | BOQ-PKG-10-00720 | PKG-10 | INV-PKG-10-011-04700 | 189.36 | 61209.12 | 3060.46 | Approved Pending Payment | 58148.66 | 2025-Q4
EXP-005277 | 2025-11-22 | BOQ-PKG-07-01297 | PKG-07 | INV-PKG-07-028-05277 | 84.64 | 26366.87 | 1318.34 | Paid | 25048.53 | 2025-Q4
EXP-006500 | 2025-11-22 | BOQ-PKG-10-00530 | PKG-10 | INV-PKG-10-026-06500 | 158.34 | 138604.45 | 6930.22 | Paid | 131674.23 | 2025-Q4
EXP-001642 | 2025-11-23 | BOQ-PKG-02-01642 | PKG-02 | INV-PKG-02-033-01642 | 317.77 | 138698.52 | 6934.93 | Paid | 131763.59 | 2025-Q4
EXP-002240 | 2025-11-23 | BOQ-PKG-10-00250 | PKG-10 | INV-PKG-10-001-02240 | 150.41 | 78143.54 | 3907.18 | Paid | 74236.36 | 2025-Q4
EXP-002714 | 2025-11-23 | BOQ-PKG-04-00724 | PKG-04 | INV-PKG-04-020-02714 | 357.7 | 119441.21 | 5972.06 | Paid | 113469.15 | 2025-Q4
EXP-002770 | 2025-11-23 | BOQ-PKG-10-00780 | PKG-10 | INV-PKG-10-006-02770 | 101.9 | 56283.69 | 2814.18 | Paid | 53469.51 | 2025-Q4
EXP-003775 | 2025-11-23 | BOQ-PKG-05-01785 | PKG-05 | INV-PKG-05-031-03775 | 18.41 | 78843.78 | 3942.19 | Paid | 74901.59 | 2025-Q4
EXP-004179 | 2025-11-23 | BOQ-PKG-09-00199 | PKG-09 | INV-PKG-09-015-04179 | 372.61 | 40038.79 | 2001.94 | Paid | 38036.85 | 2025-Q4
EXP-005365 | 2025-11-23 | BOQ-PKG-05-01385 | PKG-05 | INV-PKG-05-011-05365 | 16.84 | 57176.9 | 2858.84 | Under Review | 54318.06 | 2025-Q4
EXP-006864 | 2025-11-23 | BOQ-PKG-04-00894 | PKG-04 | INV-PKG-04-005-06864 | 245.09 | 128553.21 | 6427.66 | Paid | 122125.55 | 2025-Q4
EXP-006969 | 2025-11-23 | BOQ-PKG-09-00999 | PKG-09 | INV-PKG-09-005-06969 | 175.62 | 168751.1 | 8437.56 | Paid | 160313.54 | 2025-Q4
EXP-002196 | 2025-11-24 | BOQ-PKG-06-00206 | PKG-06 | INV-PKG-06-027-02196 | 400.62 | 181516.44 | 9075.82 | Paid | 172440.62 | 2025-Q4
EXP-003157 | 2025-11-24 | BOQ-PKG-07-01167 | PKG-07 | INV-PKG-07-008-03157 | 438.93 | 188286.95 | 9414.35 | Paid | 178872.6 | 2025-Q4
EXP-004727 | 2025-11-24 | BOQ-PKG-07-00747 | PKG-07 | INV-PKG-07-003-04727 | 377.79 | 110529.88 | 5526.49 | Paid | 105003.39 | 2025-Q4
EXP-005367 | 2025-11-24 | BOQ-PKG-07-01387 | PKG-07 | INV-PKG-07-013-05367 | 407.57 | 50332.86 | 2516.64 | Disputed | 47816.22 | 2025-Q4
EXP-006821 | 2025-11-24 | BOQ-PKG-01-00851 | PKG-01 | INV-PKG-01-032-06821 | 196.33 | 189172.43 | 9458.62 | Under Review | 179713.81 | 2025-Q4
EXP-001294 | 2025-11-25 | BOQ-PKG-04-01294 | PKG-04 | INV-PKG-04-035-01294 | 180.44 | 150074.29 | 7503.71 | Disputed | 142570.58 | 2025-Q4
EXP-001389 | 2025-11-25 | BOQ-PKG-09-01389 | PKG-09 | INV-PKG-09-025-01389 | 269.74 | 81441.54 | 4072.08 | Approved Pending Payment | 77369.46 | 2025-Q4
EXP-002852 | 2025-11-25 | BOQ-PKG-02-00862 | PKG-02 | INV-PKG-02-018-02852 | 138.37 | 53481.87 | 2674.09 | Paid | 50807.78 | 2025-Q4
EXP-002982 | 2025-11-25 | BOQ-PKG-02-00992 | PKG-02 | INV-PKG-02-008-02982 | 160.82 | 166598.72 | 8329.94 | Paid | 158268.78 | 2025-Q4
EXP-003591 | 2025-11-25 | BOQ-PKG-01-01601 | PKG-01 | INV-PKG-01-022-03591 | 399.23 | 24347.9 | 1217.4 | Approved Pending Payment | 23130.5 | 2025-Q4
EXP-004059 | 2025-11-25 | BOQ-PKG-09-00079 | PKG-09 | INV-PKG-09-035-04059 | 27.43 | 110492.43 | 5524.62 | Paid | 104967.81 | 2025-Q4
EXP-005623 | 2025-11-25 | BOQ-PKG-03-01643 | PKG-03 | INV-PKG-03-024-05623 | 412.72 | 198997.22 | 9949.86 | Paid | 189047.36 | 2025-Q4
EXP-000390 | 2025-11-26 | BOQ-PKG-10-00390 | PKG-10 | INV-PKG-10-006-00390 | 350.69 | 151015.75 | 7550.79 | Under Review | 143464.96 | 2025-Q4
EXP-001183 | 2025-11-26 | BOQ-PKG-03-01183 | PKG-03 | INV-PKG-03-029-01183 | 42.5 | 178531.86 | 8926.59 | Approved Pending Payment | 169605.27 | 2025-Q4
EXP-001759 | 2025-11-26 | BOQ-PKG-09-01759 | PKG-09 | INV-PKG-09-010-01759 | 277.03 | 56716.22 | 2835.81 | Paid | 53880.41 | 2025-Q4
EXP-001792 | 2025-11-26 | BOQ-PKG-02-01792 | PKG-02 | INV-PKG-02-008-01792 | 253.33 | 33615.92 | 1680.8 | Paid | 31935.12 | 2025-Q4
EXP-002543 | 2025-11-26 | BOQ-PKG-03-00553 | PKG-03 | INV-PKG-03-024-02543 | 145.86 | 165636.38 | 8281.82 | Approved Pending Payment | 157354.56 | 2025-Q4
EXP-002760 | 2025-11-26 | BOQ-PKG-10-00770 | PKG-10 | INV-PKG-10-031-02760 | 376.15 | 26088.83 | 1304.44 | Approved Pending Payment | 24784.39 | 2025-Q4
EXP-003266 | 2025-11-26 | BOQ-PKG-06-01276 | PKG-06 | INV-PKG-06-012-03266 | 169.09 | 64346.48 | 3217.32 | Approved Pending Payment | 61129.16 | 2025-Q4
EXP-004080 | 2025-11-26 | BOQ-PKG-10-00100 | PKG-10 | INV-PKG-10-021-04080 | 262.41 | 64347.73 | 3217.39 | Paid | 61130.34 | 2025-Q4
EXP-004715 | 2025-11-26 | BOQ-PKG-05-00735 | PKG-05 | INV-PKG-05-026-04715 | 109.67 | 161429.14 | 8071.46 | Paid | 153357.68 | 2025-Q4
EXP-004967 | 2025-11-26 | BOQ-PKG-07-00987 | PKG-07 | INV-PKG-07-033-04967 | 68.74 | 28986.68 | 1449.33 | Approved Pending Payment | 27537.35 | 2025-Q4
EXP-005771 | 2025-11-26 | BOQ-PKG-01-01791 | PKG-01 | INV-PKG-01-032-05771 | 170.07 | 121362.2 | 6068.11 | Paid | 115294.09 | 2025-Q4
EXP-006193 | 2025-11-26 | BOQ-PKG-03-00223 | PKG-03 | INV-PKG-03-034-06193 | 197.01 | 187968.87 | 9398.44 | Paid | 178570.43 | 2025-Q4
EXP-000153 | 2025-11-27 | BOQ-PKG-03-00153 | PKG-03 | INV-PKG-03-014-00153 | 54.22 | 31766.82 | 1588.34 | Paid | 30178.48 | 2025-Q4
EXP-000383 | 2025-11-27 | BOQ-PKG-03-00383 | PKG-03 | INV-PKG-03-034-00383 | 265.87 | 113076.08 | 5653.8 | Paid | 107422.28 | 2025-Q4
EXP-003121 | 2025-11-27 | BOQ-PKG-01-01131 | PKG-01 | INV-PKG-01-007-03121 | 223.09 | 164368.43 | 8218.42 | Paid | 156150.01 | 2025-Q4
EXP-004713 | 2025-11-27 | BOQ-PKG-03-00733 | PKG-03 | INV-PKG-03-024-04713 | 325.25 | 113688.49 | 5684.42 | Paid | 108004.07 | 2025-Q4
EXP-004772 | 2025-11-27 | BOQ-PKG-02-00792 | PKG-02 | INV-PKG-02-013-04772 | 15.73 | 88931.46 | 4446.57 | Paid | 84484.89 | 2025-Q4
EXP-005280 | 2025-11-27 | BOQ-PKG-10-01300 | PKG-10 | INV-PKG-10-031-05280 | 100.15 | 170399.86 | 8519.99 | Paid | 161879.87 | 2025-Q4
EXP-005563 | 2025-11-27 | BOQ-PKG-03-01583 | PKG-03 | INV-PKG-03-034-05563 | 241.98 | 76904.09 | 3845.2 | Paid | 73058.89 | 2025-Q4
EXP-006936 | 2025-11-27 | BOQ-PKG-06-00966 | PKG-06 | INV-PKG-06-007-06936 | 223.75 | 106943.67 | 5347.18 | Paid | 101596.49 | 2025-Q4
EXP-000634 | 2025-11-28 | BOQ-PKG-04-00634 | PKG-04 | INV-PKG-04-005-00634 | 340.45 | 64549.3 | 3227.46 | Paid | 61321.84 | 2025-Q4
EXP-001012 | 2025-11-28 | BOQ-PKG-02-01012 | PKG-02 | INV-PKG-02-033-01012 | 52.82 | 185277.39 | 9263.87 | Paid | 176013.52 | 2025-Q4
EXP-002024 | 2025-11-28 | BOQ-PKG-04-00034 | PKG-04 | INV-PKG-04-030-02024 | 255.4 | 208955.39 | 10447.77 | Under Review | 198507.62 | 2025-Q4
EXP-002068 | 2025-11-28 | BOQ-PKG-08-00078 | PKG-08 | INV-PKG-08-004-02068 | 61.3 | 34035.45 | 1701.77 | Paid | 32333.68 | 2025-Q4
EXP-002640 | 2025-11-28 | BOQ-PKG-10-00650 | PKG-10 | INV-PKG-10-016-02640 | 194.36 | 83986.27 | 4199.31 | Approved Pending Payment | 79786.96 | 2025-Q4
EXP-004183 | 2025-11-28 | BOQ-PKG-03-00203 | PKG-03 | INV-PKG-03-019-04183 | 294.87 | 51270.63 | 2563.53 | Paid | 48707.1 | 2025-Q4
EXP-006949 | 2025-11-28 | BOQ-PKG-09-00979 | PKG-09 | INV-PKG-09-020-06949 | 292.18 | 45482.14 | 2274.11 | Approved Pending Payment | 43208.03 | 2025-Q4
EXP-000117 | 2025-11-29 | BOQ-PKG-07-00117 | PKG-07 | INV-PKG-07-013-00117 | 132.81 | 181553.17 | 9077.66 | Paid | 172475.51 | 2025-Q4
EXP-000627 | 2025-11-29 | BOQ-PKG-07-00627 | PKG-07 | INV-PKG-07-033-00627 | 413.64 | 97702.57 | 4885.13 | Paid | 92817.44 | 2025-Q4
EXP-000805 | 2025-11-29 | BOQ-PKG-05-00805 | PKG-05 | INV-PKG-05-001-00805 | 310.84 | 43200.1 | 2160 | Paid | 41040.1 | 2025-Q4
EXP-001042 | 2025-11-29 | BOQ-PKG-02-01042 | PKG-02 | INV-PKG-02-028-01042 | 329.17 | 24798.81 | 1239.94 | Approved Pending Payment | 23558.87 | 2025-Q4
EXP-003497 | 2025-11-29 | BOQ-PKG-07-01507 | PKG-07 | INV-PKG-07-033-03497 | 298.49 | 167986.1 | 8399.3 | Paid | 159586.8 | 2025-Q4
EXP-004997 | 2025-11-29 | BOQ-PKG-07-01017 | PKG-07 | INV-PKG-07-028-04997 | 318.27 | 159703.31 | 7985.17 | Paid | 151718.14 | 2025-Q4
EXP-005251 | 2025-11-29 | BOQ-PKG-01-01271 | PKG-01 | INV-PKG-01-002-05251 | 245.3 | 178075.15 | 8903.76 | Paid | 169171.39 | 2025-Q4
EXP-000491 | 2025-11-30 | BOQ-PKG-01-00491 | PKG-01 | INV-PKG-01-002-00491 | 423.87 | 188774.21 | 9438.71 | Approved Pending Payment | 179335.5 | 2025-Q4
EXP-002117 | 2025-11-30 | BOQ-PKG-07-00127 | PKG-07 | INV-PKG-07-018-02117 | 32.58 | 114231.34 | 5711.57 | Paid | 108519.77 | 2025-Q4
EXP-002681 | 2025-11-30 | BOQ-PKG-01-00691 | PKG-01 | INV-PKG-01-022-02681 | 341.03 | 65205.71 | 3260.29 | Paid | 61945.42 | 2025-Q4
EXP-004674 | 2025-11-30 | BOQ-PKG-04-00694 | PKG-04 | INV-PKG-04-020-04674 | 154.64 | 57998.02 | 2899.9 | Paid | 55098.12 | 2025-Q4
EXP-005883 | 2025-11-30 | BOQ-PKG-03-01903 | PKG-03 | INV-PKG-03-004-05883 | 323.54 | 154841.72 | 7742.09 | Paid | 147099.63 | 2025-Q4
EXP-006084 | 2025-11-30 | BOQ-PKG-04-00114 | PKG-04 | INV-PKG-04-030-06084 | 436.76 | 169762.32 | 8488.12 | Paid | 161274.2 | 2025-Q4
EXP-006603 | 2025-11-30 | BOQ-PKG-03-00633 | PKG-03 | INV-PKG-03-024-06603 | 137.48 | 183243.26 | 9162.16 | Paid | 174081.1 | 2025-Q4
EXP-000663 | 2025-12-01 | BOQ-PKG-03-00663 | PKG-03 | INV-PKG-03-034-00663 | 39.71 | 43728.56 | 2186.43 | Paid | 41542.13 | 2025-Q4
EXP-001430 | 2025-12-01 | BOQ-PKG-10-01430 | PKG-10 | INV-PKG-10-031-01430 | 376.81 | 98060.74 | 4903.04 | Approved Pending Payment | 93157.7 | 2025-Q4
EXP-001998 | 2025-12-01 | BOQ-PKG-08-00008 | PKG-08 | INV-PKG-08-004-01998 | 433.96 | 201774.03 | 10088.7 | Paid | 191685.33 | 2025-Q4
EXP-005521 | 2025-12-01 | BOQ-PKG-01-01541 | PKG-01 | INV-PKG-01-027-05521 | 280.72 | 104124.59 | 5206.23 | Under Review | 98918.36 | 2025-Q4
EXP-006881 | 2025-12-01 | BOQ-PKG-01-00911 | PKG-01 | INV-PKG-01-022-06881 | 372.98 | 84124.49 | 4206.22 | Paid | 79918.27 | 2025-Q4
EXP-001266 | 2025-12-02 | BOQ-PKG-06-01266 | PKG-06 | INV-PKG-06-007-01266 | 409.08 | 70115.95 | 3505.8 | Paid | 66610.15 | 2025-Q4
EXP-001441 | 2025-12-02 | BOQ-PKG-01-01441 | PKG-01 | INV-PKG-01-007-01441 | 407.93 | 173614.9 | 8680.75 | Paid | 164934.15 | 2025-Q4
EXP-003085 | 2025-12-02 | BOQ-PKG-05-01095 | PKG-05 | INV-PKG-05-006-03085 | 227.49 | 132646 | 6632.3 | Approved Pending Payment | 126013.7 | 2025-Q4
EXP-004743 | 2025-12-02 | BOQ-PKG-03-00763 | PKG-03 | INV-PKG-03-019-04743 | 369.37 | 131875.32 | 6593.77 | Paid | 125281.55 | 2025-Q4
EXP-005669 | 2025-12-02 | BOQ-PKG-09-01689 | PKG-09 | INV-PKG-09-035-05669 | 125.05 | 178739.86 | 8936.99 | Paid | 169802.87 | 2025-Q4
EXP-000950 | 2025-12-03 | BOQ-PKG-10-00950 | PKG-10 | INV-PKG-10-006-00950 | 184.7 | 63310.57 | 3165.53 | Paid | 60145.04 | 2025-Q4
EXP-001876 | 2025-12-03 | BOQ-PKG-06-01876 | PKG-06 | INV-PKG-06-022-01876 | 20.82 | 216295.26 | 10814.76 | Paid | 205480.5 | 2025-Q4
EXP-003613 | 2025-12-03 | BOQ-PKG-03-01623 | PKG-03 | INV-PKG-03-009-03613 | 287.75 | 156400.38 | 7820.02 | Approved Pending Payment | 148580.36 | 2025-Q4
EXP-005741 | 2025-12-03 | BOQ-PKG-01-01761 | PKG-01 | INV-PKG-01-002-05741 | 372.96 | 60616.61 | 3030.83 | Approved Pending Payment | 57585.78 | 2025-Q4
EXP-001343 | 2025-12-04 | BOQ-PKG-03-01343 | PKG-03 | INV-PKG-03-014-01343 | 35.42 | 197402.68 | 9870.13 | Under Review | 187532.55 | 2025-Q4
EXP-002668 | 2025-12-04 | BOQ-PKG-08-00678 | PKG-08 | INV-PKG-08-009-02668 | 226.89 | 141836.08 | 7091.8 | Paid | 134744.28 | 2025-Q4
EXP-003440 | 2025-12-04 | BOQ-PKG-10-01450 | PKG-10 | INV-PKG-10-011-03440 | 26.93 | 154273.55 | 7713.68 | Paid | 146559.87 | 2025-Q4
EXP-003513 | 2025-12-04 | BOQ-PKG-03-01523 | PKG-03 | INV-PKG-03-014-03513 | 222.51 | 179032.61 | 8951.63 | Under Review | 170080.98 | 2025-Q4
EXP-003820 | 2025-12-04 | BOQ-PKG-10-01830 | PKG-10 | INV-PKG-10-006-03820 | 229.81 | 137389.9 | 6869.5 | Paid | 130520.4 | 2025-Q4
EXP-003966 | 2025-12-04 | BOQ-PKG-06-01976 | PKG-06 | INV-PKG-06-012-03966 | 263.01 | 50382.69 | 2519.13 | Paid | 47863.56 | 2025-Q4
EXP-004345 | 2025-12-04 | BOQ-PKG-05-00365 | PKG-05 | INV-PKG-05-006-04345 | 24.3 | 174232.88 | 8711.64 | Paid | 165521.24 | 2025-Q4
EXP-004527 | 2025-12-04 | BOQ-PKG-07-00547 | PKG-07 | INV-PKG-07-013-04527 | 22.44 | 123700.96 | 6185.05 | Paid | 117515.91 | 2025-Q4
EXP-005373 | 2025-12-04 | BOQ-PKG-03-01393 | PKG-03 | INV-PKG-03-019-05373 | 49.08 | 159970.54 | 7998.53 | Under Review | 151972.01 | 2025-Q4
EXP-006382 | 2025-12-04 | BOQ-PKG-02-00412 | PKG-02 | INV-PKG-02-013-06382 | 218.1 | 163796.7 | 8189.84 | Paid | 155606.86 | 2025-Q4
EXP-001834 | 2025-12-05 | BOQ-PKG-04-01834 | PKG-04 | INV-PKG-04-015-01834 | 425.23 | 140304.62 | 7015.23 | Approved Pending Payment | 133289.39 | 2025-Q4
EXP-003178 | 2025-12-05 | BOQ-PKG-08-01188 | PKG-08 | INV-PKG-08-029-03178 | 165.69 | 127358.15 | 6367.91 | Paid | 120990.24 | 2025-Q4
EXP-003877 | 2025-12-05 | BOQ-PKG-07-01887 | PKG-07 | INV-PKG-07-028-03877 | 11.8 | 68712.32 | 3435.62 | Approved Pending Payment | 65276.7 | 2025-Q4
EXP-004018 | 2025-12-05 | BOQ-PKG-08-00038 | PKG-08 | INV-PKG-08-029-04018 | 65.83 | 90355.99 | 4517.8 | Paid | 85838.19 | 2025-Q4
EXP-005011 | 2025-12-05 | BOQ-PKG-01-01031 | PKG-01 | INV-PKG-01-007-05011 | 99.15 | 112801.66 | 5640.08 | Paid | 107161.58 | 2025-Q4
EXP-005850 | 2025-12-05 | BOQ-PKG-10-01870 | PKG-10 | INV-PKG-10-006-05850 | 160.6 | 162975.58 | 8148.78 | Paid | 154826.8 | 2025-Q4
EXP-006048 | 2025-12-05 | BOQ-PKG-08-00078 | PKG-08 | INV-PKG-08-029-06048 | 112.2 | 38633.4 | 1931.67 | Paid | 36701.73 | 2025-Q4
EXP-006310 | 2025-12-05 | BOQ-PKG-10-00340 | PKG-10 | INV-PKG-10-011-06310 | 338.94 | 133830.09 | 6691.5 | Paid | 127138.59 | 2025-Q4
EXP-006904 | 2025-12-05 | BOQ-PKG-04-00934 | PKG-04 | INV-PKG-04-010-06904 | 177.35 | 161678.89 | 8083.94 | Approved Pending Payment | 153594.95 | 2025-Q4
EXP-004064 | 2025-12-06 | BOQ-PKG-04-00084 | PKG-04 | INV-PKG-04-005-04064 | 250.28 | 114551.81 | 5727.59 | Approved Pending Payment | 108824.22 | 2025-Q4
EXP-004678 | 2025-12-06 | BOQ-PKG-08-00698 | PKG-08 | INV-PKG-08-024-04678 | 239.83 | 201598.37 | 10079.92 | Approved Pending Payment | 191518.45 | 2025-Q4
EXP-005216 | 2025-12-06 | BOQ-PKG-06-01236 | PKG-06 | INV-PKG-06-002-05216 | 368.4 | 34075.1 | 1703.76 | Approved Pending Payment | 32371.34 | 2025-Q4
EXP-005400 | 2025-12-06 | BOQ-PKG-10-01420 | PKG-10 | INV-PKG-10-011-05400 | 165.95 | 166986.77 | 8349.34 | Paid | 158637.43 | 2025-Q4
EXP-005812 | 2025-12-06 | BOQ-PKG-02-01832 | PKG-02 | INV-PKG-02-003-05812 | 139.2 | 89156.45 | 4457.82 | Paid | 84698.63 | 2025-Q4
EXP-006191 | 2025-12-06 | BOQ-PKG-01-00221 | PKG-01 | INV-PKG-01-032-06191 | 390.36 | 98863.92 | 4943.2 | Approved Pending Payment | 93920.72 | 2025-Q4
EXP-006835 | 2025-12-06 | BOQ-PKG-05-00865 | PKG-05 | INV-PKG-05-011-06835 | 8.74 | 43377.84 | 2168.89 | Paid | 41208.95 | 2025-Q4
EXP-000528 | 2025-12-07 | BOQ-PKG-08-00528 | PKG-08 | INV-PKG-08-004-00528 | 93.85 | 93270.83 | 4663.54 | Approved Pending Payment | 88607.29 | 2025-Q4
EXP-001295 | 2025-12-07 | BOQ-PKG-05-01295 | PKG-05 | INV-PKG-05-001-01295 | 428.86 | 185512.19 | 9275.61 | Approved Pending Payment | 176236.58 | 2025-Q4
EXP-001478 | 2025-12-07 | BOQ-PKG-08-01478 | PKG-08 | INV-PKG-08-009-01478 | 191.75 | 204730.38 | 10236.52 | Under Review | 194493.86 | 2025-Q4
EXP-001741 | 2025-12-07 | BOQ-PKG-01-01741 | PKG-01 | INV-PKG-01-027-01741 | 337.76 | 95920.9 | 4796.04 | Paid | 91124.86 | 2025-Q4
EXP-001855 | 2025-12-07 | BOQ-PKG-05-01855 | PKG-05 | INV-PKG-05-001-01855 | 201.41 | 85755.72 | 4287.79 | Paid | 81467.93 | 2025-Q4
EXP-002030 | 2025-12-07 | BOQ-PKG-10-00040 | PKG-10 | INV-PKG-10-001-02030 | 312.3 | 45771.3 | 2288.56 | Paid | 43482.74 | 2025-Q4
EXP-002593 | 2025-12-07 | BOQ-PKG-03-00603 | PKG-03 | INV-PKG-03-004-02593 | 20.89 | 91967.76 | 4598.39 | Paid | 87369.37 | 2025-Q4
EXP-005964 | 2025-12-07 | BOQ-PKG-04-01984 | PKG-04 | INV-PKG-04-015-05964 | 222.15 | 107018.47 | 5350.92 | Paid | 101667.55 | 2025-Q4
EXP-000050 | 2025-12-08 | BOQ-PKG-10-00050 | PKG-10 | INV-PKG-10-016-00050 | 167.35 | 143233.35 | 7161.67 | Paid | 136071.68 | 2025-Q4
EXP-000637 | 2025-12-08 | BOQ-PKG-07-00637 | PKG-07 | INV-PKG-07-008-00637 | 187.87 | 143628.44 | 7181.42 | Paid | 136447.02 | 2025-Q4
EXP-003205 | 2025-12-08 | BOQ-PKG-05-01215 | PKG-05 | INV-PKG-05-021-03205 | 87.11 | 89793.38 | 4489.67 | Paid | 85303.71 | 2025-Q4
EXP-003801 | 2025-12-08 | BOQ-PKG-01-01811 | PKG-01 | INV-PKG-01-022-03801 | 369.96 | 186614.67 | 9330.73 | Paid | 177283.94 | 2025-Q4
EXP-004768 | 2025-12-08 | BOQ-PKG-08-00788 | PKG-08 | INV-PKG-08-009-04768 | 133.11 | 34784.65 | 1739.23 | Paid | 33045.42 | 2025-Q4
EXP-005401 | 2025-12-08 | BOQ-PKG-01-01421 | PKG-01 | INV-PKG-01-012-05401 | 436.05 | 65172.61 | 3258.63 | Paid | 61913.98 | 2025-Q4
EXP-006416 | 2025-12-08 | BOQ-PKG-06-00446 | PKG-06 | INV-PKG-06-012-06416 | 328.81 | 103554.85 | 5177.74 | Under Review | 98377.11 | 2025-Q4
EXP-006428 | 2025-12-08 | BOQ-PKG-08-00458 | PKG-08 | INV-PKG-08-024-06428 | 310.29 | 140839.15 | 7041.96 | Under Review | 133797.19 | 2025-Q4
EXP-002371 | 2025-12-09 | BOQ-PKG-01-00381 | PKG-01 | INV-PKG-01-027-02371 | 138.09 | 105239.94 | 5262 | Approved Pending Payment | 99977.94 | 2025-Q4
EXP-003823 | 2025-12-09 | BOQ-PKG-03-01833 | PKG-03 | INV-PKG-03-009-03823 | 13.46 | 114142.79 | 5707.14 | Paid | 108435.65 | 2025-Q4
EXP-003846 | 2025-12-09 | BOQ-PKG-06-01856 | PKG-06 | INV-PKG-06-032-03846 | 103.57 | 192447.65 | 9622.38 | Paid | 182825.27 | 2025-Q4
EXP-000392 | 2025-12-10 | BOQ-PKG-02-00392 | PKG-02 | INV-PKG-02-008-00392 | 309.7 | 62236.79 | 3111.84 | Paid | 59124.95 | 2025-Q4
EXP-000974 | 2025-12-10 | BOQ-PKG-04-00974 | PKG-04 | INV-PKG-04-030-00974 | 420.24 | 145944.17 | 7297.21 | Paid | 138646.96 | 2025-Q4
EXP-000987 | 2025-12-10 | BOQ-PKG-07-00987 | PKG-07 | INV-PKG-07-008-00987 | 350.74 | 182675.67 | 9133.78 | Paid | 173541.89 | 2025-Q4
EXP-001062 | 2025-12-10 | BOQ-PKG-02-01062 | PKG-02 | INV-PKG-02-013-01062 | 276.87 | 175766.28 | 8788.31 | Paid | 166977.97 | 2025-Q4
EXP-002673 | 2025-12-10 | BOQ-PKG-03-00683 | PKG-03 | INV-PKG-03-014-02673 | 313.57 | 168603.73 | 8430.19 | Paid | 160173.54 | 2025-Q4
EXP-004762 | 2025-12-10 | BOQ-PKG-02-00782 | PKG-02 | INV-PKG-02-003-04762 | 30.18 | 131115.14 | 6555.76 | Paid | 124559.38 | 2025-Q4
EXP-006763 | 2025-12-10 | BOQ-PKG-03-00793 | PKG-03 | INV-PKG-03-009-06763 | 274.38 | 154912.2 | 7745.61 | Under Review | 147166.59 | 2025-Q4
EXP-000275 | 2025-12-11 | BOQ-PKG-05-00275 | PKG-05 | INV-PKG-05-031-00275 | 447.96 | 77851.8 | 3892.59 | Paid | 73959.21 | 2025-Q4
EXP-000906 | 2025-12-11 | BOQ-PKG-06-00906 | PKG-06 | INV-PKG-06-032-00906 | 5.18 | 139658.83 | 6982.94 | Paid | 132675.89 | 2025-Q4
EXP-002671 | 2025-12-11 | BOQ-PKG-01-00681 | PKG-01 | INV-PKG-01-012-02671 | 276.57 | 57444.8 | 2872.24 | Paid | 54572.56 | 2025-Q4
EXP-002930 | 2025-12-11 | BOQ-PKG-10-00940 | PKG-10 | INV-PKG-10-026-02930 | 54.22 | 65911.97 | 3295.6 | Approved Pending Payment | 62616.37 | 2025-Q4
EXP-003177 | 2025-12-11 | BOQ-PKG-07-01187 | PKG-07 | INV-PKG-07-028-03177 | 420.44 | 65413.25 | 3270.66 | Approved Pending Payment | 62142.59 | 2025-Q4
EXP-003809 | 2025-12-11 | BOQ-PKG-09-01819 | PKG-09 | INV-PKG-09-030-03809 | 60.66 | 74001.51 | 3700.08 | Paid | 70301.43 | 2025-Q4
EXP-003989 | 2025-12-11 | BOQ-PKG-09-00009 | PKG-09 | INV-PKG-09-035-03989 | 14.34 | 100820.04 | 5041 | Paid | 95779.04 | 2025-Q4
EXP-004124 | 2025-12-11 | BOQ-PKG-04-00144 | PKG-04 | INV-PKG-04-030-04124 | 228.34 | 163148.71 | 8157.44 | Paid | 154991.27 | 2025-Q4
EXP-005663 | 2025-12-11 | BOQ-PKG-03-01683 | PKG-03 | INV-PKG-03-029-05663 | 235.47 | 176980.37 | 8849.02 | Paid | 168131.35 | 2025-Q4
EXP-005794 | 2025-12-11 | BOQ-PKG-04-01814 | PKG-04 | INV-PKG-04-020-05794 | 353.8 | 157306.16 | 7865.31 | Paid | 149440.85 | 2025-Q4
EXP-006441 | 2025-12-11 | BOQ-PKG-01-00471 | PKG-01 | INV-PKG-01-002-06441 | 206.74 | 123659.06 | 6182.95 | Approved Pending Payment | 117476.11 | 2025-Q4
EXP-000023 | 2025-12-12 | BOQ-PKG-03-00023 | PKG-03 | INV-PKG-03-024-00023 | 156.89 | 117090.2 | 5854.51 | Paid | 111235.69 | 2025-Q4
EXP-001840 | 2025-12-12 | BOQ-PKG-10-01840 | PKG-10 | INV-PKG-10-021-01840 | 342.08 | 100584.61 | 5029.23 | Paid | 95555.38 | 2025-Q4
EXP-002123 | 2025-12-12 | BOQ-PKG-03-00133 | PKG-03 | INV-PKG-03-024-02123 | 447.67 | 177652.69 | 8882.63 | Paid | 168770.06 | 2025-Q4
EXP-002835 | 2025-12-12 | BOQ-PKG-05-00845 | PKG-05 | INV-PKG-05-001-02835 | 404.22 | 101967.03 | 5098.35 | Paid | 96868.68 | 2025-Q4
EXP-003337 | 2025-12-12 | BOQ-PKG-07-01347 | PKG-07 | INV-PKG-07-013-03337 | 244.45 | 63345.03 | 3167.25 | Disputed | 60177.78 | 2025-Q4
EXP-004732 | 2025-12-12 | BOQ-PKG-02-00752 | PKG-02 | INV-PKG-02-008-04732 | 26.11 | 70733.02 | 3536.65 | Under Review | 67196.37 | 2025-Q4
EXP-005181 | 2025-12-12 | BOQ-PKG-01-01201 | PKG-01 | INV-PKG-01-002-05181 | 449.88 | 103512.58 | 5175.63 | Paid | 98336.95 | 2025-Q4
EXP-006359 | 2025-12-12 | BOQ-PKG-09-00389 | PKG-09 | INV-PKG-09-025-06359 | 433.81 | 68976.83 | 3448.84 | Under Review | 65527.99 | 2025-Q4
EXP-000717 | 2025-12-13 | BOQ-PKG-07-00717 | PKG-07 | INV-PKG-07-018-00717 | 300.39 | 45887.79 | 2294.39 | Paid | 43593.4 | 2025-Q4
EXP-001729 | 2025-12-13 | BOQ-PKG-09-01729 | PKG-09 | INV-PKG-09-015-01729 | 387.54 | 194903.21 | 9745.16 | Paid | 185158.05 | 2025-Q4
EXP-003122 | 2025-12-13 | BOQ-PKG-02-01132 | PKG-02 | INV-PKG-02-008-03122 | 375.79 | 193724.37 | 9686.22 | Approved Pending Payment | 184038.15 | 2025-Q4
EXP-003584 | 2025-12-13 | BOQ-PKG-04-01594 | PKG-04 | INV-PKG-04-015-03584 | 37.35 | 30694.03 | 1534.7 | Paid | 29159.33 | 2025-Q4
EXP-003772 | 2025-12-13 | BOQ-PKG-02-01782 | PKG-02 | INV-PKG-02-028-03772 | 24.08 | 60288.39 | 3014.42 | Paid | 57273.97 | 2025-Q4
EXP-004278 | 2025-12-13 | BOQ-PKG-08-00298 | PKG-08 | INV-PKG-08-009-04278 | 443.41 | 79956.88 | 3997.84 | Approved Pending Payment | 75959.04 | 2025-Q4
EXP-005468 | 2025-12-13 | BOQ-PKG-08-01488 | PKG-08 | INV-PKG-08-009-05468 | 289.86 | 157698.02 | 7884.9 | Paid | 149813.12 | 2025-Q4
EXP-005833 | 2025-12-13 | BOQ-PKG-03-01853 | PKG-03 | INV-PKG-03-024-05833 | 133.68 | 152618.56 | 7630.93 | Paid | 144987.63 | 2025-Q4
EXP-003285 | 2025-12-14 | BOQ-PKG-05-01295 | PKG-05 | INV-PKG-05-031-03285 | 160.35 | 203551.01 | 10177.55 | Paid | 193373.46 | 2025-Q4
EXP-003712 | 2025-12-14 | BOQ-PKG-02-01722 | PKG-02 | INV-PKG-02-003-03712 | 153.28 | 159769.64 | 7988.48 | Paid | 151781.16 | 2025-Q4
EXP-004508 | 2025-12-14 | BOQ-PKG-08-00528 | PKG-08 | INV-PKG-08-029-04508 | 292.31 | 211892.92 | 10594.65 | Paid | 201298.27 | 2025-Q4
EXP-004521 | 2025-12-14 | BOQ-PKG-01-00541 | PKG-01 | INV-PKG-01-007-04521 | 74.32 | 71930.29 | 3596.51 | Under Review | 68333.78 | 2025-Q4
EXP-004788 | 2025-12-14 | BOQ-PKG-08-00808 | PKG-08 | INV-PKG-08-029-04788 | 258.33 | 151750.18 | 7587.51 | Paid | 144162.67 | 2025-Q4
EXP-005147 | 2025-12-14 | BOQ-PKG-07-01167 | PKG-07 | INV-PKG-07-003-05147 | 66.8 | 181928.52 | 9096.43 | Under Review | 172832.09 | 2025-Q4
EXP-005561 | 2025-12-14 | BOQ-PKG-01-01581 | PKG-01 | INV-PKG-01-032-05561 | 129.95 | 143064.93 | 7153.25 | Paid | 135911.68 | 2025-Q4
EXP-006235 | 2025-12-14 | BOQ-PKG-05-00265 | PKG-05 | INV-PKG-05-006-06235 | 377.27 | 159323.8 | 7966.19 | Paid | 151357.61 | 2025-Q4
EXP-000358 | 2025-12-15 | BOQ-PKG-08-00358 | PKG-08 | INV-PKG-08-009-00358 | 117.51 | 35837.07 | 1791.85 | Under Review | 34045.22 | 2025-Q4
EXP-003039 | 2025-12-15 | BOQ-PKG-09-01049 | PKG-09 | INV-PKG-09-030-03039 | 406.38 | 67844.02 | 3392.2 | Paid | 64451.82 | 2025-Q4
EXP-003843 | 2025-12-15 | BOQ-PKG-03-01853 | PKG-03 | INV-PKG-03-029-03843 | 75.18 | 73091 | 3654.55 | Paid | 69436.45 | 2025-Q4
EXP-004869 | 2025-12-15 | BOQ-PKG-09-00889 | PKG-09 | INV-PKG-09-005-04869 | 438.39 | 91670.84 | 4583.54 | Disputed | 87087.3 | 2025-Q4
EXP-005601 | 2025-12-15 | BOQ-PKG-01-01621 | PKG-01 | INV-PKG-01-002-05601 | 173.34 | 212164.86 | 10608.24 | Approved Pending Payment | 201556.62 | 2025-Q4
EXP-006147 | 2025-12-15 | BOQ-PKG-07-00177 | PKG-07 | INV-PKG-07-023-06147 | 334.86 | 179424.74 | 8971.24 | Paid | 170453.5 | 2025-Q4
EXP-006929 | 2025-12-15 | BOQ-PKG-09-00959 | PKG-09 | INV-PKG-09-035-06929 | 11.52 | 113508.2 | 5675.41 | Paid | 107832.79 | 2025-Q4
EXP-006957 | 2025-12-15 | BOQ-PKG-07-00987 | PKG-07 | INV-PKG-07-028-06957 | 59.66 | 70259.31 | 3512.97 | Approved Pending Payment | 66746.34 | 2025-Q4
EXP-000632 | 2025-12-16 | BOQ-PKG-02-00632 | PKG-02 | INV-PKG-02-003-00632 | 390.75 | 142733.28 | 7136.66 | Paid | 135596.62 | 2025-Q4
EXP-002160 | 2025-12-16 | BOQ-PKG-10-00170 | PKG-10 | INV-PKG-10-026-02160 | 122.99 | 27048.62 | 1352.43 | Approved Pending Payment | 25696.19 | 2025-Q4
EXP-002189 | 2025-12-16 | BOQ-PKG-09-00199 | PKG-09 | INV-PKG-09-020-02189 | 408.74 | 196443.94 | 9822.2 | Paid | 186621.74 | 2025-Q4
EXP-002755 | 2025-12-16 | BOQ-PKG-05-00765 | PKG-05 | INV-PKG-05-026-02755 | 135.79 | 130373.72 | 6518.69 | Paid | 123855.03 | 2025-Q4
EXP-003206 | 2025-12-16 | BOQ-PKG-06-01216 | PKG-06 | INV-PKG-06-022-03206 | 432.74 | 46448.37 | 2322.42 | Paid | 44125.95 | 2025-Q4
EXP-003251 | 2025-12-16 | BOQ-PKG-01-01261 | PKG-01 | INV-PKG-01-032-03251 | 150.67 | 182145.46 | 9107.27 | Paid | 173038.19 | 2025-Q4
EXP-004017 | 2025-12-16 | BOQ-PKG-07-00037 | PKG-07 | INV-PKG-07-028-04017 | 338.73 | 148148.53 | 7407.43 | Paid | 140741.1 | 2025-Q4
EXP-000292 | 2025-12-17 | BOQ-PKG-02-00292 | PKG-02 | INV-PKG-02-013-00292 | 98.88 | 174417.52 | 8720.88 | Approved Pending Payment | 165696.64 | 2025-Q4
EXP-003757 | 2025-12-17 | BOQ-PKG-07-01767 | PKG-07 | INV-PKG-07-013-03757 | 413.43 | 194023.72 | 9701.19 | Under Review | 184322.53 | 2025-Q4
EXP-000544 | 2025-12-18 | BOQ-PKG-04-00544 | PKG-04 | INV-PKG-04-020-00544 | 299.53 | 92504.41 | 4625.22 | Paid | 87879.19 | 2025-Q4
EXP-001020 | 2025-12-18 | BOQ-PKG-10-01020 | PKG-10 | INV-PKG-10-006-01020 | 353.96 | 169354.81 | 8467.74 | Paid | 160887.07 | 2025-Q4
EXP-004904 | 2025-12-18 | BOQ-PKG-04-00924 | PKG-04 | INV-PKG-04-005-04904 | 105.04 | 130416.07 | 6520.8 | Paid | 123895.27 | 2025-Q4
EXP-000134 | 2025-12-19 | BOQ-PKG-04-00134 | PKG-04 | INV-PKG-04-030-00134 | 306.59 | 73123.84 | 3656.19 | Paid | 69467.65 | 2025-Q4
EXP-000335 | 2025-12-19 | BOQ-PKG-05-00335 | PKG-05 | INV-PKG-05-021-00335 | 305.48 | 61657.46 | 3082.87 | Paid | 58574.59 | 2025-Q4
EXP-000424 | 2025-12-19 | BOQ-PKG-04-00424 | PKG-04 | INV-PKG-04-005-00424 | 28.26 | 178788.97 | 8939.45 | Under Review | 169849.52 | 2025-Q4
EXP-002262 | 2025-12-19 | BOQ-PKG-02-00272 | PKG-02 | INV-PKG-02-023-02262 | 314.78 | 193461.92 | 9673.1 | Disputed | 183788.82 | 2025-Q4
EXP-002547 | 2025-12-19 | BOQ-PKG-07-00557 | PKG-07 | INV-PKG-07-028-02547 | 151.12 | 119818.52 | 5990.93 | Under Review | 113827.59 | 2025-Q4
EXP-003063 | 2025-12-19 | BOQ-PKG-03-01073 | PKG-03 | INV-PKG-03-019-03063 | 448.47 | 178259.62 | 8912.98 | Under Review | 169346.64 | 2025-Q4
EXP-003110 | 2025-12-19 | BOQ-PKG-10-01120 | PKG-10 | INV-PKG-10-031-03110 | 275.14 | 80967.51 | 4048.38 | Paid | 76919.13 | 2025-Q4
EXP-004297 | 2025-12-19 | BOQ-PKG-07-00317 | PKG-07 | INV-PKG-07-028-04297 | 84.38 | 102076.86 | 5103.84 | Approved Pending Payment | 96973.02 | 2025-Q4
EXP-005462 | 2025-12-19 | BOQ-PKG-02-01482 | PKG-02 | INV-PKG-02-003-05462 | 97.19 | 181276.05 | 9063.8 | Paid | 172212.25 | 2025-Q4
EXP-000102 | 2025-12-20 | BOQ-PKG-02-00102 | PKG-02 | INV-PKG-02-033-00102 | 16.21 | 92168.58 | 4608.43 | Paid | 87560.15 | 2025-Q4
EXP-000860 | 2025-12-20 | BOQ-PKG-10-00860 | PKG-10 | INV-PKG-10-021-00860 | 231.83 | 101992.68 | 5099.63 | Paid | 96893.05 | 2025-Q4
EXP-005165 | 2025-12-20 | BOQ-PKG-05-01185 | PKG-05 | INV-PKG-05-021-05165 | 229.28 | 25551.54 | 1277.58 | Paid | 24273.96 | 2025-Q4
EXP-005249 | 2025-12-20 | BOQ-PKG-09-01269 | PKG-09 | INV-PKG-09-035-05249 | 259.87 | 160969.33 | 8048.47 | Paid | 152920.86 | 2025-Q4
EXP-006299 | 2025-12-20 | BOQ-PKG-09-00329 | PKG-09 | INV-PKG-09-035-06299 | 187.03 | 43067.1 | 2153.36 | Approved Pending Payment | 40913.74 | 2025-Q4
EXP-001685 | 2025-12-21 | BOQ-PKG-05-01685 | PKG-05 | INV-PKG-05-006-01685 | 239.99 | 98894.79 | 4944.74 | Disputed | 93950.05 | 2025-Q4
EXP-001872 | 2025-12-21 | BOQ-PKG-02-01872 | PKG-02 | INV-PKG-02-018-01872 | 386.09 | 81134.07 | 4056.7 | Paid | 77077.37 | 2025-Q4
EXP-002216 | 2025-12-21 | BOQ-PKG-06-00226 | PKG-06 | INV-PKG-06-012-02216 | 67.32 | 146088.38 | 7304.42 | Paid | 138783.96 | 2025-Q4
EXP-003348 | 2025-12-21 | BOQ-PKG-08-01358 | PKG-08 | INV-PKG-08-024-03348 | 53.66 | 101915.81 | 5095.79 | Paid | 96820.02 | 2025-Q4
EXP-003483 | 2025-12-21 | BOQ-PKG-03-01493 | PKG-03 | INV-PKG-03-019-03483 | 24.17 | 183944.78 | 9197.24 | Approved Pending Payment | 174747.54 | 2025-Q4
EXP-003815 | 2025-12-21 | BOQ-PKG-05-01825 | PKG-05 | INV-PKG-05-001-03815 | 112.38 | 135238.03 | 6761.9 | Paid | 128476.13 | 2025-Q4
EXP-005471 | 2025-12-21 | BOQ-PKG-01-01491 | PKG-01 | INV-PKG-01-012-05471 | 362.23 | 122060.03 | 6103 | Approved Pending Payment | 115957.03 | 2025-Q4
EXP-005860 | 2025-12-21 | BOQ-PKG-10-01880 | PKG-10 | INV-PKG-10-016-05860 | 412.78 | 169244.69 | 8462.23 | Paid | 160782.46 | 2025-Q4
EXP-006051 | 2025-12-21 | BOQ-PKG-01-00081 | PKG-01 | INV-PKG-01-032-06051 | 260.83 | 99420.49 | 4971.02 | Paid | 94449.47 | 2025-Q4
EXP-006925 | 2025-12-21 | BOQ-PKG-05-00955 | PKG-05 | INV-PKG-05-031-06925 | 90.57 | 186582.75 | 9329.14 | Paid | 177253.61 | 2025-Q4
EXP-000472 | 2025-12-22 | BOQ-PKG-02-00472 | PKG-02 | INV-PKG-02-018-00472 | 79.87 | 59217.9 | 2960.9 | Paid | 56257 | 2025-Q4
EXP-000871 | 2025-12-22 | BOQ-PKG-01-00871 | PKG-01 | INV-PKG-01-032-00871 | 280.65 | 172952.95 | 8647.65 | Approved Pending Payment | 164305.3 | 2025-Q4
EXP-001138 | 2025-12-22 | BOQ-PKG-08-01138 | PKG-08 | INV-PKG-08-019-01138 | 26.15 | 65930.78 | 3296.54 | Approved Pending Payment | 62634.24 | 2025-Q4
EXP-003184 | 2025-12-22 | BOQ-PKG-04-01194 | PKG-04 | INV-PKG-04-035-03184 | 125.39 | 145930.97 | 7296.55 | Paid | 138634.42 | 2025-Q4
EXP-003609 | 2025-12-22 | BOQ-PKG-09-01619 | PKG-09 | INV-PKG-09-005-03609 | 191.47 | 117394.88 | 5869.74 | Paid | 111525.14 | 2025-Q4
EXP-003716 | 2025-12-22 | BOQ-PKG-06-01726 | PKG-06 | INV-PKG-06-007-03716 | 14.11 | 140907.27 | 7045.36 | Paid | 133861.91 | 2025-Q4
EXP-006695 | 2025-12-22 | BOQ-PKG-05-00725 | PKG-05 | INV-PKG-05-011-06695 | 314.36 | 178984.45 | 8949.22 | Approved Pending Payment | 170035.23 | 2025-Q4
EXP-001284 | 2025-12-23 | BOQ-PKG-04-01284 | PKG-04 | INV-PKG-04-025-01284 | 229.87 | 144902.84 | 7245.14 | Paid | 137657.7 | 2025-Q4
EXP-001429 | 2025-12-23 | BOQ-PKG-09-01429 | PKG-09 | INV-PKG-09-030-01429 | 96.14 | 94200.03 | 4710 | Paid | 89490.03 | 2025-Q4
EXP-002627 | 2025-12-23 | BOQ-PKG-07-00637 | PKG-07 | INV-PKG-07-003-02627 | 285.66 | 106922.41 | 5346.12 | Paid | 101576.29 | 2025-Q4
EXP-002731 | 2025-12-23 | BOQ-PKG-01-00741 | PKG-01 | INV-PKG-01-002-02731 | 226.11 | 111378.1 | 5568.91 | Paid | 105809.19 | 2025-Q4
EXP-002960 | 2025-12-23 | BOQ-PKG-10-00970 | PKG-10 | INV-PKG-10-021-02960 | 97.02 | 173520.58 | 8676.03 | Approved Pending Payment | 164844.55 | 2025-Q4
EXP-004805 | 2025-12-23 | BOQ-PKG-05-00825 | PKG-05 | INV-PKG-05-011-04805 | 121.62 | 148353.87 | 7417.69 | Paid | 140936.18 | 2025-Q4
EXP-001857 | 2025-12-24 | BOQ-PKG-07-01857 | PKG-07 | INV-PKG-07-003-01857 | 149.83 | 151231.97 | 7561.6 | Paid | 143670.37 | 2025-Q4
EXP-001928 | 2025-12-24 | BOQ-PKG-08-01928 | PKG-08 | INV-PKG-08-004-01928 | 53.89 | 99332.03 | 4966.6 | Paid | 94365.43 | 2025-Q4
EXP-001988 | 2025-12-24 | BOQ-PKG-08-01988 | PKG-08 | INV-PKG-08-029-01988 | 363.08 | 166828.99 | 8341.45 | Paid | 158487.54 | 2025-Q4
EXP-002431 | 2025-12-24 | BOQ-PKG-01-00441 | PKG-01 | INV-PKG-01-017-02431 | 418.96 | 186681.82 | 9334.09 | Paid | 177347.73 | 2025-Q4
EXP-002775 | 2025-12-24 | BOQ-PKG-05-00785 | PKG-05 | INV-PKG-05-011-02775 | 446.51 | 138089.78 | 6904.49 | Paid | 131185.29 | 2025-Q4
EXP-004395 | 2025-12-24 | BOQ-PKG-05-00415 | PKG-05 | INV-PKG-05-021-04395 | 264.57 | 55935.5 | 2796.78 | Paid | 53138.72 | 2025-Q4
EXP-004402 | 2025-12-24 | BOQ-PKG-02-00422 | PKG-02 | INV-PKG-02-028-04402 | 136.83 | 72383.76 | 3619.19 | Paid | 68764.57 | 2025-Q4
EXP-004513 | 2025-12-24 | BOQ-PKG-03-00533 | PKG-03 | INV-PKG-03-034-04513 | 331.44 | 192554.69 | 9627.73 | Paid | 182926.96 | 2025-Q4
EXP-004585 | 2025-12-24 | BOQ-PKG-05-00605 | PKG-05 | INV-PKG-05-001-04585 | 80.63 | 69582.24 | 3479.11 | Paid | 66103.13 | 2025-Q4
EXP-004968 | 2025-12-24 | BOQ-PKG-08-00988 | PKG-08 | INV-PKG-08-034-04968 | 129.57 | 141335.53 | 7066.78 | Paid | 134268.75 | 2025-Q4
EXP-006117 | 2025-12-24 | BOQ-PKG-07-00147 | PKG-07 | INV-PKG-07-028-06117 | 292.68 | 170059.28 | 8502.96 | Paid | 161556.32 | 2025-Q4
EXP-006892 | 2025-12-24 | BOQ-PKG-02-00922 | PKG-02 | INV-PKG-02-033-06892 | 353.46 | 120412.09 | 6020.6 | Paid | 114391.49 | 2025-Q4
EXP-006992 | 2025-12-24 | BOQ-PKG-02-01022 | PKG-02 | INV-PKG-02-028-06992 | 223.86 | 67760.99 | 3388.05 | Approved Pending Payment | 64372.94 | 2025-Q4
EXP-000756 | 2025-12-25 | BOQ-PKG-06-00756 | PKG-06 | INV-PKG-06-022-00756 | 121.61 | 194352.37 | 9717.62 | Paid | 184634.75 | 2025-Q4
EXP-001311 | 2025-12-25 | BOQ-PKG-01-01311 | PKG-01 | INV-PKG-01-017-01311 | 342.66 | 194844.22 | 9742.21 | Paid | 185102.01 | 2025-Q4
EXP-002287 | 2025-12-25 | BOQ-PKG-07-00297 | PKG-07 | INV-PKG-07-013-02287 | 252.78 | 185947.15 | 9297.36 | Paid | 176649.79 | 2025-Q4
EXP-003517 | 2025-12-25 | BOQ-PKG-07-01527 | PKG-07 | INV-PKG-07-018-03517 | 82.96 | 100069.08 | 5003.45 | Paid | 95065.63 | 2025-Q4
EXP-004026 | 2025-12-25 | BOQ-PKG-06-00046 | PKG-06 | INV-PKG-06-002-04026 | 364.61 | 122073.36 | 6103.67 | Paid | 115969.69 | 2025-Q4
EXP-005760 | 2025-12-25 | BOQ-PKG-10-01780 | PKG-10 | INV-PKG-10-021-05760 | 417.66 | 126683.41 | 6334.17 | Disputed | 120349.24 | 2025-Q4
EXP-006739 | 2025-12-25 | BOQ-PKG-09-00769 | PKG-09 | INV-PKG-09-020-06739 | 53.41 | 201165.45 | 10058.27 | Paid | 191107.18 | 2025-Q4
EXP-000196 | 2025-12-26 | BOQ-PKG-06-00196 | PKG-06 | INV-PKG-06-022-00196 | 163.86 | 138953.2 | 6947.66 | Approved Pending Payment | 132005.54 | 2025-Q4
EXP-002105 | 2025-12-26 | BOQ-PKG-05-00115 | PKG-05 | INV-PKG-05-006-02105 | 406.49 | 33292.41 | 1664.62 | Paid | 31627.79 | 2025-Q4
EXP-002832 | 2025-12-26 | BOQ-PKG-02-00842 | PKG-02 | INV-PKG-02-033-02832 | 394.05 | 184756.65 | 9237.83 | Under Review | 175518.82 | 2025-Q4
EXP-004027 | 2025-12-26 | BOQ-PKG-07-00047 | PKG-07 | INV-PKG-07-003-04027 | 115.8 | 114730.77 | 5736.54 | Paid | 108994.23 | 2025-Q4
EXP-005610 | 2025-12-26 | BOQ-PKG-10-01630 | PKG-10 | INV-PKG-10-011-05610 | 28.39 | 73026.14 | 3651.31 | Under Review | 69374.83 | 2025-Q4
EXP-005816 | 2025-12-26 | BOQ-PKG-06-01836 | PKG-06 | INV-PKG-06-007-05816 | 98.77 | 50087.03 | 2504.35 | Paid | 47582.68 | 2025-Q4
EXP-006492 | 2025-12-26 | BOQ-PKG-02-00522 | PKG-02 | INV-PKG-02-018-06492 | 266.56 | 30388.43 | 1519.42 | Paid | 28869.01 | 2025-Q4
EXP-002511 | 2025-12-27 | BOQ-PKG-01-00521 | PKG-01 | INV-PKG-01-027-02511 | 285.87 | 80794.58 | 4039.73 | Paid | 76754.85 | 2025-Q4
EXP-003812 | 2025-12-27 | BOQ-PKG-02-01822 | PKG-02 | INV-PKG-02-033-03812 | 355.54 | 126945.04 | 6347.25 | Under Review | 120597.79 | 2025-Q4
EXP-004060 | 2025-12-27 | BOQ-PKG-10-00080 | PKG-10 | INV-PKG-10-001-04060 | 209.17 | 53397.71 | 2669.89 | Paid | 50727.82 | 2025-Q4
EXP-004676 | 2025-12-27 | BOQ-PKG-06-00696 | PKG-06 | INV-PKG-06-022-04676 | 304.35 | 25274.44 | 1263.72 | Paid | 24010.72 | 2025-Q4
EXP-005414 | 2025-12-27 | BOQ-PKG-04-01434 | PKG-04 | INV-PKG-04-025-05414 | 82.3 | 35849.45 | 1792.47 | Paid | 34056.98 | 2025-Q4
EXP-006494 | 2025-12-27 | BOQ-PKG-04-00524 | PKG-04 | INV-PKG-04-020-06494 | 260.06 | 113040.14 | 5652.01 | Paid | 107388.13 | 2025-Q4
EXP-001680 | 2025-12-28 | BOQ-PKG-10-01680 | PKG-10 | INV-PKG-10-001-01680 | 33.45 | 157715.1 | 7885.76 | Under Review | 149829.34 | 2025-Q4
EXP-002647 | 2025-12-28 | BOQ-PKG-07-00657 | PKG-07 | INV-PKG-07-023-02647 | 69.02 | 135478.83 | 6773.94 | Paid | 128704.89 | 2025-Q4
EXP-002818 | 2025-12-28 | BOQ-PKG-08-00828 | PKG-08 | INV-PKG-08-019-02818 | 95.19 | 150316.01 | 7515.8 | Under Review | 142800.21 | 2025-Q4
EXP-005298 | 2025-12-28 | BOQ-PKG-08-01318 | PKG-08 | INV-PKG-08-014-05298 | 105.53 | 42241.56 | 2112.08 | Under Review | 40129.48 | 2025-Q4
EXP-006595 | 2025-12-28 | BOQ-PKG-05-00625 | PKG-05 | INV-PKG-05-016-06595 | 439.31 | 135332.48 | 6766.62 | Paid | 128565.86 | 2025-Q4
EXP-003123 | 2025-12-29 | BOQ-PKG-03-01133 | PKG-03 | INV-PKG-03-009-03123 | 74.31 | 52764.35 | 2638.22 | Paid | 50126.13 | 2025-Q4
EXP-003546 | 2025-12-29 | BOQ-PKG-06-01556 | PKG-06 | INV-PKG-06-012-03546 | 406.06 | 81086.25 | 4054.31 | Under Review | 77031.94 | 2025-Q4
EXP-004890 | 2025-12-29 | BOQ-PKG-10-00910 | PKG-10 | INV-PKG-10-026-04890 | 150.43 | 132260.61 | 6613.03 | Paid | 125647.58 | 2025-Q4
EXP-006459 | 2025-12-29 | BOQ-PKG-09-00489 | PKG-09 | INV-PKG-09-020-06459 | 385.46 | 68853.29 | 3442.66 | Approved Pending Payment | 65410.63 | 2025-Q4
EXP-006778 | 2025-12-29 | BOQ-PKG-08-00808 | PKG-08 | INV-PKG-08-024-06778 | 374.03 | 194000.55 | 9700.03 | Paid | 184300.52 | 2025-Q4
EXP-000043 | 2025-12-30 | BOQ-PKG-03-00043 | PKG-03 | INV-PKG-03-009-00043 | 393.42 | 119401.37 | 5970.07 | Paid | 113431.3 | 2025-Q4
EXP-000408 | 2025-12-30 | BOQ-PKG-08-00408 | PKG-08 | INV-PKG-08-024-00408 | 63.95 | 126510.1 | 6325.51 | Paid | 120184.59 | 2025-Q4
EXP-000595 | 2025-12-30 | BOQ-PKG-05-00595 | PKG-05 | INV-PKG-05-001-00595 | 215.83 | 103210.6 | 5160.53 | Approved Pending Payment | 98050.07 | 2025-Q4
EXP-000736 | 2025-12-30 | BOQ-PKG-06-00736 | PKG-06 | INV-PKG-06-002-00736 | 323.76 | 148651.74 | 7432.59 | Paid | 141219.15 | 2025-Q4
EXP-000874 | 2025-12-30 | BOQ-PKG-04-00874 | PKG-04 | INV-PKG-04-035-00874 | 365.97 | 29990.74 | 1499.54 | Paid | 28491.2 | 2025-Q4
EXP-001740 | 2025-12-30 | BOQ-PKG-10-01740 | PKG-10 | INV-PKG-10-026-01740 | 135.98 | 169657.16 | 8482.86 | Paid | 161174.3 | 2025-Q4
EXP-002288 | 2025-12-30 | BOQ-PKG-08-00298 | PKG-08 | INV-PKG-08-014-02288 | 72.41 | 98599.65 | 4929.98 | Paid | 93669.67 | 2025-Q4
EXP-002626 | 2025-12-30 | BOQ-PKG-06-00636 | PKG-06 | INV-PKG-06-002-02626 | 328.3 | 197840.91 | 9892.05 | Approved Pending Payment | 187948.86 | 2025-Q4
EXP-002683 | 2025-12-30 | BOQ-PKG-03-00693 | PKG-03 | INV-PKG-03-024-02683 | 390.09 | 192164.18 | 9608.21 | Paid | 182555.97 | 2025-Q4
EXP-004228 | 2025-12-30 | BOQ-PKG-08-00248 | PKG-08 | INV-PKG-08-029-04228 | 6.99 | 81271.43 | 4063.57 | Paid | 77207.86 | 2025-Q4
EXP-004961 | 2025-12-30 | BOQ-PKG-01-00981 | PKG-01 | INV-PKG-01-027-04961 | 382.2 | 139649.56 | 6982.48 | Paid | 132667.08 | 2025-Q4
EXP-005404 | 2025-12-30 | BOQ-PKG-04-01424 | PKG-04 | INV-PKG-04-015-05404 | 356.01 | 105770.16 | 5288.51 | Under Review | 100481.65 | 2025-Q4
EXP-005742 | 2025-12-30 | BOQ-PKG-02-01762 | PKG-02 | INV-PKG-02-003-05742 | 31.78 | 83483.13 | 4174.16 | Approved Pending Payment | 79308.97 | 2025-Q4
EXP-006924 | 2025-12-30 | BOQ-PKG-04-00954 | PKG-04 | INV-PKG-04-030-06924 | 359.04 | 104578.55 | 5228.93 | Paid | 99349.62 | 2025-Q4
EXP-002537 | 2025-12-31 | BOQ-PKG-07-00547 | PKG-07 | INV-PKG-07-018-02537 | 69.81 | 188289.81 | 9414.49 | Paid | 178875.32 | 2025-Q4
EXP-003468 | 2025-12-31 | BOQ-PKG-08-01478 | PKG-08 | INV-PKG-08-004-03468 | 108.3 | 56262.98 | 2813.15 | Paid | 53449.83 | 2025-Q4
EXP-003718 | 2025-12-31 | BOQ-PKG-08-01728 | PKG-08 | INV-PKG-08-009-03718 | 22.07 | 28048.1 | 1402.4 | Paid | 26645.7 | 2025-Q4
EXP-004614 | 2025-12-31 | BOQ-PKG-04-00634 | PKG-04 | INV-PKG-04-030-04614 | 21.39 | 99548.82 | 4977.44 | Under Review | 94571.38 | 2025-Q4
EXP-005108 | 2025-12-31 | BOQ-PKG-08-01128 | PKG-08 | INV-PKG-08-034-05108 | 233.17 | 79510.2 | 3975.51 | Paid | 75534.69 | 2025-Q4
EXP-001001 | 2026-01-01 | BOQ-PKG-01-01001 | PKG-01 | INV-PKG-01-022-01001 | 293.67 | 143554.79 | 7177.74 | Paid | 136377.05 | 2026-Q1
EXP-001417 | 2026-01-01 | BOQ-PKG-07-01417 | PKG-07 | INV-PKG-07-018-01417 | 44.59 | 189274.4 | 9463.72 | Paid | 179810.68 | 2026-Q1
EXP-001781 | 2026-01-01 | BOQ-PKG-01-01781 | PKG-01 | INV-PKG-01-032-01781 | 362.67 | 127071 | 6353.55 | Paid | 120717.45 | 2026-Q1
EXP-002791 | 2026-01-01 | BOQ-PKG-01-00801 | PKG-01 | INV-PKG-01-027-02791 | 235.13 | 126971.94 | 6348.6 | Approved Pending Payment | 120623.34 | 2026-Q1
EXP-002796 | 2026-01-01 | BOQ-PKG-06-00806 | PKG-06 | INV-PKG-06-032-02796 | 148.84 | 192504.75 | 9625.24 | Disputed | 182879.51 | 2026-Q1
EXP-003007 | 2026-01-01 | BOQ-PKG-07-01017 | PKG-07 | INV-PKG-07-033-03007 | 325.96 | 91391.93 | 4569.6 | Paid | 86822.33 | 2026-Q1
EXP-004222 | 2026-01-01 | BOQ-PKG-02-00242 | PKG-02 | INV-PKG-02-023-04222 | 387.6 | 115774.43 | 5788.72 | Paid | 109985.71 | 2026-Q1
EXP-004548 | 2026-01-01 | BOQ-PKG-08-00568 | PKG-08 | INV-PKG-08-034-04548 | 67.65 | 114925.5 | 5746.28 | Paid | 109179.22 | 2026-Q1
EXP-000331 | 2026-01-02 | BOQ-PKG-01-00331 | PKG-01 | INV-PKG-01-017-00331 | 264.18 | 57340.86 | 2867.04 | Paid | 54473.82 | 2026-Q1
EXP-000533 | 2026-01-02 | BOQ-PKG-03-00533 | PKG-03 | INV-PKG-03-009-00533 | 358.39 | 119880.51 | 5994.03 | Paid | 113886.48 | 2026-Q1
EXP-000538 | 2026-01-02 | BOQ-PKG-08-00538 | PKG-08 | INV-PKG-08-014-00538 | 152.74 | 158492.56 | 7924.63 | Paid | 150567.93 | 2026-Q1
EXP-001510 | 2026-01-02 | BOQ-PKG-10-01510 | PKG-10 | INV-PKG-10-006-01510 | 54.21 | 181250.31 | 9062.52 | Paid | 172187.79 | 2026-Q1
EXP-001586 | 2026-01-02 | BOQ-PKG-06-01586 | PKG-06 | INV-PKG-06-012-01586 | 352.08 | 112541.65 | 5627.08 | Paid | 106914.57 | 2026-Q1
EXP-002064 | 2026-01-02 | BOQ-PKG-04-00074 | PKG-04 | INV-PKG-04-035-02064 | 367.07 | 24776.68 | 1238.83 | Paid | 23537.85 | 2026-Q1
EXP-004295 | 2026-01-02 | BOQ-PKG-05-00315 | PKG-05 | INV-PKG-05-026-04295 | 308.69 | 100047.43 | 5002.37 | Paid | 95045.06 | 2026-Q1
EXP-004911 | 2026-01-02 | BOQ-PKG-01-00931 | PKG-01 | INV-PKG-01-012-04911 | 144.82 | 210861.39 | 10543.07 | Paid | 200318.32 | 2026-Q1
EXP-005301 | 2026-01-02 | BOQ-PKG-01-01321 | PKG-01 | INV-PKG-01-017-05301 | 36.91 | 187381.14 | 9369.06 | Paid | 178012.08 | 2026-Q1
EXP-002415 | 2026-01-03 | BOQ-PKG-05-00425 | PKG-05 | INV-PKG-05-001-02415 | 238.91 | 143420 | 7171 | Approved Pending Payment | 136249 | 2026-Q1
EXP-006173 | 2026-01-03 | BOQ-PKG-03-00203 | PKG-03 | INV-PKG-03-014-06173 | 142.89 | 154355.4 | 7717.77 | Paid | 146637.63 | 2026-Q1
EXP-006452 | 2026-01-03 | BOQ-PKG-02-00482 | PKG-02 | INV-PKG-02-013-06452 | 175.07 | 49442.6 | 2472.13 | Paid | 46970.47 | 2026-Q1
EXP-006515 | 2026-01-03 | BOQ-PKG-05-00545 | PKG-05 | INV-PKG-05-006-06515 | 118.84 | 120689.71 | 6034.49 | Paid | 114655.22 | 2026-Q1
EXP-000414 | 2026-01-04 | BOQ-PKG-04-00414 | PKG-04 | INV-PKG-04-030-00414 | 52.08 | 121359.01 | 6067.95 | Under Review | 115291.06 | 2026-Q1
EXP-003903 | 2026-01-04 | BOQ-PKG-03-01913 | PKG-03 | INV-PKG-03-019-03903 | 369.92 | 195207.86 | 9760.39 | Disputed | 185447.47 | 2026-Q1
EXP-004087 | 2026-01-04 | BOQ-PKG-07-00107 | PKG-07 | INV-PKG-07-028-04087 | 138.18 | 174966.64 | 8748.33 | Approved Pending Payment | 166218.31 | 2026-Q1
EXP-000342 | 2026-01-05 | BOQ-PKG-02-00342 | PKG-02 | INV-PKG-02-028-00342 | 227.78 | 188804.24 | 9440.21 | Paid | 179364.03 | 2026-Q1
EXP-002351 | 2026-01-05 | BOQ-PKG-01-00361 | PKG-01 | INV-PKG-01-007-02351 | 354.01 | 194312.92 | 9715.65 | Paid | 184597.27 | 2026-Q1
EXP-003414 | 2026-01-05 | BOQ-PKG-04-01424 | PKG-04 | INV-PKG-04-020-03414 | 176.97 | 170470.99 | 8523.55 | Paid | 161947.44 | 2026-Q1
EXP-003994 | 2026-01-05 | BOQ-PKG-04-00014 | PKG-04 | INV-PKG-04-005-03994 | 250.8 | 172877.68 | 8643.88 | Under Review | 164233.8 | 2026-Q1
EXP-005009 | 2026-01-05 | BOQ-PKG-09-01029 | PKG-09 | INV-PKG-09-005-05009 | 148.55 | 70797.95 | 3539.9 | Approved Pending Payment | 67258.05 | 2026-Q1
EXP-005223 | 2026-01-05 | BOQ-PKG-03-01243 | PKG-03 | INV-PKG-03-009-05223 | 309.68 | 74538.79 | 3726.94 | Under Review | 70811.85 | 2026-Q1
EXP-006934 | 2026-01-05 | BOQ-PKG-04-00964 | PKG-04 | INV-PKG-04-005-06934 | 314.64 | 177840.95 | 8892.05 | Paid | 168948.9 | 2026-Q1
EXP-000676 | 2026-01-06 | BOQ-PKG-06-00676 | PKG-06 | INV-PKG-06-012-00676 | 443.29 | 195767.92 | 9788.4 | Under Review | 185979.52 | 2026-Q1
EXP-002657 | 2026-01-06 | BOQ-PKG-07-00667 | PKG-07 | INV-PKG-07-033-02657 | 178.13 | 162817.48 | 8140.87 | Under Review | 154676.61 | 2026-Q1
EXP-002795 | 2026-01-06 | BOQ-PKG-05-00805 | PKG-05 | INV-PKG-05-031-02795 | 241.5 | 36196.06 | 1809.8 | Under Review | 34386.26 | 2026-Q1
EXP-002992 | 2026-01-06 | BOQ-PKG-02-01002 | PKG-02 | INV-PKG-02-018-02992 | 325.83 | 185702.87 | 9285.14 | Paid | 176417.73 | 2026-Q1
EXP-003278 | 2026-01-06 | BOQ-PKG-08-01288 | PKG-08 | INV-PKG-08-024-03278 | 421.44 | 114839.62 | 5741.98 | Paid | 109097.64 | 2026-Q1
EXP-005019 | 2026-01-06 | BOQ-PKG-09-01039 | PKG-09 | INV-PKG-09-015-05019 | 299.22 | 112161.72 | 5608.09 | Paid | 106553.63 | 2026-Q1
EXP-005319 | 2026-01-06 | BOQ-PKG-09-01339 | PKG-09 | INV-PKG-09-035-05319 | 323.59 | 154063.01 | 7703.15 | Paid | 146359.86 | 2026-Q1
EXP-002416 | 2026-01-07 | BOQ-PKG-06-00426 | PKG-06 | INV-PKG-06-002-02416 | 162.53 | 208961.21 | 10448.06 | Paid | 198513.15 | 2026-Q1
EXP-002882 | 2026-01-07 | BOQ-PKG-02-00892 | PKG-02 | INV-PKG-02-013-02882 | 238.41 | 26883.58 | 1344.18 | Approved Pending Payment | 25539.4 | 2026-Q1
EXP-004024 | 2026-01-07 | BOQ-PKG-04-00044 | PKG-04 | INV-PKG-04-035-04024 | 234.52 | 193626.02 | 9681.3 | Paid | 183944.72 | 2026-Q1
EXP-006547 | 2026-01-07 | BOQ-PKG-07-00577 | PKG-07 | INV-PKG-07-003-06547 | 336.07 | 98388.87 | 4919.44 | Paid | 93469.43 | 2026-Q1
EXP-000213 | 2026-01-08 | BOQ-PKG-03-00213 | PKG-03 | INV-PKG-03-004-00213 | 268.31 | 60571.31 | 3028.57 | Paid | 57542.74 | 2026-Q1
EXP-000357 | 2026-01-08 | BOQ-PKG-07-00357 | PKG-07 | INV-PKG-07-008-00357 | 421.6 | 194503.15 | 9725.16 | Under Review | 184777.99 | 2026-Q1
EXP-000376 | 2026-01-08 | BOQ-PKG-06-00376 | PKG-06 | INV-PKG-06-027-00376 | 69.02 | 24586.22 | 1229.31 | Paid | 23356.91 | 2026-Q1
EXP-003046 | 2026-01-08 | BOQ-PKG-06-01056 | PKG-06 | INV-PKG-06-002-03046 | 429.17 | 206667.14 | 10333.36 | Under Review | 196333.78 | 2026-Q1
EXP-003065 | 2026-01-08 | BOQ-PKG-05-01075 | PKG-05 | INV-PKG-05-021-03065 | 325.79 | 206157.59 | 10307.88 | Approved Pending Payment | 195849.71 | 2026-Q1
EXP-003743 | 2026-01-08 | BOQ-PKG-03-01753 | PKG-03 | INV-PKG-03-034-03743 | 448.76 | 176005.04 | 8800.25 | Approved Pending Payment | 167204.79 | 2026-Q1
EXP-004599 | 2026-01-08 | BOQ-PKG-09-00619 | PKG-09 | INV-PKG-09-015-04599 | 97.79 | 136493.21 | 6824.66 | Paid | 129668.55 | 2026-Q1
EXP-005697 | 2026-01-08 | BOQ-PKG-07-01717 | PKG-07 | INV-PKG-07-028-05697 | 25.37 | 43449.51 | 2172.48 | Paid | 41277.03 | 2026-Q1
EXP-006125 | 2026-01-08 | BOQ-PKG-05-00155 | PKG-05 | INV-PKG-05-001-06125 | 156.29 | 44466.91 | 2223.35 | Paid | 42243.56 | 2026-Q1
EXP-006208 | 2026-01-08 | BOQ-PKG-08-00238 | PKG-08 | INV-PKG-08-014-06208 | 102.52 | 50986.07 | 2549.3 | Paid | 48436.77 | 2026-Q1
EXP-000594 | 2026-01-09 | BOQ-PKG-04-00594 | PKG-04 | INV-PKG-04-035-00594 | 65.74 | 68629.55 | 3431.48 | Paid | 65198.07 | 2026-Q1
EXP-000878 | 2026-01-09 | BOQ-PKG-08-00878 | PKG-08 | INV-PKG-08-004-00878 | 204.06 | 173004.11 | 8650.21 | Paid | 164353.9 | 2026-Q1
EXP-000965 | 2026-01-09 | BOQ-PKG-05-00965 | PKG-05 | INV-PKG-05-021-00965 | 119.93 | 118088.42 | 5904.42 | Paid | 112184 | 2026-Q1
EXP-003810 | 2026-01-09 | BOQ-PKG-10-01820 | PKG-10 | INV-PKG-10-031-03810 | 322.6 | 141929.48 | 7096.47 | Paid | 134833.01 | 2026-Q1
EXP-006806 | 2026-01-09 | BOQ-PKG-06-00836 | PKG-06 | INV-PKG-06-017-06806 | 216.73 | 82003.57 | 4100.18 | Under Review | 77903.39 | 2026-Q1
EXP-001310 | 2026-01-10 | BOQ-PKG-10-01310 | PKG-10 | INV-PKG-10-016-01310 | 264.24 | 38337.76 | 1916.89 | Paid | 36420.87 | 2026-Q1
EXP-001662 | 2026-01-10 | BOQ-PKG-02-01662 | PKG-02 | INV-PKG-02-018-01662 | 344.99 | 75965.43 | 3798.27 | Paid | 72167.16 | 2026-Q1
EXP-001983 | 2026-01-10 | BOQ-PKG-03-01983 | PKG-03 | INV-PKG-03-024-01983 | 378.74 | 81140.57 | 4057.03 | Paid | 77083.54 | 2026-Q1
EXP-002276 | 2026-01-10 | BOQ-PKG-06-00286 | PKG-06 | INV-PKG-06-002-02276 | 270.97 | 195453.96 | 9772.7 | Paid | 185681.26 | 2026-Q1
EXP-003605 | 2026-01-10 | BOQ-PKG-05-01615 | PKG-05 | INV-PKG-05-001-03605 | 7.9 | 115610.29 | 5780.51 | Paid | 109829.78 | 2026-Q1
EXP-005060 | 2026-01-10 | BOQ-PKG-10-01080 | PKG-10 | INV-PKG-10-021-05060 | 119.69 | 151532.65 | 7576.63 | Paid | 143956.02 | 2026-Q1
EXP-000902 | 2026-01-11 | BOQ-PKG-02-00902 | PKG-02 | INV-PKG-02-028-00902 | 45.71 | 117363.99 | 5868.2 | Paid | 111495.79 | 2026-Q1
EXP-001159 | 2026-01-11 | BOQ-PKG-09-01159 | PKG-09 | INV-PKG-09-005-01159 | 155.77 | 56379.79 | 2818.99 | Approved Pending Payment | 53560.8 | 2026-Q1
EXP-002227 | 2026-01-11 | BOQ-PKG-07-00237 | PKG-07 | INV-PKG-07-023-02227 | 336.18 | 185187.4 | 9259.37 | Paid | 175928.03 | 2026-Q1
EXP-004577 | 2026-01-11 | BOQ-PKG-07-00597 | PKG-07 | INV-PKG-07-028-04577 | 268.66 | 65967.05 | 3298.35 | Approved Pending Payment | 62668.7 | 2026-Q1
EXP-005428 | 2026-01-11 | BOQ-PKG-08-01448 | PKG-08 | INV-PKG-08-004-05428 | 143.3 | 174409.37 | 8720.47 | Paid | 165688.9 | 2026-Q1
EXP-006512 | 2026-01-11 | BOQ-PKG-02-00542 | PKG-02 | INV-PKG-02-003-06512 | 227.97 | 164919.23 | 8245.96 | Paid | 156673.27 | 2026-Q1
EXP-000581 | 2026-01-12 | BOQ-PKG-01-00581 | PKG-01 | INV-PKG-01-022-00581 | 96.62 | 83773.28 | 4188.66 | Under Review | 79584.62 | 2026-Q1
EXP-001433 | 2026-01-12 | BOQ-PKG-03-01433 | PKG-03 | INV-PKG-03-034-01433 | 424.18 | 65670.01 | 3283.5 | Paid | 62386.51 | 2026-Q1
EXP-004374 | 2026-01-12 | BOQ-PKG-04-00394 | PKG-04 | INV-PKG-04-035-04374 | 272.07 | 29314 | 1465.7 | Paid | 27848.3 | 2026-Q1
EXP-004971 | 2026-01-12 | BOQ-PKG-01-00991 | PKG-01 | INV-PKG-01-002-04971 | 169.11 | 54905.69 | 2745.28 | Paid | 52160.41 | 2026-Q1
EXP-000742 | 2026-01-13 | BOQ-PKG-02-00742 | PKG-02 | INV-PKG-02-008-00742 | 337.51 | 80889.82 | 4044.49 | Approved Pending Payment | 76845.33 | 2026-Q1
EXP-001162 | 2026-01-13 | BOQ-PKG-02-01162 | PKG-02 | INV-PKG-02-008-01162 | 44.7 | 63373.93 | 3168.7 | Paid | 60205.23 | 2026-Q1
EXP-002012 | 2026-01-13 | BOQ-PKG-02-00022 | PKG-02 | INV-PKG-02-018-02012 | 133.53 | 100492.72 | 5024.64 | Paid | 95468.08 | 2026-Q1
EXP-002063 | 2026-01-13 | BOQ-PKG-03-00073 | PKG-03 | INV-PKG-03-034-02063 | 10.63 | 62303.12 | 3115.16 | Approved Pending Payment | 59187.96 | 2026-Q1
EXP-004104 | 2026-01-13 | BOQ-PKG-04-00124 | PKG-04 | INV-PKG-04-010-04104 | 104.13 | 207072.78 | 10353.64 | Paid | 196719.14 | 2026-Q1
EXP-004457 | 2026-01-13 | BOQ-PKG-07-00477 | PKG-07 | INV-PKG-07-013-04457 | 390.99 | 88676.36 | 4433.82 | Paid | 84242.54 | 2026-Q1
EXP-005422 | 2026-01-13 | BOQ-PKG-02-01442 | PKG-02 | INV-PKG-02-033-05422 | 435.39 | 90841.37 | 4542.07 | Paid | 86299.3 | 2026-Q1
EXP-006288 | 2026-01-13 | BOQ-PKG-08-00318 | PKG-08 | INV-PKG-08-024-06288 | 48.81 | 129825.32 | 6491.27 | Paid | 123334.05 | 2026-Q1
EXP-006350 | 2026-01-13 | BOQ-PKG-10-00380 | PKG-10 | INV-PKG-10-016-06350 | 82.08 | 91722.34 | 4586.12 | Approved Pending Payment | 87136.22 | 2026-Q1
EXP-006572 | 2026-01-13 | BOQ-PKG-02-00602 | PKG-02 | INV-PKG-02-028-06572 | 433.63 | 141498.96 | 7074.95 | Paid | 134424.01 | 2026-Q1
EXP-001477 | 2026-01-14 | BOQ-PKG-07-01477 | PKG-07 | INV-PKG-07-008-01477 | 195.84 | 163888.28 | 8194.41 | Paid | 155693.87 | 2026-Q1
EXP-002090 | 2026-01-14 | BOQ-PKG-10-00100 | PKG-10 | INV-PKG-10-026-02090 | 319.58 | 31546.74 | 1577.34 | Paid | 29969.4 | 2026-Q1
EXP-003650 | 2026-01-14 | BOQ-PKG-10-01660 | PKG-10 | INV-PKG-10-011-03650 | 389.17 | 92238.63 | 4611.93 | Paid | 87626.7 | 2026-Q1
EXP-004186 | 2026-01-14 | BOQ-PKG-06-00206 | PKG-06 | INV-PKG-06-022-04186 | 448.29 | 71291.95 | 3564.6 | Paid | 67727.35 | 2026-Q1
EXP-000635 | 2026-01-15 | BOQ-PKG-05-00635 | PKG-05 | INV-PKG-05-006-00635 | 51.26 | 209847 | 10492.35 | Paid | 199354.65 | 2026-Q1
EXP-000739 | 2026-01-15 | BOQ-PKG-09-00739 | PKG-09 | INV-PKG-09-005-00739 | 254.8 | 189185.36 | 9459.27 | Paid | 179726.09 | 2026-Q1
EXP-001149 | 2026-01-15 | BOQ-PKG-09-01149 | PKG-09 | INV-PKG-09-030-01149 | 210.74 | 160172.85 | 8008.64 | Paid | 152164.21 | 2026-Q1
EXP-002017 | 2026-01-15 | BOQ-PKG-07-00027 | PKG-07 | INV-PKG-07-023-02017 | 434.85 | 119721.45 | 5986.07 | Approved Pending Payment | 113735.38 | 2026-Q1
EXP-002631 | 2026-01-15 | BOQ-PKG-01-00641 | PKG-01 | INV-PKG-01-007-02631 | 104.22 | 136192.94 | 6809.65 | Disputed | 129383.29 | 2026-Q1
EXP-002906 | 2026-01-15 | BOQ-PKG-06-00916 | PKG-06 | INV-PKG-06-002-02906 | 248.96 | 120648.57 | 6032.43 | Paid | 114616.14 | 2026-Q1
EXP-003062 | 2026-01-15 | BOQ-PKG-02-01072 | PKG-02 | INV-PKG-02-018-03062 | 287.6 | 70223.54 | 3511.18 | Approved Pending Payment | 66712.36 | 2026-Q1
EXP-003829 | 2026-01-15 | BOQ-PKG-09-01839 | PKG-09 | INV-PKG-09-015-03829 | 164.96 | 56110.7 | 2805.54 | Paid | 53305.16 | 2026-Q1
EXP-003883 | 2026-01-15 | BOQ-PKG-03-01893 | PKG-03 | INV-PKG-03-034-03883 | 122.61 | 163937.38 | 8196.87 | Approved Pending Payment | 155740.51 | 2026-Q1
EXP-006182 | 2026-01-15 | BOQ-PKG-02-00212 | PKG-02 | INV-PKG-02-023-06182 | 426.43 | 132530.9 | 6626.54 | Paid | 125904.36 | 2026-Q1
EXP-006669 | 2026-01-15 | BOQ-PKG-09-00699 | PKG-09 | INV-PKG-09-020-06669 | 356.9 | 80964.94 | 4048.25 | Approved Pending Payment | 76916.69 | 2026-Q1
EXP-001861 | 2026-01-16 | BOQ-PKG-01-01861 | PKG-01 | INV-PKG-01-007-01861 | 33.78 | 137008.8 | 6850.44 | Paid | 130158.36 | 2026-Q1
EXP-003166 | 2026-01-16 | BOQ-PKG-06-01176 | PKG-06 | INV-PKG-06-017-03166 | 283.97 | 27550.65 | 1377.53 | Paid | 26173.12 | 2026-Q1
EXP-003263 | 2026-01-16 | BOQ-PKG-03-01273 | PKG-03 | INV-PKG-03-009-03263 | 367.19 | 124620.77 | 6231.04 | Paid | 118389.73 | 2026-Q1
EXP-003755 | 2026-01-16 | BOQ-PKG-05-01765 | PKG-05 | INV-PKG-05-011-03755 | 412.83 | 186860.44 | 9343.02 | Disputed | 177517.42 | 2026-Q1
EXP-004990 | 2026-01-16 | BOQ-PKG-10-01010 | PKG-10 | INV-PKG-10-021-04990 | 227.16 | 93067.52 | 4653.38 | Paid | 88414.14 | 2026-Q1
EXP-005311 | 2026-01-16 | BOQ-PKG-01-01331 | PKG-01 | INV-PKG-01-027-05311 | 260.99 | 74199.06 | 3709.95 | Disputed | 70489.11 | 2026-Q1
EXP-005702 | 2026-01-16 | BOQ-PKG-02-01722 | PKG-02 | INV-PKG-02-033-05702 | 242.93 | 114402.03 | 5720.1 | Paid | 108681.93 | 2026-Q1
EXP-005798 | 2026-01-16 | BOQ-PKG-08-01818 | PKG-08 | INV-PKG-08-024-05798 | 262.51 | 204705.09 | 10235.25 | Approved Pending Payment | 194469.84 | 2026-Q1
EXP-005905 | 2026-01-16 | BOQ-PKG-05-01925 | PKG-05 | INV-PKG-05-026-05905 | 290.35 | 154245.03 | 7712.25 | Under Review | 146532.78 | 2026-Q1
EXP-000549 | 2026-01-17 | BOQ-PKG-09-00549 | PKG-09 | INV-PKG-09-025-00549 | 38.61 | 177446.19 | 8872.31 | Paid | 168573.88 | 2026-Q1
EXP-000808 | 2026-01-17 | BOQ-PKG-08-00808 | PKG-08 | INV-PKG-08-004-00808 | 215.58 | 138798.39 | 6939.92 | Under Review | 131858.47 | 2026-Q1
EXP-001340 | 2026-01-17 | BOQ-PKG-10-01340 | PKG-10 | INV-PKG-10-011-01340 | 394.39 | 135224.1 | 6761.21 | Paid | 128462.89 | 2026-Q1
EXP-002156 | 2026-01-17 | BOQ-PKG-06-00166 | PKG-06 | INV-PKG-06-022-02156 | 234.91 | 140189.88 | 7009.49 | Paid | 133180.39 | 2026-Q1
EXP-002682 | 2026-01-17 | BOQ-PKG-02-00692 | PKG-02 | INV-PKG-02-023-02682 | 282.01 | 115278.01 | 5763.9 | Paid | 109514.11 | 2026-Q1
EXP-003405 | 2026-01-17 | BOQ-PKG-05-01415 | PKG-05 | INV-PKG-05-011-03405 | 219.11 | 165525.13 | 8276.26 | Paid | 157248.87 | 2026-Q1
EXP-003839 | 2026-01-17 | BOQ-PKG-09-01849 | PKG-09 | INV-PKG-09-025-03839 | 125.88 | 165784.52 | 8289.23 | Approved Pending Payment | 157495.29 | 2026-Q1
EXP-004449 | 2026-01-17 | BOQ-PKG-09-00469 | PKG-09 | INV-PKG-09-005-04449 | 179.69 | 150300.89 | 7515.04 | Paid | 142785.85 | 2026-Q1
EXP-005721 | 2026-01-17 | BOQ-PKG-01-01741 | PKG-01 | INV-PKG-01-017-05721 | 172.92 | 55145.71 | 2757.29 | Paid | 52388.42 | 2026-Q1
EXP-001454 | 2026-01-18 | BOQ-PKG-04-01454 | PKG-04 | INV-PKG-04-020-01454 | 216.1 | 88526.66 | 4426.33 | Approved Pending Payment | 84100.33 | 2026-Q1
EXP-001937 | 2026-01-18 | BOQ-PKG-07-01937 | PKG-07 | INV-PKG-07-013-01937 | 116.11 | 139651.89 | 6982.59 | Paid | 132669.3 | 2026-Q1
EXP-003316 | 2026-01-18 | BOQ-PKG-06-01326 | PKG-06 | INV-PKG-06-027-03316 | 184.73 | 146838.35 | 7341.92 | Paid | 139496.43 | 2026-Q1
EXP-004326 | 2026-01-18 | BOQ-PKG-06-00346 | PKG-06 | INV-PKG-06-022-04326 | 414.62 | 136066.95 | 6803.35 | Approved Pending Payment | 129263.6 | 2026-Q1
EXP-005797 | 2026-01-18 | BOQ-PKG-07-01817 | PKG-07 | INV-PKG-07-023-05797 | 326.67 | 166020.36 | 8301.02 | Disputed | 157719.34 | 2026-Q1
EXP-000567 | 2026-01-19 | BOQ-PKG-07-00567 | PKG-07 | INV-PKG-07-008-00567 | 28.17 | 26941.03 | 1347.05 | Paid | 25593.98 | 2026-Q1
EXP-001126 | 2026-01-19 | BOQ-PKG-06-01126 | PKG-06 | INV-PKG-06-007-01126 | 367.15 | 113402.87 | 5670.14 | Approved Pending Payment | 107732.73 | 2026-Q1
EXP-002039 | 2026-01-19 | BOQ-PKG-09-00049 | PKG-09 | INV-PKG-09-010-02039 | 18.54 | 153292.95 | 7664.65 | Under Review | 145628.3 | 2026-Q1
EXP-004463 | 2026-01-19 | BOQ-PKG-03-00483 | PKG-03 | INV-PKG-03-019-04463 | 136.86 | 153606.58 | 7680.33 | Paid | 145926.25 | 2026-Q1
EXP-004978 | 2026-01-19 | BOQ-PKG-08-00998 | PKG-08 | INV-PKG-08-009-04978 | 181.09 | 205472.23 | 10273.61 | Disputed | 195198.62 | 2026-Q1
EXP-005184 | 2026-01-19 | BOQ-PKG-04-01204 | PKG-04 | INV-PKG-04-005-05184 | 113.11 | 76963.64 | 3848.18 | Under Review | 73115.46 | 2026-Q1
EXP-001431 | 2026-01-20 | BOQ-PKG-01-01431 | PKG-01 | INV-PKG-01-032-01431 | 133.23 | 85610.84 | 4280.54 | Paid | 81330.3 | 2026-Q1
EXP-001677 | 2026-01-20 | BOQ-PKG-07-01677 | PKG-07 | INV-PKG-07-033-01677 | 155.11 | 137138.45 | 6856.92 | Paid | 130281.53 | 2026-Q1
EXP-002162 | 2026-01-20 | BOQ-PKG-02-00172 | PKG-02 | INV-PKG-02-028-02162 | 334.22 | 120393.97 | 6019.7 | Under Review | 114374.27 | 2026-Q1
EXP-003092 | 2026-01-20 | BOQ-PKG-02-01102 | PKG-02 | INV-PKG-02-013-03092 | 202.31 | 29486.26 | 1474.31 | Under Review | 28011.95 | 2026-Q1
EXP-003129 | 2026-01-20 | BOQ-PKG-09-01139 | PKG-09 | INV-PKG-09-015-03129 | 238.55 | 78937.71 | 3946.89 | Paid | 74990.82 | 2026-Q1
EXP-003776 | 2026-01-20 | BOQ-PKG-06-01786 | PKG-06 | INV-PKG-06-032-03776 | 294.99 | 65825.5 | 3291.28 | Paid | 62534.22 | 2026-Q1
EXP-003783 | 2026-01-20 | BOQ-PKG-03-01793 | PKG-03 | INV-PKG-03-004-03783 | 60.43 | 143661.46 | 7183.07 | Approved Pending Payment | 136478.39 | 2026-Q1
EXP-004049 | 2026-01-20 | BOQ-PKG-09-00069 | PKG-09 | INV-PKG-09-025-04049 | 423.63 | 82654.32 | 4132.72 | Paid | 78521.6 | 2026-Q1
EXP-005399 | 2026-01-20 | BOQ-PKG-09-01419 | PKG-09 | INV-PKG-09-010-05399 | 121.53 | 104837.3 | 5241.87 | Paid | 99595.43 | 2026-Q1
EXP-006200 | 2026-01-20 | BOQ-PKG-10-00230 | PKG-10 | INV-PKG-10-006-06200 | 392.39 | 107949.99 | 5397.5 | Disputed | 102552.49 | 2026-Q1
EXP-006930 | 2026-01-20 | BOQ-PKG-10-00960 | PKG-10 | INV-PKG-10-001-06930 | 233.24 | 88209.87 | 4410.49 | Paid | 83799.38 | 2026-Q1
EXP-000308 | 2026-01-21 | BOQ-PKG-08-00308 | PKG-08 | INV-PKG-08-029-00308 | 364.54 | 162230.33 | 8111.52 | Paid | 154118.81 | 2026-Q1
EXP-001323 | 2026-01-21 | BOQ-PKG-03-01323 | PKG-03 | INV-PKG-03-029-01323 | 283.5 | 98396.68 | 4919.83 | Approved Pending Payment | 93476.85 | 2026-Q1
EXP-002198 | 2026-01-21 | BOQ-PKG-08-00208 | PKG-08 | INV-PKG-08-029-02198 | 197.09 | 85371.43 | 4268.57 | Paid | 81102.86 | 2026-Q1
EXP-003314 | 2026-01-21 | BOQ-PKG-04-01324 | PKG-04 | INV-PKG-04-025-03314 | 355.61 | 31304.78 | 1565.24 | Under Review | 29739.54 | 2026-Q1
EXP-005432 | 2026-01-21 | BOQ-PKG-02-01452 | PKG-02 | INV-PKG-02-008-05432 | 181.6 | 193975.56 | 9698.78 | Paid | 184276.78 | 2026-Q1
EXP-006004 | 2026-01-21 | BOQ-PKG-04-00034 | PKG-04 | INV-PKG-04-020-06004 | 339.1 | 85556.08 | 4277.8 | Approved Pending Payment | 81278.28 | 2026-Q1
EXP-006713 | 2026-01-21 | BOQ-PKG-03-00743 | PKG-03 | INV-PKG-03-029-06713 | 159.66 | 118650.04 | 5932.5 | Paid | 112717.54 | 2026-Q1
EXP-006720 | 2026-01-21 | BOQ-PKG-10-00750 | PKG-10 | INV-PKG-10-001-06720 | 377.87 | 49496.09 | 2474.8 | Paid | 47021.29 | 2026-Q1
EXP-001090 | 2026-01-22 | BOQ-PKG-10-01090 | PKG-10 | INV-PKG-10-006-01090 | 132.01 | 180600.55 | 9030.03 | Approved Pending Payment | 171570.52 | 2026-Q1
EXP-003042 | 2026-01-22 | BOQ-PKG-02-01052 | PKG-02 | INV-PKG-02-033-03042 | 366.5 | 127881.84 | 6394.09 | Paid | 121487.75 | 2026-Q1
EXP-004255 | 2026-01-22 | BOQ-PKG-05-00275 | PKG-05 | INV-PKG-05-021-04255 | 433.38 | 85602.31 | 4280.12 | Paid | 81322.19 | 2026-Q1
EXP-004661 | 2026-01-22 | BOQ-PKG-01-00681 | PKG-01 | INV-PKG-01-007-04661 | 181.01 | 175594.56 | 8779.73 | Paid | 166814.83 | 2026-Q1
EXP-005703 | 2026-01-22 | BOQ-PKG-03-01723 | PKG-03 | INV-PKG-03-034-05703 | 401.61 | 121320.71 | 6066.04 | Paid | 115254.67 | 2026-Q1
EXP-006596 | 2026-01-22 | BOQ-PKG-06-00626 | PKG-06 | INV-PKG-06-017-06596 | 294.4 | 53122.45 | 2656.12 | Approved Pending Payment | 50466.33 | 2026-Q1
EXP-006767 | 2026-01-22 | BOQ-PKG-07-00797 | PKG-07 | INV-PKG-07-013-06767 | 328.14 | 201314.67 | 10065.73 | Paid | 191248.94 | 2026-Q1
EXP-000831 | 2026-01-23 | BOQ-PKG-01-00831 | PKG-01 | INV-PKG-01-027-00831 | 275.81 | 203185.82 | 10159.29 | Paid | 193026.53 | 2026-Q1
EXP-001717 | 2026-01-23 | BOQ-PKG-07-01717 | PKG-07 | INV-PKG-07-003-01717 | 115.67 | 155305.91 | 7765.3 | Paid | 147540.61 | 2026-Q1
EXP-002445 | 2026-01-23 | BOQ-PKG-05-00455 | PKG-05 | INV-PKG-05-031-02445 | 347.7 | 68651.94 | 3432.6 | Disputed | 65219.34 | 2026-Q1
EXP-002699 | 2026-01-23 | BOQ-PKG-09-00709 | PKG-09 | INV-PKG-09-005-02699 | 149.91 | 111645.08 | 5582.25 | Paid | 106062.83 | 2026-Q1
EXP-003490 | 2026-01-23 | BOQ-PKG-10-01500 | PKG-10 | INV-PKG-10-026-03490 | 138.2 | 63627.33 | 3181.37 | Paid | 60445.96 | 2026-Q1
EXP-003547 | 2026-01-23 | BOQ-PKG-07-01557 | PKG-07 | INV-PKG-07-013-03547 | 180.09 | 175391.91 | 8769.6 | Approved Pending Payment | 166622.31 | 2026-Q1
EXP-005962 | 2026-01-23 | BOQ-PKG-02-01982 | PKG-02 | INV-PKG-02-013-05962 | 440.88 | 41480.48 | 2074.02 | Paid | 39406.46 | 2026-Q1
EXP-001234 | 2026-01-24 | BOQ-PKG-04-01234 | PKG-04 | INV-PKG-04-010-01234 | 353.85 | 124283.2 | 6214.16 | Paid | 118069.04 | 2026-Q1
EXP-001468 | 2026-01-24 | BOQ-PKG-08-01468 | PKG-08 | INV-PKG-08-034-01468 | 272.94 | 107657.65 | 5382.88 | Under Review | 102274.77 | 2026-Q1
EXP-001718 | 2026-01-24 | BOQ-PKG-08-01718 | PKG-08 | INV-PKG-08-004-01718 | 327.53 | 35275.57 | 1763.78 | Paid | 33511.79 | 2026-Q1
EXP-001778 | 2026-01-24 | BOQ-PKG-08-01778 | PKG-08 | INV-PKG-08-029-01778 | 156.35 | 57685.41 | 2884.27 | Paid | 54801.14 | 2026-Q1
EXP-002354 | 2026-01-24 | BOQ-PKG-04-00364 | PKG-04 | INV-PKG-04-010-02354 | 290.23 | 34137.67 | 1706.88 | Paid | 32430.79 | 2026-Q1
EXP-002871 | 2026-01-24 | BOQ-PKG-01-00881 | PKG-01 | INV-PKG-01-002-02871 | 227.91 | 91380.59 | 4569.03 | Paid | 86811.56 | 2026-Q1
EXP-002913 | 2026-01-24 | BOQ-PKG-03-00923 | PKG-03 | INV-PKG-03-009-02913 | 433.61 | 118076.79 | 5903.84 | Paid | 112172.95 | 2026-Q1
EXP-003782 | 2026-01-24 | BOQ-PKG-02-01792 | PKG-02 | INV-PKG-02-003-03782 | 277.56 | 39366.31 | 1968.32 | Paid | 37397.99 | 2026-Q1
EXP-004082 | 2026-01-24 | BOQ-PKG-02-00102 | PKG-02 | INV-PKG-02-023-04082 | 290.98 | 206678.09 | 10333.9 | Under Review | 196344.19 | 2026-Q1
EXP-004166 | 2026-01-24 | BOQ-PKG-06-00186 | PKG-06 | INV-PKG-06-002-04166 | 246.58 | 71495.7 | 3574.78 | Under Review | 67920.92 | 2026-Q1
EXP-004554 | 2026-01-24 | BOQ-PKG-04-00574 | PKG-04 | INV-PKG-04-005-04554 | 205.64 | 204169.16 | 10208.46 | Paid | 193960.7 | 2026-Q1
EXP-005139 | 2026-01-24 | BOQ-PKG-09-01159 | PKG-09 | INV-PKG-09-030-05139 | 414.99 | 74535.46 | 3726.77 | Paid | 70808.69 | 2026-Q1
EXP-005348 | 2026-01-24 | BOQ-PKG-08-01368 | PKG-08 | INV-PKG-08-029-05348 | 114.79 | 100821.05 | 5041.05 | Approved Pending Payment | 95780 | 2026-Q1
EXP-005945 | 2026-01-24 | BOQ-PKG-05-01965 | PKG-05 | INV-PKG-05-031-05945 | 19.24 | 120223.93 | 6011.2 | Paid | 114212.73 | 2026-Q1
EXP-006838 | 2026-01-24 | BOQ-PKG-08-00868 | PKG-08 | INV-PKG-08-014-06838 | 104.17 | 121348.52 | 6067.43 | Paid | 115281.09 | 2026-Q1
EXP-006854 | 2026-01-24 | BOQ-PKG-04-00884 | PKG-04 | INV-PKG-04-030-06854 | 350.77 | 211035.44 | 10551.77 | Paid | 200483.67 | 2026-Q1
EXP-001079 | 2026-01-25 | BOQ-PKG-09-01079 | PKG-09 | INV-PKG-09-030-01079 | 90.34 | 34259.31 | 1712.97 | Paid | 32546.34 | 2026-Q1
EXP-001145 | 2026-01-25 | BOQ-PKG-05-01145 | PKG-05 | INV-PKG-05-026-01145 | 100.68 | 161258.62 | 8062.93 | Paid | 153195.69 | 2026-Q1
EXP-001920 | 2026-01-25 | BOQ-PKG-10-01920 | PKG-10 | INV-PKG-10-031-01920 | 145.04 | 118097.5 | 5904.88 | Paid | 112192.62 | 2026-Q1
EXP-002622 | 2026-01-25 | BOQ-PKG-02-00632 | PKG-02 | INV-PKG-02-033-02622 | 358.53 | 71989.75 | 3599.49 | Disputed | 68390.26 | 2026-Q1
EXP-002675 | 2026-01-25 | BOQ-PKG-05-00685 | PKG-05 | INV-PKG-05-016-02675 | 325.7 | 142435.09 | 7121.75 | Paid | 135313.34 | 2026-Q1
EXP-002917 | 2026-01-25 | BOQ-PKG-07-00927 | PKG-07 | INV-PKG-07-013-02917 | 291.51 | 45295.36 | 2264.77 | Paid | 43030.59 | 2026-Q1
EXP-003771 | 2026-01-25 | BOQ-PKG-01-01781 | PKG-01 | INV-PKG-01-027-03771 | 181.86 | 96808.35 | 4840.42 | Paid | 91967.93 | 2026-Q1
EXP-004317 | 2026-01-25 | BOQ-PKG-07-00337 | PKG-07 | INV-PKG-07-013-04317 | 38.08 | 82241.04 | 4112.05 | Paid | 78128.99 | 2026-Q1
EXP-004951 | 2026-01-25 | BOQ-PKG-01-00971 | PKG-01 | INV-PKG-01-017-04951 | 11.41 | 49643.7 | 2482.18 | Paid | 47161.52 | 2026-Q1
EXP-005013 | 2026-01-25 | BOQ-PKG-03-01033 | PKG-03 | INV-PKG-03-009-05013 | 295.99 | 107436.59 | 5371.83 | Paid | 102064.76 | 2026-Q1
EXP-006993 | 2026-01-25 | BOQ-PKG-03-01023 | PKG-03 | INV-PKG-03-029-06993 | 240.27 | 48101.1 | 2405.05 | Approved Pending Payment | 45696.05 | 2026-Q1
EXP-000338 | 2026-01-26 | BOQ-PKG-08-00338 | PKG-08 | INV-PKG-08-024-00338 | 317.96 | 173493.24 | 8674.66 | Approved Pending Payment | 164818.58 | 2026-Q1
EXP-000802 | 2026-01-26 | BOQ-PKG-02-00802 | PKG-02 | INV-PKG-02-033-00802 | 353.86 | 111051.91 | 5552.6 | Approved Pending Payment | 105499.31 | 2026-Q1
EXP-002790 | 2026-01-26 | BOQ-PKG-10-00800 | PKG-10 | INV-PKG-10-026-02790 | 79.12 | 32799.31 | 1639.97 | Approved Pending Payment | 31159.34 | 2026-Q1
EXP-003835 | 2026-01-26 | BOQ-PKG-05-01845 | PKG-05 | INV-PKG-05-021-03835 | 205.19 | 122583.92 | 6129.2 | Paid | 116454.72 | 2026-Q1
EXP-004406 | 2026-01-26 | BOQ-PKG-06-00426 | PKG-06 | INV-PKG-06-032-04406 | 11.53 | 141493.53 | 7074.68 | Paid | 134418.85 | 2026-Q1
EXP-004440 | 2026-01-26 | BOQ-PKG-10-00460 | PKG-10 | INV-PKG-10-031-04440 | 320.48 | 60090.27 | 3004.51 | Approved Pending Payment | 57085.76 | 2026-Q1
EXP-004565 | 2026-01-26 | BOQ-PKG-05-00585 | PKG-05 | INV-PKG-05-016-04565 | 374.28 | 208444.9 | 10422.25 | Under Review | 198022.65 | 2026-Q1
EXP-005394 | 2026-01-26 | BOQ-PKG-04-01414 | PKG-04 | INV-PKG-04-005-05394 | 44.44 | 38257.98 | 1912.9 | Paid | 36345.08 | 2026-Q1
EXP-000465 | 2026-01-27 | BOQ-PKG-05-00465 | PKG-05 | INV-PKG-05-011-00465 | 201.98 | 117036.27 | 5851.81 | Paid | 111184.46 | 2026-Q1
EXP-001979 | 2026-01-27 | BOQ-PKG-09-01979 | PKG-09 | INV-PKG-09-020-01979 | 142.62 | 148338.91 | 7416.95 | Paid | 140921.96 | 2026-Q1
EXP-002269 | 2026-01-27 | BOQ-PKG-09-00279 | PKG-09 | INV-PKG-09-030-02269 | 337.04 | 34411.85 | 1720.59 | Paid | 32691.26 | 2026-Q1
EXP-002458 | 2026-01-27 | BOQ-PKG-08-00468 | PKG-08 | INV-PKG-08-009-02458 | 430.34 | 134159.59 | 6707.98 | Paid | 127451.61 | 2026-Q1
EXP-002656 | 2026-01-27 | BOQ-PKG-06-00666 | PKG-06 | INV-PKG-06-032-02656 | 15.26 | 209910.98 | 10495.55 | Approved Pending Payment | 199415.43 | 2026-Q1
EXP-002976 | 2026-01-27 | BOQ-PKG-06-00986 | PKG-06 | INV-PKG-06-002-02976 | 76.47 | 203199.91 | 10160 | Paid | 193039.91 | 2026-Q1
EXP-003364 | 2026-01-27 | BOQ-PKG-04-01374 | PKG-04 | INV-PKG-04-005-03364 | 420.59 | 93954.94 | 4697.75 | Paid | 89257.19 | 2026-Q1
EXP-005320 | 2026-01-27 | BOQ-PKG-10-01340 | PKG-10 | INV-PKG-10-001-05320 | 46.86 | 26832.61 | 1341.63 | Paid | 25490.98 | 2026-Q1
EXP-005386 | 2026-01-27 | BOQ-PKG-06-01406 | PKG-06 | INV-PKG-06-032-05386 | 98.27 | 155282.07 | 7764.1 | Under Review | 147517.97 | 2026-Q1
EXP-006421 | 2026-01-27 | BOQ-PKG-01-00451 | PKG-01 | INV-PKG-01-017-06421 | 320.52 | 71879.92 | 3594 | Paid | 68285.92 | 2026-Q1
EXP-006808 | 2026-01-27 | BOQ-PKG-08-00838 | PKG-08 | INV-PKG-08-019-06808 | 181.86 | 54453.71 | 2722.69 | Paid | 51731.02 | 2026-Q1
EXP-000265 | 2026-01-28 | BOQ-PKG-05-00265 | PKG-05 | INV-PKG-05-021-00265 | 9.68 | 171311.76 | 8565.59 | Paid | 162746.17 | 2026-Q1
EXP-000613 | 2026-01-28 | BOQ-PKG-03-00613 | PKG-03 | INV-PKG-03-019-00613 | 180.69 | 140606.25 | 7030.31 | Under Review | 133575.94 | 2026-Q1
EXP-001248 | 2026-01-28 | BOQ-PKG-08-01248 | PKG-08 | INV-PKG-08-024-01248 | 282.02 | 83033.99 | 4151.7 | Paid | 78882.29 | 2026-Q1
EXP-003038 | 2026-01-28 | BOQ-PKG-08-01048 | PKG-08 | INV-PKG-08-029-03038 | 14.61 | 92317.28 | 4615.86 | Approved Pending Payment | 87701.42 | 2026-Q1
EXP-003433 | 2026-01-28 | BOQ-PKG-03-01443 | PKG-03 | INV-PKG-03-004-03433 | 40.47 | 50568.14 | 2528.41 | Paid | 48039.73 | 2026-Q1
EXP-003763 | 2026-01-28 | BOQ-PKG-03-01773 | PKG-03 | INV-PKG-03-019-03763 | 328.91 | 99858.55 | 4992.93 | Approved Pending Payment | 94865.62 | 2026-Q1
EXP-003905 | 2026-01-28 | BOQ-PKG-05-01915 | PKG-05 | INV-PKG-05-021-03905 | 418.93 | 164140.58 | 8207.03 | Paid | 155933.55 | 2026-Q1
EXP-004145 | 2026-01-28 | BOQ-PKG-05-00165 | PKG-05 | INV-PKG-05-016-04145 | 449.68 | 186444.09 | 9322.2 | Paid | 177121.89 | 2026-Q1
EXP-005025 | 2026-01-28 | BOQ-PKG-05-01045 | PKG-05 | INV-PKG-05-021-05025 | 372.98 | 186260.88 | 9313.04 | Under Review | 176947.84 | 2026-Q1
EXP-000075 | 2026-01-29 | BOQ-PKG-05-00075 | PKG-05 | INV-PKG-05-006-00075 | 271.36 | 104895.16 | 5244.76 | Paid | 99650.4 | 2026-Q1
EXP-001165 | 2026-01-29 | BOQ-PKG-05-01165 | PKG-05 | INV-PKG-05-011-01165 | 94 | 49033.48 | 2451.67 | Paid | 46581.81 | 2026-Q1
EXP-001895 | 2026-01-29 | BOQ-PKG-05-01895 | PKG-05 | INV-PKG-05-006-01895 | 270.29 | 185834.75 | 9291.74 | Paid | 176543.01 | 2026-Q1
EXP-002745 | 2026-01-29 | BOQ-PKG-05-00755 | PKG-05 | INV-PKG-05-016-02745 | 54.89 | 97133.13 | 4856.66 | Paid | 92276.47 | 2026-Q1
EXP-005341 | 2026-01-29 | BOQ-PKG-01-01361 | PKG-01 | INV-PKG-01-022-05341 | 37.03 | 201832.59 | 10091.63 | Paid | 191740.96 | 2026-Q1
EXP-006771 | 2026-01-29 | BOQ-PKG-01-00801 | PKG-01 | INV-PKG-01-017-06771 | 35.75 | 99708.42 | 4985.42 | Under Review | 94723 | 2026-Q1
EXP-001528 | 2026-01-30 | BOQ-PKG-08-01528 | PKG-08 | INV-PKG-08-024-01528 | 148.01 | 31949.41 | 1597.47 | Paid | 30351.94 | 2026-Q1
EXP-002109 | 2026-01-30 | BOQ-PKG-09-00119 | PKG-09 | INV-PKG-09-010-02109 | 424.15 | 183399.41 | 9169.97 | Paid | 174229.44 | 2026-Q1
EXP-002264 | 2026-01-30 | BOQ-PKG-04-00274 | PKG-04 | INV-PKG-04-025-02264 | 405.67 | 65379.66 | 3268.98 | Paid | 62110.68 | 2026-Q1
EXP-003211 | 2026-01-30 | BOQ-PKG-01-01221 | PKG-01 | INV-PKG-01-027-03211 | 55.06 | 157734.49 | 7886.72 | Paid | 149847.77 | 2026-Q1
EXP-004588 | 2026-01-30 | BOQ-PKG-08-00608 | PKG-08 | INV-PKG-08-004-04588 | 250.2 | 45760.34 | 2288.02 | Approved Pending Payment | 43472.32 | 2026-Q1
EXP-004631 | 2026-01-30 | BOQ-PKG-01-00651 | PKG-01 | INV-PKG-01-012-04631 | 263.94 | 176253.03 | 8812.65 | Paid | 167440.38 | 2026-Q1
EXP-004822 | 2026-01-30 | BOQ-PKG-02-00842 | PKG-02 | INV-PKG-02-028-04822 | 54.31 | 196168.22 | 9808.41 | Paid | 186359.81 | 2026-Q1
EXP-004936 | 2026-01-30 | BOQ-PKG-06-00956 | PKG-06 | INV-PKG-06-002-04936 | 102.74 | 172869.26 | 8643.46 | Paid | 164225.8 | 2026-Q1
EXP-005444 | 2026-01-30 | BOQ-PKG-04-01464 | PKG-04 | INV-PKG-04-020-05444 | 360.96 | 179490.56 | 8974.53 | Under Review | 170516.03 | 2026-Q1
EXP-006319 | 2026-01-30 | BOQ-PKG-09-00349 | PKG-09 | INV-PKG-09-020-06319 | 17.46 | 36229.35 | 1811.47 | Paid | 34417.88 | 2026-Q1
EXP-006886 | 2026-01-30 | BOQ-PKG-06-00916 | PKG-06 | INV-PKG-06-027-06886 | 370.23 | 126402.15 | 6320.11 | Paid | 120082.04 | 2026-Q1
EXP-000430 | 2026-01-31 | BOQ-PKG-10-00430 | PKG-10 | INV-PKG-10-011-00430 | 231.83 | 77779.47 | 3888.97 | Paid | 73890.5 | 2026-Q1
EXP-001272 | 2026-01-31 | BOQ-PKG-02-01272 | PKG-02 | INV-PKG-02-013-01272 | 116.28 | 100613.31 | 5030.67 | Approved Pending Payment | 95582.64 | 2026-Q1
EXP-001363 | 2026-01-31 | BOQ-PKG-03-01363 | PKG-03 | INV-PKG-03-034-01363 | 155.83 | 171799.66 | 8589.98 | Paid | 163209.68 | 2026-Q1
EXP-002174 | 2026-01-31 | BOQ-PKG-04-00184 | PKG-04 | INV-PKG-04-005-02174 | 167.2 | 210084.6 | 10504.23 | Paid | 199580.37 | 2026-Q1
EXP-002792 | 2026-01-31 | BOQ-PKG-02-00802 | PKG-02 | INV-PKG-02-028-02792 | 297.13 | 115018.76 | 5750.94 | Under Review | 109267.82 | 2026-Q1
EXP-000865 | 2026-02-01 | BOQ-PKG-05-00865 | PKG-05 | INV-PKG-05-026-00865 | 120.27 | 152766.29 | 7638.31 | Paid | 145127.98 | 2026-Q1
EXP-001076 | 2026-02-01 | BOQ-PKG-06-01076 | PKG-06 | INV-PKG-06-027-01076 | 376.79 | 55814.01 | 2790.7 | Paid | 53023.31 | 2026-Q1
EXP-002720 | 2026-02-01 | BOQ-PKG-10-00730 | PKG-10 | INV-PKG-10-026-02720 | 17.34 | 33387.4 | 1669.37 | Approved Pending Payment | 31718.03 | 2026-Q1
EXP-002858 | 2026-02-01 | BOQ-PKG-08-00868 | PKG-08 | INV-PKG-08-024-02858 | 297.97 | 116099.83 | 5804.99 | Paid | 110294.84 | 2026-Q1
EXP-002958 | 2026-02-01 | BOQ-PKG-08-00968 | PKG-08 | INV-PKG-08-019-02958 | 283.52 | 88422.6 | 4421.13 | Approved Pending Payment | 84001.47 | 2026-Q1
EXP-004447 | 2026-02-01 | BOQ-PKG-07-00467 | PKG-07 | INV-PKG-07-003-04447 | 203.96 | 81077.53 | 4053.88 | Approved Pending Payment | 77023.65 | 2026-Q1
EXP-006661 | 2026-02-01 | BOQ-PKG-01-00691 | PKG-01 | INV-PKG-01-012-06661 | 428.53 | 89934.88 | 4496.74 | Paid | 85438.14 | 2026-Q1
EXP-001281 | 2026-02-02 | BOQ-PKG-01-01281 | PKG-01 | INV-PKG-01-022-01281 | 320.07 | 73428.26 | 3671.41 | Under Review | 69756.85 | 2026-Q1
EXP-001526 | 2026-02-02 | BOQ-PKG-06-01526 | PKG-06 | INV-PKG-06-022-01526 | 161.39 | 53121.98 | 2656.1 | Paid | 50465.88 | 2026-Q1
EXP-002342 | 2026-02-02 | BOQ-PKG-02-00352 | PKG-02 | INV-PKG-02-033-02342 | 418.86 | 44987.39 | 2249.37 | Under Review | 42738.02 | 2026-Q1
EXP-003455 | 2026-02-02 | BOQ-PKG-05-01465 | PKG-05 | INV-PKG-05-026-03455 | 7.68 | 47824.85 | 2391.24 | Paid | 45433.61 | 2026-Q1
EXP-004696 | 2026-02-02 | BOQ-PKG-06-00716 | PKG-06 | INV-PKG-06-007-04696 | 229.38 | 118375.24 | 5918.76 | Under Review | 112456.48 | 2026-Q1
EXP-005559 | 2026-02-02 | BOQ-PKG-09-01579 | PKG-09 | INV-PKG-09-030-05559 | 81.77 | 137686.76 | 6884.34 | Under Review | 130802.42 | 2026-Q1
EXP-006322 | 2026-02-02 | BOQ-PKG-02-00352 | PKG-02 | INV-PKG-02-023-06322 | 348.06 | 111687.37 | 5584.37 | Paid | 106103 | 2026-Q1
EXP-000543 | 2026-02-03 | BOQ-PKG-03-00543 | PKG-03 | INV-PKG-03-019-00543 | 101.91 | 153919.75 | 7695.99 | Paid | 146223.76 | 2026-Q1
EXP-001166 | 2026-02-03 | BOQ-PKG-06-01166 | PKG-06 | INV-PKG-06-012-01166 | 333.77 | 146031.62 | 7301.58 | Paid | 138730.04 | 2026-Q1
EXP-001670 | 2026-02-03 | BOQ-PKG-10-01670 | PKG-10 | INV-PKG-10-026-01670 | 353.75 | 46413.9 | 2320.7 | Paid | 44093.2 | 2026-Q1
EXP-003111 | 2026-02-03 | BOQ-PKG-01-01121 | PKG-01 | INV-PKG-01-032-03111 | 100.37 | 90761.28 | 4538.06 | Paid | 86223.22 | 2026-Q1
EXP-005900 | 2026-02-03 | BOQ-PKG-10-01920 | PKG-10 | INV-PKG-10-021-05900 | 89.84 | 89129.8 | 4456.49 | Under Review | 84673.31 | 2026-Q1
EXP-006106 | 2026-02-03 | BOQ-PKG-06-00136 | PKG-06 | INV-PKG-06-017-06106 | 386.3 | 194832.82 | 9741.64 | Paid | 185091.18 | 2026-Q1
EXP-000399 | 2026-02-04 | BOQ-PKG-09-00399 | PKG-09 | INV-PKG-09-015-00399 | 94.41 | 179042.59 | 8952.13 | Paid | 170090.46 | 2026-Q1
EXP-002601 | 2026-02-04 | BOQ-PKG-01-00611 | PKG-01 | INV-PKG-01-012-02601 | 162.94 | 207638.82 | 10381.94 | Paid | 197256.88 | 2026-Q1
EXP-003489 | 2026-02-04 | BOQ-PKG-09-01499 | PKG-09 | INV-PKG-09-025-03489 | 94.56 | 115466.41 | 5773.32 | Paid | 109693.09 | 2026-Q1
EXP-003687 | 2026-02-04 | BOQ-PKG-07-01697 | PKG-07 | INV-PKG-07-013-03687 | 41.13 | 191228.67 | 9561.43 | Under Review | 181667.24 | 2026-Q1
EXP-005300 | 2026-02-04 | BOQ-PKG-10-01320 | PKG-10 | INV-PKG-10-016-05300 | 436.01 | 114526.33 | 5726.32 | Paid | 108800.01 | 2026-Q1
EXP-006718 | 2026-02-04 | BOQ-PKG-08-00748 | PKG-08 | INV-PKG-08-034-06718 | 434.7 | 137546.49 | 6877.32 | Under Review | 130669.17 | 2026-Q1
EXP-001170 | 2026-02-05 | BOQ-PKG-10-01170 | PKG-10 | INV-PKG-10-016-01170 | 216.69 | 126768.06 | 6338.4 | Paid | 120429.66 | 2026-Q1
EXP-004045 | 2026-02-05 | BOQ-PKG-05-00065 | PKG-05 | INV-PKG-05-021-04045 | 71.35 | 211068.91 | 10553.45 | Paid | 200515.46 | 2026-Q1
EXP-004073 | 2026-02-05 | BOQ-PKG-03-00093 | PKG-03 | INV-PKG-03-014-04073 | 132.76 | 166982.83 | 8349.14 | Paid | 158633.69 | 2026-Q1
EXP-004515 | 2026-02-05 | BOQ-PKG-05-00535 | PKG-05 | INV-PKG-05-001-04515 | 197.68 | 27320.13 | 1366.01 | Paid | 25954.12 | 2026-Q1
EXP-006151 | 2026-02-05 | BOQ-PKG-01-00181 | PKG-01 | INV-PKG-01-027-06151 | 103.79 | 121937.26 | 6096.86 | Paid | 115840.4 | 2026-Q1
EXP-004787 | 2026-02-06 | BOQ-PKG-07-00807 | PKG-07 | INV-PKG-07-028-04787 | 174.29 | 132724.83 | 6636.24 | Approved Pending Payment | 126088.59 | 2026-Q1
EXP-005107 | 2026-02-06 | BOQ-PKG-07-01127 | PKG-07 | INV-PKG-07-033-05107 | 11.45 | 195009.92 | 9750.5 | Paid | 185259.42 | 2026-Q1
EXP-006316 | 2026-02-06 | BOQ-PKG-06-00346 | PKG-06 | INV-PKG-06-017-06316 | 225.95 | 25433.29 | 1271.66 | Approved Pending Payment | 24161.63 | 2026-Q1
EXP-000280 | 2026-02-07 | BOQ-PKG-10-00280 | PKG-10 | INV-PKG-10-001-00280 | 261.54 | 89938.1 | 4496.91 | Paid | 85441.19 | 2026-Q1
EXP-000418 | 2026-02-07 | BOQ-PKG-08-00418 | PKG-08 | INV-PKG-08-034-00418 | 221.48 | 83649.92 | 4182.5 | Paid | 79467.42 | 2026-Q1
EXP-001287 | 2026-02-07 | BOQ-PKG-07-01287 | PKG-07 | INV-PKG-07-028-01287 | 354.42 | 67117.94 | 3355.9 | Under Review | 63762.04 | 2026-Q1
EXP-004418 | 2026-02-07 | BOQ-PKG-08-00438 | PKG-08 | INV-PKG-08-009-04418 | 428.47 | 67638.81 | 3381.94 | Under Review | 64256.87 | 2026-Q1
EXP-005236 | 2026-02-07 | BOQ-PKG-06-01256 | PKG-06 | INV-PKG-06-022-05236 | 227 | 66152.88 | 3307.64 | Paid | 62845.24 | 2026-Q1
EXP-005989 | 2026-02-07 | BOQ-PKG-09-00019 | PKG-09 | INV-PKG-09-005-05989 | 36.07 | 148309.19 | 7415.46 | Paid | 140893.73 | 2026-Q1
EXP-000364 | 2026-02-08 | BOQ-PKG-04-00364 | PKG-04 | INV-PKG-04-015-00364 | 65.41 | 213946.04 | 10697.3 | Paid | 203248.74 | 2026-Q1
EXP-004114 | 2026-02-08 | BOQ-PKG-04-00134 | PKG-04 | INV-PKG-04-020-04114 | 183.97 | 153207.03 | 7660.35 | Paid | 145546.68 | 2026-Q1
EXP-004251 | 2026-02-08 | BOQ-PKG-01-00271 | PKG-01 | INV-PKG-01-017-04251 | 121.16 | 46489.55 | 2324.48 | Under Review | 44165.07 | 2026-Q1
EXP-005506 | 2026-02-08 | BOQ-PKG-06-01526 | PKG-06 | INV-PKG-06-012-05506 | 118.21 | 103128.52 | 5156.43 | Paid | 97972.09 | 2026-Q1
EXP-005572 | 2026-02-08 | BOQ-PKG-02-01592 | PKG-02 | INV-PKG-02-008-05572 | 219.51 | 191974.34 | 9598.72 | Paid | 182375.62 | 2026-Q1
EXP-000171 | 2026-02-09 | BOQ-PKG-01-00171 | PKG-01 | INV-PKG-01-032-00171 | 334.06 | 140571.58 | 7028.58 | Paid | 133543 | 2026-Q1
EXP-001451 | 2026-02-09 | BOQ-PKG-01-01451 | PKG-01 | INV-PKG-01-017-01451 | 276.31 | 45031.44 | 2251.57 | Paid | 42779.87 | 2026-Q1
EXP-001817 | 2026-02-09 | BOQ-PKG-07-01817 | PKG-07 | INV-PKG-07-033-01817 | 133.26 | 62456.23 | 3122.81 | Paid | 59333.42 | 2026-Q1
EXP-002798 | 2026-02-09 | BOQ-PKG-08-00808 | PKG-08 | INV-PKG-08-034-02798 | 379.88 | 98308.95 | 4915.45 | Paid | 93393.5 | 2026-Q1
EXP-002868 | 2026-02-09 | BOQ-PKG-08-00878 | PKG-08 | INV-PKG-08-034-02868 | 29.77 | 213665.92 | 10683.3 | Paid | 202982.62 | 2026-Q1
EXP-003176 | 2026-02-09 | BOQ-PKG-06-01186 | PKG-06 | INV-PKG-06-027-03176 | 8.58 | 187703.96 | 9385.2 | Paid | 178318.76 | 2026-Q1
EXP-003802 | 2026-02-09 | BOQ-PKG-02-01812 | PKG-02 | INV-PKG-02-023-03802 | 117.31 | 34598.16 | 1729.91 | Approved Pending Payment | 32868.25 | 2026-Q1
EXP-004957 | 2026-02-09 | BOQ-PKG-07-00977 | PKG-07 | INV-PKG-07-023-04957 | 101.39 | 197182.36 | 9859.12 | Paid | 187323.24 | 2026-Q1
EXP-005894 | 2026-02-09 | BOQ-PKG-04-01914 | PKG-04 | INV-PKG-04-015-05894 | 73.94 | 127054.69 | 6352.73 | Disputed | 120701.96 | 2026-Q1
EXP-006990 | 2026-02-09 | BOQ-PKG-10-01020 | PKG-10 | INV-PKG-10-026-06990 | 289.68 | 58301.98 | 2915.1 | Paid | 55386.88 | 2026-Q1
EXP-001524 | 2026-02-10 | BOQ-PKG-04-01524 | PKG-04 | INV-PKG-04-020-01524 | 234.17 | 47268.28 | 2363.41 | Paid | 44904.87 | 2026-Q1
EXP-001890 | 2026-02-10 | BOQ-PKG-10-01890 | PKG-10 | INV-PKG-10-001-01890 | 159.19 | 165391.67 | 8269.58 | Paid | 157122.09 | 2026-Q1
EXP-003993 | 2026-02-10 | BOQ-PKG-03-00013 | PKG-03 | INV-PKG-03-004-03993 | 438.42 | 85711.22 | 4285.56 | Paid | 81425.66 | 2026-Q1
EXP-004063 | 2026-02-10 | BOQ-PKG-03-00083 | PKG-03 | INV-PKG-03-004-04063 | 77.14 | 139595.1 | 6979.76 | Paid | 132615.34 | 2026-Q1
EXP-004316 | 2026-02-10 | BOQ-PKG-06-00336 | PKG-06 | INV-PKG-06-012-04316 | 203.76 | 86007.38 | 4300.37 | Paid | 81707.01 | 2026-Q1
EXP-005164 | 2026-02-10 | BOQ-PKG-04-01184 | PKG-04 | INV-PKG-04-020-05164 | 406.15 | 64782.41 | 3239.12 | Approved Pending Payment | 61543.29 | 2026-Q1
EXP-006607 | 2026-02-10 | BOQ-PKG-07-00637 | PKG-07 | INV-PKG-07-028-06607 | 158.03 | 65888.77 | 3294.44 | Paid | 62594.33 | 2026-Q1
EXP-006609 | 2026-02-10 | BOQ-PKG-09-00639 | PKG-09 | INV-PKG-09-030-06609 | 337.88 | 93226.24 | 4661.31 | Approved Pending Payment | 88564.93 | 2026-Q1
EXP-000244 | 2026-02-11 | BOQ-PKG-04-00244 | PKG-04 | INV-PKG-04-035-00244 | 333.65 | 35532.07 | 1776.6 | Paid | 33755.47 | 2026-Q1
EXP-000449 | 2026-02-11 | BOQ-PKG-09-00449 | PKG-09 | INV-PKG-09-030-00449 | 319.72 | 58863.17 | 2943.16 | Paid | 55920.01 | 2026-Q1
EXP-002363 | 2026-02-11 | BOQ-PKG-03-00373 | PKG-03 | INV-PKG-03-019-02363 | 209.05 | 62738.63 | 3136.93 | Paid | 59601.7 | 2026-Q1
EXP-002885 | 2026-02-11 | BOQ-PKG-05-00895 | PKG-05 | INV-PKG-05-016-02885 | 259.29 | 209512.05 | 10475.6 | Paid | 199036.45 | 2026-Q1
EXP-003952 | 2026-02-11 | BOQ-PKG-02-01962 | PKG-02 | INV-PKG-02-033-03952 | 429.43 | 171229.81 | 8561.49 | Approved Pending Payment | 162668.32 | 2026-Q1
EXP-004095 | 2026-02-11 | BOQ-PKG-05-00115 | PKG-05 | INV-PKG-05-001-04095 | 167.18 | 53388.33 | 2669.42 | Paid | 50718.91 | 2026-Q1
EXP-004185 | 2026-02-11 | BOQ-PKG-05-00205 | PKG-05 | INV-PKG-05-021-04185 | 328.04 | 38069.68 | 1903.48 | Under Review | 36166.2 | 2026-Q1
EXP-004636 | 2026-02-11 | BOQ-PKG-06-00656 | PKG-06 | INV-PKG-06-017-04636 | 246.71 | 195652.62 | 9782.63 | Paid | 185869.99 | 2026-Q1
EXP-005112 | 2026-02-11 | BOQ-PKG-02-01132 | PKG-02 | INV-PKG-02-003-05112 | 343.4 | 83521.71 | 4176.09 | Paid | 79345.62 | 2026-Q1
EXP-006435 | 2026-02-11 | BOQ-PKG-05-00465 | PKG-05 | INV-PKG-05-031-06435 | 91.24 | 102871.9 | 5143.6 | Paid | 97728.3 | 2026-Q1
EXP-000566 | 2026-02-12 | BOQ-PKG-06-00566 | PKG-06 | INV-PKG-06-007-00566 | 334.07 | 102187.81 | 5109.39 | Paid | 97078.42 | 2026-Q1
EXP-001762 | 2026-02-12 | BOQ-PKG-02-01762 | PKG-02 | INV-PKG-02-013-01762 | 21.13 | 206932.49 | 10346.62 | Paid | 196585.87 | 2026-Q1
EXP-003466 | 2026-02-12 | BOQ-PKG-06-01476 | PKG-06 | INV-PKG-06-002-03466 | 58.51 | 48881.67 | 2444.08 | Approved Pending Payment | 46437.59 | 2026-Q1
EXP-005853 | 2026-02-12 | BOQ-PKG-03-01873 | PKG-03 | INV-PKG-03-009-05853 | 94.53 | 75763.52 | 3788.18 | Paid | 71975.34 | 2026-Q1
EXP-006898 | 2026-02-12 | BOQ-PKG-08-00928 | PKG-08 | INV-PKG-08-004-06898 | 246.63 | 126480.37 | 6324.02 | Paid | 120156.35 | 2026-Q1
EXP-000297 | 2026-02-13 | BOQ-PKG-07-00297 | PKG-07 | INV-PKG-07-018-00297 | 112.54 | 36115.43 | 1805.77 | Paid | 34309.66 | 2026-Q1
EXP-003055 | 2026-02-13 | BOQ-PKG-05-01065 | PKG-05 | INV-PKG-05-011-03055 | 186.2 | 83383.03 | 4169.15 | Paid | 79213.88 | 2026-Q1
EXP-005628 | 2026-02-13 | BOQ-PKG-08-01648 | PKG-08 | INV-PKG-08-029-05628 | 107.49 | 114278.05 | 5713.9 | Paid | 108564.15 | 2026-Q1
EXP-001721 | 2026-02-14 | BOQ-PKG-01-01721 | PKG-01 | INV-PKG-01-007-01721 | 412.21 | 169375.25 | 8468.76 | Paid | 160906.49 | 2026-Q1
EXP-003615 | 2026-02-14 | BOQ-PKG-05-01625 | PKG-05 | INV-PKG-05-011-03615 | 108.94 | 115028.78 | 5751.44 | Paid | 109277.34 | 2026-Q1
EXP-004769 | 2026-02-14 | BOQ-PKG-09-00789 | PKG-09 | INV-PKG-09-010-04769 | 279.17 | 54703.66 | 2735.18 | Paid | 51968.48 | 2026-Q1
EXP-004773 | 2026-02-14 | BOQ-PKG-03-00793 | PKG-03 | INV-PKG-03-014-04773 | 411.99 | 91505.2 | 4575.26 | Paid | 86929.94 | 2026-Q1
EXP-006006 | 2026-02-14 | BOQ-PKG-06-00036 | PKG-06 | INV-PKG-06-022-06006 | 367.32 | 68801.32 | 3440.07 | Paid | 65361.25 | 2026-Q1
EXP-006190 | 2026-02-14 | BOQ-PKG-10-00220 | PKG-10 | INV-PKG-10-031-06190 | 110.36 | 117228.33 | 5861.42 | Paid | 111366.91 | 2026-Q1
EXP-006230 | 2026-02-14 | BOQ-PKG-10-00260 | PKG-10 | INV-PKG-10-001-06230 | 324.76 | 133506.83 | 6675.34 | Paid | 126831.49 | 2026-Q1
EXP-000442 | 2026-02-15 | BOQ-PKG-02-00442 | PKG-02 | INV-PKG-02-023-00442 | 355.68 | 77164.05 | 3858.2 | Paid | 73305.85 | 2026-Q1
EXP-004810 | 2026-02-15 | BOQ-PKG-10-00830 | PKG-10 | INV-PKG-10-016-04810 | 113.33 | 83606.63 | 4180.33 | Under Review | 79426.3 | 2026-Q1
EXP-004920 | 2026-02-15 | BOQ-PKG-10-00940 | PKG-10 | INV-PKG-10-021-04920 | 126.56 | 178679.72 | 8933.99 | Paid | 169745.73 | 2026-Q1
EXP-006948 | 2026-02-15 | BOQ-PKG-08-00978 | PKG-08 | INV-PKG-08-019-06948 | 233.27 | 46071.96 | 2303.6 | Paid | 43768.36 | 2026-Q1
EXP-000407 | 2026-02-16 | BOQ-PKG-07-00407 | PKG-07 | INV-PKG-07-023-00407 | 368.93 | 206749.48 | 10337.47 | Paid | 196412.01 | 2026-Q1
EXP-000448 | 2026-02-16 | BOQ-PKG-08-00448 | PKG-08 | INV-PKG-08-029-00448 | 73.27 | 91460.79 | 4573.04 | Paid | 86887.75 | 2026-Q1
EXP-000958 | 2026-02-16 | BOQ-PKG-08-00958 | PKG-08 | INV-PKG-08-014-00958 | 357.42 | 47304.93 | 2365.25 | Paid | 44939.68 | 2026-Q1
EXP-001122 | 2026-02-16 | BOQ-PKG-02-01122 | PKG-02 | INV-PKG-02-003-01122 | 85.39 | 98719.6 | 4935.98 | Approved Pending Payment | 93783.62 | 2026-Q1
EXP-004094 | 2026-02-16 | BOQ-PKG-04-00114 | PKG-04 | INV-PKG-04-035-04094 | 200.57 | 49791.04 | 2489.55 | Paid | 47301.49 | 2026-Q1
EXP-004619 | 2026-02-16 | BOQ-PKG-09-00639 | PKG-09 | INV-PKG-09-035-04619 | 202.32 | 117158.94 | 5857.95 | Paid | 111300.99 | 2026-Q1
EXP-005221 | 2026-02-16 | BOQ-PKG-01-01241 | PKG-01 | INV-PKG-01-007-05221 | 416.29 | 164968.2 | 8248.41 | Paid | 156719.79 | 2026-Q1
EXP-005484 | 2026-02-16 | BOQ-PKG-04-01504 | PKG-04 | INV-PKG-04-025-05484 | 193.12 | 40860.4 | 2043.02 | Disputed | 38817.38 | 2026-Q1
EXP-001703 | 2026-02-17 | BOQ-PKG-03-01703 | PKG-03 | INV-PKG-03-024-01703 | 97.15 | 84174.12 | 4208.71 | Paid | 79965.41 | 2026-Q1
EXP-002316 | 2026-02-17 | BOQ-PKG-06-00326 | PKG-06 | INV-PKG-06-007-02316 | 413.83 | 197668 | 9883.4 | Under Review | 187784.6 | 2026-Q1
EXP-002670 | 2026-02-17 | BOQ-PKG-10-00680 | PKG-10 | INV-PKG-10-011-02670 | 249.71 | 75946.99 | 3797.35 | Paid | 72149.64 | 2026-Q1
EXP-003233 | 2026-02-17 | BOQ-PKG-03-01243 | PKG-03 | INV-PKG-03-014-03233 | 82.36 | 117672.21 | 5883.61 | Paid | 111788.6 | 2026-Q1
EXP-003897 | 2026-02-17 | BOQ-PKG-07-01907 | PKG-07 | INV-PKG-07-013-03897 | 115.96 | 31029.48 | 1551.47 | Paid | 29478.01 | 2026-Q1
EXP-004300 | 2026-02-17 | BOQ-PKG-10-00320 | PKG-10 | INV-PKG-10-031-04300 | 44.75 | 181687.78 | 9084.39 | Paid | 172603.39 | 2026-Q1
EXP-005796 | 2026-02-17 | BOQ-PKG-06-01816 | PKG-06 | INV-PKG-06-022-05796 | 339.82 | 134233.11 | 6711.66 | Approved Pending Payment | 127521.45 | 2026-Q1
EXP-000947 | 2026-02-18 | BOQ-PKG-07-00947 | PKG-07 | INV-PKG-07-003-00947 | 133.83 | 147087.44 | 7354.37 | Under Review | 139733.07 | 2026-Q1
EXP-001967 | 2026-02-18 | BOQ-PKG-07-01967 | PKG-07 | INV-PKG-07-008-01967 | 9.11 | 80187.62 | 4009.38 | Paid | 76178.24 | 2026-Q1
EXP-002053 | 2026-02-18 | BOQ-PKG-03-00063 | PKG-03 | INV-PKG-03-024-02053 | 400.35 | 181929.24 | 9096.46 | Approved Pending Payment | 172832.78 | 2026-Q1
EXP-003244 | 2026-02-18 | BOQ-PKG-04-01254 | PKG-04 | INV-PKG-04-025-03244 | 242.46 | 44644.57 | 2232.23 | Under Review | 42412.34 | 2026-Q1
EXP-004085 | 2026-02-18 | BOQ-PKG-05-00105 | PKG-05 | INV-PKG-05-026-04085 | 36.87 | 72172.59 | 3608.63 | Approved Pending Payment | 68563.96 | 2026-Q1
EXP-004365 | 2026-02-18 | BOQ-PKG-05-00385 | PKG-05 | INV-PKG-05-026-04365 | 226.43 | 124148.58 | 6207.43 | Paid | 117941.15 | 2026-Q1
EXP-005105 | 2026-02-18 | BOQ-PKG-05-01125 | PKG-05 | INV-PKG-05-031-05105 | 69.76 | 115936.51 | 5796.83 | Paid | 110139.68 | 2026-Q1
EXP-005943 | 2026-02-18 | BOQ-PKG-03-01963 | PKG-03 | INV-PKG-03-029-05943 | 445.44 | 185634.75 | 9281.74 | Paid | 176353.01 | 2026-Q1
EXP-006174 | 2026-02-18 | BOQ-PKG-04-00204 | PKG-04 | INV-PKG-04-015-06174 | 277.31 | 174631.27 | 8731.56 | Approved Pending Payment | 165899.71 | 2026-Q1
EXP-001705 | 2026-02-19 | BOQ-PKG-05-01705 | PKG-05 | INV-PKG-05-026-01705 | 12.36 | 59530.53 | 2976.53 | Paid | 56554 | 2026-Q1
EXP-002212 | 2026-02-19 | BOQ-PKG-02-00222 | PKG-02 | INV-PKG-02-008-02212 | 175.82 | 115273.41 | 5763.67 | Paid | 109509.74 | 2026-Q1
EXP-003300 | 2026-02-19 | BOQ-PKG-10-01310 | PKG-10 | INV-PKG-10-011-03300 | 265.76 | 133933.18 | 6696.66 | Paid | 127236.52 | 2026-Q1
EXP-004109 | 2026-02-19 | BOQ-PKG-09-00129 | PKG-09 | INV-PKG-09-015-04109 | 162.86 | 181372.08 | 9068.6 | Under Review | 172303.48 | 2026-Q1
EXP-005150 | 2026-02-19 | BOQ-PKG-10-01170 | PKG-10 | INV-PKG-10-006-05150 | 354.49 | 25970.36 | 1298.52 | Paid | 24671.84 | 2026-Q1
EXP-000506 | 2026-02-20 | BOQ-PKG-06-00506 | PKG-06 | INV-PKG-06-017-00506 | 348.31 | 200214.87 | 10010.74 | Paid | 190204.13 | 2026-Q1
EXP-002555 | 2026-02-20 | BOQ-PKG-05-00565 | PKG-05 | INV-PKG-05-001-02555 | 277.34 | 59891.81 | 2994.59 | Paid | 56897.22 | 2026-Q1
EXP-003164 | 2026-02-20 | BOQ-PKG-04-01174 | PKG-04 | INV-PKG-04-015-03164 | 338.31 | 63589.17 | 3179.46 | Paid | 60409.71 | 2026-Q1
EXP-004770 | 2026-02-20 | BOQ-PKG-10-00790 | PKG-10 | INV-PKG-10-011-04770 | 349.48 | 76901.45 | 3845.07 | Paid | 73056.38 | 2026-Q1
EXP-006332 | 2026-02-20 | BOQ-PKG-02-00362 | PKG-02 | INV-PKG-02-033-06332 | 73.65 | 24649.2 | 1232.46 | Paid | 23416.74 | 2026-Q1
EXP-006341 | 2026-02-20 | BOQ-PKG-01-00371 | PKG-01 | INV-PKG-01-007-06341 | 247.93 | 88473.84 | 4423.69 | Approved Pending Payment | 84050.15 | 2026-Q1
EXP-000932 | 2026-02-21 | BOQ-PKG-02-00932 | PKG-02 | INV-PKG-02-023-00932 | 361.16 | 110181.22 | 5509.06 | Paid | 104672.16 | 2026-Q1
EXP-001344 | 2026-02-21 | BOQ-PKG-04-01344 | PKG-04 | INV-PKG-04-015-01344 | 435.7 | 115181.35 | 5759.07 | Paid | 109422.28 | 2026-Q1
EXP-002186 | 2026-02-21 | BOQ-PKG-06-00196 | PKG-06 | INV-PKG-06-017-02186 | 206.38 | 114178.9 | 5708.94 | Paid | 108469.96 | 2026-Q1
EXP-003786 | 2026-02-21 | BOQ-PKG-06-01796 | PKG-06 | INV-PKG-06-007-03786 | 162.33 | 196389.14 | 9819.46 | Paid | 186569.68 | 2026-Q1
EXP-004518 | 2026-02-21 | BOQ-PKG-08-00538 | PKG-08 | INV-PKG-08-004-04518 | 353.42 | 101344.8 | 5067.24 | Paid | 96277.56 | 2026-Q1
EXP-006224 | 2026-02-21 | BOQ-PKG-04-00254 | PKG-04 | INV-PKG-04-030-06224 | 238.09 | 71109.11 | 3555.46 | Paid | 67553.65 | 2026-Q1
EXP-006617 | 2026-02-21 | BOQ-PKG-07-00647 | PKG-07 | INV-PKG-07-003-06617 | 290.42 | 134692.34 | 6734.62 | Approved Pending Payment | 127957.72 | 2026-Q1
EXP-000903 | 2026-02-22 | BOQ-PKG-03-00903 | PKG-03 | INV-PKG-03-029-00903 | 65.09 | 115268.98 | 5763.45 | Paid | 109505.53 | 2026-Q1
EXP-001215 | 2026-02-22 | BOQ-PKG-05-01215 | PKG-05 | INV-PKG-05-026-01215 | 209.79 | 191321.52 | 9566.08 | Paid | 181755.44 | 2026-Q1
EXP-002304 | 2026-02-22 | BOQ-PKG-04-00314 | PKG-04 | INV-PKG-04-030-02304 | 186.38 | 27877.27 | 1393.86 | Approved Pending Payment | 26483.41 | 2026-Q1
EXP-002396 | 2026-02-22 | BOQ-PKG-06-00406 | PKG-06 | INV-PKG-06-017-02396 | 343.15 | 114724.21 | 5736.21 | Paid | 108988 | 2026-Q1
EXP-002898 | 2026-02-22 | BOQ-PKG-08-00908 | PKG-08 | INV-PKG-08-029-02898 | 257.92 | 43782.88 | 2189.14 | Paid | 41593.74 | 2026-Q1
EXP-000273 | 2026-02-23 | BOQ-PKG-03-00273 | PKG-03 | INV-PKG-03-029-00273 | 427.02 | 39902.19 | 1995.11 | Disputed | 37907.08 | 2026-Q1
EXP-000570 | 2026-02-23 | BOQ-PKG-10-00570 | PKG-10 | INV-PKG-10-011-00570 | 92.77 | 64687.73 | 3234.39 | Paid | 61453.34 | 2026-Q1
EXP-003336 | 2026-02-23 | BOQ-PKG-06-01346 | PKG-06 | INV-PKG-06-012-03336 | 66.68 | 112574.37 | 5628.72 | Paid | 106945.65 | 2026-Q1
EXP-004596 | 2026-02-23 | BOQ-PKG-06-00616 | PKG-06 | INV-PKG-06-012-04596 | 228.31 | 153790.24 | 7689.51 | Paid | 146100.73 | 2026-Q1
EXP-004792 | 2026-02-23 | BOQ-PKG-02-00812 | PKG-02 | INV-PKG-02-033-04792 | 410.53 | 38314.05 | 1915.7 | Paid | 36398.35 | 2026-Q1
EXP-005504 | 2026-02-23 | BOQ-PKG-04-01524 | PKG-04 | INV-PKG-04-010-05504 | 220.24 | 51060.98 | 2553.05 | Paid | 48507.93 | 2026-Q1
EXP-000114 | 2026-02-24 | BOQ-PKG-04-00114 | PKG-04 | INV-PKG-04-010-00114 | 11.17 | 147105.13 | 7355.26 | Approved Pending Payment | 139749.87 | 2026-Q1
EXP-000301 | 2026-02-24 | BOQ-PKG-01-00301 | PKG-01 | INV-PKG-01-022-00301 | 135.79 | 109179.74 | 5458.99 | Paid | 103720.75 | 2026-Q1
EXP-000593 | 2026-02-24 | BOQ-PKG-03-00593 | PKG-03 | INV-PKG-03-034-00593 | 390.88 | 144287.98 | 7214.4 | Paid | 137073.58 | 2026-Q1
EXP-001674 | 2026-02-24 | BOQ-PKG-04-01674 | PKG-04 | INV-PKG-04-030-01674 | 74.38 | 165579.27 | 8278.96 | Paid | 157300.31 | 2026-Q1
EXP-004893 | 2026-02-24 | BOQ-PKG-03-00913 | PKG-03 | INV-PKG-03-029-04893 | 379.44 | 150723.88 | 7536.19 | Under Review | 143187.69 | 2026-Q1
EXP-005398 | 2026-02-24 | BOQ-PKG-08-01418 | PKG-08 | INV-PKG-08-009-05398 | 108.66 | 87816.37 | 4390.82 | Paid | 83425.55 | 2026-Q1
EXP-006092 | 2026-02-24 | BOQ-PKG-02-00122 | PKG-02 | INV-PKG-02-003-06092 | 66.61 | 145716.66 | 7285.83 | Approved Pending Payment | 138430.83 | 2026-Q1
EXP-000877 | 2026-02-25 | BOQ-PKG-07-00877 | PKG-07 | INV-PKG-07-003-00877 | 64.01 | 67268.9 | 3363.44 | Paid | 63905.46 | 2026-Q1
EXP-002340 | 2026-02-25 | BOQ-PKG-10-00350 | PKG-10 | INV-PKG-10-031-02340 | 140.77 | 137807.83 | 6890.39 | Paid | 130917.44 | 2026-Q1
EXP-002605 | 2026-02-25 | BOQ-PKG-05-00615 | PKG-05 | INV-PKG-05-016-02605 | 306.95 | 189185.14 | 9459.26 | Under Review | 179725.88 | 2026-Q1
EXP-003212 | 2026-02-25 | BOQ-PKG-02-01222 | PKG-02 | INV-PKG-02-028-03212 | 262.94 | 70058.02 | 3502.9 | Paid | 66555.12 | 2026-Q1
EXP-005244 | 2026-02-25 | BOQ-PKG-04-01264 | PKG-04 | INV-PKG-04-030-05244 | 237.08 | 162895.12 | 8144.76 | Approved Pending Payment | 154750.36 | 2026-Q1
EXP-006505 | 2026-02-25 | BOQ-PKG-05-00535 | PKG-05 | INV-PKG-05-031-06505 | 90.51 | 127321.15 | 6366.06 | Paid | 120955.09 | 2026-Q1
EXP-002550 | 2026-02-26 | BOQ-PKG-10-00560 | PKG-10 | INV-PKG-10-031-02550 | 19.32 | 33594.61 | 1679.73 | Paid | 31914.88 | 2026-Q1
EXP-001100 | 2026-02-27 | BOQ-PKG-10-01100 | PKG-10 | INV-PKG-10-016-01100 | 440.59 | 185045.88 | 9252.29 | Paid | 175793.59 | 2026-Q1
EXP-002302 | 2026-02-27 | BOQ-PKG-02-00312 | PKG-02 | INV-PKG-02-028-02302 | 384.83 | 37894.1 | 1894.7 | Paid | 35999.4 | 2026-Q1
EXP-002680 | 2026-02-27 | BOQ-PKG-10-00690 | PKG-10 | INV-PKG-10-021-02680 | 164.83 | 117693.39 | 5884.67 | Paid | 111808.72 | 2026-Q1
EXP-003331 | 2026-02-27 | BOQ-PKG-01-01341 | PKG-01 | INV-PKG-01-007-03331 | 309.65 | 183048.42 | 9152.42 | Paid | 173896 | 2026-Q1
EXP-003393 | 2026-02-27 | BOQ-PKG-03-01403 | PKG-03 | INV-PKG-03-034-03393 | 339.92 | 178781.88 | 8939.09 | Approved Pending Payment | 169842.79 | 2026-Q1
EXP-003680 | 2026-02-27 | BOQ-PKG-10-01690 | PKG-10 | INV-PKG-10-006-03680 | 32.32 | 72129.07 | 3606.45 | Under Review | 68522.62 | 2026-Q1
EXP-003983 | 2026-02-27 | BOQ-PKG-03-00003 | PKG-03 | INV-PKG-03-029-03983 | 196.7 | 146532.16 | 7326.61 | Paid | 139205.55 | 2026-Q1
EXP-004340 | 2026-02-27 | BOQ-PKG-10-00360 | PKG-10 | INV-PKG-10-001-04340 | 107.59 | 33503.66 | 1675.18 | Disputed | 31828.48 | 2026-Q1
EXP-005002 | 2026-02-27 | BOQ-PKG-02-01022 | PKG-02 | INV-PKG-02-033-05002 | 449.08 | 97100.21 | 4855.01 | Paid | 92245.2 | 2026-Q1
EXP-005524 | 2026-02-27 | BOQ-PKG-04-01544 | PKG-04 | INV-PKG-04-030-05524 | 43.45 | 68872.2 | 3443.61 | Paid | 65428.59 | 2026-Q1
EXP-005874 | 2026-02-27 | BOQ-PKG-04-01894 | PKG-04 | INV-PKG-04-030-05874 | 54.01 | 150316.57 | 7515.83 | Paid | 142800.74 | 2026-Q1
EXP-006245 | 2026-02-27 | BOQ-PKG-05-00275 | PKG-05 | INV-PKG-05-016-06245 | 411.53 | 67411.8 | 3370.59 | Paid | 64041.21 | 2026-Q1
EXP-000240 | 2026-02-28 | BOQ-PKG-10-00240 | PKG-10 | INV-PKG-10-031-00240 | 398.93 | 40247.28 | 2012.36 | Under Review | 38234.92 | 2026-Q1
EXP-000825 | 2026-02-28 | BOQ-PKG-05-00825 | PKG-05 | INV-PKG-05-021-00825 | 444.78 | 93118.51 | 4655.93 | Approved Pending Payment | 88462.58 | 2026-Q1
EXP-000839 | 2026-02-28 | BOQ-PKG-09-00839 | PKG-09 | INV-PKG-09-035-00839 | 362.14 | 112941.28 | 5647.06 | Paid | 107294.22 | 2026-Q1
EXP-004357 | 2026-02-28 | BOQ-PKG-07-00377 | PKG-07 | INV-PKG-07-018-04357 | 273.44 | 90830.29 | 4541.51 | Approved Pending Payment | 86288.78 | 2026-Q1
EXP-004472 | 2026-02-28 | BOQ-PKG-02-00492 | PKG-02 | INV-PKG-02-028-04472 | 383.86 | 68427.01 | 3421.35 | Approved Pending Payment | 65005.66 | 2026-Q1
EXP-004846 | 2026-02-28 | BOQ-PKG-06-00866 | PKG-06 | INV-PKG-06-017-04846 | 123.21 | 25250.2 | 1262.51 | Disputed | 23987.69 | 2026-Q1
EXP-004947 | 2026-02-28 | BOQ-PKG-07-00967 | PKG-07 | INV-PKG-07-013-04947 | 102.77 | 158216.76 | 7910.84 | Paid | 150305.92 | 2026-Q1
EXP-005230 | 2026-02-28 | BOQ-PKG-10-01250 | PKG-10 | INV-PKG-10-016-05230 | 345.87 | 83767.49 | 4188.37 | Paid | 79579.12 | 2026-Q1
EXP-005698 | 2026-02-28 | BOQ-PKG-08-01718 | PKG-08 | INV-PKG-08-029-05698 | 307.39 | 51436.75 | 2571.84 | Paid | 48864.91 | 2026-Q1
EXP-005725 | 2026-02-28 | BOQ-PKG-05-01745 | PKG-05 | INV-PKG-05-021-05725 | 259.75 | 47443.13 | 2372.16 | Under Review | 45070.97 | 2026-Q1
EXP-006533 | 2026-02-28 | BOQ-PKG-03-00563 | PKG-03 | INV-PKG-03-024-06533 | 445.46 | 157763.87 | 7888.19 | Paid | 149875.68 | 2026-Q1
EXP-006559 | 2026-02-28 | BOQ-PKG-09-00589 | PKG-09 | INV-PKG-09-015-06559 | 401.96 | 92964.68 | 4648.23 | Paid | 88316.45 | 2026-Q1
EXP-002338 | 2026-03-01 | BOQ-PKG-08-00348 | PKG-08 | INV-PKG-08-029-02338 | 247.19 | 30227.95 | 1511.4 | Paid | 28716.55 | 2026-Q1
EXP-002769 | 2026-03-01 | BOQ-PKG-09-00779 | PKG-09 | INV-PKG-09-005-02769 | 109.53 | 149482.12 | 7474.11 | Paid | 142008.01 | 2026-Q1
EXP-003653 | 2026-03-01 | BOQ-PKG-03-01663 | PKG-03 | INV-PKG-03-014-03653 | 128.07 | 199373.38 | 9968.67 | Approved Pending Payment | 189404.71 | 2026-Q1
EXP-004451 | 2026-03-01 | BOQ-PKG-01-00471 | PKG-01 | INV-PKG-01-007-04451 | 256.89 | 189022.63 | 9451.13 | Under Review | 179571.5 | 2026-Q1
EXP-005629 | 2026-03-01 | BOQ-PKG-09-01649 | PKG-09 | INV-PKG-09-030-05629 | 53.62 | 100909.78 | 5045.49 | Paid | 95864.29 | 2026-Q1
EXP-005656 | 2026-03-01 | BOQ-PKG-06-01676 | PKG-06 | INV-PKG-06-022-05656 | 333.73 | 49643.13 | 2482.16 | Paid | 47160.97 | 2026-Q1
EXP-006308 | 2026-03-01 | BOQ-PKG-08-00338 | PKG-08 | INV-PKG-08-009-06308 | 248.27 | 195259.29 | 9762.96 | Approved Pending Payment | 185496.33 | 2026-Q1
EXP-000546 | 2026-03-02 | BOQ-PKG-06-00546 | PKG-06 | INV-PKG-06-022-00546 | 418.82 | 127301.32 | 6365.07 | Under Review | 120936.25 | 2026-Q1
EXP-000699 | 2026-03-02 | BOQ-PKG-09-00699 | PKG-09 | INV-PKG-09-035-00699 | 22.07 | 186712.5 | 9335.62 | Paid | 177376.88 | 2026-Q1
EXP-001563 | 2026-03-02 | BOQ-PKG-03-01563 | PKG-03 | INV-PKG-03-024-01563 | 7.52 | 203960.61 | 10198.03 | Paid | 193762.58 | 2026-Q1
EXP-002181 | 2026-03-02 | BOQ-PKG-01-00191 | PKG-01 | INV-PKG-01-012-02181 | 94.12 | 131740.13 | 6587.01 | Paid | 125153.12 | 2026-Q1
EXP-002966 | 2026-03-02 | BOQ-PKG-06-00976 | PKG-06 | INV-PKG-06-027-02966 | 443.69 | 69303.39 | 3465.17 | Approved Pending Payment | 65838.22 | 2026-Q1
EXP-003410 | 2026-03-02 | BOQ-PKG-10-01420 | PKG-10 | INV-PKG-10-016-03410 | 181.25 | 131299.09 | 6564.95 | Paid | 124734.14 | 2026-Q1
EXP-003717 | 2026-03-02 | BOQ-PKG-07-01727 | PKG-07 | INV-PKG-07-008-03717 | 248.69 | 192449.48 | 9622.47 | Paid | 182827.01 | 2026-Q1
EXP-005100 | 2026-03-02 | BOQ-PKG-10-01120 | PKG-10 | INV-PKG-10-026-05100 | 378.16 | 156138.48 | 7806.92 | Approved Pending Payment | 148331.56 | 2026-Q1
EXP-006368 | 2026-03-02 | BOQ-PKG-08-00398 | PKG-08 | INV-PKG-08-034-06368 | 123.52 | 187536.98 | 9376.85 | Approved Pending Payment | 178160.13 | 2026-Q1
EXP-000653 | 2026-03-03 | BOQ-PKG-03-00653 | PKG-03 | INV-PKG-03-024-00653 | 407.98 | 46413.98 | 2320.7 | Paid | 44093.28 | 2026-Q1
EXP-001015 | 2026-03-03 | BOQ-PKG-05-01015 | PKG-05 | INV-PKG-05-001-01015 | 248.47 | 31095.37 | 1554.77 | Paid | 29540.6 | 2026-Q1
EXP-002009 | 2026-03-03 | BOQ-PKG-09-00019 | PKG-09 | INV-PKG-09-015-02009 | 127.79 | 87434.17 | 4371.71 | Paid | 83062.46 | 2026-Q1
EXP-004704 | 2026-03-03 | BOQ-PKG-04-00724 | PKG-04 | INV-PKG-04-015-04704 | 188.24 | 92245.26 | 4612.26 | Under Review | 87633 | 2026-Q1
EXP-005592 | 2026-03-03 | BOQ-PKG-02-01612 | PKG-02 | INV-PKG-02-028-05592 | 381.73 | 186383.07 | 9319.15 | Approved Pending Payment | 177063.92 | 2026-Q1
EXP-005789 | 2026-03-03 | BOQ-PKG-09-01809 | PKG-09 | INV-PKG-09-015-05789 | 309.23 | 106229.37 | 5311.47 | Paid | 100917.9 | 2026-Q1
EXP-006449 | 2026-03-03 | BOQ-PKG-09-00479 | PKG-09 | INV-PKG-09-010-06449 | 399.11 | 135335.35 | 6766.77 | Paid | 128568.58 | 2026-Q1
EXP-006911 | 2026-03-03 | BOQ-PKG-01-00941 | PKG-01 | INV-PKG-01-017-06911 | 146.85 | 37531.3 | 1876.57 | Under Review | 35654.73 | 2026-Q1
EXP-000048 | 2026-03-04 | BOQ-PKG-08-00048 | PKG-08 | INV-PKG-08-014-00048 | 23.5 | 118678.7 | 5933.94 | Paid | 112744.76 | 2026-Q1
EXP-000708 | 2026-03-04 | BOQ-PKG-08-00708 | PKG-08 | INV-PKG-08-009-00708 | 131.93 | 70143.25 | 3507.16 | Paid | 66636.09 | 2026-Q1
EXP-001038 | 2026-03-04 | BOQ-PKG-08-01038 | PKG-08 | INV-PKG-08-024-01038 | 385.01 | 55082.08 | 2754.1 | Paid | 52327.98 | 2026-Q1
EXP-002341 | 2026-03-04 | BOQ-PKG-01-00351 | PKG-01 | INV-PKG-01-032-02341 | 9.22 | 25119.2 | 1255.96 | Approved Pending Payment | 23863.24 | 2026-Q1
EXP-004000 | 2026-03-04 | BOQ-PKG-10-00020 | PKG-10 | INV-PKG-10-011-04000 | 142.17 | 210172.52 | 10508.63 | Approved Pending Payment | 199663.89 | 2026-Q1
EXP-004192 | 2026-03-04 | BOQ-PKG-02-00212 | PKG-02 | INV-PKG-02-028-04192 | 327.62 | 181778.14 | 9088.91 | Paid | 172689.23 | 2026-Q1
EXP-004267 | 2026-03-04 | BOQ-PKG-07-00287 | PKG-07 | INV-PKG-07-033-04267 | 65.53 | 160845.3 | 8042.26 | Paid | 152803.04 | 2026-Q1
EXP-004589 | 2026-03-04 | BOQ-PKG-09-00609 | PKG-09 | INV-PKG-09-005-04589 | 89.74 | 73457.48 | 3672.87 | Paid | 69784.61 | 2026-Q1
EXP-005208 | 2026-03-04 | BOQ-PKG-08-01228 | PKG-08 | INV-PKG-08-029-05208 | 16.51 | 43666.51 | 2183.33 | Paid | 41483.18 | 2026-Q1
EXP-005393 | 2026-03-04 | BOQ-PKG-03-01413 | PKG-03 | INV-PKG-03-004-05393 | 128.7 | 150418.81 | 7520.94 | Approved Pending Payment | 142897.87 | 2026-Q1
EXP-005955 | 2026-03-04 | BOQ-PKG-05-01975 | PKG-05 | INV-PKG-05-006-05955 | 119.54 | 79808.56 | 3990.43 | Paid | 75818.13 | 2026-Q1
EXP-006213 | 2026-03-04 | BOQ-PKG-03-00243 | PKG-03 | INV-PKG-03-019-06213 | 318.51 | 109289.94 | 5464.5 | Paid | 103825.44 | 2026-Q1
EXP-006680 | 2026-03-04 | BOQ-PKG-10-00710 | PKG-10 | INV-PKG-10-031-06680 | 136.38 | 101770.14 | 5088.51 | Paid | 96681.63 | 2026-Q1
EXP-000351 | 2026-03-05 | BOQ-PKG-01-00351 | PKG-01 | INV-PKG-01-002-00351 | 162.56 | 146814.85 | 7340.74 | Paid | 139474.11 | 2026-Q1
EXP-000791 | 2026-03-05 | BOQ-PKG-01-00791 | PKG-01 | INV-PKG-01-022-00791 | 347.32 | 133627.14 | 6681.36 | Paid | 126945.78 | 2026-Q1
EXP-000873 | 2026-03-05 | BOQ-PKG-03-00873 | PKG-03 | INV-PKG-03-034-00873 | 251.75 | 57362.76 | 2868.14 | Disputed | 54494.62 | 2026-Q1
EXP-001230 | 2026-03-05 | BOQ-PKG-10-01230 | PKG-10 | INV-PKG-10-006-01230 | 224.4 | 183478.94 | 9173.95 | Paid | 174304.99 | 2026-Q1
EXP-003964 | 2026-03-05 | BOQ-PKG-04-01974 | PKG-04 | INV-PKG-04-010-03964 | 150.13 | 109114.76 | 5455.74 | Paid | 103659.02 | 2026-Q1
EXP-004412 | 2026-03-05 | BOQ-PKG-02-00432 | PKG-02 | INV-PKG-02-003-04412 | 91.38 | 40421 | 2021.05 | Paid | 38399.95 | 2026-Q1
EXP-005839 | 2026-03-05 | BOQ-PKG-09-01859 | PKG-09 | INV-PKG-09-030-05839 | 267.82 | 116205.36 | 5810.27 | Approved Pending Payment | 110395.09 | 2026-Q1
EXP-005967 | 2026-03-05 | BOQ-PKG-07-01987 | PKG-07 | INV-PKG-07-018-05967 | 329.67 | 128569.9 | 6428.5 | Approved Pending Payment | 122141.4 | 2026-Q1
EXP-000636 | 2026-03-06 | BOQ-PKG-06-00636 | PKG-06 | INV-PKG-06-007-00636 | 235.65 | 108561.31 | 5428.07 | Paid | 103133.24 | 2026-Q1
EXP-000782 | 2026-03-06 | BOQ-PKG-02-00782 | PKG-02 | INV-PKG-02-013-00782 | 98.47 | 96116.96 | 4805.85 | Paid | 91311.11 | 2026-Q1
EXP-001091 | 2026-03-06 | BOQ-PKG-01-01091 | PKG-01 | INV-PKG-01-007-01091 | 89.05 | 152309.98 | 7615.5 | Paid | 144694.48 | 2026-Q1
EXP-001589 | 2026-03-06 | BOQ-PKG-09-01589 | PKG-09 | INV-PKG-09-015-01589 | 107.77 | 43906.13 | 2195.31 | Paid | 41710.82 | 2026-Q1
EXP-004578 | 2026-03-06 | BOQ-PKG-08-00598 | PKG-08 | INV-PKG-08-029-04578 | 315.43 | 38491.36 | 1924.57 | Approved Pending Payment | 36566.79 | 2026-Q1
EXP-004764 | 2026-03-06 | BOQ-PKG-04-00784 | PKG-04 | INV-PKG-04-005-04764 | 383.47 | 147492.22 | 7374.61 | Paid | 140117.61 | 2026-Q1
EXP-005116 | 2026-03-06 | BOQ-PKG-06-01136 | PKG-06 | INV-PKG-06-007-05116 | 347.05 | 161223.67 | 8061.18 | Paid | 153162.49 | 2026-Q1
EXP-001191 | 2026-03-07 | BOQ-PKG-01-01191 | PKG-01 | INV-PKG-01-002-01191 | 50.85 | 63820.45 | 3191.02 | Paid | 60629.43 | 2026-Q1
EXP-003321 | 2026-03-07 | BOQ-PKG-01-01331 | PKG-01 | INV-PKG-01-032-03321 | 105.01 | 84821.11 | 4241.06 | Paid | 80580.05 | 2026-Q1
EXP-004083 | 2026-03-07 | BOQ-PKG-03-00103 | PKG-03 | INV-PKG-03-024-04083 | 319 | 143201.68 | 7160.08 | Paid | 136041.6 | 2026-Q1
EXP-004238 | 2026-03-07 | BOQ-PKG-08-00258 | PKG-08 | INV-PKG-08-004-04238 | 329.32 | 69102.36 | 3455.12 | Paid | 65647.24 | 2026-Q1
EXP-004362 | 2026-03-07 | BOQ-PKG-02-00382 | PKG-02 | INV-PKG-02-023-04362 | 80.27 | 99624.48 | 4981.22 | Paid | 94643.26 | 2026-Q1
EXP-004623 | 2026-03-07 | BOQ-PKG-03-00643 | PKG-03 | INV-PKG-03-004-04623 | 352.91 | 188985.25 | 9449.26 | Paid | 179535.99 | 2026-Q1
EXP-004915 | 2026-03-07 | BOQ-PKG-05-00935 | PKG-05 | INV-PKG-05-016-04915 | 250.02 | 55437.36 | 2771.87 | Paid | 52665.49 | 2026-Q1
EXP-000010 | 2026-03-08 | BOQ-PKG-10-00010 | PKG-10 | INV-PKG-10-011-00010 | 181.66 | 54113.98 | 2705.7 | Paid | 51408.28 | 2026-Q1
EXP-001766 | 2026-03-08 | BOQ-PKG-06-01766 | PKG-06 | INV-PKG-06-017-01766 | 110.5 | 84245.87 | 4212.29 | Paid | 80033.58 | 2026-Q1
EXP-002080 | 2026-03-08 | BOQ-PKG-10-00090 | PKG-10 | INV-PKG-10-016-02080 | 380.53 | 147306.82 | 7365.34 | Paid | 139941.48 | 2026-Q1
EXP-002947 | 2026-03-08 | BOQ-PKG-07-00957 | PKG-07 | INV-PKG-07-008-02947 | 316.36 | 209545.46 | 10477.27 | Paid | 199068.19 | 2026-Q1
EXP-003067 | 2026-03-08 | BOQ-PKG-07-01077 | PKG-07 | INV-PKG-07-023-03067 | 247.68 | 64182.74 | 3209.14 | Paid | 60973.6 | 2026-Q1
EXP-003929 | 2026-03-08 | BOQ-PKG-09-01939 | PKG-09 | INV-PKG-09-010-03929 | 342.87 | 89082.57 | 4454.13 | Paid | 84628.44 | 2026-Q1
EXP-005247 | 2026-03-08 | BOQ-PKG-07-01267 | PKG-07 | INV-PKG-07-033-05247 | 133.14 | 100144.41 | 5007.22 | Paid | 95137.19 | 2026-Q1
EXP-006211 | 2026-03-08 | BOQ-PKG-01-00241 | PKG-01 | INV-PKG-01-017-06211 | 38.82 | 127742.26 | 6387.11 | Approved Pending Payment | 121355.15 | 2026-Q1
EXP-000563 | 2026-03-09 | BOQ-PKG-03-00563 | PKG-03 | INV-PKG-03-004-00563 | 140.06 | 96928.19 | 4846.41 | Paid | 92081.78 | 2026-Q1
EXP-000870 | 2026-03-09 | BOQ-PKG-10-00870 | PKG-10 | INV-PKG-10-031-00870 | 61.04 | 198050.71 | 9902.54 | Paid | 188148.17 | 2026-Q1
EXP-001288 | 2026-03-09 | BOQ-PKG-08-01288 | PKG-08 | INV-PKG-08-029-01288 | 315.52 | 39039.92 | 1952 | Paid | 37087.92 | 2026-Q1
EXP-001594 | 2026-03-09 | BOQ-PKG-04-01594 | PKG-04 | INV-PKG-04-020-01594 | 153.66 | 75094.69 | 3754.73 | Approved Pending Payment | 71339.96 | 2026-Q1
EXP-004889 | 2026-03-09 | BOQ-PKG-09-00909 | PKG-09 | INV-PKG-09-025-04889 | 166.77 | 88672.25 | 4433.61 | Paid | 84238.64 | 2026-Q1
EXP-005481 | 2026-03-09 | BOQ-PKG-01-01501 | PKG-01 | INV-PKG-01-022-05481 | 364.29 | 165574.9 | 8278.75 | Paid | 157296.15 | 2026-Q1
EXP-006063 | 2026-03-09 | BOQ-PKG-03-00093 | PKG-03 | INV-PKG-03-009-06063 | 147.81 | 175503.45 | 8775.17 | Paid | 166728.28 | 2026-Q1
EXP-006289 | 2026-03-09 | BOQ-PKG-09-00319 | PKG-09 | INV-PKG-09-025-06289 | 278.87 | 144476.37 | 7223.82 | Under Review | 137252.55 | 2026-Q1
EXP-000461 | 2026-03-10 | BOQ-PKG-01-00461 | PKG-01 | INV-PKG-01-007-00461 | 255.38 | 169029.02 | 8451.45 | Paid | 160577.57 | 2026-Q1
EXP-000933 | 2026-03-10 | BOQ-PKG-03-00933 | PKG-03 | INV-PKG-03-024-00933 | 194.13 | 73979.74 | 3698.99 | Paid | 70280.75 | 2026-Q1
EXP-001116 | 2026-03-10 | BOQ-PKG-06-01116 | PKG-06 | INV-PKG-06-032-01116 | 52.58 | 120005.92 | 6000.3 | Paid | 114005.62 | 2026-Q1
EXP-002228 | 2026-03-10 | BOQ-PKG-08-00238 | PKG-08 | INV-PKG-08-024-02228 | 303.41 | 184308.69 | 9215.43 | Paid | 175093.26 | 2026-Q1
EXP-003171 | 2026-03-10 | BOQ-PKG-01-01181 | PKG-01 | INV-PKG-01-022-03171 | 125.64 | 130102.78 | 6505.14 | Paid | 123597.64 | 2026-Q1
EXP-003671 | 2026-03-10 | BOQ-PKG-01-01681 | PKG-01 | INV-PKG-01-032-03671 | 82.5 | 103243.28 | 5162.16 | Disputed | 98081.12 | 2026-Q1
EXP-003750 | 2026-03-10 | BOQ-PKG-10-01760 | PKG-10 | INV-PKG-10-006-03750 | 159.09 | 39271.36 | 1963.57 | Paid | 37307.79 | 2026-Q1
EXP-004202 | 2026-03-10 | BOQ-PKG-02-00222 | PKG-02 | INV-PKG-02-003-04202 | 328.84 | 100082.34 | 5004.12 | Under Review | 95078.22 | 2026-Q1
EXP-004427 | 2026-03-10 | BOQ-PKG-07-00447 | PKG-07 | INV-PKG-07-018-04427 | 417.37 | 102784.63 | 5139.23 | Paid | 97645.4 | 2026-Q1
EXP-004478 | 2026-03-10 | BOQ-PKG-08-00498 | PKG-08 | INV-PKG-08-034-04478 | 383.16 | 66419.43 | 3320.97 | Approved Pending Payment | 63098.46 | 2026-Q1
EXP-004800 | 2026-03-10 | BOQ-PKG-10-00820 | PKG-10 | INV-PKG-10-006-04800 | 407.96 | 95852.69 | 4792.63 | Under Review | 91060.06 | 2026-Q1
EXP-005510 | 2026-03-10 | BOQ-PKG-10-01530 | PKG-10 | INV-PKG-10-016-05510 | 400.8 | 130213.06 | 6510.65 | Paid | 123702.41 | 2026-Q1
EXP-005740 | 2026-03-10 | BOQ-PKG-10-01760 | PKG-10 | INV-PKG-10-001-05740 | 71.04 | 108626.48 | 5431.32 | Paid | 103195.16 | 2026-Q1
EXP-000160 | 2026-03-11 | BOQ-PKG-10-00160 | PKG-10 | INV-PKG-10-021-00160 | 5.27 | 79760.63 | 3988.03 | Paid | 75772.6 | 2026-Q1
EXP-003970 | 2026-03-11 | BOQ-PKG-10-01980 | PKG-10 | INV-PKG-10-016-03970 | 349.64 | 151935.09 | 7596.75 | Disputed | 144338.34 | 2026-Q1
EXP-004587 | 2026-03-11 | BOQ-PKG-07-00607 | PKG-07 | INV-PKG-07-003-04587 | 389.85 | 131805.61 | 6590.28 | Paid | 125215.33 | 2026-Q1
EXP-006237 | 2026-03-11 | BOQ-PKG-07-00267 | PKG-07 | INV-PKG-07-008-06237 | 335.31 | 183913.99 | 9195.7 | Paid | 174718.29 | 2026-Q1
EXP-006952 | 2026-03-11 | BOQ-PKG-02-00982 | PKG-02 | INV-PKG-02-023-06952 | 99.71 | 101517.74 | 5075.89 | Paid | 96441.85 | 2026-Q1
EXP-002027 | 2026-03-12 | BOQ-PKG-07-00037 | PKG-07 | INV-PKG-07-033-02027 | 273.21 | 59029.57 | 2951.48 | Paid | 56078.09 | 2026-Q1
EXP-002143 | 2026-03-12 | BOQ-PKG-03-00153 | PKG-03 | INV-PKG-03-009-02143 | 89.9 | 176802.58 | 8840.13 | Paid | 167962.45 | 2026-Q1
EXP-003041 | 2026-03-12 | BOQ-PKG-01-01051 | PKG-01 | INV-PKG-01-032-03041 | 125.94 | 200122.18 | 10006.11 | Under Review | 190116.07 | 2026-Q1
EXP-003789 | 2026-03-12 | BOQ-PKG-09-01799 | PKG-09 | INV-PKG-09-010-03789 | 405 | 36090.69 | 1804.53 | Paid | 34286.16 | 2026-Q1
EXP-006613 | 2026-03-12 | BOQ-PKG-03-00643 | PKG-03 | INV-PKG-03-034-06613 | 422.35 | 177214.16 | 8860.71 | Paid | 168353.45 | 2026-Q1
EXP-006703 | 2026-03-12 | BOQ-PKG-03-00733 | PKG-03 | INV-PKG-03-019-06703 | 303.56 | 206215.9 | 10310.8 | Paid | 195905.1 | 2026-Q1
EXP-000875 | 2026-03-13 | BOQ-PKG-05-00875 | PKG-05 | INV-PKG-05-001-00875 | 26.93 | 183792.66 | 9189.63 | Paid | 174603.03 | 2026-Q1
EXP-001701 | 2026-03-13 | BOQ-PKG-01-01701 | PKG-01 | INV-PKG-01-022-01701 | 384.63 | 62752.82 | 3137.64 | Approved Pending Payment | 59615.18 | 2026-Q1
EXP-002429 | 2026-03-13 | BOQ-PKG-09-00439 | PKG-09 | INV-PKG-09-015-02429 | 307.4 | 67378.26 | 3368.91 | Paid | 64009.35 | 2026-Q1
EXP-003385 | 2026-03-13 | BOQ-PKG-05-01395 | PKG-05 | INV-PKG-05-026-03385 | 70.63 | 128282.05 | 6414.1 | Under Review | 121867.95 | 2026-Q1
EXP-003936 | 2026-03-13 | BOQ-PKG-06-01946 | PKG-06 | INV-PKG-06-017-03936 | 108 | 96560.91 | 4828.05 | Paid | 91732.86 | 2026-Q1
EXP-005265 | 2026-03-13 | BOQ-PKG-05-01285 | PKG-05 | INV-PKG-05-016-05265 | 83.93 | 64127.96 | 3206.4 | Approved Pending Payment | 60921.56 | 2026-Q1
EXP-005552 | 2026-03-13 | BOQ-PKG-02-01572 | PKG-02 | INV-PKG-02-023-05552 | 438.5 | 105837.35 | 5291.87 | Approved Pending Payment | 100545.48 | 2026-Q1
EXP-006434 | 2026-03-13 | BOQ-PKG-04-00464 | PKG-04 | INV-PKG-04-030-06434 | 202.73 | 57502.93 | 2875.15 | Paid | 54627.78 | 2026-Q1
EXP-006899 | 2026-03-13 | BOQ-PKG-09-00929 | PKG-09 | INV-PKG-09-005-06899 | 233.94 | 71663.61 | 3583.18 | Under Review | 68080.43 | 2026-Q1
EXP-002007 | 2026-03-14 | BOQ-PKG-07-00017 | PKG-07 | INV-PKG-07-013-02007 | 410.72 | 72950.69 | 3647.53 | Paid | 69303.16 | 2026-Q1
EXP-002625 | 2026-03-14 | BOQ-PKG-05-00635 | PKG-05 | INV-PKG-05-001-02625 | 383.08 | 140431.3 | 7021.56 | Paid | 133409.74 | 2026-Q1
EXP-002819 | 2026-03-14 | BOQ-PKG-09-00829 | PKG-09 | INV-PKG-09-020-02819 | 422.62 | 191535.75 | 9576.79 | Paid | 181958.96 | 2026-Q1
EXP-005284 | 2026-03-14 | BOQ-PKG-04-01304 | PKG-04 | INV-PKG-04-035-05284 | 376.96 | 135450.65 | 6772.53 | Under Review | 128678.12 | 2026-Q1
EXP-006726 | 2026-03-14 | BOQ-PKG-06-00756 | PKG-06 | INV-PKG-06-007-06726 | 357.42 | 48113.93 | 2405.7 | Under Review | 45708.23 | 2026-Q1
EXP-006776 | 2026-03-14 | BOQ-PKG-06-00806 | PKG-06 | INV-PKG-06-022-06776 | 63.42 | 166550.61 | 8327.53 | Paid | 158223.08 | 2026-Q1
EXP-000001 | 2026-03-15 | BOQ-PKG-01-00001 | PKG-01 | INV-PKG-01-002-00001 | 363.51 | 64408.34 | 3220.42 | Approved Pending Payment | 61187.92 | 2026-Q1
EXP-001494 | 2026-03-15 | BOQ-PKG-04-01494 | PKG-04 | INV-PKG-04-025-01494 | 403.73 | 97523.39 | 4876.17 | Under Review | 92647.22 | 2026-Q1
EXP-001690 | 2026-03-15 | BOQ-PKG-10-01690 | PKG-10 | INV-PKG-10-011-01690 | 209.15 | 132315.29 | 6615.76 | Paid | 125699.53 | 2026-Q1
EXP-002036 | 2026-03-15 | BOQ-PKG-06-00046 | PKG-06 | INV-PKG-06-007-02036 | 396.86 | 141118.31 | 7055.92 | Paid | 134062.39 | 2026-Q1
EXP-004681 | 2026-03-15 | BOQ-PKG-01-00701 | PKG-01 | INV-PKG-01-027-04681 | 297.14 | 116619.04 | 5830.95 | Under Review | 110788.09 | 2026-Q1
EXP-006274 | 2026-03-15 | BOQ-PKG-04-00304 | PKG-04 | INV-PKG-04-010-06274 | 119.45 | 107822.93 | 5391.15 | Paid | 102431.78 | 2026-Q1
EXP-006392 | 2026-03-15 | BOQ-PKG-02-00422 | PKG-02 | INV-PKG-02-023-06392 | 332.3 | 77049.55 | 3852.48 | Paid | 73197.07 | 2026-Q1
EXP-001117 | 2026-03-16 | BOQ-PKG-07-01117 | PKG-07 | INV-PKG-07-033-01117 | 37.16 | 153307.55 | 7665.38 | Paid | 145642.17 | 2026-Q1
EXP-001513 | 2026-03-16 | BOQ-PKG-03-01513 | PKG-03 | INV-PKG-03-009-01513 | 59.07 | 174930.64 | 8746.53 | Paid | 166184.11 | 2026-Q1
EXP-001693 | 2026-03-16 | BOQ-PKG-03-01693 | PKG-03 | INV-PKG-03-014-01693 | 278.41 | 190369.43 | 9518.47 | Paid | 180850.96 | 2026-Q1
EXP-001873 | 2026-03-16 | BOQ-PKG-03-01873 | PKG-03 | INV-PKG-03-019-01873 | 24.73 | 82669.21 | 4133.46 | Paid | 78535.75 | 2026-Q1
EXP-001896 | 2026-03-16 | BOQ-PKG-06-01896 | PKG-06 | INV-PKG-06-007-01896 | 13.56 | 46611.7 | 2330.58 | Paid | 44281.12 | 2026-Q1
EXP-002612 | 2026-03-16 | BOQ-PKG-02-00622 | PKG-02 | INV-PKG-02-023-02612 | 51.82 | 52148.03 | 2607.4 | Paid | 49540.63 | 2026-Q1
EXP-003383 | 2026-03-16 | BOQ-PKG-03-01393 | PKG-03 | INV-PKG-03-024-03383 | 303.89 | 58647.54 | 2932.38 | Paid | 55715.16 | 2026-Q1
EXP-004529 | 2026-03-16 | BOQ-PKG-09-00549 | PKG-09 | INV-PKG-09-015-04529 | 102.04 | 173818.98 | 8690.95 | Paid | 165128.03 | 2026-Q1
EXP-000309 | 2026-03-17 | BOQ-PKG-09-00309 | PKG-09 | INV-PKG-09-030-00309 | 261.92 | 144158.15 | 7207.91 | Paid | 136950.24 | 2026-Q1
EXP-001471 | 2026-03-17 | BOQ-PKG-01-01471 | PKG-01 | INV-PKG-01-002-01471 | 67.43 | 192880.16 | 9644.01 | Paid | 183236.15 | 2026-Q1
EXP-002274 | 2026-03-17 | BOQ-PKG-04-00284 | PKG-04 | INV-PKG-04-035-02274 | 180.79 | 126526.42 | 6326.32 | Paid | 120200.1 | 2026-Q1
EXP-002438 | 2026-03-17 | BOQ-PKG-08-00448 | PKG-08 | INV-PKG-08-024-02438 | 216.92 | 207381.61 | 10369.08 | Paid | 197012.53 | 2026-Q1
EXP-003255 | 2026-03-17 | BOQ-PKG-05-01265 | PKG-05 | INV-PKG-05-001-03255 | 174.82 | 175494.91 | 8774.75 | Paid | 166720.16 | 2026-Q1
EXP-004329 | 2026-03-17 | BOQ-PKG-09-00349 | PKG-09 | INV-PKG-09-025-04329 | 248.11 | 111558.63 | 5577.93 | Paid | 105980.7 | 2026-Q1
EXP-004887 | 2026-03-17 | BOQ-PKG-07-00907 | PKG-07 | INV-PKG-07-023-04887 | 54.64 | 208867.47 | 10443.37 | Paid | 198424.1 | 2026-Q1
EXP-005385 | 2026-03-17 | BOQ-PKG-05-01405 | PKG-05 | INV-PKG-05-031-05385 | 178.02 | 137258.42 | 6862.92 | Under Review | 130395.5 | 2026-Q1
EXP-006469 | 2026-03-17 | BOQ-PKG-09-00499 | PKG-09 | INV-PKG-09-030-06469 | 429.77 | 49304.22 | 2465.21 | Approved Pending Payment | 46839.01 | 2026-Q1
EXP-006670 | 2026-03-17 | BOQ-PKG-10-00700 | PKG-10 | INV-PKG-10-021-06670 | 320.33 | 128112.02 | 6405.6 | Paid | 121706.42 | 2026-Q1
EXP-006914 | 2026-03-17 | BOQ-PKG-04-00944 | PKG-04 | INV-PKG-04-020-06914 | 344.27 | 156487.32 | 7824.37 | Paid | 148662.95 | 2026-Q1
EXP-002124 | 2026-03-18 | BOQ-PKG-04-00134 | PKG-04 | INV-PKG-04-025-02124 | 421.51 | 206943.95 | 10347.2 | Disputed | 196596.75 | 2026-Q1
EXP-002175 | 2026-03-18 | BOQ-PKG-05-00185 | PKG-05 | INV-PKG-05-006-02175 | 329.79 | 159937.08 | 7996.85 | Paid | 151940.23 | 2026-Q1
EXP-002272 | 2026-03-18 | BOQ-PKG-02-00282 | PKG-02 | INV-PKG-02-033-02272 | 19.74 | 73871.05 | 3693.55 | Paid | 70177.5 | 2026-Q1
EXP-003453 | 2026-03-18 | BOQ-PKG-03-01463 | PKG-03 | INV-PKG-03-024-03453 | 178.73 | 25740.46 | 1287.02 | Paid | 24453.44 | 2026-Q1
EXP-004397 | 2026-03-18 | BOQ-PKG-07-00417 | PKG-07 | INV-PKG-07-023-04397 | 398.2 | 100412.18 | 5020.61 | Paid | 95391.57 | 2026-Q1
EXP-004871 | 2026-03-18 | BOQ-PKG-01-00891 | PKG-01 | INV-PKG-01-007-04871 | 396.75 | 114653.34 | 5732.67 | Paid | 108920.67 | 2026-Q1
EXP-005178 | 2026-03-18 | BOQ-PKG-08-01198 | PKG-08 | INV-PKG-08-034-05178 | 11.79 | 136448.95 | 6822.45 | Paid | 129626.5 | 2026-Q1
EXP-005193 | 2026-03-18 | BOQ-PKG-03-01213 | PKG-03 | INV-PKG-03-014-05193 | 262.16 | 186797.91 | 9339.9 | Under Review | 177458.01 | 2026-Q1
EXP-006136 | 2026-03-18 | BOQ-PKG-06-00166 | PKG-06 | INV-PKG-06-012-06136 | 124.47 | 185354.26 | 9267.71 | Paid | 176086.55 | 2026-Q1
EXP-000612 | 2026-03-19 | BOQ-PKG-02-00612 | PKG-02 | INV-PKG-02-018-00612 | 122.91 | 108020.8 | 5401.04 | Paid | 102619.76 | 2026-Q1
EXP-002082 | 2026-03-19 | BOQ-PKG-02-00092 | PKG-02 | INV-PKG-02-018-02082 | 367.46 | 142867.22 | 7143.36 | Paid | 135723.86 | 2026-Q1
EXP-002136 | 2026-03-19 | BOQ-PKG-06-00146 | PKG-06 | INV-PKG-06-002-02136 | 306.74 | 148388.48 | 7419.42 | Disputed | 140969.06 | 2026-Q1
EXP-004648 | 2026-03-19 | BOQ-PKG-08-00668 | PKG-08 | INV-PKG-08-029-04648 | 297.18 | 86064.96 | 4303.25 | Disputed | 81761.71 | 2026-Q1
EXP-006743 | 2026-03-19 | BOQ-PKG-03-00773 | PKG-03 | INV-PKG-03-024-06743 | 381.34 | 147199.91 | 7360 | Approved Pending Payment | 139839.91 | 2026-Q1
EXP-000707 | 2026-03-20 | BOQ-PKG-07-00707 | PKG-07 | INV-PKG-07-008-00707 | 447.99 | 27297.66 | 1364.88 | Paid | 25932.78 | 2026-Q1
EXP-001756 | 2026-03-20 | BOQ-PKG-06-01756 | PKG-06 | INV-PKG-06-007-01756 | 171.13 | 183027.89 | 9151.39 | Paid | 173876.5 | 2026-Q1
EXP-001843 | 2026-03-20 | BOQ-PKG-03-01843 | PKG-03 | INV-PKG-03-024-01843 | 166.9 | 37710.68 | 1885.53 | Paid | 35825.15 | 2026-Q1
EXP-002164 | 2026-03-20 | BOQ-PKG-04-00174 | PKG-04 | INV-PKG-04-030-02164 | 134.02 | 58362.67 | 2918.13 | Approved Pending Payment | 55444.54 | 2026-Q1
EXP-002356 | 2026-03-20 | BOQ-PKG-06-00366 | PKG-06 | INV-PKG-06-012-02356 | 300.95 | 71540.75 | 3577.04 | Paid | 67963.71 | 2026-Q1
EXP-002422 | 2026-03-20 | BOQ-PKG-02-00432 | PKG-02 | INV-PKG-02-008-02422 | 259.53 | 188692.9 | 9434.64 | Under Review | 179258.26 | 2026-Q1
EXP-003334 | 2026-03-20 | BOQ-PKG-04-01344 | PKG-04 | INV-PKG-04-010-03334 | 33.21 | 76650.47 | 3832.52 | Paid | 72817.95 | 2026-Q1
EXP-003526 | 2026-03-20 | BOQ-PKG-06-01536 | PKG-06 | INV-PKG-06-027-03526 | 222.9 | 173455.15 | 8672.76 | Paid | 164782.39 | 2026-Q1
EXP-003629 | 2026-03-20 | BOQ-PKG-09-01639 | PKG-09 | INV-PKG-09-025-03629 | 11.75 | 206508.2 | 10325.41 | Approved Pending Payment | 196182.79 | 2026-Q1
EXP-004298 | 2026-03-20 | BOQ-PKG-08-00318 | PKG-08 | INV-PKG-08-029-04298 | 47.17 | 131696.76 | 6584.84 | Approved Pending Payment | 125111.92 | 2026-Q1
EXP-004932 | 2026-03-20 | BOQ-PKG-02-00952 | PKG-02 | INV-PKG-02-033-04932 | 338.64 | 97778.09 | 4888.9 | Paid | 92889.19 | 2026-Q1
EXP-004960 | 2026-03-20 | BOQ-PKG-10-00980 | PKG-10 | INV-PKG-10-026-04960 | 278.75 | 68314.59 | 3415.73 | Approved Pending Payment | 64898.86 | 2026-Q1
EXP-005649 | 2026-03-20 | BOQ-PKG-09-01669 | PKG-09 | INV-PKG-09-015-05649 | 315.62 | 26078.93 | 1303.95 | Paid | 24774.98 | 2026-Q1
EXP-000328 | 2026-03-21 | BOQ-PKG-08-00328 | PKG-08 | INV-PKG-08-014-00328 | 395.32 | 69616.92 | 3480.85 | Paid | 66136.07 | 2026-Q1
EXP-002268 | 2026-03-21 | BOQ-PKG-08-00278 | PKG-08 | INV-PKG-08-029-02268 | 14.63 | 68828.82 | 3441.44 | Paid | 65387.38 | 2026-Q1
EXP-003551 | 2026-03-21 | BOQ-PKG-01-01561 | PKG-01 | INV-PKG-01-017-03551 | 445.26 | 116281.76 | 5814.09 | Paid | 110467.67 | 2026-Q1
EXP-004923 | 2026-03-21 | BOQ-PKG-03-00943 | PKG-03 | INV-PKG-03-024-04923 | 317.35 | 87763.84 | 4388.19 | Paid | 83375.65 | 2026-Q1
EXP-005467 | 2026-03-21 | BOQ-PKG-07-01487 | PKG-07 | INV-PKG-07-008-05467 | 405.56 | 109357.67 | 5467.88 | Under Review | 103889.79 | 2026-Q1
EXP-006721 | 2026-03-21 | BOQ-PKG-01-00751 | PKG-01 | INV-PKG-01-002-06721 | 402.33 | 78256.85 | 3912.84 | Paid | 74344.01 | 2026-Q1
EXP-006775 | 2026-03-21 | BOQ-PKG-05-00805 | PKG-05 | INV-PKG-05-021-06775 | 130.21 | 134695.97 | 6734.8 | Paid | 127961.17 | 2026-Q1
EXP-006972 | 2026-03-21 | BOQ-PKG-02-01002 | PKG-02 | INV-PKG-02-008-06972 | 220.13 | 84207.82 | 4210.39 | Paid | 79997.43 | 2026-Q1
EXP-000779 | 2026-03-22 | BOQ-PKG-09-00779 | PKG-09 | INV-PKG-09-010-00779 | 19.24 | 205607.04 | 10280.35 | Paid | 195326.69 | 2026-Q1
EXP-000807 | 2026-03-22 | BOQ-PKG-07-00807 | PKG-07 | INV-PKG-07-003-00807 | 204.44 | 139697.62 | 6984.88 | Paid | 132712.74 | 2026-Q1
EXP-003257 | 2026-03-22 | BOQ-PKG-07-01267 | PKG-07 | INV-PKG-07-003-03257 | 390.26 | 125514.62 | 6275.73 | Paid | 119238.89 | 2026-Q1
EXP-003631 | 2026-03-22 | BOQ-PKG-01-01641 | PKG-01 | INV-PKG-01-027-03631 | 43.87 | 100794.77 | 5039.74 | Paid | 95755.03 | 2026-Q1
EXP-003831 | 2026-03-22 | BOQ-PKG-01-01841 | PKG-01 | INV-PKG-01-017-03831 | 117.44 | 47795.13 | 2389.76 | Disputed | 45405.37 | 2026-Q1
EXP-006719 | 2026-03-22 | BOQ-PKG-09-00749 | PKG-09 | INV-PKG-09-035-06719 | 324.83 | 115257.08 | 5762.85 | Under Review | 109494.23 | 2026-Q1
EXP-001290 | 2026-03-23 | BOQ-PKG-10-01290 | PKG-10 | INV-PKG-10-031-01290 | 149.01 | 174919.71 | 8745.99 | Approved Pending Payment | 166173.72 | 2026-Q1
EXP-001506 | 2026-03-23 | BOQ-PKG-06-01506 | PKG-06 | INV-PKG-06-002-01506 | 398.1 | 53207.92 | 2660.4 | Paid | 50547.52 | 2026-Q1
EXP-003538 | 2026-03-23 | BOQ-PKG-08-01548 | PKG-08 | INV-PKG-08-004-03538 | 424.28 | 146893.8 | 7344.69 | Paid | 139549.11 | 2026-Q1
EXP-003662 | 2026-03-23 | BOQ-PKG-02-01672 | PKG-02 | INV-PKG-02-023-03662 | 371.83 | 163192.76 | 8159.64 | Paid | 155033.12 | 2026-Q1
EXP-003955 | 2026-03-23 | BOQ-PKG-05-01965 | PKG-05 | INV-PKG-05-001-03955 | 86.69 | 192387.1 | 9619.36 | Paid | 182767.74 | 2026-Q1
EXP-004079 | 2026-03-23 | BOQ-PKG-09-00099 | PKG-09 | INV-PKG-09-020-04079 | 174.07 | 32850.98 | 1642.55 | Under Review | 31208.43 | 2026-Q1
EXP-000495 | 2026-03-24 | BOQ-PKG-05-00495 | PKG-05 | INV-PKG-05-006-00495 | 448.6 | 102820.01 | 5141 | Under Review | 97679.01 | 2026-Q1
EXP-000864 | 2026-03-24 | BOQ-PKG-04-00864 | PKG-04 | INV-PKG-04-025-00864 | 279.87 | 138929.72 | 6946.49 | Approved Pending Payment | 131983.23 | 2026-Q1
EXP-000966 | 2026-03-24 | BOQ-PKG-06-00966 | PKG-06 | INV-PKG-06-022-00966 | 189.61 | 161285.12 | 8064.26 | Paid | 153220.86 | 2026-Q1
EXP-002137 | 2026-03-24 | BOQ-PKG-07-00147 | PKG-07 | INV-PKG-07-003-02137 | 356.11 | 85831.7 | 4291.58 | Paid | 81540.12 | 2026-Q1
EXP-003349 | 2026-03-24 | BOQ-PKG-09-01359 | PKG-09 | INV-PKG-09-025-03349 | 157.14 | 198126.4 | 9906.32 | Paid | 188220.08 | 2026-Q1
EXP-005279 | 2026-03-24 | BOQ-PKG-09-01299 | PKG-09 | INV-PKG-09-030-05279 | 192.09 | 186297.58 | 9314.88 | Paid | 176982.7 | 2026-Q1
EXP-005487 | 2026-03-24 | BOQ-PKG-07-01507 | PKG-07 | INV-PKG-07-028-05487 | 109.79 | 96505.34 | 4825.27 | Under Review | 91680.07 | 2026-Q1
EXP-006132 | 2026-03-24 | BOQ-PKG-02-00162 | PKG-02 | INV-PKG-02-008-06132 | 118.8 | 135330.06 | 6766.5 | Paid | 128563.56 | 2026-Q1
EXP-006249 | 2026-03-24 | BOQ-PKG-09-00279 | PKG-09 | INV-PKG-09-020-06249 | 221.46 | 210231.86 | 10511.59 | Paid | 199720.27 | 2026-Q1
EXP-006900 | 2026-03-24 | BOQ-PKG-10-00930 | PKG-10 | INV-PKG-10-006-06900 | 93.27 | 83214.55 | 4160.73 | Paid | 79053.82 | 2026-Q1
EXP-006956 | 2026-03-24 | BOQ-PKG-06-00986 | PKG-06 | INV-PKG-06-027-06956 | 312.36 | 145972.05 | 7298.6 | Paid | 138673.45 | 2026-Q1
EXP-000084 | 2026-03-25 | BOQ-PKG-04-00084 | PKG-04 | INV-PKG-04-015-00084 | 136.99 | 37357.76 | 1867.89 | Paid | 35489.87 | 2026-Q1
EXP-000369 | 2026-03-25 | BOQ-PKG-09-00369 | PKG-09 | INV-PKG-09-020-00369 | 203.42 | 159076.57 | 7953.83 | Paid | 151122.74 | 2026-Q1
EXP-000452 | 2026-03-25 | BOQ-PKG-02-00452 | PKG-02 | INV-PKG-02-033-00452 | 291.67 | 149614.64 | 7480.73 | Under Review | 142133.91 | 2026-Q1
EXP-003188 | 2026-03-25 | BOQ-PKG-08-01198 | PKG-08 | INV-PKG-08-004-03188 | 155.51 | 66569.39 | 3328.47 | Under Review | 63240.92 | 2026-Q1
EXP-004699 | 2026-03-25 | BOQ-PKG-09-00719 | PKG-09 | INV-PKG-09-010-04699 | 440.3 | 62710.33 | 3135.52 | Paid | 59574.81 | 2026-Q1
EXP-005029 | 2026-03-25 | BOQ-PKG-09-01049 | PKG-09 | INV-PKG-09-025-05029 | 13.84 | 69909.4 | 3495.47 | Paid | 66413.93 | 2026-Q1
EXP-005407 | 2026-03-25 | BOQ-PKG-07-01427 | PKG-07 | INV-PKG-07-018-05407 | 44.41 | 28029.48 | 1401.47 | Paid | 26628.01 | 2026-Q1
EXP-005942 | 2026-03-25 | BOQ-PKG-02-01962 | PKG-02 | INV-PKG-02-028-05942 | 52.05 | 62522.81 | 3126.14 | Approved Pending Payment | 59396.67 | 2026-Q1
EXP-006009 | 2026-03-25 | BOQ-PKG-09-00039 | PKG-09 | INV-PKG-09-025-06009 | 83.33 | 79043.49 | 3952.17 | Approved Pending Payment | 75091.32 | 2026-Q1
EXP-000330 | 2026-03-26 | BOQ-PKG-10-00330 | PKG-10 | INV-PKG-10-016-00330 | 199.93 | 88186.83 | 4409.34 | Paid | 83777.49 | 2026-Q1
EXP-001439 | 2026-03-26 | BOQ-PKG-09-01439 | PKG-09 | INV-PKG-09-005-01439 | 324.51 | 203158.42 | 10157.92 | Under Review | 193000.5 | 2026-Q1
EXP-003076 | 2026-03-26 | BOQ-PKG-06-01086 | PKG-06 | INV-PKG-06-032-03076 | 332.96 | 188740.23 | 9437.01 | Paid | 179303.22 | 2026-Q1
EXP-003265 | 2026-03-26 | BOQ-PKG-05-01275 | PKG-05 | INV-PKG-05-011-03265 | 135.52 | 140940.68 | 7047.03 | Paid | 133893.65 | 2026-Q1
EXP-004134 | 2026-03-26 | BOQ-PKG-04-00154 | PKG-04 | INV-PKG-04-005-04134 | 323.92 | 43110.43 | 2155.52 | Paid | 40954.91 | 2026-Q1
EXP-004241 | 2026-03-26 | BOQ-PKG-01-00261 | PKG-01 | INV-PKG-01-007-04241 | 212.06 | 170285.27 | 8514.26 | Paid | 161771.01 | 2026-Q1
EXP-004403 | 2026-03-26 | BOQ-PKG-03-00423 | PKG-03 | INV-PKG-03-029-04403 | 163.18 | 104801.86 | 5240.09 | Paid | 99561.77 | 2026-Q1
EXP-005446 | 2026-03-26 | BOQ-PKG-06-01466 | PKG-06 | INV-PKG-06-022-05446 | 121.37 | 99101.36 | 4955.07 | Paid | 94146.29 | 2026-Q1
EXP-005728 | 2026-03-26 | BOQ-PKG-08-01748 | PKG-08 | INV-PKG-08-024-05728 | 302.4 | 52388.06 | 2619.4 | Under Review | 49768.66 | 2026-Q1
EXP-005884 | 2026-03-26 | BOQ-PKG-04-01904 | PKG-04 | INV-PKG-04-005-05884 | 404.78 | 73223.64 | 3661.18 | Approved Pending Payment | 69562.46 | 2026-Q1
EXP-000948 | 2026-03-27 | BOQ-PKG-08-00948 | PKG-08 | INV-PKG-08-004-00948 | 238.82 | 157645.93 | 7882.3 | Paid | 149763.63 | 2026-Q1
EXP-002306 | 2026-03-27 | BOQ-PKG-06-00316 | PKG-06 | INV-PKG-06-032-02306 | 345.8 | 94569.52 | 4728.48 | Paid | 89841.04 | 2026-Q1
EXP-003141 | 2026-03-27 | BOQ-PKG-01-01151 | PKG-01 | INV-PKG-01-027-03141 | 120.94 | 143647.46 | 7182.37 | Paid | 136465.09 | 2026-Q1
EXP-003301 | 2026-03-27 | BOQ-PKG-01-01311 | PKG-01 | INV-PKG-01-012-03301 | 44.1 | 183888.65 | 9194.43 | Approved Pending Payment | 174694.22 | 2026-Q1
EXP-003531 | 2026-03-27 | BOQ-PKG-01-01541 | PKG-01 | INV-PKG-01-032-03531 | 330.44 | 156022.32 | 7801.12 | Paid | 148221.2 | 2026-Q1
EXP-004077 | 2026-03-27 | BOQ-PKG-07-00097 | PKG-07 | INV-PKG-07-018-04077 | 329.55 | 175180.09 | 8759 | Paid | 166421.09 | 2026-Q1
EXP-004373 | 2026-03-27 | BOQ-PKG-03-00393 | PKG-03 | INV-PKG-03-034-04373 | 243 | 193518.69 | 9675.93 | Paid | 183842.76 | 2026-Q1
EXP-006696 | 2026-03-27 | BOQ-PKG-06-00726 | PKG-06 | INV-PKG-06-012-06696 | 158.82 | 91106.92 | 4555.35 | Under Review | 86551.57 | 2026-Q1
EXP-002820 | 2026-03-28 | BOQ-PKG-10-00830 | PKG-10 | INV-PKG-10-021-02820 | 275.33 | 91672.15 | 4583.61 | Paid | 87088.54 | 2026-Q1
EXP-003073 | 2026-03-28 | BOQ-PKG-03-01083 | PKG-03 | INV-PKG-03-029-03073 | 291.81 | 177445.4 | 8872.27 | Paid | 168573.13 | 2026-Q1
EXP-004602 | 2026-03-28 | BOQ-PKG-02-00622 | PKG-02 | INV-PKG-02-018-04602 | 292.73 | 29810.91 | 1490.55 | Under Review | 28320.36 | 2026-Q1
EXP-005103 | 2026-03-28 | BOQ-PKG-03-01123 | PKG-03 | INV-PKG-03-029-05103 | 329.32 | 130289.19 | 6514.46 | Paid | 123774.73 | 2026-Q1
EXP-005621 | 2026-03-28 | BOQ-PKG-01-01641 | PKG-01 | INV-PKG-01-022-05621 | 444.71 | 152946.24 | 7647.31 | Paid | 145298.93 | 2026-Q1
EXP-005646 | 2026-03-28 | BOQ-PKG-06-01666 | PKG-06 | INV-PKG-06-012-05646 | 406.95 | 63275.89 | 3163.79 | Paid | 60112.1 | 2026-Q1
EXP-006293 | 2026-03-28 | BOQ-PKG-03-00323 | PKG-03 | INV-PKG-03-029-06293 | 385.89 | 142517.35 | 7125.87 | Approved Pending Payment | 135391.48 | 2026-Q1
EXP-006865 | 2026-03-28 | BOQ-PKG-05-00895 | PKG-05 | INV-PKG-05-006-06865 | 166.72 | 56374.37 | 2818.72 | Paid | 53555.65 | 2026-Q1
EXP-000862 | 2026-03-29 | BOQ-PKG-02-00862 | PKG-02 | INV-PKG-02-023-00862 | 201.37 | 26380.91 | 1319.05 | Paid | 25061.86 | 2026-Q1
EXP-000923 | 2026-03-29 | BOQ-PKG-03-00923 | PKG-03 | INV-PKG-03-014-00923 | 9.24 | 102325.28 | 5116.26 | Approved Pending Payment | 97209.02 | 2026-Q1
EXP-001596 | 2026-03-29 | BOQ-PKG-06-01596 | PKG-06 | INV-PKG-06-022-01596 | 306.92 | 202238.35 | 10111.92 | Under Review | 192126.43 | 2026-Q1
EXP-002016 | 2026-03-29 | BOQ-PKG-06-00026 | PKG-06 | INV-PKG-06-022-02016 | 223.91 | 176208.4 | 8810.42 | Disputed | 167397.98 | 2026-Q1
EXP-002495 | 2026-03-29 | BOQ-PKG-05-00505 | PKG-05 | INV-PKG-05-011-02495 | 75.34 | 28602.64 | 1430.13 | Paid | 27172.51 | 2026-Q1
EXP-003430 | 2026-03-29 | BOQ-PKG-10-01440 | PKG-10 | INV-PKG-10-001-03430 | 155.66 | 168206.03 | 8410.3 | Approved Pending Payment | 159795.73 | 2026-Q1
EXP-003514 | 2026-03-29 | BOQ-PKG-04-01524 | PKG-04 | INV-PKG-04-015-03514 | 320.18 | 177253.62 | 8862.68 | Paid | 168390.94 | 2026-Q1
EXP-003915 | 2026-03-29 | BOQ-PKG-05-01925 | PKG-05 | INV-PKG-05-031-03915 | 139.38 | 90908.53 | 4545.43 | Paid | 86363.1 | 2026-Q1
EXP-004021 | 2026-03-29 | BOQ-PKG-01-00041 | PKG-01 | INV-PKG-01-032-04021 | 63.7 | 30267.19 | 1513.36 | Disputed | 28753.83 | 2026-Q1
EXP-005023 | 2026-03-29 | BOQ-PKG-03-01043 | PKG-03 | INV-PKG-03-019-05023 | 422.28 | 106941.5 | 5347.08 | Paid | 101594.42 | 2026-Q1
EXP-006747 | 2026-03-29 | BOQ-PKG-07-00777 | PKG-07 | INV-PKG-07-028-06747 | 144.23 | 116944 | 5847.2 | Paid | 111096.8 | 2026-Q1
EXP-001626 | 2026-03-30 | BOQ-PKG-06-01626 | PKG-06 | INV-PKG-06-017-01626 | 342.72 | 78949.33 | 3947.47 | Paid | 75001.86 | 2026-Q1
EXP-001932 | 2026-03-30 | BOQ-PKG-02-01932 | PKG-02 | INV-PKG-02-008-01932 | 339.56 | 108854.01 | 5442.7 | Paid | 103411.31 | 2026-Q1
EXP-002951 | 2026-03-30 | BOQ-PKG-01-00961 | PKG-01 | INV-PKG-01-012-02951 | 388.58 | 143651.62 | 7182.58 | Paid | 136469.04 | 2026-Q1
EXP-004827 | 2026-03-30 | BOQ-PKG-07-00847 | PKG-07 | INV-PKG-07-033-04827 | 150.25 | 156403.33 | 7820.17 | Paid | 148583.16 | 2026-Q1
EXP-006065 | 2026-03-30 | BOQ-PKG-05-00095 | PKG-05 | INV-PKG-05-011-06065 | 136.14 | 31692.18 | 1584.61 | Approved Pending Payment | 30107.57 | 2026-Q1
EXP-000784 | 2026-03-31 | BOQ-PKG-04-00784 | PKG-04 | INV-PKG-04-015-00784 | 319.2 | 113319.12 | 5665.96 | Under Review | 107653.16 | 2026-Q1
EXP-001177 | 2026-03-31 | BOQ-PKG-07-01177 | PKG-07 | INV-PKG-07-023-01177 | 237.11 | 202942.52 | 10147.13 | Paid | 192795.39 | 2026-Q1
EXP-001302 | 2026-03-31 | BOQ-PKG-02-01302 | PKG-02 | INV-PKG-02-008-01302 | 9.43 | 200896.47 | 10044.82 | Paid | 190851.65 | 2026-Q1
EXP-001842 | 2026-03-31 | BOQ-PKG-02-01842 | PKG-02 | INV-PKG-02-023-01842 | 109.86 | 205618.55 | 10280.93 | Under Review | 195337.62 | 2026-Q1
EXP-001987 | 2026-03-31 | BOQ-PKG-07-01987 | PKG-07 | INV-PKG-07-028-01987 | 66.94 | 136292.71 | 6814.64 | Paid | 129478.07 | 2026-Q1
EXP-002208 | 2026-03-31 | BOQ-PKG-08-00218 | PKG-08 | INV-PKG-08-004-02208 | 232.63 | 152133.33 | 7606.67 | Paid | 144526.66 | 2026-Q1
EXP-002522 | 2026-03-31 | BOQ-PKG-02-00532 | PKG-02 | INV-PKG-02-003-02522 | 77.5 | 71849.95 | 3592.5 | Paid | 68257.45 | 2026-Q1
EXP-003338 | 2026-03-31 | BOQ-PKG-08-01348 | PKG-08 | INV-PKG-08-014-03338 | 396.58 | 110892.58 | 5544.63 | Paid | 105347.95 | 2026-Q1
EXP-003657 | 2026-03-31 | BOQ-PKG-07-01667 | PKG-07 | INV-PKG-07-018-03657 | 266.39 | 51990.32 | 2599.52 | Paid | 49390.8 | 2026-Q1
EXP-003881 | 2026-03-31 | BOQ-PKG-01-01891 | PKG-01 | INV-PKG-01-032-03881 | 248.42 | 202406.84 | 10120.34 | Under Review | 192286.5 | 2026-Q1
EXP-005345 | 2026-03-31 | BOQ-PKG-05-01365 | PKG-05 | INV-PKG-05-026-05345 | 429.14 | 163244.87 | 8162.24 | Disputed | 155082.63 | 2026-Q1
EXP-005554 | 2026-03-31 | BOQ-PKG-04-01574 | PKG-04 | INV-PKG-04-025-05554 | 191.1 | 50830.38 | 2541.52 | Disputed | 48288.86 | 2026-Q1
EXP-005919 | 2026-03-31 | BOQ-PKG-09-01939 | PKG-09 | INV-PKG-09-005-05919 | 9.62 | 180700.77 | 9035.04 | Approved Pending Payment | 171665.73 | 2026-Q1
EXP-000045 | 2026-04-01 | BOQ-PKG-05-00045 | PKG-05 | INV-PKG-05-011-00045 | 92.33 | 49099.27 | 2454.96 | Paid | 46644.31 | 2026-Q2
EXP-001844 | 2026-04-01 | BOQ-PKG-04-01844 | PKG-04 | INV-PKG-04-025-01844 | 448.22 | 117376.16 | 5868.81 | Paid | 111507.35 | 2026-Q2
EXP-000339 | 2026-04-02 | BOQ-PKG-09-00339 | PKG-09 | INV-PKG-09-025-00339 | 132.33 | 141427.91 | 7071.4 | Under Review | 134356.51 | 2026-Q2
EXP-001512 | 2026-04-02 | BOQ-PKG-02-01512 | PKG-02 | INV-PKG-02-008-01512 | 408.28 | 119356.78 | 5967.84 | Paid | 113388.94 | 2026-Q2
EXP-002545 | 2026-04-02 | BOQ-PKG-05-00555 | PKG-05 | INV-PKG-05-026-02545 | 29.72 | 52020.42 | 2601.02 | Approved Pending Payment | 49419.4 | 2026-Q2
EXP-002933 | 2026-04-02 | BOQ-PKG-03-00943 | PKG-03 | INV-PKG-03-029-02933 | 362.52 | 114000.17 | 5700.01 | Approved Pending Payment | 108300.16 | 2026-Q2
EXP-003325 | 2026-04-02 | BOQ-PKG-05-01335 | PKG-05 | INV-PKG-05-001-03325 | 145.44 | 206958.15 | 10347.91 | Paid | 196610.24 | 2026-Q2
EXP-003836 | 2026-04-02 | BOQ-PKG-06-01846 | PKG-06 | INV-PKG-06-022-03836 | 230.78 | 112298.78 | 5614.94 | Paid | 106683.84 | 2026-Q2
EXP-001964 | 2026-04-03 | BOQ-PKG-04-01964 | PKG-04 | INV-PKG-04-005-01964 | 434.37 | 136730.25 | 6836.51 | Approved Pending Payment | 129893.74 | 2026-Q2
EXP-002150 | 2026-04-03 | BOQ-PKG-10-00160 | PKG-10 | INV-PKG-10-016-02150 | 263.03 | 125178.13 | 6258.91 | Under Review | 118919.22 | 2026-Q2
EXP-005166 | 2026-04-03 | BOQ-PKG-06-01186 | PKG-06 | INV-PKG-06-022-05166 | 379.19 | 45014.7 | 2250.74 | Paid | 42763.96 | 2026-Q2
EXP-006847 | 2026-04-03 | BOQ-PKG-07-00877 | PKG-07 | INV-PKG-07-023-06847 | 255.08 | 149415.2 | 7470.76 | Paid | 141944.44 | 2026-Q2
EXP-000655 | 2026-04-04 | BOQ-PKG-05-00655 | PKG-05 | INV-PKG-05-026-00655 | 411.88 | 75794.21 | 3789.71 | Paid | 72004.5 | 2026-Q2
EXP-001879 | 2026-04-04 | BOQ-PKG-09-01879 | PKG-09 | INV-PKG-09-025-01879 | 114.98 | 27471.33 | 1373.57 | Paid | 26097.76 | 2026-Q2
EXP-002126 | 2026-04-04 | BOQ-PKG-06-00136 | PKG-06 | INV-PKG-06-027-02126 | 351.61 | 141920.46 | 7096.02 | Paid | 134824.44 | 2026-Q2
EXP-005752 | 2026-04-04 | BOQ-PKG-02-01772 | PKG-02 | INV-PKG-02-013-05752 | 172.68 | 90656.38 | 4532.82 | Paid | 86123.56 | 2026-Q2
EXP-006236 | 2026-04-04 | BOQ-PKG-06-00266 | PKG-06 | INV-PKG-06-007-06236 | 338.6 | 120628.47 | 6031.42 | Paid | 114597.05 | 2026-Q2
EXP-000956 | 2026-04-05 | BOQ-PKG-06-00956 | PKG-06 | INV-PKG-06-012-00956 | 107.57 | 83164.47 | 4158.22 | Paid | 79006.25 | 2026-Q2
EXP-001373 | 2026-04-05 | BOQ-PKG-03-01373 | PKG-03 | INV-PKG-03-009-01373 | 214.76 | 183082.7 | 9154.14 | Paid | 173928.56 | 2026-Q2
EXP-001773 | 2026-04-05 | BOQ-PKG-03-01773 | PKG-03 | INV-PKG-03-024-01773 | 259.38 | 105905.31 | 5295.27 | Paid | 100610.04 | 2026-Q2
EXP-002734 | 2026-04-05 | BOQ-PKG-04-00744 | PKG-04 | INV-PKG-04-005-02734 | 39.93 | 156440.49 | 7822.02 | Disputed | 148618.47 | 2026-Q2
EXP-002874 | 2026-04-05 | BOQ-PKG-04-00884 | PKG-04 | INV-PKG-04-005-02874 | 339.23 | 175361.14 | 8768.06 | Paid | 166593.08 | 2026-Q2
EXP-003397 | 2026-04-05 | BOQ-PKG-07-01407 | PKG-07 | INV-PKG-07-003-03397 | 71.69 | 200671.47 | 10033.57 | Under Review | 190637.9 | 2026-Q2
EXP-003574 | 2026-04-05 | BOQ-PKG-04-01584 | PKG-04 | INV-PKG-04-005-03574 | 192.09 | 143489.44 | 7174.47 | Paid | 136314.97 | 2026-Q2
EXP-004168 | 2026-04-05 | BOQ-PKG-08-00188 | PKG-08 | INV-PKG-08-004-04168 | 271.48 | 74750.88 | 3737.54 | Paid | 71013.34 | 2026-Q2
EXP-004444 | 2026-04-05 | BOQ-PKG-04-00464 | PKG-04 | INV-PKG-04-035-04444 | 280.27 | 142274.89 | 7113.74 | Paid | 135161.15 | 2026-Q2
EXP-004611 | 2026-04-05 | BOQ-PKG-01-00631 | PKG-01 | INV-PKG-01-027-04611 | 34.66 | 97937.29 | 4896.86 | Paid | 93040.43 | 2026-Q2
EXP-006238 | 2026-04-05 | BOQ-PKG-08-00268 | PKG-08 | INV-PKG-08-009-06238 | 108.38 | 107851.42 | 5392.57 | Under Review | 102458.85 | 2026-Q2
EXP-006281 | 2026-04-05 | BOQ-PKG-01-00311 | PKG-01 | INV-PKG-01-017-06281 | 388.74 | 65241.58 | 3262.08 | Disputed | 61979.5 | 2026-Q2
EXP-006978 | 2026-04-05 | BOQ-PKG-08-01008 | PKG-08 | INV-PKG-08-014-06978 | 437.38 | 32750.09 | 1637.5 | Approved Pending Payment | 31112.59 | 2026-Q2
EXP-001374 | 2026-04-06 | BOQ-PKG-04-01374 | PKG-04 | INV-PKG-04-010-01374 | 266.4 | 196456.15 | 9822.81 | Paid | 186633.34 | 2026-Q2
EXP-001383 | 2026-04-06 | BOQ-PKG-03-01383 | PKG-03 | INV-PKG-03-019-01383 | 45.89 | 177780.59 | 8889.03 | Paid | 168891.56 | 2026-Q2
EXP-002400 | 2026-04-06 | BOQ-PKG-10-00410 | PKG-10 | INV-PKG-10-021-02400 | 212.86 | 175296.39 | 8764.82 | Paid | 166531.57 | 2026-Q2
EXP-004343 | 2026-04-06 | BOQ-PKG-03-00363 | PKG-03 | INV-PKG-03-004-04343 | 226.77 | 204132.57 | 10206.63 | Paid | 193925.94 | 2026-Q2
EXP-004591 | 2026-04-06 | BOQ-PKG-01-00611 | PKG-01 | INV-PKG-01-007-04591 | 15.19 | 124887.97 | 6244.4 | Paid | 118643.57 | 2026-Q2
EXP-005519 | 2026-04-06 | BOQ-PKG-09-01539 | PKG-09 | INV-PKG-09-025-05519 | 230.18 | 196768.31 | 9838.42 | Disputed | 186929.89 | 2026-Q2
EXP-006509 | 2026-04-06 | BOQ-PKG-09-00539 | PKG-09 | INV-PKG-09-035-06509 | 19.28 | 202694.78 | 10134.74 | Paid | 192560.04 | 2026-Q2
EXP-000770 | 2026-04-07 | BOQ-PKG-10-00770 | PKG-10 | INV-PKG-10-001-00770 | 425.12 | 87074.85 | 4353.74 | Paid | 82721.11 | 2026-Q2
EXP-001547 | 2026-04-07 | BOQ-PKG-07-01547 | PKG-07 | INV-PKG-07-008-01547 | 57.27 | 151597.58 | 7579.88 | Paid | 144017.7 | 2026-Q2
EXP-001903 | 2026-04-07 | BOQ-PKG-03-01903 | PKG-03 | INV-PKG-03-014-01903 | 79.5 | 73202.1 | 3660.11 | Paid | 69541.99 | 2026-Q2
EXP-002441 | 2026-04-07 | BOQ-PKG-01-00451 | PKG-01 | INV-PKG-01-027-02441 | 409.76 | 106039.3 | 5301.96 | Paid | 100737.34 | 2026-Q2
EXP-002559 | 2026-04-07 | BOQ-PKG-09-00569 | PKG-09 | INV-PKG-09-005-02559 | 403.08 | 147625.21 | 7381.26 | Paid | 140243.95 | 2026-Q2
EXP-003276 | 2026-04-07 | BOQ-PKG-06-01286 | PKG-06 | INV-PKG-06-022-03276 | 209.87 | 177181.62 | 8859.08 | Paid | 168322.54 | 2026-Q2
EXP-003938 | 2026-04-07 | BOQ-PKG-08-01948 | PKG-08 | INV-PKG-08-019-03938 | 235.01 | 64639.58 | 3231.98 | Paid | 61407.6 | 2026-Q2
EXP-004452 | 2026-04-07 | BOQ-PKG-02-00472 | PKG-02 | INV-PKG-02-008-04452 | 9.87 | 183012.55 | 9150.63 | Approved Pending Payment | 173861.92 | 2026-Q2
EXP-006231 | 2026-04-07 | BOQ-PKG-01-00261 | PKG-01 | INV-PKG-01-002-06231 | 347.61 | 138589.48 | 6929.47 | Paid | 131660.01 | 2026-Q2
EXP-000129 | 2026-04-08 | BOQ-PKG-09-00129 | PKG-09 | INV-PKG-09-025-00129 | 345.27 | 52092.49 | 2604.62 | Under Review | 49487.87 | 2026-Q2
EXP-001204 | 2026-04-08 | BOQ-PKG-04-01204 | PKG-04 | INV-PKG-04-015-01204 | 404.39 | 199088.15 | 9954.41 | Paid | 189133.74 | 2026-Q2
EXP-003731 | 2026-04-08 | BOQ-PKG-01-01741 | PKG-01 | INV-PKG-01-022-03731 | 368.37 | 215051.71 | 10752.59 | Paid | 204299.12 | 2026-Q2
EXP-005856 | 2026-04-08 | BOQ-PKG-06-01876 | PKG-06 | INV-PKG-06-012-05856 | 444.9 | 89449.65 | 4472.48 | Paid | 84977.17 | 2026-Q2
EXP-006812 | 2026-04-08 | BOQ-PKG-02-00842 | PKG-02 | INV-PKG-02-023-06812 | 401.99 | 172854.03 | 8642.7 | Approved Pending Payment | 164211.33 | 2026-Q2
EXP-006909 | 2026-04-08 | BOQ-PKG-09-00939 | PKG-09 | INV-PKG-09-015-06909 | 261.9 | 34477.4 | 1723.87 | Paid | 32753.53 | 2026-Q2
EXP-006968 | 2026-04-08 | BOQ-PKG-08-00998 | PKG-08 | INV-PKG-08-004-06968 | 297.6 | 180941.09 | 9047.05 | Paid | 171894.04 | 2026-Q2
EXP-000540 | 2026-04-09 | BOQ-PKG-10-00540 | PKG-10 | INV-PKG-10-016-00540 | 287.03 | 71521.77 | 3576.09 | Paid | 67945.68 | 2026-Q2
EXP-001396 | 2026-04-09 | BOQ-PKG-06-01396 | PKG-06 | INV-PKG-06-032-01396 | 184.59 | 155776.85 | 7788.84 | Approved Pending Payment | 147988.01 | 2026-Q2
EXP-001537 | 2026-04-09 | BOQ-PKG-07-01537 | PKG-07 | INV-PKG-07-033-01537 | 449.38 | 144770.58 | 7238.53 | Approved Pending Payment | 137532.05 | 2026-Q2
EXP-003214 | 2026-04-09 | BOQ-PKG-04-01224 | PKG-04 | INV-PKG-04-030-03214 | 144.6 | 60555.73 | 3027.79 | Under Review | 57527.94 | 2026-Q2
EXP-003945 | 2026-04-09 | BOQ-PKG-05-01955 | PKG-05 | INV-PKG-05-026-03945 | 138.96 | 196210.25 | 9810.51 | Under Review | 186399.74 | 2026-Q2
EXP-005564 | 2026-04-09 | BOQ-PKG-04-01584 | PKG-04 | INV-PKG-04-035-05564 | 393.45 | 107346.31 | 5367.32 | Under Review | 101978.99 | 2026-Q2
EXP-000856 | 2026-04-10 | BOQ-PKG-06-00856 | PKG-06 | INV-PKG-06-017-00856 | 117.06 | 208952.6 | 10447.63 | Approved Pending Payment | 198504.97 | 2026-Q2
EXP-001173 | 2026-04-10 | BOQ-PKG-03-01173 | PKG-03 | INV-PKG-03-019-01173 | 446.26 | 80136.71 | 4006.84 | Paid | 76129.87 | 2026-Q2
EXP-002159 | 2026-04-10 | BOQ-PKG-09-00169 | PKG-09 | INV-PKG-09-025-02159 | 391.47 | 112205.06 | 5610.25 | Approved Pending Payment | 106594.81 | 2026-Q2
EXP-003295 | 2026-04-10 | BOQ-PKG-05-01305 | PKG-05 | INV-PKG-05-006-03295 | 436.1 | 147392.3 | 7369.62 | Paid | 140022.68 | 2026-Q2
EXP-005599 | 2026-04-10 | BOQ-PKG-09-01619 | PKG-09 | INV-PKG-09-035-05599 | 50.15 | 43110.84 | 2155.54 | Paid | 40955.3 | 2026-Q2
EXP-005892 | 2026-04-10 | BOQ-PKG-02-01912 | PKG-02 | INV-PKG-02-013-05892 | 171.79 | 212270.96 | 10613.55 | Paid | 201657.41 | 2026-Q2
EXP-006800 | 2026-04-10 | BOQ-PKG-10-00830 | PKG-10 | INV-PKG-10-011-06800 | 317.63 | 142243.42 | 7112.17 | Paid | 135131.25 | 2026-Q2
EXP-000729 | 2026-04-11 | BOQ-PKG-09-00729 | PKG-09 | INV-PKG-09-030-00729 | 256.81 | 54091.13 | 2704.56 | Paid | 51386.57 | 2026-Q2
EXP-001128 | 2026-04-11 | BOQ-PKG-08-01128 | PKG-08 | INV-PKG-08-009-01128 | 311.11 | 202682.83 | 10134.14 | Paid | 192548.69 | 2026-Q2
EXP-001600 | 2026-04-11 | BOQ-PKG-10-01600 | PKG-10 | INV-PKG-10-026-01600 | 204.16 | 194665.76 | 9733.29 | Paid | 184932.47 | 2026-Q2
EXP-002449 | 2026-04-11 | BOQ-PKG-09-00459 | PKG-09 | INV-PKG-09-035-02449 | 165.04 | 84710.86 | 4235.54 | Paid | 80475.32 | 2026-Q2
EXP-002773 | 2026-04-11 | BOQ-PKG-03-00783 | PKG-03 | INV-PKG-03-009-02773 | 9.26 | 201841.26 | 10092.06 | Disputed | 191749.2 | 2026-Q2
EXP-003794 | 2026-04-11 | BOQ-PKG-04-01804 | PKG-04 | INV-PKG-04-015-03794 | 287.08 | 63313.14 | 3165.66 | Approved Pending Payment | 60147.48 | 2026-Q2
EXP-005126 | 2026-04-11 | BOQ-PKG-06-01146 | PKG-06 | INV-PKG-06-017-05126 | 188.76 | 139758.78 | 6987.94 | Approved Pending Payment | 132770.84 | 2026-Q2
EXP-006764 | 2026-04-11 | BOQ-PKG-04-00794 | PKG-04 | INV-PKG-04-010-06764 | 73.16 | 70828.14 | 3541.41 | Paid | 67286.73 | 2026-Q2
EXP-000109 | 2026-04-12 | BOQ-PKG-09-00109 | PKG-09 | INV-PKG-09-005-00109 | 261.82 | 191679.14 | 9583.96 | Approved Pending Payment | 182095.18 | 2026-Q2
EXP-001910 | 2026-04-12 | BOQ-PKG-10-01910 | PKG-10 | INV-PKG-10-021-01910 | 374.85 | 76884.75 | 3844.24 | Paid | 73040.51 | 2026-Q2
EXP-002176 | 2026-04-12 | BOQ-PKG-06-00186 | PKG-06 | INV-PKG-06-007-02176 | 229.3 | 152590.48 | 7629.52 | Approved Pending Payment | 144960.96 | 2026-Q2
EXP-005630 | 2026-04-12 | BOQ-PKG-10-01650 | PKG-10 | INV-PKG-10-031-05630 | 102.08 | 43552.77 | 2177.64 | Paid | 41375.13 | 2026-Q2
EXP-005782 | 2026-04-12 | BOQ-PKG-02-01802 | PKG-02 | INV-PKG-02-008-05782 | 295.15 | 46491.23 | 2324.56 | Paid | 44166.67 | 2026-Q2
EXP-005876 | 2026-04-12 | BOQ-PKG-06-01896 | PKG-06 | INV-PKG-06-032-05876 | 33.28 | 137565.75 | 6878.29 | Paid | 130687.46 | 2026-Q2
EXP-006480 | 2026-04-12 | BOQ-PKG-10-00510 | PKG-10 | INV-PKG-10-006-06480 | 269.41 | 90418.51 | 4520.93 | Paid | 85897.58 | 2026-Q2
EXP-006627 | 2026-04-12 | BOQ-PKG-07-00657 | PKG-07 | INV-PKG-07-013-06627 | 35.55 | 75292.26 | 3764.61 | Paid | 71527.65 | 2026-Q2
EXP-000823 | 2026-04-13 | BOQ-PKG-03-00823 | PKG-03 | INV-PKG-03-019-00823 | 202.28 | 138297.25 | 6914.86 | Paid | 131382.39 | 2026-Q2
EXP-002293 | 2026-04-13 | BOQ-PKG-03-00303 | PKG-03 | INV-PKG-03-019-02293 | 75.15 | 120871.26 | 6043.56 | Paid | 114827.7 | 2026-Q2
EXP-003262 | 2026-04-13 | BOQ-PKG-02-01272 | PKG-02 | INV-PKG-02-008-03262 | 402.72 | 71313.57 | 3565.68 | Approved Pending Payment | 67747.89 | 2026-Q2
EXP-005710 | 2026-04-13 | BOQ-PKG-10-01730 | PKG-10 | INV-PKG-10-006-05710 | 267.11 | 109031.71 | 5451.59 | Paid | 103580.12 | 2026-Q2
EXP-006618 | 2026-04-13 | BOQ-PKG-08-00648 | PKG-08 | INV-PKG-08-004-06618 | 83.04 | 58425.15 | 2921.26 | Paid | 55503.89 | 2026-Q2
EXP-000994 | 2026-04-14 | BOQ-PKG-04-00994 | PKG-04 | INV-PKG-04-015-00994 | 352.78 | 193793.1 | 9689.66 | Paid | 184103.44 | 2026-Q2
EXP-001391 | 2026-04-14 | BOQ-PKG-01-01391 | PKG-01 | INV-PKG-01-027-01391 | 170.33 | 64296.13 | 3214.81 | Paid | 61081.32 | 2026-Q2
EXP-003863 | 2026-04-14 | BOQ-PKG-03-01873 | PKG-03 | INV-PKG-03-014-03863 | 119.11 | 134051.6 | 6702.58 | Under Review | 127349.02 | 2026-Q2
EXP-005809 | 2026-04-14 | BOQ-PKG-09-01829 | PKG-09 | INV-PKG-09-035-05809 | 160.01 | 139326 | 6966.3 | Paid | 132359.7 | 2026-Q2
EXP-006099 | 2026-04-14 | BOQ-PKG-09-00129 | PKG-09 | INV-PKG-09-010-06099 | 278.61 | 67786.66 | 3389.33 | Paid | 64397.33 | 2026-Q2
EXP-004605 | 2026-04-15 | BOQ-PKG-05-00625 | PKG-05 | INV-PKG-05-021-04605 | 16.7 | 191079.68 | 9553.98 | Paid | 181525.7 | 2026-Q2
EXP-004853 | 2026-04-15 | BOQ-PKG-03-00873 | PKG-03 | INV-PKG-03-024-04853 | 38.01 | 92692.36 | 4634.62 | Disputed | 88057.74 | 2026-Q2
EXP-005597 | 2026-04-15 | BOQ-PKG-07-01617 | PKG-07 | INV-PKG-07-033-05597 | 375.27 | 164214.88 | 8210.74 | Approved Pending Payment | 156004.14 | 2026-Q2
EXP-005940 | 2026-04-15 | BOQ-PKG-10-01960 | PKG-10 | INV-PKG-10-026-05940 | 405.7 | 115509.26 | 5775.46 | Paid | 109733.8 | 2026-Q2
EXP-000013 | 2026-04-16 | BOQ-PKG-03-00013 | PKG-03 | INV-PKG-03-014-00013 | 133.8 | 112299.9 | 5615 | Paid | 106684.9 | 2026-Q2
EXP-000156 | 2026-04-16 | BOQ-PKG-06-00156 | PKG-06 | INV-PKG-06-017-00156 | 9.41 | 168688.04 | 8434.4 | Disputed | 160253.64 | 2026-Q2
EXP-000608 | 2026-04-16 | BOQ-PKG-08-00608 | PKG-08 | INV-PKG-08-014-00608 | 112.4 | 38167.03 | 1908.35 | Approved Pending Payment | 36258.68 | 2026-Q2
EXP-001206 | 2026-04-16 | BOQ-PKG-06-01206 | PKG-06 | INV-PKG-06-017-01206 | 19.29 | 147124.8 | 7356.24 | Approved Pending Payment | 139768.56 | 2026-Q2
EXP-002249 | 2026-04-16 | BOQ-PKG-09-00259 | PKG-09 | INV-PKG-09-010-02249 | 422.8 | 216819.43 | 10840.97 | Paid | 205978.46 | 2026-Q2
EXP-002606 | 2026-04-16 | BOQ-PKG-06-00616 | PKG-06 | INV-PKG-06-017-02606 | 200.09 | 98325.84 | 4916.29 | Paid | 93409.55 | 2026-Q2
EXP-003001 | 2026-04-16 | BOQ-PKG-01-01011 | PKG-01 | INV-PKG-01-027-03001 | 370.98 | 46476.09 | 2323.8 | Paid | 44152.29 | 2026-Q2
EXP-004363 | 2026-04-16 | BOQ-PKG-03-00383 | PKG-03 | INV-PKG-03-024-04363 | 226.5 | 93477.36 | 4673.87 | Paid | 88803.49 | 2026-Q2
EXP-005148 | 2026-04-16 | BOQ-PKG-08-01168 | PKG-08 | INV-PKG-08-004-05148 | 38.32 | 49966.46 | 2498.32 | Paid | 47468.14 | 2026-Q2
EXP-005233 | 2026-04-16 | BOQ-PKG-03-01253 | PKG-03 | INV-PKG-03-019-05233 | 428.09 | 84010.28 | 4200.51 | Paid | 79809.77 | 2026-Q2
EXP-003512 | 2026-04-17 | BOQ-PKG-02-01522 | PKG-02 | INV-PKG-02-013-03512 | 247.19 | 31142.87 | 1557.14 | Approved Pending Payment | 29585.73 | 2026-Q2
EXP-003900 | 2026-04-17 | BOQ-PKG-10-01910 | PKG-10 | INV-PKG-10-016-03900 | 143.06 | 38600.01 | 1930 | Approved Pending Payment | 36670.01 | 2026-Q2
EXP-006225 | 2026-04-17 | BOQ-PKG-05-00255 | PKG-05 | INV-PKG-05-031-06225 | 59.99 | 94521.56 | 4726.08 | Under Review | 89795.48 | 2026-Q2
EXP-006337 | 2026-04-17 | BOQ-PKG-07-00367 | PKG-07 | INV-PKG-07-003-06337 | 153.44 | 71453.39 | 3572.67 | Paid | 67880.72 | 2026-Q2
EXP-003139 | 2026-04-18 | BOQ-PKG-09-01149 | PKG-09 | INV-PKG-09-025-03139 | 304.88 | 149087.35 | 7454.37 | Paid | 141632.98 | 2026-Q2
EXP-003353 | 2026-04-18 | BOQ-PKG-03-01363 | PKG-03 | INV-PKG-03-029-03353 | 271.5 | 172485.45 | 8624.27 | Paid | 163861.18 | 2026-Q2
EXP-006632 | 2026-04-18 | BOQ-PKG-02-00662 | PKG-02 | INV-PKG-02-018-06632 | 243.31 | 131069.54 | 6553.48 | Approved Pending Payment | 124516.06 | 2026-Q2
EXP-001976 | 2026-04-19 | BOQ-PKG-06-01976 | PKG-06 | INV-PKG-06-017-01976 | 37.16 | 187832.95 | 9391.65 | Paid | 178441.3 | 2026-Q2
EXP-003200 | 2026-04-19 | BOQ-PKG-10-01210 | PKG-10 | INV-PKG-10-016-03200 | 13.97 | 67174.33 | 3358.72 | Paid | 63815.61 | 2026-Q2
EXP-005057 | 2026-04-19 | BOQ-PKG-07-01077 | PKG-07 | INV-PKG-07-018-05057 | 49.87 | 65963.92 | 3298.2 | Paid | 62665.72 | 2026-Q2
EXP-000527 | 2026-04-20 | BOQ-PKG-07-00527 | PKG-07 | INV-PKG-07-003-00527 | 345.02 | 67657.4 | 3382.87 | Paid | 64274.53 | 2026-Q2
EXP-002103 | 2026-04-20 | BOQ-PKG-03-00113 | PKG-03 | INV-PKG-03-004-02103 | 337.09 | 62660.62 | 3133.03 | Paid | 59527.59 | 2026-Q2
EXP-002215 | 2026-04-20 | BOQ-PKG-05-00225 | PKG-05 | INV-PKG-05-011-02215 | 350.26 | 40830.65 | 2041.53 | Paid | 38789.12 | 2026-Q2
EXP-002974 | 2026-04-20 | BOQ-PKG-04-00984 | PKG-04 | INV-PKG-04-035-02974 | 350.27 | 146932.21 | 7346.61 | Paid | 139585.6 | 2026-Q2
EXP-003713 | 2026-04-20 | BOQ-PKG-03-01723 | PKG-03 | INV-PKG-03-004-03713 | 102.29 | 112074.14 | 5603.71 | Approved Pending Payment | 106470.43 | 2026-Q2
EXP-003913 | 2026-04-20 | BOQ-PKG-03-01923 | PKG-03 | INV-PKG-03-029-03913 | 304.16 | 94955.09 | 4747.75 | Under Review | 90207.34 | 2026-Q2
EXP-005671 | 2026-04-20 | BOQ-PKG-01-01691 | PKG-01 | INV-PKG-01-002-05671 | 391.1 | 129917.26 | 6495.86 | Approved Pending Payment | 123421.4 | 2026-Q2
EXP-000849 | 2026-04-21 | BOQ-PKG-09-00849 | PKG-09 | INV-PKG-09-010-00849 | 90.7 | 43477.93 | 2173.9 | Paid | 41304.03 | 2026-Q2
EXP-001562 | 2026-04-21 | BOQ-PKG-02-01562 | PKG-02 | INV-PKG-02-023-01562 | 392.2 | 131306.77 | 6565.34 | Paid | 124741.43 | 2026-Q2
EXP-001590 | 2026-04-21 | BOQ-PKG-10-01590 | PKG-10 | INV-PKG-10-016-01590 | 6.84 | 27788.61 | 1389.43 | Paid | 26399.18 | 2026-Q2
EXP-001789 | 2026-04-21 | BOQ-PKG-09-01789 | PKG-09 | INV-PKG-09-005-01789 | 99.99 | 107114.43 | 5355.72 | Paid | 101758.71 | 2026-Q2
EXP-004158 | 2026-04-21 | BOQ-PKG-08-00178 | PKG-08 | INV-PKG-08-029-04158 | 86.26 | 150342.73 | 7517.14 | Disputed | 142825.59 | 2026-Q2
EXP-004499 | 2026-04-21 | BOQ-PKG-09-00519 | PKG-09 | INV-PKG-09-020-04499 | 290.64 | 95672.07 | 4783.6 | Approved Pending Payment | 90888.47 | 2026-Q2
EXP-006302 | 2026-04-21 | BOQ-PKG-02-00332 | PKG-02 | INV-PKG-02-003-06302 | 53.59 | 65009.38 | 3250.47 | Paid | 61758.91 | 2026-Q2
EXP-006354 | 2026-04-21 | BOQ-PKG-04-00384 | PKG-04 | INV-PKG-04-020-06354 | 131.71 | 114904.68 | 5745.23 | Paid | 109159.45 | 2026-Q2
EXP-001024 | 2026-04-22 | BOQ-PKG-04-01024 | PKG-04 | INV-PKG-04-010-01024 | 133.58 | 41410.54 | 2070.53 | Paid | 39340.01 | 2026-Q2
EXP-001564 | 2026-04-22 | BOQ-PKG-04-01564 | PKG-04 | INV-PKG-04-025-01564 | 105.14 | 109710.17 | 5485.51 | Paid | 104224.66 | 2026-Q2
EXP-002829 | 2026-04-22 | BOQ-PKG-09-00839 | PKG-09 | INV-PKG-09-030-02829 | 437.82 | 167858.54 | 8392.93 | Paid | 159465.61 | 2026-Q2
EXP-003350 | 2026-04-22 | BOQ-PKG-10-01360 | PKG-10 | INV-PKG-10-026-03350 | 339.73 | 69805.29 | 3490.26 | Paid | 66315.03 | 2026-Q2
EXP-005792 | 2026-04-22 | BOQ-PKG-02-01812 | PKG-02 | INV-PKG-02-018-05792 | 233.99 | 185248.97 | 9262.45 | Paid | 175986.52 | 2026-Q2
EXP-005862 | 2026-04-22 | BOQ-PKG-02-01882 | PKG-02 | INV-PKG-02-018-05862 | 315.48 | 53745.81 | 2687.29 | Paid | 51058.52 | 2026-Q2
EXP-006328 | 2026-04-22 | BOQ-PKG-08-00358 | PKG-08 | INV-PKG-08-029-06328 | 142.28 | 72277.7 | 3613.88 | Paid | 68663.82 | 2026-Q2
EXP-006446 | 2026-04-22 | BOQ-PKG-06-00476 | PKG-06 | INV-PKG-06-007-06446 | 130.9 | 69766.21 | 3488.31 | Paid | 66277.9 | 2026-Q2
EXP-000843 | 2026-04-23 | BOQ-PKG-03-00843 | PKG-03 | INV-PKG-03-004-00843 | 180.77 | 84504.77 | 4225.24 | Paid | 80279.53 | 2026-Q2
EXP-004896 | 2026-04-23 | BOQ-PKG-06-00916 | PKG-06 | INV-PKG-06-032-04896 | 43.28 | 29865.91 | 1493.3 | Paid | 28372.61 | 2026-Q2
EXP-005690 | 2026-04-23 | BOQ-PKG-10-01710 | PKG-10 | INV-PKG-10-021-05690 | 364.46 | 149614.19 | 7480.71 | Paid | 142133.48 | 2026-Q2
EXP-006460 | 2026-04-23 | BOQ-PKG-10-00490 | PKG-10 | INV-PKG-10-021-06460 | 132.9 | 42476.39 | 2123.82 | Under Review | 40352.57 | 2026-Q2
EXP-000093 | 2026-04-24 | BOQ-PKG-03-00093 | PKG-03 | INV-PKG-03-024-00093 | 374.63 | 65364.34 | 3268.22 | Paid | 62096.12 | 2026-Q2
EXP-002319 | 2026-04-24 | BOQ-PKG-09-00329 | PKG-09 | INV-PKG-09-010-02319 | 258.9 | 183456.77 | 9172.84 | Paid | 174283.93 | 2026-Q2
EXP-003741 | 2026-04-24 | BOQ-PKG-01-01751 | PKG-01 | INV-PKG-01-032-03741 | 74.12 | 174164.38 | 8708.22 | Paid | 165456.16 | 2026-Q2
EXP-005090 | 2026-04-24 | BOQ-PKG-10-01110 | PKG-10 | INV-PKG-10-016-05090 | 27.48 | 100625.77 | 5031.29 | Paid | 95594.48 | 2026-Q2
EXP-005122 | 2026-04-24 | BOQ-PKG-02-01142 | PKG-02 | INV-PKG-02-013-05122 | 138.65 | 80253.75 | 4012.69 | Disputed | 76241.06 | 2026-Q2
EXP-006095 | 2026-04-24 | BOQ-PKG-05-00125 | PKG-05 | INV-PKG-05-006-06095 | 38.35 | 124245.41 | 6212.27 | Paid | 118033.14 | 2026-Q2
EXP-006181 | 2026-04-24 | BOQ-PKG-01-00211 | PKG-01 | INV-PKG-01-022-06181 | 443.93 | 179596.93 | 8979.85 | Paid | 170617.08 | 2026-Q2
EXP-000562 | 2026-04-25 | BOQ-PKG-02-00562 | PKG-02 | INV-PKG-02-003-00562 | 422.73 | 179043.74 | 8952.19 | Paid | 170091.55 | 2026-Q2
EXP-000660 | 2026-04-25 | BOQ-PKG-10-00660 | PKG-10 | INV-PKG-10-031-00660 | 139.15 | 42434.14 | 2121.71 | Paid | 40312.43 | 2026-Q2
EXP-001620 | 2026-04-25 | BOQ-PKG-10-01620 | PKG-10 | INV-PKG-10-011-01620 | 89.26 | 121524.95 | 6076.25 | Approved Pending Payment | 115448.7 | 2026-Q2
EXP-002079 | 2026-04-25 | BOQ-PKG-09-00089 | PKG-09 | INV-PKG-09-015-02079 | 319.41 | 166233.98 | 8311.7 | Under Review | 157922.28 | 2026-Q2
EXP-004336 | 2026-04-25 | BOQ-PKG-06-00356 | PKG-06 | INV-PKG-06-032-04336 | 447.54 | 116811.4 | 5840.57 | Paid | 110970.83 | 2026-Q2
EXP-005033 | 2026-04-25 | BOQ-PKG-03-01053 | PKG-03 | INV-PKG-03-029-05033 | 298.91 | 180224.88 | 9011.24 | Paid | 171213.64 | 2026-Q2
EXP-005397 | 2026-04-25 | BOQ-PKG-07-01417 | PKG-07 | INV-PKG-07-008-05397 | 318.49 | 147013.28 | 7350.66 | Paid | 139662.62 | 2026-Q2
EXP-005947 | 2026-04-25 | BOQ-PKG-07-01967 | PKG-07 | INV-PKG-07-033-05947 | 332.77 | 57554.28 | 2877.71 | Paid | 54676.57 | 2026-Q2
EXP-006732 | 2026-04-25 | BOQ-PKG-02-00762 | PKG-02 | INV-PKG-02-013-06732 | 165.77 | 102783.06 | 5139.15 | Paid | 97643.91 | 2026-Q2
EXP-001082 | 2026-04-26 | BOQ-PKG-02-01082 | PKG-02 | INV-PKG-02-033-01082 | 411.06 | 73379.92 | 3669 | Paid | 69710.92 | 2026-Q2
EXP-001428 | 2026-04-26 | BOQ-PKG-08-01428 | PKG-08 | INV-PKG-08-029-01428 | 418.06 | 125110.79 | 6255.54 | Paid | 118855.25 | 2026-Q2
EXP-001938 | 2026-04-26 | BOQ-PKG-08-01938 | PKG-08 | INV-PKG-08-014-01938 | 202.49 | 79526.14 | 3976.31 | Under Review | 75549.83 | 2026-Q2
EXP-002040 | 2026-04-26 | BOQ-PKG-10-00050 | PKG-10 | INV-PKG-10-011-02040 | 147.13 | 129001.49 | 6450.07 | Paid | 122551.42 | 2026-Q2
EXP-002808 | 2026-04-26 | BOQ-PKG-08-00818 | PKG-08 | INV-PKG-08-009-02808 | 238.98 | 187446.75 | 9372.34 | Paid | 178074.41 | 2026-Q2
EXP-004979 | 2026-04-26 | BOQ-PKG-09-00999 | PKG-09 | INV-PKG-09-010-04979 | 279.44 | 131743.76 | 6587.19 | Approved Pending Payment | 125156.57 | 2026-Q2
EXP-005169 | 2026-04-26 | BOQ-PKG-09-01189 | PKG-09 | INV-PKG-09-025-05169 | 307.09 | 74666.36 | 3733.32 | Paid | 70933.04 | 2026-Q2
EXP-005384 | 2026-04-26 | BOQ-PKG-04-01404 | PKG-04 | INV-PKG-04-030-05384 | 357 | 27290.94 | 1364.55 | Approved Pending Payment | 25926.39 | 2026-Q2
EXP-006064 | 2026-04-26 | BOQ-PKG-04-00094 | PKG-04 | INV-PKG-04-010-06064 | 231.61 | 144923.68 | 7246.18 | Paid | 137677.5 | 2026-Q2
EXP-006779 | 2026-04-26 | BOQ-PKG-09-00809 | PKG-09 | INV-PKG-09-025-06779 | 182.42 | 147639.08 | 7381.95 | Paid | 140257.13 | 2026-Q2
EXP-001695 | 2026-04-27 | BOQ-PKG-05-01695 | PKG-05 | INV-PKG-05-016-01695 | 352.87 | 27481.26 | 1374.06 | Paid | 26107.2 | 2026-Q2
EXP-001746 | 2026-04-27 | BOQ-PKG-06-01746 | PKG-06 | INV-PKG-06-032-01746 | 85.53 | 172213.46 | 8610.67 | Paid | 163602.79 | 2026-Q2
EXP-002841 | 2026-04-27 | BOQ-PKG-01-00851 | PKG-01 | INV-PKG-01-007-02841 | 52.87 | 30320.73 | 1516.04 | Paid | 28804.69 | 2026-Q2
EXP-003204 | 2026-04-27 | BOQ-PKG-04-01214 | PKG-04 | INV-PKG-04-020-03204 | 25.83 | 80283.77 | 4014.19 | Paid | 76269.58 | 2026-Q2
EXP-005035 | 2026-04-27 | BOQ-PKG-05-01055 | PKG-05 | INV-PKG-05-031-05035 | 187.3 | 102330.05 | 5116.5 | Paid | 97213.55 | 2026-Q2
EXP-006646 | 2026-04-27 | BOQ-PKG-06-00676 | PKG-06 | INV-PKG-06-032-06646 | 319.96 | 167495.48 | 8374.77 | Paid | 159120.71 | 2026-Q2
EXP-000615 | 2026-04-28 | BOQ-PKG-05-00615 | PKG-05 | INV-PKG-05-021-00615 | 239.63 | 197305.21 | 9865.26 | Paid | 187439.95 | 2026-Q2
EXP-000797 | 2026-04-28 | BOQ-PKG-07-00797 | PKG-07 | INV-PKG-07-028-00797 | 145.15 | 47900.85 | 2395.04 | Paid | 45505.81 | 2026-Q2
EXP-000144 | 2026-04-29 | BOQ-PKG-04-00144 | PKG-04 | INV-PKG-04-005-00144 | 229.96 | 115378.75 | 5768.94 | Disputed | 109609.81 | 2026-Q2
EXP-000234 | 2026-04-29 | BOQ-PKG-04-00234 | PKG-04 | INV-PKG-04-025-00234 | 293.66 | 193694.37 | 9684.72 | Paid | 184009.65 | 2026-Q2
EXP-002131 | 2026-04-29 | BOQ-PKG-01-00141 | PKG-01 | INV-PKG-01-032-02131 | 351.75 | 60457.63 | 3022.88 | Paid | 57434.75 | 2026-Q2
EXP-002390 | 2026-04-29 | BOQ-PKG-10-00400 | PKG-10 | INV-PKG-10-011-02390 | 73.78 | 182316.16 | 9115.81 | Paid | 173200.35 | 2026-Q2
EXP-002507 | 2026-04-29 | BOQ-PKG-07-00517 | PKG-07 | INV-PKG-07-023-02507 | 200.94 | 140566.04 | 7028.3 | Under Review | 133537.74 | 2026-Q2
EXP-002767 | 2026-04-29 | BOQ-PKG-07-00777 | PKG-07 | INV-PKG-07-003-02767 | 77.3 | 35310.32 | 1765.52 | Paid | 33544.8 | 2026-Q2
EXP-003159 | 2026-04-29 | BOQ-PKG-09-01169 | PKG-09 | INV-PKG-09-010-03159 | 417.49 | 29589.62 | 1479.48 | Paid | 28110.14 | 2026-Q2
EXP-003708 | 2026-04-29 | BOQ-PKG-08-01718 | PKG-08 | INV-PKG-08-034-03708 | 159.71 | 166967.64 | 8348.38 | Approved Pending Payment | 158619.26 | 2026-Q2
EXP-003856 | 2026-04-29 | BOQ-PKG-06-01866 | PKG-06 | INV-PKG-06-007-03856 | 117.11 | 27290.5 | 1364.52 | Paid | 25925.98 | 2026-Q2
EXP-005887 | 2026-04-29 | BOQ-PKG-07-01907 | PKG-07 | INV-PKG-07-008-05887 | 298.85 | 62919.67 | 3145.98 | Paid | 59773.69 | 2026-Q2
EXP-006376 | 2026-04-29 | BOQ-PKG-06-00406 | PKG-06 | INV-PKG-06-007-06376 | 445.98 | 97436.84 | 4871.84 | Approved Pending Payment | 92565 | 2026-Q2
EXP-000787 | 2026-04-30 | BOQ-PKG-07-00787 | PKG-07 | INV-PKG-07-018-00787 | 188.75 | 119906.35 | 5995.32 | Paid | 113911.03 | 2026-Q2
EXP-001277 | 2026-04-30 | BOQ-PKG-07-01277 | PKG-07 | INV-PKG-07-018-01277 | 400.05 | 208584.71 | 10429.24 | Paid | 198155.47 | 2026-Q2
EXP-002018 | 2026-04-30 | BOQ-PKG-08-00028 | PKG-08 | INV-PKG-08-024-02018 | 434.04 | 86513.29 | 4325.66 | Paid | 82187.63 | 2026-Q2
EXP-003495 | 2026-04-30 | BOQ-PKG-05-01505 | PKG-05 | INV-PKG-05-031-03495 | 329.3 | 44514.2 | 2225.71 | Paid | 42288.49 | 2026-Q2
EXP-005535 | 2026-04-30 | BOQ-PKG-05-01555 | PKG-05 | INV-PKG-05-006-05535 | 58.86 | 123576.27 | 6178.81 | Paid | 117397.46 | 2026-Q2
EXP-006094 | 2026-04-30 | BOQ-PKG-04-00124 | PKG-04 | INV-PKG-04-005-06094 | 399.84 | 97302.71 | 4865.14 | Paid | 92437.57 | 2026-Q2
EXP-006950 | 2026-04-30 | BOQ-PKG-10-00980 | PKG-10 | INV-PKG-10-021-06950 | 26 | 32179.66 | 1608.98 | Paid | 30570.68 | 2026-Q2
EXP-000464 | 2026-05-01 | BOQ-PKG-04-00464 | PKG-04 | INV-PKG-04-010-00464 | 160.83 | 40177.22 | 2008.86 | Paid | 38168.36 | 2026-Q2
EXP-000521 | 2026-05-01 | BOQ-PKG-01-00521 | PKG-01 | INV-PKG-01-032-00521 | 424.15 | 156776.94 | 7838.85 | Paid | 148938.09 | 2026-Q2
EXP-001723 | 2026-05-01 | BOQ-PKG-03-01723 | PKG-03 | INV-PKG-03-009-01723 | 289.22 | 95758.36 | 4787.92 | Paid | 90970.44 | 2026-Q2
EXP-002210 | 2026-05-01 | BOQ-PKG-10-00220 | PKG-10 | INV-PKG-10-006-02210 | 140.37 | 145977.88 | 7298.89 | Paid | 138678.99 | 2026-Q2
EXP-002915 | 2026-05-01 | BOQ-PKG-05-00925 | PKG-05 | INV-PKG-05-011-02915 | 384.17 | 118391.49 | 5919.57 | Paid | 112471.92 | 2026-Q2
EXP-002918 | 2026-05-01 | BOQ-PKG-08-00928 | PKG-08 | INV-PKG-08-014-02918 | 338.58 | 167351.41 | 8367.57 | Paid | 158983.84 | 2026-Q2
EXP-003000 | 2026-05-01 | BOQ-PKG-10-01010 | PKG-10 | INV-PKG-10-026-03000 | 291.59 | 154331.42 | 7716.57 | Paid | 146614.85 | 2026-Q2
EXP-003058 | 2026-05-01 | BOQ-PKG-08-01068 | PKG-08 | INV-PKG-08-014-03058 | 19.35 | 166291.04 | 8314.55 | Approved Pending Payment | 157976.49 | 2026-Q2
EXP-003345 | 2026-05-01 | BOQ-PKG-05-01355 | PKG-05 | INV-PKG-05-021-03345 | 151.45 | 103100.65 | 5155.03 | Approved Pending Payment | 97945.62 | 2026-Q2
EXP-003371 | 2026-05-01 | BOQ-PKG-01-01381 | PKG-01 | INV-PKG-01-012-03371 | 243.67 | 212147.06 | 10607.35 | Paid | 201539.71 | 2026-Q2
EXP-003792 | 2026-05-01 | BOQ-PKG-02-01802 | PKG-02 | INV-PKG-02-013-03792 | 63.49 | 167675.33 | 8383.77 | Paid | 159291.56 | 2026-Q2
EXP-005254 | 2026-05-01 | BOQ-PKG-04-01274 | PKG-04 | INV-PKG-04-005-05254 | 403.21 | 75772.27 | 3788.61 | Paid | 71983.66 | 2026-Q2
EXP-005777 | 2026-05-01 | BOQ-PKG-07-01797 | PKG-07 | INV-PKG-07-003-05777 | 212.25 | 114914.41 | 5745.72 | Paid | 109168.69 | 2026-Q2
EXP-006564 | 2026-05-01 | BOQ-PKG-04-00594 | PKG-04 | INV-PKG-04-020-06564 | 194.61 | 116116.05 | 5805.8 | Paid | 110310.25 | 2026-Q2
EXP-002226 | 2026-05-02 | BOQ-PKG-06-00236 | PKG-06 | INV-PKG-06-022-02226 | 36.13 | 102854.07 | 5142.7 | Paid | 97711.37 | 2026-Q2
EXP-002348 | 2026-05-02 | BOQ-PKG-08-00358 | PKG-08 | INV-PKG-08-004-02348 | 13.78 | 163638.27 | 8181.91 | Approved Pending Payment | 155456.36 | 2026-Q2
EXP-002903 | 2026-05-02 | BOQ-PKG-03-00913 | PKG-03 | INV-PKG-03-034-02903 | 70.82 | 120220.44 | 6011.02 | Paid | 114209.42 | 2026-Q2
EXP-003082 | 2026-05-02 | BOQ-PKG-02-01092 | PKG-02 | INV-PKG-02-003-03082 | 203.01 | 117940.52 | 5897.03 | Paid | 112043.49 | 2026-Q2
EXP-004240 | 2026-05-02 | BOQ-PKG-10-00260 | PKG-10 | INV-PKG-10-006-04240 | 445.41 | 174389.06 | 8719.45 | Approved Pending Payment | 165669.61 | 2026-Q2
EXP-004937 | 2026-05-02 | BOQ-PKG-07-00957 | PKG-07 | INV-PKG-07-003-04937 | 50 | 186856.54 | 9342.83 | Paid | 177513.71 | 2026-Q2
EXP-005476 | 2026-05-02 | BOQ-PKG-06-01496 | PKG-06 | INV-PKG-06-017-05476 | 136.83 | 81479.37 | 4073.97 | Paid | 77405.4 | 2026-Q2
EXP-000182 | 2026-05-03 | BOQ-PKG-02-00182 | PKG-02 | INV-PKG-02-008-00182 | 157.6 | 145987.35 | 7299.37 | Paid | 138687.98 | 2026-Q2
EXP-002399 | 2026-05-03 | BOQ-PKG-09-00409 | PKG-09 | INV-PKG-09-020-02399 | 7.32 | 198434.19 | 9921.71 | Paid | 188512.48 | 2026-Q2
EXP-002428 | 2026-05-03 | BOQ-PKG-08-00438 | PKG-08 | INV-PKG-08-014-02428 | 421.99 | 86202.2 | 4310.11 | Paid | 81892.09 | 2026-Q2
EXP-002469 | 2026-05-03 | BOQ-PKG-09-00479 | PKG-09 | INV-PKG-09-020-02469 | 410.25 | 207298.67 | 10364.93 | Under Review | 196933.74 | 2026-Q2
EXP-003982 | 2026-05-03 | BOQ-PKG-02-00002 | PKG-02 | INV-PKG-02-028-03982 | 157.32 | 47652.93 | 2382.65 | Paid | 45270.28 | 2026-Q2
EXP-004230 | 2026-05-03 | BOQ-PKG-10-00250 | PKG-10 | INV-PKG-10-031-04230 | 414.78 | 98645.29 | 4932.26 | Paid | 93713.03 | 2026-Q2
EXP-005550 | 2026-05-03 | BOQ-PKG-10-01570 | PKG-10 | INV-PKG-10-021-05550 | 195.61 | 58131.53 | 2906.58 | Paid | 55224.95 | 2026-Q2
EXP-006255 | 2026-05-03 | BOQ-PKG-05-00285 | PKG-05 | INV-PKG-05-026-06255 | 12.04 | 35467.11 | 1773.36 | Paid | 33693.75 | 2026-Q2
EXP-006889 | 2026-05-03 | BOQ-PKG-09-00919 | PKG-09 | INV-PKG-09-030-06889 | 187.82 | 86629.93 | 4331.5 | Paid | 82298.43 | 2026-Q2
EXP-000187 | 2026-05-04 | BOQ-PKG-07-00187 | PKG-07 | INV-PKG-07-013-00187 | 251.53 | 120794.49 | 6039.72 | Paid | 114754.77 | 2026-Q2
EXP-002128 | 2026-05-04 | BOQ-PKG-08-00138 | PKG-08 | INV-PKG-08-029-02128 | 117.15 | 97170.77 | 4858.54 | Paid | 92312.23 | 2026-Q2
EXP-003322 | 2026-05-04 | BOQ-PKG-02-01332 | PKG-02 | INV-PKG-02-033-03322 | 158.62 | 96504.41 | 4825.22 | Paid | 91679.19 | 2026-Q2
EXP-004721 | 2026-05-04 | BOQ-PKG-01-00741 | PKG-01 | INV-PKG-01-032-04721 | 356.03 | 62482.71 | 3124.14 | Paid | 59358.57 | 2026-Q2
EXP-005895 | 2026-05-04 | BOQ-PKG-05-01915 | PKG-05 | INV-PKG-05-016-05895 | 389.64 | 71998.33 | 3599.92 | Paid | 68398.41 | 2026-Q2
EXP-006450 | 2026-05-04 | BOQ-PKG-10-00480 | PKG-10 | INV-PKG-10-011-06450 | 322.77 | 188945.59 | 9447.28 | Paid | 179498.31 | 2026-Q2
EXP-006598 | 2026-05-04 | BOQ-PKG-08-00628 | PKG-08 | INV-PKG-08-019-06598 | 332.84 | 133339.39 | 6666.97 | Paid | 126672.42 | 2026-Q2
EXP-001207 | 2026-05-05 | BOQ-PKG-07-01207 | PKG-07 | INV-PKG-07-018-01207 | 329.42 | 194586.75 | 9729.34 | Paid | 184857.41 | 2026-Q2
EXP-001785 | 2026-05-05 | BOQ-PKG-05-01785 | PKG-05 | INV-PKG-05-001-01785 | 125.81 | 32064.46 | 1603.22 | Under Review | 30461.24 | 2026-Q2
EXP-003995 | 2026-05-05 | BOQ-PKG-05-00015 | PKG-05 | INV-PKG-05-006-03995 | 355.81 | 110968.04 | 5548.4 | Paid | 105419.64 | 2026-Q2
EXP-000140 | 2026-05-06 | BOQ-PKG-10-00140 | PKG-10 | INV-PKG-10-001-00140 | 26 | 206301.08 | 10315.05 | Paid | 195986.03 | 2026-Q2
EXP-001019 | 2026-05-06 | BOQ-PKG-09-01019 | PKG-09 | INV-PKG-09-005-01019 | 339.5 | 103030.54 | 5151.53 | Paid | 97879.01 | 2026-Q2
EXP-001283 | 2026-05-06 | BOQ-PKG-03-01283 | PKG-03 | INV-PKG-03-024-01283 | 246.05 | 145142.68 | 7257.13 | Paid | 137885.55 | 2026-Q2
EXP-002070 | 2026-05-06 | BOQ-PKG-10-00080 | PKG-10 | INV-PKG-10-006-02070 | 187.83 | 91832.32 | 4591.62 | Paid | 87240.7 | 2026-Q2
EXP-002095 | 2026-05-06 | BOQ-PKG-05-00105 | PKG-05 | INV-PKG-05-031-02095 | 80.41 | 116438.07 | 5821.9 | Paid | 110616.17 | 2026-Q2
EXP-002277 | 2026-05-06 | BOQ-PKG-07-00287 | PKG-07 | INV-PKG-07-003-02277 | 26.91 | 47786.41 | 2389.32 | Approved Pending Payment | 45397.09 | 2026-Q2
EXP-002810 | 2026-05-06 | BOQ-PKG-10-00820 | PKG-10 | INV-PKG-10-011-02810 | 206.6 | 172527 | 8626.35 | Paid | 163900.65 | 2026-Q2
EXP-003600 | 2026-05-06 | BOQ-PKG-10-01610 | PKG-10 | INV-PKG-10-031-03600 | 94.16 | 72362.51 | 3618.13 | Paid | 68744.38 | 2026-Q2
EXP-001894 | 2026-05-07 | BOQ-PKG-04-01894 | PKG-04 | INV-PKG-04-005-01894 | 177.47 | 134941.31 | 6747.07 | Paid | 128194.24 | 2026-Q2
EXP-003390 | 2026-05-07 | BOQ-PKG-10-01400 | PKG-10 | INV-PKG-10-031-03390 | 185.29 | 29990.42 | 1499.52 | Paid | 28490.9 | 2026-Q2
EXP-004486 | 2026-05-07 | BOQ-PKG-06-00506 | PKG-06 | INV-PKG-06-007-04486 | 286.61 | 160072.86 | 8003.64 | Paid | 152069.22 | 2026-Q2
EXP-005289 | 2026-05-07 | BOQ-PKG-09-01309 | PKG-09 | INV-PKG-09-005-05289 | 101.72 | 44367.38 | 2218.37 | Approved Pending Payment | 42149.01 | 2026-Q2
EXP-006303 | 2026-05-07 | BOQ-PKG-03-00333 | PKG-03 | INV-PKG-03-004-06303 | 318.25 | 37535.81 | 1876.79 | Paid | 35659.02 | 2026-Q2
EXP-000486 | 2026-05-08 | BOQ-PKG-06-00486 | PKG-06 | INV-PKG-06-032-00486 | 151.44 | 82753.23 | 4137.66 | Under Review | 78615.57 | 2026-Q2
EXP-001029 | 2026-05-08 | BOQ-PKG-09-01029 | PKG-09 | INV-PKG-09-015-01029 | 213.19 | 151229.94 | 7561.5 | Paid | 143668.44 | 2026-Q2
EXP-001235 | 2026-05-08 | BOQ-PKG-05-01235 | PKG-05 | INV-PKG-05-011-01235 | 111.9 | 73588.12 | 3679.41 | Approved Pending Payment | 69908.71 | 2026-Q2
EXP-002099 | 2026-05-08 | BOQ-PKG-09-00109 | PKG-09 | INV-PKG-09-035-02099 | 447.05 | 41259.91 | 2063 | Paid | 39196.91 | 2026-Q2
EXP-002129 | 2026-05-08 | BOQ-PKG-09-00139 | PKG-09 | INV-PKG-09-030-02129 | 159.15 | 95724.67 | 4786.23 | Paid | 90938.44 | 2026-Q2
EXP-002281 | 2026-05-08 | BOQ-PKG-01-00291 | PKG-01 | INV-PKG-01-007-02281 | 148.38 | 27151.53 | 1357.58 | Under Review | 25793.95 | 2026-Q2
EXP-002904 | 2026-05-08 | BOQ-PKG-04-00914 | PKG-04 | INV-PKG-04-035-02904 | 445.36 | 44244.56 | 2212.23 | Paid | 42032.33 | 2026-Q2
EXP-002952 | 2026-05-08 | BOQ-PKG-02-00962 | PKG-02 | INV-PKG-02-013-02952 | 207.06 | 78167.96 | 3908.4 | Paid | 74259.56 | 2026-Q2
EXP-004394 | 2026-05-08 | BOQ-PKG-04-00414 | PKG-04 | INV-PKG-04-020-04394 | 332.29 | 185893.35 | 9294.67 | Paid | 176598.68 | 2026-Q2
EXP-004776 | 2026-05-08 | BOQ-PKG-06-00796 | PKG-06 | INV-PKG-06-017-04776 | 358.57 | 154549.94 | 7727.5 | Paid | 146822.44 | 2026-Q2
EXP-005724 | 2026-05-08 | BOQ-PKG-04-01744 | PKG-04 | INV-PKG-04-020-05724 | 435.69 | 149616.71 | 7480.84 | Paid | 142135.87 | 2026-Q2
EXP-006585 | 2026-05-08 | BOQ-PKG-05-00615 | PKG-05 | INV-PKG-05-006-06585 | 365.94 | 55197.76 | 2759.89 | Disputed | 52437.87 | 2026-Q2
EXP-006790 | 2026-05-08 | BOQ-PKG-10-00820 | PKG-10 | INV-PKG-10-001-06790 | 189.63 | 25621.66 | 1281.08 | Under Review | 24340.58 | 2026-Q2
EXP-002182 | 2026-05-09 | BOQ-PKG-02-00192 | PKG-02 | INV-PKG-02-013-02182 | 199.63 | 39334.79 | 1966.74 | Under Review | 37368.05 | 2026-Q2
EXP-002389 | 2026-05-09 | BOQ-PKG-09-00399 | PKG-09 | INV-PKG-09-010-02389 | 418.02 | 67989.93 | 3399.5 | Paid | 64590.43 | 2026-Q2
EXP-002971 | 2026-05-09 | BOQ-PKG-01-00981 | PKG-01 | INV-PKG-01-032-02971 | 243.25 | 77965.17 | 3898.26 | Paid | 74066.91 | 2026-Q2
EXP-003201 | 2026-05-09 | BOQ-PKG-01-01211 | PKG-01 | INV-PKG-01-017-03201 | 213.06 | 180117.84 | 9005.89 | Paid | 171111.95 | 2026-Q2
EXP-004070 | 2026-05-09 | BOQ-PKG-10-00090 | PKG-10 | INV-PKG-10-011-04070 | 317.65 | 35592.68 | 1779.63 | Paid | 33813.05 | 2026-Q2
EXP-005054 | 2026-05-09 | BOQ-PKG-04-01074 | PKG-04 | INV-PKG-04-015-05054 | 279.29 | 80006.2 | 4000.31 | Paid | 76005.89 | 2026-Q2
EXP-005648 | 2026-05-09 | BOQ-PKG-08-01668 | PKG-08 | INV-PKG-08-014-05648 | 45.24 | 158787.75 | 7939.39 | Paid | 150848.36 | 2026-Q2
EXP-000353 | 2026-05-10 | BOQ-PKG-03-00353 | PKG-03 | INV-PKG-03-004-00353 | 258.43 | 186262 | 9313.1 | Paid | 176948.9 | 2026-Q2
EXP-001664 | 2026-05-10 | BOQ-PKG-04-01664 | PKG-04 | INV-PKG-04-020-01664 | 223.53 | 131509.83 | 6575.49 | Paid | 124934.34 | 2026-Q2
EXP-002153 | 2026-05-10 | BOQ-PKG-03-00163 | PKG-03 | INV-PKG-03-019-02153 | 269.19 | 173418.77 | 8670.94 | Paid | 164747.83 | 2026-Q2
EXP-002845 | 2026-05-10 | BOQ-PKG-05-00855 | PKG-05 | INV-PKG-05-011-02845 | 282.05 | 214043.76 | 10702.19 | Paid | 203341.57 | 2026-Q2
EXP-003540 | 2026-05-10 | BOQ-PKG-10-01550 | PKG-10 | INV-PKG-10-006-03540 | 41.22 | 113389.09 | 5669.45 | Paid | 107719.64 | 2026-Q2
EXP-004388 | 2026-05-10 | BOQ-PKG-08-00408 | PKG-08 | INV-PKG-08-014-04388 | 268.93 | 129348.85 | 6467.44 | Paid | 122881.41 | 2026-Q2
EXP-004866 | 2026-05-10 | BOQ-PKG-06-00886 | PKG-06 | INV-PKG-06-002-04866 | 187.46 | 29403.11 | 1470.16 | Approved Pending Payment | 27932.95 | 2026-Q2
EXP-005239 | 2026-05-10 | BOQ-PKG-09-01259 | PKG-09 | INV-PKG-09-025-05239 | 423.9 | 115180.96 | 5759.05 | Paid | 109421.91 | 2026-Q2
EXP-005292 | 2026-05-10 | BOQ-PKG-02-01312 | PKG-02 | INV-PKG-02-008-05292 | 102.23 | 163606.44 | 8180.32 | Paid | 155426.12 | 2026-Q2
EXP-006750 | 2026-05-10 | BOQ-PKG-10-00780 | PKG-10 | INV-PKG-10-031-06750 | 332.92 | 55943.38 | 2797.17 | Disputed | 53146.21 | 2026-Q2
EXP-003118 | 2026-05-11 | BOQ-PKG-08-01128 | PKG-08 | INV-PKG-08-004-03118 | 168.88 | 153982.43 | 7699.12 | Paid | 146283.31 | 2026-Q2
EXP-003621 | 2026-05-11 | BOQ-PKG-01-01631 | PKG-01 | INV-PKG-01-017-03621 | 279.54 | 120716.76 | 6035.84 | Paid | 114680.92 | 2026-Q2
EXP-003714 | 2026-05-11 | BOQ-PKG-04-01724 | PKG-04 | INV-PKG-04-005-03714 | 423.49 | 108743.05 | 5437.15 | Paid | 103305.9 | 2026-Q2
EXP-003876 | 2026-05-11 | BOQ-PKG-06-01886 | PKG-06 | INV-PKG-06-027-03876 | 10.06 | 24866.69 | 1243.33 | Disputed | 23623.36 | 2026-Q2
EXP-003890 | 2026-05-11 | BOQ-PKG-10-01900 | PKG-10 | INV-PKG-10-006-03890 | 27.9 | 118601.15 | 5930.06 | Paid | 112671.09 | 2026-Q2
EXP-005364 | 2026-05-11 | BOQ-PKG-04-01384 | PKG-04 | INV-PKG-04-010-05364 | 77.54 | 158728.15 | 7936.41 | Approved Pending Payment | 150791.74 | 2026-Q2
EXP-005587 | 2026-05-11 | BOQ-PKG-07-01607 | PKG-07 | INV-PKG-07-023-05587 | 381.3 | 95534.31 | 4776.72 | Paid | 90757.59 | 2026-Q2
EXP-006415 | 2026-05-11 | BOQ-PKG-05-00445 | PKG-05 | INV-PKG-05-011-06415 | 265.45 | 157292.43 | 7864.62 | Paid | 149427.81 | 2026-Q2
EXP-006582 | 2026-05-11 | BOQ-PKG-02-00612 | PKG-02 | INV-PKG-02-003-06582 | 288.54 | 73592.6 | 3679.63 | Paid | 69912.97 | 2026-Q2
EXP-002061 | 2026-05-12 | BOQ-PKG-01-00071 | PKG-01 | INV-PKG-01-032-02061 | 288.26 | 154649.93 | 7732.5 | Paid | 146917.43 | 2026-Q2
EXP-004523 | 2026-05-12 | BOQ-PKG-03-00543 | PKG-03 | INV-PKG-03-009-04523 | 92.78 | 164421.76 | 8221.09 | Paid | 156200.67 | 2026-Q2
EXP-006650 | 2026-05-12 | BOQ-PKG-10-00680 | PKG-10 | INV-PKG-10-001-06650 | 178.57 | 181663.24 | 9083.16 | Under Review | 172580.08 | 2026-Q2
EXP-000718 | 2026-05-13 | BOQ-PKG-08-00718 | PKG-08 | INV-PKG-08-019-00718 | 414.34 | 35095.78 | 1754.79 | Paid | 33340.99 | 2026-Q2
EXP-001965 | 2026-05-13 | BOQ-PKG-05-01965 | PKG-05 | INV-PKG-05-006-01965 | 10.17 | 203860.11 | 10193.01 | Approved Pending Payment | 193667.1 | 2026-Q2
EXP-003361 | 2026-05-13 | BOQ-PKG-01-01371 | PKG-01 | INV-PKG-01-002-03361 | 30.63 | 56612.22 | 2830.61 | Paid | 53781.61 | 2026-Q2
EXP-003935 | 2026-05-13 | BOQ-PKG-05-01945 | PKG-05 | INV-PKG-05-016-03935 | 85.68 | 110344.55 | 5517.23 | Paid | 104827.32 | 2026-Q2
EXP-004348 | 2026-05-13 | BOQ-PKG-08-00368 | PKG-08 | INV-PKG-08-009-04348 | 96.68 | 100145.91 | 5007.3 | Approved Pending Payment | 95138.61 | 2026-Q2
EXP-006098 | 2026-05-13 | BOQ-PKG-08-00128 | PKG-08 | INV-PKG-08-009-06098 | 311.87 | 168874.28 | 8443.71 | Paid | 160430.57 | 2026-Q2
EXP-006112 | 2026-05-13 | BOQ-PKG-02-00142 | PKG-02 | INV-PKG-02-023-06112 | 49.57 | 137311.37 | 6865.57 | Approved Pending Payment | 130445.8 | 2026-Q2
EXP-000286 | 2026-05-14 | BOQ-PKG-06-00286 | PKG-06 | INV-PKG-06-007-00286 | 435.15 | 105236.61 | 5261.83 | Paid | 99974.78 | 2026-Q2
EXP-001458 | 2026-05-14 | BOQ-PKG-08-01458 | PKG-08 | INV-PKG-08-024-01458 | 305.02 | 64219.13 | 3210.96 | Paid | 61008.17 | 2026-Q2
EXP-002712 | 2026-05-14 | BOQ-PKG-02-00722 | PKG-02 | INV-PKG-02-018-02712 | 66.58 | 189073.76 | 9453.69 | Paid | 179620.07 | 2026-Q2
EXP-003083 | 2026-05-14 | BOQ-PKG-03-01093 | PKG-03 | INV-PKG-03-004-03083 | 355.72 | 47972.37 | 2398.62 | Disputed | 45573.75 | 2026-Q2
EXP-003109 | 2026-05-14 | BOQ-PKG-09-01119 | PKG-09 | INV-PKG-09-030-03109 | 309.98 | 100044.69 | 5002.23 | Approved Pending Payment | 95042.46 | 2026-Q2
EXP-003202 | 2026-05-14 | BOQ-PKG-02-01212 | PKG-02 | INV-PKG-02-018-03202 | 194.49 | 167860.94 | 8393.05 | Under Review | 159467.89 | 2026-Q2
EXP-003355 | 2026-05-14 | BOQ-PKG-05-01365 | PKG-05 | INV-PKG-05-031-03355 | 254.17 | 79983.09 | 3999.15 | Paid | 75983.94 | 2026-Q2
EXP-003524 | 2026-05-14 | BOQ-PKG-04-01534 | PKG-04 | INV-PKG-04-025-03524 | 383.41 | 214761.13 | 10738.06 | Approved Pending Payment | 204023.07 | 2026-Q2
EXP-003744 | 2026-05-14 | BOQ-PKG-04-01754 | PKG-04 | INV-PKG-04-035-03744 | 38.95 | 195964.21 | 9798.21 | Under Review | 186166 | 2026-Q2
EXP-003951 | 2026-05-14 | BOQ-PKG-01-01961 | PKG-01 | INV-PKG-01-032-03951 | 149.38 | 96846.05 | 4842.3 | Approved Pending Payment | 92003.75 | 2026-Q2
EXP-004355 | 2026-05-14 | BOQ-PKG-05-00375 | PKG-05 | INV-PKG-05-016-04355 | 252.78 | 193646.95 | 9682.35 | Approved Pending Payment | 183964.6 | 2026-Q2
EXP-004462 | 2026-05-14 | BOQ-PKG-02-00482 | PKG-02 | INV-PKG-02-018-04462 | 152.85 | 129281.43 | 6464.07 | Approved Pending Payment | 122817.36 | 2026-Q2
EXP-005410 | 2026-05-14 | BOQ-PKG-10-01430 | PKG-10 | INV-PKG-10-021-05410 | 32.97 | 184915.73 | 9245.79 | Under Review | 175669.94 | 2026-Q2
EXP-005496 | 2026-05-14 | BOQ-PKG-06-01516 | PKG-06 | INV-PKG-06-002-05496 | 84.02 | 125906.62 | 6295.33 | Paid | 119611.29 | 2026-Q2
EXP-005523 | 2026-05-14 | BOQ-PKG-03-01543 | PKG-03 | INV-PKG-03-029-05523 | 339.17 | 163558.51 | 8177.93 | Under Review | 155380.58 | 2026-Q2
EXP-000584 | 2026-05-15 | BOQ-PKG-04-00584 | PKG-04 | INV-PKG-04-025-00584 | 363.98 | 24273.17 | 1213.66 | Paid | 23059.51 | 2026-Q2
EXP-000692 | 2026-05-15 | BOQ-PKG-02-00692 | PKG-02 | INV-PKG-02-028-00692 | 98.76 | 65274.26 | 3263.71 | Paid | 62010.55 | 2026-Q2
EXP-000963 | 2026-05-15 | BOQ-PKG-03-00963 | PKG-03 | INV-PKG-03-019-00963 | 30.72 | 51051.04 | 2552.55 | Paid | 48498.49 | 2026-Q2
EXP-002161 | 2026-05-15 | BOQ-PKG-01-00171 | PKG-01 | INV-PKG-01-027-02161 | 430.52 | 189342.68 | 9467.13 | Paid | 179875.55 | 2026-Q2
EXP-002486 | 2026-05-15 | BOQ-PKG-06-00496 | PKG-06 | INV-PKG-06-002-02486 | 111.22 | 61120.42 | 3056.02 | Under Review | 58064.4 | 2026-Q2
EXP-003576 | 2026-05-15 | BOQ-PKG-06-01586 | PKG-06 | INV-PKG-06-007-03576 | 67.03 | 159396.05 | 7969.8 | Paid | 151426.25 | 2026-Q2
EXP-004571 | 2026-05-15 | BOQ-PKG-01-00591 | PKG-01 | INV-PKG-01-022-04571 | 445.96 | 96576.19 | 4828.81 | Approved Pending Payment | 91747.38 | 2026-Q2
EXP-005031 | 2026-05-15 | BOQ-PKG-01-01051 | PKG-01 | INV-PKG-01-027-05031 | 441.03 | 207730.49 | 10386.52 | Approved Pending Payment | 197343.97 | 2026-Q2
EXP-005131 | 2026-05-15 | BOQ-PKG-01-01151 | PKG-01 | INV-PKG-01-022-05131 | 294.53 | 169728.12 | 8486.41 | Paid | 161241.71 | 2026-Q2
EXP-006478 | 2026-05-15 | BOQ-PKG-08-00508 | PKG-08 | INV-PKG-08-004-06478 | 192.64 | 130139.11 | 6506.96 | Paid | 123632.15 | 2026-Q2
EXP-006679 | 2026-05-15 | BOQ-PKG-09-00709 | PKG-09 | INV-PKG-09-030-06679 | 199.94 | 158768.36 | 7938.42 | Paid | 150829.94 | 2026-Q2
EXP-000118 | 2026-05-16 | BOQ-PKG-08-00118 | PKG-08 | INV-PKG-08-014-00118 | 119.01 | 63289.52 | 3164.48 | Approved Pending Payment | 60125.04 | 2026-Q2
EXP-000126 | 2026-05-16 | BOQ-PKG-06-00126 | PKG-06 | INV-PKG-06-022-00126 | 381.53 | 60146.55 | 3007.33 | Paid | 57139.22 | 2026-Q2
EXP-000204 | 2026-05-16 | BOQ-PKG-04-00204 | PKG-04 | INV-PKG-04-030-00204 | 58.12 | 87255.78 | 4362.79 | Paid | 82892.99 | 2026-Q2
EXP-000398 | 2026-05-16 | BOQ-PKG-08-00398 | PKG-08 | INV-PKG-08-014-00398 | 408.95 | 41635.78 | 2081.79 | Approved Pending Payment | 39553.99 | 2026-Q2
EXP-002575 | 2026-05-16 | BOQ-PKG-05-00585 | PKG-05 | INV-PKG-05-021-02575 | 12.62 | 159916.68 | 7995.83 | Paid | 151920.85 | 2026-Q2
EXP-005533 | 2026-05-16 | BOQ-PKG-03-01553 | PKG-03 | INV-PKG-03-004-05533 | 145.89 | 87733.63 | 4386.68 | Paid | 83346.95 | 2026-Q2
EXP-002763 | 2026-05-17 | BOQ-PKG-03-00773 | PKG-03 | INV-PKG-03-034-02763 | 212.87 | 98856.36 | 4942.82 | Under Review | 93913.54 | 2026-Q2
EXP-005079 | 2026-05-17 | BOQ-PKG-09-01099 | PKG-09 | INV-PKG-09-005-05079 | 120.8 | 136270.62 | 6813.53 | Paid | 129457.09 | 2026-Q2
EXP-005332 | 2026-05-17 | BOQ-PKG-02-01352 | PKG-02 | INV-PKG-02-013-05332 | 396.99 | 50414.78 | 2520.74 | Paid | 47894.04 | 2026-Q2
EXP-005930 | 2026-05-17 | BOQ-PKG-10-01950 | PKG-10 | INV-PKG-10-016-05930 | 23.11 | 32970.85 | 1648.54 | Paid | 31322.31 | 2026-Q2
EXP-002954 | 2026-05-18 | BOQ-PKG-04-00964 | PKG-04 | INV-PKG-04-015-02954 | 6.75 | 89556.76 | 4477.84 | Approved Pending Payment | 85078.92 | 2026-Q2
EXP-003208 | 2026-05-18 | BOQ-PKG-08-01218 | PKG-08 | INV-PKG-08-024-03208 | 335.11 | 207050.59 | 10352.53 | Paid | 196698.06 | 2026-Q2
EXP-004120 | 2026-05-18 | BOQ-PKG-10-00140 | PKG-10 | INV-PKG-10-026-04120 | 152 | 176824.53 | 8841.23 | Paid | 167983.3 | 2026-Q2
EXP-005515 | 2026-05-18 | BOQ-PKG-05-01535 | PKG-05 | INV-PKG-05-021-05515 | 72.42 | 42257.55 | 2112.88 | Paid | 40144.67 | 2026-Q2
EXP-006813 | 2026-05-18 | BOQ-PKG-03-00843 | PKG-03 | INV-PKG-03-024-06813 | 30.25 | 101953.87 | 5097.69 | Paid | 96856.18 | 2026-Q2
EXP-001320 | 2026-05-19 | BOQ-PKG-10-01320 | PKG-10 | INV-PKG-10-026-01320 | 439.53 | 186708.57 | 9335.43 | Approved Pending Payment | 177373.14 | 2026-Q2
EXP-002749 | 2026-05-19 | BOQ-PKG-09-00759 | PKG-09 | INV-PKG-09-020-02749 | 141.65 | 60354.95 | 3017.75 | Approved Pending Payment | 57337.2 | 2026-Q2
EXP-003487 | 2026-05-19 | BOQ-PKG-07-01497 | PKG-07 | INV-PKG-07-023-03487 | 149.73 | 163736.8 | 8186.84 | Paid | 155549.96 | 2026-Q2
EXP-003692 | 2026-05-19 | BOQ-PKG-02-01702 | PKG-02 | INV-PKG-02-018-03692 | 327.72 | 206671.72 | 10333.59 | Under Review | 196338.13 | 2026-Q2
EXP-003891 | 2026-05-19 | BOQ-PKG-01-01901 | PKG-01 | INV-PKG-01-007-03891 | 226.07 | 159917.94 | 7995.9 | Paid | 151922.04 | 2026-Q2
EXP-003973 | 2026-05-19 | BOQ-PKG-03-01983 | PKG-03 | INV-PKG-03-019-03973 | 40.53 | 185450.27 | 9272.51 | Paid | 176177.76 | 2026-Q2
EXP-004384 | 2026-05-19 | BOQ-PKG-04-00404 | PKG-04 | INV-PKG-04-010-04384 | 177.01 | 179487.49 | 8974.37 | Paid | 170513.12 | 2026-Q2
EXP-005154 | 2026-05-19 | BOQ-PKG-04-01174 | PKG-04 | INV-PKG-04-010-05154 | 178.05 | 57686.8 | 2884.34 | Paid | 54802.46 | 2026-Q2
EXP-005575 | 2026-05-19 | BOQ-PKG-05-01595 | PKG-05 | INV-PKG-05-011-05575 | 436.37 | 65640.69 | 3282.03 | Under Review | 62358.66 | 2026-Q2
EXP-001875 | 2026-05-20 | BOQ-PKG-05-01875 | PKG-05 | INV-PKG-05-021-01875 | 121.07 | 188073.09 | 9403.65 | Paid | 178669.44 | 2026-Q2
EXP-002996 | 2026-05-20 | BOQ-PKG-06-01006 | PKG-06 | INV-PKG-06-022-02996 | 196.04 | 174431.75 | 8721.59 | Approved Pending Payment | 165710.16 | 2026-Q2
EXP-003742 | 2026-05-20 | BOQ-PKG-02-01752 | PKG-02 | INV-PKG-02-033-03742 | 207.25 | 59113.7 | 2955.68 | Paid | 56158.02 | 2026-Q2
EXP-004289 | 2026-05-20 | BOQ-PKG-09-00309 | PKG-09 | INV-PKG-09-020-04289 | 425.15 | 183682.38 | 9184.12 | Under Review | 174498.26 | 2026-Q2
EXP-005146 | 2026-05-20 | BOQ-PKG-06-01166 | PKG-06 | INV-PKG-06-002-05146 | 231.86 | 152976.97 | 7648.85 | Paid | 145328.12 | 2026-Q2
EXP-006575 | 2026-05-20 | BOQ-PKG-05-00605 | PKG-05 | INV-PKG-05-031-06575 | 449.59 | 95256.74 | 4762.84 | Paid | 90493.9 | 2026-Q2
EXP-001064 | 2026-05-21 | BOQ-PKG-04-01064 | PKG-04 | INV-PKG-04-015-01064 | 394.69 | 179600.76 | 8980.04 | Paid | 170620.72 | 2026-Q2
EXP-002312 | 2026-05-21 | BOQ-PKG-02-00322 | PKG-02 | INV-PKG-02-003-02312 | 131.53 | 146435.24 | 7321.76 | Paid | 139113.48 | 2026-Q2
EXP-002910 | 2026-05-21 | BOQ-PKG-10-00920 | PKG-10 | INV-PKG-10-006-02910 | 106.84 | 59682.45 | 2984.12 | Paid | 56698.33 | 2026-Q2
EXP-003760 | 2026-05-21 | BOQ-PKG-10-01770 | PKG-10 | INV-PKG-10-016-03760 | 227.28 | 109581.99 | 5479.1 | Paid | 104102.89 | 2026-Q2
EXP-004322 | 2026-05-21 | BOQ-PKG-02-00342 | PKG-02 | INV-PKG-02-018-04322 | 55.71 | 80179.75 | 4008.99 | Paid | 76170.76 | 2026-Q2
EXP-005815 | 2026-05-21 | BOQ-PKG-05-01835 | PKG-05 | INV-PKG-05-006-05815 | 77.7 | 82885.35 | 4144.27 | Approved Pending Payment | 78741.08 | 2026-Q2
EXP-006979 | 2026-05-21 | BOQ-PKG-09-01009 | PKG-09 | INV-PKG-09-015-06979 | 239.94 | 165034.44 | 8251.72 | Paid | 156782.72 | 2026-Q2
EXP-001043 | 2026-05-22 | BOQ-PKG-03-01043 | PKG-03 | INV-PKG-03-029-01043 | 11.96 | 203112.46 | 10155.62 | Approved Pending Payment | 192956.84 | 2026-Q2
EXP-001527 | 2026-05-22 | BOQ-PKG-07-01527 | PKG-07 | INV-PKG-07-023-01527 | 111.35 | 64795.98 | 3239.8 | Paid | 61556.18 | 2026-Q2
EXP-004334 | 2026-05-22 | BOQ-PKG-04-00354 | PKG-04 | INV-PKG-04-030-04334 | 423.24 | 55974.61 | 2798.73 | Paid | 53175.88 | 2026-Q2
EXP-006026 | 2026-05-22 | BOQ-PKG-06-00056 | PKG-06 | INV-PKG-06-007-06026 | 422.19 | 131333.46 | 6566.67 | Approved Pending Payment | 124766.79 | 2026-Q2
EXP-006336 | 2026-05-22 | BOQ-PKG-06-00366 | PKG-06 | INV-PKG-06-002-06336 | 174.24 | 117282.37 | 5864.12 | Paid | 111418.25 | 2026-Q2
EXP-003854 | 2026-05-23 | BOQ-PKG-04-01864 | PKG-04 | INV-PKG-04-005-03854 | 84.55 | 117818.12 | 5890.91 | Paid | 111927.21 | 2026-Q2
EXP-004207 | 2026-05-23 | BOQ-PKG-07-00227 | PKG-07 | INV-PKG-07-008-04207 | 234.43 | 144150.05 | 7207.5 | Paid | 136942.55 | 2026-Q2
EXP-005998 | 2026-05-23 | BOQ-PKG-08-00028 | PKG-08 | INV-PKG-08-014-05998 | 72.26 | 31630.64 | 1581.53 | Paid | 30049.11 | 2026-Q2
EXP-006937 | 2026-05-23 | BOQ-PKG-07-00967 | PKG-07 | INV-PKG-07-008-06937 | 358.48 | 172659.32 | 8632.97 | Paid | 164026.35 | 2026-Q2
EXP-000558 | 2026-05-24 | BOQ-PKG-08-00558 | PKG-08 | INV-PKG-08-034-00558 | 438.91 | 69319.17 | 3465.96 | Paid | 65853.21 | 2026-Q2
EXP-000824 | 2026-05-24 | BOQ-PKG-04-00824 | PKG-04 | INV-PKG-04-020-00824 | 41.95 | 59332.64 | 2966.63 | Paid | 56366.01 | 2026-Q2
EXP-002573 | 2026-05-24 | BOQ-PKG-03-00583 | PKG-03 | INV-PKG-03-019-02573 | 383.45 | 181320.15 | 9066.01 | Paid | 172254.14 | 2026-Q2
EXP-002972 | 2026-05-24 | BOQ-PKG-02-00982 | PKG-02 | INV-PKG-02-033-02972 | 22.87 | 101601.68 | 5080.08 | Paid | 96521.6 | 2026-Q2
EXP-003225 | 2026-05-24 | BOQ-PKG-05-01235 | PKG-05 | INV-PKG-05-006-03225 | 28.79 | 80164.89 | 4008.24 | Paid | 76156.65 | 2026-Q2
EXP-003764 | 2026-05-24 | BOQ-PKG-04-01774 | PKG-04 | INV-PKG-04-020-03764 | 206.09 | 26216.96 | 1310.85 | Paid | 24906.11 | 2026-Q2
EXP-005183 | 2026-05-24 | BOQ-PKG-03-01203 | PKG-03 | INV-PKG-03-004-05183 | 247.45 | 113330.05 | 5666.5 | Paid | 107663.55 | 2026-Q2
EXP-005270 | 2026-05-24 | BOQ-PKG-10-01290 | PKG-10 | INV-PKG-10-021-05270 | 291.33 | 201639.06 | 10081.95 | Paid | 191557.11 | 2026-Q2
EXP-005473 | 2026-05-24 | BOQ-PKG-03-01493 | PKG-03 | INV-PKG-03-014-05473 | 28.88 | 40147.27 | 2007.36 | Paid | 38139.91 | 2026-Q2
EXP-006403 | 2026-05-24 | BOQ-PKG-03-00433 | PKG-03 | INV-PKG-03-034-06403 | 406.65 | 210068.08 | 10503.4 | Paid | 199564.68 | 2026-Q2
EXP-006486 | 2026-05-24 | BOQ-PKG-06-00516 | PKG-06 | INV-PKG-06-012-06486 | 83.25 | 99175.58 | 4958.78 | Approved Pending Payment | 94216.8 | 2026-Q2
EXP-000099 | 2026-05-25 | BOQ-PKG-09-00099 | PKG-09 | INV-PKG-09-030-00099 | 446.23 | 62121.11 | 3106.06 | Paid | 59015.05 | 2026-Q2
EXP-004656 | 2026-05-25 | BOQ-PKG-06-00676 | PKG-06 | INV-PKG-06-002-04656 | 85.3 | 31703.17 | 1585.16 | Paid | 30118.01 | 2026-Q2
EXP-004753 | 2026-05-25 | BOQ-PKG-03-00773 | PKG-03 | INV-PKG-03-029-04753 | 258.48 | 193065.28 | 9653.26 | Paid | 183412.02 | 2026-Q2
EXP-006071 | 2026-05-25 | BOQ-PKG-01-00101 | PKG-01 | INV-PKG-01-017-06071 | 43.89 | 100490.06 | 5024.5 | Paid | 95465.56 | 2026-Q2
EXP-006121 | 2026-05-25 | BOQ-PKG-01-00151 | PKG-01 | INV-PKG-01-032-06121 | 37.2 | 139675.5 | 6983.78 | Paid | 132691.72 | 2026-Q2
EXP-000628 | 2026-05-26 | BOQ-PKG-08-00628 | PKG-08 | INV-PKG-08-034-00628 | 362.95 | 36775.23 | 1838.76 | Paid | 34936.47 | 2026-Q2
EXP-000629 | 2026-05-26 | BOQ-PKG-09-00629 | PKG-09 | INV-PKG-09-035-00629 | 59.5 | 127323.92 | 6366.2 | Paid | 120957.72 | 2026-Q2
EXP-001802 | 2026-05-26 | BOQ-PKG-02-01802 | PKG-02 | INV-PKG-02-018-01802 | 425.47 | 25011.34 | 1250.57 | Paid | 23760.77 | 2026-Q2
EXP-002247 | 2026-05-26 | BOQ-PKG-07-00257 | PKG-07 | INV-PKG-07-008-02247 | 243.3 | 177728.04 | 8886.4 | Paid | 168841.64 | 2026-Q2
EXP-002380 | 2026-05-26 | BOQ-PKG-10-00390 | PKG-10 | INV-PKG-10-001-02380 | 79.71 | 24881.96 | 1244.1 | Paid | 23637.86 | 2026-Q2
EXP-004493 | 2026-05-26 | BOQ-PKG-03-00513 | PKG-03 | INV-PKG-03-014-04493 | 45.83 | 87133.34 | 4356.67 | Under Review | 82776.67 | 2026-Q2
EXP-004685 | 2026-05-26 | BOQ-PKG-05-00705 | PKG-05 | INV-PKG-05-031-04685 | 239.34 | 126361.41 | 6318.07 | Paid | 120043.34 | 2026-Q2
EXP-001037 | 2026-05-27 | BOQ-PKG-07-01037 | PKG-07 | INV-PKG-07-023-01037 | 288.88 | 165826.12 | 8291.31 | Disputed | 157534.81 | 2026-Q2
EXP-001047 | 2026-05-27 | BOQ-PKG-07-01047 | PKG-07 | INV-PKG-07-033-01047 | 424.19 | 35671.81 | 1783.59 | Paid | 33888.22 | 2026-Q2
EXP-001339 | 2026-05-27 | BOQ-PKG-09-01339 | PKG-09 | INV-PKG-09-010-01339 | 100.69 | 60587.52 | 3029.38 | Paid | 57558.14 | 2026-Q2
EXP-001803 | 2026-05-27 | BOQ-PKG-03-01803 | PKG-03 | INV-PKG-03-019-01803 | 235.69 | 36772.59 | 1838.63 | Paid | 34933.96 | 2026-Q2
EXP-002518 | 2026-05-27 | BOQ-PKG-08-00528 | PKG-08 | INV-PKG-08-034-02518 | 238.14 | 142802.48 | 7140.12 | Paid | 135662.36 | 2026-Q2
EXP-004794 | 2026-05-27 | BOQ-PKG-04-00814 | PKG-04 | INV-PKG-04-035-04794 | 330.18 | 74642.75 | 3732.14 | Paid | 70910.61 | 2026-Q2
EXP-005163 | 2026-05-27 | BOQ-PKG-03-01183 | PKG-03 | INV-PKG-03-019-05163 | 139.71 | 164380.29 | 8219.01 | Under Review | 156161.28 | 2026-Q2
EXP-006311 | 2026-05-27 | BOQ-PKG-01-00341 | PKG-01 | INV-PKG-01-012-06311 | 169.56 | 166768.58 | 8338.43 | Paid | 158430.15 | 2026-Q2
EXP-006573 | 2026-05-27 | BOQ-PKG-03-00603 | PKG-03 | INV-PKG-03-029-06573 | 76.91 | 172028.01 | 8601.4 | Paid | 163426.61 | 2026-Q2
EXP-006667 | 2026-05-27 | BOQ-PKG-07-00697 | PKG-07 | INV-PKG-07-018-06667 | 286.26 | 84501.33 | 4225.07 | Paid | 80276.26 | 2026-Q2
EXP-006836 | 2026-05-27 | BOQ-PKG-06-00866 | PKG-06 | INV-PKG-06-012-06836 | 222.9 | 71466.47 | 3573.32 | Approved Pending Payment | 67893.15 | 2026-Q2
EXP-000362 | 2026-05-28 | BOQ-PKG-02-00362 | PKG-02 | INV-PKG-02-013-00362 | 124.99 | 183903.83 | 9195.19 | Paid | 174708.64 | 2026-Q2
EXP-000911 | 2026-05-28 | BOQ-PKG-01-00911 | PKG-01 | INV-PKG-01-002-00911 | 13.02 | 130825.01 | 6541.25 | Paid | 124283.76 | 2026-Q2
EXP-002888 | 2026-05-28 | BOQ-PKG-08-00898 | PKG-08 | INV-PKG-08-019-02888 | 101.69 | 182026.8 | 9101.34 | Disputed | 172925.46 | 2026-Q2
EXP-002980 | 2026-05-28 | BOQ-PKG-10-00990 | PKG-10 | INV-PKG-10-006-02980 | 51.72 | 205606.31 | 10280.32 | Paid | 195325.99 | 2026-Q2
EXP-004243 | 2026-05-28 | BOQ-PKG-03-00263 | PKG-03 | INV-PKG-03-009-04243 | 439.46 | 64770.74 | 3238.54 | Paid | 61532.2 | 2026-Q2
EXP-005245 | 2026-05-28 | BOQ-PKG-05-01265 | PKG-05 | INV-PKG-05-031-05245 | 196.86 | 194602.3 | 9730.12 | Under Review | 184872.18 | 2026-Q2
EXP-001265 | 2026-05-29 | BOQ-PKG-05-01265 | PKG-05 | INV-PKG-05-006-01265 | 370.18 | 49692.68 | 2484.63 | Paid | 47208.05 | 2026-Q2
EXP-001577 | 2026-05-29 | BOQ-PKG-07-01577 | PKG-07 | INV-PKG-07-003-01577 | 11.6 | 181017.68 | 9050.88 | Approved Pending Payment | 171966.8 | 2026-Q2
EXP-005327 | 2026-05-29 | BOQ-PKG-07-01347 | PKG-07 | INV-PKG-07-008-05327 | 127.8 | 67443.61 | 3372.18 | Disputed | 64071.43 | 2026-Q2
EXP-005580 | 2026-05-29 | BOQ-PKG-10-01600 | PKG-10 | INV-PKG-10-016-05580 | 343.51 | 44657.44 | 2232.87 | Paid | 42424.57 | 2026-Q2
EXP-005673 | 2026-05-29 | BOQ-PKG-03-01693 | PKG-03 | INV-PKG-03-004-05673 | 326.53 | 75590.02 | 3779.5 | Paid | 71810.52 | 2026-Q2
EXP-003462 | 2026-05-30 | BOQ-PKG-02-01472 | PKG-02 | INV-PKG-02-033-03462 | 335.95 | 94594.05 | 4729.7 | Paid | 89864.35 | 2026-Q2
EXP-003498 | 2026-05-30 | BOQ-PKG-08-01508 | PKG-08 | INV-PKG-08-034-03498 | 13.11 | 94035.26 | 4701.76 | Paid | 89333.5 | 2026-Q2
EXP-004323 | 2026-05-30 | BOQ-PKG-03-00343 | PKG-03 | INV-PKG-03-019-04323 | 352.78 | 159323.09 | 7966.15 | Under Review | 151356.94 | 2026-Q2
EXP-005338 | 2026-05-30 | BOQ-PKG-08-01358 | PKG-08 | INV-PKG-08-019-05338 | 66.95 | 55753.86 | 2787.69 | Paid | 52966.17 | 2026-Q2
EXP-005477 | 2026-05-30 | BOQ-PKG-07-01497 | PKG-07 | INV-PKG-07-018-05477 | 242.98 | 81704.15 | 4085.21 | Paid | 77618.94 | 2026-Q2
EXP-006119 | 2026-05-30 | BOQ-PKG-09-00149 | PKG-09 | INV-PKG-09-030-06119 | 11.33 | 177046.67 | 8852.33 | Paid | 168194.34 | 2026-Q2
EXP-006413 | 2026-05-30 | BOQ-PKG-03-00443 | PKG-03 | INV-PKG-03-009-06413 | 233.35 | 69952.83 | 3497.64 | Paid | 66455.19 | 2026-Q2
EXP-006754 | 2026-05-30 | BOQ-PKG-04-00784 | PKG-04 | INV-PKG-04-035-06754 | 207.54 | 170675 | 8533.75 | Paid | 162141.25 | 2026-Q2
EXP-001005 | 2026-05-31 | BOQ-PKG-05-01005 | PKG-05 | INV-PKG-05-026-01005 | 238.79 | 158489.39 | 7924.47 | Paid | 150564.92 | 2026-Q2
EXP-003291 | 2026-05-31 | BOQ-PKG-01-01301 | PKG-01 | INV-PKG-01-002-03291 | 186.73 | 114438.2 | 5721.91 | Paid | 108716.29 | 2026-Q2
EXP-003421 | 2026-05-31 | BOQ-PKG-01-01431 | PKG-01 | INV-PKG-01-027-03421 | 357.12 | 83660.62 | 4183.03 | Paid | 79477.59 | 2026-Q2
EXP-003427 | 2026-05-31 | BOQ-PKG-07-01437 | PKG-07 | INV-PKG-07-033-03427 | 11.94 | 139118.8 | 6955.94 | Paid | 132162.86 | 2026-Q2
EXP-004004 | 2026-05-31 | BOQ-PKG-04-00024 | PKG-04 | INV-PKG-04-015-04004 | 195.67 | 92501.23 | 4625.06 | Paid | 87876.17 | 2026-Q2
EXP-005356 | 2026-05-31 | BOQ-PKG-06-01376 | PKG-06 | INV-PKG-06-002-05356 | 347.06 | 207244.26 | 10362.21 | Paid | 196882.05 | 2026-Q2
EXP-005526 | 2026-05-31 | BOQ-PKG-06-01546 | PKG-06 | INV-PKG-06-032-05526 | 173.6 | 92811.89 | 4640.59 | Paid | 88171.3 | 2026-Q2
EXP-005813 | 2026-05-31 | BOQ-PKG-03-01833 | PKG-03 | INV-PKG-03-004-05813 | 37.73 | 157384.98 | 7869.25 | Approved Pending Payment | 149515.73 | 2026-Q2
EXP-000666 | 2026-06-01 | BOQ-PKG-06-00666 | PKG-06 | INV-PKG-06-002-00666 | 375.68 | 81299.08 | 4064.95 | Paid | 77234.13 | 2026-Q2
EXP-000915 | 2026-06-01 | BOQ-PKG-05-00915 | PKG-05 | INV-PKG-05-006-00915 | 45.51 | 143980.57 | 7199.03 | Paid | 136781.54 | 2026-Q2
EXP-003920 | 2026-06-01 | BOQ-PKG-10-01930 | PKG-10 | INV-PKG-10-001-03920 | 117.92 | 100073.03 | 5003.65 | Paid | 95069.38 | 2026-Q2
EXP-004175 | 2026-06-01 | BOQ-PKG-05-00195 | PKG-05 | INV-PKG-05-011-04175 | 406.16 | 121300.56 | 6065.03 | Paid | 115235.53 | 2026-Q2
EXP-004959 | 2026-06-01 | BOQ-PKG-09-00979 | PKG-09 | INV-PKG-09-025-04959 | 48.91 | 73752.93 | 3687.65 | Paid | 70065.28 | 2026-Q2
EXP-005143 | 2026-06-01 | BOQ-PKG-03-01163 | PKG-03 | INV-PKG-03-034-05143 | 290.97 | 152441.17 | 7622.06 | Paid | 144819.11 | 2026-Q2
EXP-006014 | 2026-06-01 | BOQ-PKG-04-00044 | PKG-04 | INV-PKG-04-030-06014 | 250.35 | 102849.82 | 5142.49 | Paid | 97707.33 | 2026-Q2
EXP-000573 | 2026-06-02 | BOQ-PKG-03-00573 | PKG-03 | INV-PKG-03-014-00573 | 79.29 | 45046.76 | 2252.34 | Under Review | 42794.42 | 2026-Q2
EXP-001054 | 2026-06-02 | BOQ-PKG-04-01054 | PKG-04 | INV-PKG-04-005-01054 | 222.69 | 105464.36 | 5273.22 | Paid | 100191.14 | 2026-Q2
EXP-001446 | 2026-06-02 | BOQ-PKG-06-01446 | PKG-06 | INV-PKG-06-012-01446 | 350.6 | 64091.91 | 3204.6 | Paid | 60887.31 | 2026-Q2
EXP-001911 | 2026-06-02 | BOQ-PKG-01-01911 | PKG-01 | INV-PKG-01-022-01911 | 184.9 | 95936.3 | 4796.82 | Paid | 91139.48 | 2026-Q2
EXP-002840 | 2026-06-02 | BOQ-PKG-10-00850 | PKG-10 | INV-PKG-10-006-02840 | 127.99 | 95565.7 | 4778.28 | Paid | 90787.42 | 2026-Q2
EXP-002931 | 2026-06-02 | BOQ-PKG-01-00941 | PKG-01 | INV-PKG-01-027-02931 | 140.22 | 165176.46 | 8258.82 | Paid | 156917.64 | 2026-Q2
EXP-003928 | 2026-06-02 | BOQ-PKG-08-01938 | PKG-08 | INV-PKG-08-009-03928 | 96.26 | 109695.17 | 5484.76 | Approved Pending Payment | 104210.41 | 2026-Q2
EXP-004101 | 2026-06-02 | BOQ-PKG-01-00121 | PKG-01 | INV-PKG-01-007-04101 | 107.73 | 71137.51 | 3556.88 | Approved Pending Payment | 67580.63 | 2026-Q2
EXP-005863 | 2026-06-02 | BOQ-PKG-03-01883 | PKG-03 | INV-PKG-03-019-05863 | 302.32 | 194788.79 | 9739.44 | Under Review | 185049.35 | 2026-Q2
EXP-000188 | 2026-06-03 | BOQ-PKG-08-00188 | PKG-08 | INV-PKG-08-014-00188 | 150.89 | 95310.96 | 4765.55 | Paid | 90545.41 | 2026-Q2
EXP-001846 | 2026-06-03 | BOQ-PKG-06-01846 | PKG-06 | INV-PKG-06-027-01846 | 284.5 | 175857.01 | 8792.85 | Approved Pending Payment | 167064.16 | 2026-Q2
EXP-002006 | 2026-06-03 | BOQ-PKG-06-00016 | PKG-06 | INV-PKG-06-012-02006 | 177.82 | 135302.09 | 6765.1 | Disputed | 128536.99 | 2026-Q2
EXP-002056 | 2026-06-03 | BOQ-PKG-06-00066 | PKG-06 | INV-PKG-06-027-02056 | 137.54 | 195785.15 | 9789.26 | Paid | 185995.89 | 2026-Q2
EXP-005421 | 2026-06-03 | BOQ-PKG-01-01441 | PKG-01 | INV-PKG-01-032-05421 | 261.01 | 49335.57 | 2466.78 | Paid | 46868.79 | 2026-Q2
EXP-006111 | 2026-06-03 | BOQ-PKG-01-00141 | PKG-01 | INV-PKG-01-022-06111 | 86.62 | 56256.08 | 2812.8 | Paid | 53443.28 | 2026-Q2
EXP-006405 | 2026-06-03 | BOQ-PKG-05-00435 | PKG-05 | INV-PKG-05-001-06405 | 427.85 | 24406.15 | 1220.31 | Approved Pending Payment | 23185.84 | 2026-Q2
EXP-006579 | 2026-06-03 | BOQ-PKG-09-00609 | PKG-09 | INV-PKG-09-035-06579 | 409.35 | 71764.34 | 3588.22 | Paid | 68176.12 | 2026-Q2
EXP-006653 | 2026-06-03 | BOQ-PKG-03-00683 | PKG-03 | INV-PKG-03-004-06653 | 60.79 | 205602.91 | 10280.15 | Paid | 195322.76 | 2026-Q2
EXP-006752 | 2026-06-03 | BOQ-PKG-02-00782 | PKG-02 | INV-PKG-02-033-06752 | 41.6 | 81268.53 | 4063.43 | Disputed | 77205.1 | 2026-Q2
EXP-006760 | 2026-06-03 | BOQ-PKG-10-00790 | PKG-10 | INV-PKG-10-006-06760 | 165.62 | 104227.33 | 5211.37 | Approved Pending Payment | 99015.96 | 2026-Q2
EXP-000979 | 2026-06-04 | BOQ-PKG-09-00979 | PKG-09 | INV-PKG-09-035-00979 | 64.62 | 143520.21 | 7176.01 | Under Review | 136344.2 | 2026-Q2
EXP-001994 | 2026-06-04 | BOQ-PKG-04-00004 | PKG-04 | INV-PKG-04-035-01994 | 39.76 | 104004.52 | 5200.23 | Under Review | 98804.29 | 2026-Q2
EXP-002552 | 2026-06-04 | BOQ-PKG-02-00562 | PKG-02 | INV-PKG-02-033-02552 | 227.69 | 129065.75 | 6453.29 | Paid | 122612.46 | 2026-Q2
EXP-004549 | 2026-06-04 | BOQ-PKG-09-00569 | PKG-09 | INV-PKG-09-035-04549 | 426.24 | 54236.61 | 2711.83 | Approved Pending Payment | 51524.78 | 2026-Q2
EXP-005557 | 2026-06-04 | BOQ-PKG-07-01577 | PKG-07 | INV-PKG-07-028-05557 | 426.85 | 77243.85 | 3862.19 | Approved Pending Payment | 73381.66 | 2026-Q2
EXP-005848 | 2026-06-04 | BOQ-PKG-08-01868 | PKG-08 | INV-PKG-08-004-05848 | 165.93 | 31614.95 | 1580.75 | Paid | 30034.2 | 2026-Q2
EXP-006431 | 2026-06-04 | BOQ-PKG-01-00461 | PKG-01 | INV-PKG-01-027-06431 | 378.96 | 83611.41 | 4180.57 | Paid | 79430.84 | 2026-Q2
EXP-006455 | 2026-06-04 | BOQ-PKG-05-00485 | PKG-05 | INV-PKG-05-016-06455 | 372.85 | 136374.78 | 6818.74 | Under Review | 129556.04 | 2026-Q2
EXP-004686 | 2026-06-05 | BOQ-PKG-06-00706 | PKG-06 | INV-PKG-06-032-04686 | 253.63 | 68942.68 | 3447.13 | Paid | 65495.55 | 2026-Q2
EXP-004903 | 2026-06-05 | BOQ-PKG-03-00923 | PKG-03 | INV-PKG-03-004-04903 | 131.69 | 142939.65 | 7146.98 | Paid | 135792.67 | 2026-Q2
EXP-005224 | 2026-06-05 | BOQ-PKG-04-01244 | PKG-04 | INV-PKG-04-010-05224 | 325.23 | 33873.08 | 1693.65 | Paid | 32179.43 | 2026-Q2
EXP-006218 | 2026-06-05 | BOQ-PKG-08-00248 | PKG-08 | INV-PKG-08-024-06218 | 302.55 | 70671.16 | 3533.56 | Paid | 67137.6 | 2026-Q2
EXP-006944 | 2026-06-05 | BOQ-PKG-04-00974 | PKG-04 | INV-PKG-04-015-06944 | 22.59 | 148042.95 | 7402.15 | Paid | 140640.8 | 2026-Q2
EXP-000453 | 2026-06-06 | BOQ-PKG-03-00453 | PKG-03 | INV-PKG-03-034-00453 | 47.21 | 127897.52 | 6394.88 | Approved Pending Payment | 121502.64 | 2026-Q2
EXP-001982 | 2026-06-06 | BOQ-PKG-02-01982 | PKG-02 | INV-PKG-02-023-01982 | 303.12 | 25835.77 | 1291.79 | Paid | 24543.98 | 2026-Q2
EXP-002688 | 2026-06-06 | BOQ-PKG-08-00698 | PKG-08 | INV-PKG-08-029-02688 | 241.03 | 98283.11 | 4914.16 | Paid | 93368.95 | 2026-Q2
EXP-005346 | 2026-06-06 | BOQ-PKG-06-01366 | PKG-06 | INV-PKG-06-027-05346 | 77.61 | 128827.6 | 6441.38 | Paid | 122386.22 | 2026-Q2
EXP-005829 | 2026-06-06 | BOQ-PKG-09-01849 | PKG-09 | INV-PKG-09-020-05829 | 419.68 | 44288.01 | 2214.4 | Paid | 42073.61 | 2026-Q2
EXP-006656 | 2026-06-06 | BOQ-PKG-06-00686 | PKG-06 | INV-PKG-06-007-06656 | 35.08 | 132614.79 | 6630.74 | Paid | 125984.05 | 2026-Q2
EXP-000975 | 2026-06-07 | BOQ-PKG-05-00975 | PKG-05 | INV-PKG-05-031-00975 | 214.28 | 29787.97 | 1489.4 | Paid | 28298.57 | 2026-Q2
EXP-003401 | 2026-06-07 | BOQ-PKG-01-01411 | PKG-01 | INV-PKG-01-007-03401 | 363.46 | 51339.37 | 2566.97 | Under Review | 48772.4 | 2026-Q2
EXP-003491 | 2026-06-07 | BOQ-PKG-01-01501 | PKG-01 | INV-PKG-01-027-03491 | 396.63 | 112926.37 | 5646.32 | Paid | 107280.05 | 2026-Q2
EXP-003602 | 2026-06-07 | BOQ-PKG-02-01612 | PKG-02 | INV-PKG-02-033-03602 | 412.22 | 96641.53 | 4832.08 | Paid | 91809.45 | 2026-Q2
EXP-005645 | 2026-06-07 | BOQ-PKG-05-01665 | PKG-05 | INV-PKG-05-011-05645 | 188.47 | 185408.5 | 9270.43 | Paid | 176138.07 | 2026-Q2
EXP-006690 | 2026-06-07 | BOQ-PKG-10-00720 | PKG-10 | INV-PKG-10-006-06690 | 227.63 | 63693.39 | 3184.67 | Paid | 60508.72 | 2026-Q2
EXP-006843 | 2026-06-07 | BOQ-PKG-03-00873 | PKG-03 | INV-PKG-03-019-06843 | 67.38 | 167099.43 | 8354.97 | Paid | 158744.46 | 2026-Q2
EXP-006953 | 2026-06-07 | BOQ-PKG-03-00983 | PKG-03 | INV-PKG-03-024-06953 | 135.24 | 35612.24 | 1780.61 | Paid | 33831.63 | 2026-Q2
EXP-000855 | 2026-06-08 | BOQ-PKG-05-00855 | PKG-05 | INV-PKG-05-016-00855 | 440.44 | 26179.04 | 1308.95 | Paid | 24870.09 | 2026-Q2
EXP-001213 | 2026-06-08 | BOQ-PKG-03-01213 | PKG-03 | INV-PKG-03-024-01213 | 67.64 | 66228.76 | 3311.44 | Approved Pending Payment | 62917.32 | 2026-Q2
EXP-001742 | 2026-06-08 | BOQ-PKG-02-01742 | PKG-02 | INV-PKG-02-028-01742 | 289.63 | 57029.15 | 2851.46 | Paid | 54177.69 | 2026-Q2
EXP-002689 | 2026-06-08 | BOQ-PKG-09-00699 | PKG-09 | INV-PKG-09-030-02689 | 84.52 | 82069.53 | 4103.48 | Paid | 77966.05 | 2026-Q2
EXP-002863 | 2026-06-08 | BOQ-PKG-03-00873 | PKG-03 | INV-PKG-03-029-02863 | 205.56 | 93090.65 | 4654.53 | Approved Pending Payment | 88436.12 | 2026-Q2
EXP-006859 | 2026-06-08 | BOQ-PKG-09-00889 | PKG-09 | INV-PKG-09-035-06859 | 438.48 | 36735.52 | 1836.78 | Paid | 34898.74 | 2026-Q2
EXP-000642 | 2026-06-09 | BOQ-PKG-02-00642 | PKG-02 | INV-PKG-02-013-00642 | 268.69 | 94888.5 | 4744.42 | Paid | 90144.08 | 2026-Q2
EXP-001017 | 2026-06-09 | BOQ-PKG-07-01017 | PKG-07 | INV-PKG-07-003-01017 | 384.44 | 167201.2 | 8360.06 | Paid | 158841.14 | 2026-Q2
EXP-001569 | 2026-06-09 | BOQ-PKG-09-01569 | PKG-09 | INV-PKG-09-030-01569 | 297.24 | 107803.42 | 5390.17 | Approved Pending Payment | 102413.25 | 2026-Q2
EXP-001630 | 2026-06-09 | BOQ-PKG-10-01630 | PKG-10 | INV-PKG-10-021-01630 | 124.86 | 211392.21 | 10569.61 | Paid | 200822.6 | 2026-Q2
EXP-002927 | 2026-06-09 | BOQ-PKG-07-00937 | PKG-07 | INV-PKG-07-023-02927 | 97.44 | 135786.89 | 6789.34 | Approved Pending Payment | 128997.55 | 2026-Q2
EXP-006037 | 2026-06-09 | BOQ-PKG-07-00067 | PKG-07 | INV-PKG-07-018-06037 | 393.2 | 135004.68 | 6750.23 | Paid | 128254.45 | 2026-Q2
EXP-006330 | 2026-06-09 | BOQ-PKG-10-00360 | PKG-10 | INV-PKG-10-031-06330 | 12.57 | 99863.97 | 4993.2 | Approved Pending Payment | 94870.77 | 2026-Q2
EXP-001408 | 2026-06-10 | BOQ-PKG-08-01408 | PKG-08 | INV-PKG-08-009-01408 | 303.33 | 196234.27 | 9811.71 | Under Review | 186422.56 | 2026-Q2
EXP-001659 | 2026-06-10 | BOQ-PKG-09-01659 | PKG-09 | INV-PKG-09-015-01659 | 39.56 | 200787.11 | 10039.36 | Paid | 190747.75 | 2026-Q2
EXP-002256 | 2026-06-10 | BOQ-PKG-06-00266 | PKG-06 | INV-PKG-06-017-02256 | 353.43 | 59047 | 2952.35 | Paid | 56094.65 | 2026-Q2
EXP-002691 | 2026-06-10 | BOQ-PKG-01-00701 | PKG-01 | INV-PKG-01-032-02691 | 448.17 | 130964.98 | 6548.25 | Paid | 124416.73 | 2026-Q2
EXP-003025 | 2026-06-10 | BOQ-PKG-05-01035 | PKG-05 | INV-PKG-05-016-03025 | 76.69 | 133739.1 | 6686.96 | Paid | 127052.14 | 2026-Q2
EXP-000500 | 2026-06-11 | BOQ-PKG-10-00500 | PKG-10 | INV-PKG-10-011-00500 | 235.12 | 45895.96 | 2294.8 | Paid | 43601.16 | 2026-Q2
EXP-001089 | 2026-06-11 | BOQ-PKG-09-01089 | PKG-09 | INV-PKG-09-005-01089 | 249.34 | 131767.66 | 6588.38 | Under Review | 125179.28 | 2026-Q2
EXP-002590 | 2026-06-11 | BOQ-PKG-10-00600 | PKG-10 | INV-PKG-10-001-02590 | 79.31 | 71326.1 | 3566.3 | Approved Pending Payment | 67759.8 | 2026-Q2
EXP-003089 | 2026-06-11 | BOQ-PKG-09-01099 | PKG-09 | INV-PKG-09-010-03089 | 244.71 | 182062.06 | 9103.1 | Paid | 172958.96 | 2026-Q2
EXP-003369 | 2026-06-11 | BOQ-PKG-09-01379 | PKG-09 | INV-PKG-09-010-03369 | 29.02 | 185686.74 | 9284.34 | Paid | 176402.4 | 2026-Q2
EXP-006802 | 2026-06-11 | BOQ-PKG-02-00832 | PKG-02 | INV-PKG-02-013-06802 | 16.01 | 43442.64 | 2172.13 | Paid | 41270.51 | 2026-Q2
EXP-001157 | 2026-06-12 | BOQ-PKG-07-01157 | PKG-07 | INV-PKG-07-003-01157 | 70.37 | 212400.75 | 10620.04 | Under Review | 201780.71 | 2026-Q2
EXP-001750 | 2026-06-12 | BOQ-PKG-10-01750 | PKG-10 | INV-PKG-10-001-01750 | 366.1 | 179611.39 | 8980.57 | Paid | 170630.82 | 2026-Q2
EXP-002924 | 2026-06-12 | BOQ-PKG-04-00934 | PKG-04 | INV-PKG-04-020-02924 | 31.09 | 26502.24 | 1325.11 | Paid | 25177.13 | 2026-Q2
EXP-002949 | 2026-06-12 | BOQ-PKG-09-00959 | PKG-09 | INV-PKG-09-010-02949 | 360.49 | 212224.33 | 10611.22 | Paid | 201613.11 | 2026-Q2
EXP-003113 | 2026-06-12 | BOQ-PKG-03-01123 | PKG-03 | INV-PKG-03-034-03113 | 259.41 | 42438.81 | 2121.94 | Disputed | 40316.87 | 2026-Q2
EXP-006280 | 2026-06-12 | BOQ-PKG-10-00310 | PKG-10 | INV-PKG-10-016-06280 | 234.1 | 118185.69 | 5909.28 | Paid | 112276.41 | 2026-Q2
EXP-001050 | 2026-06-13 | BOQ-PKG-10-01050 | PKG-10 | INV-PKG-10-001-01050 | 184.16 | 188439.46 | 9421.97 | Approved Pending Payment | 179017.49 | 2026-Q2
EXP-001587 | 2026-06-13 | BOQ-PKG-07-01587 | PKG-07 | INV-PKG-07-013-01587 | 273.47 | 63902.33 | 3195.12 | Under Review | 60707.21 | 2026-Q2
EXP-002548 | 2026-06-13 | BOQ-PKG-08-00558 | PKG-08 | INV-PKG-08-029-02548 | 121.79 | 66275.08 | 3313.75 | Paid | 62961.33 | 2026-Q2
EXP-002719 | 2026-06-13 | BOQ-PKG-09-00729 | PKG-09 | INV-PKG-09-025-02719 | 445.52 | 128411.9 | 6420.6 | Paid | 121991.3 | 2026-Q2
EXP-004632 | 2026-06-13 | BOQ-PKG-02-00652 | PKG-02 | INV-PKG-02-013-04632 | 313.6 | 148937.2 | 7446.86 | Paid | 141490.34 | 2026-Q2
EXP-006837 | 2026-06-13 | BOQ-PKG-07-00867 | PKG-07 | INV-PKG-07-013-06837 | 56.72 | 170229.19 | 8511.46 | Paid | 161717.73 | 2026-Q2
EXP-000945 | 2026-06-14 | BOQ-PKG-05-00945 | PKG-05 | INV-PKG-05-001-00945 | 373.63 | 82507.92 | 4125.4 | Paid | 78382.52 | 2026-Q2
EXP-001606 | 2026-06-14 | BOQ-PKG-06-01606 | PKG-06 | INV-PKG-06-032-01606 | 195.79 | 185597.29 | 9279.86 | Disputed | 176317.43 | 2026-Q2
EXP-001815 | 2026-06-14 | BOQ-PKG-05-01815 | PKG-05 | INV-PKG-05-031-01815 | 186.26 | 211740.11 | 10587.01 | Paid | 201153.1 | 2026-Q2
EXP-002607 | 2026-06-14 | BOQ-PKG-07-00617 | PKG-07 | INV-PKG-07-018-02607 | 359.65 | 133557.55 | 6677.88 | Paid | 126879.67 | 2026-Q2
EXP-004256 | 2026-06-14 | BOQ-PKG-06-00276 | PKG-06 | INV-PKG-06-022-04256 | 304.44 | 167672.14 | 8383.61 | Paid | 159288.53 | 2026-Q2
EXP-005747 | 2026-06-14 | BOQ-PKG-07-01767 | PKG-07 | INV-PKG-07-008-05747 | 60.05 | 70024.24 | 3501.21 | Paid | 66523.03 | 2026-Q2
EXP-006456 | 2026-06-14 | BOQ-PKG-06-00486 | PKG-06 | INV-PKG-06-017-06456 | 103.69 | 159255.22 | 7962.76 | Approved Pending Payment | 151292.46 | 2026-Q2
EXP-006965 | 2026-06-14 | BOQ-PKG-05-00995 | PKG-05 | INV-PKG-05-001-06965 | 353.41 | 139403.68 | 6970.18 | Paid | 132433.5 | 2026-Q2
EXP-001244 | 2026-06-15 | BOQ-PKG-04-01244 | PKG-04 | INV-PKG-04-020-01244 | 324.26 | 162444.84 | 8122.24 | Paid | 154322.6 | 2026-Q2
EXP-001531 | 2026-06-15 | BOQ-PKG-01-01531 | PKG-01 | INV-PKG-01-027-01531 | 410.28 | 162310.9 | 8115.54 | Paid | 154195.36 | 2026-Q2
EXP-003868 | 2026-06-15 | BOQ-PKG-08-01878 | PKG-08 | INV-PKG-08-019-03868 | 309.04 | 146949.99 | 7347.5 | Paid | 139602.49 | 2026-Q2
EXP-005155 | 2026-06-15 | BOQ-PKG-05-01175 | PKG-05 | INV-PKG-05-011-05155 | 15.18 | 197319.18 | 9865.96 | Approved Pending Payment | 187453.22 | 2026-Q2
EXP-005426 | 2026-06-15 | BOQ-PKG-06-01446 | PKG-06 | INV-PKG-06-002-05426 | 442.26 | 109239.98 | 5462 | Approved Pending Payment | 103777.98 | 2026-Q2
EXP-006042 | 2026-06-15 | BOQ-PKG-02-00072 | PKG-02 | INV-PKG-02-023-06042 | 214.64 | 204364.42 | 10218.22 | Paid | 194146.2 | 2026-Q2
EXP-006390 | 2026-06-15 | BOQ-PKG-10-00420 | PKG-10 | INV-PKG-10-021-06390 | 15.89 | 145479.17 | 7273.96 | Paid | 138205.21 | 2026-Q2
EXP-006741 | 2026-06-15 | BOQ-PKG-01-00771 | PKG-01 | INV-PKG-01-022-06741 | 103.03 | 201451.1 | 10072.56 | Paid | 191378.54 | 2026-Q2
EXP-006785 | 2026-06-15 | BOQ-PKG-05-00815 | PKG-05 | INV-PKG-05-031-06785 | 259.54 | 104074.36 | 5203.72 | Paid | 98870.64 | 2026-Q2
EXP-000002 | 2026-06-16 | BOQ-PKG-02-00002 | PKG-02 | INV-PKG-02-003-00002 | 47.44 | 106594.4 | 5329.72 | Under Review | 101264.68 | 2026-Q2
EXP-001906 | 2026-06-16 | BOQ-PKG-06-01906 | PKG-06 | INV-PKG-06-017-01906 | 250.53 | 170362.44 | 8518.12 | Paid | 161844.32 | 2026-Q2
EXP-002541 | 2026-06-16 | BOQ-PKG-01-00551 | PKG-01 | INV-PKG-01-022-02541 | 283.7 | 40807.66 | 2040.38 | Paid | 38767.28 | 2026-Q2
EXP-002703 | 2026-06-16 | BOQ-PKG-03-00713 | PKG-03 | INV-PKG-03-009-02703 | 8.54 | 189222.04 | 9461.1 | Paid | 179760.94 | 2026-Q2
EXP-003521 | 2026-06-16 | BOQ-PKG-01-01531 | PKG-01 | INV-PKG-01-022-03521 | 283.41 | 58574.31 | 2928.72 | Paid | 55645.59 | 2026-Q2
EXP-003543 | 2026-06-16 | BOQ-PKG-03-01553 | PKG-03 | INV-PKG-03-009-03543 | 334.56 | 76345.99 | 3817.3 | Paid | 72528.69 | 2026-Q2
EXP-004236 | 2026-06-16 | BOQ-PKG-06-00256 | PKG-06 | INV-PKG-06-002-04236 | 327.7 | 75794.92 | 3789.75 | Paid | 72005.17 | 2026-Q2
EXP-004398 | 2026-06-16 | BOQ-PKG-08-00418 | PKG-08 | INV-PKG-08-024-04398 | 34.29 | 160767.03 | 8038.35 | Under Review | 152728.68 | 2026-Q2
EXP-005285 | 2026-06-16 | BOQ-PKG-05-01305 | PKG-05 | INV-PKG-05-001-05285 | 300.59 | 24598.73 | 1229.94 | Approved Pending Payment | 23368.79 | 2026-Q2
EXP-006370 | 2026-06-16 | BOQ-PKG-10-00400 | PKG-10 | INV-PKG-10-001-06370 | 125.8 | 84793.7 | 4239.69 | Paid | 80554.01 | 2026-Q2
EXP-006501 | 2026-06-16 | BOQ-PKG-01-00531 | PKG-01 | INV-PKG-01-027-06501 | 147.69 | 124424.56 | 6221.23 | Approved Pending Payment | 118203.33 | 2026-Q2
EXP-000571 | 2026-06-17 | BOQ-PKG-01-00571 | PKG-01 | INV-PKG-01-012-00571 | 44.61 | 123361.44 | 6168.07 | Under Review | 117193.37 | 2026-Q2
EXP-002750 | 2026-06-17 | BOQ-PKG-10-00760 | PKG-10 | INV-PKG-10-021-02750 | 78.66 | 51036.11 | 2551.81 | Paid | 48484.3 | 2026-Q2
EXP-002786 | 2026-06-17 | BOQ-PKG-06-00796 | PKG-06 | INV-PKG-06-022-02786 | 180.7 | 104522.5 | 5226.12 | Paid | 99296.38 | 2026-Q2
EXP-003011 | 2026-06-17 | BOQ-PKG-01-01021 | PKG-01 | INV-PKG-01-002-03011 | 251.93 | 194444.68 | 9722.23 | Paid | 184722.45 | 2026-Q2
EXP-003241 | 2026-06-17 | BOQ-PKG-01-01251 | PKG-01 | INV-PKG-01-022-03241 | 302.92 | 201410.69 | 10070.53 | Paid | 191340.16 | 2026-Q2
EXP-003641 | 2026-06-17 | BOQ-PKG-01-01651 | PKG-01 | INV-PKG-01-002-03641 | 217.97 | 89148.77 | 4457.44 | Under Review | 84691.33 | 2026-Q2
EXP-005092 | 2026-06-17 | BOQ-PKG-02-01112 | PKG-02 | INV-PKG-02-018-05092 | 296.31 | 45366.05 | 2268.3 | Paid | 43097.75 | 2026-Q2
EXP-005313 | 2026-06-17 | BOQ-PKG-03-01333 | PKG-03 | INV-PKG-03-029-05313 | 290.94 | 185254.72 | 9262.74 | Approved Pending Payment | 175991.98 | 2026-Q2
EXP-006018 | 2026-06-17 | BOQ-PKG-08-00048 | PKG-08 | INV-PKG-08-034-06018 | 230.37 | 164880.27 | 8244.01 | Approved Pending Payment | 156636.26 | 2026-Q2
EXP-006699 | 2026-06-17 | BOQ-PKG-09-00729 | PKG-09 | INV-PKG-09-015-06699 | 430.34 | 182993.16 | 9149.66 | Paid | 173843.5 | 2026-Q2
EXP-000582 | 2026-06-18 | BOQ-PKG-02-00582 | PKG-02 | INV-PKG-02-023-00582 | 97.06 | 88327.31 | 4416.37 | Paid | 83910.94 | 2026-Q2
EXP-001852 | 2026-06-18 | BOQ-PKG-02-01852 | PKG-02 | INV-PKG-02-033-01852 | 110.43 | 159158.24 | 7957.91 | Disputed | 151200.33 | 2026-Q2
EXP-003103 | 2026-06-18 | BOQ-PKG-03-01113 | PKG-03 | INV-PKG-03-024-03103 | 441.78 | 173497.65 | 8674.88 | Paid | 164822.77 | 2026-Q2
EXP-005824 | 2026-06-18 | BOQ-PKG-04-01844 | PKG-04 | INV-PKG-04-015-05824 | 140.26 | 125272.13 | 6263.61 | Paid | 119008.52 | 2026-Q2
EXP-006304 | 2026-06-18 | BOQ-PKG-04-00334 | PKG-04 | INV-PKG-04-005-06304 | 192.39 | 104095.26 | 5204.76 | Paid | 98890.5 | 2026-Q2
EXP-000115 | 2026-06-19 | BOQ-PKG-05-00115 | PKG-05 | INV-PKG-05-011-00115 | 13.96 | 54243.44 | 2712.17 | Paid | 51531.27 | 2026-Q2
EXP-000217 | 2026-06-19 | BOQ-PKG-07-00217 | PKG-07 | INV-PKG-07-008-00217 | 415.58 | 116149.31 | 5807.47 | Approved Pending Payment | 110341.84 | 2026-Q2
EXP-000468 | 2026-06-19 | BOQ-PKG-08-00468 | PKG-08 | INV-PKG-08-014-00468 | 326.97 | 133229.4 | 6661.47 | Paid | 126567.93 | 2026-Q2
EXP-001479 | 2026-06-19 | BOQ-PKG-09-01479 | PKG-09 | INV-PKG-09-010-01479 | 112.62 | 172068.6 | 8603.43 | Under Review | 163465.17 | 2026-Q2
EXP-001889 | 2026-06-19 | BOQ-PKG-09-01889 | PKG-09 | INV-PKG-09-035-01889 | 102.96 | 182778.29 | 9138.91 | Under Review | 173639.38 | 2026-Q2
EXP-002219 | 2026-06-19 | BOQ-PKG-09-00229 | PKG-09 | INV-PKG-09-015-02219 | 105.35 | 133531.34 | 6676.57 | Under Review | 126854.77 | 2026-Q2
EXP-002387 | 2026-06-19 | BOQ-PKG-07-00397 | PKG-07 | INV-PKG-07-008-02387 | 341.29 | 166078.39 | 8303.92 | Approved Pending Payment | 157774.47 | 2026-Q2
EXP-002624 | 2026-06-19 | BOQ-PKG-04-00634 | PKG-04 | INV-PKG-04-035-02624 | 337.45 | 66256.53 | 3312.83 | Paid | 62943.7 | 2026-Q2
EXP-003227 | 2026-06-19 | BOQ-PKG-07-01237 | PKG-07 | INV-PKG-07-008-03227 | 374.68 | 119018.57 | 5950.93 | Paid | 113067.64 | 2026-Q2
EXP-004040 | 2026-06-19 | BOQ-PKG-10-00060 | PKG-10 | INV-PKG-10-016-04040 | 270.17 | 189199.54 | 9459.98 | Paid | 179739.56 | 2026-Q2
EXP-006044 | 2026-06-19 | BOQ-PKG-04-00074 | PKG-04 | INV-PKG-04-025-06044 | 194.85 | 190736.3 | 9536.82 | Paid | 181199.48 | 2026-Q2
EXP-006902 | 2026-06-19 | BOQ-PKG-02-00932 | PKG-02 | INV-PKG-02-008-06902 | 142.18 | 186832.93 | 9341.65 | Under Review | 177491.28 | 2026-Q2
EXP-006912 | 2026-06-19 | BOQ-PKG-02-00942 | PKG-02 | INV-PKG-02-018-06912 | 105.04 | 123667.8 | 6183.39 | Paid | 117484.41 | 2026-Q2
EXP-000015 | 2026-06-20 | BOQ-PKG-05-00015 | PKG-05 | INV-PKG-05-016-00015 | 311.64 | 178434.82 | 8921.74 | Approved Pending Payment | 169513.08 | 2026-Q2
EXP-000054 | 2026-06-20 | BOQ-PKG-04-00054 | PKG-04 | INV-PKG-04-020-00054 | 116.64 | 46733.97 | 2336.7 | Disputed | 44397.27 | 2026-Q2
EXP-000121 | 2026-06-20 | BOQ-PKG-01-00121 | PKG-01 | INV-PKG-01-017-00121 | 140.01 | 173464.93 | 8673.25 | Paid | 164791.68 | 2026-Q2
EXP-000589 | 2026-06-20 | BOQ-PKG-09-00589 | PKG-09 | INV-PKG-09-030-00589 | 26.57 | 63524.85 | 3176.24 | Paid | 60348.61 | 2026-Q2
EXP-001336 | 2026-06-20 | BOQ-PKG-06-01336 | PKG-06 | INV-PKG-06-007-01336 | 197.29 | 124016.15 | 6200.81 | Paid | 117815.34 | 2026-Q2
EXP-002107 | 2026-06-20 | BOQ-PKG-07-00117 | PKG-07 | INV-PKG-07-008-02107 | 341.94 | 42339.35 | 2116.97 | Paid | 40222.38 | 2026-Q2
EXP-006120 | 2026-06-20 | BOQ-PKG-10-00150 | PKG-10 | INV-PKG-10-031-06120 | 267.51 | 67315.66 | 3365.78 | Paid | 63949.88 | 2026-Q2
EXP-000168 | 2026-06-21 | BOQ-PKG-08-00168 | PKG-08 | INV-PKG-08-029-00168 | 409.59 | 182352.82 | 9117.64 | Paid | 173235.18 | 2026-Q2
EXP-002081 | 2026-06-21 | BOQ-PKG-01-00091 | PKG-01 | INV-PKG-01-017-02081 | 265.82 | 77416.76 | 3870.84 | Approved Pending Payment | 73545.92 | 2026-Q2
EXP-003386 | 2026-06-21 | BOQ-PKG-06-01396 | PKG-06 | INV-PKG-06-027-03386 | 354.16 | 145070.49 | 7253.52 | Paid | 137816.97 | 2026-Q2
EXP-003638 | 2026-06-21 | BOQ-PKG-08-01648 | PKG-08 | INV-PKG-08-034-03638 | 106.23 | 97633.17 | 4881.66 | Paid | 92751.51 | 2026-Q2
EXP-003850 | 2026-06-21 | BOQ-PKG-10-01860 | PKG-10 | INV-PKG-10-001-03850 | 197.47 | 30892.3 | 1544.62 | Paid | 29347.68 | 2026-Q2
EXP-004302 | 2026-06-21 | BOQ-PKG-02-00322 | PKG-02 | INV-PKG-02-033-04302 | 234.82 | 109278.18 | 5463.91 | Paid | 103814.27 | 2026-Q2
EXP-004461 | 2026-06-21 | BOQ-PKG-01-00481 | PKG-01 | INV-PKG-01-017-04461 | 179.5 | 111783.67 | 5589.18 | Paid | 106194.49 | 2026-Q2
EXP-005890 | 2026-06-21 | BOQ-PKG-10-01910 | PKG-10 | INV-PKG-10-011-05890 | 283.33 | 114965.73 | 5748.29 | Approved Pending Payment | 109217.44 | 2026-Q2
EXP-005912 | 2026-06-21 | BOQ-PKG-02-01932 | PKG-02 | INV-PKG-02-033-05912 | 16.54 | 64447.57 | 3222.38 | Paid | 61225.19 | 2026-Q2
EXP-001219 | 2026-06-22 | BOQ-PKG-09-01219 | PKG-09 | INV-PKG-09-030-01219 | 364.28 | 140418.2 | 7020.91 | Disputed | 133397.29 | 2026-Q2
EXP-001335 | 2026-06-22 | BOQ-PKG-05-01335 | PKG-05 | INV-PKG-05-006-01335 | 372.99 | 182585.97 | 9129.3 | Paid | 173456.67 | 2026-Q2
EXP-001580 | 2026-06-22 | BOQ-PKG-10-01580 | PKG-10 | INV-PKG-10-006-01580 | 362.39 | 104697.71 | 5234.89 | Approved Pending Payment | 99462.82 | 2026-Q2
EXP-002261 | 2026-06-22 | BOQ-PKG-01-00271 | PKG-01 | INV-PKG-01-022-02261 | 382.37 | 194989.15 | 9749.46 | Paid | 185239.69 | 2026-Q2
EXP-003502 | 2026-06-22 | BOQ-PKG-02-01512 | PKG-02 | INV-PKG-02-003-03502 | 280.01 | 34428.69 | 1721.43 | Paid | 32707.26 | 2026-Q2
EXP-003838 | 2026-06-22 | BOQ-PKG-08-01848 | PKG-08 | INV-PKG-08-024-03838 | 282.4 | 186609.02 | 9330.45 | Paid | 177278.57 | 2026-Q2
EXP-004089 | 2026-06-22 | BOQ-PKG-09-00109 | PKG-09 | INV-PKG-09-030-04089 | 363.16 | 164008.89 | 8200.44 | Paid | 155808.45 | 2026-Q2
EXP-005776 | 2026-06-22 | BOQ-PKG-06-01796 | PKG-06 | INV-PKG-06-002-05776 | 449.38 | 102686.28 | 5134.31 | Paid | 97551.97 | 2026-Q2
EXP-006430 | 2026-06-22 | BOQ-PKG-10-00460 | PKG-10 | INV-PKG-10-026-06430 | 45.55 | 40880.95 | 2044.05 | Paid | 38836.9 | 2026-Q2
EXP-006941 | 2026-06-22 | BOQ-PKG-01-00971 | PKG-01 | INV-PKG-01-012-06941 | 448.81 | 146802.43 | 7340.12 | Paid | 139462.31 | 2026-Q2
EXP-000741 | 2026-06-23 | BOQ-PKG-01-00741 | PKG-01 | INV-PKG-01-007-00741 | 240.79 | 138556.56 | 6927.83 | Paid | 131628.73 | 2026-Q2
EXP-001960 | 2026-06-23 | BOQ-PKG-10-01960 | PKG-10 | INV-PKG-10-001-01960 | 185.46 | 133096.56 | 6654.83 | Paid | 126441.73 | 2026-Q2
EXP-002494 | 2026-06-23 | BOQ-PKG-04-00504 | PKG-04 | INV-PKG-04-010-02494 | 372.88 | 189907.09 | 9495.35 | Paid | 180411.74 | 2026-Q2
EXP-004525 | 2026-06-23 | BOQ-PKG-05-00545 | PKG-05 | INV-PKG-05-011-04525 | 209.45 | 207786.85 | 10389.34 | Approved Pending Payment | 197397.51 | 2026-Q2
EXP-005832 | 2026-06-23 | BOQ-PKG-02-01852 | PKG-02 | INV-PKG-02-023-05832 | 185.4 | 148713.53 | 7435.68 | Approved Pending Payment | 141277.85 | 2026-Q2
EXP-001188 | 2026-06-24 | BOQ-PKG-08-01188 | PKG-08 | INV-PKG-08-034-01188 | 59.52 | 61184.79 | 3059.24 | Paid | 58125.55 | 2026-Q2
EXP-001193 | 2026-06-24 | BOQ-PKG-03-01193 | PKG-03 | INV-PKG-03-004-01193 | 28.98 | 26542.88 | 1327.14 | Paid | 25215.74 | 2026-Q2
EXP-003091 | 2026-06-24 | BOQ-PKG-01-01101 | PKG-01 | INV-PKG-01-012-03091 | 43.18 | 84708.67 | 4235.43 | Paid | 80473.24 | 2026-Q2
EXP-004102 | 2026-06-24 | BOQ-PKG-02-00122 | PKG-02 | INV-PKG-02-008-04102 | 102.93 | 181724.6 | 9086.23 | Disputed | 172638.37 | 2026-Q2
EXP-004627 | 2026-06-24 | BOQ-PKG-07-00647 | PKG-07 | INV-PKG-07-008-04627 | 439.69 | 212563.77 | 10628.19 | Under Review | 201935.58 | 2026-Q2
EXP-004666 | 2026-06-24 | BOQ-PKG-06-00686 | PKG-06 | INV-PKG-06-012-04666 | 406.79 | 199865.15 | 9993.26 | Approved Pending Payment | 189871.89 | 2026-Q2
EXP-005030 | 2026-06-24 | BOQ-PKG-10-01050 | PKG-10 | INV-PKG-10-026-05030 | 127.02 | 63205.63 | 3160.28 | Paid | 60045.35 | 2026-Q2
EXP-005358 | 2026-06-24 | BOQ-PKG-08-01378 | PKG-08 | INV-PKG-08-004-05358 | 178.22 | 67450.8 | 3372.54 | Paid | 64078.26 | 2026-Q2
EXP-006318 | 2026-06-24 | BOQ-PKG-08-00348 | PKG-08 | INV-PKG-08-019-06318 | 164.88 | 202044.42 | 10102.22 | Under Review | 191942.2 | 2026-Q2
EXP-002203 | 2026-06-25 | BOQ-PKG-03-00213 | PKG-03 | INV-PKG-03-034-02203 | 263.09 | 67733.79 | 3386.69 | Approved Pending Payment | 64347.1 | 2026-Q2
EXP-002334 | 2026-06-25 | BOQ-PKG-04-00344 | PKG-04 | INV-PKG-04-025-02334 | 365.11 | 172928.87 | 8646.44 | Paid | 164282.43 | 2026-Q2
EXP-003655 | 2026-06-25 | BOQ-PKG-05-01665 | PKG-05 | INV-PKG-05-016-03655 | 24.29 | 140776.46 | 7038.82 | Paid | 133737.64 | 2026-Q2
EXP-003659 | 2026-06-25 | BOQ-PKG-09-01669 | PKG-09 | INV-PKG-09-020-03659 | 247.64 | 143533.38 | 7176.67 | Under Review | 136356.71 | 2026-Q2
EXP-003837 | 2026-06-25 | BOQ-PKG-07-01847 | PKG-07 | INV-PKG-07-023-03837 | 145.66 | 176362.12 | 8818.11 | Approved Pending Payment | 167544.01 | 2026-Q2
EXP-000194 | 2026-06-26 | BOQ-PKG-04-00194 | PKG-04 | INV-PKG-04-020-00194 | 282.33 | 166289.82 | 8314.49 | Approved Pending Payment | 157975.33 | 2026-Q2
EXP-001503 | 2026-06-26 | BOQ-PKG-03-01503 | PKG-03 | INV-PKG-03-034-01503 | 135.69 | 103837.2 | 5191.86 | Paid | 98645.34 | 2026-Q2
EXP-001804 | 2026-06-26 | BOQ-PKG-04-01804 | PKG-04 | INV-PKG-04-020-01804 | 313.34 | 183987.87 | 9199.39 | Paid | 174788.48 | 2026-Q2
EXP-002891 | 2026-06-26 | BOQ-PKG-01-00901 | PKG-01 | INV-PKG-01-022-02891 | 338.97 | 24672.52 | 1233.63 | Approved Pending Payment | 23438.89 | 2026-Q2
EXP-003374 | 2026-06-26 | BOQ-PKG-04-01384 | PKG-04 | INV-PKG-04-015-03374 | 365.95 | 65295.24 | 3264.76 | Paid | 62030.48 | 2026-Q2
EXP-005157 | 2026-06-26 | BOQ-PKG-07-01177 | PKG-07 | INV-PKG-07-013-05157 | 207.93 | 152142.32 | 7607.12 | Under Review | 144535.2 | 2026-Q2
EXP-000242 | 2026-06-27 | BOQ-PKG-02-00242 | PKG-02 | INV-PKG-02-033-00242 | 306.09 | 94939.99 | 4747 | Paid | 90192.99 | 2026-Q2
EXP-001941 | 2026-06-27 | BOQ-PKG-01-01941 | PKG-01 | INV-PKG-01-017-01941 | 383.04 | 181635.54 | 9081.78 | Approved Pending Payment | 172553.76 | 2026-Q2
EXP-002708 | 2026-06-27 | BOQ-PKG-08-00718 | PKG-08 | INV-PKG-08-014-02708 | 334 | 129202.91 | 6460.15 | Paid | 122742.76 | 2026-Q2
EXP-002973 | 2026-06-27 | BOQ-PKG-03-00983 | PKG-03 | INV-PKG-03-034-02973 | 429.49 | 189585.28 | 9479.26 | Paid | 180106.02 | 2026-Q2
EXP-003770 | 2026-06-27 | BOQ-PKG-10-01780 | PKG-10 | INV-PKG-10-026-03770 | 281.33 | 178482.02 | 8924.1 | Approved Pending Payment | 169557.92 | 2026-Q2
EXP-001070 | 2026-06-28 | BOQ-PKG-10-01070 | PKG-10 | INV-PKG-10-021-01070 | 341.01 | 61980.25 | 3099.01 | Approved Pending Payment | 58881.24 | 2026-Q2
EXP-002321 | 2026-06-28 | BOQ-PKG-01-00331 | PKG-01 | INV-PKG-01-012-02321 | 182.22 | 62721.62 | 3136.08 | Paid | 59585.54 | 2026-Q2
EXP-002777 | 2026-06-28 | BOQ-PKG-07-00787 | PKG-07 | INV-PKG-07-013-02777 | 79.06 | 76386.95 | 3819.35 | Approved Pending Payment | 72567.6 | 2026-Q2
EXP-003389 | 2026-06-28 | BOQ-PKG-09-01399 | PKG-09 | INV-PKG-09-030-03389 | 315.02 | 67209.91 | 3360.5 | Under Review | 63849.41 | 2026-Q2
EXP-006283 | 2026-06-28 | BOQ-PKG-03-00313 | PKG-03 | INV-PKG-03-019-06283 | 412.25 | 192162.3 | 9608.12 | Paid | 182554.18 | 2026-Q2
EXP-006634 | 2026-06-28 | BOQ-PKG-04-00664 | PKG-04 | INV-PKG-04-020-06634 | 162.2 | 210477.3 | 10523.86 | Paid | 199953.44 | 2026-Q2
EXP-000617 | 2026-06-29 | BOQ-PKG-07-00617 | PKG-07 | INV-PKG-07-023-00617 | 236.5 | 153639.6 | 7681.98 | Paid | 145957.62 | 2026-Q2
EXP-000673 | 2026-06-29 | BOQ-PKG-03-00673 | PKG-03 | INV-PKG-03-009-00673 | 181.34 | 153362.09 | 7668.1 | Paid | 145693.99 | 2026-Q2
EXP-001027 | 2026-06-29 | BOQ-PKG-07-01027 | PKG-07 | INV-PKG-07-013-01027 | 239.86 | 124386.88 | 6219.34 | Paid | 118167.54 | 2026-Q2
EXP-002192 | 2026-06-29 | BOQ-PKG-02-00202 | PKG-02 | INV-PKG-02-023-02192 | 349.14 | 178684.12 | 8934.21 | Approved Pending Payment | 169749.91 | 2026-Q2
EXP-003648 | 2026-06-29 | BOQ-PKG-08-01658 | PKG-08 | INV-PKG-08-009-03648 | 31.09 | 164963.43 | 8248.17 | Under Review | 156715.26 | 2026-Q2
EXP-004875 | 2026-06-29 | BOQ-PKG-05-00895 | PKG-05 | INV-PKG-05-011-04875 | 296.04 | 120537.17 | 6026.86 | Approved Pending Payment | 114510.31 | 2026-Q2
EXP-005076 | 2026-06-29 | BOQ-PKG-06-01096 | PKG-06 | INV-PKG-06-002-05076 | 108.4 | 35321.43 | 1766.07 | Approved Pending Payment | 33555.36 | 2026-Q2
EXP-006021 | 2026-06-29 | BOQ-PKG-01-00051 | PKG-01 | INV-PKG-01-002-06021 | 188.57 | 133712.25 | 6685.61 | Paid | 127026.64 | 2026-Q2
EXP-006177 | 2026-06-29 | BOQ-PKG-07-00207 | PKG-07 | INV-PKG-07-018-06177 | 420.88 | 90123.28 | 4506.16 | Paid | 85617.12 | 2026-Q2
EXP-006215 | 2026-06-29 | BOQ-PKG-05-00245 | PKG-05 | INV-PKG-05-021-06215 | 409.24 | 107831.23 | 5391.56 | Paid | 102439.67 | 2026-Q2
EXP-000272 | 2026-06-30 | BOQ-PKG-02-00272 | PKG-02 | INV-PKG-02-028-00272 | 154.02 | 134710.66 | 6735.53 | Paid | 127975.13 | 2026-Q2
EXP-001412 | 2026-06-30 | BOQ-PKG-02-01412 | PKG-02 | INV-PKG-02-013-01412 | 275.78 | 73854.29 | 3692.71 | Approved Pending Payment | 70161.58 | 2026-Q2
EXP-001665 | 2026-06-30 | BOQ-PKG-05-01665 | PKG-05 | INV-PKG-05-021-01665 | 267.33 | 89129.08 | 4456.45 | Under Review | 84672.63 | 2026-Q2
EXP-003439 | 2026-06-30 | BOQ-PKG-09-01449 | PKG-09 | INV-PKG-09-010-03439 | 260.7 | 45859.13 | 2292.96 | Disputed | 43566.17 | 2026-Q2
EXP-005354 | 2026-06-30 | BOQ-PKG-04-01374 | PKG-04 | INV-PKG-04-035-05354 | 41.53 | 45548.18 | 2277.41 | Paid | 43270.77 | 2026-Q2
EXP-005677 | 2026-06-30 | BOQ-PKG-07-01697 | PKG-07 | INV-PKG-07-008-05677 | 207.06 | 38048.02 | 1902.4 | Paid | 36145.62 | 2026-Q2
EXP-000133 | 2026-07-01 | BOQ-PKG-03-00133 | PKG-03 | INV-PKG-03-029-00133 | 144.25 | 178916.39 | 8945.82 | Paid | 169970.57 | 2026-Q3
EXP-000633 | 2026-07-01 | BOQ-PKG-03-00633 | PKG-03 | INV-PKG-03-004-00633 | 64 | 165473.11 | 8273.66 | Under Review | 157199.45 | 2026-Q3
EXP-000649 | 2026-07-01 | BOQ-PKG-09-00649 | PKG-09 | INV-PKG-09-020-00649 | 113.9 | 47751.2 | 2387.56 | Under Review | 45363.64 | 2026-Q3
EXP-000715 | 2026-07-01 | BOQ-PKG-05-00715 | PKG-05 | INV-PKG-05-016-00715 | 186.97 | 147129.4 | 7356.47 | Paid | 139772.93 | 2026-Q3
EXP-001045 | 2026-07-01 | BOQ-PKG-05-01045 | PKG-05 | INV-PKG-05-031-01045 | 202.11 | 135581.35 | 6779.07 | Under Review | 128802.28 | 2026-Q3
EXP-001945 | 2026-07-01 | BOQ-PKG-05-01945 | PKG-05 | INV-PKG-05-021-01945 | 321.8 | 162407.28 | 8120.36 | Paid | 154286.92 | 2026-Q3
EXP-002450 | 2026-07-01 | BOQ-PKG-10-00460 | PKG-10 | INV-PKG-10-001-02450 | 68.98 | 186261.09 | 9313.05 | Approved Pending Payment | 176948.04 | 2026-Q3
EXP-003070 | 2026-07-01 | BOQ-PKG-10-01080 | PKG-10 | INV-PKG-10-026-03070 | 11.13 | 121696.8 | 6084.84 | Paid | 115611.96 | 2026-Q3
EXP-004086 | 2026-07-01 | BOQ-PKG-06-00106 | PKG-06 | INV-PKG-06-027-04086 | 448.91 | 204767.79 | 10238.39 | Paid | 194529.4 | 2026-Q3
EXP-004249 | 2026-07-01 | BOQ-PKG-09-00269 | PKG-09 | INV-PKG-09-015-04249 | 425.77 | 83327.42 | 4166.37 | Paid | 79161.05 | 2026-Q3
EXP-004662 | 2026-07-01 | BOQ-PKG-02-00682 | PKG-02 | INV-PKG-02-008-04662 | 41.82 | 139541.84 | 6977.09 | Paid | 132564.75 | 2026-Q3
EXP-006464 | 2026-07-01 | BOQ-PKG-04-00494 | PKG-04 | INV-PKG-04-025-06464 | 151.65 | 147854.88 | 7392.74 | Paid | 140462.14 | 2026-Q3
EXP-006991 | 2026-07-01 | BOQ-PKG-01-01021 | PKG-01 | INV-PKG-01-027-06991 | 399.51 | 40000.77 | 2000.04 | Disputed | 38000.73 | 2026-Q3
EXP-000603 | 2026-07-02 | BOQ-PKG-03-00603 | PKG-03 | INV-PKG-03-009-00603 | 112.12 | 66495.77 | 3324.79 | Under Review | 63170.98 | 2026-Q3
EXP-000706 | 2026-07-02 | BOQ-PKG-06-00706 | PKG-06 | INV-PKG-06-007-00706 | 189.67 | 85691.86 | 4284.59 | Under Review | 81407.27 | 2026-Q3
EXP-000939 | 2026-07-02 | BOQ-PKG-09-00939 | PKG-09 | INV-PKG-09-030-00939 | 65.49 | 114238.71 | 5711.94 | Paid | 108526.77 | 2026-Q3
EXP-003165 | 2026-07-02 | BOQ-PKG-05-01175 | PKG-05 | INV-PKG-05-016-03165 | 36.93 | 115591.48 | 5779.57 | Paid | 109811.91 | 2026-Q3
EXP-003181 | 2026-07-02 | BOQ-PKG-01-01191 | PKG-01 | INV-PKG-01-032-03181 | 345.53 | 156286.58 | 7814.33 | Paid | 148472.25 | 2026-Q3
EXP-003968 | 2026-07-02 | BOQ-PKG-08-01978 | PKG-08 | INV-PKG-08-014-03968 | 157.57 | 81158.07 | 4057.9 | Approved Pending Payment | 77100.17 | 2026-Q3
EXP-005987 | 2026-07-02 | BOQ-PKG-07-00017 | PKG-07 | INV-PKG-07-003-05987 | 168.39 | 32344.79 | 1617.24 | Paid | 30727.55 | 2026-Q3
EXP-006019 | 2026-07-02 | BOQ-PKG-09-00049 | PKG-09 | INV-PKG-09-035-06019 | 227.29 | 87991.44 | 4399.57 | Under Review | 83591.87 | 2026-Q3
EXP-006998 | 2026-07-02 | BOQ-PKG-08-01028 | PKG-08 | INV-PKG-08-034-06998 | 272.05 | 49467.85 | 2473.39 | Approved Pending Payment | 46994.46 | 2026-Q3
EXP-000247 | 2026-07-03 | BOQ-PKG-07-00247 | PKG-07 | INV-PKG-07-003-00247 | 102.35 | 86549.59 | 4327.48 | Paid | 82222.11 | 2026-Q3
EXP-000446 | 2026-07-03 | BOQ-PKG-06-00446 | PKG-06 | INV-PKG-06-027-00446 | 120.06 | 86234 | 4311.7 | Paid | 81922.3 | 2026-Q3
EXP-002395 | 2026-07-03 | BOQ-PKG-05-00405 | PKG-05 | INV-PKG-05-016-02395 | 56.53 | 85202.09 | 4260.1 | Paid | 80941.99 | 2026-Q3
EXP-003431 | 2026-07-03 | BOQ-PKG-01-01441 | PKG-01 | INV-PKG-01-002-03431 | 11.12 | 107387.72 | 5369.39 | Paid | 102018.33 | 2026-Q3
EXP-003976 | 2026-07-03 | BOQ-PKG-06-01986 | PKG-06 | INV-PKG-06-022-03976 | 371.79 | 200305.39 | 10015.27 | Paid | 190290.12 | 2026-Q3
EXP-004016 | 2026-07-03 | BOQ-PKG-06-00036 | PKG-06 | INV-PKG-06-027-04016 | 246.57 | 36325.49 | 1816.27 | Paid | 34509.22 | 2026-Q3
EXP-005037 | 2026-07-03 | BOQ-PKG-07-01057 | PKG-07 | INV-PKG-07-033-05037 | 405.96 | 155972.17 | 7798.61 | Paid | 148173.56 | 2026-Q3
EXP-005337 | 2026-07-03 | BOQ-PKG-07-01357 | PKG-07 | INV-PKG-07-018-05337 | 44.97 | 205317.18 | 10265.86 | Paid | 195051.32 | 2026-Q3
EXP-006000 | 2026-07-03 | BOQ-PKG-10-00030 | PKG-10 | INV-PKG-10-016-06000 | 56.48 | 61682.74 | 3084.14 | Under Review | 58598.6 | 2026-Q3
EXP-000419 | 2026-07-04 | BOQ-PKG-09-00419 | PKG-09 | INV-PKG-09-035-00419 | 140.77 | 55294.78 | 2764.74 | Paid | 52530.04 | 2026-Q3
EXP-001083 | 2026-07-04 | BOQ-PKG-03-01083 | PKG-03 | INV-PKG-03-034-01083 | 449.38 | 69098.01 | 3454.9 | Paid | 65643.11 | 2026-Q3
EXP-001406 | 2026-07-04 | BOQ-PKG-06-01406 | PKG-06 | INV-PKG-06-007-01406 | 290.46 | 190257.24 | 9512.86 | Paid | 180744.38 | 2026-Q3
EXP-003454 | 2026-07-04 | BOQ-PKG-04-01464 | PKG-04 | INV-PKG-04-025-03454 | 423.76 | 56285.72 | 2814.29 | Paid | 53471.43 | 2026-Q3
EXP-005371 | 2026-07-04 | BOQ-PKG-01-01391 | PKG-01 | INV-PKG-01-017-05371 | 295.98 | 196528.3 | 9826.41 | Approved Pending Payment | 186701.89 | 2026-Q3
EXP-000795 | 2026-07-05 | BOQ-PKG-05-00795 | PKG-05 | INV-PKG-05-026-00795 | 33.15 | 131791.67 | 6589.58 | Under Review | 125202.09 | 2026-Q3
EXP-000928 | 2026-07-05 | BOQ-PKG-08-00928 | PKG-08 | INV-PKG-08-019-00928 | 431.46 | 40578.24 | 2028.91 | Paid | 38549.33 | 2026-Q3
EXP-001377 | 2026-07-05 | BOQ-PKG-07-01377 | PKG-07 | INV-PKG-07-013-01377 | 156.09 | 44152.17 | 2207.61 | Paid | 41944.56 | 2026-Q3
EXP-002812 | 2026-07-05 | BOQ-PKG-02-00822 | PKG-02 | INV-PKG-02-013-02812 | 212.03 | 157710.18 | 7885.51 | Paid | 149824.67 | 2026-Q3
EXP-000070 | 2026-07-06 | BOQ-PKG-10-00070 | PKG-10 | INV-PKG-10-001-00070 | 14.82 | 200663.48 | 10033.17 | Approved Pending Payment | 190630.31 | 2026-Q3
EXP-001016 | 2026-07-06 | BOQ-PKG-06-01016 | PKG-06 | INV-PKG-06-002-01016 | 387.31 | 65114.8 | 3255.74 | Paid | 61859.06 | 2026-Q3
EXP-002089 | 2026-07-06 | BOQ-PKG-09-00099 | PKG-09 | INV-PKG-09-025-02089 | 244.56 | 144712.87 | 7235.64 | Paid | 137477.23 | 2026-Q3
EXP-003134 | 2026-07-06 | BOQ-PKG-04-01144 | PKG-04 | INV-PKG-04-020-03134 | 54.93 | 180750.59 | 9037.53 | Paid | 171713.06 | 2026-Q3
EXP-003351 | 2026-07-06 | BOQ-PKG-01-01361 | PKG-01 | INV-PKG-01-027-03351 | 229.74 | 111596.01 | 5579.8 | Paid | 106016.21 | 2026-Q3
EXP-003583 | 2026-07-06 | BOQ-PKG-03-01593 | PKG-03 | INV-PKG-03-014-03583 | 31.32 | 213436.39 | 10671.82 | Paid | 202764.57 | 2026-Q3
EXP-003672 | 2026-07-06 | BOQ-PKG-02-01682 | PKG-02 | INV-PKG-02-033-03672 | 405.21 | 55245.04 | 2762.25 | Under Review | 52482.79 | 2026-Q3
EXP-004226 | 2026-07-06 | BOQ-PKG-06-00246 | PKG-06 | INV-PKG-06-027-04226 | 40.23 | 137007.59 | 6850.38 | Paid | 130157.21 | 2026-Q3
EXP-005209 | 2026-07-06 | BOQ-PKG-09-01229 | PKG-09 | INV-PKG-09-030-05209 | 199.05 | 105557.42 | 5277.87 | Approved Pending Payment | 100279.55 | 2026-Q3
EXP-000132 | 2026-07-07 | BOQ-PKG-02-00132 | PKG-02 | INV-PKG-02-028-00132 | 151.33 | 150511.19 | 7525.56 | Approved Pending Payment | 142985.63 | 2026-Q3
EXP-000189 | 2026-07-07 | BOQ-PKG-09-00189 | PKG-09 | INV-PKG-09-015-00189 | 333.38 | 139527.22 | 6976.36 | Paid | 132550.86 | 2026-Q3
EXP-000400 | 2026-07-07 | BOQ-PKG-10-00400 | PKG-10 | INV-PKG-10-016-00400 | 27.19 | 52080.29 | 2604.01 | Paid | 49476.28 | 2026-Q3
EXP-001456 | 2026-07-07 | BOQ-PKG-06-01456 | PKG-06 | INV-PKG-06-022-01456 | 16.07 | 97220.86 | 4861.04 | Paid | 92359.82 | 2026-Q3
EXP-001474 | 2026-07-07 | BOQ-PKG-04-01474 | PKG-04 | INV-PKG-04-005-01474 | 426.11 | 49703.03 | 2485.15 | Under Review | 47217.88 | 2026-Q3
EXP-001617 | 2026-07-07 | BOQ-PKG-07-01617 | PKG-07 | INV-PKG-07-008-01617 | 357.88 | 133505.9 | 6675.3 | Under Review | 126830.6 | 2026-Q3
EXP-001764 | 2026-07-07 | BOQ-PKG-04-01764 | PKG-04 | INV-PKG-04-015-01764 | 371.59 | 115306.4 | 5765.32 | Paid | 109541.08 | 2026-Q3
EXP-002077 | 2026-07-07 | BOQ-PKG-07-00087 | PKG-07 | INV-PKG-07-013-02077 | 356.6 | 151200.9 | 7560.04 | Paid | 143640.86 | 2026-Q3
EXP-002632 | 2026-07-07 | BOQ-PKG-02-00642 | PKG-02 | INV-PKG-02-008-02632 | 255.65 | 158077.58 | 7903.88 | Approved Pending Payment | 150173.7 | 2026-Q3
EXP-002861 | 2026-07-07 | BOQ-PKG-01-00871 | PKG-01 | INV-PKG-01-027-02861 | 122.53 | 40234.43 | 2011.72 | Approved Pending Payment | 38222.71 | 2026-Q3
EXP-004532 | 2026-07-07 | BOQ-PKG-02-00552 | PKG-02 | INV-PKG-02-018-04532 | 298.21 | 24721.04 | 1236.05 | Paid | 23484.99 | 2026-Q3
EXP-005204 | 2026-07-07 | BOQ-PKG-04-01224 | PKG-04 | INV-PKG-04-025-05204 | 337.78 | 27356.37 | 1367.82 | Paid | 25988.55 | 2026-Q3
EXP-005458 | 2026-07-07 | BOQ-PKG-08-01478 | PKG-08 | INV-PKG-08-034-05458 | 230.69 | 105715.7 | 5285.78 | Paid | 100429.92 | 2026-Q3
EXP-005764 | 2026-07-07 | BOQ-PKG-04-01784 | PKG-04 | INV-PKG-04-025-05764 | 264.35 | 112671.09 | 5633.55 | Paid | 107037.54 | 2026-Q3
EXP-006199 | 2026-07-07 | BOQ-PKG-09-00229 | PKG-09 | INV-PKG-09-005-06199 | 203.34 | 101390.33 | 5069.52 | Paid | 96320.81 | 2026-Q3
EXP-001423 | 2026-07-08 | BOQ-PKG-03-01423 | PKG-03 | INV-PKG-03-024-01423 | 358.58 | 30995.9 | 1549.8 | Paid | 29446.1 | 2026-Q3
EXP-001833 | 2026-07-08 | BOQ-PKG-03-01833 | PKG-03 | INV-PKG-03-014-01833 | 130.41 | 92220.87 | 4611.04 | Paid | 87609.83 | 2026-Q3
EXP-002587 | 2026-07-08 | BOQ-PKG-07-00597 | PKG-07 | INV-PKG-07-033-02587 | 300.74 | 195063.16 | 9753.16 | Paid | 185310 | 2026-Q3
EXP-005429 | 2026-07-08 | BOQ-PKG-09-01449 | PKG-09 | INV-PKG-09-005-05429 | 345.45 | 205769.53 | 10288.48 | Paid | 195481.05 | 2026-Q3
EXP-006016 | 2026-07-08 | BOQ-PKG-06-00046 | PKG-06 | INV-PKG-06-032-06016 | 150.81 | 53025.41 | 2651.27 | Approved Pending Payment | 50374.14 | 2026-Q3
EXP-006124 | 2026-07-08 | BOQ-PKG-04-00154 | PKG-04 | INV-PKG-04-035-06124 | 396.84 | 200973.23 | 10048.66 | Under Review | 190924.57 | 2026-Q3
EXP-006198 | 2026-07-08 | BOQ-PKG-08-00228 | PKG-08 | INV-PKG-08-004-06198 | 324.62 | 166623.07 | 8331.15 | Under Review | 158291.92 | 2026-Q3
EXP-006257 | 2026-07-08 | BOQ-PKG-07-00287 | PKG-07 | INV-PKG-07-028-06257 | 313.61 | 131391.69 | 6569.58 | Paid | 124822.11 | 2026-Q3
EXP-000748 | 2026-07-09 | BOQ-PKG-08-00748 | PKG-08 | INV-PKG-08-014-00748 | 104.35 | 195005.33 | 9750.27 | Disputed | 185255.06 | 2026-Q3
EXP-001098 | 2026-07-09 | BOQ-PKG-08-01098 | PKG-08 | INV-PKG-08-014-01098 | 416.98 | 193893.3 | 9694.66 | Paid | 184198.64 | 2026-Q3
EXP-001950 | 2026-07-09 | BOQ-PKG-10-01950 | PKG-10 | INV-PKG-10-026-01950 | 445.76 | 170469.81 | 8523.49 | Paid | 161946.32 | 2026-Q3
EXP-002969 | 2026-07-09 | BOQ-PKG-09-00979 | PKG-09 | INV-PKG-09-030-02969 | 128.96 | 110153.91 | 5507.7 | Paid | 104646.21 | 2026-Q3
EXP-003450 | 2026-07-09 | BOQ-PKG-10-01460 | PKG-10 | INV-PKG-10-021-03450 | 205.61 | 46701.35 | 2335.07 | Paid | 44366.28 | 2026-Q3
EXP-004710 | 2026-07-09 | BOQ-PKG-10-00730 | PKG-10 | INV-PKG-10-021-04710 | 268.89 | 140136.71 | 7006.84 | Paid | 133129.87 | 2026-Q3
EXP-000173 | 2026-07-10 | BOQ-PKG-03-00173 | PKG-03 | INV-PKG-03-034-00173 | 429.37 | 86510.38 | 4325.52 | Paid | 82184.86 | 2026-Q3
EXP-001692 | 2026-07-10 | BOQ-PKG-02-01692 | PKG-02 | INV-PKG-02-013-01692 | 220.09 | 83725.98 | 4186.3 | Paid | 79539.68 | 2026-Q3
EXP-003557 | 2026-07-10 | BOQ-PKG-07-01567 | PKG-07 | INV-PKG-07-023-03557 | 179.45 | 120801.79 | 6040.09 | Paid | 114761.7 | 2026-Q3
EXP-003872 | 2026-07-10 | BOQ-PKG-02-01882 | PKG-02 | INV-PKG-02-023-03872 | 188.53 | 177758.34 | 8887.92 | Paid | 168870.42 | 2026-Q3
EXP-005357 | 2026-07-10 | BOQ-PKG-07-01377 | PKG-07 | INV-PKG-07-003-05357 | 6.83 | 162645.34 | 8132.27 | Approved Pending Payment | 154513.07 | 2026-Q3
EXP-006424 | 2026-07-10 | BOQ-PKG-04-00454 | PKG-04 | INV-PKG-04-020-06424 | 138.59 | 108826.22 | 5441.31 | Approved Pending Payment | 103384.91 | 2026-Q3
EXP-002023 | 2026-07-11 | BOQ-PKG-03-00033 | PKG-03 | INV-PKG-03-029-02023 | 179.12 | 106142.22 | 5307.11 | Paid | 100835.11 | 2026-Q3
EXP-003463 | 2026-07-11 | BOQ-PKG-03-01473 | PKG-03 | INV-PKG-03-034-03463 | 143.11 | 83454.44 | 4172.72 | Approved Pending Payment | 79281.72 | 2026-Q3
EXP-003525 | 2026-07-11 | BOQ-PKG-05-01535 | PKG-05 | INV-PKG-05-026-03525 | 390.94 | 154471.79 | 7723.59 | Paid | 146748.2 | 2026-Q3
EXP-001862 | 2026-07-12 | BOQ-PKG-02-01862 | PKG-02 | INV-PKG-02-008-01862 | 396.18 | 97841.44 | 4892.07 | Paid | 92949.37 | 2026-Q3
EXP-004011 | 2026-07-12 | BOQ-PKG-01-00031 | PKG-01 | INV-PKG-01-022-04011 | 83.84 | 50715.69 | 2535.78 | Paid | 48179.91 | 2026-Q3
EXP-004566 | 2026-07-12 | BOQ-PKG-06-00586 | PKG-06 | INV-PKG-06-017-04566 | 81.94 | 109544.14 | 5477.21 | Paid | 104066.93 | 2026-Q3
EXP-004862 | 2026-07-12 | BOQ-PKG-02-00882 | PKG-02 | INV-PKG-02-033-04862 | 301.18 | 44171.58 | 2208.58 | Paid | 41963 | 2026-Q3
EXP-005253 | 2026-07-12 | BOQ-PKG-03-01273 | PKG-03 | INV-PKG-03-004-05253 | 159 | 192715.85 | 9635.79 | Under Review | 183080.06 | 2026-Q3
EXP-005562 | 2026-07-12 | BOQ-PKG-02-01582 | PKG-02 | INV-PKG-02-033-05562 | 284.56 | 34545.73 | 1727.29 | Paid | 32818.44 | 2026-Q3
EXP-006922 | 2026-07-12 | BOQ-PKG-02-00952 | PKG-02 | INV-PKG-02-028-06922 | 89.54 | 76885.23 | 3844.26 | Paid | 73040.97 | 2026-Q3
EXP-001858 | 2026-07-13 | BOQ-PKG-08-01858 | PKG-08 | INV-PKG-08-004-01858 | 14.54 | 167669.59 | 8383.48 | Under Review | 159286.11 | 2026-Q3
EXP-002595 | 2026-07-13 | BOQ-PKG-05-00605 | PKG-05 | INV-PKG-05-006-02595 | 42.01 | 149443.95 | 7472.2 | Disputed | 141971.75 | 2026-Q3
EXP-004194 | 2026-07-13 | BOQ-PKG-04-00214 | PKG-04 | INV-PKG-04-030-04194 | 22 | 192076.15 | 9603.81 | Under Review | 182472.34 | 2026-Q3
EXP-005160 | 2026-07-13 | BOQ-PKG-10-01180 | PKG-10 | INV-PKG-10-016-05160 | 152.2 | 166409.93 | 8320.5 | Paid | 158089.43 | 2026-Q3
EXP-005672 | 2026-07-13 | BOQ-PKG-02-01692 | PKG-02 | INV-PKG-02-003-05672 | 383.47 | 176841.09 | 8842.05 | Paid | 167999.04 | 2026-Q3
EXP-006001 | 2026-07-13 | BOQ-PKG-01-00031 | PKG-01 | INV-PKG-01-017-06001 | 121.5 | 79753.17 | 3987.66 | Paid | 75765.51 | 2026-Q3
EXP-006647 | 2026-07-13 | BOQ-PKG-07-00677 | PKG-07 | INV-PKG-07-033-06647 | 409.57 | 69662.95 | 3483.15 | Paid | 66179.8 | 2026-Q3
EXP-001332 | 2026-07-14 | BOQ-PKG-02-01332 | PKG-02 | INV-PKG-02-003-01332 | 202.56 | 168163.02 | 8408.15 | Paid | 159754.87 | 2026-Q3
EXP-001361 | 2026-07-14 | BOQ-PKG-01-01361 | PKG-01 | INV-PKG-01-032-01361 | 228.57 | 198309.47 | 9915.47 | Approved Pending Payment | 188394 | 2026-Q3
EXP-001607 | 2026-07-14 | BOQ-PKG-07-01607 | PKG-07 | INV-PKG-07-033-01607 | 151.47 | 194506.17 | 9725.31 | Paid | 184780.86 | 2026-Q3
EXP-001892 | 2026-07-14 | BOQ-PKG-02-01892 | PKG-02 | INV-PKG-02-003-01892 | 154.1 | 174015 | 8700.75 | Paid | 165314.25 | 2026-Q3
EXP-002872 | 2026-07-14 | BOQ-PKG-02-00882 | PKG-02 | INV-PKG-02-003-02872 | 346.8 | 62220.4 | 3111.02 | Paid | 59109.38 | 2026-Q3
EXP-004213 | 2026-07-14 | BOQ-PKG-03-00233 | PKG-03 | INV-PKG-03-014-04213 | 274.43 | 117698.85 | 5884.94 | Paid | 111813.91 | 2026-Q3
EXP-005806 | 2026-07-14 | BOQ-PKG-06-01826 | PKG-06 | INV-PKG-06-032-05806 | 146.83 | 142219.72 | 7110.99 | Paid | 135108.73 | 2026-Q3
EXP-006418 | 2026-07-14 | BOQ-PKG-08-00448 | PKG-08 | INV-PKG-08-014-06418 | 165.94 | 79630.2 | 3981.51 | Paid | 75648.69 | 2026-Q3
EXP-002305 | 2026-07-15 | BOQ-PKG-05-00315 | PKG-05 | INV-PKG-05-031-02305 | 311.34 | 95129.24 | 4756.46 | Paid | 90372.78 | 2026-Q3
EXP-003304 | 2026-07-15 | BOQ-PKG-04-01314 | PKG-04 | INV-PKG-04-015-03304 | 185.2 | 28890.71 | 1444.54 | Paid | 27446.17 | 2026-Q3
EXP-006108 | 2026-07-15 | BOQ-PKG-08-00138 | PKG-08 | INV-PKG-08-019-06108 | 258.38 | 112121.54 | 5606.08 | Paid | 106515.46 | 2026-Q3
EXP-006292 | 2026-07-15 | BOQ-PKG-02-00322 | PKG-02 | INV-PKG-02-028-06292 | 45.55 | 139269.1 | 6963.46 | Under Review | 132305.64 | 2026-Q3
EXP-001030 | 2026-07-16 | BOQ-PKG-10-01030 | PKG-10 | INV-PKG-10-016-01030 | 190.02 | 138404.89 | 6920.24 | Under Review | 131484.65 | 2026-Q3
EXP-002072 | 2026-07-16 | BOQ-PKG-02-00082 | PKG-02 | INV-PKG-02-008-02072 | 262.42 | 206252.82 | 10312.64 | Paid | 195940.18 | 2026-Q3
EXP-004052 | 2026-07-16 | BOQ-PKG-02-00072 | PKG-02 | INV-PKG-02-028-04052 | 345.09 | 86597.13 | 4329.86 | Paid | 82267.27 | 2026-Q3
EXP-004221 | 2026-07-16 | BOQ-PKG-01-00241 | PKG-01 | INV-PKG-01-022-04221 | 439.41 | 159092.48 | 7954.62 | Paid | 151137.86 | 2026-Q3
EXP-004926 | 2026-07-16 | BOQ-PKG-06-00946 | PKG-06 | INV-PKG-06-027-04926 | 112.41 | 167192.12 | 8359.61 | Paid | 158832.51 | 2026-Q3
EXP-005238 | 2026-07-16 | BOQ-PKG-08-01258 | PKG-08 | INV-PKG-08-024-05238 | 387.93 | 187320.35 | 9366.02 | Paid | 177954.33 | 2026-Q3
EXP-000406 | 2026-07-17 | BOQ-PKG-06-00406 | PKG-06 | INV-PKG-06-022-00406 | 235.67 | 37921.59 | 1896.08 | Paid | 36025.51 | 2026-Q3
EXP-000837 | 2026-07-17 | BOQ-PKG-07-00837 | PKG-07 | INV-PKG-07-033-00837 | 61.36 | 102321.45 | 5116.07 | Paid | 97205.38 | 2026-Q3
EXP-000897 | 2026-07-17 | BOQ-PKG-07-00897 | PKG-07 | INV-PKG-07-023-00897 | 406.16 | 76190.88 | 3809.54 | Disputed | 72381.34 | 2026-Q3
EXP-003155 | 2026-07-18 | BOQ-PKG-05-01165 | PKG-05 | INV-PKG-05-006-03155 | 75.39 | 33944.83 | 1697.24 | Disputed | 32247.59 | 2026-Q3
EXP-003946 | 2026-07-18 | BOQ-PKG-06-01956 | PKG-06 | INV-PKG-06-027-03946 | 69.74 | 199207.74 | 9960.39 | Paid | 189247.35 | 2026-Q3
EXP-004260 | 2026-07-18 | BOQ-PKG-10-00280 | PKG-10 | INV-PKG-10-026-04260 | 161.81 | 159075.06 | 7953.75 | Paid | 151121.31 | 2026-Q3
EXP-005478 | 2026-07-18 | BOQ-PKG-08-01498 | PKG-08 | INV-PKG-08-019-05478 | 442.43 | 143944.46 | 7197.22 | Paid | 136747.24 | 2026-Q3
EXP-006736 | 2026-07-18 | BOQ-PKG-06-00766 | PKG-06 | INV-PKG-06-017-06736 | 81.24 | 169689.11 | 8484.46 | Paid | 161204.65 | 2026-Q3
EXP-005056 | 2026-07-19 | BOQ-PKG-06-01076 | PKG-06 | INV-PKG-06-017-05056 | 17.35 | 154191.16 | 7709.56 | Paid | 146481.6 | 2026-Q3
EXP-005305 | 2026-07-19 | BOQ-PKG-05-01325 | PKG-05 | INV-PKG-05-021-05305 | 348.53 | 28701.09 | 1435.05 | Approved Pending Payment | 27266.04 | 2026-Q3
EXP-005540 | 2026-07-19 | BOQ-PKG-10-01560 | PKG-10 | INV-PKG-10-011-05540 | 175.56 | 196405.17 | 9820.26 | Paid | 186584.91 | 2026-Q3
EXP-005950 | 2026-07-19 | BOQ-PKG-10-01970 | PKG-10 | INV-PKG-10-001-05950 | 5 | 85893.47 | 4294.67 | Paid | 81598.8 | 2026-Q3
EXP-006583 | 2026-07-19 | BOQ-PKG-03-00613 | PKG-03 | INV-PKG-03-004-06583 | 7.6 | 126119.18 | 6305.96 | Paid | 119813.22 | 2026-Q3
EXP-000122 | 2026-07-20 | BOQ-PKG-02-00122 | PKG-02 | INV-PKG-02-018-00122 | 180.13 | 48994.28 | 2449.71 | Approved Pending Payment | 46544.57 | 2026-Q3
EXP-001150 | 2026-07-20 | BOQ-PKG-10-01150 | PKG-10 | INV-PKG-10-031-01150 | 370.36 | 60590.13 | 3029.51 | Paid | 57560.62 | 2026-Q3
EXP-001567 | 2026-07-20 | BOQ-PKG-07-01567 | PKG-07 | INV-PKG-07-028-01567 | 423.68 | 58552.32 | 2927.62 | Paid | 55624.7 | 2026-Q3
EXP-002165 | 2026-07-20 | BOQ-PKG-05-00175 | PKG-05 | INV-PKG-05-031-02165 | 365.13 | 193895.83 | 9694.79 | Paid | 184201.04 | 2026-Q3
EXP-003216 | 2026-07-20 | BOQ-PKG-06-01226 | PKG-06 | INV-PKG-06-032-03216 | 107 | 52399.82 | 2619.99 | Paid | 49779.83 | 2026-Q3
EXP-003598 | 2026-07-20 | BOQ-PKG-08-01608 | PKG-08 | INV-PKG-08-029-03598 | 207.3 | 176311.68 | 8815.58 | Paid | 167496.1 | 2026-Q3
EXP-003813 | 2026-07-20 | BOQ-PKG-03-01823 | PKG-03 | INV-PKG-03-034-03813 | 95.05 | 159667.49 | 7983.37 | Paid | 151684.12 | 2026-Q3
EXP-004892 | 2026-07-20 | BOQ-PKG-02-00912 | PKG-02 | INV-PKG-02-028-04892 | 50.96 | 109161.67 | 5458.08 | Paid | 103703.59 | 2026-Q3
EXP-000667 | 2026-07-21 | BOQ-PKG-07-00667 | PKG-07 | INV-PKG-07-003-00667 | 239.33 | 79696.69 | 3984.83 | Paid | 75711.86 | 2026-Q3
EXP-001143 | 2026-07-21 | BOQ-PKG-03-01143 | PKG-03 | INV-PKG-03-024-01143 | 200.2 | 100024.8 | 5001.24 | Paid | 95023.56 | 2026-Q3
EXP-001254 | 2026-07-21 | BOQ-PKG-04-01254 | PKG-04 | INV-PKG-04-030-01254 | 76.23 | 177423.87 | 8871.19 | Paid | 168552.68 | 2026-Q3
EXP-001372 | 2026-07-21 | BOQ-PKG-02-01372 | PKG-02 | INV-PKG-02-008-01372 | 260.85 | 192345.38 | 9617.27 | Paid | 182728.11 | 2026-Q3
EXP-001719 | 2026-07-21 | BOQ-PKG-09-01719 | PKG-09 | INV-PKG-09-005-01719 | 366.08 | 43108.11 | 2155.41 | Paid | 40952.7 | 2026-Q3
EXP-002566 | 2026-07-21 | BOQ-PKG-06-00576 | PKG-06 | INV-PKG-06-012-02566 | 200.39 | 204899.11 | 10244.96 | Paid | 194654.15 | 2026-Q3
EXP-002586 | 2026-07-21 | BOQ-PKG-06-00596 | PKG-06 | INV-PKG-06-032-02586 | 166.54 | 36662.89 | 1833.14 | Paid | 34829.75 | 2026-Q3
EXP-002678 | 2026-07-21 | BOQ-PKG-08-00688 | PKG-08 | INV-PKG-08-019-02678 | 328.56 | 211793.21 | 10589.66 | Paid | 201203.55 | 2026-Q3
EXP-003399 | 2026-07-21 | BOQ-PKG-09-01409 | PKG-09 | INV-PKG-09-005-03399 | 312.99 | 73135.82 | 3656.79 | Paid | 69479.03 | 2026-Q3
EXP-005132 | 2026-07-21 | BOQ-PKG-02-01152 | PKG-02 | INV-PKG-02-023-05132 | 130.78 | 51841.83 | 2592.09 | Paid | 49249.74 | 2026-Q3
EXP-006662 | 2026-07-21 | BOQ-PKG-02-00692 | PKG-02 | INV-PKG-02-013-06662 | 401.4 | 152633.57 | 7631.68 | Paid | 145001.89 | 2026-Q3
EXP-000476 | 2026-07-22 | BOQ-PKG-06-00476 | PKG-06 | INV-PKG-06-022-00476 | 245.55 | 113306.64 | 5665.33 | Paid | 107641.31 | 2026-Q3
EXP-001597 | 2026-07-22 | BOQ-PKG-07-01597 | PKG-07 | INV-PKG-07-023-01597 | 381.99 | 79827.49 | 3991.37 | Paid | 75836.12 | 2026-Q3
EXP-002447 | 2026-07-22 | BOQ-PKG-07-00457 | PKG-07 | INV-PKG-07-033-02447 | 50.17 | 116214.36 | 5810.72 | Paid | 110403.64 | 2026-Q3
EXP-003855 | 2026-07-22 | BOQ-PKG-05-01865 | PKG-05 | INV-PKG-05-006-03855 | 48.2 | 191651.48 | 9582.57 | Paid | 182068.91 | 2026-Q3
EXP-003948 | 2026-07-22 | BOQ-PKG-08-01958 | PKG-08 | INV-PKG-08-029-03948 | 353.59 | 64774.62 | 3238.73 | Paid | 61535.89 | 2026-Q3
EXP-004019 | 2026-07-22 | BOQ-PKG-09-00039 | PKG-09 | INV-PKG-09-030-04019 | 44.57 | 109226.5 | 5461.33 | Paid | 103765.17 | 2026-Q3
EXP-004621 | 2026-07-22 | BOQ-PKG-01-00641 | PKG-01 | INV-PKG-01-002-04621 | 395.27 | 76398.65 | 3819.93 | Paid | 72578.72 | 2026-Q3
EXP-005880 | 2026-07-22 | BOQ-PKG-10-01900 | PKG-10 | INV-PKG-10-001-05880 | 399.9 | 85491.36 | 4274.57 | Paid | 81216.79 | 2026-Q3
EXP-006358 | 2026-07-22 | BOQ-PKG-08-00388 | PKG-08 | INV-PKG-08-024-06358 | 351.65 | 76755.77 | 3837.79 | Paid | 72917.98 | 2026-Q3
EXP-006451 | 2026-07-22 | BOQ-PKG-01-00481 | PKG-01 | INV-PKG-01-012-06451 | 413.52 | 46128.28 | 2306.41 | Paid | 43821.87 | 2026-Q3
EXP-000863 | 2026-07-23 | BOQ-PKG-03-00863 | PKG-03 | INV-PKG-03-024-00863 | 313.48 | 36273.81 | 1813.69 | Approved Pending Payment | 34460.12 | 2026-Q3
EXP-001652 | 2026-07-23 | BOQ-PKG-02-01652 | PKG-02 | INV-PKG-02-008-01652 | 348.46 | 189151.91 | 9457.6 | Disputed | 179694.31 | 2026-Q3
EXP-002097 | 2026-07-23 | BOQ-PKG-07-00107 | PKG-07 | INV-PKG-07-033-02097 | 349.17 | 66875.44 | 3343.77 | Disputed | 63531.67 | 2026-Q3
EXP-002151 | 2026-07-23 | BOQ-PKG-01-00161 | PKG-01 | INV-PKG-01-017-02151 | 60.79 | 54662.03 | 2733.1 | Paid | 51928.93 | 2026-Q3
EXP-002608 | 2026-07-23 | BOQ-PKG-08-00618 | PKG-08 | INV-PKG-08-019-02608 | 147.14 | 42021.58 | 2101.08 | Approved Pending Payment | 39920.5 | 2026-Q3
EXP-002742 | 2026-07-23 | BOQ-PKG-02-00752 | PKG-02 | INV-PKG-02-013-02742 | 74.76 | 186092.23 | 9304.61 | Approved Pending Payment | 176787.62 | 2026-Q3
EXP-006845 | 2026-07-23 | BOQ-PKG-05-00875 | PKG-05 | INV-PKG-05-021-06845 | 87.54 | 124871.5 | 6243.58 | Under Review | 118627.92 | 2026-Q3
EXP-000227 | 2026-07-24 | BOQ-PKG-07-00227 | PKG-07 | INV-PKG-07-018-00227 | 389.96 | 138254.45 | 6912.72 | Paid | 131341.73 | 2026-Q3
EXP-001378 | 2026-07-24 | BOQ-PKG-08-01378 | PKG-08 | INV-PKG-08-014-01378 | 22.21 | 164949.79 | 8247.49 | Paid | 156702.3 | 2026-Q3
EXP-002472 | 2026-07-24 | BOQ-PKG-02-00482 | PKG-02 | INV-PKG-02-023-02472 | 158.38 | 89574.3 | 4478.72 | Paid | 85095.58 | 2026-Q3
EXP-003533 | 2026-07-24 | BOQ-PKG-03-01543 | PKG-03 | INV-PKG-03-034-03533 | 270.79 | 68221.29 | 3411.06 | Paid | 64810.23 | 2026-Q3
EXP-003739 | 2026-07-24 | BOQ-PKG-09-01749 | PKG-09 | INV-PKG-09-030-03739 | 352.45 | 77084.89 | 3854.24 | Paid | 73230.65 | 2026-Q3
EXP-004597 | 2026-07-24 | BOQ-PKG-07-00617 | PKG-07 | INV-PKG-07-013-04597 | 256.71 | 48037.48 | 2401.87 | Paid | 45635.61 | 2026-Q3
EXP-006133 | 2026-07-24 | BOQ-PKG-03-00163 | PKG-03 | INV-PKG-03-009-06133 | 388.05 | 126522.53 | 6326.13 | Under Review | 120196.4 | 2026-Q3
EXP-006516 | 2026-07-24 | BOQ-PKG-06-00546 | PKG-06 | INV-PKG-06-007-06516 | 411.1 | 104100.76 | 5205.04 | Approved Pending Payment | 98895.72 | 2026-Q3
EXP-006737 | 2026-07-24 | BOQ-PKG-07-00767 | PKG-07 | INV-PKG-07-018-06737 | 362.15 | 143869.92 | 7193.5 | Disputed | 136676.42 | 2026-Q3
EXP-001511 | 2026-07-25 | BOQ-PKG-01-01511 | PKG-01 | INV-PKG-01-007-01511 | 42.24 | 186578.11 | 9328.91 | Paid | 177249.2 | 2026-Q3
EXP-002638 | 2026-07-25 | BOQ-PKG-08-00648 | PKG-08 | INV-PKG-08-014-02638 | 302.01 | 210755.34 | 10537.77 | Paid | 200217.57 | 2026-Q3
EXP-002765 | 2026-07-25 | BOQ-PKG-05-00775 | PKG-05 | INV-PKG-05-001-02765 | 424.83 | 72022.11 | 3601.11 | Under Review | 68421 | 2026-Q3
EXP-002823 | 2026-07-25 | BOQ-PKG-03-00833 | PKG-03 | INV-PKG-03-024-02823 | 260.39 | 47249.33 | 2362.47 | Paid | 44886.86 | 2026-Q3
EXP-002995 | 2026-07-25 | BOQ-PKG-05-01005 | PKG-05 | INV-PKG-05-021-02995 | 62.69 | 194096.3 | 9704.82 | Paid | 184391.48 | 2026-Q3
EXP-003033 | 2026-07-25 | BOQ-PKG-03-01043 | PKG-03 | INV-PKG-03-024-03033 | 323.85 | 152109.84 | 7605.49 | Paid | 144504.35 | 2026-Q3
EXP-003072 | 2026-07-25 | BOQ-PKG-02-01082 | PKG-02 | INV-PKG-02-028-03072 | 231.9 | 144048.64 | 7202.43 | Paid | 136846.21 | 2026-Q3
EXP-003396 | 2026-07-25 | BOQ-PKG-06-01406 | PKG-06 | INV-PKG-06-002-03396 | 314.55 | 197451.8 | 9872.59 | Paid | 187579.21 | 2026-Q3
EXP-003544 | 2026-07-25 | BOQ-PKG-04-01554 | PKG-04 | INV-PKG-04-010-03544 | 235.2 | 188943.07 | 9447.15 | Under Review | 179495.92 | 2026-Q3
EXP-003893 | 2026-07-25 | BOQ-PKG-03-01903 | PKG-03 | INV-PKG-03-009-03893 | 373.04 | 211486.03 | 10574.3 | Approved Pending Payment | 200911.73 | 2026-Q3
EXP-003987 | 2026-07-25 | BOQ-PKG-07-00007 | PKG-07 | INV-PKG-07-033-03987 | 395.83 | 45455.8 | 2272.79 | Paid | 43183.01 | 2026-Q3
EXP-004501 | 2026-07-25 | BOQ-PKG-01-00521 | PKG-01 | INV-PKG-01-022-04501 | 312.23 | 42202.44 | 2110.12 | Paid | 40092.32 | 2026-Q3
EXP-004610 | 2026-07-25 | BOQ-PKG-10-00630 | PKG-10 | INV-PKG-10-026-04610 | 366.99 | 43095.83 | 2154.79 | Paid | 40941.04 | 2026-Q3
EXP-005636 | 2026-07-25 | BOQ-PKG-06-01656 | PKG-06 | INV-PKG-06-002-05636 | 188.17 | 64735.25 | 3236.76 | Paid | 61498.49 | 2026-Q3
EXP-000650 | 2026-07-26 | BOQ-PKG-10-00650 | PKG-10 | INV-PKG-10-021-00650 | 387.4 | 46038.03 | 2301.9 | Paid | 43736.13 | 2026-Q3
EXP-001225 | 2026-07-26 | BOQ-PKG-05-01225 | PKG-05 | INV-PKG-05-001-01225 | 279.81 | 204547.16 | 10227.36 | Paid | 194319.8 | 2026-Q3
EXP-001936 | 2026-07-26 | BOQ-PKG-06-01936 | PKG-06 | INV-PKG-06-012-01936 | 165.86 | 95249.09 | 4762.45 | Paid | 90486.64 | 2026-Q3
EXP-002746 | 2026-07-26 | BOQ-PKG-06-00756 | PKG-06 | INV-PKG-06-017-02746 | 332.4 | 27630.14 | 1381.51 | Paid | 26248.63 | 2026-Q3
EXP-003486 | 2026-07-26 | BOQ-PKG-06-01496 | PKG-06 | INV-PKG-06-022-03486 | 386.42 | 166314.09 | 8315.7 | Paid | 157998.39 | 2026-Q3
EXP-003773 | 2026-07-26 | BOQ-PKG-03-01783 | PKG-03 | INV-PKG-03-029-03773 | 391.44 | 144396.66 | 7219.83 | Under Review | 137176.83 | 2026-Q3
EXP-004705 | 2026-07-26 | BOQ-PKG-05-00725 | PKG-05 | INV-PKG-05-016-04705 | 68.32 | 187791.49 | 9389.57 | Paid | 178401.92 | 2026-Q3
EXP-006379 | 2026-07-26 | BOQ-PKG-09-00409 | PKG-09 | INV-PKG-09-010-06379 | 71.87 | 190808.69 | 9540.43 | Paid | 181268.26 | 2026-Q3
EXP-000778 | 2026-07-27 | BOQ-PKG-08-00778 | PKG-08 | INV-PKG-08-009-00778 | 91.2 | 87522.47 | 4376.12 | Paid | 83146.35 | 2026-Q3
EXP-003068 | 2026-07-27 | BOQ-PKG-08-01078 | PKG-08 | INV-PKG-08-024-03068 | 7.51 | 215800.56 | 10790.03 | Disputed | 205010.53 | 2026-Q3
EXP-003137 | 2026-07-27 | BOQ-PKG-07-01147 | PKG-07 | INV-PKG-07-023-03137 | 38.64 | 24335.68 | 1216.78 | Paid | 23118.9 | 2026-Q3
EXP-003303 | 2026-07-27 | BOQ-PKG-03-01313 | PKG-03 | INV-PKG-03-014-03303 | 42.6 | 37002.61 | 1850.13 | Approved Pending Payment | 35152.48 | 2026-Q3
EXP-004065 | 2026-07-27 | BOQ-PKG-05-00085 | PKG-05 | INV-PKG-05-006-04065 | 285.06 | 179890.54 | 8994.53 | Paid | 170896.01 | 2026-Q3
EXP-004435 | 2026-07-27 | BOQ-PKG-05-00455 | PKG-05 | INV-PKG-05-026-04435 | 182.72 | 63324.7 | 3166.24 | Paid | 60158.46 | 2026-Q3
EXP-006210 | 2026-07-27 | BOQ-PKG-10-00240 | PKG-10 | INV-PKG-10-016-06210 | 27.08 | 82388.9 | 4119.44 | Disputed | 78269.46 | 2026-Q3
EXP-001805 | 2026-07-28 | BOQ-PKG-05-01805 | PKG-05 | INV-PKG-05-021-01805 | 12.64 | 198809.62 | 9940.48 | Paid | 188869.14 | 2026-Q3
EXP-003628 | 2026-07-28 | BOQ-PKG-08-01638 | PKG-08 | INV-PKG-08-024-03628 | 404.75 | 86215.66 | 4310.78 | Approved Pending Payment | 81904.88 | 2026-Q3
EXP-005007 | 2026-07-28 | BOQ-PKG-07-01027 | PKG-07 | INV-PKG-07-003-05007 | 369.64 | 37495.85 | 1874.79 | Paid | 35621.06 | 2026-Q3
EXP-005342 | 2026-07-28 | BOQ-PKG-02-01362 | PKG-02 | INV-PKG-02-023-05342 | 421.47 | 138371.44 | 6918.57 | Approved Pending Payment | 131452.87 | 2026-Q3
EXP-000203 | 2026-07-29 | BOQ-PKG-03-00203 | PKG-03 | INV-PKG-03-029-00203 | 260.24 | 88746.34 | 4437.32 | Paid | 84309.02 | 2026-Q3
EXP-000319 | 2026-07-29 | BOQ-PKG-09-00319 | PKG-09 | INV-PKG-09-005-00319 | 34.05 | 179418.07 | 8970.9 | Paid | 170447.17 | 2026-Q3
EXP-001897 | 2026-07-29 | BOQ-PKG-07-01897 | PKG-07 | INV-PKG-07-008-01897 | 86.23 | 93167.89 | 4658.39 | Paid | 88509.5 | 2026-Q3
EXP-002641 | 2026-07-29 | BOQ-PKG-01-00651 | PKG-01 | INV-PKG-01-017-02641 | 290.7 | 108431.16 | 5421.56 | Paid | 103009.6 | 2026-Q3
EXP-002975 | 2026-07-29 | BOQ-PKG-05-00985 | PKG-05 | INV-PKG-05-001-02975 | 30.54 | 49693.47 | 2484.67 | Paid | 47208.8 | 2026-Q3
EXP-003395 | 2026-07-29 | BOQ-PKG-05-01405 | PKG-05 | INV-PKG-05-001-03395 | 444.79 | 174096.42 | 8704.82 | Paid | 165391.6 | 2026-Q3
EXP-003572 | 2026-07-29 | BOQ-PKG-02-01582 | PKG-02 | INV-PKG-02-003-03572 | 313.43 | 98931.48 | 4946.57 | Paid | 93984.91 | 2026-Q3
EXP-003962 | 2026-07-29 | BOQ-PKG-02-01972 | PKG-02 | INV-PKG-02-008-03962 | 300.83 | 105503.06 | 5275.15 | Paid | 100227.91 | 2026-Q3
EXP-004250 | 2026-07-29 | BOQ-PKG-10-00270 | PKG-10 | INV-PKG-10-016-04250 | 217.54 | 172125.73 | 8606.29 | Paid | 163519.44 | 2026-Q3
EXP-006871 | 2026-07-29 | BOQ-PKG-01-00901 | PKG-01 | INV-PKG-01-012-06871 | 404.67 | 216397.87 | 10819.89 | Paid | 205577.98 | 2026-Q3
EXP-000427 | 2026-07-30 | BOQ-PKG-07-00427 | PKG-07 | INV-PKG-07-008-00427 | 172.44 | 197015.85 | 9850.79 | Paid | 187165.06 | 2026-Q3
EXP-001247 | 2026-07-30 | BOQ-PKG-07-01247 | PKG-07 | INV-PKG-07-023-01247 | 152.39 | 46346.12 | 2317.31 | Under Review | 44028.81 | 2026-Q3
EXP-001267 | 2026-07-30 | BOQ-PKG-07-01267 | PKG-07 | INV-PKG-07-008-01267 | 130.16 | 194893.41 | 9744.67 | Paid | 185148.74 | 2026-Q3
EXP-002052 | 2026-07-30 | BOQ-PKG-02-00062 | PKG-02 | INV-PKG-02-023-02052 | 422.89 | 74759.65 | 3737.98 | Paid | 71021.67 | 2026-Q3
EXP-002435 | 2026-07-30 | BOQ-PKG-05-00445 | PKG-05 | INV-PKG-05-021-02435 | 253.24 | 127510.98 | 6375.55 | Paid | 121135.43 | 2026-Q3
EXP-002534 | 2026-07-30 | BOQ-PKG-04-00544 | PKG-04 | INV-PKG-04-015-02534 | 426.47 | 88321.48 | 4416.07 | Paid | 83905.41 | 2026-Q3
EXP-003726 | 2026-07-30 | BOQ-PKG-06-01736 | PKG-06 | INV-PKG-06-017-03726 | 373.37 | 211830.08 | 10591.5 | Paid | 201238.58 | 2026-Q3
EXP-005687 | 2026-07-30 | BOQ-PKG-07-01707 | PKG-07 | INV-PKG-07-018-05687 | 247.14 | 104629.64 | 5231.48 | Disputed | 99398.16 | 2026-Q3
EXP-006185 | 2026-07-30 | BOQ-PKG-05-00215 | PKG-05 | INV-PKG-05-026-06185 | 303.24 | 151985.95 | 7599.3 | Disputed | 144386.65 | 2026-Q3
EXP-000201 | 2026-07-31 | BOQ-PKG-01-00201 | PKG-01 | INV-PKG-01-027-00201 | 112.85 | 151711.29 | 7585.56 | Paid | 144125.73 | 2026-Q3
EXP-003800 | 2026-07-31 | BOQ-PKG-10-01810 | PKG-10 | INV-PKG-10-021-03800 | 364.19 | 76752.22 | 3837.61 | Approved Pending Payment | 72914.61 | 2026-Q3
EXP-003857 | 2026-07-31 | BOQ-PKG-07-01867 | PKG-07 | INV-PKG-07-008-03857 | 54.6 | 107432.55 | 5371.63 | Approved Pending Payment | 102060.92 | 2026-Q3
EXP-005180 | 2026-07-31 | BOQ-PKG-10-01200 | PKG-10 | INV-PKG-10-001-05180 | 354.66 | 166583.29 | 8329.16 | Paid | 158254.13 | 2026-Q3
EXP-005867 | 2026-07-31 | BOQ-PKG-07-01887 | PKG-07 | INV-PKG-07-023-05867 | 40.07 | 161275.4 | 8063.77 | Paid | 153211.63 | 2026-Q3
EXP-000094 | 2026-08-01 | BOQ-PKG-04-00094 | PKG-04 | INV-PKG-04-025-00094 | 85.5 | 170901.49 | 8545.07 | Approved Pending Payment | 162356.42 | 2026-Q3
EXP-000664 | 2026-08-01 | BOQ-PKG-04-00664 | PKG-04 | INV-PKG-04-035-00664 | 75.54 | 113730.36 | 5686.52 | Paid | 108043.84 | 2026-Q3
EXP-000904 | 2026-08-01 | BOQ-PKG-04-00904 | PKG-04 | INV-PKG-04-030-00904 | 447.46 | 124379.3 | 6218.96 | Paid | 118160.34 | 2026-Q3
EXP-001264 | 2026-08-01 | BOQ-PKG-04-01264 | PKG-04 | INV-PKG-04-005-01264 | 393.98 | 87741.45 | 4387.07 | Approved Pending Payment | 83354.38 | 2026-Q3
EXP-001689 | 2026-08-01 | BOQ-PKG-09-01689 | PKG-09 | INV-PKG-09-010-01689 | 198.32 | 51889.43 | 2594.47 | Paid | 49294.96 | 2026-Q3
EXP-003558 | 2026-08-01 | BOQ-PKG-08-01568 | PKG-08 | INV-PKG-08-024-03558 | 448.89 | 167322.88 | 8366.14 | Paid | 158956.74 | 2026-Q3
EXP-003941 | 2026-08-01 | BOQ-PKG-01-01951 | PKG-01 | INV-PKG-01-022-03941 | 447.02 | 133769.54 | 6688.48 | Paid | 127081.06 | 2026-Q3
EXP-004076 | 2026-08-01 | BOQ-PKG-06-00096 | PKG-06 | INV-PKG-06-017-04076 | 324.18 | 71210.23 | 3560.51 | Paid | 67649.72 | 2026-Q3
EXP-005925 | 2026-08-01 | BOQ-PKG-05-01945 | PKG-05 | INV-PKG-05-011-05925 | 400.38 | 170653.74 | 8532.69 | Paid | 162121.05 | 2026-Q3
EXP-006294 | 2026-08-01 | BOQ-PKG-04-00324 | PKG-04 | INV-PKG-04-030-06294 | 239.04 | 73030.84 | 3651.54 | Paid | 69379.3 | 2026-Q3
EXP-000253 | 2026-08-02 | BOQ-PKG-03-00253 | PKG-03 | INV-PKG-03-009-00253 | 192.23 | 121434.87 | 6071.74 | Paid | 115363.13 | 2026-Q3
EXP-000813 | 2026-08-02 | BOQ-PKG-03-00813 | PKG-03 | INV-PKG-03-009-00813 | 124.38 | 32096.03 | 1604.8 | Paid | 30491.23 | 2026-Q3
EXP-002243 | 2026-08-02 | BOQ-PKG-03-00253 | PKG-03 | INV-PKG-03-004-02243 | 37.68 | 75399.4 | 3769.97 | Paid | 71629.43 | 2026-Q3
EXP-002424 | 2026-08-02 | BOQ-PKG-04-00434 | PKG-04 | INV-PKG-04-010-02424 | 224.73 | 96662.06 | 4833.1 | Approved Pending Payment | 91828.96 | 2026-Q3
EXP-003044 | 2026-08-02 | BOQ-PKG-04-01054 | PKG-04 | INV-PKG-04-035-03044 | 83.86 | 85083.59 | 4254.18 | Paid | 80829.41 | 2026-Q3
EXP-005034 | 2026-08-02 | BOQ-PKG-04-01054 | PKG-04 | INV-PKG-04-030-05034 | 73.3 | 197350.29 | 9867.51 | Paid | 187482.78 | 2026-Q3
EXP-006104 | 2026-08-02 | BOQ-PKG-04-00134 | PKG-04 | INV-PKG-04-015-06104 | 194.64 | 173342.61 | 8667.13 | Paid | 164675.48 | 2026-Q3
EXP-006525 | 2026-08-02 | BOQ-PKG-05-00555 | PKG-05 | INV-PKG-05-016-06525 | 193.41 | 59701.21 | 2985.06 | Approved Pending Payment | 56716.15 | 2026-Q3
EXP-003607 | 2026-08-03 | BOQ-PKG-07-01617 | PKG-07 | INV-PKG-07-003-03607 | 318.98 | 126239.24 | 6311.96 | Paid | 119927.28 | 2026-Q3
EXP-004494 | 2026-08-03 | BOQ-PKG-04-00514 | PKG-04 | INV-PKG-04-015-04494 | 288.96 | 58292.61 | 2914.63 | Under Review | 55377.98 | 2026-Q3
EXP-004638 | 2026-08-03 | BOQ-PKG-08-00658 | PKG-08 | INV-PKG-08-019-04638 | 349.34 | 121166.39 | 6058.32 | Paid | 115108.07 | 2026-Q3
EXP-005260 | 2026-08-03 | BOQ-PKG-10-01280 | PKG-10 | INV-PKG-10-011-05260 | 159.65 | 176659.03 | 8832.95 | Paid | 167826.08 | 2026-Q3
EXP-006489 | 2026-08-03 | BOQ-PKG-09-00519 | PKG-09 | INV-PKG-09-015-06489 | 298.58 | 87794 | 4389.7 | Disputed | 83404.3 | 2026-Q3
EXP-006874 | 2026-08-03 | BOQ-PKG-04-00904 | PKG-04 | INV-PKG-04-015-06874 | 278.95 | 102483.06 | 5124.15 | Paid | 97358.91 | 2026-Q3
EXP-000175 | 2026-08-04 | BOQ-PKG-05-00175 | PKG-05 | INV-PKG-05-001-00175 | 174.82 | 166603.67 | 8330.18 | Paid | 158273.49 | 2026-Q3
EXP-000952 | 2026-08-04 | BOQ-PKG-02-00952 | PKG-02 | INV-PKG-02-008-00952 | 179.04 | 37622.35 | 1881.12 | Paid | 35741.23 | 2026-Q3
EXP-001657 | 2026-08-04 | BOQ-PKG-07-01657 | PKG-07 | INV-PKG-07-013-01657 | 187.91 | 161253.15 | 8062.66 | Approved Pending Payment | 153190.49 | 2026-Q3
EXP-002520 | 2026-08-04 | BOQ-PKG-10-00530 | PKG-10 | INV-PKG-10-001-02520 | 330.28 | 176272.89 | 8813.64 | Paid | 167459.25 | 2026-Q3
EXP-002684 | 2026-08-04 | BOQ-PKG-04-00694 | PKG-04 | INV-PKG-04-025-02684 | 173.92 | 139375.82 | 6968.79 | Disputed | 132407.03 | 2026-Q3
EXP-003273 | 2026-08-04 | BOQ-PKG-03-01283 | PKG-03 | INV-PKG-03-019-03273 | 130.38 | 102711.63 | 5135.58 | Under Review | 97576.05 | 2026-Q3
EXP-003346 | 2026-08-04 | BOQ-PKG-06-01356 | PKG-06 | INV-PKG-06-022-03346 | 349.77 | 107943.03 | 5397.15 | Under Review | 102545.88 | 2026-Q3
EXP-004332 | 2026-08-04 | BOQ-PKG-02-00352 | PKG-02 | INV-PKG-02-028-04332 | 366.74 | 185573.32 | 9278.67 | Paid | 176294.65 | 2026-Q3
EXP-004918 | 2026-08-04 | BOQ-PKG-08-00938 | PKG-08 | INV-PKG-08-019-04918 | 376.76 | 101996.53 | 5099.83 | Paid | 96896.7 | 2026-Q3
EXP-005961 | 2026-08-04 | BOQ-PKG-01-01981 | PKG-01 | INV-PKG-01-012-05961 | 38.11 | 117604.09 | 5880.2 | Paid | 111723.89 | 2026-Q3
EXP-006448 | 2026-08-04 | BOQ-PKG-08-00478 | PKG-08 | INV-PKG-08-009-06448 | 405.37 | 60335.29 | 3016.76 | Paid | 57318.53 | 2026-Q3
EXP-006714 | 2026-08-04 | BOQ-PKG-04-00744 | PKG-04 | INV-PKG-04-030-06714 | 138.38 | 78829.67 | 3941.48 | Approved Pending Payment | 74888.19 | 2026-Q3
EXP-000799 | 2026-08-05 | BOQ-PKG-09-00799 | PKG-09 | INV-PKG-09-030-00799 | 288.49 | 55837.65 | 2791.88 | Paid | 53045.77 | 2026-Q3
EXP-001706 | 2026-08-05 | BOQ-PKG-06-01706 | PKG-06 | INV-PKG-06-027-01706 | 301.11 | 197800.73 | 9890.04 | Under Review | 187910.69 | 2026-Q3
EXP-002476 | 2026-08-05 | BOQ-PKG-06-00486 | PKG-06 | INV-PKG-06-027-02476 | 30.81 | 131321.39 | 6566.07 | Approved Pending Payment | 124755.32 | 2026-Q3
EXP-002695 | 2026-08-05 | BOQ-PKG-05-00705 | PKG-05 | INV-PKG-05-001-02695 | 74.73 | 120989.07 | 6049.45 | Paid | 114939.62 | 2026-Q3
EXP-003354 | 2026-08-05 | BOQ-PKG-04-01364 | PKG-04 | INV-PKG-04-030-03354 | 143.74 | 58271.22 | 2913.56 | Paid | 55357.66 | 2026-Q3
EXP-003277 | 2026-08-06 | BOQ-PKG-07-01287 | PKG-07 | INV-PKG-07-023-03277 | 140.23 | 87617.47 | 4380.87 | Paid | 83236.6 | 2026-Q3
EXP-003534 | 2026-08-06 | BOQ-PKG-04-01544 | PKG-04 | INV-PKG-04-035-03534 | 382.03 | 29848.02 | 1492.4 | Approved Pending Payment | 28355.62 | 2026-Q3
EXP-003554 | 2026-08-06 | BOQ-PKG-04-01564 | PKG-04 | INV-PKG-04-020-03554 | 134.83 | 102970.68 | 5148.53 | Paid | 97822.15 | 2026-Q3
EXP-005686 | 2026-08-06 | BOQ-PKG-06-01706 | PKG-06 | INV-PKG-06-017-05686 | 272.39 | 153699.44 | 7684.97 | Approved Pending Payment | 146014.47 | 2026-Q3
EXP-000238 | 2026-08-07 | BOQ-PKG-08-00238 | PKG-08 | INV-PKG-08-029-00238 | 98.05 | 47155 | 2357.75 | Approved Pending Payment | 44797.25 | 2026-Q3
EXP-003737 | 2026-08-07 | BOQ-PKG-07-01747 | PKG-07 | INV-PKG-07-028-03737 | 234 | 164784.06 | 8239.2 | Approved Pending Payment | 156544.86 | 2026-Q3
EXP-004189 | 2026-08-07 | BOQ-PKG-09-00209 | PKG-09 | INV-PKG-09-025-04189 | 208.03 | 46667.39 | 2333.37 | Paid | 44334.02 | 2026-Q3
EXP-005264 | 2026-08-07 | BOQ-PKG-04-01284 | PKG-04 | INV-PKG-04-015-05264 | 184.09 | 175605.48 | 8780.27 | Paid | 166825.21 | 2026-Q3
EXP-005347 | 2026-08-07 | BOQ-PKG-07-01367 | PKG-07 | INV-PKG-07-028-05347 | 31.53 | 137789.46 | 6889.47 | Paid | 130899.99 | 2026-Q3
EXP-005482 | 2026-08-07 | BOQ-PKG-02-01502 | PKG-02 | INV-PKG-02-023-05482 | 445.05 | 138654.35 | 6932.72 | Under Review | 131721.63 | 2026-Q3
EXP-005870 | 2026-08-07 | BOQ-PKG-10-01890 | PKG-10 | INV-PKG-10-026-05870 | 395.09 | 87753.4 | 4387.67 | Paid | 83365.73 | 2026-Q3
EXP-006600 | 2026-08-07 | BOQ-PKG-10-00630 | PKG-10 | INV-PKG-10-021-06600 | 265.91 | 30031.45 | 1501.57 | Under Review | 28529.88 | 2026-Q3
EXP-001533 | 2026-08-08 | BOQ-PKG-03-01533 | PKG-03 | INV-PKG-03-029-01533 | 370.4 | 107025.86 | 5351.29 | Paid | 101674.57 | 2026-Q3
EXP-001691 | 2026-08-08 | BOQ-PKG-01-01691 | PKG-01 | INV-PKG-01-012-01691 | 26.83 | 190388.16 | 9519.41 | Paid | 180868.75 | 2026-Q3
EXP-002994 | 2026-08-08 | BOQ-PKG-04-01004 | PKG-04 | INV-PKG-04-020-02994 | 30.29 | 158967.73 | 7948.39 | Paid | 151019.34 | 2026-Q3
EXP-004280 | 2026-08-08 | BOQ-PKG-10-00300 | PKG-10 | INV-PKG-10-011-04280 | 361.01 | 188988.08 | 9449.4 | Paid | 179538.68 | 2026-Q3
EXP-004483 | 2026-08-08 | BOQ-PKG-03-00503 | PKG-03 | INV-PKG-03-004-04483 | 379.64 | 104878.98 | 5243.95 | Paid | 99635.03 | 2026-Q3
EXP-004854 | 2026-08-08 | BOQ-PKG-04-00874 | PKG-04 | INV-PKG-04-025-04854 | 89.46 | 141950.31 | 7097.52 | Paid | 134852.79 | 2026-Q3
EXP-005823 | 2026-08-08 | BOQ-PKG-03-01843 | PKG-03 | INV-PKG-03-014-05823 | 66.36 | 34211.45 | 1710.57 | Paid | 32500.88 | 2026-Q3
EXP-001579 | 2026-08-09 | BOQ-PKG-09-01579 | PKG-09 | INV-PKG-09-005-01579 | 182.13 | 86745.83 | 4337.29 | Approved Pending Payment | 82408.54 | 2026-Q3
EXP-003917 | 2026-08-09 | BOQ-PKG-07-01927 | PKG-07 | INV-PKG-07-033-03917 | 384.84 | 99500.33 | 4975.02 | Paid | 94525.31 | 2026-Q3
EXP-004383 | 2026-08-09 | BOQ-PKG-03-00403 | PKG-03 | INV-PKG-03-009-04383 | 131.97 | 125509.98 | 6275.5 | Paid | 119234.48 | 2026-Q3
EXP-005333 | 2026-08-09 | BOQ-PKG-03-01353 | PKG-03 | INV-PKG-03-014-05333 | 14.6 | 150846.25 | 7542.31 | Paid | 143303.94 | 2026-Q3
EXP-006166 | 2026-08-09 | BOQ-PKG-06-00196 | PKG-06 | INV-PKG-06-007-06166 | 162.4 | 121767.98 | 6088.4 | Paid | 115679.58 | 2026-Q3
EXP-006730 | 2026-08-09 | BOQ-PKG-10-00760 | PKG-10 | INV-PKG-10-011-06730 | 15.36 | 92570.79 | 4628.54 | Paid | 87942.25 | 2026-Q3
EXP-000012 | 2026-08-10 | BOQ-PKG-02-00012 | PKG-02 | INV-PKG-02-013-00012 | 439.89 | 174303.02 | 8715.15 | Paid | 165587.87 | 2026-Q3
EXP-000261 | 2026-08-10 | BOQ-PKG-01-00261 | PKG-01 | INV-PKG-01-017-00261 | 220.93 | 59147.92 | 2957.4 | Paid | 56190.52 | 2026-Q3
EXP-000302 | 2026-08-10 | BOQ-PKG-02-00302 | PKG-02 | INV-PKG-02-023-00302 | 105.2 | 148868.61 | 7443.43 | Under Review | 141425.18 | 2026-Q3
EXP-000489 | 2026-08-10 | BOQ-PKG-09-00489 | PKG-09 | INV-PKG-09-035-00489 | 212.05 | 34163.02 | 1708.15 | Paid | 32454.87 | 2026-Q3
EXP-001885 | 2026-08-10 | BOQ-PKG-05-01885 | PKG-05 | INV-PKG-05-031-01885 | 298.18 | 91949.94 | 4597.5 | Paid | 87352.44 | 2026-Q3
EXP-005546 | 2026-08-10 | BOQ-PKG-06-01566 | PKG-06 | INV-PKG-06-017-05546 | 20.28 | 109053.97 | 5452.7 | Paid | 103601.27 | 2026-Q3
EXP-005716 | 2026-08-10 | BOQ-PKG-06-01736 | PKG-06 | INV-PKG-06-012-05716 | 277.34 | 99616.31 | 4980.82 | Paid | 94635.49 | 2026-Q3
EXP-006437 | 2026-08-10 | BOQ-PKG-07-00467 | PKG-07 | INV-PKG-07-033-06437 | 390.18 | 192415.91 | 9620.8 | Paid | 182795.11 | 2026-Q3
EXP-000668 | 2026-08-11 | BOQ-PKG-08-00668 | PKG-08 | INV-PKG-08-004-00668 | 22.48 | 145561 | 7278.05 | Under Review | 138282.95 | 2026-Q3
EXP-001588 | 2026-08-11 | BOQ-PKG-08-01588 | PKG-08 | INV-PKG-08-014-01588 | 393.96 | 206031.92 | 10301.6 | Approved Pending Payment | 195730.32 | 2026-Q3
EXP-002496 | 2026-08-11 | BOQ-PKG-06-00506 | PKG-06 | INV-PKG-06-012-02496 | 305.28 | 161338.32 | 8066.92 | Paid | 153271.4 | 2026-Q3
EXP-002880 | 2026-08-11 | BOQ-PKG-10-00890 | PKG-10 | INV-PKG-10-011-02880 | 374.78 | 135609.11 | 6780.46 | Paid | 128828.65 | 2026-Q3
EXP-003239 | 2026-08-11 | BOQ-PKG-09-01249 | PKG-09 | INV-PKG-09-020-03239 | 37.05 | 31526.41 | 1576.32 | Paid | 29950.09 | 2026-Q3
EXP-004537 | 2026-08-11 | BOQ-PKG-07-00557 | PKG-07 | INV-PKG-07-023-04537 | 73.26 | 137769.13 | 6888.46 | Paid | 130880.67 | 2026-Q3
EXP-005418 | 2026-08-11 | BOQ-PKG-08-01438 | PKG-08 | INV-PKG-08-029-05418 | 50.24 | 178056.17 | 8902.81 | Paid | 169153.36 | 2026-Q3
EXP-005844 | 2026-08-11 | BOQ-PKG-04-01864 | PKG-04 | INV-PKG-04-035-05844 | 81.15 | 24401.94 | 1220.1 | Under Review | 23181.84 | 2026-Q3
EXP-000278 | 2026-08-12 | BOQ-PKG-08-00278 | PKG-08 | INV-PKG-08-034-00278 | 277.05 | 95189.77 | 4759.49 | Paid | 90430.28 | 2026-Q3
EXP-000724 | 2026-08-12 | BOQ-PKG-04-00724 | PKG-04 | INV-PKG-04-025-00724 | 98.19 | 27155.32 | 1357.77 | Paid | 25797.55 | 2026-Q3
EXP-001442 | 2026-08-12 | BOQ-PKG-02-01442 | PKG-02 | INV-PKG-02-008-01442 | 45.34 | 146000.62 | 7300.03 | Paid | 138700.59 | 2026-Q3
EXP-002265 | 2026-08-12 | BOQ-PKG-05-00275 | PKG-05 | INV-PKG-05-026-02265 | 218.08 | 65951.71 | 3297.59 | Paid | 62654.12 | 2026-Q3
EXP-002672 | 2026-08-12 | BOQ-PKG-02-00682 | PKG-02 | INV-PKG-02-013-02672 | 8.25 | 71413.81 | 3570.69 | Paid | 67843.12 | 2026-Q3
EXP-003578 | 2026-08-12 | BOQ-PKG-08-01588 | PKG-08 | INV-PKG-08-009-03578 | 231.61 | 45463.13 | 2273.16 | Paid | 43189.97 | 2026-Q3
EXP-003999 | 2026-08-12 | BOQ-PKG-09-00019 | PKG-09 | INV-PKG-09-010-03999 | 242.5 | 78855.15 | 3942.76 | Paid | 74912.39 | 2026-Q3
EXP-005532 | 2026-08-12 | BOQ-PKG-02-01552 | PKG-02 | INV-PKG-02-003-05532 | 365.23 | 51237.99 | 2561.9 | Paid | 48676.09 | 2026-Q3
EXP-005736 | 2026-08-12 | BOQ-PKG-06-01756 | PKG-06 | INV-PKG-06-032-05736 | 323.76 | 100863.64 | 5043.18 | Paid | 95820.46 | 2026-Q3
EXP-006114 | 2026-08-12 | BOQ-PKG-04-00144 | PKG-04 | INV-PKG-04-025-06114 | 312.47 | 156122.04 | 7806.1 | Paid | 148315.94 | 2026-Q3
EXP-001902 | 2026-08-13 | BOQ-PKG-02-01902 | PKG-02 | INV-PKG-02-013-01902 | 241.38 | 148305.34 | 7415.27 | Paid | 140890.07 | 2026-Q3
EXP-003173 | 2026-08-13 | BOQ-PKG-03-01183 | PKG-03 | INV-PKG-03-024-03173 | 258.02 | 173320.31 | 8666.02 | Paid | 164654.29 | 2026-Q3
EXP-003807 | 2026-08-13 | BOQ-PKG-07-01817 | PKG-07 | INV-PKG-07-028-03807 | 239.36 | 79489.06 | 3974.45 | Paid | 75514.61 | 2026-Q3
EXP-004881 | 2026-08-13 | BOQ-PKG-01-00901 | PKG-01 | INV-PKG-01-017-04881 | 163.39 | 110909.21 | 5545.46 | Paid | 105363.75 | 2026-Q3
EXP-005911 | 2026-08-13 | BOQ-PKG-01-01931 | PKG-01 | INV-PKG-01-032-05911 | 178.53 | 168222.78 | 8411.14 | Paid | 159811.64 | 2026-Q3
EXP-006834 | 2026-08-13 | BOQ-PKG-04-00864 | PKG-04 | INV-PKG-04-010-06834 | 431.3 | 173821.33 | 8691.07 | Paid | 165130.26 | 2026-Q3
EXP-000158 | 2026-08-14 | BOQ-PKG-08-00158 | PKG-08 | INV-PKG-08-019-00158 | 386.6 | 42797.93 | 2139.9 | Paid | 40658.03 | 2026-Q3
EXP-000786 | 2026-08-14 | BOQ-PKG-06-00786 | PKG-06 | INV-PKG-06-017-00786 | 63.01 | 171151.07 | 8557.55 | Paid | 162593.52 | 2026-Q3
EXP-001704 | 2026-08-14 | BOQ-PKG-04-01704 | PKG-04 | INV-PKG-04-025-01704 | 296.74 | 127756.42 | 6387.82 | Approved Pending Payment | 121368.6 | 2026-Q3
EXP-005276 | 2026-08-14 | BOQ-PKG-06-01296 | PKG-06 | INV-PKG-06-027-05276 | 185.14 | 44943.31 | 2247.17 | Paid | 42696.14 | 2026-Q3
EXP-005416 | 2026-08-14 | BOQ-PKG-06-01436 | PKG-06 | INV-PKG-06-027-05416 | 139.53 | 147775.41 | 7388.77 | Paid | 140386.64 | 2026-Q3
EXP-006551 | 2026-08-14 | BOQ-PKG-01-00581 | PKG-01 | INV-PKG-01-007-06551 | 44.05 | 116206.53 | 5810.33 | Approved Pending Payment | 110396.2 | 2026-Q3
EXP-006856 | 2026-08-14 | BOQ-PKG-06-00886 | PKG-06 | INV-PKG-06-032-06856 | 383.01 | 79168.55 | 3958.43 | Disputed | 75210.12 | 2026-Q3
EXP-006894 | 2026-08-14 | BOQ-PKG-04-00924 | PKG-04 | INV-PKG-04-035-06894 | 189.85 | 191956.86 | 9597.84 | Paid | 182359.02 | 2026-Q3
EXP-001231 | 2026-08-15 | BOQ-PKG-01-01231 | PKG-01 | INV-PKG-01-007-01231 | 108.39 | 139999.47 | 6999.97 | Paid | 132999.5 | 2026-Q3
EXP-001595 | 2026-08-15 | BOQ-PKG-05-01595 | PKG-05 | INV-PKG-05-021-01595 | 63.55 | 33645.46 | 1682.27 | Approved Pending Payment | 31963.19 | 2026-Q3
EXP-002267 | 2026-08-15 | BOQ-PKG-07-00277 | PKG-07 | INV-PKG-07-028-02267 | 315.93 | 52165.93 | 2608.3 | Paid | 49557.63 | 2026-Q3
EXP-003360 | 2026-08-15 | BOQ-PKG-10-01370 | PKG-10 | INV-PKG-10-001-03360 | 168.02 | 110444.6 | 5522.23 | Under Review | 104922.37 | 2026-Q3
EXP-005121 | 2026-08-15 | BOQ-PKG-01-01141 | PKG-01 | INV-PKG-01-012-05121 | 177.39 | 130668.43 | 6533.42 | Paid | 124135.01 | 2026-Q3
EXP-005842 | 2026-08-15 | BOQ-PKG-02-01862 | PKG-02 | INV-PKG-02-033-05842 | 263.09 | 126870.1 | 6343.51 | Paid | 120526.59 | 2026-Q3
EXP-006291 | 2026-08-15 | BOQ-PKG-01-00321 | PKG-01 | INV-PKG-01-027-06291 | 186.01 | 186786.15 | 9339.31 | Paid | 177446.84 | 2026-Q3
EXP-006411 | 2026-08-15 | BOQ-PKG-01-00441 | PKG-01 | INV-PKG-01-007-06411 | 256.5 | 25110.39 | 1255.52 | Paid | 23854.87 | 2026-Q3
EXP-000554 | 2026-08-16 | BOQ-PKG-04-00554 | PKG-04 | INV-PKG-04-030-00554 | 307.23 | 39226.18 | 1961.31 | Paid | 37264.87 | 2026-Q3
EXP-002145 | 2026-08-16 | BOQ-PKG-05-00155 | PKG-05 | INV-PKG-05-011-02145 | 10.34 | 125654.88 | 6282.74 | Under Review | 119372.14 | 2026-Q3
EXP-002253 | 2026-08-16 | BOQ-PKG-03-00263 | PKG-03 | INV-PKG-03-014-02253 | 246.88 | 116371.76 | 5818.59 | Paid | 110553.17 | 2026-Q3
EXP-002576 | 2026-08-16 | BOQ-PKG-06-00586 | PKG-06 | INV-PKG-06-022-02576 | 310.96 | 31130.99 | 1556.55 | Paid | 29574.44 | 2026-Q3
EXP-002916 | 2026-08-16 | BOQ-PKG-06-00926 | PKG-06 | INV-PKG-06-012-02916 | 54.47 | 136046.97 | 6802.35 | Under Review | 129244.62 | 2026-Q3
EXP-004042 | 2026-08-16 | BOQ-PKG-02-00062 | PKG-02 | INV-PKG-02-018-04042 | 26.59 | 158129.94 | 7906.5 | Paid | 150223.44 | 2026-Q3
EXP-004723 | 2026-08-16 | BOQ-PKG-03-00743 | PKG-03 | INV-PKG-03-034-04723 | 86.26 | 81702.94 | 4085.15 | Approved Pending Payment | 77617.79 | 2026-Q3
EXP-005151 | 2026-08-16 | BOQ-PKG-01-01171 | PKG-01 | INV-PKG-01-007-05151 | 157.33 | 85708.9 | 4285.44 | Paid | 81423.46 | 2026-Q3
EXP-006160 | 2026-08-16 | BOQ-PKG-10-00190 | PKG-10 | INV-PKG-10-001-06160 | 131.58 | 155085.91 | 7754.3 | Under Review | 147331.61 | 2026-Q3
EXP-006170 | 2026-08-16 | BOQ-PKG-10-00200 | PKG-10 | INV-PKG-10-011-06170 | 405.69 | 146872.69 | 7343.63 | Under Review | 139529.06 | 2026-Q3
EXP-000040 | 2026-08-17 | BOQ-PKG-10-00040 | PKG-10 | INV-PKG-10-006-00040 | 264.31 | 173255.68 | 8662.78 | Paid | 164592.9 | 2026-Q3
EXP-001832 | 2026-08-17 | BOQ-PKG-02-01832 | PKG-02 | INV-PKG-02-013-01832 | 422.33 | 25483.79 | 1274.19 | Paid | 24209.6 | 2026-Q3
EXP-001961 | 2026-08-17 | BOQ-PKG-01-01961 | PKG-01 | INV-PKG-01-002-01961 | 11.09 | 88697.44 | 4434.87 | Paid | 84262.57 | 2026-Q3
EXP-003016 | 2026-08-17 | BOQ-PKG-06-01026 | PKG-06 | INV-PKG-06-007-03016 | 304.78 | 35692.31 | 1784.62 | Under Review | 33907.69 | 2026-Q3
EXP-006248 | 2026-08-17 | BOQ-PKG-08-00278 | PKG-08 | INV-PKG-08-019-06248 | 190.5 | 120097.33 | 6004.87 | Paid | 114092.46 | 2026-Q3
EXP-000371 | 2026-08-18 | BOQ-PKG-01-00371 | PKG-01 | INV-PKG-01-022-00371 | 216.17 | 175367.36 | 8768.37 | Approved Pending Payment | 166598.99 | 2026-Q3
EXP-000745 | 2026-08-18 | BOQ-PKG-05-00745 | PKG-05 | INV-PKG-05-011-00745 | 339.1 | 142678.97 | 7133.95 | Paid | 135545.02 | 2026-Q3
EXP-000929 | 2026-08-18 | BOQ-PKG-09-00929 | PKG-09 | INV-PKG-09-020-00929 | 85.1 | 120983.49 | 6049.17 | Paid | 114934.32 | 2026-Q3
EXP-001421 | 2026-08-18 | BOQ-PKG-01-01421 | PKG-01 | INV-PKG-01-022-01421 | 151.65 | 96071.03 | 4803.55 | Paid | 91267.48 | 2026-Q3
EXP-002091 | 2026-08-18 | BOQ-PKG-01-00101 | PKG-01 | INV-PKG-01-027-02091 | 404.3 | 28656.57 | 1432.83 | Under Review | 27223.74 | 2026-Q3
EXP-002456 | 2026-08-18 | BOQ-PKG-06-00466 | PKG-06 | INV-PKG-06-007-02456 | 332.77 | 38752.42 | 1937.62 | Paid | 36814.8 | 2026-Q3
EXP-002776 | 2026-08-18 | BOQ-PKG-06-00786 | PKG-06 | INV-PKG-06-012-02776 | 250.43 | 153595.17 | 7679.76 | Paid | 145915.41 | 2026-Q3
EXP-003054 | 2026-08-18 | BOQ-PKG-04-01064 | PKG-04 | INV-PKG-04-010-03054 | 386.64 | 37128.58 | 1856.43 | Paid | 35272.15 | 2026-Q3
EXP-003196 | 2026-08-18 | BOQ-PKG-06-01206 | PKG-06 | INV-PKG-06-012-03196 | 348.92 | 186462.19 | 9323.11 | Paid | 177139.08 | 2026-Q3
EXP-001824 | 2026-08-19 | BOQ-PKG-04-01824 | PKG-04 | INV-PKG-04-005-01824 | 78.03 | 33662.52 | 1683.13 | Paid | 31979.39 | 2026-Q3
EXP-001995 | 2026-08-19 | BOQ-PKG-05-00005 | PKG-05 | INV-PKG-05-001-01995 | 340.26 | 209810.83 | 10490.54 | Disputed | 199320.29 | 2026-Q3
EXP-004037 | 2026-08-19 | BOQ-PKG-07-00057 | PKG-07 | INV-PKG-07-013-04037 | 440.47 | 162987.12 | 8149.36 | Paid | 154837.76 | 2026-Q3
EXP-004468 | 2026-08-19 | BOQ-PKG-08-00488 | PKG-08 | INV-PKG-08-024-04468 | 266.91 | 82817.15 | 4140.86 | Approved Pending Payment | 78676.29 | 2026-Q3
EXP-000510 | 2026-08-20 | BOQ-PKG-10-00510 | PKG-10 | INV-PKG-10-021-00510 | 16.04 | 177990.96 | 8899.55 | Approved Pending Payment | 169091.41 | 2026-Q3
EXP-000696 | 2026-08-20 | BOQ-PKG-06-00696 | PKG-06 | INV-PKG-06-032-00696 | 275.45 | 97359.46 | 4867.97 | Paid | 92491.49 | 2026-Q3
EXP-001074 | 2026-08-20 | BOQ-PKG-04-01074 | PKG-04 | INV-PKG-04-025-01074 | 339.82 | 187432.87 | 9371.64 | Approved Pending Payment | 178061.23 | 2026-Q3
EXP-002194 | 2026-08-20 | BOQ-PKG-04-00204 | PKG-04 | INV-PKG-04-025-02194 | 26.89 | 105905.62 | 5295.28 | Paid | 100610.34 | 2026-Q3
EXP-004400 | 2026-08-20 | BOQ-PKG-10-00420 | PKG-10 | INV-PKG-10-026-04400 | 235.32 | 203214.51 | 10160.73 | Approved Pending Payment | 193053.78 | 2026-Q3
EXP-004641 | 2026-08-20 | BOQ-PKG-01-00661 | PKG-01 | INV-PKG-01-022-04641 | 262.4 | 35685.05 | 1784.25 | Paid | 33900.8 | 2026-Q3
EXP-004811 | 2026-08-20 | BOQ-PKG-01-00831 | PKG-01 | INV-PKG-01-017-04811 | 349.43 | 109979.28 | 5498.96 | Paid | 104480.32 | 2026-Q3
EXP-005294 | 2026-08-20 | BOQ-PKG-04-01314 | PKG-04 | INV-PKG-04-010-05294 | 303.59 | 96368.15 | 4818.41 | Paid | 91549.74 | 2026-Q3
EXP-006491 | 2026-08-20 | BOQ-PKG-01-00521 | PKG-01 | INV-PKG-01-017-06491 | 289.64 | 104335.86 | 5216.79 | Paid | 99119.07 | 2026-Q3
EXP-002199 | 2026-08-21 | BOQ-PKG-09-00209 | PKG-09 | INV-PKG-09-030-02199 | 224.38 | 61205.8 | 3060.29 | Paid | 58145.51 | 2026-Q3
EXP-002234 | 2026-08-21 | BOQ-PKG-04-00244 | PKG-04 | INV-PKG-04-030-02234 | 321.01 | 171858.07 | 8592.9 | Paid | 163265.17 | 2026-Q3
EXP-005460 | 2026-08-21 | BOQ-PKG-10-01480 | PKG-10 | INV-PKG-10-001-05460 | 148.47 | 186504.77 | 9325.24 | Disputed | 177179.53 | 2026-Q3

## Variation Orders
VO_Number | Package_ID | Claim_Amount | Approved_Amount | Status | Time_Impact_Days | Submission_Date | Decision_Date | VO_Title
VO-PKG-03-00943 | PKG-03 | 44101.84 | 38028.07 | Approved | 6 | 2024-02-14 | 2024-03-24 | Viaduct pier foundation redesign due to utility clash
VO-PKG-04-02234 | PKG-04 | 25015.16 | 20578.97 | Approved | 43 | 2024-02-14 | 2024-04-10 | Station box diaphragm wall water ingress mitigation
VO-PKG-05-02575 | PKG-05 | 349946.84 | 332320.54 | Approved | 55 | 2024-02-14 | 2024-04-05 | HV substation redundancy transformer capacity upgrade
VO-PKG-07-02927 | PKG-07 | 220359.71 | 202354.05 | Approved | 14 | 2024-02-14 | 2024-03-05 | Fiber optic telemetry routing realignment along guideway
VO-PKG-02-01712 | PKG-02 | 181127.81 | 158820.2 | Approved | 34 | 2024-02-15 | 2024-03-15 | TBM Cutterhead refurbishment and rock fissure sealing
VO-PKG-02-02202 | PKG-02 | 124753.67 | 102141.55 | Approved | 11 | 2024-02-15 | 2024-04-04 | TBM Cutterhead refurbishment and rock fissure sealing
VO-PKG-02-02732 | PKG-02 | 42866.59 | 38581.78 | Approved | 55 | 2024-02-15 | 2024-03-21 | TBM Cutterhead refurbishment and rock fissure sealing
VO-PKG-04-02094 | PKG-04 | 64374.99 | 0 | Pending Approval | 12 | 2024-02-15 |  | Station box diaphragm wall water ingress mitigation
VO-PKG-08-02578 | PKG-08 | 49052.14 | 41327.53 | Approved | 19 | 2024-02-15 | 2024-03-15 | Track vibration damping rubber pads acoustic upgrade
VO-PKG-04-02014 | PKG-04 | 80299.66 | 71947.96 | Approved | 24 | 2024-02-16 | 2024-03-06 | Station box diaphragm wall water ingress mitigation
VO-PKG-08-00568 | PKG-08 | 47250.63 | 45844.45 | Approved | 11 | 2024-02-16 | 2024-03-06 | Track vibration damping rubber pads acoustic upgrade
VO-PKG-08-02948 | PKG-08 | 179203.82 | 0 | Pending Approval | 43 | 2024-02-16 |  | Track vibration damping rubber pads acoustic upgrade
VO-PKG-10-01920 | PKG-10 | 62643.27 | 56066.54 | Approved | 57 | 2024-02-17 | 2024-03-13 | HVAC chilled water pipe rerouting around station concourse
VO-PKG-01-01641 | PKG-01 | 272202.42 | 263231.7 | Approved | 54 | 2024-02-18 | 2024-03-07 | Unforeseen soft ground stabilization and grouting
VO-PKG-02-02992 | PKG-02 | 213357.33 | 0 | Pending Approval | 30 | 2024-02-18 |  | TBM Cutterhead refurbishment and rock fissure sealing
VO-PKG-04-02354 | PKG-04 | 321781.59 | 0 | Pending Approval | 10 | 2024-02-18 |  | Station box diaphragm wall water ingress mitigation
VO-PKG-07-00097 | PKG-07 | 243189.81 | 211544.4 | Approved | 14 | 2024-02-18 | 2024-03-17 | Fiber optic telemetry routing realignment along guideway
VO-PKG-07-01877 | PKG-07 | 27045.71 | 0 | Rejected | 0 | 2024-02-18 | 2024-03-03 | Fiber optic telemetry routing realignment along guideway
VO-PKG-10-01360 | PKG-10 | 331203.4 | 314960.77 | Approved | 6 | 2024-02-18 | 2024-03-30 | HVAC chilled water pipe rerouting around station concourse
VO-PKG-06-00416 | PKG-06 | 103344.99 | 88017.13 | Approved | 38 | 2024-02-19 | 2024-04-12 | Additional smoke evacuation shafts in underground platforms
VO-PKG-09-01489 | PKG-09 | 245078.28 | 0 | Rejected | 0 | 2024-02-19 | 2024-03-03 | Drainage box culvert capacity expansion for 100-year flood event
VO-PKG-03-00373 | PKG-03 | 133858.19 | 124321.66 | Approved | 8 | 2024-02-20 | 2024-04-07 | Viaduct pier foundation redesign due to utility clash
VO-PKG-05-01085 | PKG-05 | 198848.58 | 183410.42 | Approved | 50 | 2024-02-20 | 2024-04-17 | HV substation redundancy transformer capacity upgrade
VO-PKG-06-02006 | PKG-06 | 199870.48 | 182018.01 | Approved | 58 | 2024-02-20 | 2024-03-09 | Additional smoke evacuation shafts in underground platforms
VO-PKG-09-01899 | PKG-09 | 21499.01 | 0 | Pending Approval | 22 | 2024-02-20 |  | Drainage box culvert capacity expansion for 100-year flood event
VO-PKG-01-01891 | PKG-01 | 87162.1 | 74742.23 | Approved | 56 | 2024-02-21 | 2024-03-11 | Unforeseen soft ground stabilization and grouting
VO-PKG-02-01292 | PKG-02 | 319614.27 | 281772.6 | Approved | 47 | 2024-02-21 | 2024-04-16 | TBM Cutterhead refurbishment and rock fissure sealing
VO-PKG-04-01084 | PKG-04 | 272503.13 | 256697.87 | Approved | 26 | 2024-02-21 | 2024-03-29 | Station box diaphragm wall water ingress mitigation
VO-PKG-01-02081 | PKG-01 | 37990.33 | 32740.41 | Approved | 16 | 2024-02-22 | 2024-03-31 | Unforeseen soft ground stabilization and grouting
VO-PKG-04-01004 | PKG-04 | 65425.45 | 0 | Rejected | 0 | 2024-02-22 | 2024-03-16 | Station box diaphragm wall water ingress mitigation
VO-PKG-04-01404 | PKG-04 | 330800.21 | 271490.87 | Approved | 37 | 2024-02-22 | 2024-04-17 | Station box diaphragm wall water ingress mitigation
VO-PKG-06-00306 | PKG-06 | 173521.46 | 166981.03 | Approved | 47 | 2024-02-22 | 2024-04-20 | Additional smoke evacuation shafts in underground platforms
VO-PKG-08-02998 | PKG-08 | 279140.08 | 225597.88 | Approved | 46 | 2024-02-22 | 2024-03-25 | Track vibration damping rubber pads acoustic upgrade
VO-PKG-03-02503 | PKG-03 | 134826.5 | 111116.1 | Approved | 6 | 2024-02-23 | 2024-04-06 | Viaduct pier foundation redesign due to utility clash
VO-PKG-08-02098 | PKG-08 | 300561.83 | 257292.48 | Approved | 6 | 2024-02-23 | 2024-04-18 | Track vibration damping rubber pads acoustic upgrade
VO-PKG-01-01451 | PKG-01 | 71516.84 | 67176.31 | Approved | 14 | 2024-02-24 | 2024-03-18 | Unforeseen soft ground stabilization and grouting
VO-PKG-01-01541 | PKG-01 | 303769.83 | 290924.5 | Approved | 32 | 2024-02-24 | 2024-04-02 | Unforeseen soft ground stabilization and grouting
VO-PKG-08-02698 | PKG-08 | 46165.58 | 36969.19 | Approved | 50 | 2024-02-24 | 2024-04-02 | Track vibration damping rubber pads acoustic upgrade
VO-PKG-09-00909 | PKG-09 | 178416.17 | 166280.72 | Approved | 57 | 2024-02-24 | 2024-03-11 | Drainage box culvert capacity expansion for 100-year flood event
VO-PKG-02-02692 | PKG-02 | 58618.35 | 0 | Pending Approval | 26 | 2024-02-25 |  | TBM Cutterhead refurbishment and rock fissure sealing
VO-PKG-06-00936 | PKG-06 | 53818.65 | 44556.42 | Approved | 12 | 2024-02-25 | 2024-04-20 | Additional smoke evacuation shafts in underground platforms
VO-PKG-03-00923 | PKG-03 | 115160.76 | 0 | Pending Approval | 18 | 2024-02-26 |  | Viaduct pier foundation redesign due to utility clash
VO-PKG-06-00226 | PKG-06 | 109115.37 | 95633.83 | Approved | 32 | 2024-02-26 | 2024-03-12 | Additional smoke evacuation shafts in underground platforms
VO-PKG-09-02329 | PKG-09 | 124588.57 | 104099.53 | Approved | 7 | 2024-02-26 | 2024-04-08 | Drainage box culvert capacity expansion for 100-year flood event
VO-PKG-02-02932 | PKG-02 | 33845.29 | 0 | Rejected | 0 | 2024-02-27 | 2024-03-11 | TBM Cutterhead refurbishment and rock fissure sealing
VO-PKG-03-02023 | PKG-03 | 256917.12 | 251155.5 | Approved | 11 | 2024-02-27 | 2024-03-28 | Viaduct pier foundation redesign due to utility clash
VO-PKG-06-02076 | PKG-06 | 64003.74 | 52936.43 | Approved | 35 | 2024-02-27 | 2024-03-19 | Additional smoke evacuation shafts in underground platforms
VO-PKG-09-01819 | PKG-09 | 246622.03 | 0 | Rejected | 0 | 2024-02-27 | 2024-04-06 | Drainage box culvert capacity expansion for 100-year flood event
VO-PKG-09-02059 | PKG-09 | 225243.12 | 210073.03 | Approved | 37 | 2024-02-27 | 2024-03-16 | Drainage box culvert capacity expansion for 100-year flood event
VO-PKG-03-00823 | PKG-03 | 171445.35 | 142305.9 | Approved | 54 | 2024-02-28 | 2024-03-21 | Viaduct pier foundation redesign due to utility clash
VO-PKG-04-01474 | PKG-04 | 272456.9 | 0 | Rejected | 0 | 2024-02-28 | 2024-04-10 | Station box diaphragm wall water ingress mitigation
VO-PKG-01-01341 | PKG-01 | 145255.52 | 119189.14 | Approved | 53 | 2024-02-29 | 2024-03-20 | Unforeseen soft ground stabilization and grouting
VO-PKG-02-00252 | PKG-02 | 106534.15 | 101855.87 | Approved | 45 | 2024-02-29 | 2024-04-24 | TBM Cutterhead refurbishment and rock fissure sealing
VO-PKG-02-01572 | PKG-02 | 127007.73 | 119835.49 | Approved | 27 | 2024-02-29 | 2024-03-25 | TBM Cutterhead refurbishment and rock fissure sealing
VO-PKG-02-01802 | PKG-02 | 63280.4 | 55363.62 | Approved | 22 | 2024-02-29 | 2024-04-19 | TBM Cutterhead refurbishment and rock fissure sealing
VO-PKG-03-00083 | PKG-03 | 298421.38 | 0 | Pending Approval | 18 | 2024-02-29 |  | Viaduct pier foundation redesign due to utility clash
VO-PKG-04-00334 | PKG-04 | 157364.12 | 135174.53 | Approved | 47 | 2024-02-29 | 2024-03-17 | Station box diaphragm wall water ingress mitigation
VO-PKG-01-00741 | PKG-01 | 279421.95 | 229872.36 | Approved | 56 | 2024-03-01 | 2024-04-05 | Unforeseen soft ground stabilization and grouting
VO-PKG-03-01773 | PKG-03 | 328734.26 | 0 | Pending Approval | 18 | 2024-03-01 |  | Viaduct pier foundation redesign due to utility clash
VO-PKG-01-00451 | PKG-01 | 249555.01 | 212308.41 | Approved | 27 | 2024-03-02 | 2024-04-09 | Unforeseen soft ground stabilization and grouting
VO-PKG-01-00561 | PKG-01 | 28002.19 | 27105.13 | Approved | 7 | 2024-03-02 | 2024-03-25 | Unforeseen soft ground stabilization and grouting
VO-PKG-09-01019 | PKG-09 | 207114.7 | 194063.41 | Approved | 42 | 2024-03-02 | 2024-04-20 | Drainage box culvert capacity expansion for 100-year flood event
VO-PKG-02-02352 | PKG-02 | 163762.79 | 0 | Pending Approval | 15 | 2024-03-03 |  | TBM Cutterhead refurbishment and rock fissure sealing
VO-PKG-06-00696 | PKG-06 | 241216.32 | 235230.76 | Approved | 11 | 2024-03-03 | 2024-03-30 | Additional smoke evacuation shafts in underground platforms
VO-PKG-02-00172 | PKG-02 | 111185.53 | 0 | Rejected | 0 | 2024-03-04 | 2024-03-14 | TBM Cutterhead refurbishment and rock fissure sealing
VO-PKG-03-02123 | PKG-03 | 179688.2 | 166400.37 | Approved | 8 | 2024-03-04 | 2024-04-02 | Viaduct pier foundation redesign due to utility clash
VO-PKG-05-01325 | PKG-05 | 280314.25 | 270610.39 | Approved | 12 | 2024-03-04 | 2024-03-26 | HV substation redundancy transformer capacity upgrade
VO-PKG-06-00506 | PKG-06 | 328327.92 | 293340.73 | Approved | 8 | 2024-03-04 | 2024-03-20 | Additional smoke evacuation shafts in underground platforms
VO-PKG-09-02479 | PKG-09 | 140911.96 | 132020.9 | Approved | 34 | 2024-03-04 | 2024-04-27 | Drainage box culvert capacity expansion for 100-year flood event
VO-PKG-01-00911 | PKG-01 | 110966.28 | 0 | Rejected | 0 | 2024-03-05 | 2024-03-19 | Unforeseen soft ground stabilization and grouting
VO-PKG-01-02361 | PKG-01 | 231091.06 | 187166.67 | Approved | 39 | 2024-03-05 | 2024-04-16 | Unforeseen soft ground stabilization and grouting
VO-PKG-06-02436 | PKG-06 | 117206.58 | 109668.65 | Approved | 8 | 2024-03-05 | 2024-04-06 | Additional smoke evacuation shafts in underground platforms
VO-PKG-07-01067 | PKG-07 | 147072.72 | 0 | Pending Approval | 38 | 2024-03-05 |  | Fiber optic telemetry routing realignment along guideway
VO-PKG-01-01301 | PKG-01 | 130889.42 | 115291.89 | Approved | 49 | 2024-03-06 | 2024-04-17 | Unforeseen soft ground stabilization and grouting
VO-PKG-04-00014 | PKG-04 | 338230.11 | 0 | Pending Approval | 38 | 2024-03-06 |  | Station box diaphragm wall water ingress mitigation
VO-PKG-05-00035 | PKG-05 | 143589.85 | 124180.95 | Approved | 10 | 2024-03-06 | 2024-04-17 | HV substation redundancy transformer capacity upgrade
VO-PKG-06-01166 | PKG-06 | 50739.15 | 42826.74 | Approved | 49 | 2024-03-06 | 2024-05-02 | Additional smoke evacuation shafts in underground platforms
VO-PKG-10-01840 | PKG-10 | 127474.57 | 0 | Pending Approval | 9 | 2024-03-06 |  | HVAC chilled water pipe rerouting around station concourse
VO-PKG-01-01991 | PKG-01 | 107938.99 | 0 | Pending Approval | 40 | 2024-03-07 |  | Unforeseen soft ground stabilization and grouting
VO-PKG-02-00092 | PKG-02 | 19511.64 | 16623.73 | Approved | 27 | 2024-03-07 | 2024-04-10 | TBM Cutterhead refurbishment and rock fissure sealing
VO-PKG-07-01907 | PKG-07 | 93781.81 | 0 | Pending Approval | 20 | 2024-03-07 |  | Fiber optic telemetry routing realignment along guideway
VO-PKG-08-00558 | PKG-08 | 58463.84 | 0 | Pending Approval | 3 | 2024-03-07 |  | Track vibration damping rubber pads acoustic upgrade
VO-PKG-10-01420 | PKG-10 | 266454.51 | 0 | Pending Approval | 16 | 2024-03-07 |  | HVAC chilled water pipe rerouting around station concourse
VO-PKG-10-02460 | PKG-10 | 242213.71 | 0 | Pending Approval | 21 | 2024-03-07 |  | HVAC chilled water pipe rerouting around station concourse
VO-PKG-01-00061 | PKG-01 | 335419.13 | 0 | Rejected | 0 | 2024-03-08 | 2024-04-01 | Unforeseen soft ground stabilization and grouting
VO-PKG-02-01382 | PKG-02 | 123319.09 | 111387.42 | Approved | 53 | 2024-03-08 | 2024-04-02 | TBM Cutterhead refurbishment and rock fissure sealing
VO-PKG-07-01537 | PKG-07 | 313525.5 | 279481.43 | Approved | 36 | 2024-03-08 | 2024-04-12 | Fiber optic telemetry routing realignment along guideway
VO-PKG-10-00090 | PKG-10 | 56614.26 | 54047.85 | Approved | 47 | 2024-03-08 | 2024-03-24 | HVAC chilled water pipe rerouting around station concourse
VO-PKG-02-00782 | PKG-02 | 323016.11 | 280304.96 | Approved | 5 | 2024-03-09 | 2024-04-30 | TBM Cutterhead refurbishment and rock fissure sealing
VO-PKG-05-01865 | PKG-05 | 299697.65 | 0 | Pending Approval | 13 | 2024-03-09 |  | HV substation redundancy transformer capacity upgrade
VO-PKG-10-01070 | PKG-10 | 268185.54 | 255310.34 | Approved | 56 | 2024-03-09 | 2024-04-13 | HVAC chilled water pipe rerouting around station concourse
VO-PKG-10-01310 | PKG-10 | 345197.85 | 0 | Rejected | 0 | 2024-03-09 | 2024-04-16 | HVAC chilled water pipe rerouting around station concourse
VO-PKG-02-00332 | PKG-02 | 302564.11 | 0 | Rejected | 0 | 2024-03-10 | 2024-03-30 | TBM Cutterhead refurbishment and rock fissure sealing
VO-PKG-02-02772 | PKG-02 | 92720.87 | 79387.32 | Approved | 30 | 2024-03-10 | 2024-04-09 | TBM Cutterhead refurbishment and rock fissure sealing
VO-PKG-08-00828 | PKG-08 | 58277.45 | 51903.57 | Approved | 25 | 2024-03-10 | 2024-04-27 | Track vibration damping rubber pads acoustic upgrade
VO-PKG-02-00042 | PKG-02 | 325842.18 | 278914.59 | Approved | 35 | 2024-03-11 | 2024-05-07 | TBM Cutterhead refurbishment and rock fissure sealing
VO-PKG-05-01005 | PKG-05 | 205389.12 | 200925.11 | Approved | 48 | 2024-03-11 | 2024-05-06 | HV substation redundancy transformer capacity upgrade
VO-PKG-05-01715 | PKG-05 | 287125.3 | 271710.58 | Approved | 37 | 2024-03-11 | 2024-04-01 | HV substation redundancy transformer capacity upgrade
VO-PKG-07-02717 | PKG-07 | 205989.87 | 166422.51 | Approved | 24 | 2024-03-11 | 2024-05-03 | Fiber optic telemetry routing realignment along guideway
VO-PKG-08-01868 | PKG-08 | 330959.51 | 0 | Pending Approval | 32 | 2024-03-11 |  | Track vibration damping rubber pads acoustic upgrade
VO-PKG-03-02573 | PKG-03 | 82968.12 | 79635.28 | Approved | 23 | 2024-03-12 | 2024-04-01 | Viaduct pier foundation redesign due to utility clash
VO-PKG-03-02833 | PKG-03 | 225987.58 | 0 | Pending Approval | 28 | 2024-03-12 |  | Viaduct pier foundation redesign due to utility clash
VO-PKG-05-00225 | PKG-05 | 257563.71 | 227503.65 | Approved | 18 | 2024-03-12 | 2024-04-09 | HV substation redundancy transformer capacity upgrade
VO-PKG-05-01845 | PKG-05 | 101421.3 | 84418.7 | Approved | 41 | 2024-03-12 | 2024-04-06 | HV substation redundancy transformer capacity upgrade
VO-PKG-02-00562 | PKG-02 | 199547 | 174168.38 | Approved | 5 | 2024-03-13 | 2024-04-28 | TBM Cutterhead refurbishment and rock fissure sealing
VO-PKG-06-01406 | PKG-06 | 74621.96 | 0 | Rejected | 0 | 2024-03-13 | 2024-04-02 | Additional smoke evacuation shafts in underground platforms
VO-PKG-06-02236 | PKG-06 | 123045.23 | 115598.63 | Approved | 49 | 2024-03-13 | 2024-05-10 | Additional smoke evacuation shafts in underground platforms
VO-PKG-01-00941 | PKG-01 | 51691.97 | 45112.95 | Approved | 23 | 2024-03-14 | 2024-05-08 | Unforeseen soft ground stabilization and grouting
VO-PKG-03-01003 | PKG-03 | 27775.99 | 25401.28 | Approved | 43 | 2024-03-14 | 2024-04-04 | Viaduct pier foundation redesign due to utility clash
VO-PKG-03-02753 | PKG-03 | 207052.54 | 194099.71 | Approved | 54 | 2024-03-14 | 2024-04-21 | Viaduct pier foundation redesign due to utility clash
VO-PKG-06-02956 | PKG-06 | 183671.05 | 157345.77 | Approved | 9 | 2024-03-14 | 2024-04-16 | Additional smoke evacuation shafts in underground platforms
VO-PKG-06-00836 | PKG-06 | 322809.15 | 300467.65 | Approved | 56 | 2024-03-15 | 2024-04-21 | Additional smoke evacuation shafts in underground platforms
VO-PKG-06-00876 | PKG-06 | 256182.47 | 0 | Pending Approval | 29 | 2024-03-15 |  | Additional smoke evacuation shafts in underground platforms
VO-PKG-07-00587 | PKG-07 | 283883.26 | 0 | Pending Approval | 39 | 2024-03-15 |  | Fiber optic telemetry routing realignment along guideway
VO-PKG-10-00810 | PKG-10 | 125887.86 | 0 | Pending Approval | 8 | 2024-03-15 |  | HVAC chilled water pipe rerouting around station concourse
VO-PKG-02-01742 | PKG-02 | 60465.92 | 0 | Pending Approval | 18 | 2024-03-16 |  | TBM Cutterhead refurbishment and rock fissure sealing
VO-PKG-05-01655 | PKG-05 | 40520.26 | 0 | Pending Approval | 43 | 2024-03-16 |  | HV substation redundancy transformer capacity upgrade
VO-PKG-06-00136 | PKG-06 | 52709.34 | 0 | Rejected | 0 | 2024-03-16 | 2024-04-17 | Additional smoke evacuation shafts in underground platforms
VO-PKG-06-02086 | PKG-06 | 140539.16 | 128840.03 | Approved | 32 | 2024-03-17 | 2024-05-02 | Additional smoke evacuation shafts in underground platforms
VO-PKG-07-02977 | PKG-07 | 324548.54 | 297503.46 | Approved | 26 | 2024-03-18 | 2024-05-03 | Fiber optic telemetry routing realignment along guideway
VO-PKG-09-02429 | PKG-09 | 254941.98 | 0 | Pending Approval | 11 | 2024-03-18 |  | Drainage box culvert capacity expansion for 100-year flood event
VO-PKG-03-02383 | PKG-03 | 142877.65 | 127463.4 | Approved | 12 | 2024-03-19 | 2024-05-12 | Viaduct pier foundation redesign due to utility clash
VO-PKG-05-01335 | PKG-05 | 265313.53 | 239493.57 | Approved | 34 | 2024-03-19 | 2024-05-15 | HV substation redundancy transformer capacity upgrade
VO-PKG-07-00627 | PKG-07 | 44279.63 | 38336.97 | Approved | 12 | 2024-03-19 | 2024-05-06 | Fiber optic telemetry routing realignment along guideway
VO-PKG-09-01089 | PKG-09 | 303760.58 | 271508.37 | Approved | 11 | 2024-03-19 | 2024-04-23 | Drainage box culvert capacity expansion for 100-year flood event
VO-PKG-09-02579 | PKG-09 | 180123.79 | 160597.32 | Approved | 9 | 2024-03-19 | 2024-05-10 | Drainage box culvert capacity expansion for 100-year flood event
VO-PKG-10-02230 | PKG-10 | 107013.25 | 0 | Pending Approval | 20 | 2024-03-19 |  | HVAC chilled water pipe rerouting around station concourse
VO-PKG-07-01207 | PKG-07 | 125695.1 | 0 | Pending Approval | 36 | 2024-03-20 |  | Fiber optic telemetry routing realignment along guideway
VO-PKG-01-02871 | PKG-01 | 259775.33 | 209770.42 | Approved | 30 | 2024-03-21 | 2024-04-20 | Unforeseen soft ground stabilization and grouting
VO-PKG-07-01777 | PKG-07 | 75164.42 | 73623.43 | Approved | 56 | 2024-03-22 | 2024-05-06 | Fiber optic telemetry routing realignment along guideway
VO-PKG-08-00348 | PKG-08 | 330221.61 | 314501.86 | Approved | 41 | 2024-03-22 | 2024-05-18 | Track vibration damping rubber pads acoustic upgrade
VO-PKG-08-01918 | PKG-08 | 178484.7 | 151634.88 | Approved | 49 | 2024-03-22 | 2024-04-24 | Track vibration damping rubber pads acoustic upgrade
VO-PKG-03-02613 | PKG-03 | 155780.6 | 129611.09 | Approved | 8 | 2024-03-23 | 2024-04-22 | Viaduct pier foundation redesign due to utility clash
VO-PKG-05-00875 | PKG-05 | 253144.49 | 0 | Pending Approval | 43 | 2024-03-23 |  | HV substation redundancy transformer capacity upgrade
VO-PKG-06-01066 | PKG-06 | 207776.57 | 178254.87 | Approved | 27 | 2024-03-23 | 2024-04-24 | Additional smoke evacuation shafts in underground platforms
VO-PKG-10-00640 | PKG-10 | 320377.94 | 293610.23 | Approved | 22 | 2024-03-23 | 2024-04-10 | HVAC chilled water pipe rerouting around station concourse
VO-PKG-02-01992 | PKG-02 | 247775.8 | 0 | Rejected | 0 | 2024-03-25 | 2024-04-15 | TBM Cutterhead refurbishment and rock fissure sealing
VO-PKG-10-01750 | PKG-10 | 123870.7 | 121171.09 | Approved | 34 | 2024-03-25 | 2024-05-23 | HVAC chilled water pipe rerouting around station concourse
VO-PKG-01-02921 | PKG-01 | 90367.43 | 80323.82 | Approved | 50 | 2024-03-26 | 2024-04-27 | Unforeseen soft ground stabilization and grouting
VO-PKG-03-00583 | PKG-03 | 314479.48 | 294561.79 | Approved | 42 | 2024-03-26 | 2024-04-16 | Viaduct pier foundation redesign due to utility clash
VO-PKG-03-02773 | PKG-03 | 147263.47 | 138724.2 | Approved | 34 | 2024-03-26 | 2024-05-07 | Viaduct pier foundation redesign due to utility clash
VO-PKG-05-01935 | PKG-05 | 183169.71 | 175293.19 | Approved | 23 | 2024-03-26 | 2024-04-15 | HV substation redundancy transformer capacity upgrade
VO-PKG-08-01318 | PKG-08 | 307380.48 | 251071.72 | Approved | 9 | 2024-03-26 | 2024-05-24 | Track vibration damping rubber pads acoustic upgrade
VO-PKG-04-01454 | PKG-04 | 298545.37 | 262793.9 | Approved | 8 | 2024-03-27 | 2024-05-10 | Station box diaphragm wall water ingress mitigation
VO-PKG-05-02665 | PKG-05 | 105023.04 | 94179.51 | Approved | 41 | 2024-03-27 | 2024-04-29 | HV substation redundancy transformer capacity upgrade
VO-PKG-02-00062 | PKG-02 | 113292.39 | 0 | Pending Approval | 3 | 2024-03-28 |  | TBM Cutterhead refurbishment and rock fissure sealing
VO-PKG-03-02443 | PKG-03 | 133958.42 | 121211.24 | Approved | 45 | 2024-03-28 | 2024-04-29 | Viaduct pier foundation redesign due to utility clash
VO-PKG-05-00655 | PKG-05 | 270489.04 | 0 | Rejected | 0 | 2024-03-28 | 2024-05-09 | HV substation redundancy transformer capacity upgrade
VO-PKG-06-02756 | PKG-06 | 282987.92 | 0 | Rejected | 0 | 2024-03-28 | 2024-04-25 | Additional smoke evacuation shafts in underground platforms
VO-PKG-03-01123 | PKG-03 | 298894.15 | 279187.92 | Approved | 28 | 2024-03-29 | 2024-04-17 | Viaduct pier foundation redesign due to utility clash
VO-PKG-09-02089 | PKG-09 | 301642.13 | 261228.98 | Approved | 10 | 2024-03-29 | 2024-05-05 | Drainage box culvert capacity expansion for 100-year flood event
VO-PKG-06-01966 | PKG-06 | 99368.15 | 82597.88 | Approved | 7 | 2024-03-30 | 2024-05-17 | Additional smoke evacuation shafts in underground platforms
VO-PKG-08-01618 | PKG-08 | 154157.98 | 0 | Rejected | 0 | 2024-03-30 | 2024-05-07 | Track vibration damping rubber pads acoustic upgrade
VO-PKG-08-02798 | PKG-08 | 105839.75 | 0 | Rejected | 0 | 2024-03-30 | 2024-04-10 | Track vibration damping rubber pads acoustic upgrade
VO-PKG-06-00356 | PKG-06 | 325932.7 | 294732.79 | Approved | 8 | 2024-03-31 | 2024-05-09 | Additional smoke evacuation shafts in underground platforms
VO-PKG-08-01958 | PKG-08 | 62498.92 | 52890.69 | Approved | 25 | 2024-03-31 | 2024-04-27 | Track vibration damping rubber pads acoustic upgrade
VO-PKG-01-01051 | PKG-01 | 41530.03 | 0 | Pending Approval | 37 | 2024-04-01 |  | Unforeseen soft ground stabilization and grouting
VO-PKG-01-02401 | PKG-01 | 232066.22 | 216077.31 | Approved | 15 | 2024-04-01 | 2024-05-14 | Unforeseen soft ground stabilization and grouting
VO-PKG-03-01643 | PKG-03 | 178088.6 | 151605.15 | Approved | 14 | 2024-04-01 | 2024-05-21 | Viaduct pier foundation redesign due to utility clash
VO-PKG-03-00103 | PKG-03 | 67893.91 | 59187.13 | Approved | 9 | 2024-04-02 | 2024-05-30 | Viaduct pier foundation redesign due to utility clash
VO-PKG-09-01679 | PKG-09 | 83933.5 | 77830.97 | Approved | 7 | 2024-04-02 | 2024-05-20 | Drainage box culvert capacity expansion for 100-year flood event
VO-PKG-10-00900 | PKG-10 | 127162.37 | 0 | Pending Approval | 36 | 2024-04-02 |  | HVAC chilled water pipe rerouting around station concourse
VO-PKG-03-00903 | PKG-03 | 295532 | 0 | Rejected | 0 | 2024-04-03 | 2024-05-10 | Viaduct pier foundation redesign due to utility clash
VO-PKG-03-01133 | PKG-03 | 101080.96 | 0 | Rejected | 0 | 2024-04-03 | 2024-05-12 | Viaduct pier foundation redesign due to utility clash
VO-PKG-09-01319 | PKG-09 | 242197.18 | 198416.79 | Approved | 5 | 2024-04-04 | 2024-04-25 | Drainage box culvert capacity expansion for 100-year flood event
VO-PKG-03-00783 | PKG-03 | 272185.01 | 0 | Rejected | 0 | 2024-04-05 | 2024-05-05 | Viaduct pier foundation redesign due to utility clash
VO-PKG-04-02784 | PKG-04 | 20160.85 | 0 | Pending Approval | 3 | 2024-04-05 |  | Station box diaphragm wall water ingress mitigation
VO-PKG-06-01996 | PKG-06 | 329078.49 | 0 | Pending Approval | 26 | 2024-04-05 |  | Additional smoke evacuation shafts in underground platforms
VO-PKG-10-00010 | PKG-10 | 109807.98 | 96997.33 | Approved | 52 | 2024-04-05 | 2024-05-08 | HVAC chilled water pipe rerouting around station concourse
VO-PKG-02-00502 | PKG-02 | 107056.76 | 0 | Pending Approval | 36 | 2024-04-06 |  | TBM Cutterhead refurbishment and rock fissure sealing
VO-PKG-09-02629 | PKG-09 | 173807.69 | 158987 | Approved | 37 | 2024-04-06 | 2024-05-09 | Drainage box culvert capacity expansion for 100-year flood event
VO-PKG-10-02190 | PKG-10 | 90928.63 | 80016.26 | Approved | 15 | 2024-04-06 | 2024-04-25 | HVAC chilled water pipe rerouting around station concourse
VO-PKG-01-00641 | PKG-01 | 328410.47 | 303306.29 | Approved | 44 | 2024-04-07 | 2024-05-25 | Unforeseen soft ground stabilization and grouting
VO-PKG-03-00253 | PKG-03 | 61099.07 | 49397.6 | Approved | 44 | 2024-04-07 | 2024-05-21 | Viaduct pier foundation redesign due to utility clash
VO-PKG-04-00044 | PKG-04 | 112375.96 | 109434.07 | Approved | 28 | 2024-04-07 | 2024-06-04 | Station box diaphragm wall water ingress mitigation
VO-PKG-04-00124 | PKG-04 | 320356.26 | 257255.43 | Approved | 24 | 2024-04-07 | 2024-04-23 | Station box diaphragm wall water ingress mitigation
VO-PKG-05-02745 | PKG-05 | 36369.22 | 0 | Pending Approval | 30 | 2024-04-07 |  | HV substation redundancy transformer capacity upgrade
VO-PKG-01-02781 | PKG-01 | 227011.01 | 186693.7 | Approved | 56 | 2024-04-08 | 2024-05-03 | Unforeseen soft ground stabilization and grouting
VO-PKG-03-01963 | PKG-03 | 295595.59 | 246759.39 | Approved | 20 | 2024-04-08 | 2024-05-09 | Viaduct pier foundation redesign due to utility clash
VO-PKG-05-01775 | PKG-05 | 313586.13 | 284656.34 | Approved | 10 | 2024-04-08 | 2024-05-27 | HV substation redundancy transformer capacity upgrade
VO-PKG-07-02047 | PKG-07 | 32046.39 | 0 | Pending Approval | 20 | 2024-04-08 |  | Fiber optic telemetry routing realignment along guideway
VO-PKG-01-02981 | PKG-01 | 277756.38 | 0 | Pending Approval | 15 | 2024-04-09 |  | Unforeseen soft ground stabilization and grouting
VO-PKG-02-01752 | PKG-02 | 249557.25 | 0 | Pending Approval | 7 | 2024-04-09 |  | TBM Cutterhead refurbishment and rock fissure sealing
VO-PKG-05-01125 | PKG-05 | 57329.1 | 0 | Rejected | 0 | 2024-04-09 | 2024-05-11 | HV substation redundancy transformer capacity upgrade
VO-PKG-07-02037 | PKG-07 | 217342.58 | 0 | Pending Approval | 1 | 2024-04-09 |  | Fiber optic telemetry routing realignment along guideway
VO-PKG-01-02341 | PKG-01 | 180530.88 | 0 | Pending Approval | 40 | 2024-04-10 |  | Unforeseen soft ground stabilization and grouting
VO-PKG-03-02723 | PKG-03 | 145393.08 | 136207.29 | Approved | 56 | 2024-04-10 | 2024-06-08 | Viaduct pier foundation redesign due to utility clash
VO-PKG-07-02027 | PKG-07 | 216096.71 | 188236.64 | Approved | 52 | 2024-04-10 | 2024-05-27 | Fiber optic telemetry routing realignment along guideway
VO-PKG-09-00469 | PKG-09 | 58687.67 | 52616.41 | Approved | 12 | 2024-04-10 | 2024-05-21 | Drainage box culvert capacity expansion for 100-year flood event
VO-PKG-03-02303 | PKG-03 | 123285.12 | 0 | Rejected | 0 | 2024-04-11 | 2024-04-29 | Viaduct pier foundation redesign due to utility clash
VO-PKG-05-00975 | PKG-05 | 61518.24 | 51119.56 | Approved | 50 | 2024-04-11 | 2024-04-28 | HV substation redundancy transformer capacity upgrade
VO-PKG-06-02536 | PKG-06 | 64704.84 | 62537.73 | Approved | 49 | 2024-04-11 | 2024-06-03 | Additional smoke evacuation shafts in underground platforms
VO-PKG-03-00913 | PKG-03 | 214911.8 | 0 | Pending Approval | 12 | 2024-04-12 |  | Viaduct pier foundation redesign due to utility clash
VO-PKG-04-02384 | PKG-04 | 74983.33 | 0 | Pending Approval | 32 | 2024-04-12 |  | Station box diaphragm wall water ingress mitigation
VO-PKG-04-02544 | PKG-04 | 223384.34 | 0 | Rejected | 0 | 2024-04-12 | 2024-05-09 | Station box diaphragm wall water ingress mitigation
VO-PKG-05-00795 | PKG-05 | 206507.71 | 183055.83 | Approved | 38 | 2024-04-12 | 2024-05-13 | HV substation redundancy transformer capacity upgrade
VO-PKG-06-01566 | PKG-06 | 19237.42 | 17264.17 | Approved | 23 | 2024-04-12 | 2024-05-11 | Additional smoke evacuation shafts in underground platforms
VO-PKG-01-01861 | PKG-01 | 302261.07 | 0 | Pending Approval | 24 | 2024-04-13 |  | Unforeseen soft ground stabilization and grouting
VO-PKG-05-01615 | PKG-05 | 343579.54 | 301608.01 | Approved | 39 | 2024-04-13 | 2024-06-11 | HV substation redundancy transformer capacity upgrade
VO-PKG-10-01960 | PKG-10 | 110016.06 | 0 | Pending Approval | 27 | 2024-04-13 |  | HVAC chilled water pipe rerouting around station concourse
VO-PKG-02-01672 | PKG-02 | 81706.99 | 78150.06 | Approved | 56 | 2024-04-14 | 2024-06-11 | TBM Cutterhead refurbishment and rock fissure sealing
VO-PKG-05-02115 | PKG-05 | 247813.42 | 0 | Rejected | 0 | 2024-04-14 | 2024-05-15 | HV substation redundancy transformer capacity upgrade
VO-PKG-05-02735 | PKG-05 | 320832.15 | 0 | Pending Approval | 13 | 2024-04-14 |  | HV substation redundancy transformer capacity upgrade
VO-PKG-09-00789 | PKG-09 | 56533.01 | 0 | Pending Approval | 22 | 2024-04-14 |  | Drainage box culvert capacity expansion for 100-year flood event
VO-PKG-09-02309 | PKG-09 | 155676.28 | 138602.55 | Approved | 9 | 2024-04-14 | 2024-06-06 | Drainage box culvert capacity expansion for 100-year flood event
VO-PKG-03-00203 | PKG-03 | 290021.39 | 234093.74 | Approved | 22 | 2024-04-15 | 2024-06-12 | Viaduct pier foundation redesign due to utility clash
VO-PKG-06-00176 | PKG-06 | 329176.75 | 285875.64 | Approved | 53 | 2024-04-15 | 2024-05-12 | Additional smoke evacuation shafts in underground platforms
VO-PKG-01-02901 | PKG-01 | 265904.37 | 0 | Pending Approval | 29 | 2024-04-16 |  | Unforeseen soft ground stabilization and grouting
VO-PKG-02-02782 | PKG-02 | 16081.68 | 0 | Pending Approval | 20 | 2024-04-16 |  | TBM Cutterhead refurbishment and rock fissure sealing
VO-PKG-06-01176 | PKG-06 | 314123.06 | 261721.04 | Approved | 45 | 2024-04-16 | 2024-05-28 | Additional smoke evacuation shafts in underground platforms
VO-PKG-09-02979 | PKG-09 | 151817.49 | 132815.57 | Approved | 17 | 2024-04-16 | 2024-06-10 | Drainage box culvert capacity expansion for 100-year flood event
VO-PKG-02-00652 | PKG-02 | 148684.26 | 0 | Pending Approval | 3 | 2024-04-17 |  | TBM Cutterhead refurbishment and rock fissure sealing
VO-PKG-03-00863 | PKG-03 | 178247.17 | 0 | Rejected | 0 | 2024-04-17 | 2024-05-19 | Viaduct pier foundation redesign due to utility clash
VO-PKG-04-01144 | PKG-04 | 132327.71 | 0 | Pending Approval | 26 | 2024-04-17 |  | Station box diaphragm wall water ingress mitigation
VO-PKG-06-00046 | PKG-06 | 246587.89 | 0 | Pending Approval | 40 | 2024-04-17 |  | Additional smoke evacuation shafts in underground platforms
VO-PKG-07-00957 | PKG-07 | 56085.8 | 0 | Rejected | 0 | 2024-04-17 | 2024-05-21 | Fiber optic telemetry routing realignment along guideway
VO-PKG-10-01300 | PKG-10 | 90565.58 | 74969.06 | Approved | 14 | 2024-04-17 | 2024-05-04 | HVAC chilled water pipe rerouting around station concourse
VO-PKG-05-00205 | PKG-05 | 335943.54 | 278514.84 | Approved | 37 | 2024-04-18 | 2024-06-16 | HV substation redundancy transformer capacity upgrade
VO-PKG-08-02868 | PKG-08 | 224702.17 | 202959.98 | Approved | 31 | 2024-04-18 | 2024-05-03 | Track vibration damping rubber pads acoustic upgrade
VO-PKG-10-01910 | PKG-10 | 189287.02 | 169007.49 | Approved | 58 | 2024-04-18 | 2024-05-24 | HVAC chilled water pipe rerouting around station concourse
VO-PKG-01-01431 | PKG-01 | 130191.68 | 0 | Pending Approval | 22 | 2024-04-19 |  | Unforeseen soft ground stabilization and grouting
VO-PKG-08-01998 | PKG-08 | 157072.15 | 0 | Pending Approval | 3 | 2024-04-19 |  | Track vibration damping rubber pads acoustic upgrade
VO-PKG-09-01629 | PKG-09 | 248241.95 | 208531.22 | Approved | 43 | 2024-04-19 | 2024-05-07 | Drainage box culvert capacity expansion for 100-year flood event
VO-PKG-02-02002 | PKG-02 | 219660.91 | 203219.31 | Approved | 6 | 2024-04-20 | 2024-06-16 | TBM Cutterhead refurbishment and rock fissure sealing
VO-PKG-02-02232 | PKG-02 | 33831.83 | 29042.12 | Approved | 31 | 2024-04-20 | 2024-05-17 | TBM Cutterhead refurbishment and rock fissure sealing
VO-PKG-02-02252 | PKG-02 | 253754.5 | 238531.85 | Approved | 11 | 2024-04-21 | 2024-05-15 | TBM Cutterhead refurbishment and rock fissure sealing
VO-PKG-05-01495 | PKG-05 | 87549.5 | 78829.75 | Approved | 14 | 2024-04-21 | 2024-05-30 | HV substation redundancy transformer capacity upgrade
VO-PKG-05-01625 | PKG-05 | 243310.18 | 0 | Pending Approval | 34 | 2024-04-21 |  | HV substation redundancy transformer capacity upgrade
VO-PKG-01-02031 | PKG-01 | 220126.74 | 0 | Pending Approval | 9 | 2024-04-22 |  | Unforeseen soft ground stabilization and grouting
VO-PKG-02-02372 | PKG-02 | 271971.57 | 0 | Pending Approval | 27 | 2024-04-22 |  | TBM Cutterhead refurbishment and rock fissure sealing
VO-PKG-03-00563 | PKG-03 | 162095.22 | 157157.99 | Approved | 27 | 2024-04-22 | 2024-05-30 | Viaduct pier foundation redesign due to utility clash
VO-PKG-03-01443 | PKG-03 | 226805.46 | 208599.37 | Approved | 13 | 2024-04-22 | 2024-05-11 | Viaduct pier foundation redesign due to utility clash
VO-PKG-04-00614 | PKG-04 | 183920.16 | 150041.45 | Approved | 45 | 2024-04-22 | 2024-05-09 | Station box diaphragm wall water ingress mitigation
VO-PKG-06-00186 | PKG-06 | 227248.67 | 215396.35 | Approved | 13 | 2024-04-22 | 2024-06-12 | Additional smoke evacuation shafts in underground platforms
VO-PKG-08-02658 | PKG-08 | 306673.11 | 0 | Pending Approval | 25 | 2024-04-22 |  | Track vibration damping rubber pads acoustic upgrade
VO-PKG-03-00723 | PKG-03 | 47007.79 | 41435.99 | Approved | 18 | 2024-04-23 | 2024-06-02 | Viaduct pier foundation redesign due to utility clash
VO-PKG-06-02596 | PKG-06 | 329873.49 | 291940.31 | Approved | 47 | 2024-04-23 | 2024-05-18 | Additional smoke evacuation shafts in underground platforms
VO-PKG-06-02676 | PKG-06 | 89152.07 | 86647.96 | Approved | 59 | 2024-04-23 | 2024-05-11 | Additional smoke evacuation shafts in underground platforms
VO-PKG-05-02695 | PKG-05 | 54491.89 | 0 | Rejected | 0 | 2024-04-24 | 2024-05-22 | HV substation redundancy transformer capacity upgrade
VO-PKG-07-01397 | PKG-07 | 135742.6 | 0 | Pending Approval | 21 | 2024-04-24 |  | Fiber optic telemetry routing realignment along guideway
VO-PKG-02-01522 | PKG-02 | 324754.17 | 288459.5 | Approved | 54 | 2024-04-25 | 2024-06-09 | TBM Cutterhead refurbishment and rock fissure sealing
VO-PKG-04-00584 | PKG-04 | 314514.15 | 276777.08 | Approved | 54 | 2024-04-25 | 2024-05-24 | Station box diaphragm wall water ingress mitigation
VO-PKG-06-01906 | PKG-06 | 94562.03 | 82429.77 | Approved | 38 | 2024-04-25 | 2024-05-29 | Additional smoke evacuation shafts in underground platforms
VO-PKG-07-00357 | PKG-07 | 70840.44 | 60067.19 | Approved | 53 | 2024-04-25 | 2024-05-10 | Fiber optic telemetry routing realignment along guideway
VO-PKG-08-00808 | PKG-08 | 125821.72 | 104809.99 | Approved | 18 | 2024-04-25 | 2024-06-04 | Track vibration damping rubber pads acoustic upgrade
VO-PKG-10-00690 | PKG-10 | 312319.17 | 281336.71 | Approved | 15 | 2024-04-25 | 2024-06-17 | HVAC chilled water pipe rerouting around station concourse
VO-PKG-02-01692 | PKG-02 | 140903.45 | 125087.78 | Approved | 18 | 2024-04-26 | 2024-06-11 | TBM Cutterhead refurbishment and rock fissure sealing
VO-PKG-03-01243 | PKG-03 | 165218.85 | 0 | Pending Approval | 11 | 2024-04-26 |  | Viaduct pier foundation redesign due to utility clash
VO-PKG-07-00887 | PKG-07 | 63154.11 | 0 | Pending Approval | 8 | 2024-04-26 |  | Fiber optic telemetry routing realignment along guideway
VO-PKG-02-00142 | PKG-02 | 226793.35 | 213723.24 | Approved | 30 | 2024-04-27 | 2024-06-01 | TBM Cutterhead refurbishment and rock fissure sealing
VO-PKG-05-01465 | PKG-05 | 242628.37 | 202900.64 | Approved | 19 | 2024-04-27 | 2024-06-18 | HV substation redundancy transformer capacity upgrade
VO-PKG-08-00588 | PKG-08 | 48555.84 | 45599.6 | Approved | 42 | 2024-04-27 | 2024-06-16 | Track vibration damping rubber pads acoustic upgrade
VO-PKG-10-00570 | PKG-10 | 342557.59 | 0 | Pending Approval | 14 | 2024-04-27 |  | HVAC chilled water pipe rerouting around station concourse
VO-PKG-02-02792 | PKG-02 | 197701.13 | 166995.96 | Approved | 24 | 2024-04-28 | 2024-05-18 | TBM Cutterhead refurbishment and rock fissure sealing
VO-PKG-05-01415 | PKG-05 | 317692.92 | 272735.23 | Approved | 37 | 2024-04-28 | 2024-06-02 | HV substation redundancy transformer capacity upgrade
VO-PKG-06-02816 | PKG-06 | 130664.85 | 126235.42 | Approved | 37 | 2024-04-28 | 2024-06-09 | Additional smoke evacuation shafts in underground platforms
VO-PKG-09-00269 | PKG-09 | 219974.22 | 0 | Pending Approval | 14 | 2024-04-28 |  | Drainage box culvert capacity expansion for 100-year flood event
VO-PKG-10-01030 | PKG-10 | 43952.61 | 37209.51 | Approved | 38 | 2024-04-28 | 2024-05-27 | HVAC chilled water pipe rerouting around station concourse
VO-PKG-03-02363 | PKG-03 | 313103.16 | 268997.71 | Approved | 56 | 2024-04-29 | 2024-06-09 | Viaduct pier foundation redesign due to utility clash
VO-PKG-06-01436 | PKG-06 | 103668.42 | 0 | Pending Approval | 38 | 2024-04-29 |  | Additional smoke evacuation shafts in underground platforms
VO-PKG-07-01347 | PKG-07 | 189581.3 | 0 | Pending Approval | 29 | 2024-04-29 |  | Fiber optic telemetry routing realignment along guideway
VO-PKG-10-00490 | PKG-10 | 291350.63 | 278305.48 | Approved | 14 | 2024-04-29 | 2024-06-20 | HVAC chilled water pipe rerouting around station concourse
VO-PKG-04-00214 | PKG-04 | 208702.25 | 198133.45 | Approved | 51 | 2024-04-30 | 2024-06-03 | Station box diaphragm wall water ingress mitigation
VO-PKG-07-01377 | PKG-07 | 183376.56 | 177812.9 | Approved | 25 | 2024-04-30 | 2024-06-08 | Fiber optic telemetry routing realignment along guideway
VO-PKG-08-00208 | PKG-08 | 295759.38 | 272930.6 | Approved | 25 | 2024-04-30 | 2024-06-11 | Track vibration damping rubber pads acoustic upgrade
VO-PKG-06-01726 | PKG-06 | 101825.32 | 0 | Rejected | 0 | 2024-05-01 | 2024-05-13 | Additional smoke evacuation shafts in underground platforms
VO-PKG-10-00670 | PKG-10 | 270552.5 | 0 | Pending Approval | 3 | 2024-05-01 |  | HVAC chilled water pipe rerouting around station concourse
VO-PKG-08-01548 | PKG-08 | 17804.34 | 17232.24 | Approved | 17 | 2024-05-02 | 2024-05-21 | Track vibration damping rubber pads acoustic upgrade
VO-PKG-01-00951 | PKG-01 | 174485.12 | 0 | Rejected | 0 | 2024-05-03 | 2024-05-19 | Unforeseen soft ground stabilization and grouting
VO-PKG-01-01921 | PKG-01 | 303522.54 | 0 | Pending Approval | 13 | 2024-05-03 |  | Unforeseen soft ground stabilization and grouting
VO-PKG-03-01783 | PKG-03 | 70019.2 | 0 | Pending Approval | 23 | 2024-05-03 |  | Viaduct pier foundation redesign due to utility clash
VO-PKG-03-01943 | PKG-03 | 61646.44 | 58276.46 | Approved | 8 | 2024-05-03 | 2024-06-17 | Viaduct pier foundation redesign due to utility clash
VO-PKG-09-01159 | PKG-09 | 65292.86 | 60782.11 | Approved | 20 | 2024-05-03 | 2024-06-12 | Drainage box culvert capacity expansion for 100-year flood event
VO-PKG-10-00850 | PKG-10 | 43023.32 | 36917.9 | Approved | 33 | 2024-05-03 | 2024-06-04 | HVAC chilled water pipe rerouting around station concourse
VO-PKG-01-02581 | PKG-01 | 298315.42 | 0 | Pending Approval | 40 | 2024-05-04 |  | Unforeseen soft ground stabilization and grouting
VO-PKG-08-01738 | PKG-08 | 37134.72 | 0 | Pending Approval | 14 | 2024-05-04 |  | Track vibration damping rubber pads acoustic upgrade
VO-PKG-04-01514 | PKG-04 | 147319.8 | 139258.79 | Approved | 32 | 2024-05-05 | 2024-05-26 | Station box diaphragm wall water ingress mitigation
VO-PKG-07-02377 | PKG-07 | 105528.68 | 85034.33 | Approved | 8 | 2024-05-05 | 2024-06-14 | Fiber optic telemetry routing realignment along guideway
VO-PKG-03-00393 | PKG-03 | 152114.17 | 0 | Rejected | 0 | 2024-05-06 | 2024-06-09 | Viaduct pier foundation redesign due to utility clash
VO-PKG-03-00883 | PKG-03 | 34977.32 | 0 | Pending Approval | 13 | 2024-05-06 |  | Viaduct pier foundation redesign due to utility clash
VO-PKG-07-02337 | PKG-07 | 323523.74 | 260725.92 | Approved | 9 | 2024-05-06 | 2024-06-18 | Fiber optic telemetry routing realignment along guideway
VO-PKG-06-01686 | PKG-06 | 327870.2 | 285359.24 | Approved | 51 | 2024-05-07 | 2024-05-22 | Additional smoke evacuation shafts in underground platforms
VO-PKG-05-00435 | PKG-05 | 346056.42 | 0 | Pending Approval | 39 | 2024-05-08 |  | HV substation redundancy transformer capacity upgrade
VO-PKG-09-02599 | PKG-09 | 237585.15 | 209451.65 | Approved | 48 | 2024-05-08 | 2024-05-30 | Drainage box culvert capacity expansion for 100-year flood event
VO-PKG-10-00610 | PKG-10 | 344506.05 | 0 | Pending Approval | 32 | 2024-05-08 |  | HVAC chilled water pipe rerouting around station concourse
VO-PKG-10-02340 | PKG-10 | 171354.68 | 147101.08 | Approved | 41 | 2024-05-08 | 2024-06-08 | HVAC chilled water pipe rerouting around station concourse
VO-PKG-08-00498 | PKG-08 | 139975.67 | 131187.58 | Approved | 19 | 2024-05-09 | 2024-05-28 | Track vibration damping rubber pads acoustic upgrade
VO-PKG-05-01675 | PKG-05 | 48037.04 | 0 | Pending Approval | 38 | 2024-05-12 |  | HV substation redundancy transformer capacity upgrade
VO-PKG-05-01855 | PKG-05 | 30687.42 | 0 | Pending Approval | 44 | 2024-05-12 |  | HV substation redundancy transformer capacity upgrade
VO-PKG-07-01037 | PKG-07 | 212303.01 | 0 | Rejected | 0 | 2024-05-12 | 2024-06-19 | Fiber optic telemetry routing realignment along guideway
VO-PKG-07-02607 | PKG-07 | 40183.22 | 0 | Pending Approval | 36 | 2024-05-12 |  | Fiber optic telemetry routing realignment along guideway
VO-PKG-08-01448 | PKG-08 | 262809.22 | 218102.81 | Approved | 13 | 2024-05-12 | 2024-07-06 | Track vibration damping rubber pads acoustic upgrade
VO-PKG-09-02129 | PKG-09 | 151537.7 | 0 | Pending Approval | 22 | 2024-05-12 |  | Drainage box culvert capacity expansion for 100-year flood event
VO-PKG-02-00322 | PKG-02 | 103936.36 | 0 | Pending Approval | 39 | 2024-05-13 |  | TBM Cutterhead refurbishment and rock fissure sealing
VO-PKG-05-00475 | PKG-05 | 215210.22 | 174036.47 | Approved | 54 | 2024-05-13 | 2024-07-02 | HV substation redundancy transformer capacity upgrade
VO-PKG-06-00736 | PKG-06 | 258805.99 | 238474.66 | Approved | 15 | 2024-05-13 | 2024-06-11 | Additional smoke evacuation shafts in underground platforms
VO-PKG-09-00889 | PKG-09 | 142088.98 | 0 | Pending Approval | 14 | 2024-05-13 |  | Drainage box culvert capacity expansion for 100-year flood event
VO-PKG-01-02111 | PKG-01 | 281204.96 | 0 | Pending Approval | 25 | 2024-05-14 |  | Unforeseen soft ground stabilization and grouting
VO-PKG-02-01812 | PKG-02 | 179925.7 | 0 | Pending Approval | 43 | 2024-05-14 |  | TBM Cutterhead refurbishment and rock fissure sealing
VO-PKG-03-00493 | PKG-03 | 91143.27 | 0 | Pending Approval | 0 | 2024-05-14 |  | Viaduct pier foundation redesign due to utility clash
VO-PKG-09-02349 | PKG-09 | 228099.42 | 0 | Pending Approval | 26 | 2024-05-14 |  | Drainage box culvert capacity expansion for 100-year flood event
VO-PKG-02-02552 | PKG-02 | 275906.36 | 0 | Rejected | 0 | 2024-05-15 | 2024-05-29 | TBM Cutterhead refurbishment and rock fissure sealing
VO-PKG-03-02413 | PKG-03 | 261351.39 | 235879.47 | Approved | 35 | 2024-05-15 | 2024-07-08 | Viaduct pier foundation redesign due to utility clash
VO-PKG-06-02196 | PKG-06 | 86826.92 | 73624.24 | Approved | 36 | 2024-05-15 | 2024-06-16 | Additional smoke evacuation shafts in underground platforms
VO-PKG-10-02730 | PKG-10 | 50389.31 | 0 | Pending Approval | 3 | 2024-05-15 |  | HVAC chilled water pipe rerouting around station concourse
VO-PKG-01-02251 | PKG-01 | 304734.79 | 0 | Pending Approval | 36 | 2024-05-16 |  | Unforeseen soft ground stabilization and grouting
VO-PKG-02-02872 | PKG-02 | 20334.04 | 19603.86 | Approved | 34 | 2024-05-16 | 2024-06-02 | TBM Cutterhead refurbishment and rock fissure sealing
VO-PKG-05-02815 | PKG-05 | 187003.98 | 181685.62 | Approved | 20 | 2024-05-16 | 2024-06-29 | HV substation redundancy transformer capacity upgrade
VO-PKG-06-00776 | PKG-06 | 345229.71 | 303512.13 | Approved | 21 | 2024-05-16 | 2024-06-29 | Additional smoke evacuation shafts in underground platforms
VO-PKG-09-00419 | PKG-09 | 219195.28 | 0 | Rejected | 0 | 2024-05-16 | 2024-06-02 | Drainage box culvert capacity expansion for 100-year flood event
VO-PKG-01-02301 | PKG-01 | 74676.25 | 0 | Pending Approval | 11 | 2024-05-17 |  | Unforeseen soft ground stabilization and grouting
VO-PKG-04-00824 | PKG-04 | 319101.16 | 276048.7 | Approved | 6 | 2024-05-17 | 2024-06-21 | Station box diaphragm wall water ingress mitigation
VO-PKG-07-00857 | PKG-07 | 63689.93 | 0 | Rejected | 0 | 2024-05-17 | 2024-06-14 | Fiber optic telemetry routing realignment along guideway
VO-PKG-08-01368 | PKG-08 | 41293.27 | 0 | Rejected | 0 | 2024-05-17 | 2024-06-01 | Track vibration damping rubber pads acoustic upgrade
VO-PKG-08-02448 | PKG-08 | 249146.04 | 238368.54 | Approved | 6 | 2024-05-17 | 2024-06-21 | Track vibration damping rubber pads acoustic upgrade
VO-PKG-09-01479 | PKG-09 | 27772.94 | 0 | Rejected | 0 | 2024-05-17 | 2024-06-05 | Drainage box culvert capacity expansion for 100-year flood event
VO-PKG-10-02530 | PKG-10 | 268011.89 | 252067.42 | Approved | 51 | 2024-05-17 | 2024-06-18 | HVAC chilled water pipe rerouting around station concourse
VO-PKG-03-01403 | PKG-03 | 55111.82 | 0 | Pending Approval | 31 | 2024-05-18 |  | Viaduct pier foundation redesign due to utility clash
VO-PKG-04-00844 | PKG-04 | 126078.47 | 0 | Pending Approval | 9 | 2024-05-18 |  | Station box diaphragm wall water ingress mitigation
VO-PKG-04-01464 | PKG-04 | 125688.85 | 0 | Rejected | 0 | 2024-05-18 | 2024-06-22 | Station box diaphragm wall water ingress mitigation
VO-PKG-04-02874 | PKG-04 | 147939.74 | 130700.71 | Approved | 11 | 2024-05-18 | 2024-07-12 | Station box diaphragm wall water ingress mitigation
VO-PKG-05-01515 | PKG-05 | 164398.1 | 148125.2 | Approved | 55 | 2024-05-18 | 2024-06-07 | HV substation redundancy transformer capacity upgrade
VO-PKG-07-02167 | PKG-07 | 128962.78 | 108974.89 | Approved | 29 | 2024-05-18 | 2024-06-13 | Fiber optic telemetry routing realignment along guideway
VO-PKG-08-01968 | PKG-08 | 238671.63 | 0 | Pending Approval | 5 | 2024-05-18 |  | Track vibration damping rubber pads acoustic upgrade
VO-PKG-03-02453 | PKG-03 | 335105.05 | 0 | Rejected | 0 | 2024-05-19 | 2024-06-23 | Viaduct pier foundation redesign due to utility clash
VO-PKG-04-00674 | PKG-04 | 262619.39 | 0 | Pending Approval | 0 | 2024-05-19 |  | Station box diaphragm wall water ingress mitigation
VO-PKG-04-02664 | PKG-04 | 256159.15 | 239336.87 | Approved | 31 | 2024-05-19 | 2024-06-27 | Station box diaphragm wall water ingress mitigation
VO-PKG-09-00969 | PKG-09 | 124526.89 | 102094.79 | Approved | 31 | 2024-05-19 | 2024-06-16 | Drainage box culvert capacity expansion for 100-year flood event
VO-PKG-09-01549 | PKG-09 | 67758.69 | 0 | Rejected | 0 | 2024-05-19 | 2024-06-18 | Drainage box culvert capacity expansion for 100-year flood event
VO-PKG-07-02537 | PKG-07 | 264909.4 | 240702.88 | Approved | 27 | 2024-05-20 | 2024-06-24 | Fiber optic telemetry routing realignment along guideway
VO-PKG-08-00188 | PKG-08 | 55095.85 | 0 | Pending Approval | 38 | 2024-05-20 |  | Track vibration damping rubber pads acoustic upgrade
VO-PKG-08-00238 | PKG-08 | 151890.97 | 125148.59 | Approved | 52 | 2024-05-21 | 2024-06-18 | Track vibration damping rubber pads acoustic upgrade
VO-PKG-10-00030 | PKG-10 | 213849.63 | 0 | Pending Approval | 38 | 2024-05-21 |  | HVAC chilled water pipe rerouting around station concourse
VO-PKG-10-00780 | PKG-10 | 94866.67 | 0 | Pending Approval | 13 | 2024-05-21 |  | HVAC chilled water pipe rerouting around station concourse
VO-PKG-08-01408 | PKG-08 | 63210.2 | 56689.92 | Approved | 56 | 2024-05-22 | 2024-06-13 | Track vibration damping rubber pads acoustic upgrade
VO-PKG-09-01459 | PKG-09 | 87143.88 | 75834 | Approved | 11 | 2024-05-22 | 2024-07-03 | Drainage box culvert capacity expansion for 100-year flood event
VO-PKG-10-01060 | PKG-10 | 330844.52 | 0 | Rejected | 0 | 2024-05-22 | 2024-06-12 | HVAC chilled water pipe rerouting around station concourse
VO-PKG-03-01033 | PKG-03 | 76784.69 | 65367.38 | Approved | 11 | 2024-05-23 | 2024-06-16 | Viaduct pier foundation redesign due to utility clash
VO-PKG-04-00174 | PKG-04 | 237365.61 | 0 | Pending Approval | 9 | 2024-05-23 |  | Station box diaphragm wall water ingress mitigation
VO-PKG-05-00695 | PKG-05 | 259359.94 | 0 | Pending Approval | 29 | 2024-05-23 |  | HV substation redundancy transformer capacity upgrade
VO-PKG-10-01810 | PKG-10 | 168056.33 | 136097.14 | Approved | 33 | 2024-05-23 | 2024-06-23 | HVAC chilled water pipe rerouting around station concourse
VO-PKG-10-02660 | PKG-10 | 231186.9 | 221057.82 | Approved | 22 | 2024-05-23 | 2024-06-22 | HVAC chilled water pipe rerouting around station concourse
VO-PKG-02-00942 | PKG-02 | 121555.81 | 102239.49 | Approved | 36 | 2024-05-24 | 2024-06-18 | TBM Cutterhead refurbishment and rock fissure sealing
VO-PKG-08-01578 | PKG-08 | 320206.47 | 303542.76 | Approved | 40 | 2024-05-24 | 2024-07-22 | Track vibration damping rubber pads acoustic upgrade
VO-PKG-01-01031 | PKG-01 | 71106.47 | 0 | Pending Approval | 44 | 2024-05-25 |  | Unforeseen soft ground stabilization and grouting
VO-PKG-06-00476 | PKG-06 | 51428.6 | 48585.49 | Approved | 5 | 2024-05-25 | 2024-06-23 | Additional smoke evacuation shafts in underground platforms
VO-PKG-07-01607 | PKG-07 | 179693.59 | 161976.61 | Approved | 9 | 2024-05-25 | 2024-06-22 | Fiber optic telemetry routing realignment along guideway
VO-PKG-02-00882 | PKG-02 | 203995.27 | 0 | Pending Approval | 35 | 2024-05-26 |  | TBM Cutterhead refurbishment and rock fissure sealing
VO-PKG-03-01163 | PKG-03 | 241520 | 209823.75 | Approved | 8 | 2024-05-26 | 2024-07-20 | Viaduct pier foundation redesign due to utility clash
VO-PKG-04-00974 | PKG-04 | 240469.93 | 234770.62 | Approved | 5 | 2024-05-26 | 2024-07-17 | Station box diaphragm wall water ingress mitigation
VO-PKG-06-01956 | PKG-06 | 257894.67 | 0 | Pending Approval | 40 | 2024-05-26 |  | Additional smoke evacuation shafts in underground platforms
VO-PKG-10-00860 | PKG-10 | 269147.62 | 0 | Pending Approval | 13 | 2024-05-27 |  | HVAC chilled water pipe rerouting around station concourse
VO-PKG-01-00041 | PKG-01 | 112657.55 | 0 | Pending Approval | 12 | 2024-05-28 |  | Unforeseen soft ground stabilization and grouting
VO-PKG-01-00601 | PKG-01 | 252824.87 | 215984.06 | Approved | 12 | 2024-05-28 | 2024-07-21 | Unforeseen soft ground stabilization and grouting
VO-PKG-01-01841 | PKG-01 | 20707.36 | 18367.15 | Approved | 16 | 2024-05-28 | 2024-06-22 | Unforeseen soft ground stabilization and grouting
VO-PKG-03-02703 | PKG-03 | 188076.16 | 152333.79 | Approved | 21 | 2024-05-28 | 2024-06-29 | Viaduct pier foundation redesign due to utility clash
VO-PKG-04-01994 | PKG-04 | 329489.81 | 295603.52 | Approved | 11 | 2024-05-28 | 2024-07-16 | Station box diaphragm wall water ingress mitigation
VO-PKG-05-01485 | PKG-05 | 213239.89 | 186479.57 | Approved | 48 | 2024-05-28 | 2024-07-25 | HV substation redundancy transformer capacity upgrade
VO-PKG-05-02175 | PKG-05 | 48454.18 | 39319.31 | Approved | 16 | 2024-05-28 | 2024-07-15 | HV substation redundancy transformer capacity upgrade
VO-PKG-03-00983 | PKG-03 | 46878.36 | 41314.25 | Approved | 58 | 2024-05-29 | 2024-06-24 | Viaduct pier foundation redesign due to utility clash
VO-PKG-04-00494 | PKG-04 | 314543.66 | 0 | Pending Approval | 21 | 2024-05-29 |  | Station box diaphragm wall water ingress mitigation
VO-PKG-04-01724 | PKG-04 | 69030.69 | 0 | Pending Approval | 17 | 2024-05-29 |  | Station box diaphragm wall water ingress mitigation
VO-PKG-08-02178 | PKG-08 | 290355.68 | 0 | Pending Approval | 25 | 2024-05-29 |  | Track vibration damping rubber pads acoustic upgrade
VO-PKG-02-01582 | PKG-02 | 96492.15 | 82944.74 | Approved | 26 | 2024-05-30 | 2024-06-16 | TBM Cutterhead refurbishment and rock fissure sealing
VO-PKG-07-02507 | PKG-07 | 150978.39 | 129548.52 | Approved | 55 | 2024-05-30 | 2024-06-24 | Fiber optic telemetry routing realignment along guideway
VO-PKG-10-00120 | PKG-10 | 270951.41 | 237136.82 | Approved | 43 | 2024-05-30 | 2024-07-27 | HVAC chilled water pipe rerouting around station concourse
VO-PKG-10-01690 | PKG-10 | 345674.47 | 295323.91 | Approved | 11 | 2024-05-30 | 2024-06-28 | HVAC chilled water pipe rerouting around station concourse
VO-PKG-01-00261 | PKG-01 | 298225.06 | 0 | Pending Approval | 32 | 2024-05-31 |  | Unforeseen soft ground stabilization and grouting
VO-PKG-02-00212 | PKG-02 | 336223.42 | 0 | Pending Approval | 34 | 2024-05-31 |  | TBM Cutterhead refurbishment and rock fissure sealing
VO-PKG-04-00264 | PKG-04 | 52550.04 | 42703.94 | Approved | 27 | 2024-06-01 | 2024-07-19 | Station box diaphragm wall water ingress mitigation
VO-PKG-01-00221 | PKG-01 | 278896.4 | 0 | Pending Approval | 11 | 2024-06-02 |  | Unforeseen soft ground stabilization and grouting
VO-PKG-03-02223 | PKG-03 | 225451.37 | 210108.27 | Approved | 41 | 2024-06-02 | 2024-07-18 | Viaduct pier foundation redesign due to utility clash
VO-PKG-07-00897 | PKG-07 | 236741.12 | 195762.34 | Approved | 45 | 2024-06-02 | 2024-06-29 | Fiber optic telemetry routing realignment along guideway
VO-PKG-08-00168 | PKG-08 | 47214.17 | 41873.42 | Approved | 53 | 2024-06-02 | 2024-06-29 | Track vibration damping rubber pads acoustic upgrade
VO-PKG-02-00262 | PKG-02 | 89209.11 | 85996.24 | Approved | 54 | 2024-06-03 | 2024-07-18 | TBM Cutterhead refurbishment and rock fissure sealing
VO-PKG-06-00296 | PKG-06 | 215242.93 | 0 | Pending Approval | 43 | 2024-06-03 |  | Additional smoke evacuation shafts in underground platforms
VO-PKG-08-01948 | PKG-08 | 171213.76 | 0 | Pending Approval | 3 | 2024-06-03 |  | Track vibration damping rubber pads acoustic upgrade
VO-PKG-08-02218 | PKG-08 | 38858.15 | 34819.41 | Approved | 30 | 2024-06-03 | 2024-07-01 | Track vibration damping rubber pads acoustic upgrade
VO-PKG-10-00700 | PKG-10 | 30516.17 | 26246.49 | Approved | 58 | 2024-06-03 | 2024-07-09 | HVAC chilled water pipe rerouting around station concourse
VO-PKG-01-00791 | PKG-01 | 253842.96 | 243731.82 | Approved | 27 | 2024-06-04 | 2024-06-19 | Unforeseen soft ground stabilization and grouting
VO-PKG-04-01524 | PKG-04 | 161160.13 | 145004.77 | Approved | 28 | 2024-06-04 | 2024-06-22 | Station box diaphragm wall water ingress mitigation
VO-PKG-10-01730 | PKG-10 | 154153.44 | 0 | Rejected | 0 | 2024-06-04 | 2024-06-16 | HVAC chilled water pipe rerouting around station concourse
VO-PKG-02-00922 | PKG-02 | 118280.23 | 111744.18 | Approved | 30 | 2024-06-05 | 2024-07-23 | TBM Cutterhead refurbishment and rock fissure sealing
VO-PKG-05-01585 | PKG-05 | 42987.73 | 35367.61 | Approved | 42 | 2024-06-05 | 2024-07-13 | HV substation redundancy transformer capacity upgrade
VO-PKG-10-01160 | PKG-10 | 190587.84 | 0 | Pending Approval | 43 | 2024-06-05 |  | HVAC chilled water pipe rerouting around station concourse
VO-PKG-03-01183 | PKG-03 | 323068.45 | 289964.72 | Approved | 13 | 2024-06-06 | 2024-07-02 | Viaduct pier foundation redesign due to utility clash
VO-PKG-05-00605 | PKG-05 | 327873.88 | 305012.13 | Approved | 41 | 2024-06-06 | 2024-06-28 | HV substation redundancy transformer capacity upgrade
VO-PKG-05-02105 | PKG-05 | 260265.65 | 229476.25 | Approved | 5 | 2024-06-06 | 2024-07-20 | HV substation redundancy transformer capacity upgrade
VO-PKG-06-02226 | PKG-06 | 281320.62 | 0 | Rejected | 0 | 2024-06-06 | 2024-07-14 | Additional smoke evacuation shafts in underground platforms
VO-PKG-07-01497 | PKG-07 | 23851.5 | 20110.32 | Approved | 41 | 2024-06-06 | 2024-07-30 | Fiber optic telemetry routing realignment along guideway
VO-PKG-04-01804 | PKG-04 | 145913.83 | 141274.4 | Approved | 58 | 2024-06-07 | 2024-07-05 | Station box diaphragm wall water ingress mitigation
VO-PKG-01-00881 | PKG-01 | 169155.43 | 160570.74 | Approved | 48 | 2024-06-08 | 2024-07-09 | Unforeseen soft ground stabilization and grouting
VO-PKG-02-00912 | PKG-02 | 56224.33 | 0 | Rejected | 0 | 2024-06-08 | 2024-06-30 | TBM Cutterhead refurbishment and rock fissure sealing
VO-PKG-03-01503 | PKG-03 | 232892.65 | 0 | Pending Approval | 3 | 2024-06-08 |  | Viaduct pier foundation redesign due to utility clash
VO-PKG-06-00916 | PKG-06 | 116205.54 | 104441.41 | Approved | 15 | 2024-06-08 | 2024-07-03 | Additional smoke evacuation shafts in underground platforms
VO-PKG-06-02326 | PKG-06 | 89750.13 | 78540.49 | Approved | 51 | 2024-06-08 | 2024-07-15 | Additional smoke evacuation shafts in underground platforms
VO-PKG-09-01719 | PKG-09 | 194593.57 | 0 | Pending Approval | 30 | 2024-06-08 |  | Drainage box culvert capacity expansion for 100-year flood event
VO-PKG-03-00633 | PKG-03 | 349561.98 | 329826.18 | Approved | 8 | 2024-06-09 | 2024-07-29 | Viaduct pier foundation redesign due to utility clash
VO-PKG-05-00615 | PKG-05 | 218977.78 | 196721.89 | Approved | 16 | 2024-06-09 | 2024-07-25 | HV substation redundancy transformer capacity upgrade
VO-PKG-07-02157 | PKG-07 | 338127.26 | 288772.2 | Approved | 37 | 2024-06-09 | 2024-07-27 | Fiber optic telemetry routing realignment along guideway
VO-PKG-07-02987 | PKG-07 | 248533.6 | 0 | Pending Approval | 24 | 2024-06-09 |  | Fiber optic telemetry routing realignment along guideway
VO-PKG-10-01330 | PKG-10 | 151368.85 | 0 | Pending Approval | 43 | 2024-06-09 |  | HVAC chilled water pipe rerouting around station concourse
VO-PKG-01-01091 | PKG-01 | 291846.11 | 235889.59 | Approved | 56 | 2024-06-10 | 2024-08-02 | Unforeseen soft ground stabilization and grouting
VO-PKG-02-01242 | PKG-02 | 88926.33 | 0 | Pending Approval | 2 | 2024-06-10 |  | TBM Cutterhead refurbishment and rock fissure sealing
VO-PKG-02-02912 | PKG-02 | 132620.92 | 122698.12 | Approved | 58 | 2024-06-10 | 2024-08-03 | TBM Cutterhead refurbishment and rock fissure sealing
VO-PKG-04-02284 | PKG-04 | 222680.53 | 204462.59 | Approved | 16 | 2024-06-10 | 2024-07-06 | Station box diaphragm wall water ingress mitigation
VO-PKG-07-00167 | PKG-07 | 273393.27 | 237838.54 | Approved | 24 | 2024-06-10 | 2024-07-23 | Fiber optic telemetry routing realignment along guideway
VO-PKG-07-00317 | PKG-07 | 218344.9 | 176418.7 | Approved | 6 | 2024-06-10 | 2024-07-01 | Fiber optic telemetry routing realignment along guideway
VO-PKG-09-01929 | PKG-09 | 145259.87 | 120315.18 | Approved | 59 | 2024-06-10 | 2024-07-28 | Drainage box culvert capacity expansion for 100-year flood event
VO-PKG-02-00642 | PKG-02 | 95879.67 | 79173.01 | Approved | 32 | 2024-06-11 | 2024-07-12 | TBM Cutterhead refurbishment and rock fissure sealing
VO-PKG-04-02754 | PKG-04 | 34978.35 | 0 | Pending Approval | 35 | 2024-06-11 |  | Station box diaphragm wall water ingress mitigation
VO-PKG-09-01989 | PKG-09 | 334767 | 297426 | Approved | 26 | 2024-06-11 | 2024-07-08 | Drainage box culvert capacity expansion for 100-year flood event
VO-PKG-10-02420 | PKG-10 | 190568.56 | 158969.97 | Approved | 19 | 2024-06-11 | 2024-06-26 | HVAC chilled water pipe rerouting around station concourse
VO-PKG-01-01781 | PKG-01 | 187744.14 | 154908.71 | Approved | 18 | 2024-06-12 | 2024-08-03 | Unforeseen soft ground stabilization and grouting
VO-PKG-02-01062 | PKG-02 | 223058.24 | 213965.68 | Approved | 43 | 2024-06-12 | 2024-06-29 | TBM Cutterhead refurbishment and rock fissure sealing
VO-PKG-02-02022 | PKG-02 | 272850.72 | 222556.87 | Approved | 44 | 2024-06-12 | 2024-07-30 | TBM Cutterhead refurbishment and rock fissure sealing
VO-PKG-03-01053 | PKG-03 | 99055.34 | 85964.04 | Approved | 40 | 2024-06-12 | 2024-08-02 | Viaduct pier foundation redesign due to utility clash
VO-PKG-06-00096 | PKG-06 | 244020.21 | 236047.44 | Approved | 31 | 2024-06-12 | 2024-06-30 | Additional smoke evacuation shafts in underground platforms
VO-PKG-06-02896 | PKG-06 | 337932.47 | 327152 | Approved | 27 | 2024-06-12 | 2024-07-15 | Additional smoke evacuation shafts in underground platforms
VO-PKG-07-00017 | PKG-07 | 46366.04 | 39747.4 | Approved | 45 | 2024-06-12 | 2024-07-23 | Fiber optic telemetry routing realignment along guideway
VO-PKG-02-00452 | PKG-02 | 102186.61 | 99891.72 | Approved | 40 | 2024-06-13 | 2024-07-01 | TBM Cutterhead refurbishment and rock fissure sealing
VO-PKG-06-02646 | PKG-06 | 281771.08 | 0 | Pending Approval | 41 | 2024-06-13 |  | Additional smoke evacuation shafts in underground platforms
VO-PKG-06-02726 | PKG-06 | 195012.82 | 168949.77 | Approved | 35 | 2024-06-13 | 2024-07-03 | Additional smoke evacuation shafts in underground platforms
VO-PKG-08-00788 | PKG-08 | 66680.89 | 55854.42 | Approved | 32 | 2024-06-13 | 2024-07-31 | Track vibration damping rubber pads acoustic upgrade
VO-PKG-01-01731 | PKG-01 | 179184.63 | 0 | Rejected | 0 | 2024-06-14 | 2024-06-29 | Unforeseen soft ground stabilization and grouting
VO-PKG-03-01873 | PKG-03 | 38709.8 | 0 | Rejected | 0 | 2024-06-15 | 2024-07-29 | Viaduct pier foundation redesign due to utility clash
VO-PKG-10-02100 | PKG-10 | 225447.26 | 0 | Pending Approval | 10 | 2024-06-15 |  | HVAC chilled water pipe rerouting around station concourse
VO-PKG-05-00155 | PKG-05 | 214669 | 204428.4 | Approved | 13 | 2024-06-16 | 2024-07-25 | HV substation redundancy transformer capacity upgrade
VO-PKG-06-00946 | PKG-06 | 89494.62 | 80689.14 | Approved | 49 | 2024-06-16 | 2024-07-12 | Additional smoke evacuation shafts in underground platforms
VO-PKG-09-02929 | PKG-09 | 76515.96 | 71069.04 | Approved | 12 | 2024-06-16 | 2024-07-16 | Drainage box culvert capacity expansion for 100-year flood event
VO-PKG-10-01340 | PKG-10 | 316112.85 | 0 | Pending Approval | 43 | 2024-06-16 |  | HVAC chilled water pipe rerouting around station concourse
VO-PKG-01-00521 | PKG-01 | 224435.02 | 199118.57 | Approved | 29 | 2024-06-17 | 2024-08-09 | Unforeseen soft ground stabilization and grouting
VO-PKG-02-00162 | PKG-02 | 204809.08 | 169499.07 | Approved | 5 | 2024-06-17 | 2024-07-04 | TBM Cutterhead refurbishment and rock fissure sealing
VO-PKG-08-01508 | PKG-08 | 287354.41 | 0 | Pending Approval | 8 | 2024-06-17 |  | Track vibration damping rubber pads acoustic upgrade
VO-PKG-08-02728 | PKG-08 | 289872.86 | 237288.64 | Approved | 51 | 2024-06-18 | 2024-07-03 | Track vibration damping rubber pads acoustic upgrade
VO-PKG-01-00311 | PKG-01 | 126968.98 | 105558.44 | Approved | 34 | 2024-06-19 | 2024-08-07 | Unforeseen soft ground stabilization and grouting
VO-PKG-01-00851 | PKG-01 | 59199.06 | 55632.25 | Approved | 34 | 2024-06-19 | 2024-07-24 | Unforeseen soft ground stabilization and grouting
VO-PKG-03-00653 | PKG-03 | 199463.06 | 170846.13 | Approved | 46 | 2024-06-19 | 2024-08-03 | Viaduct pier foundation redesign due to utility clash
VO-PKG-01-00981 | PKG-01 | 122795.86 | 106234.02 | Approved | 6 | 2024-06-20 | 2024-07-25 | Unforeseen soft ground stabilization and grouting
VO-PKG-07-00367 | PKG-07 | 139950.94 | 0 | Pending Approval | 33 | 2024-06-20 |  | Fiber optic telemetry routing realignment along guideway
VO-PKG-09-01579 | PKG-09 | 172208.15 | 0 | Pending Approval | 40 | 2024-06-20 |  | Drainage box culvert capacity expansion for 100-year flood event
VO-PKG-03-01593 | PKG-03 | 57930.35 | 0 | Pending Approval | 20 | 2024-06-21 |  | Viaduct pier foundation redesign due to utility clash
VO-PKG-01-01581 | PKG-01 | 130333.8 | 125165.11 | Approved | 45 | 2024-06-22 | 2024-07-24 | Unforeseen soft ground stabilization and grouting
VO-PKG-08-01088 | PKG-08 | 127393.45 | 0 | Pending Approval | 24 | 2024-06-22 |  | Track vibration damping rubber pads acoustic upgrade
VO-PKG-09-00359 | PKG-09 | 148795.55 | 141068.44 | Approved | 26 | 2024-06-22 | 2024-07-21 | Drainage box culvert capacity expansion for 100-year flood event
VO-PKG-09-01439 | PKG-09 | 294331.4 | 240326.19 | Approved | 27 | 2024-06-22 | 2024-07-12 | Drainage box culvert capacity expansion for 100-year flood event
VO-PKG-09-01799 | PKG-09 | 197121.84 | 188468.87 | Approved | 26 | 2024-06-22 | 2024-07-17 | Drainage box culvert capacity expansion for 100-year flood event
VO-PKG-01-00181 | PKG-01 | 157123.37 | 0 | Pending Approval | 8 | 2024-06-23 |  | Unforeseen soft ground stabilization and grouting
VO-PKG-01-02971 | PKG-01 | 275250.33 | 0 | Rejected | 0 | 2024-06-23 | 2024-07-13 | Unforeseen soft ground stabilization and grouting
VO-PKG-08-01558 | PKG-08 | 60340.51 | 52740.76 | Approved | 32 | 2024-06-23 | 2024-07-08 | Track vibration damping rubber pads acoustic upgrade
VO-PKG-05-00385 | PKG-05 | 88889.5 | 83621.97 | Approved | 25 | 2024-06-24 | 2024-07-31 | HV substation redundancy transformer capacity upgrade
VO-PKG-06-00366 | PKG-06 | 24535.18 | 21890.43 | Approved | 10 | 2024-06-24 | 2024-07-15 | Additional smoke evacuation shafts in underground platforms
VO-PKG-04-01294 | PKG-04 | 170403.04 | 160081.6 | Approved | 16 | 2024-06-25 | 2024-08-15 | Station box diaphragm wall water ingress mitigation
VO-PKG-08-00148 | PKG-08 | 59592.39 | 0 | Rejected | 0 | 2024-06-25 | 2024-08-04 | Track vibration damping rubber pads acoustic upgrade
VO-PKG-08-02338 | PKG-08 | 294499.51 | 0 | Pending Approval | 29 | 2024-06-25 |  | Track vibration damping rubber pads acoustic upgrade
VO-PKG-03-01853 | PKG-03 | 248342.78 | 206270.87 | Approved | 37 | 2024-06-26 | 2024-07-23 | Viaduct pier foundation redesign due to utility clash
VO-PKG-03-02763 | PKG-03 | 229777.92 | 214157.69 | Approved | 58 | 2024-06-26 | 2024-08-08 | Viaduct pier foundation redesign due to utility clash
VO-PKG-05-02975 | PKG-05 | 304581.66 | 273572.83 | Approved | 42 | 2024-06-26 | 2024-08-07 | HV substation redundancy transformer capacity upgrade
VO-PKG-08-02468 | PKG-08 | 228475.24 | 0 | Rejected | 0 | 2024-06-26 | 2024-08-07 | Track vibration damping rubber pads acoustic upgrade
VO-PKG-01-00771 | PKG-01 | 87020.57 | 71989.03 | Approved | 25 | 2024-06-27 | 2024-08-06 | Unforeseen soft ground stabilization and grouting
VO-PKG-01-00931 | PKG-01 | 98191.4 | 79917.95 | Approved | 47 | 2024-06-27 | 2024-07-30 | Unforeseen soft ground stabilization and grouting
VO-PKG-02-00992 | PKG-02 | 313866.76 | 0 | Rejected | 0 | 2024-06-27 | 2024-07-22 | TBM Cutterhead refurbishment and rock fissure sealing
VO-PKG-05-02335 | PKG-05 | 288617.45 | 0 | Pending Approval | 27 | 2024-06-27 |  | HV substation redundancy transformer capacity upgrade
VO-PKG-06-01646 | PKG-06 | 103795.54 | 0 | Rejected | 0 | 2024-06-27 | 2024-07-15 | Additional smoke evacuation shafts in underground platforms
VO-PKG-07-02007 | PKG-07 | 75784.81 | 0 | Pending Approval | 30 | 2024-06-27 |  | Fiber optic telemetry routing realignment along guideway
VO-PKG-08-00318 | PKG-08 | 32598.88 | 0 | Pending Approval | 14 | 2024-06-27 |  | Track vibration damping rubber pads acoustic upgrade
VO-PKG-02-02652 | PKG-02 | 90453.98 | 74584.19 | Approved | 36 | 2024-06-28 | 2024-07-19 | TBM Cutterhead refurbishment and rock fissure sealing
VO-PKG-03-01903 | PKG-03 | 177698.54 | 166171.12 | Approved | 59 | 2024-06-28 | 2024-08-19 | Viaduct pier foundation redesign due to utility clash
VO-PKG-06-01446 | PKG-06 | 213433.91 | 205225.36 | Approved | 29 | 2024-06-28 | 2024-07-25 | Additional smoke evacuation shafts in underground platforms
VO-PKG-08-01058 | PKG-08 | 348965.3 | 0 | Pending Approval | 20 | 2024-06-28 |  | Track vibration damping rubber pads acoustic upgrade
VO-PKG-02-00982 | PKG-02 | 319153.12 | 0 | Pending Approval | 25 | 2024-06-29 |  | TBM Cutterhead refurbishment and rock fissure sealing
VO-PKG-09-00919 | PKG-09 | 240026.38 | 208271.69 | Approved | 25 | 2024-06-29 | 2024-08-26 | Drainage box culvert capacity expansion for 100-year flood event
VO-PKG-10-00870 | PKG-10 | 119362.35 | 0 | Pending Approval | 4 | 2024-06-29 |  | HVAC chilled water pipe rerouting around station concourse
VO-PKG-10-02280 | PKG-10 | 155189.11 | 132446.62 | Approved | 57 | 2024-06-29 | 2024-08-01 | HVAC chilled water pipe rerouting around station concourse
VO-PKG-10-02780 | PKG-10 | 37866.31 | 0 | Pending Approval | 18 | 2024-06-29 |  | HVAC chilled water pipe rerouting around station concourse
VO-PKG-03-01143 | PKG-03 | 107998.39 | 0 | Pending Approval | 37 | 2024-06-30 |  | Viaduct pier foundation redesign due to utility clash
VO-PKG-04-01494 | PKG-04 | 112192.17 | 0 | Rejected | 0 | 2024-06-30 | 2024-07-24 | Station box diaphragm wall water ingress mitigation
VO-PKG-08-01978 | PKG-08 | 347243.06 | 297210.03 | Approved | 49 | 2024-06-30 | 2024-08-23 | Track vibration damping rubber pads acoustic upgrade
VO-PKG-09-02829 | PKG-09 | 27440.61 | 25446.25 | Approved | 43 | 2024-06-30 | 2024-08-02 | Drainage box culvert capacity expansion for 100-year flood event
VO-PKG-01-01751 | PKG-01 | 330208.58 | 311142.18 | Approved | 55 | 2024-07-01 | 2024-08-22 | Unforeseen soft ground stabilization and grouting
VO-PKG-06-00786 | PKG-06 | 194702.22 | 0 | Pending Approval | 37 | 2024-07-01 |  | Additional smoke evacuation shafts in underground platforms
VO-PKG-07-01077 | PKG-07 | 103573.18 | 90689.19 | Approved | 44 | 2024-07-01 | 2024-07-27 | Fiber optic telemetry routing realignment along guideway
VO-PKG-10-01590 | PKG-10 | 49582.32 | 46969.2 | Approved | 8 | 2024-07-01 | 2024-08-22 | HVAC chilled water pipe rerouting around station concourse
VO-PKG-01-00431 | PKG-01 | 47826.87 | 0 | Pending Approval | 22 | 2024-07-02 |  | Unforeseen soft ground stabilization and grouting
VO-PKG-04-01854 | PKG-04 | 158524.15 | 137129.06 | Approved | 5 | 2024-07-02 | 2024-08-07 | Station box diaphragm wall water ingress mitigation
VO-PKG-08-02638 | PKG-08 | 154009.19 | 0 | Pending Approval | 6 | 2024-07-02 |  | Track vibration damping rubber pads acoustic upgrade
VO-PKG-08-02748 | PKG-08 | 47959.08 | 46367.84 | Approved | 40 | 2024-07-02 | 2024-08-05 | Track vibration damping rubber pads acoustic upgrade
VO-PKG-02-02082 | PKG-02 | 159397.93 | 0 | Pending Approval | 9 | 2024-07-03 |  | TBM Cutterhead refurbishment and rock fissure sealing
VO-PKG-03-00213 | PKG-03 | 298621.87 | 0 | Pending Approval | 1 | 2024-07-03 |  | Viaduct pier foundation redesign due to utility clash
VO-PKG-04-01554 | PKG-04 | 193044.11 | 160552.58 | Approved | 38 | 2024-07-03 | 2024-08-21 | Station box diaphragm wall water ingress mitigation
VO-PKG-04-02824 | PKG-04 | 298879.49 | 239814.51 | Approved | 30 | 2024-07-03 | 2024-08-06 | Station box diaphragm wall water ingress mitigation
VO-PKG-08-01378 | PKG-08 | 337611.03 | 325933.53 | Approved | 29 | 2024-07-03 | 2024-08-21 | Track vibration damping rubber pads acoustic upgrade
VO-PKG-08-02788 | PKG-08 | 318128.77 | 276622.63 | Approved | 13 | 2024-07-03 | 2024-07-25 | Track vibration damping rubber pads acoustic upgrade
VO-PKG-01-01161 | PKG-01 | 327300.16 | 0 | Pending Approval | 14 | 2024-07-04 |  | Unforeseen soft ground stabilization and grouting
VO-PKG-02-01922 | PKG-02 | 326995.72 | 0 | Pending Approval | 19 | 2024-07-04 |  | TBM Cutterhead refurbishment and rock fissure sealing
VO-PKG-06-00396 | PKG-06 | 275589.86 | 267454.55 | Approved | 54 | 2024-07-04 | 2024-07-28 | Additional smoke evacuation shafts in underground platforms
VO-PKG-01-02451 | PKG-01 | 257245.15 | 0 | Pending Approval | 27 | 2024-07-05 |  | Unforeseen soft ground stabilization and grouting
VO-PKG-04-01094 | PKG-04 | 35168.49 | 0 | Pending Approval | 42 | 2024-07-06 |  | Station box diaphragm wall water ingress mitigation
VO-PKG-07-01237 | PKG-07 | 92967.6 | 0 | Pending Approval | 36 | 2024-07-06 |  | Fiber optic telemetry routing realignment along guideway
VO-PKG-08-02358 | PKG-08 | 70938.57 | 67190.03 | Approved | 14 | 2024-07-06 | 2024-08-06 | Track vibration damping rubber pads acoustic upgrade
VO-PKG-08-02588 | PKG-08 | 161019.06 | 152189.93 | Approved | 30 | 2024-07-06 | 2024-07-23 | Track vibration damping rubber pads acoustic upgrade
VO-PKG-09-01829 | PKG-09 | 302904.1 | 254241.92 | Approved | 39 | 2024-07-06 | 2024-08-06 | Drainage box culvert capacity expansion for 100-year flood event
VO-PKG-04-00424 | PKG-04 | 50626.8 | 43056.45 | Approved | 14 | 2024-07-07 | 2024-08-31 | Station box diaphragm wall water ingress mitigation
VO-PKG-05-02495 | PKG-05 | 344685.46 | 0 | Rejected | 0 | 2024-07-07 | 2024-07-20 | HV substation redundancy transformer capacity upgrade
VO-PKG-05-02825 | PKG-05 | 323445.12 | 0 | Pending Approval | 23 | 2024-07-07 |  | HV substation redundancy transformer capacity upgrade
VO-PKG-07-00447 | PKG-07 | 349342.21 | 306357.38 | Approved | 53 | 2024-07-07 | 2024-08-07 | Fiber optic telemetry routing realignment along guideway
VO-PKG-07-01647 | PKG-07 | 241794.16 | 204797.11 | Approved | 32 | 2024-07-07 | 2024-08-21 | Fiber optic telemetry routing realignment along guideway
VO-PKG-09-02239 | PKG-09 | 171883.73 | 151331.55 | Approved | 28 | 2024-07-07 | 2024-08-28 | Drainage box culvert capacity expansion for 100-year flood event
VO-PKG-01-01501 | PKG-01 | 172573.32 | 0 | Pending Approval | 21 | 2024-07-08 |  | Unforeseen soft ground stabilization and grouting
VO-PKG-05-01225 | PKG-05 | 131091.02 | 113782.41 | Approved | 13 | 2024-07-08 | 2024-07-24 | HV substation redundancy transformer capacity upgrade
VO-PKG-08-02118 | PKG-08 | 26346.99 | 0 | Pending Approval | 27 | 2024-07-08 |  | Track vibration damping rubber pads acoustic upgrade
VO-PKG-01-01041 | PKG-01 | 166350.82 | 0 | Rejected | 0 | 2024-07-09 | 2024-07-28 | Unforeseen soft ground stabilization and grouting
VO-PKG-03-02003 | PKG-03 | 198745.23 | 0 | Rejected | 0 | 2024-07-09 | 2024-08-17 | Viaduct pier foundation redesign due to utility clash
VO-PKG-04-01354 | PKG-04 | 58028.92 | 0 | Rejected | 0 | 2024-07-09 | 2024-08-13 | Station box diaphragm wall water ingress mitigation
VO-PKG-09-01409 | PKG-09 | 47963.53 | 0 | Pending Approval | 34 | 2024-07-09 |  | Drainage box culvert capacity expansion for 100-year flood event
VO-PKG-10-01780 | PKG-10 | 166177.75 | 143236.71 | Approved | 32 | 2024-07-09 | 2024-08-29 | HVAC chilled water pipe rerouting around station concourse
VO-PKG-01-01241 | PKG-01 | 212450.65 | 197644.4 | Approved | 9 | 2024-07-11 | 2024-07-31 | Unforeseen soft ground stabilization and grouting
VO-PKG-03-01393 | PKG-03 | 327104.55 | 316228.97 | Approved | 9 | 2024-07-11 | 2024-08-12 | Viaduct pier foundation redesign due to utility clash
VO-PKG-06-02466 | PKG-06 | 325687.14 | 306398.24 | Approved | 44 | 2024-07-11 | 2024-08-30 | Additional smoke evacuation shafts in underground platforms
VO-PKG-07-02147 | PKG-07 | 186645.69 | 181938.76 | Approved | 27 | 2024-07-11 | 2024-08-30 | Fiber optic telemetry routing realignment along guideway
VO-PKG-09-01109 | PKG-09 | 287778.95 | 243122.08 | Approved | 48 | 2024-07-11 | 2024-08-14 | Drainage box culvert capacity expansion for 100-year flood event
VO-PKG-02-01942 | PKG-02 | 150226 | 0 | Pending Approval | 7 | 2024-07-12 |  | TBM Cutterhead refurbishment and rock fissure sealing
VO-PKG-09-00459 | PKG-09 | 185531.18 | 0 | Pending Approval | 16 | 2024-07-12 |  | Drainage box culvert capacity expansion for 100-year flood event
VO-PKG-09-01889 | PKG-09 | 232315.72 | 215381.33 | Approved | 25 | 2024-07-12 | 2024-08-27 | Drainage box culvert capacity expansion for 100-year flood event
VO-PKG-09-02889 | PKG-09 | 74140.08 | 62913.48 | Approved | 17 | 2024-07-13 | 2024-08-10 | Drainage box culvert capacity expansion for 100-year flood event
VO-PKG-03-02743 | PKG-03 | 178422.15 | 161747.54 | Approved | 13 | 2024-07-14 | 2024-09-10 | Viaduct pier foundation redesign due to utility clash
VO-PKG-03-02173 | PKG-03 | 289746.6 | 0 | Pending Approval | 38 | 2024-07-15 |  | Viaduct pier foundation redesign due to utility clash
VO-PKG-05-01735 | PKG-05 | 195068.33 | 161461.29 | Approved | 41 | 2024-07-15 | 2024-08-10 | HV substation redundancy transformer capacity upgrade
VO-PKG-09-00489 | PKG-09 | 251436.4 | 0 | Pending Approval | 25 | 2024-07-15 |  | Drainage box culvert capacity expansion for 100-year flood event
VO-PKG-01-01591 | PKG-01 | 38010.79 | 0 | Pending Approval | 12 | 2024-07-16 |  | Unforeseen soft ground stabilization and grouting
VO-PKG-03-02043 | PKG-03 | 271752.21 | 263634.97 | Approved | 49 | 2024-07-16 | 2024-08-29 | Viaduct pier foundation redesign due to utility clash
VO-PKG-10-01250 | PKG-10 | 79547.2 | 76374.48 | Approved | 47 | 2024-07-16 | 2024-09-03 | HVAC chilled water pipe rerouting around station concourse
VO-PKG-10-02550 | PKG-10 | 315054.06 | 0 | Pending Approval | 11 | 2024-07-16 |  | HVAC chilled water pipe rerouting around station concourse
VO-PKG-02-02482 | PKG-02 | 162019.99 | 143312.56 | Approved | 10 | 2024-07-17 | 2024-08-30 | TBM Cutterhead refurbishment and rock fissure sealing
VO-PKG-05-01595 | PKG-05 | 58800.21 | 55346.16 | Approved | 51 | 2024-07-17 | 2024-09-09 | HV substation redundancy transformer capacity upgrade
VO-PKG-02-00552 | PKG-02 | 17624.78 | 16688.41 | Approved | 57 | 2024-07-18 | 2024-08-15 | TBM Cutterhead refurbishment and rock fissure sealing
VO-PKG-09-00019 | PKG-09 | 213363.84 | 187701.05 | Approved | 6 | 2024-07-18 | 2024-08-03 | Drainage box culvert capacity expansion for 100-year flood event
VO-PKG-01-02371 | PKG-01 | 282817.13 | 0 | Pending Approval | 23 | 2024-07-19 |  | Unforeseen soft ground stabilization and grouting
VO-PKG-01-02621 | PKG-01 | 266032 | 0 | Pending Approval | 25 | 2024-07-19 |  | Unforeseen soft ground stabilization and grouting
VO-PKG-05-00765 | PKG-05 | 20662.93 | 17635.13 | Approved | 56 | 2024-07-19 | 2024-08-03 | HV substation redundancy transformer capacity upgrade
VO-PKG-02-02342 | PKG-02 | 56267.94 | 52447.63 | Approved | 13 | 2024-07-20 | 2024-08-31 | TBM Cutterhead refurbishment and rock fissure sealing
VO-PKG-04-01964 | PKG-04 | 180839.63 | 172060.41 | Approved | 20 | 2024-07-20 | 2024-08-19 | Station box diaphragm wall water ingress mitigation
VO-PKG-09-02179 | PKG-09 | 198049.89 | 161015.64 | Approved | 36 | 2024-07-20 | 2024-09-01 | Drainage box culvert capacity expansion for 100-year flood event
VO-PKG-10-00760 | PKG-10 | 288509.61 | 249089.69 | Approved | 7 | 2024-07-20 | 2024-09-13 | HVAC chilled water pipe rerouting around station concourse
VO-PKG-10-02380 | PKG-10 | 232312.35 | 0 | Pending Approval | 11 | 2024-07-20 |  | HVAC chilled water pipe rerouting around station concourse
VO-PKG-04-00374 | PKG-04 | 115567.19 | 99239.34 | Approved | 12 | 2024-07-21 | 2024-09-18 | Station box diaphragm wall water ingress mitigation
VO-PKG-05-00685 | PKG-05 | 148255.76 | 0 | Rejected | 0 | 2024-07-21 | 2024-08-21 | HV substation redundancy transformer capacity upgrade
VO-PKG-06-01826 | PKG-06 | 89239.35 | 72955.17 | Approved | 17 | 2024-07-21 | 2024-08-19 | Additional smoke evacuation shafts in underground platforms
VO-PKG-07-01867 | PKG-07 | 277776.75 | 253661.42 | Approved | 54 | 2024-07-21 | 2024-09-11 | Fiber optic telemetry routing realignment along guideway
VO-PKG-10-02360 | PKG-10 | 28650.41 | 22958.91 | Approved | 51 | 2024-07-21 | 2024-08-05 | HVAC chilled water pipe rerouting around station concourse
VO-PKG-02-00392 | PKG-02 | 191302.53 | 0 | Pending Approval | 33 | 2024-07-22 |  | TBM Cutterhead refurbishment and rock fissure sealing
VO-PKG-04-02024 | PKG-04 | 108607.47 | 104891.4 | Approved | 49 | 2024-07-22 | 2024-08-21 | Station box diaphragm wall water ingress mitigation
VO-PKG-05-01355 | PKG-05 | 83744.35 | 68877.05 | Approved | 36 | 2024-07-22 | 2024-08-20 | HV substation redundancy transformer capacity upgrade
VO-PKG-08-01228 | PKG-08 | 259320.85 | 210688.03 | Approved | 19 | 2024-07-22 | 2024-08-31 | Track vibration damping rubber pads acoustic upgrade
VO-PKG-09-00499 | PKG-09 | 348970.45 | 323900.04 | Approved | 36 | 2024-07-22 | 2024-08-09 | Drainage box culvert capacity expansion for 100-year flood event
VO-PKG-10-01470 | PKG-10 | 156816.26 | 0 | Pending Approval | 18 | 2024-07-22 |  | HVAC chilled water pipe rerouting around station concourse
VO-PKG-02-00822 | PKG-02 | 197861.57 | 0 | Pending Approval | 38 | 2024-07-24 |  | TBM Cutterhead refurbishment and rock fissure sealing
VO-PKG-08-02068 | PKG-08 | 294159.68 | 0 | Pending Approval | 26 | 2024-07-24 |  | Track vibration damping rubber pads acoustic upgrade
VO-PKG-08-02878 | PKG-08 | 56485.38 | 0 | Pending Approval | 20 | 2024-07-24 |  | Track vibration damping rubber pads acoustic upgrade
VO-PKG-10-02260 | PKG-10 | 328392.18 | 319052.28 | Approved | 20 | 2024-07-24 | 2024-09-17 | HVAC chilled water pipe rerouting around station concourse
VO-PKG-02-01502 | PKG-02 | 226482.98 | 196919.39 | Approved | 10 | 2024-07-25 | 2024-08-20 | TBM Cutterhead refurbishment and rock fissure sealing
VO-PKG-05-01195 | PKG-05 | 278698.55 | 0 | Rejected | 0 | 2024-07-25 | 2024-08-25 | HV substation redundancy transformer capacity upgrade
VO-PKG-09-00259 | PKG-09 | 145310.51 | 0 | Pending Approval | 4 | 2024-07-25 |  | Drainage box culvert capacity expansion for 100-year flood event
VO-PKG-10-02240 | PKG-10 | 181565.04 | 167861.46 | Approved | 38 | 2024-07-25 | 2024-08-24 | HVAC chilled water pipe rerouting around station concourse
VO-PKG-01-02991 | PKG-01 | 25766.9 | 21093.64 | Approved | 48 | 2024-07-26 | 2024-08-20 | Unforeseen soft ground stabilization and grouting
VO-PKG-02-00352 | PKG-02 | 30152.56 | 25014.84 | Approved | 48 | 2024-07-26 | 2024-09-07 | TBM Cutterhead refurbishment and rock fissure sealing
VO-PKG-05-01905 | PKG-05 | 22560.01 | 19658.55 | Approved | 46 | 2024-07-26 | 2024-09-04 | HV substation redundancy transformer capacity upgrade
VO-PKG-06-01776 | PKG-06 | 125404.19 | 0 | Pending Approval | 17 | 2024-07-26 |  | Additional smoke evacuation shafts in underground platforms
VO-PKG-02-00412 | PKG-02 | 315522.77 | 307342.02 | Approved | 19 | 2024-07-27 | 2024-09-15 | TBM Cutterhead refurbishment and rock fissure sealing
VO-PKG-03-00143 | PKG-03 | 54651.85 | 0 | Pending Approval | 4 | 2024-07-27 |  | Viaduct pier foundation redesign due to utility clash
VO-PKG-08-01198 | PKG-08 | 239026.66 | 0 | Pending Approval | 21 | 2024-07-27 |  | Track vibration damping rubber pads acoustic upgrade
VO-PKG-08-01278 | PKG-08 | 203032.64 | 0 | Rejected | 0 | 2024-07-27 | 2024-08-27 | Track vibration damping rubber pads acoustic upgrade
VO-PKG-01-02951 | PKG-01 | 304772.06 | 260389.48 | Approved | 30 | 2024-07-28 | 2024-09-09 | Unforeseen soft ground stabilization and grouting
VO-PKG-09-02219 | PKG-09 | 83885.02 | 70851.49 | Approved | 40 | 2024-07-28 | 2024-08-20 | Drainage box culvert capacity expansion for 100-year flood event
VO-PKG-01-01771 | PKG-01 | 176369.01 | 150730.96 | Approved | 25 | 2024-07-29 | 2024-09-24 | Unforeseen soft ground stabilization and grouting
VO-PKG-02-02982 | PKG-02 | 68178.92 | 0 | Pending Approval | 43 | 2024-07-29 |  | TBM Cutterhead refurbishment and rock fissure sealing
VO-PKG-05-00335 | PKG-05 | 320440.26 | 311340.76 | Approved | 24 | 2024-07-29 | 2024-08-28 | HV substation redundancy transformer capacity upgrade
VO-PKG-07-02107 | PKG-07 | 138099.64 | 121112.04 | Approved | 9 | 2024-07-29 | 2024-08-15 | Fiber optic telemetry routing realignment along guideway
VO-PKG-10-00440 | PKG-10 | 322493.07 | 265264.63 | Approved | 41 | 2024-07-29 | 2024-09-03 | HVAC chilled water pipe rerouting around station concourse
VO-PKG-03-01893 | PKG-03 | 338231.05 | 0 | Pending Approval | 34 | 2024-07-31 |  | Viaduct pier foundation redesign due to utility clash
VO-PKG-05-01555 | PKG-05 | 119630.8 | 108843.04 | Approved | 16 | 2024-07-31 | 2024-08-22 | HV substation redundancy transformer capacity upgrade
VO-PKG-01-02761 | PKG-01 | 231590.09 | 198431.61 | Approved | 20 | 2024-08-01 | 2024-08-30 | Unforeseen soft ground stabilization and grouting
VO-PKG-01-02881 | PKG-01 | 178043.88 | 169765.49 | Approved | 58 | 2024-08-01 | 2024-09-17 | Unforeseen soft ground stabilization and grouting
VO-PKG-10-00680 | PKG-10 | 280670.44 | 242473.94 | Approved | 13 | 2024-08-01 | 2024-09-05 | HVAC chilled water pipe rerouting around station concourse
VO-PKG-05-00135 | PKG-05 | 24058.01 | 0 | Pending Approval | 16 | 2024-08-02 |  | HV substation redundancy transformer capacity upgrade
VO-PKG-10-02740 | PKG-10 | 214014.92 | 194140.86 | Approved | 32 | 2024-08-02 | 2024-09-04 | HVAC chilled water pipe rerouting around station concourse
VO-PKG-07-01427 | PKG-07 | 320189.84 | 0 | Pending Approval | 23 | 2024-08-03 |  | Fiber optic telemetry routing realignment along guideway
VO-PKG-07-02787 | PKG-07 | 297830.09 | 0 | Rejected | 0 | 2024-08-03 | 2024-08-27 | Fiber optic telemetry routing realignment along guideway
VO-PKG-08-00608 | PKG-08 | 191011.85 | 154726.12 | Approved | 23 | 2024-08-03 | 2024-09-28 | Track vibration damping rubber pads acoustic upgrade
VO-PKG-09-00189 | PKG-09 | 181340.06 | 166869.1 | Approved | 13 | 2024-08-03 | 2024-09-21 | Drainage box culvert capacity expansion for 100-year flood event
VO-PKG-07-01577 | PKG-07 | 36807.63 | 31721.85 | Approved | 32 | 2024-08-04 | 2024-08-28 | Fiber optic telemetry routing realignment along guideway
VO-PKG-02-01552 | PKG-02 | 166048.02 | 160787.92 | Approved | 37 | 2024-08-05 | 2024-09-24 | TBM Cutterhead refurbishment and rock fissure sealing
VO-PKG-04-02134 | PKG-04 | 26193.64 | 22959.94 | Approved | 41 | 2024-08-05 | 2024-09-28 | Station box diaphragm wall water ingress mitigation
VO-PKG-02-00682 | PKG-02 | 94571.98 | 81325.58 | Approved | 12 | 2024-08-06 | 2024-09-07 | TBM Cutterhead refurbishment and rock fissure sealing
VO-PKG-04-00644 | PKG-04 | 154526.77 | 0 | Rejected | 0 | 2024-08-06 | 2024-09-17 | Station box diaphragm wall water ingress mitigation
VO-PKG-06-00496 | PKG-06 | 252387.57 | 0 | Pending Approval | 33 | 2024-08-06 |  | Additional smoke evacuation shafts in underground platforms
VO-PKG-06-01256 | PKG-06 | 82607.37 | 0 | Pending Approval | 29 | 2024-08-06 |  | Additional smoke evacuation shafts in underground platforms
VO-PKG-09-02229 | PKG-09 | 96453.59 | 91268.05 | Approved | 54 | 2024-08-06 | 2024-09-19 | Drainage box culvert capacity expansion for 100-year flood event
VO-PKG-05-00645 | PKG-05 | 118856.15 | 0 | Pending Approval | 5 | 2024-08-07 |  | HV substation redundancy transformer capacity upgrade
VO-PKG-01-02941 | PKG-01 | 57702.63 | 48886.29 | Approved | 8 | 2024-08-08 | 2024-09-10 | Unforeseen soft ground stabilization and grouting
VO-PKG-04-00534 | PKG-04 | 330006.01 | 0 | Rejected | 0 | 2024-08-08 | 2024-08-21 | Station box diaphragm wall water ingress mitigation
VO-PKG-06-01286 | PKG-06 | 297673.8 | 288079.85 | Approved | 9 | 2024-08-08 | 2024-09-26 | Additional smoke evacuation shafts in underground platforms
VO-PKG-08-00028 | PKG-08 | 69098.85 | 0 | Pending Approval | 38 | 2024-08-08 |  | Track vibration damping rubber pads acoustic upgrade
VO-PKG-08-00648 | PKG-08 | 303066.4 | 243548.66 | Approved | 14 | 2024-08-08 | 2024-09-02 | Track vibration damping rubber pads acoustic upgrade
VO-PKG-10-02640 | PKG-10 | 88883.27 | 75207.73 | Approved | 36 | 2024-08-08 | 2024-09-18 | HVAC chilled water pipe rerouting around station concourse
VO-PKG-03-02203 | PKG-03 | 311755.08 | 0 | Rejected | 0 | 2024-08-09 | 2024-09-11 | Viaduct pier foundation redesign due to utility clash
VO-PKG-07-01277 | PKG-07 | 305358.52 | 257916.47 | Approved | 27 | 2024-08-09 | 2024-09-04 | Fiber optic telemetry routing realignment along guideway
VO-PKG-07-02867 | PKG-07 | 153138.44 | 139945.55 | Approved | 23 | 2024-08-09 | 2024-09-11 | Fiber optic telemetry routing realignment along guideway
VO-PKG-08-00178 | PKG-08 | 124319.23 | 0 | Pending Approval | 35 | 2024-08-09 |  | Track vibration damping rubber pads acoustic upgrade
VO-PKG-08-00618 | PKG-08 | 261690.42 | 225641.68 | Approved | 8 | 2024-08-09 | 2024-09-27 | Track vibration damping rubber pads acoustic upgrade
VO-PKG-08-01328 | PKG-08 | 318232.43 | 307269.33 | Approved | 44 | 2024-08-10 | 2024-09-22 | Track vibration damping rubber pads acoustic upgrade
VO-PKG-02-00802 | PKG-02 | 185134.21 | 157558.65 | Approved | 50 | 2024-08-11 | 2024-08-27 | TBM Cutterhead refurbishment and rock fissure sealing
VO-PKG-01-02021 | PKG-01 | 157837.6 | 132987.42 | Approved | 55 | 2024-08-12 | 2024-09-15 | Unforeseen soft ground stabilization and grouting
VO-PKG-02-02672 | PKG-02 | 203882.17 | 176202.76 | Approved | 30 | 2024-08-12 | 2024-09-27 | TBM Cutterhead refurbishment and rock fissure sealing
VO-PKG-06-00796 | PKG-06 | 345744.5 | 304012.51 | Approved | 17 | 2024-08-12 | 2024-09-23 | Additional smoke evacuation shafts in underground platforms
VO-PKG-07-02997 | PKG-07 | 233688.98 | 0 | Rejected | 0 | 2024-08-12 | 2024-09-09 | Fiber optic telemetry routing realignment along guideway
VO-PKG-06-00016 | PKG-06 | 333763.68 | 0 | Pending Approval | 13 | 2024-08-14 |  | Additional smoke evacuation shafts in underground platforms
VO-PKG-10-00360 | PKG-10 | 288304.65 | 0 | Pending Approval | 10 | 2024-08-14 |  | HVAC chilled water pipe rerouting around station concourse
VO-PKG-10-00890 | PKG-10 | 119125.41 | 0 | Pending Approval | 27 | 2024-08-14 |  | HVAC chilled water pipe rerouting around station concourse
VO-PKG-05-01365 | PKG-05 | 213432.05 | 0 | Pending Approval | 44 | 2024-08-15 |  | HV substation redundancy transformer capacity upgrade
VO-PKG-05-02285 | PKG-05 | 38668.04 | 36212.01 | Approved | 52 | 2024-08-15 | 2024-09-25 | HV substation redundancy transformer capacity upgrade
VO-PKG-02-00432 | PKG-02 | 223737.26 | 0 | Pending Approval | 8 | 2024-08-16 |  | TBM Cutterhead refurbishment and rock fissure sealing
VO-PKG-02-02012 | PKG-02 | 320989.07 | 260300.03 | Approved | 29 | 2024-08-16 | 2024-09-04 | TBM Cutterhead refurbishment and rock fissure sealing
VO-PKG-03-02893 | PKG-03 | 199709.71 | 162778.27 | Approved | 17 | 2024-08-16 | 2024-09-30 | Viaduct pier foundation redesign due to utility clash
VO-PKG-07-02467 | PKG-07 | 156887.4 | 135762.14 | Approved | 8 | 2024-08-16 | 2024-10-02 | Fiber optic telemetry routing realignment along guideway
VO-PKG-08-01698 | PKG-08 | 186027.22 | 149544.09 | Approved | 54 | 2024-08-16 | 2024-10-06 | Track vibration damping rubber pads acoustic upgrade
VO-PKG-08-01708 | PKG-08 | 55430.01 | 0 | Pending Approval | 13 | 2024-08-16 |  | Track vibration damping rubber pads acoustic upgrade
VO-PKG-02-00382 | PKG-02 | 173724.12 | 0 | Pending Approval | 8 | 2024-08-17 |  | TBM Cutterhead refurbishment and rock fissure sealing
VO-PKG-03-01043 | PKG-03 | 83297.56 | 0 | Pending Approval | 33 | 2024-08-17 |  | Viaduct pier foundation redesign due to utility clash
VO-PKG-05-02715 | PKG-05 | 169258.89 | 147908.04 | Approved | 6 | 2024-08-17 | 2024-09-20 | HV substation redundancy transformer capacity upgrade
VO-PKG-07-02017 | PKG-07 | 172846.75 | 140442.55 | Approved | 32 | 2024-08-17 | 2024-09-08 | Fiber optic telemetry routing realignment along guideway
VO-PKG-07-02827 | PKG-07 | 309691.45 | 276146.01 | Approved | 21 | 2024-08-17 | 2024-09-01 | Fiber optic telemetry routing realignment along guideway
VO-PKG-08-02628 | PKG-08 | 278342.71 | 233145.69 | Approved | 36 | 2024-08-17 | 2024-10-01 | Track vibration damping rubber pads acoustic upgrade
VO-PKG-09-01949 | PKG-09 | 324420.82 | 271839.62 | Approved | 26 | 2024-08-17 | 2024-09-18 | Drainage box culvert capacity expansion for 100-year flood event
VO-PKG-10-02980 | PKG-10 | 344218.08 | 0 | Pending Approval | 33 | 2024-08-17 |  | HVAC chilled water pipe rerouting around station concourse
VO-PKG-03-00413 | PKG-03 | 117874.12 | 0 | Rejected | 0 | 2024-08-18 | 2024-09-12 | Viaduct pier foundation redesign due to utility clash
VO-PKG-05-00495 | PKG-05 | 185330.31 | 166768.01 | Approved | 48 | 2024-08-18 | 2024-09-25 | HV substation redundancy transformer capacity upgrade
VO-PKG-07-01157 | PKG-07 | 120359.85 | 111772.85 | Approved | 21 | 2024-08-18 | 2024-10-10 | Fiber optic telemetry routing realignment along guideway
VO-PKG-09-01749 | PKG-09 | 125340.65 | 0 | Rejected | 0 | 2024-08-18 | 2024-10-01 | Drainage box culvert capacity expansion for 100-year flood event
VO-PKG-09-02359 | PKG-09 | 279099.63 | 236585.78 | Approved | 34 | 2024-08-18 | 2024-09-30 | Drainage box culvert capacity expansion for 100-year flood event
VO-PKG-10-02300 | PKG-10 | 290414.04 | 0 | Pending Approval | 13 | 2024-08-18 |  | HVAC chilled water pipe rerouting around station concourse
VO-PKG-05-02155 | PKG-05 | 261807.56 | 0 | Rejected | 0 | 2024-08-19 | 2024-09-22 | HV substation redundancy transformer capacity upgrade
VO-PKG-07-02407 | PKG-07 | 266627.79 | 0 | Rejected | 0 | 2024-08-19 | 2024-09-03 | Fiber optic telemetry routing realignment along guideway
VO-PKG-07-02567 | PKG-07 | 311029.1 | 277989.6 | Approved | 17 | 2024-08-19 | 2024-10-10 | Fiber optic telemetry routing realignment along guideway
VO-PKG-09-01169 | PKG-09 | 164816.44 | 0 | Rejected | 0 | 2024-08-19 | 2024-09-03 | Drainage box culvert capacity expansion for 100-year flood event
VO-PKG-09-02029 | PKG-09 | 239872.01 | 224982.27 | Approved | 27 | 2024-08-19 | 2024-09-03 | Drainage box culvert capacity expansion for 100-year flood event
VO-PKG-01-00011 | PKG-01 | 123254.37 | 108366.94 | Approved | 43 | 2024-08-20 | 2024-10-15 | Unforeseen soft ground stabilization and grouting
VO-PKG-03-01613 | PKG-03 | 136586.18 | 0 | Rejected | 0 | 2024-08-20 | 2024-09-25 | Viaduct pier foundation redesign due to utility clash
VO-PKG-04-02034 | PKG-04 | 143359.66 | 0 | Pending Approval | 16 | 2024-08-20 |  | Station box diaphragm wall water ingress mitigation
VO-PKG-10-01870 | PKG-10 | 55193.33 | 53161.89 | Approved | 50 | 2024-08-20 | 2024-10-17 | HVAC chilled water pipe rerouting around station concourse
VO-PKG-02-02392 | PKG-02 | 84751.95 | 72732.82 | Approved | 25 | 2024-08-21 | 2024-10-15 | TBM Cutterhead refurbishment and rock fissure sealing
VO-PKG-04-02984 | PKG-04 | 336810.33 | 310256.42 | Approved | 22 | 2024-08-21 | 2024-09-19 | Station box diaphragm wall water ingress mitigation
VO-PKG-06-02506 | PKG-06 | 311774.6 | 0 | Pending Approval | 41 | 2024-08-21 |  | Additional smoke evacuation shafts in underground platforms
VO-PKG-04-01164 | PKG-04 | 176140.15 | 171509.88 | Approved | 15 | 2024-08-22 | 2024-09-06 | Station box diaphragm wall water ingress mitigation
VO-PKG-05-01305 | PKG-05 | 73273.63 | 64008.96 | Approved | 27 | 2024-08-22 | 2024-10-12 | HV substation redundancy transformer capacity upgrade
VO-PKG-03-00093 | PKG-03 | 321419.2 | 0 | Pending Approval | 5 | 2024-08-23 |  | Viaduct pier foundation redesign due to utility clash
VO-PKG-04-01904 | PKG-04 | 112699.17 | 102663.22 | Approved | 56 | 2024-08-23 | 2024-09-17 | Station box diaphragm wall water ingress mitigation
VO-PKG-05-01345 | PKG-05 | 48047.07 | 38821.06 | Approved | 14 | 2024-08-23 | 2024-09-23 | HV substation redundancy transformer capacity upgrade
VO-PKG-06-00146 | PKG-06 | 232241.47 | 0 | Pending Approval | 40 | 2024-08-23 |  | Additional smoke evacuation shafts in underground platforms
VO-PKG-02-02302 | PKG-02 | 156983.42 | 0 | Pending Approval | 18 | 2024-08-24 |  | TBM Cutterhead refurbishment and rock fissure sealing
VO-PKG-07-02967 | PKG-07 | 255598.83 | 230351.01 | Approved | 21 | 2024-08-24 | 2024-10-08 | Fiber optic telemetry routing realignment along guideway
VO-PKG-10-01540 | PKG-10 | 194946.46 | 0 | Pending Approval | 36 | 2024-08-24 |  | HVAC chilled water pipe rerouting around station concourse
VO-PKG-10-02090 | PKG-10 | 216782.42 | 185028.67 | Approved | 54 | 2024-08-24 | 2024-10-07 | HVAC chilled water pipe rerouting around station concourse
VO-PKG-04-02894 | PKG-04 | 308757.24 | 296284.57 | Approved | 46 | 2024-08-25 | 2024-10-21 | Station box diaphragm wall water ingress mitigation
VO-PKG-06-00216 | PKG-06 | 333000.13 | 304677.6 | Approved | 20 | 2024-08-25 | 2024-09-20 | Additional smoke evacuation shafts in underground platforms
VO-PKG-08-00798 | PKG-08 | 106581.29 | 89866.42 | Approved | 43 | 2024-08-25 | 2024-10-07 | Track vibration damping rubber pads acoustic upgrade
VO-PKG-08-01418 | PKG-08 | 349163.02 | 296106.06 | Approved | 16 | 2024-08-25 | 2024-09-19 | Track vibration damping rubber pads acoustic upgrade
VO-PKG-09-01199 | PKG-09 | 242921.8 | 0 | Pending Approval | 22 | 2024-08-25 |  | Drainage box culvert capacity expansion for 100-year flood event
VO-PKG-02-02382 | PKG-02 | 149523.58 | 140493.76 | Approved | 13 | 2024-08-26 | 2024-09-20 | TBM Cutterhead refurbishment and rock fissure sealing
VO-PKG-07-02287 | PKG-07 | 319029.1 | 287027.82 | Approved | 12 | 2024-08-26 | 2024-10-01 | Fiber optic telemetry routing realignment along guideway
VO-PKG-01-00231 | PKG-01 | 86642.11 | 73885.31 | Approved | 15 | 2024-08-27 | 2024-09-20 | Unforeseen soft ground stabilization and grouting
VO-PKG-09-02769 | PKG-09 | 161091.25 | 147007.07 | Approved | 53 | 2024-08-28 | 2024-10-11 | Drainage box culvert capacity expansion for 100-year flood event
VO-PKG-02-01592 | PKG-02 | 259761.25 | 220805.55 | Approved | 12 | 2024-08-29 | 2024-09-27 | TBM Cutterhead refurbishment and rock fissure sealing
VO-PKG-03-00353 | PKG-03 | 183867.96 | 149592.81 | Approved | 17 | 2024-08-29 | 2024-09-30 | Viaduct pier foundation redesign due to utility clash
VO-PKG-06-00066 | PKG-06 | 339059.26 | 324008.22 | Approved | 19 | 2024-08-29 | 2024-10-24 | Additional smoke evacuation shafts in underground platforms
VO-PKG-10-01550 | PKG-10 | 43348.15 | 36101.46 | Approved | 38 | 2024-08-29 | 2024-10-14 | HVAC chilled water pipe rerouting around station concourse
VO-PKG-05-01235 | PKG-05 | 280042.63 | 256134.36 | Approved | 38 | 2024-08-30 | 2024-09-17 | HV substation redundancy transformer capacity upgrade
VO-PKG-09-02559 | PKG-09 | 225408.45 | 212309.76 | Approved | 28 | 2024-08-30 | 2024-10-15 | Drainage box culvert capacity expansion for 100-year flood event
VO-PKG-01-00571 | PKG-01 | 312427.12 | 0 | Pending Approval | 2 | 2024-08-31 |  | Unforeseen soft ground stabilization and grouting
VO-PKG-03-01953 | PKG-03 | 313128.88 | 273230.4 | Approved | 10 | 2024-08-31 | 2024-09-21 | Viaduct pier foundation redesign due to utility clash
VO-PKG-03-02903 | PKG-03 | 185216.54 | 153193.41 | Approved | 35 | 2024-08-31 | 2024-10-23 | Viaduct pier foundation redesign due to utility clash
VO-PKG-04-00084 | PKG-04 | 199793.9 | 0 | Rejected | 0 | 2024-08-31 | 2024-09-28 | Station box diaphragm wall water ingress mitigation
VO-PKG-07-02277 | PKG-07 | 318248.09 | 280574 | Approved | 37 | 2024-08-31 | 2024-09-23 | Fiber optic telemetry routing realignment along guideway
VO-PKG-01-00031 | PKG-01 | 175756.81 | 0 | Pending Approval | 6 | 2024-09-01 |  | Unforeseen soft ground stabilization and grouting
VO-PKG-01-02321 | PKG-01 | 139316.34 | 0 | Pending Approval | 11 | 2024-09-01 |  | Unforeseen soft ground stabilization and grouting
VO-PKG-04-00834 | PKG-04 | 165285.53 | 0 | Pending Approval | 19 | 2024-09-01 |  | Station box diaphragm wall water ingress mitigation
VO-PKG-04-02184 | PKG-04 | 305809.62 | 0 | Pending Approval | 25 | 2024-09-01 |  | Station box diaphragm wall water ingress mitigation
VO-PKG-06-02316 | PKG-06 | 93316.12 | 0 | Pending Approval | 14 | 2024-09-01 |  | Additional smoke evacuation shafts in underground platforms
VO-PKG-07-02877 | PKG-07 | 329065.45 | 281517.26 | Approved | 11 | 2024-09-01 | 2024-10-17 | Fiber optic telemetry routing realignment along guideway
VO-PKG-08-01718 | PKG-08 | 19642.36 | 18037.66 | Approved | 20 | 2024-09-01 | 2024-10-14 | Track vibration damping rubber pads acoustic upgrade
VO-PKG-01-00441 | PKG-01 | 255588.62 | 222376.32 | Approved | 27 | 2024-09-02 | 2024-09-30 | Unforeseen soft ground stabilization and grouting
VO-PKG-09-00119 | PKG-09 | 134509.64 | 129290.59 | Approved | 24 | 2024-09-02 | 2024-09-27 | Drainage box culvert capacity expansion for 100-year flood event
VO-PKG-03-02583 | PKG-03 | 335163.34 | 0 | Rejected | 0 | 2024-09-03 | 2024-10-03 | Viaduct pier foundation redesign due to utility clash
VO-PKG-03-02653 | PKG-03 | 129476.97 | 0 | Pending Approval | 2 | 2024-09-03 |  | Viaduct pier foundation redesign due to utility clash
VO-PKG-05-00045 | PKG-05 | 162327.25 | 131173.15 | Approved | 5 | 2024-09-03 | 2024-10-05 | HV substation redundancy transformer capacity upgrade
VO-PKG-05-00125 | PKG-05 | 227673.99 | 210116.7 | Approved | 55 | 2024-09-03 | 2024-11-01 | HV substation redundancy transformer capacity upgrade
VO-PKG-05-02185 | PKG-05 | 64525.28 | 59669.63 | Approved | 40 | 2024-09-03 | 2024-10-09 | HV substation redundancy transformer capacity upgrade
VO-PKG-06-00896 | PKG-06 | 308286.6 | 270784.05 | Approved | 14 | 2024-09-03 | 2024-09-24 | Additional smoke evacuation shafts in underground platforms
VO-PKG-05-01535 | PKG-05 | 306058.78 | 284109.74 | Approved | 23 | 2024-09-04 | 2024-10-21 | HV substation redundancy transformer capacity upgrade
VO-PKG-01-00731 | PKG-01 | 106364.7 | 0 | Pending Approval | 18 | 2024-09-05 |  | Unforeseen soft ground stabilization and grouting
VO-PKG-08-00478 | PKG-08 | 315089.99 | 0 | Pending Approval | 32 | 2024-09-05 |  | Track vibration damping rubber pads acoustic upgrade
VO-PKG-09-00049 | PKG-09 | 191454.2 | 0 | Pending Approval | 22 | 2024-09-05 |  | Drainage box culvert capacity expansion for 100-year flood event
VO-PKG-10-00720 | PKG-10 | 119993.73 | 113901.38 | Approved | 30 | 2024-09-05 | 2024-10-10 | HVAC chilled water pipe rerouting around station concourse
VO-PKG-10-01970 | PKG-10 | 135152.93 | 0 | Rejected | 0 | 2024-09-05 | 2024-09-28 | HVAC chilled water pipe rerouting around station concourse
VO-PKG-02-00612 | PKG-02 | 232667.49 | 0 | Rejected | 0 | 2024-09-06 | 2024-09-17 | TBM Cutterhead refurbishment and rock fissure sealing
VO-PKG-03-02313 | PKG-03 | 94873.81 | 0 | Rejected | 0 | 2024-09-06 | 2024-10-11 | Viaduct pier foundation redesign due to utility clash
VO-PKG-02-01412 | PKG-02 | 21253.84 | 0 | Pending Approval | 4 | 2024-09-07 |  | TBM Cutterhead refurbishment and rock fissure sealing
VO-PKG-02-02852 | PKG-02 | 56701.58 | 0 | Pending Approval | 18 | 2024-09-07 |  | TBM Cutterhead refurbishment and rock fissure sealing
VO-PKG-09-02799 | PKG-09 | 31028.74 | 28393.94 | Approved | 49 | 2024-09-07 | 2024-09-22 | Drainage box culvert capacity expansion for 100-year flood event
VO-PKG-01-00241 | PKG-01 | 40893.17 | 33424.76 | Approved | 9 | 2024-09-08 | 2024-11-03 | Unforeseen soft ground stabilization and grouting
VO-PKG-09-01589 | PKG-09 | 171740.98 | 168227.04 | Approved | 24 | 2024-09-08 | 2024-10-27 | Drainage box culvert capacity expansion for 100-year flood event
VO-PKG-01-00481 | PKG-01 | 51589.06 | 0 | Pending Approval | 22 | 2024-09-09 |  | Unforeseen soft ground stabilization and grouting
VO-PKG-02-00052 | PKG-02 | 347152.98 | 297455.8 | Approved | 8 | 2024-09-09 | 2024-11-07 | TBM Cutterhead refurbishment and rock fissure sealing
VO-PKG-03-01753 | PKG-03 | 251794.9 | 0 | Rejected | 0 | 2024-09-09 | 2024-10-03 | Viaduct pier foundation redesign due to utility clash
VO-PKG-05-01995 | PKG-05 | 304801.7 | 271050.19 | Approved | 24 | 2024-09-09 | 2024-10-30 | HV substation redundancy transformer capacity upgrade
VO-PKG-05-02475 | PKG-05 | 213329.7 | 0 | Pending Approval | 40 | 2024-09-09 |  | HV substation redundancy transformer capacity upgrade
VO-PKG-08-01878 | PKG-08 | 188681.26 | 153447.17 | Approved | 44 | 2024-09-09 | 2024-09-28 | Track vibration damping rubber pads acoustic upgrade
VO-PKG-08-01938 | PKG-08 | 114248.58 | 0 | Pending Approval | 6 | 2024-09-09 |  | Track vibration damping rubber pads acoustic upgrade
VO-PKG-08-02738 | PKG-08 | 20881.76 | 0 | Pending Approval | 22 | 2024-09-09 |  | Track vibration damping rubber pads acoustic upgrade
VO-PKG-10-01850 | PKG-10 | 142685.09 | 0 | Pending Approval | 18 | 2024-09-09 |  | HVAC chilled water pipe rerouting around station concourse
VO-PKG-02-01492 | PKG-02 | 280432.12 | 267231.11 | Approved | 51 | 2024-09-10 | 2024-10-17 | TBM Cutterhead refurbishment and rock fissure sealing
VO-PKG-09-00629 | PKG-09 | 109848.83 | 101925.42 | Approved | 19 | 2024-09-10 | 2024-10-03 | Drainage box culvert capacity expansion for 100-year flood event
VO-PKG-03-02213 | PKG-03 | 296367.91 | 272768.36 | Approved | 35 | 2024-09-11 | 2024-10-13 | Viaduct pier foundation redesign due to utility clash
VO-PKG-01-02591 | PKG-01 | 108160.25 | 99211.8 | Approved | 9 | 2024-09-12 | 2024-10-28 | Unforeseen soft ground stabilization and grouting
VO-PKG-02-01982 | PKG-02 | 77410.12 | 0 | Pending Approval | 9 | 2024-09-12 |  | TBM Cutterhead refurbishment and rock fissure sealing
VO-PKG-03-02783 | PKG-03 | 130232.96 | 110415.87 | Approved | 50 | 2024-09-12 | 2024-10-31 | Viaduct pier foundation redesign due to utility clash
VO-PKG-04-00324 | PKG-04 | 99633.68 | 80835.38 | Approved | 57 | 2024-09-12 | 2024-10-17 | Station box diaphragm wall water ingress mitigation
VO-PKG-09-01769 | PKG-09 | 140154.83 | 133625.89 | Approved | 19 | 2024-09-12 | 2024-11-07 | Drainage box culvert capacity expansion for 100-year flood event
VO-PKG-06-02386 | PKG-06 | 248302.33 | 216444.01 | Approved | 26 | 2024-09-13 | 2024-10-10 | Additional smoke evacuation shafts in underground platforms
VO-PKG-01-00511 | PKG-01 | 167898.03 | 154281.7 | Approved | 19 | 2024-09-14 | 2024-10-21 | Unforeseen soft ground stabilization and grouting
VO-PKG-01-00541 | PKG-01 | 28990.14 | 0 | Rejected | 0 | 2024-09-14 | 2024-09-30 | Unforeseen soft ground stabilization and grouting
VO-PKG-02-01702 | PKG-02 | 240064.77 | 223735.48 | Approved | 38 | 2024-09-14 | 2024-10-08 | TBM Cutterhead refurbishment and rock fissure sealing
VO-PKG-02-02222 | PKG-02 | 207696.26 | 184773.58 | Approved | 59 | 2024-09-14 | 2024-10-28 | TBM Cutterhead refurbishment and rock fissure sealing
VO-PKG-03-01983 | PKG-03 | 20146.76 | 0 | Pending Approval | 23 | 2024-09-14 |  | Viaduct pier foundation redesign due to utility clash
VO-PKG-06-01046 | PKG-06 | 236772.23 | 0 | Pending Approval | 19 | 2024-09-14 |  | Additional smoke evacuation shafts in underground platforms
VO-PKG-07-02767 | PKG-07 | 153166.26 | 0 | Rejected | 0 | 2024-09-15 | 2024-10-19 | Fiber optic telemetry routing realignment along guideway
VO-PKG-03-01463 | PKG-03 | 151040.65 | 140383 | Approved | 30 | 2024-09-16 | 2024-10-22 | Viaduct pier foundation redesign due to utility clash
VO-PKG-05-02515 | PKG-05 | 70135.84 | 68160.8 | Approved | 38 | 2024-09-16 | 2024-10-22 | HV substation redundancy transformer capacity upgrade
VO-PKG-10-00920 | PKG-10 | 246643.66 | 215485.1 | Approved | 46 | 2024-09-16 | 2024-10-02 | HVAC chilled water pipe rerouting around station concourse
VO-PKG-02-00932 | PKG-02 | 116002.21 | 97127.82 | Approved | 56 | 2024-09-17 | 2024-10-23 | TBM Cutterhead refurbishment and rock fissure sealing
VO-PKG-09-01069 | PKG-09 | 212764.98 | 199382.83 | Approved | 7 | 2024-09-17 | 2024-10-20 | Drainage box culvert capacity expansion for 100-year flood event
VO-PKG-09-02339 | PKG-09 | 94710.85 | 86762.25 | Approved | 26 | 2024-09-17 | 2024-11-03 | Drainage box culvert capacity expansion for 100-year flood event
VO-PKG-09-02589 | PKG-09 | 188886.13 | 153339.94 | Approved | 36 | 2024-09-17 | 2024-11-15 | Drainage box culvert capacity expansion for 100-year flood event
VO-PKG-07-00547 | PKG-07 | 296478.41 | 245961.27 | Approved | 7 | 2024-09-18 | 2024-11-11 | Fiber optic telemetry routing realignment along guideway
VO-PKG-07-02817 | PKG-07 | 159929.34 | 147682.51 | Approved | 50 | 2024-09-18 | 2024-10-05 | Fiber optic telemetry routing realignment along guideway
VO-PKG-09-02489 | PKG-09 | 292793.28 | 262419.99 | Approved | 51 | 2024-09-18 | 2024-11-16 | Drainage box culvert capacity expansion for 100-year flood event
VO-PKG-01-00751 | PKG-01 | 86572.5 | 73943.49 | Approved | 14 | 2024-09-19 | 2024-10-14 | Unforeseen soft ground stabilization and grouting
VO-PKG-02-00072 | PKG-02 | 309083.16 | 0 | Pending Approval | 6 | 2024-09-19 |  | TBM Cutterhead refurbishment and rock fissure sealing
VO-PKG-06-01156 | PKG-06 | 35857.03 | 28980.93 | Approved | 36 | 2024-09-19 | 2024-10-29 | Additional smoke evacuation shafts in underground platforms
VO-PKG-03-00123 | PKG-03 | 92795.25 | 90805.38 | Approved | 5 | 2024-09-20 | 2024-10-07 | Viaduct pier foundation redesign due to utility clash
VO-PKG-03-01423 | PKG-03 | 342427 | 301773.72 | Approved | 39 | 2024-09-20 | 2024-11-07 | Viaduct pier foundation redesign due to utility clash
VO-PKG-03-01733 | PKG-03 | 148821.29 | 139158.89 | Approved | 56 | 2024-09-20 | 2024-10-07 | Viaduct pier foundation redesign due to utility clash
VO-PKG-05-00395 | PKG-05 | 314670.18 | 290375.2 | Approved | 50 | 2024-09-20 | 2024-10-27 | HV substation redundancy transformer capacity upgrade
VO-PKG-05-02615 | PKG-05 | 238058.06 | 213183.87 | Approved | 39 | 2024-09-20 | 2024-10-18 | HV substation redundancy transformer capacity upgrade
VO-PKG-06-01626 | PKG-06 | 140921.19 | 0 | Pending Approval | 38 | 2024-09-20 |  | Additional smoke evacuation shafts in underground platforms
VO-PKG-07-00307 | PKG-07 | 283582.68 | 0 | Rejected | 0 | 2024-09-20 | 2024-10-22 | Fiber optic telemetry routing realignment along guideway
VO-PKG-07-00337 | PKG-07 | 241422.73 | 208794.54 | Approved | 37 | 2024-09-20 | 2024-10-09 | Fiber optic telemetry routing realignment along guideway
VO-PKG-08-02138 | PKG-08 | 205078.26 | 0 | Pending Approval | 35 | 2024-09-20 |  | Track vibration damping rubber pads acoustic upgrade
VO-PKG-01-01361 | PKG-01 | 193686.76 | 179555.72 | Approved | 53 | 2024-09-21 | 2024-10-25 | Unforeseen soft ground stabilization and grouting
VO-PKG-02-01222 | PKG-02 | 305193.32 | 0 | Pending Approval | 2 | 2024-09-21 |  | TBM Cutterhead refurbishment and rock fissure sealing
VO-PKG-02-01312 | PKG-02 | 198757.85 | 0 | Pending Approval | 13 | 2024-09-21 |  | TBM Cutterhead refurbishment and rock fissure sealing
VO-PKG-02-01622 | PKG-02 | 340662.25 | 316655.46 | Approved | 18 | 2024-09-21 | 2024-10-27 | TBM Cutterhead refurbishment and rock fissure sealing
VO-PKG-09-00519 | PKG-09 | 308024.69 | 248970.83 | Approved | 30 | 2024-09-21 | 2024-10-31 | Drainage box culvert capacity expansion for 100-year flood event
VO-PKG-10-00730 | PKG-10 | 150799.78 | 129061.24 | Approved | 53 | 2024-09-21 | 2024-10-21 | HVAC chilled water pipe rerouting around station concourse
VO-PKG-05-00595 | PKG-05 | 63675.71 | 54002.95 | Approved | 35 | 2024-09-22 | 2024-10-16 | HV substation redundancy transformer capacity upgrade
VO-PKG-03-00243 | PKG-03 | 211683.93 | 184922.41 | Approved | 26 | 2024-09-23 | 2024-10-08 | Viaduct pier foundation redesign due to utility clash
VO-PKG-04-02764 | PKG-04 | 321227.14 | 283339.91 | Approved | 37 | 2024-09-23 | 2024-11-17 | Station box diaphragm wall water ingress mitigation
VO-PKG-07-02857 | PKG-07 | 137059.96 | 120219.74 | Approved | 6 | 2024-09-23 | 2024-11-01 | Fiber optic telemetry routing realignment along guideway
VO-PKG-10-02790 | PKG-10 | 207059.81 | 0 | Pending Approval | 21 | 2024-09-23 |  | HVAC chilled water pipe rerouting around station concourse
VO-PKG-04-00164 | PKG-04 | 184226.62 | 0 | Pending Approval | 44 | 2024-09-24 |  | Station box diaphragm wall water ingress mitigation
VO-PKG-04-01134 | PKG-04 | 260397.85 | 247859.77 | Approved | 39 | 2024-09-24 | 2024-11-13 | Station box diaphragm wall water ingress mitigation
VO-PKG-05-00865 | PKG-05 | 326359.17 | 0 | Pending Approval | 8 | 2024-09-24 |  | HV substation redundancy transformer capacity upgrade
VO-PKG-05-02915 | PKG-05 | 21456.66 | 0 | Rejected | 0 | 2024-09-24 | 2024-10-12 | HV substation redundancy transformer capacity upgrade
VO-PKG-07-01527 | PKG-07 | 316005.57 | 296418.94 | Approved | 8 | 2024-09-24 | 2024-10-15 | Fiber optic telemetry routing realignment along guideway
VO-PKG-08-00268 | PKG-08 | 88372.57 | 80464.17 | Approved | 51 | 2024-09-24 | 2024-11-08 | Track vibration damping rubber pads acoustic upgrade
VO-PKG-08-02928 | PKG-08 | 129665.75 | 0 | Pending Approval | 6 | 2024-09-24 |  | Track vibration damping rubber pads acoustic upgrade
VO-PKG-04-00054 | PKG-04 | 176380.73 | 164790.05 | Approved | 27 | 2024-09-25 | 2024-10-27 | Station box diaphragm wall water ingress mitigation
VO-PKG-05-02675 | PKG-05 | 83182.63 | 80153.23 | Approved | 58 | 2024-09-25 | 2024-11-10 | HV substation redundancy transformer capacity upgrade
VO-PKG-05-02905 | PKG-05 | 274225.3 | 0 | Pending Approval | 40 | 2024-09-25 |  | HV substation redundancy transformer capacity upgrade
VO-PKG-08-02768 | PKG-08 | 293459.56 | 241912.42 | Approved | 34 | 2024-09-25 | 2024-11-17 | Track vibration damping rubber pads acoustic upgrade
VO-PKG-08-02988 | PKG-08 | 299976.5 | 256015.99 | Approved | 5 | 2024-09-25 | 2024-11-01 | Track vibration damping rubber pads acoustic upgrade
VO-PKG-01-00471 | PKG-01 | 228609.64 | 0 | Pending Approval | 39 | 2024-09-26 |  | Unforeseen soft ground stabilization and grouting
VO-PKG-04-01054 | PKG-04 | 262108.87 | 0 | Pending Approval | 24 | 2024-09-26 |  | Station box diaphragm wall water ingress mitigation
VO-PKG-10-00970 | PKG-10 | 181034.76 | 0 | Pending Approval | 13 | 2024-09-26 |  | HVAC chilled water pipe rerouting around station concourse
VO-PKG-02-00152 | PKG-02 | 48697.59 | 39565.49 | Approved | 47 | 2024-09-27 | 2024-11-21 | TBM Cutterhead refurbishment and rock fissure sealing
VO-PKG-05-00375 | PKG-05 | 331740.15 | 0 | Pending Approval | 7 | 2024-09-27 |  | HV substation redundancy transformer capacity upgrade
VO-PKG-07-01127 | PKG-07 | 202902.91 | 169298.62 | Approved | 39 | 2024-09-27 | 2024-10-19 | Fiber optic telemetry routing realignment along guideway
VO-PKG-09-01919 | PKG-09 | 196332.38 | 183282.42 | Approved | 59 | 2024-09-27 | 2024-10-19 | Drainage box culvert capacity expansion for 100-year flood event
VO-PKG-06-01206 | PKG-06 | 164712.89 | 132811.08 | Approved | 6 | 2024-09-28 | 2024-11-04 | Additional smoke evacuation shafts in underground platforms
VO-PKG-04-01574 | PKG-04 | 119352.32 | 0 | Pending Approval | 8 | 2024-09-29 |  | Station box diaphragm wall water ingress mitigation
VO-PKG-04-01944 | PKG-04 | 166479.52 | 142499.05 | Approved | 52 | 2024-09-29 | 2024-10-31 | Station box diaphragm wall water ingress mitigation
VO-PKG-07-00827 | PKG-07 | 112500.99 | 110047.61 | Approved | 5 | 2024-09-29 | 2024-11-24 | Fiber optic telemetry routing realignment along guideway
VO-PKG-01-00841 | PKG-01 | 217307.8 | 176053.15 | Approved | 32 | 2024-09-30 | 2024-11-03 | Unforeseen soft ground stabilization and grouting
VO-PKG-04-02554 | PKG-04 | 302221.57 | 248622.13 | Approved | 28 | 2024-09-30 | 2024-10-27 | Station box diaphragm wall water ingress mitigation
VO-PKG-05-02785 | PKG-05 | 196228.79 | 171592.82 | Approved | 19 | 2024-09-30 | 2024-10-23 | HV substation redundancy transformer capacity upgrade
VO-PKG-06-01356 | PKG-06 | 35574.39 | 29141.65 | Approved | 12 | 2024-09-30 | 2024-11-18 | Additional smoke evacuation shafts in underground platforms
VO-PKG-10-00540 | PKG-10 | 104794.61 | 0 | Rejected | 0 | 2024-09-30 | 2024-10-28 | HVAC chilled water pipe rerouting around station concourse
VO-PKG-10-02390 | PKG-10 | 232297.6 | 222898.79 | Approved | 23 | 2024-09-30 | 2024-11-15 | HVAC chilled water pipe rerouting around station concourse
VO-PKG-03-00933 | PKG-03 | 142825.51 | 118400.2 | Approved | 51 | 2024-10-01 | 2024-11-29 | Viaduct pier foundation redesign due to utility clash
VO-PKG-04-01774 | PKG-04 | 50559.3 | 0 | Pending Approval | 40 | 2024-10-01 |  | Station box diaphragm wall water ingress mitigation
VO-PKG-05-00425 | PKG-05 | 264388.09 | 0 | Pending Approval | 17 | 2024-10-01 |  | HV substation redundancy transformer capacity upgrade
VO-PKG-08-00858 | PKG-08 | 117152.62 | 114141.97 | Approved | 10 | 2024-10-01 | 2024-11-25 | Track vibration damping rubber pads acoustic upgrade
VO-PKG-09-01909 | PKG-09 | 117573.12 | 104492.52 | Approved | 49 | 2024-10-01 | 2024-11-22 | Drainage box culvert capacity expansion for 100-year flood event
VO-PKG-04-01534 | PKG-04 | 153202.15 | 139308.08 | Approved | 49 | 2024-10-02 | 2024-11-20 | Station box diaphragm wall water ingress mitigation
VO-PKG-04-01754 | PKG-04 | 290683.2 | 0 | Pending Approval | 16 | 2024-10-02 |  | Station box diaphragm wall water ingress mitigation
VO-PKG-06-01926 | PKG-06 | 211487.44 | 0 | Pending Approval | 10 | 2024-10-02 |  | Additional smoke evacuation shafts in underground platforms
VO-PKG-07-01007 | PKG-07 | 224854.26 | 0 | Rejected | 0 | 2024-10-02 | 2024-10-23 | Fiber optic telemetry routing realignment along guideway
VO-PKG-07-02057 | PKG-07 | 331556.57 | 0 | Rejected | 0 | 2024-10-02 | 2024-10-24 | Fiber optic telemetry routing realignment along guideway
VO-PKG-01-02791 | PKG-01 | 268209.83 | 0 | Pending Approval | 31 | 2024-10-03 |  | Unforeseen soft ground stabilization and grouting
VO-PKG-02-02452 | PKG-02 | 214681.74 | 186963.22 | Approved | 32 | 2024-10-03 | 2024-11-05 | TBM Cutterhead refurbishment and rock fissure sealing
VO-PKG-06-02156 | PKG-06 | 238772.91 | 218838.01 | Approved | 40 | 2024-10-03 | 2024-11-13 | Additional smoke evacuation shafts in underground platforms
VO-PKG-09-02449 | PKG-09 | 62216.52 | 58814.85 | Approved | 24 | 2024-10-03 | 2024-10-21 | Drainage box culvert capacity expansion for 100-year flood event
VO-PKG-10-02630 | PKG-10 | 133917.81 | 0 | Pending Approval | 35 | 2024-10-03 |  | HVAC chilled water pipe rerouting around station concourse
VO-PKG-05-02595 | PKG-05 | 57629.86 | 54888.96 | Approved | 37 | 2024-10-04 | 2024-11-21 | HV substation redundancy transformer capacity upgrade
VO-PKG-05-00145 | PKG-05 | 185666.24 | 160037.66 | Approved | 24 | 2024-10-05 | 2024-11-10 | HV substation redundancy transformer capacity upgrade
VO-PKG-06-02166 | PKG-06 | 270815.09 | 262724.12 | Approved | 58 | 2024-10-05 | 2024-11-02 | Additional smoke evacuation shafts in underground platforms
VO-PKG-07-00207 | PKG-07 | 178286.94 | 145672.41 | Approved | 7 | 2024-10-05 | 2024-11-02 | Fiber optic telemetry routing realignment along guideway
VO-PKG-02-01192 | PKG-02 | 140837.76 | 0 | Pending Approval | 10 | 2024-10-06 |  | TBM Cutterhead refurbishment and rock fissure sealing
VO-PKG-04-01954 | PKG-04 | 51071.34 | 0 | Rejected | 0 | 2024-10-06 | 2024-10-30 | Station box diaphragm wall water ingress mitigation
VO-PKG-06-02736 | PKG-06 | 202673.66 | 172933.99 | Approved | 51 | 2024-10-06 | 2024-10-30 | Additional smoke evacuation shafts in underground platforms
VO-PKG-09-01649 | PKG-09 | 296927.86 | 252505.12 | Approved | 46 | 2024-10-06 | 2024-11-28 | Drainage box culvert capacity expansion for 100-year flood event
VO-PKG-09-01869 | PKG-09 | 306870 | 0 | Pending Approval | 42 | 2024-10-06 |  | Drainage box culvert capacity expansion for 100-year flood event
VO-PKG-10-01530 | PKG-10 | 215767.97 | 0 | Pending Approval | 2 | 2024-10-06 |  | HVAC chilled water pipe rerouting around station concourse
VO-PKG-02-01002 | PKG-02 | 269836.36 | 218440.48 | Approved | 28 | 2024-10-07 | 2024-12-04 | TBM Cutterhead refurbishment and rock fissure sealing
VO-PKG-03-02593 | PKG-03 | 307972.95 | 0 | Rejected | 0 | 2024-10-07 | 2024-10-22 | Viaduct pier foundation redesign due to utility clash
VO-PKG-05-02125 | PKG-05 | 104368.22 | 88795.62 | Approved | 18 | 2024-10-07 | 2024-10-30 | HV substation redundancy transformer capacity upgrade
VO-PKG-07-02477 | PKG-07 | 66783.5 | 62000.67 | Approved | 50 | 2024-10-07 | 2024-11-05 | Fiber optic telemetry routing realignment along guideway
VO-PKG-08-02148 | PKG-08 | 176007.86 | 0 | Rejected | 0 | 2024-10-07 | 2024-10-26 | Track vibration damping rubber pads acoustic upgrade
VO-PKG-04-00244 | PKG-04 | 280965.49 | 0 | Rejected | 0 | 2024-10-08 | 2024-11-04 | Station box diaphragm wall water ingress mitigation
VO-PKG-07-02667 | PKG-07 | 289099.3 | 0 | Pending Approval | 42 | 2024-10-08 |  | Fiber optic telemetry routing realignment along guideway
VO-PKG-09-00759 | PKG-09 | 315621.34 | 0 | Rejected | 0 | 2024-10-08 | 2024-11-12 | Drainage box culvert capacity expansion for 100-year flood event
VO-PKG-02-01032 | PKG-02 | 166444.51 | 157517.21 | Approved | 19 | 2024-10-09 | 2024-12-07 | TBM Cutterhead refurbishment and rock fissure sealing
VO-PKG-03-01493 | PKG-03 | 149863.34 | 137930.86 | Approved | 56 | 2024-10-09 | 2024-11-09 | Viaduct pier foundation redesign due to utility clash
VO-PKG-04-01824 | PKG-04 | 311641.9 | 251353.79 | Approved | 46 | 2024-10-09 | 2024-12-03 | Station box diaphragm wall water ingress mitigation
VO-PKG-09-01999 | PKG-09 | 182068.47 | 0 | Pending Approval | 33 | 2024-10-09 |  | Drainage box culvert capacity expansion for 100-year flood event
VO-PKG-01-01471 | PKG-01 | 142656.62 | 134564.88 | Approved | 18 | 2024-10-10 | 2024-11-19 | Unforeseen soft ground stabilization and grouting
VO-PKG-05-00445 | PKG-05 | 310183.05 | 276449.28 | Approved | 36 | 2024-10-10 | 2024-10-26 | HV substation redundancy transformer capacity upgrade
VO-PKG-07-00607 | PKG-07 | 217842.11 | 0 | Rejected | 0 | 2024-10-10 | 2024-11-11 | Fiber optic telemetry routing realignment along guideway
VO-PKG-01-02821 | PKG-01 | 160200.33 | 0 | Pending Approval | 37 | 2024-10-11 |  | Unforeseen soft ground stabilization and grouting
VO-PKG-02-02542 | PKG-02 | 260099.78 | 229727.38 | Approved | 6 | 2024-10-11 | 2024-11-07 | TBM Cutterhead refurbishment and rock fissure sealing
VO-PKG-05-02135 | PKG-05 | 30416.97 | 27194.8 | Approved | 34 | 2024-10-11 | 2024-11-15 | HV substation redundancy transformer capacity upgrade
VO-PKG-06-01316 | PKG-06 | 51176.84 | 46048.06 | Approved | 8 | 2024-10-11 | 2024-11-12 | Additional smoke evacuation shafts in underground platforms
VO-PKG-07-00147 | PKG-07 | 84447.39 | 79544.64 | Approved | 14 | 2024-10-11 | 2024-12-04 | Fiber optic telemetry routing realignment along guideway
VO-PKG-07-00867 | PKG-07 | 131071 | 127908.83 | Approved | 17 | 2024-10-11 | 2024-12-08 | Fiber optic telemetry routing realignment along guideway
VO-PKG-10-01500 | PKG-10 | 138543.14 | 126110.01 | Approved | 29 | 2024-10-11 | 2024-11-05 | HVAC chilled water pipe rerouting around station concourse
VO-PKG-01-00861 | PKG-01 | 128220.94 | 122209.39 | Approved | 13 | 2024-10-12 | 2024-11-06 | Unforeseen soft ground stabilization and grouting
VO-PKG-02-01462 | PKG-02 | 349940.96 | 301287.89 | Approved | 10 | 2024-10-12 | 2024-11-30 | TBM Cutterhead refurbishment and rock fissure sealing
VO-PKG-04-02704 | PKG-04 | 136494.31 | 0 | Pending Approval | 38 | 2024-10-12 |  | Station box diaphragm wall water ingress mitigation
VO-PKG-06-00756 | PKG-06 | 172944.07 | 0 | Pending Approval | 13 | 2024-10-13 |  | Additional smoke evacuation shafts in underground platforms
VO-PKG-02-01932 | PKG-02 | 191484.86 | 165246.48 | Approved | 6 | 2024-10-14 | 2024-11-29 | TBM Cutterhead refurbishment and rock fissure sealing
VO-PKG-06-00346 | PKG-06 | 152526.63 | 0 | Rejected | 0 | 2024-10-14 | 2024-10-25 | Additional smoke evacuation shafts in underground platforms
VO-PKG-10-02450 | PKG-10 | 69708.73 | 57411.47 | Approved | 12 | 2024-10-14 | 2024-11-17 | HVAC chilled water pipe rerouting around station concourse
VO-PKG-10-02760 | PKG-10 | 251610.72 | 240166.06 | Approved | 16 | 2024-10-14 | 2024-11-05 | HVAC chilled water pipe rerouting around station concourse
VO-PKG-01-02231 | PKG-01 | 170088.64 | 0 | Rejected | 0 | 2024-10-15 | 2024-10-25 | Unforeseen soft ground stabilization and grouting
VO-PKG-02-00512 | PKG-02 | 195327.62 | 0 | Pending Approval | 17 | 2024-10-15 |  | TBM Cutterhead refurbishment and rock fissure sealing
VO-PKG-04-01444 | PKG-04 | 170028.31 | 141641.17 | Approved | 26 | 2024-10-15 | 2024-12-09 | Station box diaphragm wall water ingress mitigation
VO-PKG-05-00825 | PKG-05 | 177554.27 | 173298.36 | Approved | 41 | 2024-10-15 | 2024-11-29 | HV substation redundancy transformer capacity upgrade
VO-PKG-05-02435 | PKG-05 | 182581.94 | 160368.85 | Approved | 39 | 2024-10-15 | 2024-12-06 | HV substation redundancy transformer capacity upgrade
VO-PKG-02-01972 | PKG-02 | 295703.77 | 240459.06 | Approved | 37 | 2024-10-16 | 2024-11-17 | TBM Cutterhead refurbishment and rock fissure sealing
VO-PKG-04-00694 | PKG-04 | 241615.17 | 198805.93 | Approved | 12 | 2024-10-16 | 2024-12-09 | Station box diaphragm wall water ingress mitigation
VO-PKG-07-00127 | PKG-07 | 300545.6 | 256172.63 | Approved | 35 | 2024-10-16 | 2024-11-30 | Fiber optic telemetry routing realignment along guideway
VO-PKG-06-01736 | PKG-06 | 56709.31 | 52857.59 | Approved | 46 | 2024-10-17 | 2024-11-10 | Additional smoke evacuation shafts in underground platforms
VO-PKG-09-00649 | PKG-09 | 257999.21 | 0 | Pending Approval | 3 | 2024-10-17 |  | Drainage box culvert capacity expansion for 100-year flood event
VO-PKG-04-01784 | PKG-04 | 238509.21 | 0 | Rejected | 0 | 2024-10-18 | 2024-11-08 | Station box diaphragm wall water ingress mitigation
VO-PKG-09-00949 | PKG-09 | 168238.37 | 157764.08 | Approved | 53 | 2024-10-18 | 2024-11-22 | Drainage box culvert capacity expansion for 100-year flood event
VO-PKG-10-02480 | PKG-10 | 167783.83 | 0 | Pending Approval | 44 | 2024-10-18 |  | HVAC chilled water pipe rerouting around station concourse
VO-PKG-01-00611 | PKG-01 | 346530.15 | 300596.09 | Approved | 47 | 2024-10-19 | 2024-11-28 | Unforeseen soft ground stabilization and grouting
VO-PKG-03-02623 | PKG-03 | 272409.06 | 223289.49 | Approved | 6 | 2024-10-19 | 2024-12-04 | Viaduct pier foundation redesign due to utility clash
VO-PKG-07-00287 | PKG-07 | 43987.34 | 41021.71 | Approved | 42 | 2024-10-19 | 2024-11-13 | Fiber optic telemetry routing realignment along guideway
VO-PKG-07-00837 | PKG-07 | 69005.07 | 0 | Pending Approval | 6 | 2024-10-19 |  | Fiber optic telemetry routing realignment along guideway
VO-PKG-07-01787 | PKG-07 | 195730.96 | 188370.77 | Approved | 12 | 2024-10-19 | 2024-12-05 | Fiber optic telemetry routing realignment along guideway
VO-PKG-09-00689 | PKG-09 | 212231.33 | 173221.16 | Approved | 15 | 2024-10-19 | 2024-11-14 | Drainage box culvert capacity expansion for 100-year flood event
VO-PKG-09-02949 | PKG-09 | 277401.78 | 261333.01 | Approved | 35 | 2024-10-19 | 2024-11-22 | Drainage box culvert capacity expansion for 100-year flood event
VO-PKG-02-02712 | PKG-02 | 271462.69 | 257812.55 | Approved | 5 | 2024-10-20 | 2024-11-21 | TBM Cutterhead refurbishment and rock fissure sealing
VO-PKG-05-01985 | PKG-05 | 84401.56 | 0 | Pending Approval | 19 | 2024-10-20 |  | HV substation redundancy transformer capacity upgrade
VO-PKG-05-02445 | PKG-05 | 90128.78 | 73084.34 | Approved | 58 | 2024-10-20 | 2024-12-02 | HV substation redundancy transformer capacity upgrade
VO-PKG-10-00060 | PKG-10 | 312635.96 | 0 | Rejected | 0 | 2024-10-20 | 2024-11-02 | HVAC chilled water pipe rerouting around station concourse
VO-PKG-05-00565 | PKG-05 | 221933.46 | 212259.97 | Approved | 58 | 2024-10-21 | 2024-12-09 | HV substation redundancy transformer capacity upgrade
VO-PKG-05-01315 | PKG-05 | 90325.22 | 78323.76 | Approved | 49 | 2024-10-21 | 2024-12-12 | HV substation redundancy transformer capacity upgrade
VO-PKG-07-01697 | PKG-07 | 128650.85 | 0 | Pending Approval | 14 | 2024-10-21 |  | Fiber optic telemetry routing realignment along guideway
VO-PKG-08-02298 | PKG-08 | 88503.46 | 72842.8 | Approved | 36 | 2024-10-21 | 2024-11-19 | Track vibration damping rubber pads acoustic upgrade
VO-PKG-03-02953 | PKG-03 | 174275.31 | 139760.38 | Approved | 52 | 2024-10-22 | 2024-11-06 | Viaduct pier foundation redesign due to utility clash
VO-PKG-06-01246 | PKG-06 | 48793.68 | 41456.29 | Approved | 5 | 2024-10-22 | 2024-12-10 | Additional smoke evacuation shafts in underground platforms
VO-PKG-06-02746 | PKG-06 | 201813.57 | 197137.53 | Approved | 12 | 2024-10-22 | 2024-11-19 | Additional smoke evacuation shafts in underground platforms
VO-PKG-08-01528 | PKG-08 | 58255.35 | 0 | Rejected | 0 | 2024-10-22 | 2024-12-04 | Track vibration damping rubber pads acoustic upgrade
VO-PKG-03-01203 | PKG-03 | 265611.09 | 0 | Pending Approval | 16 | 2024-10-23 |  | Viaduct pier foundation redesign due to utility clash
VO-PKG-08-00278 | PKG-08 | 348551.27 | 294504.58 | Approved | 22 | 2024-10-23 | 2024-12-11 | Track vibration damping rubber pads acoustic upgrade
VO-PKG-02-02272 | PKG-02 | 47712.49 | 0 | Pending Approval | 34 | 2024-10-24 |  | TBM Cutterhead refurbishment and rock fissure sealing
VO-PKG-03-00603 | PKG-03 | 287883.93 | 0 | Pending Approval | 28 | 2024-10-24 |  | Viaduct pier foundation redesign due to utility clash
VO-PKG-04-00744 | PKG-04 | 54822.58 | 44249.21 | Approved | 35 | 2024-10-24 | 2024-11-23 | Station box diaphragm wall water ingress mitigation
VO-PKG-05-02795 | PKG-05 | 240703.23 | 0 | Pending Approval | 32 | 2024-10-25 |  | HV substation redundancy transformer capacity upgrade
VO-PKG-06-02216 | PKG-06 | 42851.38 | 37378.19 | Approved | 42 | 2024-10-25 | 2024-11-09 | Additional smoke evacuation shafts in underground platforms
VO-PKG-08-01178 | PKG-08 | 259291.02 | 0 | Pending Approval | 13 | 2024-10-25 |  | Track vibration damping rubber pads acoustic upgrade
VO-PKG-09-00039 | PKG-09 | 153008.74 | 144977.14 | Approved | 58 | 2024-10-25 | 2024-11-13 | Drainage box culvert capacity expansion for 100-year flood event
VO-PKG-09-00389 | PKG-09 | 17599.13 | 0 | Rejected | 0 | 2024-10-25 | 2024-11-19 | Drainage box culvert capacity expansion for 100-year flood event
VO-PKG-10-01520 | PKG-10 | 259840.69 | 232156.09 | Approved | 52 | 2024-10-25 | 2024-11-30 | HVAC chilled water pipe rerouting around station concourse
VO-PKG-03-00013 | PKG-03 | 119365.44 | 96735.42 | Approved | 35 | 2024-10-27 | 2024-12-17 | Viaduct pier foundation redesign due to utility clash
VO-PKG-04-02444 | PKG-04 | 60156.08 | 0 | Pending Approval | 23 | 2024-10-27 |  | Station box diaphragm wall water ingress mitigation
VO-PKG-06-02026 | PKG-06 | 195603.29 | 0 | Pending Approval | 13 | 2024-10-27 |  | Additional smoke evacuation shafts in underground platforms
VO-PKG-09-02139 | PKG-09 | 293689.61 | 274678.3 | Approved | 53 | 2024-10-27 | 2024-12-20 | Drainage box culvert capacity expansion for 100-year flood event
VO-PKG-10-02940 | PKG-10 | 152839.3 | 0 | Rejected | 0 | 2024-10-27 | 2024-12-03 | HVAC chilled water pipe rerouting around station concourse
VO-PKG-02-00402 | PKG-02 | 199066.25 | 0 | Pending Approval | 34 | 2024-10-28 |  | TBM Cutterhead refurbishment and rock fissure sealing
VO-PKG-02-00462 | PKG-02 | 199679.94 | 187742.02 | Approved | 30 | 2024-10-28 | 2024-11-14 | TBM Cutterhead refurbishment and rock fissure sealing
VO-PKG-03-00963 | PKG-03 | 307790.78 | 269555.21 | Approved | 6 | 2024-10-28 | 2024-11-20 | Viaduct pier foundation redesign due to utility clash
VO-PKG-04-02404 | PKG-04 | 284752.3 | 229846.66 | Approved | 28 | 2024-10-28 | 2024-12-08 | Station box diaphragm wall water ingress mitigation
VO-PKG-07-02417 | PKG-07 | 120036.23 | 107593.68 | Approved | 25 | 2024-10-28 | 2024-11-23 | Fiber optic telemetry routing realignment along guideway
VO-PKG-02-02042 | PKG-02 | 227277.95 | 208713.68 | Approved | 56 | 2024-10-29 | 2024-11-24 | TBM Cutterhead refurbishment and rock fissure sealing
VO-PKG-04-00954 | PKG-04 | 20204.25 | 18449.03 | Approved | 8 | 2024-10-29 | 2024-12-15 | Station box diaphragm wall water ingress mitigation
VO-PKG-07-00757 | PKG-07 | 293324.86 | 0 | Pending Approval | 10 | 2024-10-29 |  | Fiber optic telemetry routing realignment along guideway
VO-PKG-07-02577 | PKG-07 | 301285.1 | 276626.68 | Approved | 48 | 2024-10-29 | 2024-12-18 | Fiber optic telemetry routing realignment along guideway
VO-PKG-03-00193 | PKG-03 | 144156.18 | 125382.56 | Approved | 49 | 2024-10-30 | 2024-11-19 | Viaduct pier foundation redesign due to utility clash
VO-PKG-03-00233 | PKG-03 | 230742.96 | 0 | Pending Approval | 13 | 2024-10-30 |  | Viaduct pier foundation redesign due to utility clash
VO-PKG-03-02163 | PKG-03 | 16771.82 | 14975.23 | Approved | 31 | 2024-10-30 | 2024-11-24 | Viaduct pier foundation redesign due to utility clash
VO-PKG-08-01768 | PKG-08 | 42276.4 | 35151.8 | Approved | 5 | 2024-10-30 | 2024-12-12 | Track vibration damping rubber pads acoustic upgrade
VO-PKG-05-01565 | PKG-05 | 102852.71 | 0 | Pending Approval | 14 | 2024-10-31 |  | HV substation redundancy transformer capacity upgrade
VO-PKG-10-00020 | PKG-10 | 212388.56 | 185318.78 | Approved | 23 | 2024-10-31 | 2024-12-06 | HVAC chilled water pipe rerouting around station concourse
VO-PKG-10-00110 | PKG-10 | 19692.18 | 19133.49 | Approved | 18 | 2024-10-31 | 2024-12-22 | HVAC chilled water pipe rerouting around station concourse
VO-PKG-02-01362 | PKG-02 | 269198.28 | 257921.53 | Approved | 10 | 2024-11-01 | 2024-12-25 | TBM Cutterhead refurbishment and rock fissure sealing
VO-PKG-03-02843 | PKG-03 | 96764.4 | 93923.38 | Approved | 14 | 2024-11-01 | 2024-12-21 | Viaduct pier foundation redesign due to utility clash
VO-PKG-04-00384 | PKG-04 | 72114.06 | 0 | Pending Approval | 42 | 2024-11-01 |  | Station box diaphragm wall water ingress mitigation
VO-PKG-05-00525 | PKG-05 | 236852.7 | 190222.96 | Approved | 44 | 2024-11-01 | 2024-11-22 | HV substation redundancy transformer capacity upgrade
VO-PKG-02-00302 | PKG-02 | 45508.76 | 39878.38 | Approved | 23 | 2024-11-02 | 2024-12-04 | TBM Cutterhead refurbishment and rock fissure sealing
VO-PKG-04-02624 | PKG-04 | 191010.18 | 176417.86 | Approved | 51 | 2024-11-02 | 2024-11-25 | Station box diaphragm wall water ingress mitigation
VO-PKG-08-00448 | PKG-08 | 156272.54 | 0 | Rejected | 0 | 2024-11-02 | 2024-12-01 | Track vibration damping rubber pads acoustic upgrade
VO-PKG-01-02121 | PKG-01 | 107864.27 | 105052.42 | Approved | 25 | 2024-11-03 | 2024-11-30 | Unforeseen soft ground stabilization and grouting
VO-PKG-02-01612 | PKG-02 | 120515.6 | 103829.95 | Approved | 51 | 2024-11-03 | 2024-12-08 | TBM Cutterhead refurbishment and rock fissure sealing
VO-PKG-06-01786 | PKG-06 | 198403.86 | 192531.73 | Approved | 10 | 2024-11-03 | 2024-12-01 | Additional smoke evacuation shafts in underground platforms
VO-PKG-07-02937 | PKG-07 | 241885.26 | 201739 | Approved | 42 | 2024-11-03 | 2024-11-22 | Fiber optic telemetry routing realignment along guideway
VO-PKG-10-02770 | PKG-10 | 23829.04 | 19614.32 | Approved | 30 | 2024-11-03 | 2024-11-20 | HVAC chilled water pipe rerouting around station concourse
VO-PKG-01-00281 | PKG-01 | 337556.84 | 0 | Rejected | 0 | 2024-11-04 | 2024-12-10 | Unforeseen soft ground stabilization and grouting
VO-PKG-03-00313 | PKG-03 | 217779.36 | 0 | Pending Approval | 38 | 2024-11-04 |  | Viaduct pier foundation redesign due to utility clash
VO-PKG-07-00457 | PKG-07 | 239022.5 | 0 | Pending Approval | 4 | 2024-11-04 |  | Fiber optic telemetry routing realignment along guideway
VO-PKG-10-01670 | PKG-10 | 70103.8 | 65847.76 | Approved | 45 | 2024-11-04 | 2025-01-01 | HVAC chilled water pipe rerouting around station concourse
VO-PKG-01-00051 | PKG-01 | 224673.76 | 0 | Pending Approval | 22 | 2024-11-05 |  | Unforeseen soft ground stabilization and grouting
VO-PKG-01-02851 | PKG-01 | 28369.08 | 0 | Pending Approval | 20 | 2024-11-05 |  | Unforeseen soft ground stabilization and grouting
VO-PKG-02-00492 | PKG-02 | 143204.41 | 115236.41 | Approved | 9 | 2024-11-05 | 2024-11-20 | TBM Cutterhead refurbishment and rock fissure sealing
VO-PKG-04-00904 | PKG-04 | 207019.69 | 200443.32 | Approved | 20 | 2024-11-05 | 2024-12-28 | Station box diaphragm wall water ingress mitigation
VO-PKG-05-01075 | PKG-05 | 56970.14 | 0 | Pending Approval | 28 | 2024-11-05 |  | HV substation redundancy transformer capacity upgrade
VO-PKG-06-01486 | PKG-06 | 189521.59 | 0 | Pending Approval | 21 | 2024-11-05 |  | Additional smoke evacuation shafts in underground platforms
VO-PKG-07-00087 | PKG-07 | 206804.9 | 191652.55 | Approved | 34 | 2024-11-05 | 2024-12-30 | Fiber optic telemetry routing realignment along guideway
VO-PKG-01-02071 | PKG-01 | 231686.29 | 0 | Pending Approval | 40 | 2024-11-06 |  | Unforeseen soft ground stabilization and grouting
VO-PKG-02-01952 | PKG-02 | 68926.74 | 64533.08 | Approved | 23 | 2024-11-06 | 2024-11-21 | TBM Cutterhead refurbishment and rock fissure sealing
VO-PKG-01-02641 | PKG-01 | 117396.08 | 99958.73 | Approved | 21 | 2024-11-07 | 2024-12-12 | Unforeseen soft ground stabilization and grouting
VO-PKG-03-02533 | PKG-03 | 143367.03 | 0 | Pending Approval | 25 | 2024-11-07 |  | Viaduct pier foundation redesign due to utility clash
VO-PKG-09-01499 | PKG-09 | 165078.32 | 137677.51 | Approved | 24 | 2024-11-07 | 2024-12-19 | Drainage box culvert capacity expansion for 100-year flood event
VO-PKG-01-00071 | PKG-01 | 260270.21 | 222873.05 | Approved | 36 | 2024-11-08 | 2024-12-22 | Unforeseen soft ground stabilization and grouting
VO-PKG-04-02914 | PKG-04 | 150177.88 | 0 | Pending Approval | 44 | 2024-11-08 |  | Station box diaphragm wall water ingress mitigation
VO-PKG-01-02141 | PKG-01 | 294280.17 | 0 | Rejected | 0 | 2024-11-10 | 2024-12-09 | Unforeseen soft ground stabilization and grouting
VO-PKG-01-02681 | PKG-01 | 107171.29 | 0 | Pending Approval | 34 | 2024-11-10 |  | Unforeseen soft ground stabilization and grouting
VO-PKG-07-02237 | PKG-07 | 126612.15 | 113202.37 | Approved | 27 | 2024-11-10 | 2024-12-26 | Fiber optic telemetry routing realignment along guideway
VO-PKG-01-02221 | PKG-01 | 322664.4 | 287449.61 | Approved | 36 | 2024-11-11 | 2024-12-14 | Unforeseen soft ground stabilization and grouting
VO-PKG-10-00160 | PKG-10 | 176565.18 | 150322.61 | Approved | 50 | 2024-11-11 | 2025-01-01 | HVAC chilled water pipe rerouting around station concourse
VO-PKG-05-02525 | PKG-05 | 167461.45 | 0 | Pending Approval | 26 | 2024-11-12 |  | HV substation redundancy transformer capacity upgrade
VO-PKG-05-02625 | PKG-05 | 178407.07 | 168490.56 | Approved | 16 | 2024-11-12 | 2025-01-06 | HV substation redundancy transformer capacity upgrade
VO-PKG-08-01898 | PKG-08 | 185950.99 | 151332.14 | Approved | 5 | 2024-11-12 | 2024-12-21 | Track vibration damping rubber pads acoustic upgrade
VO-PKG-09-02289 | PKG-09 | 236288.69 | 213135.36 | Approved | 36 | 2024-11-12 | 2024-12-07 | Drainage box culvert capacity expansion for 100-year flood event
VO-PKG-03-02643 | PKG-03 | 223680.11 | 181495.92 | Approved | 24 | 2024-11-13 | 2025-01-03 | Viaduct pier foundation redesign due to utility clash
VO-PKG-09-00799 | PKG-09 | 121003.65 | 110529.28 | Approved | 21 | 2024-11-13 | 2024-12-13 | Drainage box culvert capacity expansion for 100-year flood event
VO-PKG-03-01433 | PKG-03 | 264584.81 | 227097.77 | Approved | 33 | 2024-11-14 | 2025-01-07 | Viaduct pier foundation redesign due to utility clash
VO-PKG-09-00309 | PKG-09 | 316672.84 | 274628.44 | Approved | 24 | 2024-11-14 | 2024-12-29 | Drainage box culvert capacity expansion for 100-year flood event
VO-PKG-05-01635 | PKG-05 | 310663.5 | 0 | Rejected | 0 | 2024-11-15 | 2024-11-30 | HV substation redundancy transformer capacity upgrade
VO-PKG-06-00996 | PKG-06 | 39883.52 | 34134.65 | Approved | 36 | 2024-11-15 | 2024-12-24 | Additional smoke evacuation shafts in underground platforms
VO-PKG-02-01892 | PKG-02 | 192531.77 | 0 | Pending Approval | 36 | 2024-11-16 |  | TBM Cutterhead refurbishment and rock fissure sealing
VO-PKG-08-02388 | PKG-08 | 85937.15 | 0 | Pending Approval | 40 | 2024-11-16 |  | Track vibration damping rubber pads acoustic upgrade
VO-PKG-10-00620 | PKG-10 | 329116.31 | 268834.09 | Approved | 31 | 2024-11-16 | 2024-12-18 | HVAC chilled water pipe rerouting around station concourse
VO-PKG-10-02690 | PKG-10 | 30272.2 | 26289.82 | Approved | 7 | 2024-11-17 | 2024-12-24 | HVAC chilled water pipe rerouting around station concourse
VO-PKG-01-02261 | PKG-01 | 106859.05 | 0 | Pending Approval | 26 | 2024-11-19 |  | Unforeseen soft ground stabilization and grouting
VO-PKG-05-02305 | PKG-05 | 72716.06 | 0 | Pending Approval | 18 | 2024-11-19 |  | HV substation redundancy transformer capacity upgrade
VO-PKG-08-02718 | PKG-08 | 187397.24 | 171764.66 | Approved | 38 | 2024-11-20 | 2025-01-04 | Track vibration damping rubber pads acoustic upgrade
VO-PKG-10-00480 | PKG-10 | 141185.33 | 0 | Rejected | 0 | 2024-11-20 | 2024-12-10 | HVAC chilled water pipe rerouting around station concourse
VO-PKG-02-01442 | PKG-02 | 143085.9 | 0 | Pending Approval | 29 | 2024-11-21 |  | TBM Cutterhead refurbishment and rock fissure sealing
VO-PKG-03-02393 | PKG-03 | 253443.62 | 222485.27 | Approved | 12 | 2024-11-21 | 2025-01-09 | Viaduct pier foundation redesign due to utility clash
VO-PKG-08-02258 | PKG-08 | 218559.66 | 0 | Pending Approval | 26 | 2024-11-21 |  | Track vibration damping rubber pads acoustic upgrade
VO-PKG-02-02112 | PKG-02 | 72908.29 | 0 | Rejected | 0 | 2024-11-22 | 2025-01-03 | TBM Cutterhead refurbishment and rock fissure sealing
VO-PKG-09-02549 | PKG-09 | 261761.44 | 0 | Pending Approval | 19 | 2024-11-22 |  | Drainage box culvert capacity expansion for 100-year flood event
VO-PKG-07-00397 | PKG-07 | 94861.69 | 0 | Pending Approval | 4 | 2024-11-23 |  | Fiber optic telemetry routing realignment along guideway
VO-PKG-07-01887 | PKG-07 | 53609.14 | 0 | Pending Approval | 3 | 2024-11-23 |  | Fiber optic telemetry routing realignment along guideway
VO-PKG-02-02702 | PKG-02 | 321720.63 | 290884.91 | Approved | 35 | 2024-11-24 | 2024-12-17 | TBM Cutterhead refurbishment and rock fissure sealing
VO-PKG-04-00274 | PKG-04 | 201574.09 | 172451.99 | Approved | 23 | 2024-11-24 | 2024-12-23 | Station box diaphragm wall water ingress mitigation
VO-PKG-04-01544 | PKG-04 | 25529.1 | 24756.77 | Approved | 38 | 2024-11-24 | 2024-12-29 | Station box diaphragm wall water ingress mitigation
VO-PKG-04-02414 | PKG-04 | 153994.53 | 0 | Pending Approval | 13 | 2024-11-24 |  | Station box diaphragm wall water ingress mitigation
VO-PKG-09-02759 | PKG-09 | 60369.23 | 0 | Pending Approval | 3 | 2024-11-24 |  | Drainage box culvert capacity expansion for 100-year flood event
VO-PKG-01-01261 | PKG-01 | 224401.93 | 0 | Pending Approval | 20 | 2024-11-25 |  | Unforeseen soft ground stabilization and grouting
VO-PKG-10-01890 | PKG-10 | 105703.98 | 0 | Pending Approval | 13 | 2024-11-25 |  | HVAC chilled water pipe rerouting around station concourse
VO-PKG-01-02131 | PKG-01 | 137163.29 | 0 | Rejected | 0 | 2024-11-26 | 2025-01-07 | Unforeseen soft ground stabilization and grouting
VO-PKG-07-00697 | PKG-07 | 176301.71 | 0 | Pending Approval | 31 | 2024-11-26 |  | Fiber optic telemetry routing realignment along guideway
VO-PKG-10-01260 | PKG-10 | 218081.59 | 205145.48 | Approved | 33 | 2024-11-26 | 2024-12-20 | HVAC chilled water pipe rerouting around station concourse
VO-PKG-06-00106 | PKG-06 | 188916.44 | 164645.97 | Approved | 22 | 2024-11-27 | 2024-12-23 | Additional smoke evacuation shafts in underground platforms
VO-PKG-07-02127 | PKG-07 | 266951.19 | 0 | Rejected | 0 | 2024-11-27 | 2024-12-22 | Fiber optic telemetry routing realignment along guideway
VO-PKG-07-02397 | PKG-07 | 27673.52 | 23113.77 | Approved | 51 | 2024-11-27 | 2025-01-23 | Fiber optic telemetry routing realignment along guideway
VO-PKG-10-00940 | PKG-10 | 300670.73 | 248012.79 | Approved | 11 | 2024-11-27 | 2024-12-16 | HVAC chilled water pipe rerouting around station concourse
VO-PKG-10-01230 | PKG-10 | 348116.23 | 0 | Pending Approval | 39 | 2024-11-27 |  | HVAC chilled water pipe rerouting around station concourse
VO-PKG-01-01221 | PKG-01 | 299271.29 | 258075.55 | Approved | 54 | 2024-11-28 | 2025-01-25 | Unforeseen soft ground stabilization and grouting
VO-PKG-03-02793 | PKG-03 | 24367.96 | 20893.18 | Approved | 48 | 2024-11-28 | 2024-12-20 | Viaduct pier foundation redesign due to utility clash
VO-PKG-04-00074 | PKG-04 | 249054.95 | 0 | Rejected | 0 | 2024-11-28 | 2025-01-09 | Station box diaphragm wall water ingress mitigation
VO-PKG-10-01630 | PKG-10 | 66718.9 | 0 | Pending Approval | 13 | 2024-11-28 |  | HVAC chilled water pipe rerouting around station concourse
VO-PKG-02-01862 | PKG-02 | 194988.66 | 0 | Rejected | 0 | 2024-11-29 | 2024-12-28 | TBM Cutterhead refurbishment and rock fissure sealing
VO-PKG-02-02402 | PKG-02 | 260799.01 | 0 | Rejected | 0 | 2024-11-29 | 2024-12-12 | TBM Cutterhead refurbishment and rock fissure sealing
VO-PKG-07-02297 | PKG-07 | 102367.54 | 0 | Pending Approval | 11 | 2024-11-29 |  | Fiber optic telemetry routing realignment along guideway
VO-PKG-08-00108 | PKG-08 | 233347.17 | 0 | Pending Approval | 26 | 2024-11-29 |  | Track vibration damping rubber pads acoustic upgrade
VO-PKG-08-02438 | PKG-08 | 244337.24 | 213688.66 | Approved | 21 | 2024-11-29 | 2025-01-19 | Track vibration damping rubber pads acoustic upgrade
VO-PKG-10-01570 | PKG-10 | 218015.93 | 187512.41 | Approved | 25 | 2024-11-29 | 2024-12-17 | HVAC chilled water pipe rerouting around station concourse
VO-PKG-01-01291 | PKG-01 | 94520.62 | 83589.19 | Approved | 14 | 2024-11-30 | 2024-12-15 | Unforeseen soft ground stabilization and grouting
VO-PKG-01-01631 | PKG-01 | 326293.05 | 265398.43 | Approved | 30 | 2024-11-30 | 2025-01-18 | Unforeseen soft ground stabilization and grouting
VO-PKG-02-00692 | PKG-02 | 193740.39 | 0 | Pending Approval | 20 | 2024-11-30 |  | TBM Cutterhead refurbishment and rock fissure sealing
VO-PKG-07-02327 | PKG-07 | 42259.45 | 0 | Pending Approval | 8 | 2024-11-30 |  | Fiber optic telemetry routing realignment along guideway
VO-PKG-10-01820 | PKG-10 | 281991.4 | 242548.19 | Approved | 36 | 2024-12-01 | 2025-01-19 | HVAC chilled water pipe rerouting around station concourse
VO-PKG-01-00371 | PKG-01 | 29337.7 | 25732.24 | Approved | 30 | 2024-12-02 | 2025-01-19 | Unforeseen soft ground stabilization and grouting
VO-PKG-03-00613 | PKG-03 | 294086.12 | 251709.51 | Approved | 42 | 2024-12-02 | 2024-12-31 | Viaduct pier foundation redesign due to utility clash
VO-PKG-03-00793 | PKG-03 | 124103.75 | 116847.3 | Approved | 26 | 2024-12-02 | 2024-12-25 | Viaduct pier foundation redesign due to utility clash
VO-PKG-08-00078 | PKG-08 | 133564.57 | 128753.35 | Approved | 11 | 2024-12-02 | 2025-01-12 | Track vibration damping rubber pads acoustic upgrade
VO-PKG-08-00868 | PKG-08 | 327988.35 | 278873.39 | Approved | 33 | 2024-12-02 | 2024-12-27 | Track vibration damping rubber pads acoustic upgrade
VO-PKG-09-00199 | PKG-09 | 214187.08 | 181150.14 | Approved | 25 | 2024-12-02 | 2025-01-24 | Drainage box culvert capacity expansion for 100-year flood event
VO-PKG-01-00291 | PKG-01 | 316546.81 | 0 | Rejected | 0 | 2024-12-03 | 2025-01-01 | Unforeseen soft ground stabilization and grouting
VO-PKG-01-01931 | PKG-01 | 196006.91 | 189970.6 | Approved | 47 | 2024-12-03 | 2024-12-18 | Unforeseen soft ground stabilization and grouting
VO-PKG-04-02614 | PKG-04 | 129383.19 | 0 | Pending Approval | 26 | 2024-12-03 |  | Station box diaphragm wall water ingress mitigation
VO-PKG-08-01668 | PKG-08 | 233484.63 | 222595.28 | Approved | 56 | 2024-12-03 | 2024-12-26 | Track vibration damping rubber pads acoustic upgrade
VO-PKG-07-02707 | PKG-07 | 134280.39 | 117224.61 | Approved | 20 | 2024-12-04 | 2025-01-20 | Fiber optic telemetry routing realignment along guideway
VO-PKG-03-00873 | PKG-03 | 174848.92 | 151726.73 | Approved | 5 | 2024-12-05 | 2024-12-31 | Viaduct pier foundation redesign due to utility clash
VO-PKG-05-00015 | PKG-05 | 259026.46 | 248587.2 | Approved | 59 | 2024-12-05 | 2024-12-20 | HV substation redundancy transformer capacity upgrade
VO-PKG-06-01146 | PKG-06 | 74776.4 | 67773.93 | Approved | 42 | 2024-12-05 | 2025-01-21 | Additional smoke evacuation shafts in underground platforms
VO-PKG-07-00817 | PKG-07 | 256117.33 | 229229.73 | Approved | 59 | 2024-12-05 | 2025-01-15 | Fiber optic telemetry routing realignment along guideway
VO-PKG-09-02109 | PKG-09 | 342182.92 | 0 | Pending Approval | 32 | 2024-12-05 |  | Drainage box culvert capacity expansion for 100-year flood event
VO-PKG-04-01664 | PKG-04 | 106783.91 | 0 | Pending Approval | 23 | 2024-12-06 |  | Station box diaphragm wall water ingress mitigation
VO-PKG-06-00156 | PKG-06 | 86090.72 | 0 | Pending Approval | 35 | 2024-12-06 |  | Additional smoke evacuation shafts in underground platforms
VO-PKG-09-00579 | PKG-09 | 106697.11 | 0 | Pending Approval | 40 | 2024-12-06 |  | Drainage box culvert capacity expansion for 100-year flood event
VO-PKG-02-02952 | PKG-02 | 307734.37 | 0 | Pending Approval | 41 | 2024-12-07 |  | TBM Cutterhead refurbishment and rock fissure sealing
VO-PKG-08-01848 | PKG-08 | 325114.12 | 311113.72 | Approved | 14 | 2024-12-07 | 2025-01-31 | Track vibration damping rubber pads acoustic upgrade
VO-PKG-09-00349 | PKG-09 | 318680.04 | 280453.83 | Approved | 21 | 2024-12-07 | 2025-01-03 | Drainage box culvert capacity expansion for 100-year flood event
VO-PKG-10-01880 | PKG-10 | 258151.03 | 215061.27 | Approved | 41 | 2024-12-07 | 2025-01-30 | HVAC chilled water pipe rerouting around station concourse
VO-PKG-03-01793 | PKG-03 | 292487.34 | 0 | Pending Approval | 5 | 2024-12-08 |  | Viaduct pier foundation redesign due to utility clash
VO-PKG-08-02688 | PKG-08 | 280083.8 | 0 | Pending Approval | 13 | 2024-12-08 |  | Track vibration damping rubber pads acoustic upgrade
VO-PKG-10-02140 | PKG-10 | 99109.7 | 0 | Pending Approval | 41 | 2024-12-08 |  | HVAC chilled water pipe rerouting around station concourse
VO-PKG-10-02250 | PKG-10 | 204977.44 | 177314.02 | Approved | 44 | 2024-12-08 | 2025-01-17 | HVAC chilled water pipe rerouting around station concourse
VO-PKG-01-01021 | PKG-01 | 106464.34 | 100423.55 | Approved | 10 | 2024-12-09 | 2025-01-11 | Unforeseen soft ground stabilization and grouting
VO-PKG-04-01744 | PKG-04 | 52709.89 | 0 | Rejected | 0 | 2024-12-09 | 2024-12-31 | Station box diaphragm wall water ingress mitigation
VO-PKG-08-00578 | PKG-08 | 283814.59 | 277241.18 | Approved | 50 | 2024-12-09 | 2025-02-05 | Track vibration damping rubber pads acoustic upgrade
VO-PKG-05-02925 | PKG-05 | 341117.02 | 328788.26 | Approved | 17 | 2024-12-10 | 2025-01-16 | HV substation redundancy transformer capacity upgrade
VO-PKG-08-02318 | PKG-08 | 243510.84 | 0 | Pending Approval | 17 | 2024-12-10 |  | Track vibration damping rubber pads acoustic upgrade
VO-PKG-01-01231 | PKG-01 | 193864.35 | 0 | Pending Approval | 39 | 2024-12-11 |  | Unforeseen soft ground stabilization and grouting
VO-PKG-05-00995 | PKG-05 | 272998.85 | 243673.63 | Approved | 42 | 2024-12-11 | 2025-01-24 | HV substation redundancy transformer capacity upgrade
VO-PKG-07-00937 | PKG-07 | 126342.62 | 103344.52 | Approved | 53 | 2024-12-11 | 2025-01-11 | Fiber optic telemetry routing realignment along guideway
VO-PKG-07-02897 | PKG-07 | 251803.97 | 203666.31 | Approved | 39 | 2024-12-11 | 2025-01-15 | Fiber optic telemetry routing realignment along guideway
VO-PKG-10-02160 | PKG-10 | 66796.25 | 54646.27 | Approved | 29 | 2024-12-11 | 2025-01-12 | HVAC chilled water pipe rerouting around station concourse
VO-PKG-07-01997 | PKG-07 | 17395.42 | 16294.86 | Approved | 53 | 2024-12-12 | 2024-12-30 | Fiber optic telemetry routing realignment along guideway
VO-PKG-01-01711 | PKG-01 | 281461.05 | 259605.62 | Approved | 40 | 2024-12-13 | 2025-01-02 | Unforeseen soft ground stabilization and grouting
VO-PKG-02-01762 | PKG-02 | 223810.05 | 200732.15 | Approved | 10 | 2024-12-13 | 2025-01-22 | TBM Cutterhead refurbishment and rock fissure sealing
VO-PKG-02-01772 | PKG-02 | 113538.31 | 110777.54 | Approved | 30 | 2024-12-13 | 2025-01-09 | TBM Cutterhead refurbishment and rock fissure sealing
VO-PKG-02-02802 | PKG-02 | 315021.13 | 300638.37 | Approved | 18 | 2024-12-13 | 2025-02-09 | TBM Cutterhead refurbishment and rock fissure sealing
VO-PKG-03-02913 | PKG-03 | 188863.81 | 0 | Pending Approval | 8 | 2024-12-13 |  | Viaduct pier foundation redesign due to utility clash
VO-PKG-07-01617 | PKG-07 | 154945.62 | 149587.98 | Approved | 35 | 2024-12-13 | 2025-01-25 | Fiber optic telemetry routing realignment along guideway
VO-PKG-03-00813 | PKG-03 | 101574.83 | 93007.07 | Approved | 17 | 2024-12-14 | 2025-02-06 | Viaduct pier foundation redesign due to utility clash
VO-PKG-03-02283 | PKG-03 | 331932.93 | 0 | Pending Approval | 36 | 2024-12-14 |  | Viaduct pier foundation redesign due to utility clash
VO-PKG-09-00859 | PKG-09 | 66768.51 | 64011.19 | Approved | 16 | 2024-12-14 | 2025-01-21 | Drainage box culvert capacity expansion for 100-year flood event
VO-PKG-01-02531 | PKG-01 | 102343.53 | 93231.31 | Approved | 21 | 2024-12-15 | 2025-01-27 | Unforeseen soft ground stabilization and grouting
VO-PKG-04-02274 | PKG-04 | 238905.09 | 0 | Pending Approval | 39 | 2024-12-15 |  | Station box diaphragm wall water ingress mitigation
VO-PKG-08-00328 | PKG-08 | 185136.27 | 180788.27 | Approved | 26 | 2024-12-15 | 2025-01-01 | Track vibration damping rubber pads acoustic upgrade
VO-PKG-04-01984 | PKG-04 | 254770.59 | 237747.61 | Approved | 11 | 2024-12-16 | 2025-02-13 | Station box diaphragm wall water ingress mitigation
VO-PKG-04-02844 | PKG-04 | 231925.41 | 193464.96 | Approved | 34 | 2024-12-16 | 2025-02-03 | Station box diaphragm wall water ingress mitigation
VO-PKG-09-00149 | PKG-09 | 111067.6 | 98663.63 | Approved | 22 | 2024-12-16 | 2025-01-08 | Drainage box culvert capacity expansion for 100-year flood event
VO-PKG-01-01111 | PKG-01 | 307671.28 | 247378.86 | Approved | 31 | 2024-12-17 | 2025-02-05 | Unforeseen soft ground stabilization and grouting
VO-PKG-02-02582 | PKG-02 | 130710.08 | 105482.41 | Approved | 41 | 2024-12-17 | 2025-01-11 | TBM Cutterhead refurbishment and rock fissure sealing
VO-PKG-03-01823 | PKG-03 | 220116.84 | 189503.47 | Approved | 28 | 2024-12-17 | 2025-01-15 | Viaduct pier foundation redesign due to utility clash
VO-PKG-07-00967 | PKG-07 | 283266.26 | 0 | Pending Approval | 30 | 2024-12-17 |  | Fiber optic telemetry routing realignment along guideway
VO-PKG-08-02538 | PKG-08 | 110605.34 | 0 | Rejected | 0 | 2024-12-17 | 2024-12-28 | Track vibration damping rubber pads acoustic upgrade
VO-PKG-09-00869 | PKG-09 | 328151.27 | 321105.97 | Approved | 56 | 2024-12-17 | 2025-01-10 | Drainage box culvert capacity expansion for 100-year flood event
VO-PKG-10-00180 | PKG-10 | 185831.61 | 0 | Pending Approval | 12 | 2024-12-17 |  | HVAC chilled water pipe rerouting around station concourse
VO-PKG-02-00952 | PKG-02 | 70785.1 | 63692.06 | Approved | 17 | 2024-12-18 | 2025-01-17 | TBM Cutterhead refurbishment and rock fissure sealing
VO-PKG-03-00803 | PKG-03 | 146059.15 | 0 | Pending Approval | 4 | 2024-12-18 |  | Viaduct pier foundation redesign due to utility clash
VO-PKG-03-01913 | PKG-03 | 194595.65 | 0 | Pending Approval | 43 | 2024-12-18 |  | Viaduct pier foundation redesign due to utility clash
VO-PKG-05-02405 | PKG-05 | 94426.52 | 82691.31 | Approved | 51 | 2024-12-18 | 2025-01-09 | HV substation redundancy transformer capacity upgrade
VO-PKG-06-01866 | PKG-06 | 31387.82 | 25526.8 | Approved | 44 | 2024-12-18 | 2025-02-04 | Additional smoke evacuation shafts in underground platforms
VO-PKG-08-02848 | PKG-08 | 110066.22 | 0 | Pending Approval | 30 | 2024-12-18 |  | Track vibration damping rubber pads acoustic upgrade
VO-PKG-09-01469 | PKG-09 | 86420.09 | 78120.82 | Approved | 44 | 2024-12-18 | 2025-01-14 | Drainage box culvert capacity expansion for 100-year flood event
VO-PKG-01-00581 | PKG-01 | 316966.32 | 0 | Rejected | 0 | 2024-12-19 | 2025-01-07 | Unforeseen soft ground stabilization and grouting
VO-PKG-06-00536 | PKG-06 | 103528.05 | 92247.01 | Approved | 24 | 2024-12-19 | 2025-01-14 | Additional smoke evacuation shafts in underground platforms
VO-PKG-06-01346 | PKG-06 | 224909.43 | 208333.1 | Approved | 31 | 2024-12-19 | 2025-01-14 | Additional smoke evacuation shafts in underground platforms
VO-PKG-07-02487 | PKG-07 | 147840.25 | 0 | Rejected | 0 | 2024-12-19 | 2025-01-17 | Fiber optic telemetry routing realignment along guideway
VO-PKG-08-00778 | PKG-08 | 335877.3 | 327590.83 | Approved | 23 | 2024-12-19 | 2025-01-04 | Track vibration damping rubber pads acoustic upgrade
VO-PKG-09-02259 | PKG-09 | 199269.87 | 0 | Pending Approval | 0 | 2024-12-19 |  | Drainage box culvert capacity expansion for 100-year flood event
VO-PKG-01-01901 | PKG-01 | 210201.66 | 205709.9 | Approved | 11 | 2024-12-20 | 2025-01-17 | Unforeseen soft ground stabilization and grouting
VO-PKG-02-01172 | PKG-02 | 132394.86 | 0 | Pending Approval | 20 | 2024-12-20 |  | TBM Cutterhead refurbishment and rock fissure sealing
VO-PKG-01-02721 | PKG-01 | 79312.22 | 0 | Pending Approval | 39 | 2024-12-21 |  | Unforeseen soft ground stabilization and grouting
VO-PKG-03-00973 | PKG-03 | 273995.53 | 0 | Rejected | 0 | 2024-12-21 | 2025-01-14 | Viaduct pier foundation redesign due to utility clash
VO-PKG-07-00347 | PKG-07 | 116935.6 | 97299.38 | Approved | 7 | 2024-12-21 | 2025-01-09 | Fiber optic telemetry routing realignment along guideway
VO-PKG-08-02238 | PKG-08 | 295006.96 | 0 | Pending Approval | 42 | 2024-12-21 |  | Track vibration damping rubber pads acoustic upgrade
VO-PKG-09-00559 | PKG-09 | 309036.86 | 281638.1 | Approved | 46 | 2024-12-21 | 2025-02-16 | Drainage box culvert capacity expansion for 100-year flood event
VO-PKG-05-01185 | PKG-05 | 32812.66 | 0 | Pending Approval | 20 | 2024-12-22 |  | HV substation redundancy transformer capacity upgrade
VO-PKG-05-01645 | PKG-05 | 169639.13 | 154703.48 | Approved | 13 | 2024-12-22 | 2025-01-17 | HV substation redundancy transformer capacity upgrade
VO-PKG-02-01142 | PKG-02 | 48888.62 | 0 | Pending Approval | 6 | 2024-12-23 |  | TBM Cutterhead refurbishment and rock fissure sealing
VO-PKG-03-01483 | PKG-03 | 114902.99 | 98962.05 | Approved | 40 | 2024-12-23 | 2025-02-12 | Viaduct pier foundation redesign due to utility clash
VO-PKG-04-01704 | PKG-04 | 104996.91 | 92355.17 | Approved | 42 | 2024-12-23 | 2025-01-14 | Station box diaphragm wall water ingress mitigation
VO-PKG-06-01836 | PKG-06 | 103794.46 | 100955.37 | Approved | 38 | 2024-12-23 | 2025-02-07 | Additional smoke evacuation shafts in underground platforms
VO-PKG-07-00997 | PKG-07 | 29466.72 | 25015.59 | Approved | 55 | 2024-12-23 | 2025-02-08 | Fiber optic telemetry routing realignment along guideway
VO-PKG-08-01128 | PKG-08 | 264571.67 | 0 | Pending Approval | 26 | 2024-12-23 |  | Track vibration damping rubber pads acoustic upgrade
VO-PKG-08-01818 | PKG-08 | 85229.96 | 74537.66 | Approved | 22 | 2024-12-23 | 2025-02-15 | Track vibration damping rubber pads acoustic upgrade
VO-PKG-02-00342 | PKG-02 | 49165.24 | 0 | Pending Approval | 10 | 2024-12-24 |  | TBM Cutterhead refurbishment and rock fissure sealing
VO-PKG-03-01023 | PKG-03 | 319408.32 | 0 | Rejected | 0 | 2024-12-24 | 2025-01-26 | Viaduct pier foundation redesign due to utility clash
VO-PKG-05-00415 | PKG-05 | 328235.61 | 307108.15 | Approved | 39 | 2024-12-24 | 2025-02-03 | HV substation redundancy transformer capacity upgrade
VO-PKG-05-02345 | PKG-05 | 168026.59 | 0 | Rejected | 0 | 2024-12-24 | 2025-01-28 | HV substation redundancy transformer capacity upgrade
VO-PKG-06-01936 | PKG-06 | 64601.31 | 0 | Pending Approval | 29 | 2024-12-24 |  | Additional smoke evacuation shafts in underground platforms
VO-PKG-10-01860 | PKG-10 | 332700.93 | 287607.59 | Approved | 30 | 2024-12-24 | 2025-01-25 | HVAC chilled water pipe rerouting around station concourse
VO-PKG-07-02227 | PKG-07 | 328507.49 | 318544.43 | Approved | 14 | 2024-12-27 | 2025-02-23 | Fiber optic telemetry routing realignment along guideway
VO-PKG-08-01298 | PKG-08 | 169446.18 | 153341.68 | Approved | 40 | 2024-12-27 | 2025-02-21 | Track vibration damping rubber pads acoustic upgrade
VO-PKG-04-02814 | PKG-04 | 24730.14 | 0 | Pending Approval | 18 | 2024-12-28 |  | Station box diaphragm wall water ingress mitigation
VO-PKG-06-01606 | PKG-06 | 174650.69 | 156721.37 | Approved | 29 | 2024-12-28 | 2025-01-21 | Additional smoke evacuation shafts in underground platforms
VO-PKG-02-01792 | PKG-02 | 327589 | 269233.08 | Approved | 36 | 2024-12-29 | 2025-01-23 | TBM Cutterhead refurbishment and rock fissure sealing
VO-PKG-05-01725 | PKG-05 | 199902.67 | 189150.32 | Approved | 34 | 2024-12-29 | 2025-01-31 | HV substation redundancy transformer capacity upgrade
VO-PKG-05-02045 | PKG-05 | 157858.5 | 0 | Pending Approval | 42 | 2024-12-29 |  | HV substation redundancy transformer capacity upgrade
VO-PKG-02-00032 | PKG-02 | 111077.27 | 93987.84 | Approved | 36 | 2024-12-30 | 2025-02-19 | TBM Cutterhead refurbishment and rock fissure sealing
VO-PKG-02-01212 | PKG-02 | 68801.4 | 59557.71 | Approved | 43 | 2024-12-30 | 2025-01-31 | TBM Cutterhead refurbishment and rock fissure sealing
VO-PKG-04-00524 | PKG-04 | 184346.41 | 157352.03 | Approved | 48 | 2024-12-30 | 2025-02-12 | Station box diaphragm wall water ingress mitigation
VO-PKG-04-01604 | PKG-04 | 258250.19 | 225465.34 | Approved | 32 | 2024-12-30 | 2025-02-20 | Station box diaphragm wall water ingress mitigation
VO-PKG-04-02794 | PKG-04 | 139481.76 | 0 | Pending Approval | 31 | 2024-12-30 |  | Station box diaphragm wall water ingress mitigation
VO-PKG-03-00483 | PKG-03 | 28649.19 | 26933.09 | Approved | 40 | 2024-12-31 | 2025-01-28 | Viaduct pier foundation redesign due to utility clash
VO-PKG-06-00576 | PKG-06 | 140348.12 | 121315.83 | Approved | 13 | 2024-12-31 | 2025-02-19 | Additional smoke evacuation shafts in underground platforms
VO-PKG-10-02030 | PKG-10 | 59826.73 | 0 | Pending Approval | 36 | 2024-12-31 |  | HVAC chilled water pipe rerouting around station concourse
VO-PKG-10-00300 | PKG-10 | 54626.03 | 0 | Rejected | 0 | 2025-01-01 | 2025-01-12 | HVAC chilled water pipe rerouting around station concourse
VO-PKG-04-02584 | PKG-04 | 23503.29 | 0 | Pending Approval | 35 | 2025-01-02 |  | Station box diaphragm wall water ingress mitigation
VO-PKG-06-01876 | PKG-06 | 250344.31 | 0 | Pending Approval | 32 | 2025-01-02 |  | Additional smoke evacuation shafts in underground platforms
VO-PKG-02-00422 | PKG-02 | 269266.08 | 261776.22 | Approved | 41 | 2025-01-03 | 2025-02-03 | TBM Cutterhead refurbishment and rock fissure sealing
VO-PKG-05-00165 | PKG-05 | 269140.58 | 249829.37 | Approved | 49 | 2025-01-03 | 2025-02-13 | HV substation redundancy transformer capacity upgrade
VO-PKG-05-00455 | PKG-05 | 211858.23 | 198496.1 | Approved | 54 | 2025-01-03 | 2025-02-07 | HV substation redundancy transformer capacity upgrade
VO-PKG-05-02555 | PKG-05 | 340731.35 | 292302.34 | Approved | 30 | 2025-01-04 | 2025-02-22 | HV substation redundancy transformer capacity upgrade
VO-PKG-08-02858 | PKG-08 | 348648.29 | 0 | Pending Approval | 22 | 2025-01-04 |  | Track vibration damping rubber pads acoustic upgrade
VO-PKG-09-02409 | PKG-09 | 115247.41 | 102098.02 | Approved | 21 | 2025-01-04 | 2025-02-19 | Drainage box culvert capacity expansion for 100-year flood event
VO-PKG-01-02201 | PKG-01 | 87769.05 | 0 | Rejected | 0 | 2025-01-05 | 2025-02-12 | Unforeseen soft ground stabilization and grouting
VO-PKG-02-01372 | PKG-02 | 114200.44 | 0 | Pending Approval | 8 | 2025-01-05 |  | TBM Cutterhead refurbishment and rock fissure sealing
VO-PKG-05-02835 | PKG-05 | 233465.61 | 223911.69 | Approved | 9 | 2025-01-05 | 2025-02-23 | HV substation redundancy transformer capacity upgrade
VO-PKG-08-00878 | PKG-08 | 69316.6 | 58432.09 | Approved | 44 | 2025-01-05 | 2025-02-06 | Track vibration damping rubber pads acoustic upgrade
VO-PKG-01-02041 | PKG-01 | 173417.36 | 0 | Rejected | 0 | 2025-01-06 | 2025-02-14 | Unforeseen soft ground stabilization and grouting
VO-PKG-02-00312 | PKG-02 | 155261.38 | 150142.5 | Approved | 24 | 2025-01-06 | 2025-02-24 | TBM Cutterhead refurbishment and rock fissure sealing
VO-PKG-05-01945 | PKG-05 | 170753.65 | 137101 | Approved | 22 | 2025-01-06 | 2025-02-11 | HV substation redundancy transformer capacity upgrade
VO-PKG-06-01116 | PKG-06 | 135566.8 | 131291.73 | Approved | 34 | 2025-01-06 | 2025-02-19 | Additional smoke evacuation shafts in underground platforms
VO-PKG-08-00358 | PKG-08 | 26277.84 | 22208.11 | Approved | 32 | 2025-01-06 | 2025-02-01 | Track vibration damping rubber pads acoustic upgrade
VO-PKG-02-00472 | PKG-02 | 240722.37 | 234562.13 | Approved | 40 | 2025-01-07 | 2025-02-19 | TBM Cutterhead refurbishment and rock fissure sealing
VO-PKG-02-01012 | PKG-02 | 299905.69 | 0 | Pending Approval | 1 | 2025-01-07 |  | TBM Cutterhead refurbishment and rock fissure sealing
VO-PKG-10-02040 | PKG-10 | 151981.83 | 128998.41 | Approved | 7 | 2025-01-07 | 2025-01-22 | HVAC chilled water pipe rerouting around station concourse
VO-PKG-03-01623 | PKG-03 | 143804.02 | 127558.19 | Approved | 52 | 2025-01-08 | 2025-01-27 | Viaduct pier foundation redesign due to utility clash
VO-PKG-05-01145 | PKG-05 | 264306.32 | 236148.99 | Approved | 15 | 2025-01-08 | 2025-02-06 | HV substation redundancy transformer capacity upgrade
VO-PKG-07-02807 | PKG-07 | 196596.79 | 180666.18 | Approved | 30 | 2025-01-08 | 2025-02-28 | Fiber optic telemetry routing realignment along guideway
VO-PKG-09-01569 | PKG-09 | 284806.43 | 249521.23 | Approved | 28 | 2025-01-08 | 2025-01-30 | Drainage box culvert capacity expansion for 100-year flood event
VO-PKG-10-00430 | PKG-10 | 333511.54 | 277687.45 | Approved | 27 | 2025-01-08 | 2025-02-03 | HVAC chilled water pipe rerouting around station concourse
VO-PKG-09-01419 | PKG-09 | 145376.43 | 0 | Pending Approval | 29 | 2025-01-09 |  | Drainage box culvert capacity expansion for 100-year flood event
VO-PKG-07-00297 | PKG-07 | 114538.17 | 93924.15 | Approved | 14 | 2025-01-10 | 2025-02-24 | Fiber optic telemetry routing realignment along guideway
VO-PKG-08-01488 | PKG-08 | 87201.65 | 83802.94 | Approved | 52 | 2025-01-10 | 2025-02-11 | Track vibration damping rubber pads acoustic upgrade
VO-PKG-09-02649 | PKG-09 | 146695 | 140281.34 | Approved | 59 | 2025-01-10 | 2025-02-03 | Drainage box culvert capacity expansion for 100-year flood event
VO-PKG-10-02010 | PKG-10 | 20126.98 | 0 | Rejected | 0 | 2025-01-10 | 2025-02-22 | HVAC chilled water pipe rerouting around station concourse
VO-PKG-04-01154 | PKG-04 | 342063.64 | 0 | Pending Approval | 30 | 2025-01-11 |  | Station box diaphragm wall water ingress mitigation
VO-PKG-08-00118 | PKG-08 | 255837.04 | 0 | Rejected | 0 | 2025-01-12 | 2025-02-15 | Track vibration damping rubber pads acoustic upgrade
VO-PKG-08-01068 | PKG-08 | 130309.94 | 110395.79 | Approved | 50 | 2025-01-12 | 2025-02-23 | Track vibration damping rubber pads acoustic upgrade
VO-PKG-03-01223 | PKG-03 | 53657.3 | 47466.29 | Approved | 6 | 2025-01-13 | 2025-02-12 | Viaduct pier foundation redesign due to utility clash
VO-PKG-06-01696 | PKG-06 | 88690.95 | 85202.06 | Approved | 11 | 2025-01-13 | 2025-02-18 | Additional smoke evacuation shafts in underground platforms
VO-PKG-07-00787 | PKG-07 | 186922.2 | 163987.1 | Approved | 46 | 2025-01-13 | 2025-02-11 | Fiber optic telemetry routing realignment along guideway
VO-PKG-07-01197 | PKG-07 | 243835.71 | 0 | Pending Approval | 0 | 2025-01-13 |  | Fiber optic telemetry routing realignment along guideway
VO-PKG-07-01417 | PKG-07 | 315963.98 | 0 | Pending Approval | 6 | 2025-01-13 |  | Fiber optic telemetry routing realignment along guideway
VO-PKG-01-00171 | PKG-01 | 159493.51 | 0 | Pending Approval | 23 | 2025-01-14 |  | Unforeseen soft ground stabilization and grouting
VO-PKG-01-02211 | PKG-01 | 182498.31 | 162265.37 | Approved | 53 | 2025-01-14 | 2025-02-22 | Unforeseen soft ground stabilization and grouting
VO-PKG-05-00295 | PKG-05 | 74185.42 | 0 | Pending Approval | 41 | 2025-01-14 |  | HV substation redundancy transformer capacity upgrade
VO-PKG-09-00089 | PKG-09 | 194887.46 | 0 | Pending Approval | 8 | 2025-01-14 |  | Drainage box culvert capacity expansion for 100-year flood event
VO-PKG-02-00872 | PKG-02 | 247131.08 | 0 | Pending Approval | 2 | 2025-01-15 |  | TBM Cutterhead refurbishment and rock fissure sealing
VO-PKG-03-00743 | PKG-03 | 135208.46 | 115566.49 | Approved | 18 | 2025-01-15 | 2025-02-04 | Viaduct pier foundation redesign due to utility clash
VO-PKG-06-02266 | PKG-06 | 101444.57 | 0 | Pending Approval | 13 | 2025-01-15 |  | Additional smoke evacuation shafts in underground platforms
VO-PKG-08-01208 | PKG-08 | 227922.68 | 223151.07 | Approved | 31 | 2025-01-15 | 2025-02-04 | Track vibration damping rubber pads acoustic upgrade
VO-PKG-01-00671 | PKG-01 | 76914.09 | 66712.05 | Approved | 35 | 2025-01-16 | 2025-02-12 | Unforeseen soft ground stabilization and grouting
VO-PKG-07-01967 | PKG-07 | 71246.61 | 69427.07 | Approved | 28 | 2025-01-16 | 2025-02-16 | Fiber optic telemetry routing realignment along guideway
VO-PKG-08-00368 | PKG-08 | 268920.1 | 233853.96 | Approved | 38 | 2025-01-16 | 2025-02-25 | Track vibration damping rubber pads acoustic upgrade
VO-PKG-10-01440 | PKG-10 | 279133.52 | 261206.03 | Approved | 38 | 2025-01-16 | 2025-03-05 | HVAC chilled water pipe rerouting around station concourse
VO-PKG-03-01533 | PKG-03 | 127635.3 | 0 | Rejected | 0 | 2025-01-17 | 2025-01-28 | Viaduct pier foundation redesign due to utility clash
VO-PKG-09-01079 | PKG-09 | 267675.84 | 0 | Pending Approval | 34 | 2025-01-17 |  | Drainage box culvert capacity expansion for 100-year flood event
VO-PKG-10-00520 | PKG-10 | 106351.65 | 89751.57 | Approved | 36 | 2025-01-17 | 2025-02-17 | HVAC chilled water pipe rerouting around station concourse
VO-PKG-01-00761 | PKG-01 | 251869.11 | 0 | Pending Approval | 21 | 2025-01-18 |  | Unforeseen soft ground stabilization and grouting
VO-PKG-06-02846 | PKG-06 | 46225.58 | 37162.24 | Approved | 22 | 2025-01-18 | 2025-02-28 | Additional smoke evacuation shafts in underground platforms
VO-PKG-10-00600 | PKG-10 | 249191.34 | 216700.57 | Approved | 12 | 2025-01-18 | 2025-02-28 | HVAC chilled water pipe rerouting around station concourse
VO-PKG-10-01010 | PKG-10 | 210496.78 | 0 | Pending Approval | 14 | 2025-01-18 |  | HVAC chilled water pipe rerouting around station concourse
VO-PKG-03-00463 | PKG-03 | 216941.95 | 0 | Pending Approval | 11 | 2025-01-19 |  | Viaduct pier foundation redesign due to utility clash
VO-PKG-05-00265 | PKG-05 | 225841.44 | 191697.21 | Approved | 25 | 2025-01-20 | 2025-03-18 | HV substation redundancy transformer capacity upgrade
VO-PKG-06-01536 | PKG-06 | 74533.04 | 0 | Pending Approval | 4 | 2025-01-20 |  | Additional smoke evacuation shafts in underground platforms
VO-PKG-10-01100 | PKG-10 | 156377.94 | 125226.67 | Approved | 14 | 2025-01-21 | 2025-03-02 | HVAC chilled water pipe rerouting around station concourse
VO-PKG-10-02170 | PKG-10 | 81957.13 | 65892.85 | Approved | 32 | 2025-01-21 | 2025-02-08 | HVAC chilled water pipe rerouting around station concourse
VO-PKG-04-00304 | PKG-04 | 269510.27 | 0 | Rejected | 0 | 2025-01-22 | 2025-02-16 | Station box diaphragm wall water ingress mitigation
VO-PKG-04-02264 | PKG-04 | 179294.1 | 0 | Rejected | 0 | 2025-01-22 | 2025-02-19 | Station box diaphragm wall water ingress mitigation
VO-PKG-05-01165 | PKG-05 | 137900.93 | 0 | Pending Approval | 1 | 2025-01-22 |  | HV substation redundancy transformer capacity upgrade
VO-PKG-07-00437 | PKG-07 | 54835.12 | 50726.44 | Approved | 40 | 2025-01-22 | 2025-03-20 | Fiber optic telemetry routing realignment along guideway
VO-PKG-07-00727 | PKG-07 | 226295.83 | 215832.5 | Approved | 28 | 2025-01-22 | 2025-03-22 | Fiber optic telemetry routing realignment along guideway
VO-PKG-08-00708 | PKG-08 | 248917.89 | 0 | Rejected | 0 | 2025-01-22 | 2025-02-25 | Track vibration damping rubber pads acoustic upgrade
VO-PKG-09-00239 | PKG-09 | 185462.82 | 178875.92 | Approved | 41 | 2025-01-22 | 2025-02-25 | Drainage box culvert capacity expansion for 100-year flood event
VO-PKG-10-02110 | PKG-10 | 187620.36 | 174316.34 | Approved | 34 | 2025-01-22 | 2025-03-11 | HVAC chilled water pipe rerouting around station concourse
VO-PKG-01-02671 | PKG-01 | 71653.34 | 0 | Pending Approval | 38 | 2025-01-23 |  | Unforeseen soft ground stabilization and grouting
VO-PKG-05-01265 | PKG-05 | 330776.66 | 276161.59 | Approved | 11 | 2025-01-23 | 2025-02-15 | HV substation redundancy transformer capacity upgrade
VO-PKG-10-01680 | PKG-10 | 331226.59 | 0 | Pending Approval | 40 | 2025-01-23 |  | HVAC chilled water pipe rerouting around station concourse
VO-PKG-01-00091 | PKG-01 | 237024.73 | 205880.27 | Approved | 58 | 2025-01-24 | 2025-03-07 | Unforeseen soft ground stabilization and grouting
VO-PKG-03-01473 | PKG-03 | 97395.46 | 92733.93 | Approved | 39 | 2025-01-24 | 2025-03-13 | Viaduct pier foundation redesign due to utility clash
VO-PKG-01-02731 | PKG-01 | 48738.73 | 0 | Rejected | 0 | 2025-01-25 | 2025-02-22 | Unforeseen soft ground stabilization and grouting
VO-PKG-06-02066 | PKG-06 | 82853.37 | 77148.17 | Approved | 21 | 2025-01-25 | 2025-02-14 | Additional smoke evacuation shafts in underground platforms
VO-PKG-06-02776 | PKG-06 | 334192.29 | 301497.82 | Approved | 27 | 2025-01-25 | 2025-03-12 | Additional smoke evacuation shafts in underground platforms
VO-PKG-10-02890 | PKG-10 | 340644.87 | 284895.05 | Approved | 46 | 2025-01-25 | 2025-02-11 | HVAC chilled water pipe rerouting around station concourse
VO-PKG-01-00801 | PKG-01 | 172124.23 | 152571.69 | Approved | 8 | 2025-01-26 | 2025-03-15 | Unforeseen soft ground stabilization and grouting
VO-PKG-01-01421 | PKG-01 | 200275.86 | 160836.25 | Approved | 15 | 2025-01-26 | 2025-02-15 | Unforeseen soft ground stabilization and grouting
VO-PKG-04-00344 | PKG-04 | 204096.67 | 0 | Pending Approval | 9 | 2025-01-26 |  | Station box diaphragm wall water ingress mitigation
VO-PKG-04-00544 | PKG-04 | 63419.63 | 52196.19 | Approved | 13 | 2025-01-27 | 2025-03-18 | Station box diaphragm wall water ingress mitigation
VO-PKG-09-02079 | PKG-09 | 279712.18 | 238961.4 | Approved | 38 | 2025-01-27 | 2025-02-21 | Drainage box culvert capacity expansion for 100-year flood event
VO-PKG-03-00833 | PKG-03 | 225899.37 | 198017.55 | Approved | 37 | 2025-01-28 | 2025-02-27 | Viaduct pier foundation redesign due to utility clash
VO-PKG-03-02863 | PKG-03 | 71616.08 | 0 | Pending Approval | 35 | 2025-01-28 |  | Viaduct pier foundation redesign due to utility clash
VO-PKG-05-02415 | PKG-05 | 190978.84 | 0 | Pending Approval | 13 | 2025-01-28 |  | HV substation redundancy transformer capacity upgrade
VO-PKG-10-00390 | PKG-10 | 173219.22 | 0 | Rejected | 0 | 2025-01-28 | 2025-02-21 | HVAC chilled water pipe rerouting around station concourse
VO-PKG-02-00182 | PKG-02 | 60557.87 | 57901.3 | Approved | 16 | 2025-01-29 | 2025-02-23 | TBM Cutterhead refurbishment and rock fissure sealing
VO-PKG-09-01059 | PKG-09 | 153435.59 | 125847.87 | Approved | 52 | 2025-01-29 | 2025-02-26 | Drainage box culvert capacity expansion for 100-year flood event
VO-PKG-01-00021 | PKG-01 | 296289.43 | 287505.13 | Approved | 22 | 2025-01-30 | 2025-02-28 | Unforeseen soft ground stabilization and grouting
VO-PKG-01-01621 | PKG-01 | 153829.55 | 132213.76 | Approved | 50 | 2025-01-30 | 2025-03-16 | Unforeseen soft ground stabilization and grouting
VO-PKG-05-02885 | PKG-05 | 305947.08 | 255200.09 | Approved | 34 | 2025-01-30 | 2025-02-23 | HV substation redundancy transformer capacity upgrade
VO-PKG-06-00986 | PKG-06 | 266289.61 | 0 | Rejected | 0 | 2025-01-30 | 2025-02-11 | Additional smoke evacuation shafts in underground platforms
VO-PKG-06-00166 | PKG-06 | 208459.53 | 198887.73 | Approved | 39 | 2025-01-31 | 2025-03-19 | Additional smoke evacuation shafts in underground platforms
VO-PKG-03-01663 | PKG-03 | 47272.01 | 0 | Pending Approval | 41 | 2025-02-01 |  | Viaduct pier foundation redesign due to utility clash
VO-PKG-04-00884 | PKG-04 | 245761.14 | 0 | Pending Approval | 15 | 2025-02-01 |  | Station box diaphragm wall water ingress mitigation
VO-PKG-07-01547 | PKG-07 | 301506.34 | 0 | Rejected | 0 | 2025-02-01 | 2025-02-13 | Fiber optic telemetry routing realignment along guideway
VO-PKG-03-01813 | PKG-03 | 72442.77 | 0 | Pending Approval | 22 | 2025-02-02 |  | Viaduct pier foundation redesign due to utility clash
VO-PKG-07-02387 | PKG-07 | 50916.19 | 46343.19 | Approved | 24 | 2025-02-02 | 2025-03-04 | Fiber optic telemetry routing realignment along guideway
VO-PKG-09-00069 | PKG-09 | 142978.25 | 129833.9 | Approved | 24 | 2025-02-02 | 2025-03-11 | Drainage box culvert capacity expansion for 100-year flood event
VO-PKG-09-00409 | PKG-09 | 290148.53 | 256269.17 | Approved | 36 | 2025-02-02 | 2025-03-18 | Drainage box culvert capacity expansion for 100-year flood event
VO-PKG-09-01449 | PKG-09 | 216279.72 | 199154.16 | Approved | 28 | 2025-02-03 | 2025-02-27 | Drainage box culvert capacity expansion for 100-year flood event
VO-PKG-07-00777 | PKG-07 | 82912.11 | 76570.17 | Approved | 48 | 2025-02-04 | 2025-03-08 | Fiber optic telemetry routing realignment along guideway
VO-PKG-07-01487 | PKG-07 | 338043.53 | 324875.82 | Approved | 58 | 2025-02-04 | 2025-03-09 | Fiber optic telemetry routing realignment along guideway
VO-PKG-07-01927 | PKG-07 | 253305.8 | 236790.57 | Approved | 7 | 2025-02-04 | 2025-02-28 | Fiber optic telemetry routing realignment along guideway
VO-PKG-03-00513 | PKG-03 | 303319.15 | 0 | Pending Approval | 20 | 2025-02-05 |  | Viaduct pier foundation redesign due to utility clash
VO-PKG-06-01706 | PKG-06 | 311344.79 | 277363.09 | Approved | 11 | 2025-02-05 | 2025-04-02 | Additional smoke evacuation shafts in underground platforms
VO-PKG-08-01458 | PKG-08 | 215860.19 | 174085.9 | Approved | 10 | 2025-02-05 | 2025-03-02 | Track vibration damping rubber pads acoustic upgrade
VO-PKG-08-02708 | PKG-08 | 284781.24 | 267894.93 | Approved | 52 | 2025-02-05 | 2025-03-21 | Track vibration damping rubber pads acoustic upgrade
VO-PKG-10-00530 | PKG-10 | 41605.92 | 0 | Pending Approval | 20 | 2025-02-05 |  | HVAC chilled water pipe rerouting around station concourse
VO-PKG-06-02016 | PKG-06 | 142972.99 | 128662.29 | Approved | 39 | 2025-02-06 | 2025-04-06 | Additional smoke evacuation shafts in underground platforms
VO-PKG-08-02378 | PKG-08 | 233871.01 | 221931.45 | Approved | 34 | 2025-02-06 | 2025-03-07 | Track vibration damping rubber pads acoustic upgrade
VO-PKG-02-01392 | PKG-02 | 91191.19 | 79975.86 | Approved | 19 | 2025-02-07 | 2025-04-01 | TBM Cutterhead refurbishment and rock fissure sealing
VO-PKG-07-00617 | PKG-07 | 251243.12 | 0 | Pending Approval | 11 | 2025-02-07 |  | Fiber optic telemetry routing realignment along guideway
VO-PKG-08-02528 | PKG-08 | 257100.89 | 0 | Pending Approval | 1 | 2025-02-07 |  | Track vibration damping rubber pads acoustic upgrade
VO-PKG-09-02669 | PKG-09 | 332480.81 | 280925.58 | Approved | 57 | 2025-02-07 | 2025-03-23 | Drainage box culvert capacity expansion for 100-year flood event
VO-PKG-07-02437 | PKG-07 | 237582.42 | 0 | Pending Approval | 41 | 2025-02-08 |  | Fiber optic telemetry routing realignment along guideway
VO-PKG-10-02680 | PKG-10 | 174875.19 | 149066.16 | Approved | 44 | 2025-02-08 | 2025-03-19 | HVAC chilled water pipe rerouting around station concourse
VO-PKG-01-02661 | PKG-01 | 312378.44 | 305248.57 | Approved | 25 | 2025-02-10 | 2025-04-02 | Unforeseen soft ground stabilization and grouting
VO-PKG-04-01394 | PKG-04 | 49447.8 | 0 | Pending Approval | 11 | 2025-02-10 |  | Station box diaphragm wall water ingress mitigation
VO-PKG-05-00245 | PKG-05 | 206163.17 | 0 | Pending Approval | 5 | 2025-02-10 |  | HV substation redundancy transformer capacity upgrade
VO-PKG-06-02426 | PKG-06 | 210895.2 | 184158.31 | Approved | 24 | 2025-02-10 | 2025-03-29 | Additional smoke evacuation shafts in underground platforms
VO-PKG-06-02566 | PKG-06 | 302549.69 | 0 | Pending Approval | 20 | 2025-02-10 |  | Additional smoke evacuation shafts in underground platforms
VO-PKG-06-02986 | PKG-06 | 327492.61 | 278967.63 | Approved | 22 | 2025-02-11 | 2025-04-11 | Additional smoke evacuation shafts in underground platforms
VO-PKG-07-02187 | PKG-07 | 67022.97 | 63184.42 | Approved | 20 | 2025-02-11 | 2025-03-12 | Fiber optic telemetry routing realignment along guideway
VO-PKG-02-01822 | PKG-02 | 237885.77 | 214835.36 | Approved | 30 | 2025-02-12 | 2025-04-05 | TBM Cutterhead refurbishment and rock fissure sealing
VO-PKG-05-00115 | PKG-05 | 279699.41 | 241913.9 | Approved | 38 | 2025-02-12 | 2025-03-25 | HV substation redundancy transformer capacity upgrade
VO-PKG-06-00656 | PKG-06 | 129413.92 | 125331.81 | Approved | 59 | 2025-02-12 | 2025-03-22 | Additional smoke evacuation shafts in underground platforms
VO-PKG-02-01152 | PKG-02 | 18187.31 | 0 | Rejected | 0 | 2025-02-13 | 2025-02-24 | TBM Cutterhead refurbishment and rock fissure sealing
VO-PKG-03-02323 | PKG-03 | 185774.81 | 0 | Pending Approval | 29 | 2025-02-13 |  | Viaduct pier foundation redesign due to utility clash
VO-PKG-06-02806 | PKG-06 | 268906.7 | 0 | Pending Approval | 24 | 2025-02-13 |  | Additional smoke evacuation shafts in underground platforms
VO-PKG-01-00871 | PKG-01 | 207589 | 184142.23 | Approved | 38 | 2025-02-14 | 2025-03-18 | Unforeseen soft ground stabilization and grouting
VO-PKG-04-00364 | PKG-04 | 284278.39 | 0 | Pending Approval | 17 | 2025-02-14 |  | Station box diaphragm wall water ingress mitigation
VO-PKG-04-01034 | PKG-04 | 194572.61 | 0 | Pending Approval | 12 | 2025-02-14 |  | Station box diaphragm wall water ingress mitigation
VO-PKG-05-00095 | PKG-05 | 243736.79 | 234563.46 | Approved | 46 | 2025-02-14 | 2025-04-06 | HV substation redundancy transformer capacity upgrade
VO-PKG-06-02606 | PKG-06 | 318464.58 | 0 | Pending Approval | 36 | 2025-02-14 |  | Additional smoke evacuation shafts in underground platforms
VO-PKG-07-02367 | PKG-07 | 35186.22 | 28922.7 | Approved | 8 | 2025-02-14 | 2025-04-06 | Fiber optic telemetry routing realignment along guideway
VO-PKG-03-01713 | PKG-03 | 45545.36 | 41684.42 | Approved | 54 | 2025-02-15 | 2025-03-11 | Viaduct pier foundation redesign due to utility clash
VO-PKG-04-02084 | PKG-04 | 147078.14 | 117868.28 | Approved | 17 | 2025-02-15 | 2025-04-10 | Station box diaphragm wall water ingress mitigation
VO-PKG-07-01917 | PKG-07 | 129331.41 | 118593.86 | Approved | 8 | 2025-02-15 | 2025-03-26 | Fiber optic telemetry routing realignment along guideway
VO-PKG-09-00819 | PKG-09 | 18710.05 | 15220.28 | Approved | 27 | 2025-02-15 | 2025-03-07 | Drainage box culvert capacity expansion for 100-year flood event
VO-PKG-10-02290 | PKG-10 | 213295.59 | 0 | Pending Approval | 39 | 2025-02-16 |  | HVAC chilled water pipe rerouting around station concourse
VO-PKG-03-00593 | PKG-03 | 323068.74 | 265555.68 | Approved | 51 | 2025-02-17 | 2025-03-04 | Viaduct pier foundation redesign due to utility clash
VO-PKG-05-02465 | PKG-05 | 56686.03 | 0 | Rejected | 0 | 2025-02-18 | 2025-03-18 | HV substation redundancy transformer capacity upgrade
VO-PKG-07-00467 | PKG-07 | 292917.54 | 272807.52 | Approved | 40 | 2025-02-18 | 2025-04-15 | Fiber optic telemetry routing realignment along guideway
VO-PKG-09-02099 | PKG-09 | 114011.23 | 100007.04 | Approved | 20 | 2025-02-18 | 2025-04-13 | Drainage box culvert capacity expansion for 100-year flood event
VO-PKG-02-01322 | PKG-02 | 109544.08 | 0 | Pending Approval | 35 | 2025-02-19 |  | TBM Cutterhead refurbishment and rock fissure sealing
VO-PKG-05-01885 | PKG-05 | 304431.84 | 254078.13 | Approved | 12 | 2025-02-19 | 2025-03-22 | HV substation redundancy transformer capacity upgrade
VO-PKG-06-02186 | PKG-06 | 68447.57 | 0 | Pending Approval | 24 | 2025-02-19 |  | Additional smoke evacuation shafts in underground platforms
VO-PKG-07-00407 | PKG-07 | 113810.16 | 0 | Rejected | 0 | 2025-02-19 | 2025-03-01 | Fiber optic telemetry routing realignment along guideway
VO-PKG-07-00677 | PKG-07 | 232342.94 | 223194.36 | Approved | 54 | 2025-02-19 | 2025-04-19 | Fiber optic telemetry routing realignment along guideway
VO-PKG-10-00310 | PKG-10 | 165145.63 | 159396.06 | Approved | 5 | 2025-02-19 | 2025-04-11 | HVAC chilled water pipe rerouting around station concourse
VO-PKG-06-00486 | PKG-06 | 186519.5 | 169779 | Approved | 7 | 2025-02-20 | 2025-04-07 | Additional smoke evacuation shafts in underground platforms
VO-PKG-07-00987 | PKG-07 | 166836.27 | 0 | Rejected | 0 | 2025-02-20 | 2025-03-24 | Fiber optic telemetry routing realignment along guideway
VO-PKG-07-01817 | PKG-07 | 278634.13 | 255312.34 | Approved | 32 | 2025-02-20 | 2025-04-08 | Fiber optic telemetry routing realignment along guideway
VO-PKG-08-01518 | PKG-08 | 148464.23 | 143812.83 | Approved | 23 | 2025-02-20 | 2025-04-15 | Track vibration damping rubber pads acoustic upgrade
VO-PKG-01-01981 | PKG-01 | 142171.37 | 119220.98 | Approved | 19 | 2025-02-21 | 2025-03-17 | Unforeseen soft ground stabilization and grouting
VO-PKG-01-01691 | PKG-01 | 192059.63 | 0 | Pending Approval | 36 | 2025-02-22 |  | Unforeseen soft ground stabilization and grouting
VO-PKG-03-01373 | PKG-03 | 343302.47 | 322206.41 | Approved | 12 | 2025-02-22 | 2025-03-17 | Viaduct pier foundation redesign due to utility clash
VO-PKG-07-02837 | PKG-07 | 214873.01 | 187513.99 | Approved | 42 | 2025-02-22 | 2025-03-20 | Fiber optic telemetry routing realignment along guideway
VO-PKG-04-02804 | PKG-04 | 159398.1 | 150092.81 | Approved | 48 | 2025-02-23 | 2025-04-12 | Station box diaphragm wall water ingress mitigation
VO-PKG-05-02985 | PKG-05 | 282029.61 | 0 | Pending Approval | 17 | 2025-02-23 |  | HV substation redundancy transformer capacity upgrade
VO-PKG-08-02458 | PKG-08 | 150365.11 | 143213.95 | Approved | 33 | 2025-02-23 | 2025-04-13 | Track vibration damping rubber pads acoustic upgrade
VO-PKG-02-00762 | PKG-02 | 117087.82 | 0 | Pending Approval | 11 | 2025-02-24 |  | TBM Cutterhead refurbishment and rock fissure sealing
VO-PKG-03-02563 | PKG-03 | 327165.1 | 306720.14 | Approved | 51 | 2025-02-24 | 2025-03-22 | Viaduct pier foundation redesign due to utility clash
VO-PKG-04-01814 | PKG-04 | 118275.76 | 103711.03 | Approved | 37 | 2025-02-24 | 2025-03-16 | Station box diaphragm wall water ingress mitigation
VO-PKG-05-01815 | PKG-05 | 300094.06 | 0 | Pending Approval | 30 | 2025-02-24 |  | HV substation redundancy transformer capacity upgrade
VO-PKG-01-01011 | PKG-01 | 118227.77 | 95790.33 | Approved | 13 | 2025-02-25 | 2025-04-17 | Unforeseen soft ground stabilization and grouting
VO-PKG-01-02061 | PKG-01 | 270440.86 | 241058.84 | Approved | 16 | 2025-02-25 | 2025-03-27 | Unforeseen soft ground stabilization and grouting
VO-PKG-07-00257 | PKG-07 | 230781.51 | 215019.89 | Approved | 37 | 2025-02-25 | 2025-04-17 | Fiber optic telemetry routing realignment along guideway
VO-PKG-09-02389 | PKG-09 | 301321.1 | 287791.27 | Approved | 13 | 2025-02-26 | 2025-03-16 | Drainage box culvert capacity expansion for 100-year flood event
VO-PKG-10-01740 | PKG-10 | 296046.52 | 241670.34 | Approved | 33 | 2025-02-26 | 2025-04-16 | HVAC chilled water pipe rerouting around station concourse
VO-PKG-03-01743 | PKG-03 | 231969.91 | 211565.92 | Approved | 31 | 2025-02-27 | 2025-04-25 | Viaduct pier foundation redesign due to utility clash
VO-PKG-04-02714 | PKG-04 | 54877.71 | 47784.58 | Approved | 36 | 2025-02-27 | 2025-04-17 | Station box diaphragm wall water ingress mitigation
VO-PKG-04-02884 | PKG-04 | 32148.06 | 30200.03 | Approved | 45 | 2025-02-27 | 2025-04-06 | Station box diaphragm wall water ingress mitigation
VO-PKG-05-01065 | PKG-05 | 118722.46 | 0 | Pending Approval | 29 | 2025-02-27 |  | HV substation redundancy transformer capacity upgrade
VO-PKG-09-00679 | PKG-09 | 264186.77 | 0 | Rejected | 0 | 2025-02-27 | 2025-04-12 | Drainage box culvert capacity expansion for 100-year flood event
VO-PKG-04-00784 | PKG-04 | 274631.89 | 0 | Rejected | 0 | 2025-02-28 | 2025-03-28 | Station box diaphragm wall water ingress mitigation
VO-PKG-03-02233 | PKG-03 | 228168.54 | 220072.52 | Approved | 29 | 2025-03-01 | 2025-03-24 | Viaduct pier foundation redesign due to utility clash
VO-PKG-04-02564 | PKG-04 | 20307.75 | 0 | Rejected | 0 | 2025-03-01 | 2025-03-18 | Station box diaphragm wall water ingress mitigation
VO-PKG-07-01267 | PKG-07 | 96593.02 | 0 | Pending Approval | 38 | 2025-03-01 |  | Fiber optic telemetry routing realignment along guideway
VO-PKG-08-00218 | PKG-08 | 279811.4 | 246050.88 | Approved | 43 | 2025-03-01 | 2025-03-21 | Track vibration damping rubber pads acoustic upgrade
VO-PKG-01-01871 | PKG-01 | 62680.32 | 50246.38 | Approved | 15 | 2025-03-02 | 2025-04-06 | Unforeseen soft ground stabilization and grouting
VO-PKG-04-00294 | PKG-04 | 340115.12 | 0 | Pending Approval | 38 | 2025-03-02 |  | Station box diaphragm wall water ingress mitigation
VO-PKG-04-01024 | PKG-04 | 209434.54 | 204083.51 | Approved | 6 | 2025-03-02 | 2025-04-28 | Station box diaphragm wall water ingress mitigation
VO-PKG-04-02604 | PKG-04 | 295104.96 | 0 | Pending Approval | 0 | 2025-03-02 |  | Station box diaphragm wall water ingress mitigation
VO-PKG-10-01650 | PKG-10 | 330096.39 | 275222.4 | Approved | 31 | 2025-03-02 | 2025-03-17 | HVAC chilled water pipe rerouting around station concourse
VO-PKG-02-02502 | PKG-02 | 96643.28 | 0 | Pending Approval | 33 | 2025-03-03 |  | TBM Cutterhead refurbishment and rock fissure sealing
VO-PKG-04-00734 | PKG-04 | 129268.65 | 125654.93 | Approved | 7 | 2025-03-04 | 2025-04-24 | Station box diaphragm wall water ingress mitigation
VO-PKG-06-01586 | PKG-06 | 179931.46 | 165863.36 | Approved | 11 | 2025-03-04 | 2025-04-28 | Additional smoke evacuation shafts in underground platforms
VO-PKG-07-01357 | PKG-07 | 163993.74 | 0 | Pending Approval | 17 | 2025-03-04 |  | Fiber optic telemetry routing realignment along guideway
VO-PKG-09-02969 | PKG-09 | 184638.32 | 0 | Rejected | 0 | 2025-03-04 | 2025-04-15 | Drainage box culvert capacity expansion for 100-year flood event
VO-PKG-10-01830 | PKG-10 | 167019.11 | 151727.11 | Approved | 25 | 2025-03-04 | 2025-04-23 | HVAC chilled water pipe rerouting around station concourse
VO-PKG-02-01162 | PKG-02 | 256985.56 | 234052.27 | Approved | 31 | 2025-03-05 | 2025-03-23 | TBM Cutterhead refurbishment and rock fissure sealing
VO-PKG-04-00604 | PKG-04 | 143576.88 | 136368.72 | Approved | 16 | 2025-03-05 | 2025-03-28 | Station box diaphragm wall water ingress mitigation
VO-PKG-04-02244 | PKG-04 | 147836.01 | 127542.25 | Approved | 7 | 2025-03-05 | 2025-05-03 | Station box diaphragm wall water ingress mitigation
VO-PKG-08-02648 | PKG-08 | 191248.4 | 186683.18 | Approved | 51 | 2025-03-05 | 2025-04-25 | Track vibration damping rubber pads acoustic upgrade
VO-PKG-10-01210 | PKG-10 | 179408.29 | 175173.69 | Approved | 53 | 2025-03-05 | 2025-04-29 | HVAC chilled water pipe rerouting around station concourse
VO-PKG-03-01553 | PKG-03 | 322569.01 | 0 | Rejected | 0 | 2025-03-06 | 2025-03-30 | Viaduct pier foundation redesign due to utility clash
VO-PKG-08-02888 | PKG-08 | 109389.71 | 0 | Rejected | 0 | 2025-03-06 | 2025-04-03 | Track vibration damping rubber pads acoustic upgrade
VO-PKG-07-01117 | PKG-07 | 75642.66 | 64090.82 | Approved | 41 | 2025-03-07 | 2025-04-05 | Fiber optic telemetry routing realignment along guideway
VO-PKG-08-01338 | PKG-08 | 81905.46 | 74445.45 | Approved | 16 | 2025-03-07 | 2025-04-02 | Track vibration damping rubber pads acoustic upgrade
VO-PKG-03-00503 | PKG-03 | 147060.27 | 0 | Pending Approval | 12 | 2025-03-08 |  | Viaduct pier foundation redesign due to utility clash
VO-PKG-08-00918 | PKG-08 | 73188.64 | 65720.84 | Approved | 58 | 2025-03-08 | 2025-04-18 | Track vibration damping rubber pads acoustic upgrade
VO-PKG-09-02519 | PKG-09 | 130253.92 | 118724.74 | Approved | 37 | 2025-03-08 | 2025-04-11 | Drainage box culvert capacity expansion for 100-year flood event
VO-PKG-10-01040 | PKG-10 | 239141.08 | 202761.82 | Approved | 40 | 2025-03-08 | 2025-04-21 | HVAC chilled water pipe rerouting around station concourse
VO-PKG-03-02263 | PKG-03 | 249722.66 | 0 | Pending Approval | 42 | 2025-03-09 |  | Viaduct pier foundation redesign due to utility clash
VO-PKG-04-02484 | PKG-04 | 199892.49 | 169106.19 | Approved | 46 | 2025-03-09 | 2025-04-13 | Station box diaphragm wall water ingress mitigation
VO-PKG-06-01986 | PKG-06 | 312608.21 | 283782.98 | Approved | 31 | 2025-03-09 | 2025-04-12 | Additional smoke evacuation shafts in underground platforms
VO-PKG-10-01700 | PKG-10 | 155731.89 | 137464.38 | Approved | 43 | 2025-03-09 | 2025-04-17 | HVAC chilled water pipe rerouting around station concourse
VO-PKG-01-02001 | PKG-01 | 43685.66 | 38267.31 | Approved | 13 | 2025-03-10 | 2025-04-30 | Unforeseen soft ground stabilization and grouting
VO-PKG-05-01025 | PKG-05 | 143784.24 | 0 | Pending Approval | 39 | 2025-03-10 |  | HV substation redundancy transformer capacity upgrade
VO-PKG-07-00267 | PKG-07 | 17080.9 | 13790.34 | Approved | 58 | 2025-03-10 | 2025-04-11 | Fiber optic telemetry routing realignment along guideway
VO-PKG-08-02228 | PKG-08 | 198095.21 | 183608.76 | Approved | 45 | 2025-03-10 | 2025-04-19 | Track vibration damping rubber pads acoustic upgrade
VO-PKG-10-02020 | PKG-10 | 290047.47 | 258137.97 | Approved | 28 | 2025-03-10 | 2025-04-04 | HVAC chilled water pipe rerouting around station concourse
VO-PKG-01-00901 | PKG-01 | 34716.92 | 33065.83 | Approved | 47 | 2025-03-11 | 2025-05-06 | Unforeseen soft ground stabilization and grouting
VO-PKG-04-00064 | PKG-04 | 80415.06 | 0 | Pending Approval | 21 | 2025-03-11 |  | Station box diaphragm wall water ingress mitigation
VO-PKG-04-00194 | PKG-04 | 62971.58 | 60957.46 | Approved | 6 | 2025-03-11 | 2025-05-08 | Station box diaphragm wall water ingress mitigation
VO-PKG-06-00846 | PKG-06 | 274488 | 224576.8 | Approved | 35 | 2025-03-11 | 2025-05-06 | Additional smoke evacuation shafts in underground platforms
VO-PKG-06-02496 | PKG-06 | 45847.32 | 41115.28 | Approved | 47 | 2025-03-11 | 2025-04-03 | Additional smoke evacuation shafts in underground platforms
VO-PKG-01-00921 | PKG-01 | 62715.54 | 0 | Pending Approval | 9 | 2025-03-12 |  | Unforeseen soft ground stabilization and grouting
VO-PKG-03-02673 | PKG-03 | 259686.71 | 0 | Rejected | 0 | 2025-03-12 | 2025-04-02 | Viaduct pier foundation redesign due to utility clash
VO-PKG-04-02294 | PKG-04 | 302987.54 | 266902.43 | Approved | 11 | 2025-03-12 | 2025-04-10 | Station box diaphragm wall water ingress mitigation
VO-PKG-05-01925 | PKG-05 | 171428.54 | 167616.7 | Approved | 13 | 2025-03-12 | 2025-04-19 | HV substation redundancy transformer capacity upgrade
VO-PKG-03-00023 | PKG-03 | 240249.96 | 196270.86 | Approved | 38 | 2025-03-13 | 2025-05-09 | Viaduct pier foundation redesign due to utility clash
VO-PKG-04-02734 | PKG-04 | 170182.33 | 158915.13 | Approved | 48 | 2025-03-13 | 2025-04-18 | Station box diaphragm wall water ingress mitigation
VO-PKG-07-00807 | PKG-07 | 314050.9 | 305828.63 | Approved | 9 | 2025-03-13 | 2025-04-05 | Fiber optic telemetry routing realignment along guideway
VO-PKG-10-00930 | PKG-10 | 334785.94 | 275349.2 | Approved | 40 | 2025-03-13 | 2025-04-10 | HVAC chilled water pipe rerouting around station concourse
VO-PKG-03-01723 | PKG-03 | 284150.43 | 257943 | Approved | 33 | 2025-03-14 | 2025-04-05 | Viaduct pier foundation redesign due to utility clash
VO-PKG-06-01396 | PKG-06 | 277297.75 | 248751.16 | Approved | 9 | 2025-03-14 | 2025-04-04 | Additional smoke evacuation shafts in underground platforms
VO-PKG-09-00709 | PKG-09 | 319275.2 | 0 | Pending Approval | 30 | 2025-03-14 |  | Drainage box culvert capacity expansion for 100-year flood event
VO-PKG-02-02192 | PKG-02 | 178129.4 | 152361.13 | Approved | 49 | 2025-03-15 | 2025-04-09 | TBM Cutterhead refurbishment and rock fissure sealing
VO-PKG-09-01049 | PKG-09 | 140192.55 | 0 | Rejected | 0 | 2025-03-15 | 2025-03-28 | Drainage box culvert capacity expansion for 100-year flood event
VO-PKG-03-02693 | PKG-03 | 128011.33 | 104046.14 | Approved | 51 | 2025-03-16 | 2025-04-11 | Viaduct pier foundation redesign due to utility clash
VO-PKG-04-01064 | PKG-04 | 301829.86 | 259192.88 | Approved | 20 | 2025-03-16 | 2025-04-09 | Station box diaphragm wall water ingress mitigation
VO-PKG-04-02344 | PKG-04 | 20273.32 | 16237.03 | Approved | 56 | 2025-03-16 | 2025-04-14 | Station box diaphragm wall water ingress mitigation
VO-PKG-06-01306 | PKG-06 | 26770.34 | 0 | Rejected | 0 | 2025-03-16 | 2025-04-20 | Additional smoke evacuation shafts in underground platforms
VO-PKG-09-00319 | PKG-09 | 294236.85 | 240237.15 | Approved | 42 | 2025-03-16 | 2025-04-22 | Drainage box culvert capacity expansion for 100-year flood event
VO-PKG-03-00333 | PKG-03 | 189434.88 | 177976.07 | Approved | 23 | 2025-03-17 | 2025-04-07 | Viaduct pier foundation redesign due to utility clash
VO-PKG-03-01283 | PKG-03 | 45861.34 | 41259.23 | Approved | 48 | 2025-03-17 | 2025-04-11 | Viaduct pier foundation redesign due to utility clash
VO-PKG-06-00446 | PKG-06 | 264482.27 | 0 | Pending Approval | 20 | 2025-03-17 |  | Additional smoke evacuation shafts in underground platforms
VO-PKG-06-00926 | PKG-06 | 100654.51 | 94904.59 | Approved | 52 | 2025-03-17 | 2025-05-06 | Additional smoke evacuation shafts in underground platforms
VO-PKG-09-00529 | PKG-09 | 301007.53 | 0 | Pending Approval | 9 | 2025-03-17 |  | Drainage box culvert capacity expansion for 100-year flood event
VO-PKG-09-02639 | PKG-09 | 129504.78 | 0 | Pending Approval | 40 | 2025-03-17 |  | Drainage box culvert capacity expansion for 100-year flood event
VO-PKG-02-01562 | PKG-02 | 16552.45 | 0 | Pending Approval | 20 | 2025-03-18 |  | TBM Cutterhead refurbishment and rock fissure sealing
VO-PKG-07-01187 | PKG-07 | 294507.36 | 247238.93 | Approved | 43 | 2025-03-18 | 2025-04-07 | Fiber optic telemetry routing realignment along guideway
VO-PKG-09-01209 | PKG-09 | 215024.49 | 201641.24 | Approved | 6 | 2025-03-18 | 2025-04-30 | Drainage box culvert capacity expansion for 100-year flood event
VO-PKG-10-02060 | PKG-10 | 347678.9 | 0 | Pending Approval | 16 | 2025-03-18 |  | HVAC chilled water pipe rerouting around station concourse
VO-PKG-05-00815 | PKG-05 | 51929.65 | 0 | Pending Approval | 15 | 2025-03-19 |  | HV substation redundancy transformer capacity upgrade
VO-PKG-07-02917 | PKG-07 | 24739.2 | 0 | Rejected | 0 | 2025-03-19 | 2025-04-07 | Fiber optic telemetry routing realignment along guideway
VO-PKG-08-01218 | PKG-08 | 247337.51 | 236001.81 | Approved | 43 | 2025-03-19 | 2025-05-03 | Track vibration damping rubber pads acoustic upgrade
VO-PKG-09-01179 | PKG-09 | 137612.41 | 117972.53 | Approved | 43 | 2025-03-19 | 2025-04-23 | Drainage box culvert capacity expansion for 100-year flood event
VO-PKG-07-02957 | PKG-07 | 190470.85 | 0 | Pending Approval | 44 | 2025-03-20 |  | Fiber optic telemetry routing realignment along guideway
VO-PKG-08-01078 | PKG-08 | 24620.5 | 22965.63 | Approved | 48 | 2025-03-20 | 2025-04-27 | Track vibration damping rubber pads acoustic upgrade
VO-PKG-03-00713 | PKG-03 | 117111.46 | 108692.7 | Approved | 24 | 2025-03-21 | 2025-04-12 | Viaduct pier foundation redesign due to utility clash
VO-PKG-05-01205 | PKG-05 | 288813.82 | 267690.61 | Approved | 38 | 2025-03-21 | 2025-04-09 | HV substation redundancy transformer capacity upgrade
VO-PKG-05-02015 | PKG-05 | 348703.88 | 323118.64 | Approved | 58 | 2025-03-21 | 2025-05-04 | HV substation redundancy transformer capacity upgrade
VO-PKG-06-01676 | PKG-06 | 77009.23 | 65731.04 | Approved | 34 | 2025-03-21 | 2025-05-17 | Additional smoke evacuation shafts in underground platforms
VO-PKG-08-00508 | PKG-08 | 160406.32 | 144629.93 | Approved | 54 | 2025-03-21 | 2025-04-23 | Track vibration damping rubber pads acoustic upgrade
VO-PKG-07-02457 | PKG-07 | 246768.44 | 224361.59 | Approved | 57 | 2025-03-22 | 2025-04-15 | Fiber optic telemetry routing realignment along guideway
VO-PKG-04-02964 | PKG-04 | 127213.28 | 109019.13 | Approved | 51 | 2025-03-23 | 2025-04-16 | Station box diaphragm wall water ingress mitigation
VO-PKG-08-00298 | PKG-08 | 298484.03 | 0 | Pending Approval | 18 | 2025-03-23 |  | Track vibration damping rubber pads acoustic upgrade
VO-PKG-09-00129 | PKG-09 | 289505.31 | 0 | Pending Approval | 44 | 2025-03-23 |  | Drainage box culvert capacity expansion for 100-year flood event
VO-PKG-10-02950 | PKG-10 | 349830.15 | 302836.37 | Approved | 55 | 2025-03-23 | 2025-05-20 | HVAC chilled water pipe rerouting around station concourse
VO-PKG-06-01886 | PKG-06 | 136693.94 | 0 | Pending Approval | 0 | 2025-03-24 |  | Additional smoke evacuation shafts in underground platforms
VO-PKG-06-02706 | PKG-06 | 21181.45 | 19303.85 | Approved | 32 | 2025-03-24 | 2025-05-06 | Additional smoke evacuation shafts in underground platforms
VO-PKG-07-00077 | PKG-07 | 40665.39 | 39686.19 | Approved | 48 | 2025-03-24 | 2025-05-08 | Fiber optic telemetry routing realignment along guideway
VO-PKG-01-00161 | PKG-01 | 98749.25 | 81132.88 | Approved | 46 | 2025-03-25 | 2025-05-06 | Unforeseen soft ground stabilization and grouting
VO-PKG-01-01201 | PKG-01 | 195416.2 | 0 | Rejected | 0 | 2025-03-25 | 2025-04-12 | Unforeseen soft ground stabilization and grouting
VO-PKG-04-00894 | PKG-04 | 31320.11 | 0 | Pending Approval | 25 | 2025-03-25 |  | Station box diaphragm wall water ingress mitigation
VO-PKG-08-01748 | PKG-08 | 172043.25 | 141010.11 | Approved | 29 | 2025-03-25 | 2025-05-09 | Track vibration damping rubber pads acoustic upgrade
VO-PKG-01-01661 | PKG-01 | 283756.07 | 258387.19 | Approved | 50 | 2025-03-26 | 2025-05-16 | Unforeseen soft ground stabilization and grouting
VO-PKG-03-02553 | PKG-03 | 336946.21 | 0 | Pending Approval | 38 | 2025-03-26 |  | Viaduct pier foundation redesign due to utility clash
VO-PKG-05-02065 | PKG-05 | 281949.27 | 228536.86 | Approved | 21 | 2025-03-26 | 2025-04-17 | HV substation redundancy transformer capacity upgrade
VO-PKG-06-02406 | PKG-06 | 95576.81 | 0 | Pending Approval | 22 | 2025-03-26 |  | Additional smoke evacuation shafts in underground platforms
VO-PKG-08-02108 | PKG-08 | 332940.46 | 283558.21 | Approved | 6 | 2025-03-26 | 2025-05-02 | Track vibration damping rubber pads acoustic upgrade
VO-PKG-02-02972 | PKG-02 | 235765.11 | 216261.59 | Approved | 24 | 2025-03-27 | 2025-04-16 | TBM Cutterhead refurbishment and rock fissure sealing
VO-PKG-06-01426 | PKG-06 | 90762.65 | 0 | Pending Approval | 16 | 2025-03-27 |  | Additional smoke evacuation shafts in underground platforms
VO-PKG-08-00758 | PKG-08 | 236067.88 | 0 | Pending Approval | 20 | 2025-03-27 |  | Track vibration damping rubber pads acoustic upgrade
VO-PKG-10-02590 | PKG-10 | 342022.99 | 0 | Pending Approval | 42 | 2025-03-27 |  | HVAC chilled water pipe rerouting around station concourse
VO-PKG-02-00742 | PKG-02 | 48785.01 | 0 | Pending Approval | 14 | 2025-03-28 |  | TBM Cutterhead refurbishment and rock fissure sealing
VO-PKG-02-01452 | PKG-02 | 259251.44 | 0 | Pending Approval | 13 | 2025-03-28 |  | TBM Cutterhead refurbishment and rock fissure sealing
VO-PKG-02-02122 | PKG-02 | 319455.03 | 0 | Pending Approval | 24 | 2025-03-28 |  | TBM Cutterhead refurbishment and rock fissure sealing
VO-PKG-03-00403 | PKG-03 | 194821.87 | 187815.49 | Approved | 21 | 2025-03-28 | 2025-05-20 | Viaduct pier foundation redesign due to utility clash
VO-PKG-05-01285 | PKG-05 | 17705.24 | 15840.04 | Approved | 56 | 2025-03-28 | 2025-04-15 | HV substation redundancy transformer capacity upgrade
VO-PKG-08-02278 | PKG-08 | 121111.41 | 0 | Pending Approval | 38 | 2025-03-28 |  | Track vibration damping rubber pads acoustic upgrade
VO-PKG-02-00372 | PKG-02 | 15621.08 | 13882.62 | Approved | 49 | 2025-03-29 | 2025-05-19 | TBM Cutterhead refurbishment and rock fissure sealing
VO-PKG-02-01282 | PKG-02 | 78365.26 | 67712.78 | Approved | 19 | 2025-03-29 | 2025-04-15 | TBM Cutterhead refurbishment and rock fissure sealing
VO-PKG-04-00714 | PKG-04 | 120665.8 | 107152.95 | Approved | 8 | 2025-03-29 | 2025-04-18 | Station box diaphragm wall water ingress mitigation
VO-PKG-09-02459 | PKG-09 | 133417.35 | 0 | Rejected | 0 | 2025-03-29 | 2025-05-07 | Drainage box culvert capacity expansion for 100-year flood event
VO-PKG-10-00910 | PKG-10 | 340078.35 | 329963.72 | Approved | 38 | 2025-03-29 | 2025-04-15 | HVAC chilled water pipe rerouting around station concourse
VO-PKG-02-00272 | PKG-02 | 212029.96 | 195633.72 | Approved | 7 | 2025-03-30 | 2025-05-11 | TBM Cutterhead refurbishment and rock fissure sealing
VO-PKG-04-00004 | PKG-04 | 82906.87 | 0 | Rejected | 0 | 2025-03-30 | 2025-05-10 | Station box diaphragm wall water ingress mitigation
VO-PKG-07-00717 | PKG-07 | 111749.35 | 107278.65 | Approved | 37 | 2025-03-31 | 2025-05-29 | Fiber optic telemetry routing realignment along guideway
VO-PKG-01-00551 | PKG-01 | 272877.55 | 230252.05 | Approved | 38 | 2025-04-01 | 2025-04-24 | Unforeseen soft ground stabilization and grouting
VO-PKG-01-01321 | PKG-01 | 92372.08 | 0 | Pending Approval | 27 | 2025-04-01 |  | Unforeseen soft ground stabilization and grouting
VO-PKG-02-01852 | PKG-02 | 225034.33 | 186957.03 | Approved | 16 | 2025-04-01 | 2025-05-24 | TBM Cutterhead refurbishment and rock fissure sealing
VO-PKG-03-01683 | PKG-03 | 150665.57 | 0 | Pending Approval | 7 | 2025-04-01 |  | Viaduct pier foundation redesign due to utility clash
VO-PKG-03-02603 | PKG-03 | 27316.41 | 26296.96 | Approved | 35 | 2025-04-01 | 2025-04-24 | Viaduct pier foundation redesign due to utility clash
VO-PKG-04-01044 | PKG-04 | 260745.72 | 210679.71 | Approved | 9 | 2025-04-01 | 2025-05-27 | Station box diaphragm wall water ingress mitigation
VO-PKG-05-00315 | PKG-05 | 281239.8 | 0 | Pending Approval | 21 | 2025-04-01 |  | HV substation redundancy transformer capacity upgrade
VO-PKG-07-00107 | PKG-07 | 235876.51 | 0 | Pending Approval | 18 | 2025-04-01 |  | Fiber optic telemetry routing realignment along guideway
VO-PKG-03-01763 | PKG-03 | 256756.44 | 244343.02 | Approved | 38 | 2025-04-02 | 2025-05-17 | Viaduct pier foundation redesign due to utility clash
VO-PKG-04-02924 | PKG-04 | 348117.32 | 302216.52 | Approved | 48 | 2025-04-02 | 2025-04-25 | Station box diaphragm wall water ingress mitigation
VO-PKG-10-00370 | PKG-10 | 272367.4 | 256264.63 | Approved | 22 | 2025-04-03 | 2025-05-26 | HVAC chilled water pipe rerouting around station concourse
VO-PKG-05-00365 | PKG-05 | 149017.71 | 0 | Pending Approval | 40 | 2025-04-04 |  | HV substation redundancy transformer capacity upgrade
VO-PKG-05-00965 | PKG-05 | 225863.63 | 191127.24 | Approved | 30 | 2025-04-04 | 2025-05-17 | HV substation redundancy transformer capacity upgrade
VO-PKG-05-02165 | PKG-05 | 185895.08 | 0 | Pending Approval | 5 | 2025-04-04 |  | HV substation redundancy transformer capacity upgrade
VO-PKG-06-02286 | PKG-06 | 144463.47 | 124911.74 | Approved | 53 | 2025-04-04 | 2025-05-16 | Additional smoke evacuation shafts in underground platforms
VO-PKG-06-02876 | PKG-06 | 200242.18 | 163346.13 | Approved | 25 | 2025-04-04 | 2025-05-30 | Additional smoke evacuation shafts in underground platforms
VO-PKG-08-00928 | PKG-08 | 52969.96 | 51699 | Approved | 59 | 2025-04-05 | 2025-04-22 | Track vibration damping rubber pads acoustic upgrade
VO-PKG-10-02080 | PKG-10 | 308269.86 | 0 | Pending Approval | 31 | 2025-04-05 |  | HVAC chilled water pipe rerouting around station concourse
VO-PKG-02-02162 | PKG-02 | 314042.64 | 289286.37 | Approved | 44 | 2025-04-06 | 2025-06-02 | TBM Cutterhead refurbishment and rock fissure sealing
VO-PKG-04-01224 | PKG-04 | 202540.29 | 191733.11 | Approved | 11 | 2025-04-06 | 2025-05-06 | Station box diaphragm wall water ingress mitigation
VO-PKG-07-01407 | PKG-07 | 28454.75 | 27656.26 | Approved | 52 | 2025-04-06 | 2025-04-22 | Fiber optic telemetry routing realignment along guideway
VO-PKG-07-02887 | PKG-07 | 56132.95 | 0 | Pending Approval | 33 | 2025-04-06 |  | Fiber optic telemetry routing realignment along guideway
VO-PKG-01-01121 | PKG-01 | 98919.6 | 91926.53 | Approved | 51 | 2025-04-07 | 2025-05-06 | Unforeseen soft ground stabilization and grouting
VO-PKG-10-02210 | PKG-10 | 125587.3 | 0 | Pending Approval | 41 | 2025-04-07 |  | HVAC chilled water pipe rerouting around station concourse
VO-PKG-03-00293 | PKG-03 | 141992.64 | 0 | Pending Approval | 19 | 2025-04-08 |  | Viaduct pier foundation redesign due to utility clash
VO-PKG-03-02333 | PKG-03 | 313788.9 | 263699.15 | Approved | 40 | 2025-04-08 | 2025-06-02 | Viaduct pier foundation redesign due to utility clash
VO-PKG-08-02508 | PKG-08 | 267890.34 | 245655.71 | Approved | 23 | 2025-04-08 | 2025-05-16 | Track vibration damping rubber pads acoustic upgrade
VO-PKG-09-01879 | PKG-09 | 347667.54 | 0 | Pending Approval | 1 | 2025-04-08 |  | Drainage box culvert capacity expansion for 100-year flood event
VO-PKG-10-01020 | PKG-10 | 307529.74 | 0 | Pending Approval | 39 | 2025-04-08 |  | HVAC chilled water pipe rerouting around station concourse
VO-PKG-02-01872 | PKG-02 | 225502.27 | 0 | Rejected | 0 | 2025-04-09 | 2025-05-11 | TBM Cutterhead refurbishment and rock fissure sealing
VO-PKG-06-00026 | PKG-06 | 77177.86 | 0 | Rejected | 0 | 2025-04-09 | 2025-04-22 | Additional smoke evacuation shafts in underground platforms
VO-PKG-08-00688 | PKG-08 | 172583.53 | 149483.76 | Approved | 35 | 2025-04-09 | 2025-05-22 | Track vibration damping rubber pads acoustic upgrade
VO-PKG-02-02942 | PKG-02 | 103724.3 | 0 | Pending Approval | 17 | 2025-04-11 |  | TBM Cutterhead refurbishment and rock fissure sealing
VO-PKG-03-00073 | PKG-03 | 330159.72 | 309038.52 | Approved | 9 | 2025-04-11 | 2025-05-13 | Viaduct pier foundation redesign due to utility clash
VO-PKG-04-00914 | PKG-04 | 178074.86 | 0 | Rejected | 0 | 2025-04-11 | 2025-05-05 | Station box diaphragm wall water ingress mitigation
VO-PKG-05-02005 | PKG-05 | 326865.95 | 0 | Pending Approval | 25 | 2025-04-11 |  | HV substation redundancy transformer capacity upgrade
VO-PKG-10-01950 | PKG-10 | 290331.44 | 0 | Pending Approval | 14 | 2025-04-11 |  | HVAC chilled water pipe rerouting around station concourse
VO-PKG-01-02191 | PKG-01 | 279092.78 | 235741.21 | Approved | 58 | 2025-04-12 | 2025-06-04 | Unforeseen soft ground stabilization and grouting
VO-PKG-02-00582 | PKG-02 | 191447.04 | 169110.13 | Approved | 9 | 2025-04-12 | 2025-05-09 | TBM Cutterhead refurbishment and rock fissure sealing
VO-PKG-09-02569 | PKG-09 | 117259.76 | 113346.33 | Approved | 23 | 2025-04-12 | 2025-06-08 | Drainage box culvert capacity expansion for 100-year flood event
VO-PKG-10-02620 | PKG-10 | 121262.86 | 0 | Pending Approval | 29 | 2025-04-12 |  | HVAC chilled water pipe rerouting around station concourse
VO-PKG-01-00681 | PKG-01 | 167658.55 | 0 | Rejected | 0 | 2025-04-13 | 2025-04-25 | Unforeseen soft ground stabilization and grouting
VO-PKG-05-01445 | PKG-05 | 185324.85 | 170657.79 | Approved | 18 | 2025-04-13 | 2025-05-04 | HV substation redundancy transformer capacity upgrade
VO-PKG-09-01389 | PKG-09 | 122850.58 | 117458.69 | Approved | 41 | 2025-04-13 | 2025-05-29 | Drainage box culvert capacity expansion for 100-year flood event
VO-PKG-05-00065 | PKG-05 | 305000.75 | 0 | Pending Approval | 29 | 2025-04-14 |  | HV substation redundancy transformer capacity upgrade
VO-PKG-06-02036 | PKG-06 | 185100.22 | 0 | Pending Approval | 30 | 2025-04-14 |  | Additional smoke evacuation shafts in underground platforms
VO-PKG-06-00406 | PKG-06 | 186354.76 | 179480.67 | Approved | 10 | 2025-04-15 | 2025-06-03 | Additional smoke evacuation shafts in underground platforms
VO-PKG-07-01507 | PKG-07 | 289384.86 | 0 | Rejected | 0 | 2025-04-15 | 2025-05-14 | Fiber optic telemetry routing realignment along guideway
VO-PKG-08-00748 | PKG-08 | 178877.61 | 162225.13 | Approved | 19 | 2025-04-15 | 2025-05-08 | Track vibration damping rubber pads acoustic upgrade
VO-PKG-10-01370 | PKG-10 | 131583.37 | 127638.82 | Approved | 42 | 2025-04-15 | 2025-05-18 | HVAC chilled water pipe rerouting around station concourse
VO-PKG-02-00622 | PKG-02 | 217369.71 | 179607.55 | Approved | 34 | 2025-04-16 | 2025-06-09 | TBM Cutterhead refurbishment and rock fissure sealing
VO-PKG-02-01632 | PKG-02 | 218786.47 | 182956.72 | Approved | 52 | 2025-04-16 | 2025-06-03 | TBM Cutterhead refurbishment and rock fissure sealing
VO-PKG-04-02394 | PKG-04 | 191845.86 | 179567.43 | Approved | 8 | 2025-04-16 | 2025-06-06 | Station box diaphragm wall water ingress mitigation
VO-PKG-07-00947 | PKG-07 | 343360.25 | 0 | Pending Approval | 4 | 2025-04-16 |  | Fiber optic telemetry routing realignment along guideway
VO-PKG-07-01807 | PKG-07 | 247834.51 | 219181.38 | Approved | 55 | 2025-04-16 | 2025-05-04 | Fiber optic telemetry routing realignment along guideway
VO-PKG-08-01858 | PKG-08 | 275717.97 | 253826.46 | Approved | 45 | 2025-04-16 | 2025-05-05 | Track vibration damping rubber pads acoustic upgrade
VO-PKG-02-02212 | PKG-02 | 325717.99 | 300957.84 | Approved | 12 | 2025-04-17 | 2025-05-26 | TBM Cutterhead refurbishment and rock fissure sealing
VO-PKG-03-01153 | PKG-03 | 151757.12 | 142579.49 | Approved | 13 | 2025-04-17 | 2025-06-15 | Viaduct pier foundation redesign due to utility clash
VO-PKG-08-00098 | PKG-08 | 193797.34 | 0 | Pending Approval | 3 | 2025-04-17 |  | Track vibration damping rubber pads acoustic upgrade
VO-PKG-10-00990 | PKG-10 | 49695.61 | 40982.46 | Approved | 49 | 2025-04-17 | 2025-06-10 | HVAC chilled water pipe rerouting around station concourse
VO-PKG-04-00104 | PKG-04 | 50532.34 | 45095.64 | Approved | 58 | 2025-04-18 | 2025-05-14 | Station box diaphragm wall water ingress mitigation
VO-PKG-04-00654 | PKG-04 | 80614.29 | 0 | Pending Approval | 11 | 2025-04-18 |  | Station box diaphragm wall water ingress mitigation
VO-PKG-05-02265 | PKG-05 | 185984.51 | 0 | Pending Approval | 34 | 2025-04-18 |  | HV substation redundancy transformer capacity upgrade
VO-PKG-08-01778 | PKG-08 | 129677.52 | 0 | Pending Approval | 20 | 2025-04-18 |  | Track vibration damping rubber pads acoustic upgrade
VO-PKG-09-00729 | PKG-09 | 318270.92 | 299810.98 | Approved | 55 | 2025-04-18 | 2025-05-10 | Drainage box culvert capacity expansion for 100-year flood event
VO-PKG-01-02511 | PKG-01 | 83640.93 | 0 | Pending Approval | 18 | 2025-04-19 |  | Unforeseen soft ground stabilization and grouting
VO-PKG-02-00082 | PKG-02 | 319763.37 | 0 | Pending Approval | 40 | 2025-04-19 |  | TBM Cutterhead refurbishment and rock fissure sealing
VO-PKG-03-02803 | PKG-03 | 313857.57 | 0 | Pending Approval | 18 | 2025-04-19 |  | Viaduct pier foundation redesign due to utility clash
VO-PKG-03-02933 | PKG-03 | 193336.81 | 160189.55 | Approved | 38 | 2025-04-19 | 2025-06-10 | Viaduct pier foundation redesign due to utility clash
VO-PKG-05-01745 | PKG-05 | 113536.65 | 0 | Pending Approval | 36 | 2025-04-19 |  | HV substation redundancy transformer capacity upgrade
VO-PKG-05-02255 | PKG-05 | 261775 | 237438.55 | Approved | 49 | 2025-04-19 | 2025-05-22 | HV substation redundancy transformer capacity upgrade
VO-PKG-05-02645 | PKG-05 | 326033.82 | 0 | Pending Approval | 42 | 2025-04-19 |  | HV substation redundancy transformer capacity upgrade
VO-PKG-01-00321 | PKG-01 | 152396.13 | 128286.33 | Approved | 37 | 2025-04-20 | 2025-05-28 | Unforeseen soft ground stabilization and grouting
VO-PKG-02-00122 | PKG-02 | 22772.88 | 0 | Rejected | 0 | 2025-04-20 | 2025-05-27 | TBM Cutterhead refurbishment and rock fissure sealing
VO-PKG-03-00153 | PKG-03 | 89776.82 | 0 | Pending Approval | 44 | 2025-04-20 |  | Viaduct pier foundation redesign due to utility clash
VO-PKG-07-00037 | PKG-07 | 36493.12 | 0 | Rejected | 0 | 2025-04-20 | 2025-05-02 | Fiber optic telemetry routing realignment along guideway
VO-PKG-09-01119 | PKG-09 | 322378.78 | 305227.49 | Approved | 36 | 2025-04-20 | 2025-06-18 | Drainage box culvert capacity expansion for 100-year flood event
VO-PKG-01-00131 | PKG-01 | 178261.69 | 0 | Pending Approval | 42 | 2025-04-21 |  | Unforeseen soft ground stabilization and grouting
VO-PKG-02-00892 | PKG-02 | 40464.94 | 0 | Pending Approval | 35 | 2025-04-21 |  | TBM Cutterhead refurbishment and rock fissure sealing
VO-PKG-03-01293 | PKG-03 | 344040.62 | 0 | Rejected | 0 | 2025-04-21 | 2025-05-08 | Viaduct pier foundation redesign due to utility clash
VO-PKG-04-02974 | PKG-04 | 301707.49 | 0 | Rejected | 0 | 2025-04-21 | 2025-05-25 | Station box diaphragm wall water ingress mitigation
VO-PKG-06-00276 | PKG-06 | 113259.06 | 91696.81 | Approved | 38 | 2025-04-21 | 2025-05-29 | Additional smoke evacuation shafts in underground platforms
VO-PKG-02-01052 | PKG-02 | 59375.57 | 0 | Rejected | 0 | 2025-04-22 | 2025-05-02 | TBM Cutterhead refurbishment and rock fissure sealing
VO-PKG-04-00414 | PKG-04 | 38078.62 | 0 | Rejected | 0 | 2025-04-22 | 2025-05-26 | Station box diaphragm wall water ingress mitigation
VO-PKG-05-02215 | PKG-05 | 80725.9 | 73691.51 | Approved | 11 | 2025-04-22 | 2025-06-03 | HV substation redundancy transformer capacity upgrade
VO-PKG-05-02855 | PKG-05 | 312285.55 | 300753.42 | Approved | 22 | 2025-04-22 | 2025-06-07 | HV substation redundancy transformer capacity upgrade
VO-PKG-07-01747 | PKG-07 | 56284.02 | 0 | Pending Approval | 33 | 2025-04-22 |  | Fiber optic telemetry routing realignment along guideway
VO-PKG-08-00518 | PKG-08 | 311131.39 | 293545.14 | Approved | 41 | 2025-04-22 | 2025-05-09 | Track vibration damping rubber pads acoustic upgrade
VO-PKG-03-00753 | PKG-03 | 34770.58 | 0 | Pending Approval | 10 | 2025-04-23 |  | Viaduct pier foundation redesign due to utility clash
VO-PKG-06-02916 | PKG-06 | 130261.05 | 114688.08 | Approved | 19 | 2025-04-23 | 2025-05-30 | Additional smoke evacuation shafts in underground platforms
VO-PKG-05-00195 | PKG-05 | 51576.8 | 0 | Rejected | 0 | 2025-04-24 | 2025-05-21 | HV substation redundancy transformer capacity upgrade
VO-PKG-06-00456 | PKG-06 | 139398.39 | 0 | Pending Approval | 17 | 2025-04-24 |  | Additional smoke evacuation shafts in underground platforms
VO-PKG-08-01018 | PKG-08 | 27276.48 | 0 | Pending Approval | 8 | 2025-04-24 |  | Track vibration damping rubber pads acoustic upgrade
VO-PKG-10-02320 | PKG-10 | 295360.52 | 286189.71 | Approved | 31 | 2025-04-24 | 2025-05-16 | HVAC chilled water pipe rerouting around station concourse
VO-PKG-02-02332 | PKG-02 | 76848.08 | 0 | Pending Approval | 28 | 2025-04-25 |  | TBM Cutterhead refurbishment and rock fissure sealing
VO-PKG-03-00283 | PKG-03 | 104025.7 | 88347.53 | Approved | 54 | 2025-04-25 | 2025-05-19 | Viaduct pier foundation redesign due to utility clash
VO-PKG-03-02243 | PKG-03 | 321562.61 | 292651.12 | Approved | 6 | 2025-04-25 | 2025-06-11 | Viaduct pier foundation redesign due to utility clash
VO-PKG-05-00935 | PKG-05 | 146073.67 | 126819.78 | Approved | 21 | 2025-04-25 | 2025-06-06 | HV substation redundancy transformer capacity upgrade
VO-PKG-01-02861 | PKG-01 | 310151.02 | 0 | Pending Approval | 13 | 2025-04-27 |  | Unforeseen soft ground stabilization and grouting
VO-PKG-03-01213 | PKG-03 | 137524.74 | 133482.03 | Approved | 10 | 2025-04-28 | 2025-06-04 | Viaduct pier foundation redesign due to utility clash
VO-PKG-04-00454 | PKG-04 | 215007.53 | 0 | Pending Approval | 43 | 2025-04-28 |  | Station box diaphragm wall water ingress mitigation
VO-PKG-04-01174 | PKG-04 | 216280.67 | 184963.19 | Approved | 58 | 2025-04-28 | 2025-06-01 | Station box diaphragm wall water ingress mitigation
VO-PKG-06-00436 | PKG-06 | 314552.9 | 288640.87 | Approved | 40 | 2025-04-28 | 2025-05-13 | Additional smoke evacuation shafts in underground platforms
VO-PKG-08-00958 | PKG-08 | 263246.98 | 0 | Pending Approval | 11 | 2025-04-28 |  | Track vibration damping rubber pads acoustic upgrade
VO-PKG-04-00134 | PKG-04 | 160387.55 | 0 | Pending Approval | 4 | 2025-04-29 |  | Station box diaphragm wall water ingress mitigation
VO-PKG-05-00775 | PKG-05 | 159964.9 | 129011.08 | Approved | 45 | 2025-04-29 | 2025-06-02 | HV substation redundancy transformer capacity upgrade
VO-PKG-06-02046 | PKG-06 | 108488.42 | 97060.51 | Approved | 18 | 2025-04-29 | 2025-05-19 | Additional smoke evacuation shafts in underground platforms
VO-PKG-01-02811 | PKG-01 | 168055.81 | 0 | Pending Approval | 36 | 2025-04-30 |  | Unforeseen soft ground stabilization and grouting
VO-PKG-03-00853 | PKG-03 | 296962.29 | 0 | Pending Approval | 0 | 2025-04-30 |  | Viaduct pier foundation redesign due to utility clash
VO-PKG-04-01624 | PKG-04 | 277500.31 | 261850.32 | Approved | 59 | 2025-04-30 | 2025-05-20 | Station box diaphragm wall water ingress mitigation
VO-PKG-10-00340 | PKG-10 | 145742.31 | 120138.18 | Approved | 35 | 2025-04-30 | 2025-06-22 | HVAC chilled water pipe rerouting around station concourse
VO-PKG-03-01653 | PKG-03 | 196634.16 | 169358.71 | Approved | 45 | 2025-05-01 | 2025-06-25 | Viaduct pier foundation redesign due to utility clash
VO-PKG-05-00025 | PKG-05 | 192175 | 0 | Pending Approval | 10 | 2025-05-01 |  | HV substation redundancy transformer capacity upgrade
VO-PKG-06-00826 | PKG-06 | 127048.3 | 113865.01 | Approved | 42 | 2025-05-01 | 2025-06-03 | Additional smoke evacuation shafts in underground platforms
VO-PKG-08-02038 | PKG-08 | 230539.04 | 221232 | Approved | 15 | 2025-05-02 | 2025-06-29 | Track vibration damping rubber pads acoustic upgrade
VO-PKG-09-00209 | PKG-09 | 318944.3 | 300364.47 | Approved | 49 | 2025-05-02 | 2025-06-10 | Drainage box culvert capacity expansion for 100-year flood event
VO-PKG-09-01789 | PKG-09 | 61500.24 | 55323.78 | Approved | 35 | 2025-05-02 | 2025-06-11 | Drainage box culvert capacity expansion for 100-year flood event
VO-PKG-10-01580 | PKG-10 | 21458 | 19214.45 | Approved | 7 | 2025-05-02 | 2025-06-21 | HVAC chilled water pipe rerouting around station concourse
VO-PKG-05-01435 | PKG-05 | 221737.56 | 0 | Rejected | 0 | 2025-05-03 | 2025-06-06 | HV substation redundancy transformer capacity upgrade
VO-PKG-08-00718 | PKG-08 | 276493.06 | 268844.53 | Approved | 53 | 2025-05-03 | 2025-06-21 | Track vibration damping rubber pads acoustic upgrade
VO-PKG-01-00001 | PKG-01 | 30621.6 | 0 | Pending Approval | 31 | 2025-05-04 |  | Unforeseen soft ground stabilization and grouting
VO-PKG-01-01131 | PKG-01 | 148928.52 | 138389.83 | Approved | 19 | 2025-05-04 | 2025-05-21 | Unforeseen soft ground stabilization and grouting
VO-PKG-01-01151 | PKG-01 | 329283.75 | 302113.52 | Approved | 49 | 2025-05-04 | 2025-07-02 | Unforeseen soft ground stabilization and grouting
VO-PKG-02-00722 | PKG-02 | 167406.97 | 162070.74 | Approved | 32 | 2025-05-04 | 2025-06-01 | TBM Cutterhead refurbishment and rock fissure sealing
VO-PKG-07-02727 | PKG-07 | 90512.07 | 73618.05 | Approved | 59 | 2025-05-04 | 2025-06-08 | Fiber optic telemetry routing realignment along guideway
VO-PKG-08-02288 | PKG-08 | 23058.48 | 18846.97 | Approved | 8 | 2025-05-04 | 2025-05-29 | Track vibration damping rubber pads acoustic upgrade
VO-PKG-09-00749 | PKG-09 | 81302.54 | 75182.26 | Approved | 44 | 2025-05-04 | 2025-06-08 | Drainage box culvert capacity expansion for 100-year flood event
VO-PKG-09-02249 | PKG-09 | 116825.93 | 0 | Pending Approval | 26 | 2025-05-04 |  | Drainage box culvert capacity expansion for 100-year flood event
VO-PKG-01-01411 | PKG-01 | 220449.43 | 0 | Pending Approval | 11 | 2025-05-05 |  | Unforeseen soft ground stabilization and grouting
VO-PKG-04-02724 | PKG-04 | 344461.74 | 325123.16 | Approved | 20 | 2025-05-05 | 2025-07-03 | Station box diaphragm wall water ingress mitigation
VO-PKG-05-02995 | PKG-05 | 161605.81 | 0 | Rejected | 0 | 2025-05-05 | 2025-05-26 | HV substation redundancy transformer capacity upgrade
VO-PKG-06-00316 | PKG-06 | 142979.71 | 0 | Pending Approval | 4 | 2025-05-05 |  | Additional smoke evacuation shafts in underground platforms
VO-PKG-10-00270 | PKG-10 | 343057.88 | 0 | Rejected | 0 | 2025-05-05 | 2025-06-07 | HVAC chilled water pipe rerouting around station concourse
VO-PKG-04-02144 | PKG-04 | 313692.32 | 0 | Pending Approval | 44 | 2025-05-06 |  | Station box diaphragm wall water ingress mitigation
VO-PKG-07-01627 | PKG-07 | 182188.67 | 155512.89 | Approved | 5 | 2025-05-06 | 2025-06-24 | Fiber optic telemetry routing realignment along guideway
VO-PKG-08-01658 | PKG-08 | 260315.56 | 0 | Pending Approval | 23 | 2025-05-06 |  | Track vibration damping rubber pads acoustic upgrade
VO-PKG-10-01080 | PKG-10 | 292235.54 | 249014.52 | Approved | 7 | 2025-05-06 | 2025-05-24 | HVAC chilled water pipe rerouting around station concourse
VO-PKG-04-01434 | PKG-04 | 292474.07 | 0 | Rejected | 0 | 2025-05-07 | 2025-06-05 | Station box diaphragm wall water ingress mitigation
VO-PKG-06-00516 | PKG-06 | 225699.33 | 0 | Rejected | 0 | 2025-05-07 | 2025-05-22 | Additional smoke evacuation shafts in underground platforms
VO-PKG-06-01496 | PKG-06 | 246495.16 | 222105.34 | Approved | 40 | 2025-05-07 | 2025-05-24 | Additional smoke evacuation shafts in underground platforms
VO-PKG-06-01546 | PKG-06 | 244197.07 | 196219.41 | Approved | 41 | 2025-05-07 | 2025-07-02 | Additional smoke evacuation shafts in underground platforms
VO-PKG-07-01047 | PKG-07 | 49674.25 | 43555.01 | Approved | 50 | 2025-05-07 | 2025-06-06 | Fiber optic telemetry routing realignment along guideway
VO-PKG-07-01457 | PKG-07 | 316558.71 | 305800.74 | Approved | 45 | 2025-05-07 | 2025-05-25 | Fiber optic telemetry routing realignment along guideway
VO-PKG-08-02598 | PKG-08 | 157694.98 | 0 | Pending Approval | 4 | 2025-05-07 |  | Track vibration damping rubber pads acoustic upgrade
VO-PKG-01-01721 | PKG-01 | 51948.07 | 0 | Pending Approval | 29 | 2025-05-08 |  | Unforeseen soft ground stabilization and grouting
VO-PKG-07-00217 | PKG-07 | 40566.25 | 38147.48 | Approved | 31 | 2025-05-08 | 2025-06-01 | Fiber optic telemetry routing realignment along guideway
VO-PKG-08-00938 | PKG-08 | 136237.31 | 0 | Pending Approval | 40 | 2025-05-08 |  | Track vibration damping rubber pads acoustic upgrade
VO-PKG-01-01791 | PKG-01 | 189375.92 | 0 | Rejected | 0 | 2025-05-09 | 2025-06-07 | Unforeseen soft ground stabilization and grouting
VO-PKG-02-00002 | PKG-02 | 56392.38 | 0 | Rejected | 0 | 2025-05-09 | 2025-06-14 | TBM Cutterhead refurbishment and rock fissure sealing
VO-PKG-04-00474 | PKG-04 | 339064.37 | 0 | Rejected | 0 | 2025-05-10 | 2025-06-09 | Station box diaphragm wall water ingress mitigation
VO-PKG-04-00574 | PKG-04 | 330849.07 | 301861.01 | Approved | 40 | 2025-05-10 | 2025-06-10 | Station box diaphragm wall water ingress mitigation
VO-PKG-05-02035 | PKG-05 | 198168.11 | 158569.41 | Approved | 43 | 2025-05-10 | 2025-06-06 | HV substation redundancy transformer capacity upgrade
VO-PKG-02-01912 | PKG-02 | 23586.33 | 0 | Pending Approval | 10 | 2025-05-11 |  | TBM Cutterhead refurbishment and rock fissure sealing
VO-PKG-05-01115 | PKG-05 | 173063.31 | 157906.99 | Approved | 23 | 2025-05-11 | 2025-06-19 | HV substation redundancy transformer capacity upgrade
VO-PKG-07-00117 | PKG-07 | 191905.64 | 0 | Rejected | 0 | 2025-05-11 | 2025-06-03 | Fiber optic telemetry routing realignment along guideway
VO-PKG-07-01687 | PKG-07 | 207701.12 | 0 | Pending Approval | 19 | 2025-05-11 |  | Fiber optic telemetry routing realignment along guideway
VO-PKG-07-01987 | PKG-07 | 188675.3 | 169213.09 | Approved | 27 | 2025-05-11 | 2025-07-03 | Fiber optic telemetry routing realignment along guideway
VO-PKG-02-00282 | PKG-02 | 200418.13 | 0 | Pending Approval | 0 | 2025-05-12 |  | TBM Cutterhead refurbishment and rock fissure sealing
VO-PKG-05-00355 | PKG-05 | 123981.81 | 113286.15 | Approved | 32 | 2025-05-12 | 2025-06-10 | HV substation redundancy transformer capacity upgrade
VO-PKG-04-00814 | PKG-04 | 340651.8 | 0 | Pending Approval | 25 | 2025-05-13 |  | Station box diaphragm wall water ingress mitigation
VO-PKG-05-02635 | PKG-05 | 32028.81 | 0 | Rejected | 0 | 2025-05-13 | 2025-06-16 | HV substation redundancy transformer capacity upgrade
VO-PKG-06-02096 | PKG-06 | 315615.94 | 276010.04 | Approved | 17 | 2025-05-13 | 2025-06-07 | Additional smoke evacuation shafts in underground platforms
VO-PKG-03-00343 | PKG-03 | 261551.02 | 229951.3 | Approved | 43 | 2025-05-14 | 2025-06-23 | Viaduct pier foundation redesign due to utility clash
VO-PKG-03-01883 | PKG-03 | 315018.74 | 0 | Pending Approval | 11 | 2025-05-14 |  | Viaduct pier foundation redesign due to utility clash
VO-PKG-04-01674 | PKG-04 | 150312.4 | 0 | Pending Approval | 25 | 2025-05-14 |  | Station box diaphragm wall water ingress mitigation
VO-PKG-07-00657 | PKG-07 | 110673.74 | 108383.15 | Approved | 35 | 2025-05-14 | 2025-06-21 | Fiber optic telemetry routing realignment along guideway
VO-PKG-10-01290 | PKG-10 | 325440.74 | 276209.34 | Approved | 59 | 2025-05-14 | 2025-07-02 | HVAC chilled water pipe rerouting around station concourse
VO-PKG-04-01794 | PKG-04 | 290052.09 | 267361.48 | Approved | 24 | 2025-05-15 | 2025-06-16 | Station box diaphragm wall water ingress mitigation
VO-PKG-06-01086 | PKG-06 | 125636.84 | 0 | Pending Approval | 32 | 2025-05-15 |  | Additional smoke evacuation shafts in underground platforms
VO-PKG-08-00488 | PKG-08 | 96073.68 | 0 | Pending Approval | 34 | 2025-05-15 |  | Track vibration damping rubber pads acoustic upgrade
VO-PKG-10-01560 | PKG-10 | 280962.18 | 0 | Pending Approval | 11 | 2025-05-15 |  | HVAC chilled water pipe rerouting around station concourse
VO-PKG-05-00895 | PKG-05 | 32225.95 | 0 | Pending Approval | 13 | 2025-05-16 |  | HV substation redundancy transformer capacity upgrade
VO-PKG-05-01505 | PKG-05 | 119828.53 | 110755.87 | Approved | 41 | 2025-05-16 | 2025-06-19 | HV substation redundancy transformer capacity upgrade
VO-PKG-06-00206 | PKG-06 | 173910.09 | 142809.5 | Approved | 35 | 2025-05-16 | 2025-06-14 | Additional smoke evacuation shafts in underground platforms
VO-PKG-05-01915 | PKG-05 | 240656.12 | 0 | Pending Approval | 43 | 2025-05-17 |  | HV substation redundancy transformer capacity upgrade
VO-PKG-03-01843 | PKG-03 | 278107.48 | 259313.94 | Approved | 24 | 2025-05-18 | 2025-07-16 | Viaduct pier foundation redesign due to utility clash
VO-PKG-06-00626 | PKG-06 | 198500.03 | 164755.18 | Approved | 54 | 2025-05-18 | 2025-06-16 | Additional smoke evacuation shafts in underground platforms
VO-PKG-09-02839 | PKG-09 | 209282.12 | 0 | Pending Approval | 15 | 2025-05-18 |  | Drainage box culvert capacity expansion for 100-year flood event
VO-PKG-01-02541 | PKG-01 | 238464.95 | 201316.64 | Approved | 42 | 2025-05-19 | 2025-06-09 | Unforeseen soft ground stabilization and grouting
VO-PKG-03-00163 | PKG-03 | 50846.05 | 45458.45 | Approved | 36 | 2025-05-19 | 2025-06-22 | Viaduct pier foundation redesign due to utility clash
VO-PKG-03-02193 | PKG-03 | 328544.81 | 0 | Rejected | 0 | 2025-05-19 | 2025-06-22 | Viaduct pier foundation redesign due to utility clash
VO-PKG-05-01685 | PKG-05 | 164329.58 | 147151.05 | Approved | 35 | 2025-05-19 | 2025-07-01 | HV substation redundancy transformer capacity upgrade
VO-PKG-08-00068 | PKG-08 | 98431.45 | 90410 | Approved | 29 | 2025-05-19 | 2025-07-02 | Track vibration damping rubber pads acoustic upgrade
VO-PKG-02-01682 | PKG-02 | 274977.59 | 241145.96 | Approved | 59 | 2025-05-20 | 2025-06-25 | TBM Cutterhead refurbishment and rock fissure sealing
VO-PKG-03-00993 | PKG-03 | 228722.69 | 192511.63 | Approved | 20 | 2025-05-20 | 2025-07-06 | Viaduct pier foundation redesign due to utility clash
VO-PKG-03-01633 | PKG-03 | 131717.13 | 120658.32 | Approved | 5 | 2025-05-20 | 2025-06-25 | Viaduct pier foundation redesign due to utility clash
VO-PKG-06-00076 | PKG-06 | 299186.29 | 270511.42 | Approved | 56 | 2025-05-20 | 2025-06-29 | Additional smoke evacuation shafts in underground platforms
VO-PKG-08-00768 | PKG-08 | 268880.32 | 253650.23 | Approved | 37 | 2025-05-20 | 2025-07-08 | Track vibration damping rubber pads acoustic upgrade
VO-PKG-01-01391 | PKG-01 | 216036.04 | 198248.18 | Approved | 35 | 2025-05-21 | 2025-06-10 | Unforeseen soft ground stabilization and grouting
VO-PKG-04-01244 | PKG-04 | 38109.28 | 0 | Rejected | 0 | 2025-05-21 | 2025-06-09 | Station box diaphragm wall water ingress mitigation
VO-PKG-05-02025 | PKG-05 | 130907.31 | 107903.36 | Approved | 25 | 2025-05-21 | 2025-06-16 | HV substation redundancy transformer capacity upgrade
VO-PKG-06-01106 | PKG-06 | 236634.47 | 195649.52 | Approved | 37 | 2025-05-21 | 2025-07-18 | Additional smoke evacuation shafts in underground platforms
VO-PKG-06-01756 | PKG-06 | 132444.18 | 0 | Pending Approval | 44 | 2025-05-21 |  | Additional smoke evacuation shafts in underground platforms
VO-PKG-09-02609 | PKG-09 | 116500.78 | 108867.02 | Approved | 58 | 2025-05-21 | 2025-06-25 | Drainage box culvert capacity expansion for 100-year flood event
VO-PKG-03-02253 | PKG-03 | 202478.9 | 177580.55 | Approved | 32 | 2025-05-22 | 2025-06-16 | Viaduct pier foundation redesign due to utility clash
VO-PKG-04-00984 | PKG-04 | 309660.22 | 0 | Pending Approval | 38 | 2025-05-22 |  | Station box diaphragm wall water ingress mitigation
VO-PKG-05-01425 | PKG-05 | 339920.19 | 317218.56 | Approved | 7 | 2025-05-22 | 2025-06-21 | HV substation redundancy transformer capacity upgrade
VO-PKG-05-00305 | PKG-05 | 182111.59 | 0 | Pending Approval | 34 | 2025-05-23 |  | HV substation redundancy transformer capacity upgrade
VO-PKG-06-01026 | PKG-06 | 39369.41 | 35542.53 | Approved | 47 | 2025-05-23 | 2025-06-28 | Additional smoke evacuation shafts in underground platforms
VO-PKG-06-01376 | PKG-06 | 222705.03 | 203836.16 | Approved | 31 | 2025-05-24 | 2025-06-28 | Additional smoke evacuation shafts in underground platforms
VO-PKG-08-01038 | PKG-08 | 82090.33 | 66610.78 | Approved | 13 | 2025-05-24 | 2025-07-16 | Track vibration damping rubber pads acoustic upgrade
VO-PKG-09-01599 | PKG-09 | 83213.93 | 66857.96 | Approved | 29 | 2025-05-25 | 2025-07-09 | Drainage box culvert capacity expansion for 100-year flood event
VO-PKG-01-00361 | PKG-01 | 315258.23 | 293450.57 | Approved | 17 | 2025-05-26 | 2025-07-22 | Unforeseen soft ground stabilization and grouting
VO-PKG-10-02150 | PKG-10 | 199193.12 | 0 | Pending Approval | 30 | 2025-05-26 |  | HVAC chilled water pipe rerouting around station concourse
VO-PKG-04-01734 | PKG-04 | 51035.27 | 42432.2 | Approved | 5 | 2025-05-27 | 2025-07-24 | Station box diaphragm wall water ingress mitigation
VO-PKG-05-01245 | PKG-05 | 21284.98 | 0 | Pending Approval | 34 | 2025-05-27 |  | HV substation redundancy transformer capacity upgrade
VO-PKG-09-02919 | PKG-09 | 275198.45 | 248080.19 | Approved | 59 | 2025-05-27 | 2025-06-14 | Drainage box culvert capacity expansion for 100-year flood event
VO-PKG-10-01050 | PKG-10 | 210814.13 | 0 | Rejected | 0 | 2025-05-27 | 2025-07-03 | HVAC chilled water pipe rerouting around station concourse
VO-PKG-04-00354 | PKG-04 | 227023.68 | 208911.29 | Approved | 47 | 2025-05-28 | 2025-07-04 | Station box diaphragm wall water ingress mitigation
VO-PKG-04-00794 | PKG-04 | 90672.8 | 72718.97 | Approved | 40 | 2025-05-28 | 2025-07-02 | Station box diaphragm wall water ingress mitigation
VO-PKG-06-01136 | PKG-06 | 300159.35 | 289579.65 | Approved | 32 | 2025-05-28 | 2025-07-04 | Additional smoke evacuation shafts in underground platforms
VO-PKG-07-01327 | PKG-07 | 39167.21 | 34951.04 | Approved | 55 | 2025-05-28 | 2025-07-19 | Fiber optic telemetry routing realignment along guideway
VO-PKG-08-00658 | PKG-08 | 268464.27 | 225288.75 | Approved | 52 | 2025-05-28 | 2025-07-18 | Track vibration damping rubber pads acoustic upgrade
VO-PKG-09-01339 | PKG-09 | 241775.95 | 205455.85 | Approved | 55 | 2025-05-28 | 2025-07-18 | Drainage box culvert capacity expansion for 100-year flood event
VO-PKG-06-02546 | PKG-06 | 303323.82 | 0 | Pending Approval | 43 | 2025-05-29 |  | Additional smoke evacuation shafts in underground platforms
VO-PKG-02-02862 | PKG-02 | 175415.56 | 159119.98 | Approved | 34 | 2025-05-30 | 2025-07-15 | TBM Cutterhead refurbishment and rock fissure sealing
VO-PKG-05-02895 | PKG-05 | 309556.78 | 0 | Pending Approval | 35 | 2025-05-30 |  | HV substation redundancy transformer capacity upgrade
VO-PKG-05-02945 | PKG-05 | 79863.51 | 75183.53 | Approved | 27 | 2025-05-30 | 2025-07-16 | HV substation redundancy transformer capacity upgrade
VO-PKG-06-02856 | PKG-06 | 303138.61 | 279817.71 | Approved | 39 | 2025-05-30 | 2025-06-23 | Additional smoke evacuation shafts in underground platforms
VO-PKG-08-01678 | PKG-08 | 55879.57 | 49385.28 | Approved | 25 | 2025-05-30 | 2025-06-17 | Track vibration damping rubber pads acoustic upgrade
VO-PKG-09-02659 | PKG-09 | 140910.63 | 0 | Pending Approval | 12 | 2025-05-30 |  | Drainage box culvert capacity expansion for 100-year flood event
VO-PKG-04-02694 | PKG-04 | 96861.8 | 83057.71 | Approved | 16 | 2025-06-01 | 2025-07-24 | Station box diaphragm wall water ingress mitigation
VO-PKG-07-02947 | PKG-07 | 269855.54 | 237581.33 | Approved | 16 | 2025-06-01 | 2025-07-15 | Fiber optic telemetry routing realignment along guideway
VO-PKG-01-00251 | PKG-01 | 196474.85 | 174782.91 | Approved | 43 | 2025-06-02 | 2025-06-29 | Unforeseen soft ground stabilization and grouting
VO-PKG-03-00423 | PKG-03 | 48522.13 | 42616.54 | Approved | 47 | 2025-06-02 | 2025-07-21 | Viaduct pier foundation redesign due to utility clash
VO-PKG-08-02018 | PKG-08 | 157465.9 | 0 | Pending Approval | 27 | 2025-06-02 |  | Track vibration damping rubber pads acoustic upgrade
VO-PKG-08-02488 | PKG-08 | 289714.55 | 242657.5 | Approved | 42 | 2025-06-02 | 2025-07-27 | Track vibration damping rubber pads acoustic upgrade
VO-PKG-08-02918 | PKG-08 | 263800.67 | 212252.54 | Approved | 34 | 2025-06-02 | 2025-07-17 | Track vibration damping rubber pads acoustic upgrade
VO-PKG-09-01969 | PKG-09 | 127121.19 | 0 | Rejected | 0 | 2025-06-02 | 2025-07-13 | Drainage box culvert capacity expansion for 100-year flood event
VO-PKG-10-00330 | PKG-10 | 121026.04 | 104572.29 | Approved | 49 | 2025-06-02 | 2025-07-10 | HVAC chilled water pipe rerouting around station concourse
VO-PKG-10-02520 | PKG-10 | 101997.43 | 0 | Pending Approval | 20 | 2025-06-02 |  | HVAC chilled water pipe rerouting around station concourse
VO-PKG-01-01881 | PKG-01 | 51686.43 | 43958.2 | Approved | 29 | 2025-06-03 | 2025-07-18 | Unforeseen soft ground stabilization and grouting
VO-PKG-01-01941 | PKG-01 | 310192.76 | 284870.75 | Approved | 24 | 2025-06-03 | 2025-06-28 | Unforeseen soft ground stabilization and grouting
VO-PKG-03-00183 | PKG-03 | 47653.53 | 0 | Pending Approval | 0 | 2025-06-03 |  | Viaduct pier foundation redesign due to utility clash
VO-PKG-04-01324 | PKG-04 | 52703.59 | 50325.59 | Approved | 6 | 2025-06-03 | 2025-07-03 | Station box diaphragm wall water ingress mitigation
VO-PKG-06-02366 | PKG-06 | 157932.44 | 134751.96 | Approved | 13 | 2025-06-03 | 2025-07-26 | Additional smoke evacuation shafts in underground platforms
VO-PKG-08-01598 | PKG-08 | 73507.03 | 65719.39 | Approved | 32 | 2025-06-03 | 2025-06-29 | Track vibration damping rubber pads acoustic upgrade
VO-PKG-08-02558 | PKG-08 | 208331.93 | 0 | Pending Approval | 37 | 2025-06-03 |  | Track vibration damping rubber pads acoustic upgrade
VO-PKG-01-02961 | PKG-01 | 211858.56 | 0 | Pending Approval | 11 | 2025-06-04 |  | Unforeseen soft ground stabilization and grouting
VO-PKG-05-00505 | PKG-05 | 233340.79 | 0 | Rejected | 0 | 2025-06-04 | 2025-07-14 | HV substation redundancy transformer capacity upgrade
VO-PKG-06-00976 | PKG-06 | 124151.79 | 110547.07 | Approved | 21 | 2025-06-04 | 2025-07-16 | Additional smoke evacuation shafts in underground platforms
VO-PKG-07-00567 | PKG-07 | 280801.24 | 241112.49 | Approved | 19 | 2025-06-04 | 2025-07-20 | Fiber optic telemetry routing realignment along guideway
VO-PKG-08-01988 | PKG-08 | 110394.9 | 93858.34 | Approved | 21 | 2025-06-04 | 2025-06-28 | Track vibration damping rubber pads acoustic upgrade
VO-PKG-01-01551 | PKG-01 | 332798.61 | 268411.78 | Approved | 58 | 2025-06-05 | 2025-06-27 | Unforeseen soft ground stabilization and grouting
VO-PKG-06-00376 | PKG-06 | 212836.13 | 201639.17 | Approved | 36 | 2025-06-05 | 2025-06-21 | Additional smoke evacuation shafts in underground platforms
VO-PKG-10-01390 | PKG-10 | 165823.9 | 155340.45 | Approved | 12 | 2025-06-05 | 2025-06-29 | HVAC chilled water pipe rerouting around station concourse
VO-PKG-10-01480 | PKG-10 | 92738.12 | 78690.13 | Approved | 43 | 2025-06-05 | 2025-07-05 | HVAC chilled water pipe rerouting around station concourse
VO-PKG-03-01543 | PKG-03 | 50046.17 | 44653.12 | Approved | 8 | 2025-06-06 | 2025-07-08 | Viaduct pier foundation redesign due to utility clash
VO-PKG-08-01358 | PKG-08 | 215880.03 | 0 | Pending Approval | 19 | 2025-06-06 |  | Track vibration damping rubber pads acoustic upgrade
VO-PKG-09-00599 | PKG-09 | 24058.1 | 20136.73 | Approved | 45 | 2025-06-06 | 2025-06-29 | Drainage box culvert capacity expansion for 100-year flood event
VO-PKG-02-02752 | PKG-02 | 319210.51 | 0 | Rejected | 0 | 2025-06-07 | 2025-07-15 | TBM Cutterhead refurbishment and rock fissure sealing
VO-PKG-02-02822 | PKG-02 | 38284.65 | 31085.85 | Approved | 47 | 2025-06-07 | 2025-07-05 | TBM Cutterhead refurbishment and rock fissure sealing
VO-PKG-07-00137 | PKG-07 | 113883.05 | 97397.15 | Approved | 19 | 2025-06-07 | 2025-07-26 | Fiber optic telemetry routing realignment along guideway
VO-PKG-07-01437 | PKG-07 | 103568.2 | 0 | Pending Approval | 27 | 2025-06-07 |  | Fiber optic telemetry routing realignment along guideway
VO-PKG-07-02497 | PKG-07 | 129794.82 | 0 | Pending Approval | 2 | 2025-06-07 |  | Fiber optic telemetry routing realignment along guideway
VO-PKG-08-01258 | PKG-08 | 180182.02 | 0 | Pending Approval | 27 | 2025-06-07 |  | Track vibration damping rubber pads acoustic upgrade
VO-PKG-09-00509 | PKG-09 | 309223.18 | 0 | Pending Approval | 8 | 2025-06-07 |  | Drainage box culvert capacity expansion for 100-year flood event
VO-PKG-10-01220 | PKG-10 | 212841.38 | 0 | Pending Approval | 37 | 2025-06-07 |  | HVAC chilled water pipe rerouting around station concourse
VO-PKG-01-01081 | PKG-01 | 176563.14 | 172227.37 | Approved | 51 | 2025-06-08 | 2025-07-11 | Unforeseen soft ground stabilization and grouting
VO-PKG-02-02062 | PKG-02 | 151488.89 | 132724.81 | Approved | 44 | 2025-06-08 | 2025-07-16 | TBM Cutterhead refurbishment and rock fissure sealing
VO-PKG-09-00549 | PKG-09 | 56687.5 | 0 | Rejected | 0 | 2025-06-08 | 2025-07-08 | Drainage box culvert capacity expansion for 100-year flood event
VO-PKG-10-00350 | PKG-10 | 325360.89 | 0 | Rejected | 0 | 2025-06-08 | 2025-07-04 | HVAC chilled water pipe rerouting around station concourse
VO-PKG-01-01971 | PKG-01 | 165744.11 | 147244.34 | Approved | 19 | 2025-06-09 | 2025-07-16 | Unforeseen soft ground stabilization and grouting
VO-PKG-03-01313 | PKG-03 | 268639.32 | 0 | Pending Approval | 0 | 2025-06-09 |  | Viaduct pier foundation redesign due to utility clash
VO-PKG-03-02813 | PKG-03 | 305008.94 | 271231.14 | Approved | 50 | 2025-06-09 | 2025-08-07 | Viaduct pier foundation redesign due to utility clash
VO-PKG-03-02883 | PKG-03 | 183622.68 | 0 | Pending Approval | 21 | 2025-06-09 |  | Viaduct pier foundation redesign due to utility clash
VO-PKG-05-00665 | PKG-05 | 77600.15 | 0 | Pending Approval | 29 | 2025-06-09 |  | HV substation redundancy transformer capacity upgrade
VO-PKG-10-02310 | PKG-10 | 204374.36 | 191252.83 | Approved | 33 | 2025-06-09 | 2025-07-18 | HVAC chilled water pipe rerouting around station concourse
VO-PKG-01-02521 | PKG-01 | 69750.04 | 0 | Pending Approval | 26 | 2025-06-11 |  | Unforeseen soft ground stabilization and grouting
VO-PKG-02-00112 | PKG-02 | 86995.28 | 77521.59 | Approved | 42 | 2025-06-11 | 2025-08-03 | TBM Cutterhead refurbishment and rock fissure sealing
VO-PKG-08-02048 | PKG-08 | 289763.65 | 0 | Pending Approval | 0 | 2025-06-11 |  | Track vibration damping rubber pads acoustic upgrade
VO-PKG-01-01461 | PKG-01 | 325771.72 | 312661.49 | Approved | 39 | 2025-06-12 | 2025-07-20 | Unforeseen soft ground stabilization and grouting
VO-PKG-03-01103 | PKG-03 | 147713.61 | 144651.6 | Approved | 53 | 2025-06-12 | 2025-07-28 | Viaduct pier foundation redesign due to utility clash
VO-PKG-06-02396 | PKG-06 | 243441.21 | 203623.96 | Approved | 7 | 2025-06-12 | 2025-07-25 | Additional smoke evacuation shafts in underground platforms
VO-PKG-08-00398 | PKG-08 | 126658.51 | 104153.13 | Approved | 14 | 2025-06-12 | 2025-07-28 | Track vibration damping rubber pads acoustic upgrade
VO-PKG-08-02328 | PKG-08 | 27739.08 | 0 | Pending Approval | 24 | 2025-06-12 |  | Track vibration damping rubber pads acoustic upgrade
VO-PKG-07-02697 | PKG-07 | 96414.44 | 90784.96 | Approved | 32 | 2025-06-13 | 2025-07-25 | Fiber optic telemetry routing realignment along guideway
VO-PKG-08-02968 | PKG-08 | 134123.85 | 108280.63 | Approved | 21 | 2025-06-13 | 2025-08-11 | Track vibration damping rubber pads acoustic upgrade
VO-PKG-03-00533 | PKG-03 | 163543.04 | 153593.41 | Approved | 9 | 2025-06-14 | 2025-07-18 | Viaduct pier foundation redesign due to utility clash
VO-PKG-05-02225 | PKG-05 | 195392.39 | 180276.07 | Approved | 15 | 2025-06-14 | 2025-06-30 | HV substation redundancy transformer capacity upgrade
VO-PKG-07-02557 | PKG-07 | 311105.17 | 250010.73 | Approved | 50 | 2025-06-14 | 2025-07-14 | Fiber optic telemetry routing realignment along guideway
VO-PKG-08-00058 | PKG-08 | 72399.54 | 65194.29 | Approved | 17 | 2025-06-15 | 2025-07-03 | Track vibration damping rubber pads acoustic upgrade
VO-PKG-01-02741 | PKG-01 | 160409.69 | 0 | Pending Approval | 0 | 2025-06-16 |  | Unforeseen soft ground stabilization and grouting
VO-PKG-02-00632 | PKG-02 | 96560.71 | 89700.52 | Approved | 43 | 2025-06-17 | 2025-07-17 | TBM Cutterhead refurbishment and rock fissure sealing
VO-PKG-05-02055 | PKG-05 | 258890.13 | 0 | Rejected | 0 | 2025-06-17 | 2025-07-16 | HV substation redundancy transformer capacity upgrade
VO-PKG-06-00676 | PKG-06 | 213726.97 | 183208.17 | Approved | 56 | 2025-06-17 | 2025-07-24 | Additional smoke evacuation shafts in underground platforms
VO-PKG-07-00977 | PKG-07 | 187010.04 | 0 | Pending Approval | 41 | 2025-06-17 |  | Fiber optic telemetry routing realignment along guideway
VO-PKG-08-02518 | PKG-08 | 290831.41 | 251847.65 | Approved | 10 | 2025-06-17 | 2025-08-05 | Track vibration damping rubber pads acoustic upgrade
VO-PKG-10-01320 | PKG-10 | 122634.53 | 114030.92 | Approved | 12 | 2025-06-17 | 2025-07-27 | HVAC chilled water pipe rerouting around station concourse
VO-PKG-01-01511 | PKG-01 | 315167.15 | 276206.62 | Approved | 41 | 2025-06-18 | 2025-08-05 | Unforeseen soft ground stabilization and grouting
VO-PKG-02-02142 | PKG-02 | 232585.2 | 211702.28 | Approved | 35 | 2025-06-18 | 2025-07-17 | TBM Cutterhead refurbishment and rock fissure sealing
VO-PKG-03-02963 | PKG-03 | 258046.73 | 0 | Pending Approval | 22 | 2025-06-18 |  | Viaduct pier foundation redesign due to utility clash
VO-PKG-05-00585 | PKG-05 | 283625.3 | 274602.04 | Approved | 7 | 2025-06-18 | 2025-07-05 | HV substation redundancy transformer capacity upgrade
VO-PKG-05-01525 | PKG-05 | 239750.05 | 228246.43 | Approved | 34 | 2025-06-18 | 2025-08-06 | HV substation redundancy transformer capacity upgrade
VO-PKG-05-01665 | PKG-05 | 311449.92 | 263558.94 | Approved | 49 | 2025-06-18 | 2025-08-02 | HV substation redundancy transformer capacity upgrade
VO-PKG-08-02308 | PKG-08 | 241731.21 | 228590.3 | Approved | 46 | 2025-06-18 | 2025-08-02 | Track vibration damping rubber pads acoustic upgrade
VO-PKG-05-00345 | PKG-05 | 152169.16 | 0 | Pending Approval | 2 | 2025-06-19 |  | HV substation redundancy transformer capacity upgrade
VO-PKG-10-01410 | PKG-10 | 88847.38 | 71497.62 | Approved | 39 | 2025-06-19 | 2025-07-07 | HVAC chilled water pipe rerouting around station concourse
VO-PKG-02-00442 | PKG-02 | 282869.99 | 254437.89 | Approved | 6 | 2025-06-20 | 2025-07-16 | TBM Cutterhead refurbishment and rock fissure sealing
VO-PKG-07-00707 | PKG-07 | 53227.72 | 47101.25 | Approved | 59 | 2025-06-20 | 2025-08-03 | Fiber optic telemetry routing realignment along guideway
VO-PKG-09-02439 | PKG-09 | 232321.37 | 211637.72 | Approved | 37 | 2025-06-20 | 2025-07-07 | Drainage box culvert capacity expansion for 100-year flood event
VO-PKG-10-00790 | PKG-10 | 87800.81 | 0 | Rejected | 0 | 2025-06-20 | 2025-07-14 | HVAC chilled water pipe rerouting around station concourse
VO-PKG-06-02136 | PKG-06 | 65205.92 | 57991.24 | Approved | 47 | 2025-06-21 | 2025-08-10 | Additional smoke evacuation shafts in underground platforms
VO-PKG-06-01456 | PKG-06 | 170800.66 | 158888.88 | Approved | 17 | 2025-06-22 | 2025-08-18 | Additional smoke evacuation shafts in underground platforms
VO-PKG-01-01401 | PKG-01 | 97834.29 | 93750.89 | Approved | 54 | 2025-06-24 | 2025-07-12 | Unforeseen soft ground stabilization and grouting
VO-PKG-02-00812 | PKG-02 | 233025.14 | 209503.77 | Approved | 36 | 2025-06-24 | 2025-08-11 | TBM Cutterhead refurbishment and rock fissure sealing
VO-PKG-03-02053 | PKG-03 | 66197.22 | 0 | Pending Approval | 9 | 2025-06-24 |  | Viaduct pier foundation redesign due to utility clash
VO-PKG-10-01270 | PKG-10 | 218853.01 | 0 | Pending Approval | 32 | 2025-06-24 |  | HVAC chilled water pipe rerouting around station concourse
VO-PKG-10-01990 | PKG-10 | 108670.02 | 0 | Pending Approval | 21 | 2025-06-24 |  | HVAC chilled water pipe rerouting around station concourse
VO-PKG-06-02246 | PKG-06 | 255651.97 | 223907.29 | Approved | 55 | 2025-06-25 | 2025-08-09 | Additional smoke evacuation shafts in underground platforms
VO-PKG-10-00050 | PKG-10 | 242691.31 | 209923.8 | Approved | 17 | 2025-06-25 | 2025-08-23 | HVAC chilled water pipe rerouting around station concourse
VO-PKG-04-00094 | PKG-04 | 282169.8 | 0 | Pending Approval | 29 | 2025-06-26 |  | Station box diaphragm wall water ingress mitigation
VO-PKG-05-02565 | PKG-05 | 26358.9 | 0 | Pending Approval | 3 | 2025-06-26 |  | HV substation redundancy transformer capacity upgrade
VO-PKG-06-02666 | PKG-06 | 106568.8 | 92080.27 | Approved | 49 | 2025-06-26 | 2025-08-02 | Additional smoke evacuation shafts in underground platforms
VO-PKG-07-01057 | PKG-07 | 345795.74 | 0 | Pending Approval | 28 | 2025-06-26 |  | Fiber optic telemetry routing realignment along guideway
VO-PKG-10-01790 | PKG-10 | 79691.44 | 68714.23 | Approved | 47 | 2025-06-26 | 2025-07-15 | HVAC chilled water pipe rerouting around station concourse
VO-PKG-03-00433 | PKG-03 | 299502 | 263527.85 | Approved | 59 | 2025-06-27 | 2025-07-30 | Viaduct pier foundation redesign due to utility clash
VO-PKG-07-02627 | PKG-07 | 48295.91 | 0 | Pending Approval | 37 | 2025-06-27 |  | Fiber optic telemetry routing realignment along guideway
VO-PKG-03-02733 | PKG-03 | 111973.63 | 0 | Pending Approval | 23 | 2025-06-28 |  | Viaduct pier foundation redesign due to utility clash
VO-PKG-05-02535 | PKG-05 | 217903.71 | 207830.71 | Approved | 47 | 2025-06-28 | 2025-07-30 | HV substation redundancy transformer capacity upgrade
VO-PKG-06-02866 | PKG-06 | 70811.24 | 66152.34 | Approved | 13 | 2025-06-28 | 2025-08-04 | Additional smoke evacuation shafts in underground platforms
VO-PKG-10-02910 | PKG-10 | 123598.13 | 108310.77 | Approved | 32 | 2025-06-28 | 2025-08-13 | HVAC chilled water pipe rerouting around station concourse
VO-PKG-01-01911 | PKG-01 | 42386.58 | 35735.28 | Approved | 36 | 2025-06-29 | 2025-08-26 | Unforeseen soft ground stabilization and grouting
VO-PKG-04-01914 | PKG-04 | 171543.66 | 153312.94 | Approved | 18 | 2025-06-29 | 2025-08-19 | Station box diaphragm wall water ingress mitigation
VO-PKG-06-00596 | PKG-06 | 23870.25 | 0 | Rejected | 0 | 2025-06-29 | 2025-07-17 | Additional smoke evacuation shafts in underground platforms
VO-PKG-09-01129 | PKG-09 | 344970.67 | 290762.38 | Approved | 6 | 2025-06-29 | 2025-07-24 | Drainage box culvert capacity expansion for 100-year flood event
VO-PKG-03-00623 | PKG-03 | 96304.61 | 88457.06 | Approved | 32 | 2025-06-30 | 2025-07-23 | Viaduct pier foundation redesign due to utility clash
VO-PKG-05-00465 | PKG-05 | 275819.55 | 0 | Pending Approval | 34 | 2025-06-30 |  | HV substation redundancy transformer capacity upgrade
VO-PKG-10-01380 | PKG-10 | 118583.28 | 97003.75 | Approved | 37 | 2025-06-30 | 2025-08-12 | HVAC chilled water pipe rerouting around station concourse
VO-PKG-01-01801 | PKG-01 | 301964.4 | 281806.11 | Approved | 36 | 2025-07-01 | 2025-08-14 | Unforeseen soft ground stabilization and grouting
VO-PKG-02-02762 | PKG-02 | 29061.45 | 0 | Pending Approval | 32 | 2025-07-01 |  | TBM Cutterhead refurbishment and rock fissure sealing
VO-PKG-09-01239 | PKG-09 | 195102.4 | 188179.67 | Approved | 59 | 2025-07-01 | 2025-07-18 | Drainage box culvert capacity expansion for 100-year flood event
VO-PKG-10-02960 | PKG-10 | 311988.4 | 285785.94 | Approved | 44 | 2025-07-01 | 2025-08-26 | HVAC chilled water pipe rerouting around station concourse
VO-PKG-08-02408 | PKG-08 | 47413.97 | 0 | Rejected | 0 | 2025-07-02 | 2025-07-21 | Track vibration damping rubber pads acoustic upgrade
VO-PKG-08-02818 | PKG-08 | 196753.42 | 181410.78 | Approved | 55 | 2025-07-02 | 2025-08-23 | Track vibration damping rubber pads acoustic upgrade
VO-PKG-09-01359 | PKG-09 | 98580.95 | 89252.98 | Approved | 27 | 2025-07-03 | 2025-07-26 | Drainage box culvert capacity expansion for 100-year flood event
VO-PKG-09-02699 | PKG-09 | 326308.6 | 290441.88 | Approved | 59 | 2025-07-03 | 2025-08-23 | Drainage box culvert capacity expansion for 100-year flood event
VO-PKG-01-00351 | PKG-01 | 346829.5 | 326364.91 | Approved | 15 | 2025-07-04 | 2025-07-31 | Unforeseen soft ground stabilization and grouting
VO-PKG-02-01022 | PKG-02 | 323165.79 | 283180.65 | Approved | 41 | 2025-07-04 | 2025-08-10 | TBM Cutterhead refurbishment and rock fissure sealing
VO-PKG-05-00945 | PKG-05 | 220398.38 | 209731.38 | Approved | 22 | 2025-07-04 | 2025-08-16 | HV substation redundancy transformer capacity upgrade
VO-PKG-07-00917 | PKG-07 | 297173.19 | 281994.58 | Approved | 31 | 2025-07-04 | 2025-08-11 | Fiber optic telemetry routing realignment along guideway
VO-PKG-08-00018 | PKG-08 | 35638.32 | 33288.85 | Approved | 43 | 2025-07-04 | 2025-07-30 | Track vibration damping rubber pads acoustic upgrade
VO-PKG-08-00138 | PKG-08 | 179527.73 | 159237.26 | Approved | 10 | 2025-07-04 | 2025-07-27 | Track vibration damping rubber pads acoustic upgrade
VO-PKG-08-01908 | PKG-08 | 77123.31 | 0 | Rejected | 0 | 2025-07-04 | 2025-07-16 | Track vibration damping rubber pads acoustic upgrade
VO-PKG-09-02819 | PKG-09 | 21273.16 | 17258.75 | Approved | 41 | 2025-07-04 | 2025-08-02 | Drainage box culvert capacity expansion for 100-year flood event
VO-PKG-10-00280 | PKG-10 | 208349.44 | 169362.85 | Approved | 7 | 2025-07-04 | 2025-09-01 | HVAC chilled water pipe rerouting around station concourse
VO-PKG-03-02983 | PKG-03 | 149535.37 | 121871.94 | Approved | 44 | 2025-07-05 | 2025-07-22 | Viaduct pier foundation redesign due to utility clash
VO-PKG-03-02993 | PKG-03 | 62321.9 | 55633.12 | Approved | 18 | 2025-07-05 | 2025-08-31 | Viaduct pier foundation redesign due to utility clash
VO-PKG-06-01056 | PKG-06 | 146637.43 | 0 | Pending Approval | 35 | 2025-07-05 |  | Additional smoke evacuation shafts in underground platforms
VO-PKG-09-02379 | PKG-09 | 192488.76 | 0 | Rejected | 0 | 2025-07-05 | 2025-08-08 | Drainage box culvert capacity expansion for 100-year flood event
VO-PKG-09-02469 | PKG-09 | 25030.07 | 20198.54 | Approved | 41 | 2025-07-05 | 2025-08-29 | Drainage box culvert capacity expansion for 100-year flood event
VO-PKG-01-01351 | PKG-01 | 161002.08 | 144411.98 | Approved | 56 | 2025-07-06 | 2025-08-31 | Unforeseen soft ground stabilization and grouting
VO-PKG-07-02427 | PKG-07 | 348098.69 | 305703.05 | Approved | 58 | 2025-07-06 | 2025-08-09 | Fiber optic telemetry routing realignment along guideway
VO-PKG-04-00804 | PKG-04 | 168206.95 | 144670.83 | Approved | 34 | 2025-07-07 | 2025-08-04 | Station box diaphragm wall water ingress mitigation
VO-PKG-04-02504 | PKG-04 | 316720.65 | 291037.69 | Approved | 43 | 2025-07-07 | 2025-09-02 | Station box diaphragm wall water ingress mitigation
VO-PKG-05-02355 | PKG-05 | 206490.44 | 0 | Pending Approval | 6 | 2025-07-07 |  | HV substation redundancy transformer capacity upgrade
VO-PKG-06-00586 | PKG-06 | 150826.75 | 134457.58 | Approved | 11 | 2025-07-07 | 2025-08-03 | Additional smoke evacuation shafts in underground platforms
VO-PKG-02-01332 | PKG-02 | 82605.32 | 0 | Pending Approval | 35 | 2025-07-08 |  | TBM Cutterhead refurbishment and rock fissure sealing
VO-PKG-04-00314 | PKG-04 | 22872.29 | 0 | Pending Approval | 24 | 2025-07-08 |  | Station box diaphragm wall water ingress mitigation
VO-PKG-10-00740 | PKG-10 | 123639.57 | 0 | Pending Approval | 15 | 2025-07-08 |  | HVAC chilled water pipe rerouting around station concourse
VO-PKG-10-02700 | PKG-10 | 15192.29 | 12880.19 | Approved | 48 | 2025-07-08 | 2025-08-13 | HVAC chilled water pipe rerouting around station concourse
VO-PKG-05-00555 | PKG-05 | 156934.21 | 131873.48 | Approved | 15 | 2025-07-09 | 2025-08-08 | HV substation redundancy transformer capacity upgrade
VO-PKG-03-02523 | PKG-03 | 87474.6 | 0 | Pending Approval | 42 | 2025-07-10 |  | Viaduct pier foundation redesign due to utility clash
VO-PKG-04-00464 | PKG-04 | 339515.9 | 0 | Pending Approval | 1 | 2025-07-10 |  | Station box diaphragm wall water ingress mitigation
VO-PKG-06-00526 | PKG-06 | 293560.38 | 0 | Pending Approval | 7 | 2025-07-10 |  | Additional smoke evacuation shafts in underground platforms
VO-PKG-06-01296 | PKG-06 | 295599.96 | 0 | Rejected | 0 | 2025-07-10 | 2025-08-16 | Additional smoke evacuation shafts in underground platforms
VO-PKG-07-01477 | PKG-07 | 176936.93 | 167101.84 | Approved | 44 | 2025-07-10 | 2025-08-30 | Fiber optic telemetry routing realignment along guideway
VO-PKG-09-00249 | PKG-09 | 38927.43 | 37094.52 | Approved | 16 | 2025-07-10 | 2025-07-31 | Drainage box culvert capacity expansion for 100-year flood event
VO-PKG-10-00960 | PKG-10 | 54986.54 | 53438.59 | Approved | 41 | 2025-07-10 | 2025-08-10 | HVAC chilled water pipe rerouting around station concourse
VO-PKG-01-02501 | PKG-01 | 117090.77 | 113560.59 | Approved | 6 | 2025-07-11 | 2025-08-13 | Unforeseen soft ground stabilization and grouting
VO-PKG-04-00204 | PKG-04 | 109605.63 | 97735.85 | Approved | 38 | 2025-07-11 | 2025-08-23 | Station box diaphragm wall water ingress mitigation
VO-PKG-05-02325 | PKG-05 | 124365.7 | 0 | Rejected | 0 | 2025-07-11 | 2025-08-16 | HV substation redundancy transformer capacity upgrade
VO-PKG-01-02151 | PKG-01 | 104170.79 | 0 | Pending Approval | 29 | 2025-07-12 |  | Unforeseen soft ground stabilization and grouting
VO-PKG-03-01303 | PKG-03 | 245285.09 | 218562.28 | Approved | 45 | 2025-07-13 | 2025-08-11 | Viaduct pier foundation redesign due to utility clash
VO-PKG-08-01628 | PKG-08 | 290890.57 | 0 | Pending Approval | 6 | 2025-07-13 |  | Track vibration damping rubber pads acoustic upgrade
VO-PKG-01-00991 | PKG-01 | 148362.99 | 139297.95 | Approved | 38 | 2025-07-15 | 2025-08-25 | Unforeseen soft ground stabilization and grouting
VO-PKG-01-01961 | PKG-01 | 137780.56 | 0 | Pending Approval | 22 | 2025-07-15 |  | Unforeseen soft ground stabilization and grouting
VO-PKG-08-00038 | PKG-08 | 152427.46 | 127397.77 | Approved | 47 | 2025-07-15 | 2025-09-05 | Track vibration damping rubber pads acoustic upgrade
VO-PKG-08-00158 | PKG-08 | 234970.13 | 194064.19 | Approved | 18 | 2025-07-15 | 2025-08-24 | Track vibration damping rubber pads acoustic upgrade
VO-PKG-08-02348 | PKG-08 | 141759.36 | 129073.72 | Approved | 26 | 2025-07-15 | 2025-08-14 | Track vibration damping rubber pads acoustic upgrade
VO-PKG-04-02434 | PKG-04 | 76675.41 | 63790.77 | Approved | 13 | 2025-07-16 | 2025-08-08 | Station box diaphragm wall water ingress mitigation
VO-PKG-05-00325 | PKG-05 | 84854.33 | 68462.76 | Approved | 51 | 2025-07-16 | 2025-09-04 | HV substation redundancy transformer capacity upgrade
VO-PKG-07-01367 | PKG-07 | 237375.96 | 0 | Rejected | 0 | 2025-07-16 | 2025-08-11 | Fiber optic telemetry routing realignment along guideway
VO-PKG-10-02710 | PKG-10 | 184125.44 | 158360.47 | Approved | 27 | 2025-07-16 | 2025-08-10 | HVAC chilled water pipe rerouting around station concourse
VO-PKG-03-00033 | PKG-03 | 218644.47 | 194601.35 | Approved | 53 | 2025-07-17 | 2025-08-28 | Viaduct pier foundation redesign due to utility clash
VO-PKG-06-02516 | PKG-06 | 335801 | 308740.27 | Approved | 18 | 2025-07-17 | 2025-08-26 | Additional smoke evacuation shafts in underground platforms
VO-PKG-08-01808 | PKG-08 | 285666 | 258216 | Approved | 39 | 2025-07-17 | 2025-08-14 | Track vibration damping rubber pads acoustic upgrade
VO-PKG-09-02009 | PKG-09 | 36883.55 | 32430.34 | Approved | 57 | 2025-07-17 | 2025-08-03 | Drainage box culvert capacity expansion for 100-year flood event
VO-PKG-01-00401 | PKG-01 | 70763.63 | 68732.27 | Approved | 32 | 2025-07-18 | 2025-09-01 | Unforeseen soft ground stabilization and grouting
VO-PKG-01-00711 | PKG-01 | 277245.58 | 221907.34 | Approved | 9 | 2025-07-18 | 2025-08-21 | Unforeseen soft ground stabilization and grouting
VO-PKG-02-02462 | PKG-02 | 105105.63 | 94624.18 | Approved | 7 | 2025-07-18 | 2025-08-09 | TBM Cutterhead refurbishment and rock fissure sealing
VO-PKG-03-00693 | PKG-03 | 280274.01 | 248054.09 | Approved | 29 | 2025-07-18 | 2025-08-21 | Viaduct pier foundation redesign due to utility clash
VO-PKG-04-00484 | PKG-04 | 268799.39 | 234256.37 | Approved | 50 | 2025-07-18 | 2025-09-08 | Station box diaphragm wall water ingress mitigation
VO-PKG-04-02934 | PKG-04 | 171155.43 | 167293.75 | Approved | 21 | 2025-07-18 | 2025-08-13 | Station box diaphragm wall water ingress mitigation
VO-PKG-05-01695 | PKG-05 | 186001.76 | 0 | Rejected | 0 | 2025-07-18 | 2025-08-06 | HV substation redundancy transformer capacity upgrade
VO-PKG-06-01816 | PKG-06 | 32190.69 | 26408.84 | Approved | 50 | 2025-07-18 | 2025-08-03 | Additional smoke evacuation shafts in underground platforms
VO-PKG-07-01667 | PKG-07 | 113133.92 | 105704.2 | Approved | 26 | 2025-07-18 | 2025-09-14 | Fiber optic telemetry routing realignment along guideway
VO-PKG-03-00003 | PKG-03 | 328110.15 | 276889.25 | Approved | 18 | 2025-07-19 | 2025-09-15 | Viaduct pier foundation redesign due to utility clash
VO-PKG-08-00598 | PKG-08 | 37502.57 | 35539.81 | Approved | 7 | 2025-07-19 | 2025-09-05 | Track vibration damping rubber pads acoustic upgrade
VO-PKG-10-00380 | PKG-10 | 73946.12 | 60713.89 | Approved | 25 | 2025-07-19 | 2025-08-09 | HVAC chilled water pipe rerouting around station concourse
VO-PKG-10-01770 | PKG-10 | 113287.96 | 98584.19 | Approved | 55 | 2025-07-19 | 2025-08-13 | HVAC chilled water pipe rerouting around station concourse
VO-PKG-04-02104 | PKG-04 | 105459.51 | 0 | Rejected | 0 | 2025-07-20 | 2025-08-03 | Station box diaphragm wall water ingress mitigation
VO-PKG-09-02019 | PKG-09 | 128817.78 | 0 | Rejected | 0 | 2025-07-20 | 2025-08-16 | Drainage box culvert capacity expansion for 100-year flood event
VO-PKG-07-00027 | PKG-07 | 128822.83 | 106536.78 | Approved | 44 | 2025-07-21 | 2025-09-07 | Fiber optic telemetry routing realignment along guideway
VO-PKG-09-02849 | PKG-09 | 344771.98 | 0 | Pending Approval | 33 | 2025-07-21 |  | Drainage box culvert capacity expansion for 100-year flood event
VO-PKG-10-00240 | PKG-10 | 183610 | 154722.55 | Approved | 22 | 2025-07-21 | 2025-08-18 | HVAC chilled water pipe rerouting around station concourse
VO-PKG-02-00672 | PKG-02 | 270605.08 | 234678.12 | Approved | 35 | 2025-07-22 | 2025-08-20 | TBM Cutterhead refurbishment and rock fissure sealing
VO-PKG-04-01644 | PKG-04 | 218214.15 | 208672.36 | Approved | 40 | 2025-07-22 | 2025-08-23 | Station box diaphragm wall water ingress mitigation
VO-PKG-05-01135 | PKG-05 | 311175.11 | 256056.53 | Approved | 44 | 2025-07-22 | 2025-08-26 | HV substation redundancy transformer capacity upgrade
VO-PKG-06-00006 | PKG-06 | 203424.22 | 193455.61 | Approved | 37 | 2025-07-22 | 2025-09-06 | Additional smoke evacuation shafts in underground platforms
VO-PKG-06-02686 | PKG-06 | 345963.12 | 296776.82 | Approved | 21 | 2025-07-22 | 2025-09-10 | Additional smoke evacuation shafts in underground platforms
VO-PKG-02-01532 | PKG-02 | 91152.06 | 0 | Rejected | 0 | 2025-07-23 | 2025-08-09 | TBM Cutterhead refurbishment and rock fissure sealing
VO-PKG-06-00816 | PKG-06 | 100672.31 | 92373.55 | Approved | 26 | 2025-07-23 | 2025-09-19 | Additional smoke evacuation shafts in underground platforms
VO-PKG-02-01882 | PKG-02 | 204828.76 | 0 | Pending Approval | 24 | 2025-07-24 |  | TBM Cutterhead refurbishment and rock fissure sealing
VO-PKG-02-00602 | PKG-02 | 323051.11 | 279727.53 | Approved | 12 | 2025-07-25 | 2025-09-05 | TBM Cutterhead refurbishment and rock fissure sealing
VO-PKG-06-02126 | PKG-06 | 247203.73 | 227955.79 | Approved | 12 | 2025-07-25 | 2025-08-18 | Additional smoke evacuation shafts in underground platforms
VO-PKG-04-01884 | PKG-04 | 268019.58 | 244694.12 | Approved | 38 | 2025-07-26 | 2025-09-11 | Station box diaphragm wall water ingress mitigation
VO-PKG-05-00835 | PKG-05 | 322510.79 | 0 | Rejected | 0 | 2025-07-26 | 2025-08-24 | HV substation redundancy transformer capacity upgrade
VO-PKG-06-00606 | PKG-06 | 172946.98 | 140033.45 | Approved | 26 | 2025-07-26 | 2025-08-15 | Additional smoke evacuation shafts in underground platforms
VO-PKG-07-00647 | PKG-07 | 148774.41 | 0 | Pending Approval | 33 | 2025-07-26 |  | Fiber optic telemetry routing realignment along guideway
VO-PKG-07-01587 | PKG-07 | 129551.2 | 116755.55 | Approved | 21 | 2025-07-26 | 2025-09-12 | Fiber optic telemetry routing realignment along guideway
VO-PKG-07-02257 | PKG-07 | 223416.32 | 0 | Pending Approval | 13 | 2025-07-26 |  | Fiber optic telemetry routing realignment along guideway
VO-PKG-09-02719 | PKG-09 | 65812.59 | 58603.85 | Approved | 45 | 2025-07-26 | 2025-08-11 | Drainage box culvert capacity expansion for 100-year flood event
VO-PKG-08-00088 | PKG-08 | 306517.18 | 261510.32 | Approved | 37 | 2025-07-27 | 2025-09-07 | Track vibration damping rubber pads acoustic upgrade
VO-PKG-03-01933 | PKG-03 | 320113.58 | 0 | Rejected | 0 | 2025-07-28 | 2025-09-04 | Viaduct pier foundation redesign due to utility clash
VO-PKG-04-00184 | PKG-04 | 88196.59 | 84765.61 | Approved | 37 | 2025-07-28 | 2025-08-14 | Station box diaphragm wall water ingress mitigation
VO-PKG-07-02267 | PKG-07 | 174846.88 | 0 | Pending Approval | 30 | 2025-07-28 |  | Fiber optic telemetry routing realignment along guideway
VO-PKG-10-02820 | PKG-10 | 102603.08 | 0 | Pending Approval | 10 | 2025-07-28 |  | HVAC chilled water pipe rerouting around station concourse
VO-PKG-03-00053 | PKG-03 | 238337.68 | 222990.26 | Approved | 57 | 2025-07-29 | 2025-09-03 | Viaduct pier foundation redesign due to utility clash
VO-PKG-09-01309 | PKG-09 | 238346.7 | 0 | Pending Approval | 24 | 2025-07-29 |  | Drainage box culvert capacity expansion for 100-year flood event
VO-PKG-09-02069 | PKG-09 | 312859.2 | 282498.84 | Approved | 21 | 2025-07-29 | 2025-09-21 | Drainage box culvert capacity expansion for 100-year flood event
VO-PKG-02-02172 | PKG-02 | 42191.87 | 40103.21 | Approved | 47 | 2025-07-30 | 2025-09-25 | TBM Cutterhead refurbishment and rock fissure sealing
VO-PKG-02-02432 | PKG-02 | 158289.47 | 146704.3 | Approved | 59 | 2025-07-30 | 2025-09-12 | TBM Cutterhead refurbishment and rock fissure sealing
VO-PKG-03-02343 | PKG-03 | 105243.46 | 95415.53 | Approved | 30 | 2025-07-30 | 2025-09-05 | Viaduct pier foundation redesign due to utility clash
VO-PKG-04-02944 | PKG-04 | 22542.38 | 20406.54 | Approved | 22 | 2025-07-30 | 2025-08-25 | Station box diaphragm wall water ingress mitigation
VO-PKG-06-00056 | PKG-06 | 123112.52 | 108376.96 | Approved | 35 | 2025-07-30 | 2025-08-16 | Additional smoke evacuation shafts in underground platforms
VO-PKG-06-01336 | PKG-06 | 255092.38 | 0 | Pending Approval | 38 | 2025-07-30 |  | Additional smoke evacuation shafts in underground platforms
VO-PKG-06-02056 | PKG-06 | 45210.54 | 0 | Pending Approval | 43 | 2025-07-30 |  | Additional smoke evacuation shafts in underground platforms
VO-PKG-07-00517 | PKG-07 | 139648.59 | 136185.66 | Approved | 36 | 2025-07-30 | 2025-09-19 | Fiber optic telemetry routing realignment along guideway
VO-PKG-07-02447 | PKG-07 | 279158.46 | 240068.29 | Approved | 35 | 2025-07-30 | 2025-09-04 | Fiber optic telemetry routing realignment along guideway
VO-PKG-08-00308 | PKG-08 | 229841.96 | 185186.33 | Approved | 25 | 2025-07-30 | 2025-09-15 | Track vibration damping rubber pads acoustic upgrade
VO-PKG-09-01509 | PKG-09 | 222425.98 | 203088.9 | Approved | 15 | 2025-07-30 | 2025-09-25 | Drainage box culvert capacity expansion for 100-year flood event
VO-PKG-04-01924 | PKG-04 | 26447.75 | 0 | Pending Approval | 13 | 2025-07-31 |  | Station box diaphragm wall water ingress mitigation
VO-PKG-07-00047 | PKG-07 | 202694.89 | 0 | Rejected | 0 | 2025-07-31 | 2025-08-12 | Fiber optic telemetry routing realignment along guideway
VO-PKG-02-02832 | PKG-02 | 242734.08 | 236702.69 | Approved | 32 | 2025-08-01 | 2025-09-04 | TBM Cutterhead refurbishment and rock fissure sealing
VO-PKG-03-02143 | PKG-03 | 75144.36 | 63757.78 | Approved | 23 | 2025-08-01 | 2025-09-13 | Viaduct pier foundation redesign due to utility clash
VO-PKG-04-02114 | PKG-04 | 63558.03 | 58784.28 | Approved | 34 | 2025-08-01 | 2025-09-08 | Station box diaphragm wall water ingress mitigation
VO-PKG-06-00086 | PKG-06 | 135634.65 | 0 | Pending Approval | 6 | 2025-08-01 |  | Additional smoke evacuation shafts in underground platforms
VO-PKG-01-00821 | PKG-01 | 253034.94 | 0 | Pending Approval | 36 | 2025-08-02 |  | Unforeseen soft ground stabilization and grouting
VO-PKG-04-02684 | PKG-04 | 311546.84 | 289464.93 | Approved | 24 | 2025-08-02 | 2025-08-18 | Station box diaphragm wall water ingress mitigation
VO-PKG-05-00745 | PKG-05 | 28638.18 | 24310.98 | Approved | 58 | 2025-08-02 | 2025-08-23 | HV substation redundancy transformer capacity upgrade
VO-PKG-09-02149 | PKG-09 | 302533.22 | 296307.02 | Approved | 7 | 2025-08-02 | 2025-08-17 | Drainage box culvert capacity expansion for 100-year flood event
VO-PKG-01-00081 | PKG-01 | 119227.94 | 112631.81 | Approved | 24 | 2025-08-03 | 2025-09-02 | Unforeseen soft ground stabilization and grouting
VO-PKG-01-01331 | PKG-01 | 52482.93 | 43198.32 | Approved | 42 | 2025-08-03 | 2025-09-22 | Unforeseen soft ground stabilization and grouting
VO-PKG-05-02865 | PKG-05 | 198018.3 | 169138.23 | Approved | 39 | 2025-08-03 | 2025-09-27 | HV substation redundancy transformer capacity upgrade
VO-PKG-06-02716 | PKG-06 | 23883.13 | 0 | Pending Approval | 17 | 2025-08-03 |  | Additional smoke evacuation shafts in underground platforms
VO-PKG-02-00592 | PKG-02 | 73135.63 | 0 | Rejected | 0 | 2025-08-04 | 2025-08-31 | TBM Cutterhead refurbishment and rock fissure sealing
VO-PKG-02-01182 | PKG-02 | 298145.22 | 267639.13 | Approved | 6 | 2025-08-04 | 2025-08-23 | TBM Cutterhead refurbishment and rock fissure sealing
VO-PKG-09-00769 | PKG-09 | 65115.69 | 58322.6 | Approved | 44 | 2025-08-04 | 2025-10-02 | Drainage box culvert capacity expansion for 100-year flood event
VO-PKG-09-01269 | PKG-09 | 335365.52 | 298387.36 | Approved | 22 | 2025-08-04 | 2025-09-07 | Drainage box culvert capacity expansion for 100-year flood event
VO-PKG-01-01061 | PKG-01 | 43204.12 | 34949.63 | Approved | 24 | 2025-08-05 | 2025-09-11 | Unforeseen soft ground stabilization and grouting
VO-PKG-02-00572 | PKG-02 | 280560.9 | 241592.23 | Approved | 17 | 2025-08-05 | 2025-09-10 | TBM Cutterhead refurbishment and rock fissure sealing
VO-PKG-08-01158 | PKG-08 | 163534.17 | 133015.91 | Approved | 15 | 2025-08-05 | 2025-08-20 | Track vibration damping rubber pads acoustic upgrade
VO-PKG-08-02078 | PKG-08 | 339793.77 | 0 | Pending Approval | 44 | 2025-08-05 |  | Track vibration damping rubber pads acoustic upgrade
VO-PKG-01-02491 | PKG-01 | 234565.66 | 218137.96 | Approved | 48 | 2025-08-06 | 2025-09-21 | Unforeseen soft ground stabilization and grouting
VO-PKG-07-00327 | PKG-07 | 64748.88 | 60475.44 | Approved | 14 | 2025-08-06 | 2025-08-25 | Fiber optic telemetry routing realignment along guideway
VO-PKG-03-00043 | PKG-03 | 201877.63 | 182641.83 | Approved | 47 | 2025-08-07 | 2025-08-29 | Viaduct pier foundation redesign due to utility clash
VO-PKG-04-00754 | PKG-04 | 156601.16 | 149700.93 | Approved | 46 | 2025-08-07 | 2025-09-05 | Station box diaphragm wall water ingress mitigation
VO-PKG-06-00426 | PKG-06 | 28894.89 | 25382.38 | Approved | 8 | 2025-08-07 | 2025-09-11 | Additional smoke evacuation shafts in underground platforms
VO-PKG-03-02663 | PKG-03 | 220962.15 | 185064.79 | Approved | 23 | 2025-08-08 | 2025-09-16 | Viaduct pier foundation redesign due to utility clash
VO-PKG-04-00684 | PKG-04 | 147828.25 | 0 | Pending Approval | 27 | 2025-08-09 |  | Station box diaphragm wall water ingress mitigation
VO-PKG-04-01274 | PKG-04 | 348756.68 | 0 | Pending Approval | 25 | 2025-08-09 |  | Station box diaphragm wall water ingress mitigation
VO-PKG-09-02399 | PKG-09 | 89847.04 | 0 | Pending Approval | 40 | 2025-08-09 |  | Drainage box culvert capacity expansion for 100-year flood event
VO-PKG-10-00560 | PKG-10 | 169678.18 | 142969.77 | Approved | 59 | 2025-08-09 | 2025-09-01 | HVAC chilled water pipe rerouting around station concourse
VO-PKG-01-02751 | PKG-01 | 287062.54 | 265885.62 | Approved | 45 | 2025-08-10 | 2025-08-29 | Unforeseen soft ground stabilization and grouting
VO-PKG-07-01567 | PKG-07 | 41951.1 | 0 | Pending Approval | 7 | 2025-08-10 |  | Fiber optic telemetry routing realignment along guideway
VO-PKG-08-01608 | PKG-08 | 104714.99 | 0 | Pending Approval | 23 | 2025-08-10 |  | Track vibration damping rubber pads acoustic upgrade
VO-PKG-09-02789 | PKG-09 | 292153.03 | 0 | Rejected | 0 | 2025-08-10 | 2025-08-31 | Drainage box culvert capacity expansion for 100-year flood event
VO-PKG-02-00012 | PKG-02 | 268505.54 | 237714.57 | Approved | 33 | 2025-08-11 | 2025-09-29 | TBM Cutterhead refurbishment and rock fissure sealing
VO-PKG-06-01126 | PKG-06 | 349467.77 | 336508.45 | Approved | 29 | 2025-08-11 | 2025-09-10 | Additional smoke evacuation shafts in underground platforms
VO-PKG-08-00898 | PKG-08 | 282946.88 | 273878.7 | Approved | 16 | 2025-08-11 | 2025-10-08 | Track vibration damping rubber pads acoustic upgrade
VO-PKG-08-02608 | PKG-08 | 291144.71 | 282948.16 | Approved | 12 | 2025-08-11 | 2025-10-09 | Track vibration damping rubber pads acoustic upgrade
VO-PKG-08-02828 | PKG-08 | 257456.75 | 216148.08 | Approved | 37 | 2025-08-11 | 2025-09-05 | Track vibration damping rubber pads acoustic upgrade
VO-PKG-10-02930 | PKG-10 | 38092.49 | 31018.31 | Approved | 20 | 2025-08-11 | 2025-09-21 | HVAC chilled water pipe rerouting around station concourse
VO-PKG-01-02631 | PKG-01 | 105166.22 | 0 | Pending Approval | 33 | 2025-08-12 |  | Unforeseen soft ground stabilization and grouting
VO-PKG-02-02922 | PKG-02 | 99145.29 | 0 | Rejected | 0 | 2025-08-12 | 2025-09-03 | TBM Cutterhead refurbishment and rock fissure sealing
VO-PKG-01-02161 | PKG-01 | 278730.52 | 267868.87 | Approved | 19 | 2025-08-13 | 2025-09-03 | Unforeseen soft ground stabilization and grouting
VO-PKG-05-01795 | PKG-05 | 274585.81 | 234109.01 | Approved | 38 | 2025-08-13 | 2025-09-15 | HV substation redundancy transformer capacity upgrade
VO-PKG-06-02996 | PKG-06 | 302284.92 | 260603.66 | Approved | 39 | 2025-08-14 | 2025-10-08 | Additional smoke evacuation shafts in underground platforms
VO-PKG-09-02169 | PKG-09 | 45807.12 | 0 | Rejected | 0 | 2025-08-14 | 2025-08-27 | Drainage box culvert capacity expansion for 100-year flood event
VO-PKG-03-00133 | PKG-03 | 152201.97 | 136488.98 | Approved | 48 | 2025-08-15 | 2025-09-07 | Viaduct pier foundation redesign due to utility clash
VO-PKG-10-02880 | PKG-10 | 337448.12 | 298850.78 | Approved | 49 | 2025-08-15 | 2025-09-05 | HVAC chilled water pipe rerouting around station concourse
VO-PKG-01-00831 | PKG-01 | 84115.66 | 0 | Pending Approval | 15 | 2025-08-16 |  | Unforeseen soft ground stabilization and grouting
VO-PKG-05-01455 | PKG-05 | 35712.99 | 0 | Pending Approval | 33 | 2025-08-16 |  | HV substation redundancy transformer capacity upgrade
VO-PKG-06-02256 | PKG-06 | 126953.57 | 111444.61 | Approved | 17 | 2025-08-16 | 2025-10-14 | Additional smoke evacuation shafts in underground platforms
VO-PKG-07-02747 | PKG-07 | 57140.39 | 49380.64 | Approved | 24 | 2025-08-16 | 2025-09-24 | Fiber optic telemetry routing realignment along guideway
VO-PKG-10-01760 | PKG-10 | 202759.37 | 183432.33 | Approved | 45 | 2025-08-16 | 2025-09-27 | HVAC chilled water pipe rerouting around station concourse
VO-PKG-01-02421 | PKG-01 | 202265.15 | 186292.96 | Approved | 58 | 2025-08-17 | 2025-09-07 | Unforeseen soft ground stabilization and grouting
VO-PKG-04-01374 | PKG-04 | 324772.64 | 277786.93 | Approved | 49 | 2025-08-18 | 2025-09-19 | Station box diaphragm wall water ingress mitigation
VO-PKG-04-02124 | PKG-04 | 49098.67 | 44366.28 | Approved | 12 | 2025-08-18 | 2025-09-15 | Station box diaphragm wall water ingress mitigation
VO-PKG-06-02106 | PKG-06 | 82796.09 | 0 | Pending Approval | 9 | 2025-08-18 |  | Additional smoke evacuation shafts in underground platforms
VO-PKG-09-01009 | PKG-09 | 62581.66 | 55240.66 | Approved | 32 | 2025-08-18 | 2025-09-28 | Drainage box culvert capacity expansion for 100-year flood event
VO-PKG-04-02654 | PKG-04 | 236703.39 | 0 | Pending Approval | 24 | 2025-08-19 |  | Station box diaphragm wall water ingress mitigation
VO-PKG-10-02670 | PKG-10 | 46336.07 | 37465.89 | Approved | 31 | 2025-08-19 | 2025-09-15 | HVAC chilled water pipe rerouting around station concourse
VO-PKG-01-01681 | PKG-01 | 244311.8 | 233345.42 | Approved | 53 | 2025-08-20 | 2025-09-08 | Unforeseen soft ground stabilization and grouting
VO-PKG-01-02351 | PKG-01 | 284426.98 | 0 | Pending Approval | 7 | 2025-08-21 |  | Unforeseen soft ground stabilization and grouting
VO-PKG-01-02611 | PKG-01 | 134455.77 | 0 | Pending Approval | 11 | 2025-08-21 |  | Unforeseen soft ground stabilization and grouting
VO-PKG-08-01188 | PKG-08 | 174979.29 | 163461.68 | Approved | 25 | 2025-08-21 | 2025-09-07 | Track vibration damping rubber pads acoustic upgrade
VO-PKG-01-00391 | PKG-01 | 194747.46 | 162900.63 | Approved | 54 | 2025-08-23 | 2025-10-20 | Unforeseen soft ground stabilization and grouting
VO-PKG-02-02362 | PKG-02 | 171050.64 | 138003.03 | Approved | 58 | 2025-08-23 | 2025-09-16 | TBM Cutterhead refurbishment and rock fissure sealing
VO-PKG-04-01204 | PKG-04 | 116794.13 | 0 | Rejected | 0 | 2025-08-23 | 2025-09-15 | Station box diaphragm wall water ingress mitigation
VO-PKG-04-01264 | PKG-04 | 25558.11 | 24061.68 | Approved | 30 | 2025-08-23 | 2025-09-28 | Station box diaphragm wall water ingress mitigation
VO-PKG-04-01344 | PKG-04 | 173263.84 | 165995.83 | Approved | 47 | 2025-08-23 | 2025-10-06 | Station box diaphragm wall water ingress mitigation
VO-PKG-09-02899 | PKG-09 | 282212.05 | 0 | Rejected | 0 | 2025-08-23 | 2025-09-18 | Drainage box culvert capacity expansion for 100-year flood event
VO-PKG-10-02050 | PKG-10 | 342047.16 | 0 | Pending Approval | 15 | 2025-08-23 |  | HVAC chilled water pipe rerouting around station concourse
VO-PKG-02-01042 | PKG-02 | 309683.35 | 255328.95 | Approved | 39 | 2025-08-24 | 2025-10-06 | TBM Cutterhead refurbishment and rock fissure sealing
VO-PKG-03-01673 | PKG-03 | 116447.9 | 108690.74 | Approved | 15 | 2025-08-24 | 2025-09-22 | Viaduct pier foundation redesign due to utility clash
VO-PKG-04-00994 | PKG-04 | 123832.84 | 0 | Rejected | 0 | 2025-08-24 | 2025-09-29 | Station box diaphragm wall water ingress mitigation
VO-PKG-04-01714 | PKG-04 | 182244 | 151899.67 | Approved | 25 | 2025-08-24 | 2025-10-17 | Station box diaphragm wall water ingress mitigation
VO-PKG-03-01343 | PKG-03 | 174601.73 | 144017.96 | Approved | 57 | 2025-08-25 | 2025-10-16 | Viaduct pier foundation redesign due to utility clash
VO-PKG-05-00955 | PKG-05 | 171792.63 | 162640.99 | Approved | 6 | 2025-08-25 | 2025-10-02 | HV substation redundancy transformer capacity upgrade
VO-PKG-05-01395 | PKG-05 | 277927.62 | 261765.74 | Approved | 59 | 2025-08-25 | 2025-09-21 | HV substation redundancy transformer capacity upgrade
VO-PKG-06-01766 | PKG-06 | 180085.14 | 0 | Pending Approval | 10 | 2025-08-25 |  | Additional smoke evacuation shafts in underground platforms
VO-PKG-08-01288 | PKG-08 | 59189.85 | 0 | Pending Approval | 11 | 2025-08-25 |  | Track vibration damping rubber pads acoustic upgrade
VO-PKG-06-00746 | PKG-06 | 47871.78 | 43832.79 | Approved | 6 | 2025-08-26 | 2025-10-16 | Additional smoke evacuation shafts in underground platforms
VO-PKG-06-02116 | PKG-06 | 344774.17 | 321689.97 | Approved | 44 | 2025-08-26 | 2025-09-15 | Additional smoke evacuation shafts in underground platforms
VO-PKG-06-02476 | PKG-06 | 17502.68 | 0 | Pending Approval | 17 | 2025-08-26 |  | Additional smoke evacuation shafts in underground platforms
VO-PKG-08-01148 | PKG-08 | 219976.03 | 0 | Pending Approval | 35 | 2025-08-26 |  | Track vibration damping rubber pads acoustic upgrade
VO-PKG-08-01498 | PKG-08 | 39307.21 | 38189.6 | Approved | 45 | 2025-08-26 | 2025-10-09 | Track vibration damping rubber pads acoustic upgrade
VO-PKG-09-00449 | PKG-09 | 27432.32 | 22737.67 | Approved | 52 | 2025-08-26 | 2025-09-29 | Drainage box culvert capacity expansion for 100-year flood event
VO-PKG-09-00779 | PKG-09 | 266244.27 | 0 | Rejected | 0 | 2025-08-26 | 2025-09-07 | Drainage box culvert capacity expansion for 100-year flood event
VO-PKG-10-02120 | PKG-10 | 200027.78 | 180113.99 | Approved | 14 | 2025-08-26 | 2025-09-27 | HVAC chilled water pipe rerouting around station concourse
VO-PKG-05-00725 | PKG-05 | 254697.4 | 226630.13 | Approved | 42 | 2025-08-27 | 2025-10-21 | HV substation redundancy transformer capacity upgrade
VO-PKG-06-01366 | PKG-06 | 284500.85 | 0 | Pending Approval | 32 | 2025-08-27 |  | Additional smoke evacuation shafts in underground platforms
VO-PKG-08-00678 | PKG-08 | 253180.16 | 204681.17 | Approved | 7 | 2025-08-27 | 2025-10-08 | Track vibration damping rubber pads acoustic upgrade
VO-PKG-05-02775 | PKG-05 | 217984.12 | 175536.78 | Approved | 5 | 2025-08-28 | 2025-09-20 | HV substation redundancy transformer capacity upgrade
VO-PKG-07-00387 | PKG-07 | 344691.18 | 0 | Pending Approval | 28 | 2025-08-28 |  | Fiber optic telemetry routing realignment along guideway
VO-PKG-09-00929 | PKG-09 | 334868.26 | 304482.31 | Approved | 28 | 2025-08-28 | 2025-09-25 | Drainage box culvert capacity expansion for 100-year flood event
VO-PKG-10-01800 | PKG-10 | 303335.56 | 263876.48 | Approved | 14 | 2025-08-28 | 2025-10-15 | HVAC chilled water pipe rerouting around station concourse
VO-PKG-07-02077 | PKG-07 | 37600.66 | 35848.84 | Approved | 25 | 2025-08-29 | 2025-09-16 | Fiber optic telemetry routing realignment along guideway
VO-PKG-09-00029 | PKG-09 | 335402.86 | 281806.48 | Approved | 36 | 2025-08-29 | 2025-09-14 | Drainage box culvert capacity expansion for 100-year flood event
VO-PKG-09-01379 | PKG-09 | 241796.99 | 223415.97 | Approved | 12 | 2025-08-29 | 2025-09-25 | Drainage box culvert capacity expansion for 100-year flood event
VO-PKG-02-00732 | PKG-02 | 94739.48 | 0 | Pending Approval | 8 | 2025-08-30 |  | TBM Cutterhead refurbishment and rock fissure sealing
VO-PKG-03-01863 | PKG-03 | 329660.66 | 0 | Pending Approval | 23 | 2025-08-30 |  | Viaduct pier foundation redesign due to utility clash
VO-PKG-04-00434 | PKG-04 | 141923.32 | 121934.26 | Approved | 45 | 2025-08-30 | 2025-09-14 | Station box diaphragm wall water ingress mitigation
VO-PKG-05-01045 | PKG-05 | 95893.03 | 0 | Pending Approval | 22 | 2025-08-30 |  | HV substation redundancy transformer capacity upgrade
VO-PKG-07-01847 | PKG-07 | 62047.46 | 0 | Rejected | 0 | 2025-08-30 | 2025-09-14 | Fiber optic telemetry routing realignment along guideway
VO-PKG-10-01980 | PKG-10 | 89445.91 | 77746.72 | Approved | 38 | 2025-08-30 | 2025-09-22 | HVAC chilled water pipe rerouting around station concourse
VO-PKG-03-00663 | PKG-03 | 135606.57 | 131628.08 | Approved | 13 | 2025-08-31 | 2025-10-27 | Viaduct pier foundation redesign due to utility clash
VO-PKG-02-01422 | PKG-02 | 143127.2 | 122001.95 | Approved | 50 | 2025-09-01 | 2025-09-16 | TBM Cutterhead refurbishment and rock fissure sealing
VO-PKG-05-00915 | PKG-05 | 31434.25 | 0 | Rejected | 0 | 2025-09-01 | 2025-09-16 | HV substation redundancy transformer capacity upgrade
VO-PKG-06-01236 | PKG-06 | 308354.78 | 271373.12 | Approved | 39 | 2025-09-01 | 2025-10-09 | Additional smoke evacuation shafts in underground platforms
VO-PKG-06-01266 | PKG-06 | 114605.77 | 109346.98 | Approved | 12 | 2025-09-01 | 2025-10-07 | Additional smoke evacuation shafts in underground platforms
VO-PKG-07-00067 | PKG-07 | 70210.9 | 60553.16 | Approved | 20 | 2025-09-01 | 2025-10-02 | Fiber optic telemetry routing realignment along guideway
VO-PKG-07-01447 | PKG-07 | 120860.79 | 101606.18 | Approved | 14 | 2025-09-02 | 2025-10-31 | Fiber optic telemetry routing realignment along guideway
VO-PKG-08-01468 | PKG-08 | 182652.64 | 171591.57 | Approved | 26 | 2025-09-02 | 2025-10-22 | Track vibration damping rubber pads acoustic upgrade
VO-PKG-07-01307 | PKG-07 | 153686.45 | 0 | Pending Approval | 43 | 2025-09-03 |  | Fiber optic telemetry routing realignment along guideway
VO-PKG-07-02247 | PKG-07 | 167516.31 | 150027.39 | Approved | 29 | 2025-09-03 | 2025-09-22 | Fiber optic telemetry routing realignment along guideway
VO-PKG-05-00785 | PKG-05 | 80564.84 | 68702.84 | Approved | 34 | 2025-09-04 | 2025-10-01 | HV substation redundancy transformer capacity upgrade
VO-PKG-08-00378 | PKG-08 | 116002.42 | 99169.32 | Approved | 5 | 2025-09-04 | 2025-10-11 | Track vibration damping rubber pads acoustic upgrade
VO-PKG-10-01430 | PKG-10 | 137382.67 | 132777.17 | Approved | 42 | 2025-09-04 | 2025-09-25 | HVAC chilled water pipe rerouting around station concourse
VO-PKG-05-00545 | PKG-05 | 289671.31 | 264605.17 | Approved | 20 | 2025-09-05 | 2025-10-06 | HV substation redundancy transformer capacity upgrade
VO-PKG-02-00772 | PKG-02 | 153910.68 | 0 | Pending Approval | 24 | 2025-09-06 |  | TBM Cutterhead refurbishment and rock fissure sealing
VO-PKG-06-01636 | PKG-06 | 79590.99 | 71749.63 | Approved | 39 | 2025-09-06 | 2025-10-01 | Additional smoke evacuation shafts in underground platforms
VO-PKG-07-02097 | PKG-07 | 289640.25 | 257967.51 | Approved | 27 | 2025-09-06 | 2025-10-26 | Fiber optic telemetry routing realignment along guideway
VO-PKG-09-00159 | PKG-09 | 322899.19 | 276353.88 | Approved | 20 | 2025-09-06 | 2025-09-28 | Drainage box culvert capacity expansion for 100-year flood event
VO-PKG-10-01140 | PKG-10 | 72671.73 | 0 | Rejected | 0 | 2025-09-06 | 2025-09-29 | HVAC chilled water pipe rerouting around station concourse
VO-PKG-03-02973 | PKG-03 | 157480.03 | 0 | Pending Approval | 35 | 2025-09-07 |  | Viaduct pier foundation redesign due to utility clash
VO-PKG-05-01215 | PKG-05 | 150303.58 | 123957.69 | Approved | 43 | 2025-09-07 | 2025-10-29 | HV substation redundancy transformer capacity upgrade
VO-PKG-05-02085 | PKG-05 | 321899.41 | 0 | Rejected | 0 | 2025-09-07 | 2025-10-17 | HV substation redundancy transformer capacity upgrade
VO-PKG-09-00589 | PKG-09 | 228265.68 | 0 | Pending Approval | 12 | 2025-09-07 |  | Drainage box culvert capacity expansion for 100-year flood event
VO-PKG-10-02920 | PKG-10 | 349552.78 | 0 | Pending Approval | 0 | 2025-09-07 |  | HVAC chilled water pipe rerouting around station concourse
VO-PKG-02-00102 | PKG-02 | 275426.63 | 0 | Rejected | 0 | 2025-09-08 | 2025-10-04 | TBM Cutterhead refurbishment and rock fissure sealing
VO-PKG-02-02892 | PKG-02 | 107599.71 | 93062.55 | Approved | 32 | 2025-09-08 | 2025-10-07 | TBM Cutterhead refurbishment and rock fissure sealing
VO-PKG-04-00284 | PKG-04 | 21212.51 | 0 | Pending Approval | 30 | 2025-09-08 |  | Station box diaphragm wall water ingress mitigation
VO-PKG-07-00177 | PKG-07 | 271519.98 | 258670.37 | Approved | 39 | 2025-09-09 | 2025-10-19 | Fiber optic telemetry routing realignment along guideway
VO-PKG-08-00738 | PKG-08 | 25486.44 | 0 | Rejected | 0 | 2025-09-09 | 2025-10-05 | Track vibration damping rubber pads acoustic upgrade
VO-PKG-03-00473 | PKG-03 | 270726.93 | 255859.83 | Approved | 44 | 2025-09-10 | 2025-10-17 | Viaduct pier foundation redesign due to utility clash
VO-PKG-04-02044 | PKG-04 | 318078.16 | 0 | Rejected | 0 | 2025-09-10 | 2025-10-03 | Station box diaphragm wall water ingress mitigation
VO-PKG-04-02054 | PKG-04 | 116340.93 | 0 | Pending Approval | 1 | 2025-09-10 |  | Station box diaphragm wall water ingress mitigation
VO-PKG-05-01105 | PKG-05 | 304869.57 | 269269.47 | Approved | 46 | 2025-09-10 | 2025-10-17 | HV substation redundancy transformer capacity upgrade
VO-PKG-07-02087 | PKG-07 | 218319.45 | 0 | Rejected | 0 | 2025-09-10 | 2025-09-28 | Fiber optic telemetry routing realignment along guideway
VO-PKG-09-02199 | PKG-09 | 298938.64 | 263529.4 | Approved | 20 | 2025-09-10 | 2025-10-25 | Drainage box culvert capacity expansion for 100-year flood event
VO-PKG-02-01662 | PKG-02 | 159816.18 | 149773.8 | Approved | 45 | 2025-09-11 | 2025-10-20 | TBM Cutterhead refurbishment and rock fissure sealing
VO-PKG-02-02572 | PKG-02 | 320733.18 | 0 | Rejected | 0 | 2025-09-11 | 2025-10-04 | TBM Cutterhead refurbishment and rock fissure sealing
VO-PKG-03-02183 | PKG-03 | 113603.68 | 109186.6 | Approved | 15 | 2025-09-11 | 2025-10-17 | Viaduct pier foundation redesign due to utility clash
VO-PKG-04-00114 | PKG-04 | 44801.75 | 42813.8 | Approved | 6 | 2025-09-11 | 2025-09-27 | Station box diaphragm wall water ingress mitigation
VO-PKG-01-01651 | PKG-01 | 175463.62 | 0 | Pending Approval | 44 | 2025-09-13 |  | Unforeseen soft ground stabilization and grouting
VO-PKG-01-02331 | PKG-01 | 340791.76 | 296919.13 | Approved | 54 | 2025-09-13 | 2025-10-16 | Unforeseen soft ground stabilization and grouting
VO-PKG-01-02441 | PKG-01 | 293629.29 | 0 | Pending Approval | 2 | 2025-09-13 |  | Unforeseen soft ground stabilization and grouting
VO-PKG-06-01716 | PKG-06 | 266127.46 | 231891.1 | Approved | 53 | 2025-09-13 | 2025-09-29 | Additional smoke evacuation shafts in underground platforms
VO-PKG-09-01149 | PKG-09 | 49867.71 | 0 | Pending Approval | 18 | 2025-09-13 |  | Drainage box culvert capacity expansion for 100-year flood event
VO-PKG-09-01189 | PKG-09 | 170381.69 | 160217.89 | Approved | 57 | 2025-09-13 | 2025-10-05 | Drainage box culvert capacity expansion for 100-year flood event
VO-PKG-02-02092 | PKG-02 | 205651.13 | 180570.23 | Approved | 25 | 2025-09-14 | 2025-10-07 | TBM Cutterhead refurbishment and rock fissure sealing
VO-PKG-03-01973 | PKG-03 | 164800.92 | 0 | Pending Approval | 30 | 2025-09-14 |  | Viaduct pier foundation redesign due to utility clash
VO-PKG-09-01729 | PKG-09 | 195734.34 | 0 | Pending Approval | 5 | 2025-09-15 |  | Drainage box culvert capacity expansion for 100-year flood event
VO-PKG-09-02619 | PKG-09 | 39865.1 | 0 | Rejected | 0 | 2025-09-15 | 2025-10-18 | Drainage box culvert capacity expansion for 100-year flood event
VO-PKG-01-00341 | PKG-01 | 198076.97 | 166215.69 | Approved | 28 | 2025-09-16 | 2025-10-07 | Unforeseen soft ground stabilization and grouting
VO-PKG-02-02182 | PKG-02 | 26801.68 | 24834.88 | Approved | 28 | 2025-09-16 | 2025-10-30 | TBM Cutterhead refurbishment and rock fissure sealing
VO-PKG-05-02195 | PKG-05 | 209903.71 | 0 | Pending Approval | 20 | 2025-09-16 |  | HV substation redundancy transformer capacity upgrade
VO-PKG-06-01896 | PKG-06 | 16207.56 | 15756.59 | Approved | 58 | 2025-09-16 | 2025-10-04 | Additional smoke evacuation shafts in underground platforms
VO-PKG-07-00197 | PKG-07 | 125199.68 | 117601.41 | Approved | 37 | 2025-09-16 | 2025-10-07 | Fiber optic telemetry routing realignment along guideway
VO-PKG-07-01597 | PKG-07 | 163996.65 | 0 | Pending Approval | 29 | 2025-09-16 |  | Fiber optic telemetry routing realignment along guideway
VO-PKG-08-02898 | PKG-08 | 32659.1 | 0 | Rejected | 0 | 2025-09-16 | 2025-10-02 | Track vibration damping rubber pads acoustic upgrade
VO-PKG-09-00109 | PKG-09 | 267004.51 | 231240.15 | Approved | 16 | 2025-09-16 | 2025-10-09 | Drainage box culvert capacity expansion for 100-year flood event
VO-PKG-09-02209 | PKG-09 | 236784.71 | 190938.13 | Approved | 18 | 2025-09-16 | 2025-10-24 | Drainage box culvert capacity expansion for 100-year flood event
VO-PKG-01-02831 | PKG-01 | 139304.61 | 129966.91 | Approved | 45 | 2025-09-17 | 2025-11-12 | Unforeseen soft ground stabilization and grouting
VO-PKG-02-01132 | PKG-02 | 22672.16 | 0 | Pending Approval | 0 | 2025-09-17 |  | TBM Cutterhead refurbishment and rock fissure sealing
VO-PKG-03-01173 | PKG-03 | 264401.23 | 0 | Pending Approval | 13 | 2025-09-17 |  | Viaduct pier foundation redesign due to utility clash
VO-PKG-03-01193 | PKG-03 | 60531.04 | 51244.18 | Approved | 37 | 2025-09-17 | 2025-10-18 | Viaduct pier foundation redesign due to utility clash
VO-PKG-05-01405 | PKG-05 | 226734.19 | 214441.42 | Approved | 47 | 2025-09-17 | 2025-11-08 | HV substation redundancy transformer capacity upgrade
VO-PKG-07-01897 | PKG-07 | 109599.48 | 0 | Pending Approval | 29 | 2025-09-17 |  | Fiber optic telemetry routing realignment along guideway
VO-PKG-01-02381 | PKG-01 | 213848.55 | 197767.8 | Approved | 29 | 2025-09-18 | 2025-11-02 | Unforeseen soft ground stabilization and grouting
VO-PKG-02-02632 | PKG-02 | 336520.48 | 0 | Pending Approval | 43 | 2025-09-18 |  | TBM Cutterhead refurbishment and rock fissure sealing
VO-PKG-03-01013 | PKG-03 | 172174.79 | 142247.46 | Approved | 51 | 2025-09-18 | 2025-10-23 | Viaduct pier foundation redesign due to utility clash
VO-PKG-03-01993 | PKG-03 | 306752.66 | 0 | Pending Approval | 29 | 2025-09-18 |  | Viaduct pier foundation redesign due to utility clash
VO-PKG-08-01108 | PKG-08 | 196612.56 | 0 | Pending Approval | 17 | 2025-09-18 |  | Track vibration damping rubber pads acoustic upgrade
VO-PKG-10-00450 | PKG-10 | 195912.97 | 0 | Pending Approval | 6 | 2025-09-18 |  | HVAC chilled water pipe rerouting around station concourse
VO-PKG-02-02282 | PKG-02 | 240711.01 | 208073.9 | Approved | 59 | 2025-09-19 | 2025-10-18 | TBM Cutterhead refurbishment and rock fissure sealing
VO-PKG-05-00755 | PKG-05 | 284569.41 | 0 | Rejected | 0 | 2025-09-19 | 2025-10-05 | HV substation redundancy transformer capacity upgrade
VO-PKG-05-02505 | PKG-05 | 20390.83 | 19677.27 | Approved | 11 | 2025-09-19 | 2025-11-10 | HV substation redundancy transformer capacity upgrade
VO-PKG-07-00377 | PKG-07 | 63677.37 | 58956.36 | Approved | 46 | 2025-09-19 | 2025-10-11 | Fiber optic telemetry routing realignment along guideway
VO-PKG-10-00230 | PKG-10 | 276340.96 | 269006.12 | Approved | 23 | 2025-09-19 | 2025-11-14 | HVAC chilled water pipe rerouting around station concourse
VO-PKG-06-02786 | PKG-06 | 244237.82 | 0 | Rejected | 0 | 2025-09-20 | 2025-10-02 | Additional smoke evacuation shafts in underground platforms
VO-PKG-10-01130 | PKG-10 | 214766.61 | 190290.96 | Approved | 25 | 2025-09-20 | 2025-11-01 | HVAC chilled water pipe rerouting around station concourse
VO-PKG-06-00966 | PKG-06 | 185090.59 | 0 | Pending Approval | 2 | 2025-09-21 |  | Additional smoke evacuation shafts in underground platforms
VO-PKG-07-01767 | PKG-07 | 103277.51 | 96615.65 | Approved | 9 | 2025-09-21 | 2025-10-16 | Fiber optic telemetry routing realignment along guideway
VO-PKG-09-02959 | PKG-09 | 340717.67 | 329859.68 | Approved | 54 | 2025-09-21 | 2025-11-07 | Drainage box culvert capacity expansion for 100-year flood event
VO-PKG-08-00848 | PKG-08 | 251066.62 | 209393.4 | Approved | 50 | 2025-09-22 | 2025-10-29 | Track vibration damping rubber pads acoustic upgrade
VO-PKG-10-00420 | PKG-10 | 52629.8 | 0 | Pending Approval | 15 | 2025-09-22 |  | HVAC chilled water pipe rerouting around station concourse
VO-PKG-02-02442 | PKG-02 | 242522.5 | 207309.84 | Approved | 42 | 2025-09-24 | 2025-11-10 | TBM Cutterhead refurbishment and rock fissure sealing
VO-PKG-05-01955 | PKG-05 | 51526.05 | 47202.89 | Approved | 43 | 2025-09-24 | 2025-10-15 | HV substation redundancy transformer capacity upgrade
VO-PKG-07-01227 | PKG-07 | 242385.51 | 230179.85 | Approved | 42 | 2025-09-24 | 2025-11-21 | Fiber optic telemetry routing realignment along guideway
VO-PKG-07-02207 | PKG-07 | 316179.23 | 0 | Pending Approval | 0 | 2025-09-24 |  | Fiber optic telemetry routing realignment along guideway
VO-PKG-08-01028 | PKG-08 | 68212.57 | 58608.04 | Approved | 45 | 2025-09-24 | 2025-10-16 | Track vibration damping rubber pads acoustic upgrade
VO-PKG-09-00399 | PKG-09 | 243701.81 | 0 | Rejected | 0 | 2025-09-24 | 2025-10-25 | Drainage box culvert capacity expansion for 100-year flood event
VO-PKG-09-02119 | PKG-09 | 159160.55 | 0 | Rejected | 0 | 2025-09-24 | 2025-10-05 | Drainage box culvert capacity expansion for 100-year flood event
VO-PKG-03-00263 | PKG-03 | 308647.77 | 0 | Pending Approval | 39 | 2025-09-25 |  | Viaduct pier foundation redesign due to utility clash
VO-PKG-03-02543 | PKG-03 | 340220.36 | 326520.92 | Approved | 19 | 2025-09-25 | 2025-10-22 | Viaduct pier foundation redesign due to utility clash
VO-PKG-07-02647 | PKG-07 | 255812.03 | 0 | Rejected | 0 | 2025-09-25 | 2025-10-19 | Fiber optic telemetry routing realignment along guideway
VO-PKG-09-02499 | PKG-09 | 229225.79 | 214599.1 | Approved | 24 | 2025-09-25 | 2025-10-14 | Drainage box culvert capacity expansion for 100-year flood event
VO-PKG-10-00510 | PKG-10 | 50044.07 | 46420.15 | Approved | 23 | 2025-09-25 | 2025-11-04 | HVAC chilled water pipe rerouting around station concourse
VO-PKG-04-00664 | PKG-04 | 348007.18 | 0 | Rejected | 0 | 2025-09-26 | 2025-10-08 | Station box diaphragm wall water ingress mitigation
VO-PKG-04-02494 | PKG-04 | 321887.72 | 0 | Rejected | 0 | 2025-09-26 | 2025-10-28 | Station box diaphragm wall water ingress mitigation
VO-PKG-08-02198 | PKG-08 | 303057.71 | 0 | Pending Approval | 43 | 2025-09-26 |  | Track vibration damping rubber pads acoustic upgrade
VO-PKG-08-00998 | PKG-08 | 67505.59 | 0 | Pending Approval | 24 | 2025-09-27 |  | Track vibration damping rubber pads acoustic upgrade
VO-PKG-10-00190 | PKG-10 | 275172.83 | 252650.94 | Approved | 16 | 2025-09-27 | 2025-10-21 | HVAC chilled water pipe rerouting around station concourse
VO-PKG-10-02430 | PKG-10 | 147599.55 | 119988.51 | Approved | 12 | 2025-09-27 | 2025-11-16 | HVAC chilled water pipe rerouting around station concourse
VO-PKG-06-01506 | PKG-06 | 181960.89 | 151102.78 | Approved | 12 | 2025-09-28 | 2025-11-16 | Additional smoke evacuation shafts in underground platforms
VO-PKG-08-02678 | PKG-08 | 122248.46 | 111057.64 | Approved | 24 | 2025-09-28 | 2025-10-30 | Track vibration damping rubber pads acoustic upgrade
VO-PKG-06-00196 | PKG-06 | 339652.61 | 328723.95 | Approved | 20 | 2025-09-29 | 2025-10-29 | Additional smoke evacuation shafts in underground platforms
VO-PKG-06-02376 | PKG-06 | 136849.97 | 126467.32 | Approved | 15 | 2025-09-29 | 2025-11-23 | Additional smoke evacuation shafts in underground platforms
VO-PKG-04-02254 | PKG-04 | 198193.26 | 189760.31 | Approved | 40 | 2025-09-30 | 2025-11-22 | Station box diaphragm wall water ingress mitigation
VO-PKG-10-00840 | PKG-10 | 126623.58 | 120686.67 | Approved | 39 | 2025-09-30 | 2025-11-18 | HVAC chilled water pipe rerouting around station concourse
VO-PKG-01-00301 | PKG-01 | 271099.4 | 235606.06 | Approved | 59 | 2025-10-01 | 2025-10-19 | Unforeseen soft ground stabilization and grouting
VO-PKG-01-01821 | PKG-01 | 36276.12 | 0 | Pending Approval | 5 | 2025-10-01 |  | Unforeseen soft ground stabilization and grouting
VO-PKG-10-01400 | PKG-10 | 30814.79 | 25727.03 | Approved | 16 | 2025-10-01 | 2025-10-31 | HVAC chilled water pipe rerouting around station concourse
VO-PKG-01-01481 | PKG-01 | 76268.68 | 65170.76 | Approved | 49 | 2025-10-02 | 2025-10-28 | Unforeseen soft ground stabilization and grouting
VO-PKG-06-00116 | PKG-06 | 230333.45 | 0 | Rejected | 0 | 2025-10-02 | 2025-10-21 | Additional smoke evacuation shafts in underground platforms
VO-PKG-02-01842 | PKG-02 | 108914.52 | 101644.31 | Approved | 59 | 2025-10-03 | 2025-11-14 | TBM Cutterhead refurbishment and rock fissure sealing
VO-PKG-05-02685 | PKG-05 | 256797.59 | 0 | Pending Approval | 7 | 2025-10-03 |  | HV substation redundancy transformer capacity upgrade
VO-PKG-09-02049 | PKG-09 | 146270.1 | 0 | Rejected | 0 | 2025-10-03 | 2025-10-13 | Drainage box culvert capacity expansion for 100-year flood event
VO-PKG-01-00691 | PKG-01 | 301503.98 | 0 | Rejected | 0 | 2025-10-04 | 2025-10-30 | Unforeseen soft ground stabilization and grouting
VO-PKG-03-00843 | PKG-03 | 296742.29 | 271841.02 | Approved | 47 | 2025-10-04 | 2025-10-25 | Viaduct pier foundation redesign due to utility clash
VO-PKG-10-00830 | PKG-10 | 62850.97 | 60502.52 | Approved | 27 | 2025-10-04 | 2025-11-16 | HVAC chilled water pipe rerouting around station concourse
VO-PKG-02-01072 | PKG-02 | 121471.81 | 0 | Rejected | 0 | 2025-10-05 | 2025-10-18 | TBM Cutterhead refurbishment and rock fissure sealing
VO-PKG-02-01262 | PKG-02 | 210033.06 | 0 | Pending Approval | 11 | 2025-10-05 |  | TBM Cutterhead refurbishment and rock fissure sealing
VO-PKG-05-01035 | PKG-05 | 69965.9 | 62987.34 | Approved | 58 | 2025-10-05 | 2025-11-06 | HV substation redundancy transformer capacity upgrade
VO-PKG-09-00659 | PKG-09 | 82172.31 | 0 | Rejected | 0 | 2025-10-05 | 2025-11-12 | Drainage box culvert capacity expansion for 100-year flood event
VO-PKG-09-01249 | PKG-09 | 96735.29 | 79699.86 | Approved | 31 | 2025-10-05 | 2025-11-29 | Drainage box culvert capacity expansion for 100-year flood event
VO-PKG-03-02433 | PKG-03 | 28400.87 | 0 | Pending Approval | 35 | 2025-10-06 |  | Viaduct pier foundation redesign due to utility clash
VO-PKG-09-00569 | PKG-09 | 186459.21 | 153257.42 | Approved | 13 | 2025-10-06 | 2025-11-22 | Drainage box culvert capacity expansion for 100-year flood event
VO-PKG-04-02454 | PKG-04 | 340456 | 277067.24 | Approved | 34 | 2025-10-07 | 2025-11-22 | Station box diaphragm wall water ingress mitigation
VO-PKG-07-00687 | PKG-07 | 310942.98 | 303545.79 | Approved | 57 | 2025-10-07 | 2025-10-22 | Fiber optic telemetry routing realignment along guideway
VO-PKG-09-01639 | PKG-09 | 231553.42 | 0 | Pending Approval | 5 | 2025-10-07 |  | Drainage box culvert capacity expansion for 100-year flood event
VO-PKG-10-00460 | PKG-10 | 297457.23 | 0 | Pending Approval | 43 | 2025-10-07 |  | HVAC chilled water pipe rerouting around station concourse
VO-PKG-03-02133 | PKG-03 | 252862.33 | 214112.92 | Approved | 28 | 2025-10-08 | 2025-11-16 | Viaduct pier foundation redesign due to utility clash
VO-PKG-04-01104 | PKG-04 | 118363.28 | 101957.86 | Approved | 9 | 2025-10-08 | 2025-10-29 | Station box diaphragm wall water ingress mitigation
VO-PKG-04-01384 | PKG-04 | 66908.96 | 59532.71 | Approved | 26 | 2025-10-08 | 2025-11-19 | Station box diaphragm wall water ingress mitigation
VO-PKG-05-02705 | PKG-05 | 297803.04 | 247575.5 | Approved | 31 | 2025-10-08 | 2025-10-31 | HV substation redundancy transformer capacity upgrade
VO-PKG-08-00288 | PKG-08 | 189357.71 | 170483.36 | Approved | 7 | 2025-10-08 | 2025-11-06 | Track vibration damping rubber pads acoustic upgrade
VO-PKG-08-02548 | PKG-08 | 204869.82 | 186145.99 | Approved | 27 | 2025-10-08 | 2025-11-21 | Track vibration damping rubber pads acoustic upgrade
VO-PKG-09-00609 | PKG-09 | 120869.99 | 0 | Pending Approval | 22 | 2025-10-08 |  | Drainage box culvert capacity expansion for 100-year flood event
VO-PKG-09-00719 | PKG-09 | 83276.76 | 0 | Pending Approval | 22 | 2025-10-08 |  | Drainage box culvert capacity expansion for 100-year flood event
VO-PKG-08-00228 | PKG-08 | 309835.05 | 0 | Pending Approval | 15 | 2025-10-09 |  | Track vibration damping rubber pads acoustic upgrade
VO-PKG-08-01168 | PKG-08 | 243807.73 | 0 | Rejected | 0 | 2025-10-09 | 2025-11-14 | Track vibration damping rubber pads acoustic upgrade
VO-PKG-10-02570 | PKG-10 | 282168.21 | 0 | Rejected | 0 | 2025-10-09 | 2025-11-09 | HVAC chilled water pipe rerouting around station concourse
VO-PKG-02-00852 | PKG-02 | 239118.24 | 0 | Pending Approval | 8 | 2025-10-10 |  | TBM Cutterhead refurbishment and rock fissure sealing
VO-PKG-02-01652 | PKG-02 | 330081.42 | 270061.78 | Approved | 14 | 2025-10-10 | 2025-10-26 | TBM Cutterhead refurbishment and rock fissure sealing
VO-PKG-03-01703 | PKG-03 | 203652.19 | 190766.94 | Approved | 23 | 2025-10-10 | 2025-11-18 | Viaduct pier foundation redesign due to utility clash
VO-PKG-07-01147 | PKG-07 | 55415.81 | 50968.54 | Approved | 5 | 2025-10-10 | 2025-11-17 | Fiber optic telemetry routing realignment along guideway
VO-PKG-08-00258 | PKG-08 | 60473.41 | 48854.11 | Approved | 47 | 2025-10-10 | 2025-11-06 | Track vibration damping rubber pads acoustic upgrade
VO-PKG-09-02419 | PKG-09 | 209976.96 | 175633.46 | Approved | 23 | 2025-10-10 | 2025-11-04 | Drainage box culvert capacity expansion for 100-year flood event
VO-PKG-04-01844 | PKG-04 | 85390.16 | 0 | Pending Approval | 10 | 2025-10-11 |  | Station box diaphragm wall water ingress mitigation
VO-PKG-04-02154 | PKG-04 | 133534.02 | 119151.85 | Approved | 6 | 2025-10-11 | 2025-12-06 | Station box diaphragm wall water ingress mitigation
VO-PKG-06-01036 | PKG-06 | 147163.11 | 0 | Rejected | 0 | 2025-10-11 | 2025-10-25 | Additional smoke evacuation shafts in underground platforms
VO-PKG-06-01466 | PKG-06 | 53749.78 | 45524.55 | Approved | 11 | 2025-10-11 | 2025-11-30 | Additional smoke evacuation shafts in underground platforms
VO-PKG-06-02906 | PKG-06 | 240376.12 | 0 | Pending Approval | 3 | 2025-10-11 |  | Additional smoke evacuation shafts in underground platforms
VO-PKG-07-01257 | PKG-07 | 24850.7 | 23141.01 | Approved | 32 | 2025-10-11 | 2025-11-06 | Fiber optic telemetry routing realignment along guideway
VO-PKG-07-02617 | PKG-07 | 274871.77 | 253986 | Approved | 14 | 2025-10-11 | 2025-12-08 | Fiber optic telemetry routing realignment along guideway
VO-PKG-08-00338 | PKG-08 | 194555.47 | 0 | Rejected | 0 | 2025-10-11 | 2025-11-24 | Track vibration damping rubber pads acoustic upgrade
VO-PKG-10-02500 | PKG-10 | 308903.56 | 298345.58 | Approved | 36 | 2025-10-11 | 2025-11-19 | HVAC chilled water pipe rerouting around station concourse
VO-PKG-05-01825 | PKG-05 | 235684.2 | 0 | Rejected | 0 | 2025-10-12 | 2025-10-31 | HV substation redundancy transformer capacity upgrade
VO-PKG-07-01857 | PKG-07 | 292173.31 | 0 | Pending Approval | 14 | 2025-10-12 |  | Fiber optic telemetry routing realignment along guideway
VO-PKG-09-00279 | PKG-09 | 89145.82 | 82216.25 | Approved | 46 | 2025-10-12 | 2025-11-29 | Drainage box culvert capacity expansion for 100-year flood event
VO-PKG-02-02312 | PKG-02 | 115066.46 | 0 | Pending Approval | 40 | 2025-10-13 |  | TBM Cutterhead refurbishment and rock fissure sealing
VO-PKG-04-02464 | PKG-04 | 189802.68 | 160221.5 | Approved | 18 | 2025-10-13 | 2025-11-18 | Station box diaphragm wall water ingress mitigation
VO-PKG-05-01575 | PKG-05 | 290438.39 | 281027.25 | Approved | 15 | 2025-10-13 | 2025-11-06 | HV substation redundancy transformer capacity upgrade
VO-PKG-05-02845 | PKG-05 | 162272.82 | 135451.98 | Approved | 17 | 2025-10-13 | 2025-11-25 | HV substation redundancy transformer capacity upgrade
VO-PKG-09-01669 | PKG-09 | 246511.09 | 223835.74 | Approved | 43 | 2025-10-13 | 2025-10-31 | Drainage box culvert capacity expansion for 100-year flood event
VO-PKG-01-00721 | PKG-01 | 273583.86 | 0 | Rejected | 0 | 2025-10-14 | 2025-11-15 | Unforeseen soft ground stabilization and grouting
VO-PKG-01-02841 | PKG-01 | 333047.61 | 280562.77 | Approved | 34 | 2025-10-14 | 2025-11-07 | Unforeseen soft ground stabilization and grouting
VO-PKG-03-02063 | PKG-03 | 290452.3 | 248394.11 | Approved | 16 | 2025-10-14 | 2025-11-23 | Viaduct pier foundation redesign due to utility clash
VO-PKG-03-02493 | PKG-03 | 302236.41 | 261161.17 | Approved | 34 | 2025-10-14 | 2025-12-07 | Viaduct pier foundation redesign due to utility clash
VO-PKG-05-00635 | PKG-05 | 182910.49 | 0 | Pending Approval | 2 | 2025-10-14 |  | HV substation redundancy transformer capacity upgrade
VO-PKG-06-00906 | PKG-06 | 308974.01 | 0 | Pending Approval | 39 | 2025-10-14 |  | Additional smoke evacuation shafts in underground platforms
VO-PKG-09-01029 | PKG-09 | 291474.63 | 0 | Rejected | 0 | 2025-10-14 | 2025-11-12 | Drainage box culvert capacity expansion for 100-year flood event
VO-PKG-09-01519 | PKG-09 | 334417.1 | 304611.36 | Approved | 40 | 2025-10-14 | 2025-12-01 | Drainage box culvert capacity expansion for 100-year flood event
VO-PKG-02-02492 | PKG-02 | 53702.02 | 0 | Pending Approval | 3 | 2025-10-15 |  | TBM Cutterhead refurbishment and rock fissure sealing
VO-PKG-03-00223 | PKG-03 | 148068.73 | 135363.85 | Approved | 15 | 2025-10-15 | 2025-12-10 | Viaduct pier foundation redesign due to utility clash
VO-PKG-08-00988 | PKG-08 | 188770.68 | 0 | Pending Approval | 10 | 2025-10-15 |  | Track vibration damping rubber pads acoustic upgrade
VO-PKG-01-02171 | PKG-01 | 61771.15 | 53227.86 | Approved | 13 | 2025-10-16 | 2025-12-08 | Unforeseen soft ground stabilization and grouting
VO-PKG-02-01342 | PKG-02 | 204496.02 | 177249.26 | Approved | 34 | 2025-10-16 | 2025-11-07 | TBM Cutterhead refurbishment and rock fissure sealing
VO-PKG-03-02513 | PKG-03 | 28316.76 | 26371.76 | Approved | 13 | 2025-10-16 | 2025-11-15 | Viaduct pier foundation redesign due to utility clash
VO-PKG-04-00144 | PKG-04 | 281492.56 | 0 | Rejected | 0 | 2025-10-16 | 2025-11-12 | Station box diaphragm wall water ingress mitigation
VO-PKG-06-00886 | PKG-06 | 333475.12 | 287726.13 | Approved | 44 | 2025-10-16 | 2025-11-09 | Additional smoke evacuation shafts in underground platforms
VO-PKG-09-02539 | PKG-09 | 235289.78 | 210384.68 | Approved | 51 | 2025-10-16 | 2025-11-04 | Drainage box culvert capacity expansion for 100-year flood event
VO-PKG-10-01710 | PKG-10 | 203453.37 | 0 | Pending Approval | 20 | 2025-10-16 |  | HVAC chilled water pipe rerouting around station concourse
VO-PKG-04-02994 | PKG-04 | 167843.1 | 0 | Rejected | 0 | 2025-10-17 | 2025-11-17 | Station box diaphragm wall water ingress mitigation
VO-PKG-05-01765 | PKG-05 | 136876.82 | 115893.23 | Approved | 17 | 2025-10-17 | 2025-11-12 | HV substation redundancy transformer capacity upgrade
VO-PKG-02-00902 | PKG-02 | 79756.23 | 67733.51 | Approved | 50 | 2025-10-18 | 2025-11-26 | TBM Cutterhead refurbishment and rock fissure sealing
VO-PKG-05-02075 | PKG-05 | 347669.32 | 300957.93 | Approved | 28 | 2025-10-18 | 2025-11-03 | HV substation redundancy transformer capacity upgrade
VO-PKG-06-00636 | PKG-06 | 103955.12 | 0 | Pending Approval | 15 | 2025-10-18 |  | Additional smoke evacuation shafts in underground platforms
VO-PKG-08-02838 | PKG-08 | 285014.59 | 0 | Rejected | 0 | 2025-10-18 | 2025-11-12 | Track vibration damping rubber pads acoustic upgrade
VO-PKG-09-01559 | PKG-09 | 167987.95 | 0 | Pending Approval | 13 | 2025-10-18 |  | Drainage box culvert capacity expansion for 100-year flood event
VO-PKG-10-00880 | PKG-10 | 64140.38 | 55352.61 | Approved | 46 | 2025-10-18 | 2025-11-30 | HVAC chilled water pipe rerouting around station concourse
VO-PKG-02-02742 | PKG-02 | 45923.99 | 41288.58 | Approved | 39 | 2025-10-19 | 2025-11-27 | TBM Cutterhead refurbishment and rock fissure sealing
VO-PKG-03-00323 | PKG-03 | 113482.16 | 100110.39 | Approved | 59 | 2025-10-19 | 2025-12-11 | Viaduct pier foundation redesign due to utility clash
VO-PKG-04-02364 | PKG-04 | 46652.75 | 0 | Pending Approval | 27 | 2025-10-19 |  | Station box diaphragm wall water ingress mitigation
VO-PKG-06-02766 | PKG-06 | 44973.13 | 36604.78 | Approved | 6 | 2025-10-19 | 2025-11-20 | Additional smoke evacuation shafts in underground platforms
VO-PKG-02-02562 | PKG-02 | 71582.24 | 65031.99 | Approved | 48 | 2025-10-20 | 2025-11-29 | TBM Cutterhead refurbishment and rock fissure sealing
VO-PKG-03-01453 | PKG-03 | 174847.87 | 161384.91 | Approved | 26 | 2025-10-20 | 2025-12-10 | Viaduct pier foundation redesign due to utility clash
VO-PKG-04-00924 | PKG-04 | 77104.18 | 71942.3 | Approved | 31 | 2025-10-20 | 2025-12-11 | Station box diaphragm wall water ingress mitigation
VO-PKG-04-01864 | PKG-04 | 120130.57 | 111885.52 | Approved | 9 | 2025-10-20 | 2025-11-09 | Station box diaphragm wall water ingress mitigation
VO-PKG-09-00999 | PKG-09 | 301143.58 | 0 | Rejected | 0 | 2025-10-20 | 2025-11-07 | Drainage box culvert capacity expansion for 100-year flood event
VO-PKG-09-02939 | PKG-09 | 72699.49 | 0 | Rejected | 0 | 2025-10-20 | 2025-11-03 | Drainage box culvert capacity expansion for 100-year flood event
VO-PKG-10-02070 | PKG-10 | 246330.89 | 228215.96 | Approved | 8 | 2025-10-20 | 2025-11-25 | HVAC chilled water pipe rerouting around station concourse
VO-PKG-01-02291 | PKG-01 | 337330.08 | 284404.42 | Approved | 28 | 2025-10-21 | 2025-11-24 | Unforeseen soft ground stabilization and grouting
VO-PKG-07-00527 | PKG-07 | 75058.41 | 68930.92 | Approved | 49 | 2025-10-21 | 2025-12-02 | Fiber optic telemetry routing realignment along guideway
VO-PKG-08-02028 | PKG-08 | 300433.96 | 0 | Pending Approval | 32 | 2025-10-21 |  | Track vibration damping rubber pads acoustic upgrade
VO-PKG-09-00339 | PKG-09 | 187651.42 | 182465.68 | Approved | 8 | 2025-10-21 | 2025-12-14 | Drainage box culvert capacity expansion for 100-year flood event
VO-PKG-10-02130 | PKG-10 | 92653.8 | 79351.43 | Approved | 54 | 2025-10-21 | 2025-11-13 | HVAC chilled water pipe rerouting around station concourse
VO-PKG-09-00989 | PKG-09 | 330468.38 | 0 | Rejected | 0 | 2025-10-22 | 2025-11-21 | Drainage box culvert capacity expansion for 100-year flood event
VO-PKG-04-00624 | PKG-04 | 50801 | 46460.27 | Approved | 33 | 2025-10-23 | 2025-11-16 | Station box diaphragm wall water ingress mitigation
VO-PKG-05-00055 | PKG-05 | 259211.08 | 208944.41 | Approved | 47 | 2025-10-23 | 2025-11-27 | HV substation redundancy transformer capacity upgrade
VO-PKG-09-02319 | PKG-09 | 89369.76 | 83207.24 | Approved | 42 | 2025-10-23 | 2025-12-09 | Drainage box culvert capacity expansion for 100-year flood event
VO-PKG-10-02650 | PKG-10 | 272612.65 | 0 | Pending Approval | 16 | 2025-10-23 |  | HVAC chilled water pipe rerouting around station concourse
VO-PKG-06-01656 | PKG-06 | 81779.85 | 72617.34 | Approved | 29 | 2025-10-24 | 2025-12-14 | Additional smoke evacuation shafts in underground platforms
VO-PKG-10-01930 | PKG-10 | 148103.55 | 123804.86 | Approved | 18 | 2025-10-24 | 2025-11-20 | HVAC chilled water pipe rerouting around station concourse
VO-PKG-07-01107 | PKG-07 | 72735.4 | 67809.64 | Approved | 45 | 2025-10-25 | 2025-12-13 | Fiber optic telemetry routing realignment along guideway
VO-PKG-10-00770 | PKG-10 | 93024.27 | 0 | Pending Approval | 9 | 2025-10-26 |  | HVAC chilled water pipe rerouting around station concourse
VO-PKG-01-00111 | PKG-01 | 23304.09 | 0 | Rejected | 0 | 2025-10-27 | 2025-12-08 | Unforeseen soft ground stabilization and grouting
VO-PKG-06-02336 | PKG-06 | 194813.1 | 185773.37 | Approved | 5 | 2025-10-27 | 2025-12-22 | Additional smoke evacuation shafts in underground platforms
VO-PKG-08-01238 | PKG-08 | 336465.66 | 0 | Rejected | 0 | 2025-10-27 | 2025-11-13 | Track vibration damping rubber pads acoustic upgrade
VO-PKG-09-02729 | PKG-09 | 267259.13 | 0 | Rejected | 0 | 2025-10-27 | 2025-11-24 | Drainage box culvert capacity expansion for 100-year flood event
VO-PKG-06-00126 | PKG-06 | 336484.83 | 318037.63 | Approved | 26 | 2025-10-28 | 2025-11-13 | Additional smoke evacuation shafts in underground platforms
VO-PKG-07-01027 | PKG-07 | 22594.9 | 21758.13 | Approved | 31 | 2025-10-28 | 2025-11-28 | Fiber optic telemetry routing realignment along guideway
VO-PKG-08-01638 | PKG-08 | 227308.9 | 216046.75 | Approved | 25 | 2025-10-28 | 2025-11-26 | Track vibration damping rubber pads acoustic upgrade
VO-PKG-01-01601 | PKG-01 | 159882.12 | 0 | Pending Approval | 38 | 2025-10-29 |  | Unforeseen soft ground stabilization and grouting
VO-PKG-06-02796 | PKG-06 | 281474.46 | 235122.65 | Approved | 50 | 2025-10-29 | 2025-12-09 | Additional smoke evacuation shafts in underground platforms
VO-PKG-07-02307 | PKG-07 | 190404.8 | 0 | Pending Approval | 16 | 2025-10-29 |  | Fiber optic telemetry routing realignment along guideway
VO-PKG-02-01122 | PKG-02 | 214150.83 | 0 | Pending Approval | 41 | 2025-10-30 |  | TBM Cutterhead refurbishment and rock fissure sealing
VO-PKG-02-01482 | PKG-02 | 174391.92 | 151079.49 | Approved | 18 | 2025-10-30 | 2025-12-21 | TBM Cutterhead refurbishment and rock fissure sealing
VO-PKG-05-01475 | PKG-05 | 78558.7 | 72910.74 | Approved | 33 | 2025-10-30 | 2025-12-07 | HV substation redundancy transformer capacity upgrade
VO-PKG-09-02189 | PKG-09 | 248605.15 | 0 | Rejected | 0 | 2025-10-30 | 2025-11-17 | Drainage box culvert capacity expansion for 100-year flood event
VO-PKG-07-01937 | PKG-07 | 43577.76 | 0 | Pending Approval | 31 | 2025-10-31 |  | Fiber optic telemetry routing realignment along guideway
VO-PKG-09-01859 | PKG-09 | 53359.71 | 44947.25 | Approved | 57 | 2025-10-31 | 2025-12-05 | Drainage box culvert capacity expansion for 100-year flood event
VO-PKG-02-01092 | PKG-02 | 205410.44 | 165774.41 | Approved | 58 | 2025-11-01 | 2025-12-28 | TBM Cutterhead refurbishment and rock fissure sealing
VO-PKG-07-01017 | PKG-07 | 100456.64 | 97113.88 | Approved | 38 | 2025-11-01 | 2025-12-20 | Fiber optic telemetry routing realignment along guideway
VO-PKG-08-02568 | PKG-08 | 52410.03 | 0 | Pending Approval | 8 | 2025-11-01 |  | Track vibration damping rubber pads acoustic upgrade
VO-PKG-10-01900 | PKG-10 | 324042.22 | 0 | Pending Approval | 39 | 2025-11-01 |  | HVAC chilled water pipe rerouting around station concourse
VO-PKG-06-01596 | PKG-06 | 83178.46 | 73691.5 | Approved | 13 | 2025-11-02 | 2025-12-14 | Additional smoke evacuation shafts in underground platforms
VO-PKG-03-00303 | PKG-03 | 206615.27 | 197831.62 | Approved | 42 | 2025-11-03 | 2025-12-19 | Viaduct pier foundation redesign due to utility clash
VO-PKG-03-02103 | PKG-03 | 252545.14 | 0 | Rejected | 0 | 2025-11-03 | 2025-11-25 | Viaduct pier foundation redesign due to utility clash
VO-PKG-03-02853 | PKG-03 | 22850.69 | 21374.33 | Approved | 40 | 2025-11-03 | 2025-12-06 | Viaduct pier foundation redesign due to utility clash
VO-PKG-04-00724 | PKG-04 | 38249.17 | 31440.06 | Approved | 52 | 2025-11-03 | 2025-11-20 | Station box diaphragm wall water ingress mitigation
VO-PKG-04-02864 | PKG-04 | 276257.62 | 0 | Rejected | 0 | 2025-11-03 | 2025-11-28 | Station box diaphragm wall water ingress mitigation
VO-PKG-08-01888 | PKG-08 | 108341.64 | 102541.54 | Approved | 50 | 2025-11-03 | 2025-12-24 | Track vibration damping rubber pads acoustic upgrade
VO-PKG-06-02586 | PKG-06 | 336543.43 | 0 | Rejected | 0 | 2025-11-04 | 2025-11-23 | Additional smoke evacuation shafts in underground platforms
VO-PKG-09-00009 | PKG-09 | 312578.25 | 302515.52 | Approved | 9 | 2025-11-04 | 2025-12-31 | Drainage box culvert capacity expansion for 100-year flood event
VO-PKG-09-02859 | PKG-09 | 124159.43 | 115918.33 | Approved | 44 | 2025-11-04 | 2025-12-30 | Drainage box culvert capacity expansion for 100-year flood event
VO-PKG-01-01441 | PKG-01 | 339208.54 | 274213.08 | Approved | 39 | 2025-11-05 | 2025-12-21 | Unforeseen soft ground stabilization and grouting
VO-PKG-01-02481 | PKG-01 | 329810.18 | 265875.85 | Approved | 52 | 2025-11-05 | 2025-12-24 | Unforeseen soft ground stabilization and grouting
VO-PKG-04-00224 | PKG-04 | 178994.02 | 166576.38 | Approved | 36 | 2025-11-05 | 2025-12-08 | Station box diaphragm wall water ingress mitigation
VO-PKG-05-01175 | PKG-05 | 54211.52 | 49478.33 | Approved | 59 | 2025-11-05 | 2025-12-22 | HV substation redundancy transformer capacity upgrade
VO-PKG-07-02197 | PKG-07 | 131136.99 | 0 | Pending Approval | 34 | 2025-11-05 |  | Fiber optic telemetry routing realignment along guideway
VO-PKG-10-01610 | PKG-10 | 92313.72 | 0 | Rejected | 0 | 2025-11-05 | 2025-11-17 | HVAC chilled water pipe rerouting around station concourse
VO-PKG-02-00712 | PKG-02 | 271396.85 | 0 | Rejected | 0 | 2025-11-07 | 2025-11-21 | TBM Cutterhead refurbishment and rock fissure sealing
VO-PKG-04-00704 | PKG-04 | 246457.92 | 216755.78 | Approved | 17 | 2025-11-07 | 2025-11-23 | Station box diaphragm wall water ingress mitigation
VO-PKG-07-01297 | PKG-07 | 267199.75 | 0 | Rejected | 0 | 2025-11-07 | 2025-12-08 | Fiber optic telemetry routing realignment along guideway
VO-PKG-10-00980 | PKG-10 | 284222.44 | 272141.87 | Approved | 54 | 2025-11-07 | 2025-11-26 | HVAC chilled water pipe rerouting around station concourse
VO-PKG-01-00531 | PKG-01 | 128278.28 | 0 | Rejected | 0 | 2025-11-08 | 2025-11-18 | Unforeseen soft ground stabilization and grouting
VO-PKG-01-00961 | PKG-01 | 15031.24 | 0 | Pending Approval | 22 | 2025-11-08 |  | Unforeseen soft ground stabilization and grouting
VO-PKG-01-01811 | PKG-01 | 67984.79 | 0 | Pending Approval | 12 | 2025-11-08 |  | Unforeseen soft ground stabilization and grouting
VO-PKG-02-02842 | PKG-02 | 34514.13 | 30920.47 | Approved | 31 | 2025-11-08 | 2025-11-24 | TBM Cutterhead refurbishment and rock fissure sealing
VO-PKG-04-01694 | PKG-04 | 96123.79 | 0 | Rejected | 0 | 2025-11-08 | 2025-12-12 | Station box diaphragm wall water ingress mitigation
VO-PKG-06-00336 | PKG-06 | 282623.23 | 242668.93 | Approved | 30 | 2025-11-08 | 2025-11-27 | Additional smoke evacuation shafts in underground platforms
VO-PKG-10-01190 | PKG-10 | 206241.54 | 0 | Rejected | 0 | 2025-11-08 | 2025-11-25 | HVAC chilled water pipe rerouting around station concourse
VO-PKG-05-00625 | PKG-05 | 32871.49 | 0 | Pending Approval | 5 | 2025-11-09 |  | HV substation redundancy transformer capacity upgrade
VO-PKG-09-01619 | PKG-09 | 81568.04 | 79174.26 | Approved | 23 | 2025-11-09 | 2025-12-19 | Drainage box culvert capacity expansion for 100-year flood event
VO-PKG-09-01849 | PKG-09 | 326946.28 | 269870.1 | Approved | 20 | 2025-11-09 | 2025-12-03 | Drainage box culvert capacity expansion for 100-year flood event
VO-PKG-01-02471 | PKG-01 | 199517.64 | 184854.73 | Approved | 26 | 2025-11-10 | 2025-12-29 | Unforeseen soft ground stabilization and grouting
VO-PKG-04-02374 | PKG-04 | 111868 | 0 | Pending Approval | 23 | 2025-11-10 |  | Station box diaphragm wall water ingress mitigation
VO-PKG-07-00187 | PKG-07 | 167612.09 | 0 | Pending Approval | 31 | 2025-11-10 |  | Fiber optic telemetry routing realignment along guideway
VO-PKG-08-01828 | PKG-08 | 304596.5 | 284058.09 | Approved | 33 | 2025-11-10 | 2025-12-28 | Track vibration damping rubber pads acoustic upgrade
VO-PKG-08-01838 | PKG-08 | 60014.14 | 56894.69 | Approved | 34 | 2025-11-10 | 2025-12-14 | Track vibration damping rubber pads acoustic upgrade
VO-PKG-09-02529 | PKG-09 | 95492.25 | 92944.22 | Approved | 32 | 2025-11-10 | 2025-11-29 | Drainage box culvert capacity expansion for 100-year flood event
VO-PKG-03-01363 | PKG-03 | 216025.47 | 0 | Pending Approval | 25 | 2025-11-11 |  | Viaduct pier foundation redesign due to utility clash
VO-PKG-05-00185 | PKG-05 | 119980.53 | 97419.25 | Approved | 6 | 2025-11-11 | 2025-12-01 | HV substation redundancy transformer capacity upgrade
VO-PKG-05-00715 | PKG-05 | 185429.82 | 0 | Rejected | 0 | 2025-11-11 | 2025-12-12 | HV substation redundancy transformer capacity upgrade
VO-PKG-06-01846 | PKG-06 | 288428.67 | 244422.73 | Approved | 5 | 2025-11-11 | 2025-12-09 | Additional smoke evacuation shafts in underground platforms
VO-PKG-07-02067 | PKG-07 | 312915.79 | 299041.76 | Approved | 21 | 2025-11-11 | 2025-12-04 | Fiber optic telemetry routing realignment along guideway
VO-PKG-08-02618 | PKG-08 | 119989.04 | 96997.02 | Approved | 58 | 2025-11-11 | 2026-01-05 | Track vibration damping rubber pads acoustic upgrade
VO-PKG-10-00550 | PKG-10 | 186946.59 | 168338.43 | Approved | 34 | 2025-11-11 | 2025-11-29 | HVAC chilled water pipe rerouting around station concourse
VO-PKG-10-01450 | PKG-10 | 203154.14 | 195261.6 | Approved | 13 | 2025-11-11 | 2025-12-28 | HVAC chilled water pipe rerouting around station concourse
VO-PKG-02-02052 | PKG-02 | 82450.95 | 0 | Pending Approval | 23 | 2025-11-12 |  | TBM Cutterhead refurbishment and rock fissure sealing
VO-PKG-03-00673 | PKG-03 | 219526.43 | 198551.12 | Approved | 25 | 2025-11-12 | 2025-12-21 | Viaduct pier foundation redesign due to utility clash
VO-PKG-06-01076 | PKG-06 | 30024.3 | 0 | Rejected | 0 | 2025-11-12 | 2025-12-05 | Additional smoke evacuation shafts in underground platforms
VO-PKG-06-01856 | PKG-06 | 181036.05 | 0 | Pending Approval | 15 | 2025-11-12 |  | Additional smoke evacuation shafts in underground platforms
VO-PKG-07-01247 | PKG-07 | 112174.7 | 0 | Pending Approval | 39 | 2025-11-12 |  | Fiber optic telemetry routing realignment along guideway
VO-PKG-09-00099 | PKG-09 | 102090.27 | 91819.61 | Approved | 55 | 2025-11-12 | 2026-01-02 | Drainage box culvert capacity expansion for 100-year flood event
VO-PKG-09-01139 | PKG-09 | 288832.8 | 254307.98 | Approved | 31 | 2025-11-12 | 2026-01-10 | Drainage box culvert capacity expansion for 100-year flood event
VO-PKG-10-00630 | PKG-10 | 255035.68 | 0 | Pending Approval | 10 | 2025-11-12 |  | HVAC chilled water pipe rerouting around station concourse
VO-PKG-01-01251 | PKG-01 | 26513.36 | 0 | Rejected | 0 | 2025-11-14 | 2025-11-27 | Unforeseen soft ground stabilization and grouting
VO-PKG-04-00234 | PKG-04 | 314204.7 | 0 | Rejected | 0 | 2025-11-14 | 2025-12-01 | Station box diaphragm wall water ingress mitigation
VO-PKG-03-02373 | PKG-03 | 299449.44 | 0 | Rejected | 0 | 2025-11-15 | 2025-12-27 | Viaduct pier foundation redesign due to utility clash
VO-PKG-04-00964 | PKG-04 | 44663.04 | 37495.59 | Approved | 28 | 2025-11-15 | 2026-01-02 | Station box diaphragm wall water ingress mitigation
VO-PKG-10-01620 | PKG-10 | 120857.68 | 113668.98 | Approved | 28 | 2025-11-15 | 2025-12-13 | HVAC chilled water pipe rerouting around station concourse
VO-PKG-10-02180 | PKG-10 | 97483.27 | 94477.46 | Approved | 24 | 2025-11-15 | 2025-12-11 | HVAC chilled water pipe rerouting around station concourse
VO-PKG-02-01252 | PKG-02 | 217765.93 | 0 | Pending Approval | 43 | 2025-11-16 |  | TBM Cutterhead refurbishment and rock fissure sealing
VO-PKG-08-01428 | PKG-08 | 184300 | 151915.09 | Approved | 17 | 2025-11-16 | 2026-01-11 | Track vibration damping rubber pads acoustic upgrade
VO-PKG-02-01272 | PKG-02 | 289849.06 | 263883.3 | Approved | 5 | 2025-11-18 | 2025-12-14 | TBM Cutterhead refurbishment and rock fissure sealing
VO-PKG-08-01048 | PKG-08 | 151208.61 | 141449.93 | Approved | 55 | 2025-11-18 | 2026-01-12 | Track vibration damping rubber pads acoustic upgrade
VO-PKG-09-00369 | PKG-09 | 122941.84 | 108314 | Approved | 8 | 2025-11-19 | 2026-01-14 | Drainage box culvert capacity expansion for 100-year flood event
VO-PKG-02-00962 | PKG-02 | 88928.53 | 77316.8 | Approved | 12 | 2025-11-20 | 2025-12-05 | TBM Cutterhead refurbishment and rock fissure sealing
VO-PKG-05-00515 | PKG-05 | 54574.54 | 51970.91 | Approved | 12 | 2025-11-20 | 2026-01-12 | HV substation redundancy transformer capacity upgrade
VO-PKG-03-01353 | PKG-03 | 169275.67 | 0 | Pending Approval | 34 | 2025-11-21 |  | Viaduct pier foundation redesign due to utility clash
VO-PKG-03-02033 | PKG-03 | 335617.4 | 311609.84 | Approved | 16 | 2025-11-21 | 2025-12-21 | Viaduct pier foundation redesign due to utility clash
VO-PKG-03-02943 | PKG-03 | 56825.38 | 0 | Rejected | 0 | 2025-11-21 | 2025-12-21 | Viaduct pier foundation redesign due to utility clash
VO-PKG-05-02455 | PKG-05 | 29900.48 | 0 | Pending Approval | 25 | 2025-11-21 |  | HV substation redundancy transformer capacity upgrade
VO-PKG-09-02679 | PKG-09 | 246743.83 | 236029.58 | Approved | 47 | 2025-11-21 | 2026-01-16 | Drainage box culvert capacity expansion for 100-year flood event
VO-PKG-10-01490 | PKG-10 | 286092.18 | 235241.81 | Approved | 24 | 2025-11-21 | 2026-01-02 | HVAC chilled water pipe rerouting around station concourse
VO-PKG-01-01371 | PKG-01 | 45938.59 | 38069.36 | Approved | 22 | 2025-11-22 | 2026-01-02 | Unforeseen soft ground stabilization and grouting
VO-PKG-05-02585 | PKG-05 | 138851.32 | 112464.43 | Approved | 40 | 2025-11-22 | 2025-12-11 | HV substation redundancy transformer capacity upgrade
VO-PKG-03-02013 | PKG-03 | 269515.9 | 235967.04 | Approved | 8 | 2025-11-23 | 2025-12-18 | Viaduct pier foundation redesign due to utility clash
VO-PKG-06-00616 | PKG-06 | 44662.08 | 38737.53 | Approved | 28 | 2025-11-23 | 2026-01-02 | Additional smoke evacuation shafts in underground platforms
VO-PKG-09-01839 | PKG-09 | 261671.3 | 237255.06 | Approved | 45 | 2025-11-23 | 2025-12-20 | Drainage box culvert capacity expansion for 100-year flood event
VO-PKG-10-00040 | PKG-10 | 90958.02 | 79849.39 | Approved | 43 | 2025-11-23 | 2026-01-20 | HVAC chilled water pipe rerouting around station concourse
VO-PKG-10-02900 | PKG-10 | 19599.75 | 18548.89 | Approved | 44 | 2025-11-23 | 2026-01-02 | HVAC chilled water pipe rerouting around station concourse
VO-PKG-02-02422 | PKG-02 | 288424.66 | 250340.25 | Approved | 55 | 2025-11-25 | 2025-12-17 | TBM Cutterhead refurbishment and rock fissure sealing
VO-PKG-02-02472 | PKG-02 | 219341.49 | 0 | Rejected | 0 | 2025-11-25 | 2025-12-29 | TBM Cutterhead refurbishment and rock fissure sealing
VO-PKG-04-00514 | PKG-04 | 83590.34 | 75831.7 | Approved | 5 | 2025-11-25 | 2026-01-04 | Station box diaphragm wall water ingress mitigation
VO-PKG-06-01186 | PKG-06 | 216904.86 | 0 | Pending Approval | 12 | 2025-11-25 |  | Additional smoke evacuation shafts in underground platforms
VO-PKG-08-01308 | PKG-08 | 248647.53 | 0 | Pending Approval | 33 | 2025-11-25 |  | Track vibration damping rubber pads acoustic upgrade
VO-PKG-10-02370 | PKG-10 | 317466.45 | 0 | Pending Approval | 32 | 2025-11-25 |  | HVAC chilled water pipe rerouting around station concourse
VO-PKG-02-00792 | PKG-02 | 337352.64 | 304108.46 | Approved | 40 | 2025-11-26 | 2026-01-20 | TBM Cutterhead refurbishment and rock fissure sealing
VO-PKG-02-00842 | PKG-02 | 161613.26 | 0 | Rejected | 0 | 2025-11-27 | 2025-12-09 | TBM Cutterhead refurbishment and rock fissure sealing
VO-PKG-02-02722 | PKG-02 | 101488.81 | 0 | Pending Approval | 36 | 2025-11-27 |  | TBM Cutterhead refurbishment and rock fissure sealing
VO-PKG-03-02633 | PKG-03 | 70856.49 | 0 | Pending Approval | 6 | 2025-11-27 |  | Viaduct pier foundation redesign due to utility clash
VO-PKG-04-00504 | PKG-04 | 230734.49 | 0 | Rejected | 0 | 2025-11-27 | 2025-12-17 | Station box diaphragm wall water ingress mitigation
VO-PKG-10-02440 | PKG-10 | 113835.43 | 108451.33 | Approved | 38 | 2025-11-27 | 2025-12-23 | HVAC chilled water pipe rerouting around station concourse
VO-PKG-10-02720 | PKG-10 | 264783.25 | 0 | Pending Approval | 7 | 2025-11-27 |  | HVAC chilled water pipe rerouting around station concourse
VO-PKG-10-02970 | PKG-10 | 71101 | 57746.8 | Approved | 14 | 2025-11-27 | 2025-12-26 | HVAC chilled water pipe rerouting around station concourse
VO-PKG-07-01337 | PKG-07 | 96971.67 | 91350.45 | Approved | 30 | 2025-11-28 | 2026-01-10 | Fiber optic telemetry routing realignment along guideway
VO-PKG-09-02509 | PKG-09 | 202131.3 | 163426.9 | Approved | 34 | 2025-11-28 | 2025-12-16 | Drainage box culvert capacity expansion for 100-year flood event
VO-PKG-01-02701 | PKG-01 | 54314.27 | 49477.25 | Approved | 5 | 2025-11-29 | 2025-12-21 | Unforeseen soft ground stabilization and grouting
VO-PKG-04-02074 | PKG-04 | 234669.9 | 0 | Pending Approval | 23 | 2025-11-29 |  | Station box diaphragm wall water ingress mitigation
VO-PKG-04-02774 | PKG-04 | 320431.99 | 256986.34 | Approved | 40 | 2025-11-29 | 2026-01-01 | Station box diaphragm wall water ingress mitigation
VO-PKG-06-02966 | PKG-06 | 72295.94 | 63286.39 | Approved | 56 | 2025-11-29 | 2026-01-02 | Additional smoke evacuation shafts in underground platforms
VO-PKG-01-01101 | PKG-01 | 91350.09 | 0 | Pending Approval | 10 | 2025-11-30 |  | Unforeseen soft ground stabilization and grouting
VO-PKG-02-01112 | PKG-02 | 33308.78 | 30256.91 | Approved | 9 | 2025-11-30 | 2025-12-20 | TBM Cutterhead refurbishment and rock fissure sealing
VO-PKG-03-02403 | PKG-03 | 22781.04 | 21847.28 | Approved | 21 | 2025-11-30 | 2026-01-05 | Viaduct pier foundation redesign due to utility clash
VO-PKG-04-02334 | PKG-04 | 348289.01 | 0 | Pending Approval | 36 | 2025-11-30 |  | Station box diaphragm wall water ingress mitigation
VO-PKG-05-02805 | PKG-05 | 217686.03 | 0 | Pending Approval | 33 | 2025-11-30 |  | HV substation redundancy transformer capacity upgrade
VO-PKG-08-00968 | PKG-08 | 73425.6 | 65101.13 | Approved | 18 | 2025-11-30 | 2025-12-20 | Track vibration damping rubber pads acoustic upgrade
VO-PKG-03-01273 | PKG-03 | 84221.39 | 0 | Pending Approval | 18 | 2025-12-01 |  | Viaduct pier foundation redesign due to utility clash
VO-PKG-03-01413 | PKG-03 | 147234.26 | 0 | Pending Approval | 43 | 2025-12-01 |  | Viaduct pier foundation redesign due to utility clash
VO-PKG-04-02174 | PKG-04 | 123710.17 | 109398.15 | Approved | 38 | 2025-12-01 | 2026-01-03 | Station box diaphragm wall water ingress mitigation
VO-PKG-06-00286 | PKG-06 | 124885.48 | 100544.23 | Approved | 43 | 2025-12-01 | 2026-01-19 | Additional smoke evacuation shafts in underground platforms
VO-PKG-06-02306 | PKG-06 | 222247.24 | 183864.98 | Approved | 26 | 2025-12-01 | 2025-12-22 | Additional smoke evacuation shafts in underground platforms
VO-PKG-03-00703 | PKG-03 | 158394.21 | 0 | Rejected | 0 | 2025-12-02 | 2026-01-07 | Viaduct pier foundation redesign due to utility clash
VO-PKG-05-00005 | PKG-05 | 285314.39 | 234978.33 | Approved | 19 | 2025-12-02 | 2025-12-22 | HV substation redundancy transformer capacity upgrade
VO-PKG-06-01516 | PKG-06 | 62579.99 | 0 | Pending Approval | 15 | 2025-12-02 |  | Additional smoke evacuation shafts in underground platforms
VO-PKG-07-00907 | PKG-07 | 181710.01 | 148194.16 | Approved | 26 | 2025-12-02 | 2026-01-08 | Fiber optic telemetry routing realignment along guideway
VO-PKG-03-00363 | PKG-03 | 112583.31 | 0 | Pending Approval | 3 | 2025-12-03 |  | Viaduct pier foundation redesign due to utility clash
VO-PKG-04-00944 | PKG-04 | 66309.49 | 0 | Rejected | 0 | 2025-12-03 | 2025-12-29 | Station box diaphragm wall water ingress mitigation
VO-PKG-06-02276 | PKG-06 | 232279.96 | 222176.27 | Approved | 26 | 2025-12-03 | 2025-12-24 | Additional smoke evacuation shafts in underground platforms
VO-PKG-07-01677 | PKG-07 | 284626.12 | 229779.9 | Approved | 54 | 2025-12-03 | 2026-01-15 | Fiber optic telemetry routing realignment along guideway
VO-PKG-01-01951 | PKG-01 | 237791.12 | 227286.45 | Approved | 48 | 2025-12-04 | 2026-01-26 | Unforeseen soft ground stabilization and grouting
VO-PKG-03-01263 | PKG-03 | 151701.93 | 0 | Pending Approval | 10 | 2025-12-04 |  | Viaduct pier foundation redesign due to utility clash
VO-PKG-06-00556 | PKG-06 | 37474.3 | 32864.56 | Approved | 29 | 2025-12-04 | 2026-01-12 | Additional smoke evacuation shafts in underground platforms
VO-PKG-07-01517 | PKG-07 | 170026.62 | 145411.91 | Approved | 46 | 2025-12-04 | 2025-12-24 | Fiber optic telemetry routing realignment along guideway
VO-PKG-10-01180 | PKG-10 | 100146.43 | 84524.46 | Approved | 49 | 2025-12-04 | 2025-12-28 | HVAC chilled water pipe rerouting around station concourse
VO-PKG-03-02683 | PKG-03 | 339883.17 | 0 | Pending Approval | 4 | 2025-12-05 |  | Viaduct pier foundation redesign due to utility clash
VO-PKG-05-00235 | PKG-05 | 288973.98 | 280911.08 | Approved | 28 | 2025-12-05 | 2026-01-16 | HV substation redundancy transformer capacity upgrade
VO-PKG-06-02926 | PKG-06 | 121335.74 | 0 | Rejected | 0 | 2025-12-05 | 2025-12-26 | Additional smoke evacuation shafts in underground platforms
VO-PKG-03-01563 | PKG-03 | 168907.9 | 143659.38 | Approved | 20 | 2025-12-06 | 2025-12-21 | Viaduct pier foundation redesign due to utility clash
VO-PKG-09-01609 | PKG-09 | 227287.97 | 201047.41 | Approved | 9 | 2025-12-06 | 2025-12-21 | Drainage box culvert capacity expansion for 100-year flood event
VO-PKG-06-00246 | PKG-06 | 348622.45 | 0 | Pending Approval | 9 | 2025-12-07 |  | Additional smoke evacuation shafts in underground platforms
VO-PKG-07-00507 | PKG-07 | 339456.79 | 326637.11 | Approved | 37 | 2025-12-07 | 2025-12-30 | Fiber optic telemetry routing realignment along guideway
VO-PKG-08-01568 | PKG-08 | 61312.68 | 58519.2 | Approved | 27 | 2025-12-07 | 2026-01-02 | Track vibration damping rubber pads acoustic upgrade
VO-PKG-06-01946 | PKG-06 | 187397.19 | 0 | Rejected | 0 | 2025-12-08 | 2025-12-29 | Additional smoke evacuation shafts in underground platforms
VO-PKG-08-00468 | PKG-08 | 284937.97 | 259320.85 | Approved | 16 | 2025-12-08 | 2026-02-04 | Track vibration damping rubber pads acoustic upgrade
VO-PKG-09-00139 | PKG-09 | 269715.14 | 0 | Rejected | 0 | 2025-12-08 | 2025-12-25 | Drainage box culvert capacity expansion for 100-year flood event
VO-PKG-10-00410 | PKG-10 | 231689.26 | 0 | Pending Approval | 10 | 2025-12-08 |  | HVAC chilled water pipe rerouting around station concourse
VO-PKG-02-01962 | PKG-02 | 216288.21 | 186931.12 | Approved | 19 | 2025-12-09 | 2026-01-26 | TBM Cutterhead refurbishment and rock fissure sealing
VO-PKG-02-00542 | PKG-02 | 343082.1 | 331196.47 | Approved | 14 | 2025-12-10 | 2026-01-08 | TBM Cutterhead refurbishment and rock fissure sealing
VO-PKG-02-01902 | PKG-02 | 232753.2 | 0 | Rejected | 0 | 2025-12-10 | 2026-01-04 | TBM Cutterhead refurbishment and rock fissure sealing
VO-PKG-03-00763 | PKG-03 | 224590.28 | 0 | Pending Approval | 24 | 2025-12-10 |  | Viaduct pier foundation redesign due to utility clash
VO-PKG-04-00034 | PKG-04 | 59916.74 | 50430.77 | Approved | 56 | 2025-12-10 | 2026-01-23 | Station box diaphragm wall water ingress mitigation
VO-PKG-05-02425 | PKG-05 | 226105.43 | 203433.49 | Approved | 39 | 2025-12-11 | 2026-01-04 | HV substation redundancy transformer capacity upgrade
VO-PKG-08-00408 | PKG-08 | 32572.37 | 30700.3 | Approved | 28 | 2025-12-12 | 2026-02-06 | Track vibration damping rubber pads acoustic upgrade
VO-PKG-10-01720 | PKG-10 | 30414.59 | 0 | Pending Approval | 25 | 2025-12-12 |  | HVAC chilled water pipe rerouting around station concourse
VO-PKG-01-00201 | PKG-01 | 299575.28 | 249948.02 | Approved | 23 | 2025-12-13 | 2026-01-12 | Unforeseen soft ground stabilization and grouting
VO-PKG-02-02152 | PKG-02 | 83678.03 | 73492.62 | Approved | 9 | 2025-12-13 | 2026-01-08 | TBM Cutterhead refurbishment and rock fissure sealing
VO-PKG-05-02295 | PKG-05 | 133022.24 | 112030.14 | Approved | 44 | 2025-12-13 | 2026-01-09 | HV substation redundancy transformer capacity upgrade
VO-PKG-08-02368 | PKG-08 | 333335.84 | 325464.13 | Approved | 22 | 2025-12-13 | 2026-01-15 | Track vibration damping rubber pads acoustic upgrade
VO-PKG-10-00800 | PKG-10 | 337875.73 | 0 | Pending Approval | 13 | 2025-12-13 |  | HVAC chilled water pipe rerouting around station concourse
VO-PKG-01-00971 | PKG-01 | 318632.02 | 0 | Rejected | 0 | 2025-12-14 | 2026-01-23 | Unforeseen soft ground stabilization and grouting
VO-PKG-03-01063 | PKG-03 | 275076.32 | 0 | Pending Approval | 9 | 2025-12-14 |  | Viaduct pier foundation redesign due to utility clash
VO-PKG-05-01255 | PKG-05 | 235738.89 | 0 | Pending Approval | 33 | 2025-12-15 |  | HV substation redundancy transformer capacity upgrade
VO-PKG-02-02642 | PKG-02 | 143290.36 | 130030.65 | Approved | 24 | 2025-12-16 | 2026-01-31 | TBM Cutterhead refurbishment and rock fissure sealing
VO-PKG-03-01333 | PKG-03 | 103673.46 | 0 | Rejected | 0 | 2025-12-16 | 2026-01-28 | Viaduct pier foundation redesign due to utility clash
VO-PKG-03-02923 | PKG-03 | 182759.76 | 164810.4 | Approved | 38 | 2025-12-16 | 2026-01-02 | Viaduct pier foundation redesign due to utility clash
VO-PKG-08-00458 | PKG-08 | 88452.56 | 86586.13 | Approved | 18 | 2025-12-16 | 2026-01-20 | Track vibration damping rubber pads acoustic upgrade
VO-PKG-10-02750 | PKG-10 | 232881.75 | 212146.64 | Approved | 51 | 2025-12-16 | 2026-02-12 | HVAC chilled water pipe rerouting around station concourse
VO-PKG-01-01181 | PKG-01 | 83407.12 | 0 | Pending Approval | 31 | 2025-12-17 |  | Unforeseen soft ground stabilization and grouting
VO-PKG-04-01934 | PKG-04 | 308450.15 | 0 | Pending Approval | 36 | 2025-12-17 |  | Station box diaphragm wall water ingress mitigation
VO-PKG-10-00950 | PKG-10 | 115989.03 | 0 | Pending Approval | 1 | 2025-12-17 |  | HVAC chilled water pipe rerouting around station concourse
VO-PKG-09-00329 | PKG-09 | 159119.62 | 143278.42 | Approved | 14 | 2025-12-18 | 2026-01-20 | Drainage box culvert capacity expansion for 100-year flood event
VO-PKG-01-01071 | PKG-01 | 227761.23 | 193553.88 | Approved | 11 | 2025-12-19 | 2026-01-19 | Unforeseen soft ground stabilization and grouting
VO-PKG-02-01722 | PKG-02 | 314646.94 | 279160.7 | Approved | 5 | 2025-12-20 | 2026-01-08 | TBM Cutterhead refurbishment and rock fissure sealing
VO-PKG-09-02739 | PKG-09 | 258850.64 | 233928.99 | Approved | 38 | 2025-12-20 | 2026-01-13 | Drainage box culvert capacity expansion for 100-year flood event
VO-PKG-10-01510 | PKG-10 | 276888.02 | 0 | Pending Approval | 13 | 2025-12-20 |  | HVAC chilled water pipe rerouting around station concourse
VO-PKG-01-00811 | PKG-01 | 158106.45 | 142815.95 | Approved | 34 | 2025-12-21 | 2026-02-07 | Unforeseen soft ground stabilization and grouting
VO-PKG-02-00522 | PKG-02 | 118730 | 114278.75 | Approved | 5 | 2025-12-21 | 2026-01-05 | TBM Cutterhead refurbishment and rock fissure sealing
VO-PKG-07-01757 | PKG-07 | 66084.22 | 62538.8 | Approved | 30 | 2025-12-21 | 2026-02-06 | Fiber optic telemetry routing realignment along guideway
VO-PKG-07-01087 | PKG-07 | 121810.76 | 98468.19 | Approved | 43 | 2025-12-22 | 2026-01-10 | Fiber optic telemetry routing realignment along guideway
VO-PKG-07-02757 | PKG-07 | 180434.83 | 0 | Pending Approval | 37 | 2025-12-22 |  | Fiber optic telemetry routing realignment along guideway
VO-PKG-08-00198 | PKG-08 | 195414.93 | 0 | Pending Approval | 22 | 2025-12-22 |  | Track vibration damping rubber pads acoustic upgrade
VO-PKG-01-02281 | PKG-01 | 137908.28 | 0 | Pending Approval | 18 | 2025-12-23 |  | Unforeseen soft ground stabilization and grouting
VO-PKG-07-01557 | PKG-07 | 225649.88 | 190925.37 | Approved | 15 | 2025-12-23 | 2026-02-14 | Fiber optic telemetry routing realignment along guideway
VO-PKG-10-00580 | PKG-10 | 313943.92 | 0 | Pending Approval | 7 | 2025-12-23 |  | HVAC chilled water pipe rerouting around station concourse
VO-PKG-02-00292 | PKG-02 | 96606.09 | 0 | Rejected | 0 | 2025-12-24 | 2026-01-23 | TBM Cutterhead refurbishment and rock fissure sealing
VO-PKG-08-01728 | PKG-08 | 208604.26 | 188717.15 | Approved | 33 | 2025-12-24 | 2026-01-24 | Track vibration damping rubber pads acoustic upgrade
VO-PKG-10-01460 | PKG-10 | 179922.59 | 0 | Pending Approval | 37 | 2025-12-24 |  | HVAC chilled water pipe rerouting around station concourse
VO-PKG-02-02662 | PKG-02 | 66932.9 | 59145.08 | Approved | 18 | 2025-12-25 | 2026-01-10 | TBM Cutterhead refurbishment and rock fissure sealing
VO-PKG-06-01386 | PKG-06 | 238142.92 | 224632.81 | Approved | 30 | 2025-12-25 | 2026-01-24 | Additional smoke evacuation shafts in underground platforms
VO-PKG-04-02574 | PKG-04 | 82749.07 | 77877.16 | Approved | 10 | 2025-12-26 | 2026-02-17 | Station box diaphragm wall water ingress mitigation
VO-PKG-09-01279 | PKG-09 | 254111.03 | 237158.42 | Approved | 41 | 2025-12-26 | 2026-01-17 | Drainage box culvert capacity expansion for 100-year flood event
VO-PKG-02-02682 | PKG-02 | 21385.9 | 0 | Pending Approval | 29 | 2025-12-27 |  | TBM Cutterhead refurbishment and rock fissure sealing
VO-PKG-04-02314 | PKG-04 | 246144.92 | 205424.16 | Approved | 40 | 2025-12-27 | 2026-02-05 | Station box diaphragm wall water ingress mitigation
VO-PKG-09-02809 | PKG-09 | 263925.52 | 236109.1 | Approved | 28 | 2025-12-27 | 2026-02-10 | Drainage box culvert capacity expansion for 100-year flood event
VO-PKG-06-01556 | PKG-06 | 245330.33 | 0 | Pending Approval | 23 | 2025-12-28 |  | Additional smoke evacuation shafts in underground platforms
VO-PKG-02-00972 | PKG-02 | 42993.63 | 34818.92 | Approved | 31 | 2025-12-29 | 2026-02-03 | TBM Cutterhead refurbishment and rock fissure sealing
VO-PKG-02-02522 | PKG-02 | 107531.21 | 0 | Pending Approval | 1 | 2025-12-29 |  | TBM Cutterhead refurbishment and rock fissure sealing
VO-PKG-02-02812 | PKG-02 | 207049.79 | 0 | Pending Approval | 14 | 2025-12-29 |  | TBM Cutterhead refurbishment and rock fissure sealing
VO-PKG-05-00175 | PKG-05 | 104497.66 | 85642.27 | Approved | 36 | 2025-12-29 | 2026-02-07 | HV substation redundancy transformer capacity upgrade
VO-PKG-05-00215 | PKG-05 | 289333.29 | 256497.08 | Approved | 7 | 2025-12-29 | 2026-01-17 | HV substation redundancy transformer capacity upgrade
VO-PKG-07-02587 | PKG-07 | 201700.92 | 0 | Pending Approval | 0 | 2025-12-29 |  | Fiber optic telemetry routing realignment along guideway
VO-PKG-08-01588 | PKG-08 | 312623.09 | 0 | Pending Approval | 40 | 2025-12-29 |  | Track vibration damping rubber pads acoustic upgrade
VO-PKG-02-00192 | PKG-02 | 222726.97 | 0 | Pending Approval | 32 | 2025-12-30 |  | TBM Cutterhead refurbishment and rock fissure sealing
VO-PKG-03-00953 | PKG-03 | 112204.43 | 0 | Pending Approval | 21 | 2025-12-30 |  | Viaduct pier foundation redesign due to utility clash
VO-PKG-07-01977 | PKG-07 | 154803.76 | 141830.18 | Approved | 29 | 2025-12-30 | 2026-02-16 | Fiber optic telemetry routing realignment along guideway
VO-PKG-08-01248 | PKG-08 | 256312.03 | 245282.57 | Approved | 49 | 2025-12-30 | 2026-01-21 | Track vibration damping rubber pads acoustic upgrade
VO-PKG-09-02039 | PKG-09 | 212506.6 | 188691.68 | Approved | 23 | 2025-12-30 | 2026-01-22 | Drainage box culvert capacity expansion for 100-year flood event
VO-PKG-01-01281 | PKG-01 | 149570.79 | 133886.72 | Approved | 23 | 2025-12-31 | 2026-02-15 | Unforeseen soft ground stabilization and grouting
VO-PKG-03-01923 | PKG-03 | 263778.28 | 0 | Pending Approval | 44 | 2025-12-31 |  | Viaduct pier foundation redesign due to utility clash
VO-PKG-05-01895 | PKG-05 | 78470.62 | 0 | Pending Approval | 15 | 2025-12-31 |  | HV substation redundancy transformer capacity upgrade
VO-PKG-06-00546 | PKG-06 | 79715.51 | 0 | Pending Approval | 27 | 2025-12-31 |  | Additional smoke evacuation shafts in underground platforms
VO-PKG-06-01916 | PKG-06 | 150192.47 | 124523.65 | Approved | 5 | 2025-12-31 | 2026-01-31 | Additional smoke evacuation shafts in underground platforms
VO-PKG-09-00439 | PKG-09 | 248734.79 | 0 | Pending Approval | 4 | 2025-12-31 |  | Drainage box culvert capacity expansion for 100-year flood event
VO-PKG-06-01796 | PKG-06 | 344550.77 | 327888.67 | Approved | 37 | 2026-01-01 | 2026-02-04 | Additional smoke evacuation shafts in underground platforms
VO-PKG-08-00548 | PKG-08 | 329703.55 | 284848.95 | Approved | 28 | 2026-01-01 | 2026-02-27 | Track vibration damping rubber pads acoustic upgrade
VO-PKG-04-02214 | PKG-04 | 215083.01 | 0 | Pending Approval | 18 | 2026-01-02 |  | Station box diaphragm wall water ingress mitigation
VO-PKG-10-00710 | PKG-10 | 97155.59 | 80348.75 | Approved | 29 | 2026-01-02 | 2026-03-02 | HVAC chilled water pipe rerouting around station concourse
VO-PKG-01-00781 | PKG-01 | 154188.67 | 127336.94 | Approved | 14 | 2026-01-03 | 2026-02-16 | Unforeseen soft ground stabilization and grouting
VO-PKG-02-01302 | PKG-02 | 83519.19 | 76196.4 | Approved | 40 | 2026-01-03 | 2026-01-19 | TBM Cutterhead refurbishment and rock fissure sealing
VO-PKG-05-02095 | PKG-05 | 211691.3 | 0 | Pending Approval | 16 | 2026-01-03 |  | HV substation redundancy transformer capacity upgrade
VO-PKG-06-02486 | PKG-06 | 238860.23 | 221519.62 | Approved | 21 | 2026-01-03 | 2026-02-17 | Additional smoke evacuation shafts in underground platforms
VO-PKG-07-00557 | PKG-07 | 341309.07 | 280310.84 | Approved | 6 | 2026-01-03 | 2026-01-19 | Fiber optic telemetry routing realignment along guideway
VO-PKG-10-00150 | PKG-10 | 71734.88 | 61466.38 | Approved | 8 | 2026-01-03 | 2026-03-01 | HVAC chilled water pipe rerouting around station concourse
VO-PKG-10-01640 | PKG-10 | 270715.57 | 0 | Pending Approval | 29 | 2026-01-03 |  | HVAC chilled water pipe rerouting around station concourse
VO-PKG-02-01542 | PKG-02 | 112857.99 | 91319.51 | Approved | 21 | 2026-01-04 | 2026-01-21 | TBM Cutterhead refurbishment and rock fissure sealing
VO-PKG-04-00764 | PKG-04 | 227321.71 | 0 | Rejected | 0 | 2026-01-04 | 2026-01-23 | Station box diaphragm wall water ingress mitigation
VO-PKG-05-01095 | PKG-05 | 45474.68 | 44412.1 | Approved | 43 | 2026-01-04 | 2026-02-21 | HV substation redundancy transformer capacity upgrade
VO-PKG-08-02008 | PKG-08 | 211213.59 | 181784.68 | Approved | 8 | 2026-01-04 | 2026-02-06 | Track vibration damping rubber pads acoustic upgrade
VO-PKG-03-00063 | PKG-03 | 110308.79 | 0 | Pending Approval | 40 | 2026-01-05 |  | Viaduct pier foundation redesign due to utility clash
VO-PKG-08-02418 | PKG-08 | 176339.24 | 166660.95 | Approved | 25 | 2026-01-05 | 2026-02-08 | Track vibration damping rubber pads acoustic upgrade
VO-PKG-01-02241 | PKG-01 | 174256.8 | 145748.72 | Approved | 22 | 2026-01-06 | 2026-02-08 | Unforeseen soft ground stabilization and grouting
VO-PKG-07-00157 | PKG-07 | 308017.43 | 266637.83 | Approved | 34 | 2026-01-06 | 2026-02-11 | Fiber optic telemetry routing realignment along guideway
VO-PKG-01-02391 | PKG-01 | 265083.61 | 246951.33 | Approved | 42 | 2026-01-08 | 2026-01-23 | Unforeseen soft ground stabilization and grouting
VO-PKG-02-02102 | PKG-02 | 129192.78 | 114976.33 | Approved | 47 | 2026-01-08 | 2026-03-02 | TBM Cutterhead refurbishment and rock fissure sealing
VO-PKG-06-02356 | PKG-06 | 32106.41 | 30063.73 | Approved | 21 | 2026-01-08 | 2026-02-28 | Additional smoke evacuation shafts in underground platforms
VO-PKG-09-01539 | PKG-09 | 71330.37 | 60451.87 | Approved | 9 | 2026-01-08 | 2026-02-16 | Drainage box culvert capacity expansion for 100-year flood event
VO-PKG-10-00750 | PKG-10 | 71465.05 | 59228.41 | Approved | 48 | 2026-01-08 | 2026-02-23 | HVAC chilled water pipe rerouting around station concourse
VO-PKG-02-00752 | PKG-02 | 144352.22 | 124384.63 | Approved | 17 | 2026-01-09 | 2026-01-28 | TBM Cutterhead refurbishment and rock fissure sealing
VO-PKG-03-02713 | PKG-03 | 205223.34 | 0 | Rejected | 0 | 2026-01-09 | 2026-01-24 | Viaduct pier foundation redesign due to utility clash
VO-PKG-08-00668 | PKG-08 | 20773.12 | 19570.49 | Approved | 19 | 2026-01-09 | 2026-02-19 | Track vibration damping rubber pads acoustic upgrade
VO-PKG-10-00080 | PKG-10 | 228995.38 | 213822.58 | Approved | 35 | 2026-01-09 | 2026-02-19 | HVAC chilled water pipe rerouting around station concourse
VO-PKG-10-01170 | PKG-10 | 76679.91 | 61826.31 | Approved | 5 | 2026-01-09 | 2026-02-04 | HVAC chilled water pipe rerouting around station concourse
VO-PKG-10-01350 | PKG-10 | 305016.55 | 0 | Pending Approval | 33 | 2026-01-09 |  | HVAC chilled water pipe rerouting around station concourse
VO-PKG-03-01513 | PKG-03 | 153790.7 | 0 | Rejected | 0 | 2026-01-10 | 2026-01-22 | Viaduct pier foundation redesign due to utility clash
VO-PKG-03-02113 | PKG-03 | 84114.57 | 70527.79 | Approved | 28 | 2026-01-10 | 2026-02-11 | Viaduct pier foundation redesign due to utility clash
VO-PKG-06-00956 | PKG-06 | 92423.51 | 90355.19 | Approved | 54 | 2026-01-10 | 2026-02-05 | Additional smoke evacuation shafts in underground platforms
VO-PKG-03-00553 | PKG-03 | 80693.72 | 0 | Pending Approval | 16 | 2026-01-11 |  | Viaduct pier foundation redesign due to utility clash
VO-PKG-03-01073 | PKG-03 | 222306.98 | 0 | Pending Approval | 32 | 2026-01-11 |  | Viaduct pier foundation redesign due to utility clash
VO-PKG-04-01214 | PKG-04 | 67797.3 | 65403.02 | Approved | 27 | 2026-01-11 | 2026-02-25 | Station box diaphragm wall water ingress mitigation
VO-PKG-07-00927 | PKG-07 | 68317.82 | 0 | Rejected | 0 | 2026-01-11 | 2026-02-14 | Fiber optic telemetry routing realignment along guideway
VO-PKG-07-01167 | PKG-07 | 265340.23 | 0 | Rejected | 0 | 2026-01-11 | 2026-02-13 | Fiber optic telemetry routing realignment along guideway
VO-PKG-07-02797 | PKG-07 | 251723.33 | 228656.14 | Approved | 19 | 2026-01-11 | 2026-02-07 | Fiber optic telemetry routing realignment along guideway
VO-PKG-01-02911 | PKG-01 | 83136.31 | 0 | Pending Approval | 18 | 2026-01-12 |  | Unforeseen soft ground stabilization and grouting
VO-PKG-06-01216 | PKG-06 | 334766.79 | 272166.97 | Approved | 24 | 2026-01-12 | 2026-02-21 | Additional smoke evacuation shafts in underground platforms
VO-PKG-09-02909 | PKG-09 | 347736.48 | 0 | Pending Approval | 19 | 2026-01-12 |  | Drainage box culvert capacity expansion for 100-year flood event
VO-PKG-07-00597 | PKG-07 | 95195.33 | 90245.95 | Approved | 54 | 2026-01-13 | 2026-03-04 | Fiber optic telemetry routing realignment along guideway
VO-PKG-08-00698 | PKG-08 | 174568.15 | 153917.26 | Approved | 41 | 2026-01-13 | 2026-03-13 | Track vibration damping rubber pads acoustic upgrade
VO-PKG-04-01584 | PKG-04 | 286721.48 | 0 | Pending Approval | 44 | 2026-01-14 |  | Station box diaphragm wall water ingress mitigation
VO-PKG-04-01614 | PKG-04 | 243666.16 | 212343.65 | Approved | 51 | 2026-01-14 | 2026-02-02 | Station box diaphragm wall water ingress mitigation
VO-PKG-05-01835 | PKG-05 | 299431.15 | 0 | Pending Approval | 21 | 2026-01-14 |  | HV substation redundancy transformer capacity upgrade
VO-PKG-10-00820 | PKG-10 | 57087.35 | 49052.71 | Approved | 17 | 2026-01-14 | 2026-02-22 | HVAC chilled water pipe rerouting around station concourse
VO-PKG-02-02622 | PKG-02 | 25810.22 | 21222.79 | Approved | 20 | 2026-01-15 | 2026-03-11 | TBM Cutterhead refurbishment and rock fissure sealing
VO-PKG-07-00537 | PKG-07 | 335931.85 | 0 | Pending Approval | 22 | 2026-01-15 |  | Fiber optic telemetry routing realignment along guideway
VO-PKG-09-02159 | PKG-09 | 168442.83 | 163018.71 | Approved | 49 | 2026-01-15 | 2026-03-02 | Drainage box culvert capacity expansion for 100-year flood event
VO-PKG-03-01383 | PKG-03 | 117867.57 | 0 | Pending Approval | 33 | 2026-01-16 |  | Viaduct pier foundation redesign due to utility clash
VO-PKG-05-01155 | PKG-05 | 315140.41 | 278831.1 | Approved | 36 | 2026-01-16 | 2026-03-15 | HV substation redundancy transformer capacity upgrade
VO-PKG-07-01717 | PKG-07 | 142269.49 | 128142.81 | Approved | 23 | 2026-01-16 | 2026-02-15 | Fiber optic telemetry routing realignment along guideway
VO-PKG-04-02954 | PKG-04 | 213948.82 | 199434.19 | Approved | 56 | 2026-01-17 | 2026-02-10 | Station box diaphragm wall water ingress mitigation
VO-PKG-10-00100 | PKG-10 | 275561.44 | 249505.25 | Approved | 15 | 2026-01-17 | 2026-02-09 | HVAC chilled water pipe rerouting around station concourse
VO-PKG-01-01141 | PKG-01 | 66496.82 | 57790.44 | Approved | 26 | 2026-01-18 | 2026-02-21 | Unforeseen soft ground stabilization and grouting
VO-PKG-01-01831 | PKG-01 | 170260.65 | 158492.65 | Approved | 45 | 2026-01-18 | 2026-03-17 | Unforeseen soft ground stabilization and grouting
VO-PKG-02-02412 | PKG-02 | 292841.5 | 259635.41 | Approved | 59 | 2026-01-18 | 2026-02-07 | TBM Cutterhead refurbishment and rock fissure sealing
VO-PKG-04-01564 | PKG-04 | 302148.8 | 254733.4 | Approved | 5 | 2026-01-18 | 2026-03-10 | Station box diaphragm wall water ingress mitigation
VO-PKG-04-02634 | PKG-04 | 145890.47 | 0 | Rejected | 0 | 2026-01-18 | 2026-02-07 | Station box diaphragm wall water ingress mitigation
VO-PKG-06-01006 | PKG-06 | 53705.65 | 43654.72 | Approved | 9 | 2026-01-18 | 2026-03-11 | Additional smoke evacuation shafts in underground platforms
VO-PKG-08-00538 | PKG-08 | 66332.56 | 62581.74 | Approved | 46 | 2026-01-18 | 2026-02-09 | Track vibration damping rubber pads acoustic upgrade
VO-PKG-09-00979 | PKG-09 | 251219.29 | 237988.59 | Approved | 44 | 2026-01-18 | 2026-02-21 | Drainage box culvert capacity expansion for 100-year flood event
VO-PKG-02-02882 | PKG-02 | 330095.46 | 304752.37 | Approved | 18 | 2026-01-19 | 2026-03-12 | TBM Cutterhead refurbishment and rock fissure sealing
VO-PKG-03-00523 | PKG-03 | 250708.62 | 0 | Pending Approval | 29 | 2026-01-19 |  | Viaduct pier foundation redesign due to utility clash
VO-PKG-05-02935 | PKG-05 | 40227.75 | 0 | Rejected | 0 | 2026-01-19 | 2026-02-18 | HV substation redundancy transformer capacity upgrade
VO-PKG-01-00591 | PKG-01 | 128147.51 | 119003.93 | Approved | 28 | 2026-01-20 | 2026-02-07 | Unforeseen soft ground stabilization and grouting
VO-PKG-04-00404 | PKG-04 | 17112.16 | 14057.54 | Approved | 29 | 2026-01-20 | 2026-03-14 | Station box diaphragm wall water ingress mitigation
VO-PKG-05-01965 | PKG-05 | 95761.23 | 89329.91 | Approved | 27 | 2026-01-20 | 2026-03-07 | HV substation redundancy transformer capacity upgrade
VO-PKG-06-01226 | PKG-06 | 246595.27 | 231593.26 | Approved | 40 | 2026-01-20 | 2026-03-13 | Additional smoke evacuation shafts in underground platforms
VO-PKG-03-01803 | PKG-03 | 340052.34 | 0 | Pending Approval | 33 | 2026-01-21 |  | Viaduct pier foundation redesign due to utility clash
VO-PKG-04-01234 | PKG-04 | 42579.67 | 0 | Rejected | 0 | 2026-01-21 | 2026-02-05 | Station box diaphragm wall water ingress mitigation
VO-PKG-08-01008 | PKG-08 | 302547.71 | 283259.75 | Approved | 51 | 2026-01-21 | 2026-02-28 | Track vibration damping rubber pads acoustic upgrade
VO-PKG-08-01438 | PKG-08 | 320393.29 | 0 | Pending Approval | 4 | 2026-01-21 |  | Track vibration damping rubber pads acoustic upgrade
VO-PKG-09-00669 | PKG-09 | 233852.94 | 0 | Pending Approval | 29 | 2026-01-21 |  | Drainage box culvert capacity expansion for 100-year flood event
VO-PKG-05-02605 | PKG-05 | 190668.27 | 0 | Pending Approval | 35 | 2026-01-22 |  | HV substation redundancy transformer capacity upgrade
VO-PKG-06-02636 | PKG-06 | 204869.43 | 0 | Pending Approval | 42 | 2026-01-22 |  | Additional smoke evacuation shafts in underground platforms
VO-PKG-01-00211 | PKG-01 | 348486 | 315171.37 | Approved | 14 | 2026-01-23 | 2026-03-13 | Unforeseen soft ground stabilization and grouting
VO-PKG-02-01432 | PKG-02 | 230790.29 | 207844.19 | Approved | 40 | 2026-01-23 | 2026-02-14 | TBM Cutterhead refurbishment and rock fissure sealing
VO-PKG-07-01707 | PKG-07 | 40134.5 | 33206.54 | Approved | 8 | 2026-01-23 | 2026-02-15 | Fiber optic telemetry routing realignment along guideway
VO-PKG-08-02268 | PKG-08 | 192064.74 | 0 | Rejected | 0 | 2026-01-23 | 2026-02-14 | Track vibration damping rubber pads acoustic upgrade
VO-PKG-10-02000 | PKG-10 | 323689.06 | 270625.17 | Approved | 51 | 2026-01-23 | 2026-03-19 | HVAC chilled water pipe rerouting around station concourse
VO-PKG-02-01402 | PKG-02 | 91307.1 | 0 | Pending Approval | 4 | 2026-01-24 |  | TBM Cutterhead refurbishment and rock fissure sealing
VO-PKG-08-01098 | PKG-08 | 202936.63 | 0 | Pending Approval | 6 | 2026-01-24 |  | Track vibration damping rubber pads acoustic upgrade
VO-PKG-09-02989 | PKG-09 | 224031.93 | 0 | Pending Approval | 13 | 2026-01-24 |  | Drainage box culvert capacity expansion for 100-year flood event
VO-PKG-01-01191 | PKG-01 | 250583.85 | 0 | Pending Approval | 2 | 2026-01-25 |  | Unforeseen soft ground stabilization and grouting
VO-PKG-03-01233 | PKG-03 | 21133.55 | 19506.31 | Approved | 27 | 2026-01-25 | 2026-03-25 | Viaduct pier foundation redesign due to utility clash
VO-PKG-05-01295 | PKG-05 | 59531.13 | 48993.19 | Approved | 48 | 2026-01-25 | 2026-03-01 | HV substation redundancy transformer capacity upgrade
VO-PKG-06-00686 | PKG-06 | 196280.68 | 175031.48 | Approved | 57 | 2026-01-25 | 2026-02-19 | Additional smoke evacuation shafts in underground platforms
VO-PKG-07-01317 | PKG-07 | 111088.66 | 0 | Pending Approval | 23 | 2026-01-25 |  | Fiber optic telemetry routing realignment along guideway
VO-PKG-08-01348 | PKG-08 | 149517.18 | 139089.3 | Approved | 45 | 2026-01-25 | 2026-03-21 | Track vibration damping rubber pads acoustic upgrade
VO-PKG-09-01699 | PKG-09 | 339734.95 | 298430.27 | Approved | 59 | 2026-01-25 | 2026-03-22 | Drainage box culvert capacity expansion for 100-year flood event
VO-PKG-10-00290 | PKG-10 | 338982.91 | 300547.68 | Approved | 31 | 2026-01-25 | 2026-02-10 | HVAC chilled water pipe rerouting around station concourse
VO-PKG-04-01484 | PKG-04 | 225900.97 | 203139.14 | Approved | 18 | 2026-01-26 | 2026-02-15 | Station box diaphragm wall water ingress mitigation
VO-PKG-08-02168 | PKG-08 | 17920.94 | 17513.68 | Approved | 20 | 2026-01-26 | 2026-03-16 | Track vibration damping rubber pads acoustic upgrade
VO-PKG-09-01369 | PKG-09 | 74719.94 | 73145.04 | Approved | 54 | 2026-01-26 | 2026-02-22 | Drainage box culvert capacity expansion for 100-year flood event
VO-PKG-10-02470 | PKG-10 | 38821.26 | 0 | Pending Approval | 5 | 2026-01-26 |  | HVAC chilled water pipe rerouting around station concourse
VO-PKG-06-02206 | PKG-06 | 96397.6 | 0 | Rejected | 0 | 2026-01-28 | 2026-03-01 | Additional smoke evacuation shafts in underground platforms
VO-PKG-01-01271 | PKG-01 | 195593.06 | 0 | Pending Approval | 15 | 2026-01-29 |  | Unforeseen soft ground stabilization and grouting
VO-PKG-01-02051 | PKG-01 | 63386.68 | 0 | Pending Approval | 26 | 2026-01-29 |  | Unforeseen soft ground stabilization and grouting
VO-PKG-05-02955 | PKG-05 | 201076.41 | 0 | Rejected | 0 | 2026-01-29 | 2026-03-11 | HV substation redundancy transformer capacity upgrade
VO-PKG-07-02217 | PKG-07 | 305782.31 | 297691.02 | Approved | 33 | 2026-01-29 | 2026-02-18 | Fiber optic telemetry routing realignment along guideway
VO-PKG-09-00899 | PKG-09 | 305790.09 | 284360.56 | Approved | 47 | 2026-01-29 | 2026-02-23 | Drainage box culvert capacity expansion for 100-year flood event
VO-PKG-09-01739 | PKG-09 | 23439.09 | 21242.1 | Approved | 30 | 2026-01-29 | 2026-02-15 | Drainage box culvert capacity expansion for 100-year flood event
VO-PKG-06-02556 | PKG-06 | 200490.61 | 175499.89 | Approved | 48 | 2026-01-30 | 2026-03-23 | Additional smoke evacuation shafts in underground platforms
VO-PKG-07-00487 | PKG-07 | 62755.82 | 58137.23 | Approved | 29 | 2026-01-30 | 2026-03-04 | Fiber optic telemetry routing realignment along guideway
VO-PKG-07-01387 | PKG-07 | 26201.92 | 21395.26 | Approved | 26 | 2026-01-30 | 2026-03-07 | Fiber optic telemetry routing realignment along guideway
VO-PKG-07-01657 | PKG-07 | 342128.09 | 0 | Pending Approval | 28 | 2026-01-30 |  | Fiber optic telemetry routing realignment along guideway
VO-PKG-10-01940 | PKG-10 | 164120.29 | 141038.67 | Approved | 34 | 2026-01-30 | 2026-02-17 | HVAC chilled water pipe rerouting around station concourse
VO-PKG-07-02677 | PKG-07 | 101075.91 | 85601.24 | Approved | 8 | 2026-02-01 | 2026-03-17 | Fiber optic telemetry routing realignment along guideway
VO-PKG-10-02200 | PKG-10 | 127131.54 | 108551.73 | Approved | 10 | 2026-02-01 | 2026-03-09 | HVAC chilled water pipe rerouting around station concourse
VO-PKG-01-00701 | PKG-01 | 286403.31 | 249714.6 | Approved | 58 | 2026-02-02 | 2026-02-23 | Unforeseen soft ground stabilization and grouting
VO-PKG-02-00702 | PKG-02 | 334090.23 | 281771.83 | Approved | 50 | 2026-02-02 | 2026-02-19 | TBM Cutterhead refurbishment and rock fissure sealing
VO-PKG-08-00248 | PKG-08 | 48348.99 | 0 | Pending Approval | 2 | 2026-02-02 |  | Track vibration damping rubber pads acoustic upgrade
VO-PKG-02-02072 | PKG-02 | 168981.7 | 142596.76 | Approved | 15 | 2026-02-03 | 2026-03-14 | TBM Cutterhead refurbishment and rock fissure sealing
VO-PKG-10-01660 | PKG-10 | 166684.45 | 133787.49 | Approved | 34 | 2026-02-03 | 2026-02-26 | HVAC chilled water pipe rerouting around station concourse
VO-PKG-03-02073 | PKG-03 | 183528.03 | 169316.08 | Approved | 54 | 2026-02-04 | 2026-03-10 | Viaduct pier foundation redesign due to utility clash
VO-PKG-06-02456 | PKG-06 | 123187.11 | 109483.68 | Approved | 25 | 2026-02-04 | 2026-03-26 | Additional smoke evacuation shafts in underground platforms
VO-PKG-07-01947 | PKG-07 | 46211.26 | 40698.88 | Approved | 16 | 2026-02-04 | 2026-03-06 | Fiber optic telemetry routing realignment along guideway
VO-PKG-09-01039 | PKG-09 | 125304.47 | 100833.79 | Approved | 16 | 2026-02-04 | 2026-03-24 | Drainage box culvert capacity expansion for 100-year flood event
VO-PKG-06-01576 | PKG-06 | 130134.56 | 113000.28 | Approved | 8 | 2026-02-05 | 2026-03-09 | Additional smoke evacuation shafts in underground platforms
VO-PKG-08-02088 | PKG-08 | 100939.95 | 84312.74 | Approved | 14 | 2026-02-05 | 2026-03-09 | Track vibration damping rubber pads acoustic upgrade
VO-PKG-10-01110 | PKG-10 | 50089.81 | 0 | Pending Approval | 18 | 2026-02-05 |  | HVAC chilled water pipe rerouting around station concourse
VO-PKG-02-02512 | PKG-02 | 163755.97 | 0 | Rejected | 0 | 2026-02-06 | 2026-02-28 | TBM Cutterhead refurbishment and rock fissure sealing
VO-PKG-03-02293 | PKG-03 | 145603.58 | 0 | Rejected | 0 | 2026-02-06 | 2026-02-28 | Viaduct pier foundation redesign due to utility clash
VO-PKG-04-02834 | PKG-04 | 55989.95 | 46997.02 | Approved | 26 | 2026-02-06 | 2026-03-30 | Station box diaphragm wall water ingress mitigation
VO-PKG-09-01299 | PKG-09 | 191909.98 | 0 | Rejected | 0 | 2026-02-06 | 2026-03-01 | Drainage box culvert capacity expansion for 100-year flood event
VO-PKG-06-02626 | PKG-06 | 57909.79 | 52095.65 | Approved | 41 | 2026-02-07 | 2026-03-07 | Additional smoke evacuation shafts in underground platforms
VO-PKG-07-02347 | PKG-07 | 38938.42 | 33256.4 | Approved | 44 | 2026-02-07 | 2026-02-25 | Fiber optic telemetry routing realignment along guideway
VO-PKG-08-02398 | PKG-08 | 338203.65 | 0 | Rejected | 0 | 2026-02-07 | 2026-03-04 | Track vibration damping rubber pads acoustic upgrade
VO-PKG-10-00130 | PKG-10 | 94161.04 | 0 | Pending Approval | 28 | 2026-02-07 |  | HVAC chilled water pipe rerouting around station concourse
VO-PKG-10-01280 | PKG-10 | 144273.25 | 0 | Pending Approval | 43 | 2026-02-07 |  | HVAC chilled water pipe rerouting around station concourse
VO-PKG-01-02311 | PKG-01 | 38585.65 | 36089.7 | Approved | 53 | 2026-02-08 | 2026-03-23 | Unforeseen soft ground stabilization and grouting
VO-PKG-09-01979 | PKG-09 | 206994.83 | 185070.44 | Approved | 43 | 2026-02-09 | 2026-03-28 | Drainage box culvert capacity expansion for 100-year flood event
VO-PKG-01-01381 | PKG-01 | 272739.4 | 241183.12 | Approved | 9 | 2026-02-10 | 2026-02-28 | Unforeseen soft ground stabilization and grouting
VO-PKG-03-01693 | PKG-03 | 119482.45 | 0 | Pending Approval | 29 | 2026-02-10 |  | Viaduct pier foundation redesign due to utility clash
VO-PKG-07-00847 | PKG-07 | 171394.09 | 143202.98 | Approved | 48 | 2026-02-11 | 2026-03-01 | Fiber optic telemetry routing realignment along guideway
VO-PKG-08-02758 | PKG-08 | 56415.22 | 0 | Pending Approval | 10 | 2026-02-11 |  | Track vibration damping rubber pads acoustic upgrade
VO-PKG-02-00482 | PKG-02 | 304237.48 | 259664.95 | Approved | 44 | 2026-02-12 | 2026-03-30 | TBM Cutterhead refurbishment and rock fissure sealing
VO-PKG-02-02532 | PKG-02 | 55158.64 | 0 | Pending Approval | 17 | 2026-02-12 |  | TBM Cutterhead refurbishment and rock fissure sealing
VO-PKG-04-02644 | PKG-04 | 50203.05 | 44108.22 | Approved | 49 | 2026-02-12 | 2026-03-18 | Station box diaphragm wall water ingress mitigation
VO-PKG-05-00735 | PKG-05 | 258286.34 | 0 | Pending Approval | 21 | 2026-02-12 |  | HV substation redundancy transformer capacity upgrade
VO-PKG-08-02668 | PKG-08 | 259573.16 | 248237.9 | Approved | 32 | 2026-02-12 | 2026-03-19 | Track vibration damping rubber pads acoustic upgrade
VO-PKG-08-00528 | PKG-08 | 92695.38 | 0 | Pending Approval | 13 | 2026-02-13 |  | Track vibration damping rubber pads acoustic upgrade
VO-PKG-02-02292 | PKG-02 | 158457.77 | 0 | Rejected | 0 | 2026-02-14 | 2026-03-14 | TBM Cutterhead refurbishment and rock fissure sealing
VO-PKG-07-00477 | PKG-07 | 336474.46 | 293351.86 | Approved | 43 | 2026-02-14 | 2026-04-01 | Fiber optic telemetry routing realignment along guideway
VO-PKG-09-00079 | PKG-09 | 323377.01 | 0 | Pending Approval | 0 | 2026-02-15 |  | Drainage box culvert capacity expansion for 100-year flood event
VO-PKG-02-01082 | PKG-02 | 20771.61 | 0 | Rejected | 0 | 2026-02-16 | 2026-02-26 | TBM Cutterhead refurbishment and rock fissure sealing
VO-PKG-03-02463 | PKG-03 | 199335.07 | 166996.42 | Approved | 8 | 2026-02-16 | 2026-04-02 | Viaduct pier foundation redesign due to utility clash
VO-PKG-07-01827 | PKG-07 | 60946.93 | 0 | Rejected | 0 | 2026-02-16 | 2026-03-31 | Fiber optic telemetry routing realignment along guideway
VO-PKG-10-00260 | PKG-10 | 297185.13 | 273071 | Approved | 28 | 2026-02-17 | 2026-03-28 | HVAC chilled water pipe rerouting around station concourse
VO-PKG-10-02800 | PKG-10 | 109037.05 | 97798.83 | Approved | 45 | 2026-02-17 | 2026-03-07 | HVAC chilled water pipe rerouting around station concourse
VO-PKG-07-02737 | PKG-07 | 137105.72 | 123839.23 | Approved | 34 | 2026-02-18 | 2026-04-15 | Fiber optic telemetry routing realignment along guideway
VO-PKG-02-02962 | PKG-02 | 198598.73 | 194148.81 | Approved | 45 | 2026-02-19 | 2026-03-06 | TBM Cutterhead refurbishment and rock fissure sealing
VO-PKG-04-02514 | PKG-04 | 146506.02 | 119806.9 | Approved | 55 | 2026-02-19 | 2026-04-18 | Station box diaphragm wall water ingress mitigation
VO-PKG-04-02904 | PKG-04 | 260691.54 | 0 | Pending Approval | 10 | 2026-02-19 |  | Station box diaphragm wall water ingress mitigation
VO-PKG-06-02526 | PKG-06 | 118838.59 | 0 | Pending Approval | 9 | 2026-02-19 |  | Additional smoke evacuation shafts in underground platforms
VO-PKG-07-00417 | PKG-07 | 237632.24 | 191146.43 | Approved | 59 | 2026-02-19 | 2026-04-10 | Fiber optic telemetry routing realignment along guideway
VO-PKG-09-01779 | PKG-09 | 194869.41 | 0 | Pending Approval | 31 | 2026-02-19 |  | Drainage box culvert capacity expansion for 100-year flood event
VO-PKG-06-01096 | PKG-06 | 67881.57 | 0 | Pending Approval | 6 | 2026-02-20 |  | Additional smoke evacuation shafts in underground platforms
VO-PKG-09-00059 | PKG-09 | 228810.72 | 184498.01 | Approved | 17 | 2026-02-20 | 2026-04-09 | Drainage box culvert capacity expansion for 100-year flood event
VO-PKG-10-02580 | PKG-10 | 208746.9 | 189528.56 | Approved | 10 | 2026-02-20 | 2026-03-25 | HVAC chilled water pipe rerouting around station concourse
VO-PKG-01-01561 | PKG-01 | 298474.77 | 0 | Pending Approval | 27 | 2026-02-21 |  | Unforeseen soft ground stabilization and grouting
VO-PKG-04-01764 | PKG-04 | 188629.93 | 0 | Rejected | 0 | 2026-02-22 | 2026-04-02 | Station box diaphragm wall water ingress mitigation
VO-PKG-05-01545 | PKG-05 | 347897.86 | 0 | Pending Approval | 15 | 2026-02-22 |  | HV substation redundancy transformer capacity upgrade
VO-PKG-01-00661 | PKG-01 | 268521.16 | 229717.15 | Approved | 53 | 2026-02-23 | 2026-04-06 | Unforeseen soft ground stabilization and grouting
VO-PKG-05-00845 | PKG-05 | 113186.73 | 97610 | Approved | 20 | 2026-02-23 | 2026-04-03 | HV substation redundancy transformer capacity upgrade
VO-PKG-08-00638 | PKG-08 | 141810.75 | 127817.5 | Approved | 17 | 2026-02-23 | 2026-04-07 | Track vibration damping rubber pads acoustic upgrade
VO-PKG-09-01659 | PKG-09 | 53206.74 | 44906.25 | Approved | 39 | 2026-02-23 | 2026-04-17 | Drainage box culvert capacity expansion for 100-year flood event
VO-PKG-05-01275 | PKG-05 | 94596.5 | 0 | Rejected | 0 | 2026-02-24 | 2026-03-18 | HV substation redundancy transformer capacity upgrade
VO-PKG-07-02907 | PKG-07 | 214135.63 | 194505.4 | Approved | 11 | 2026-02-24 | 2026-03-16 | Fiber optic telemetry routing realignment along guideway
VO-PKG-09-00809 | PKG-09 | 109757.13 | 0 | Pending Approval | 42 | 2026-02-24 |  | Drainage box culvert capacity expansion for 100-year flood event
VO-PKG-01-00411 | PKG-01 | 326532.28 | 309564.28 | Approved | 28 | 2026-02-25 | 2026-03-12 | Unforeseen soft ground stabilization and grouting
VO-PKG-05-02765 | PKG-05 | 66037.18 | 60061 | Approved | 56 | 2026-02-25 | 2026-04-19 | HV substation redundancy transformer capacity upgrade
VO-PKG-06-01616 | PKG-06 | 273340.06 | 219467.85 | Approved | 56 | 2026-02-25 | 2026-04-20 | Additional smoke evacuation shafts in underground platforms
VO-PKG-07-00227 | PKG-07 | 215771.85 | 198059.87 | Approved | 25 | 2026-02-25 | 2026-04-13 | Fiber optic telemetry routing realignment along guideway
VO-PKG-08-00628 | PKG-08 | 348144.72 | 339558.58 | Approved | 57 | 2026-02-25 | 2026-04-19 | Track vibration damping rubber pads acoustic upgrade
VO-PKG-08-01798 | PKG-08 | 127549.92 | 0 | Pending Approval | 4 | 2026-02-25 |  | Track vibration damping rubber pads acoustic upgrade
VO-PKG-01-02601 | PKG-01 | 203893.19 | 0 | Pending Approval | 1 | 2026-02-26 |  | Unforeseen soft ground stabilization and grouting
VO-PKG-07-02687 | PKG-07 | 323127.25 | 0 | Pending Approval | 6 | 2026-02-26 |  | Fiber optic telemetry routing realignment along guideway
VO-PKG-02-02132 | PKG-02 | 241752.34 | 221299.25 | Approved | 44 | 2026-02-27 | 2026-04-14 | TBM Cutterhead refurbishment and rock fissure sealing
VO-PKG-05-00285 | PKG-05 | 203828.74 | 0 | Rejected | 0 | 2026-02-27 | 2026-03-29 | HV substation redundancy transformer capacity upgrade
VO-PKG-07-01837 | PKG-07 | 225396.97 | 0 | Rejected | 0 | 2026-02-27 | 2026-04-11 | Fiber optic telemetry routing realignment along guideway
VO-PKG-01-00631 | PKG-01 | 341282.09 | 316388.56 | Approved | 42 | 2026-02-28 | 2026-04-12 | Unforeseen soft ground stabilization and grouting
VO-PKG-01-02651 | PKG-01 | 60705.13 | 53598.96 | Approved | 50 | 2026-02-28 | 2026-04-20 | Unforeseen soft ground stabilization and grouting
VO-PKG-06-02696 | PKG-06 | 70499.57 | 68942.22 | Approved | 9 | 2026-02-28 | 2026-03-31 | Additional smoke evacuation shafts in underground platforms
VO-PKG-08-02498 | PKG-08 | 179425.88 | 174144.57 | Approved | 43 | 2026-02-28 | 2026-04-02 | Track vibration damping rubber pads acoustic upgrade
VO-PKG-09-01349 | PKG-09 | 329673.25 | 308399.25 | Approved | 18 | 2026-02-28 | 2026-04-22 | Drainage box culvert capacity expansion for 100-year flood event
VO-PKG-09-02299 | PKG-09 | 335034.89 | 328268.17 | Approved | 16 | 2026-02-28 | 2026-04-06 | Drainage box culvert capacity expansion for 100-year flood event
VO-PKG-03-01253 | PKG-03 | 332353.66 | 294118.62 | Approved | 13 | 2026-03-01 | 2026-04-16 | Viaduct pier foundation redesign due to utility clash
VO-PKG-04-00394 | PKG-04 | 102618.4 | 93309.01 | Approved | 40 | 2026-03-01 | 2026-03-23 | Station box diaphragm wall water ingress mitigation
VO-PKG-04-01184 | PKG-04 | 112311.62 | 0 | Pending Approval | 2 | 2026-03-01 |  | Station box diaphragm wall water ingress mitigation
VO-PKG-09-00879 | PKG-09 | 346780.86 | 0 | Pending Approval | 31 | 2026-03-01 |  | Drainage box culvert capacity expansion for 100-year flood event
VO-PKG-03-00453 | PKG-03 | 179143.91 | 147138.6 | Approved | 47 | 2026-03-02 | 2026-03-23 | Viaduct pier foundation redesign due to utility clash
VO-PKG-03-02873 | PKG-03 | 214494.17 | 195005.2 | Approved | 39 | 2026-03-03 | 2026-04-29 | Viaduct pier foundation redesign due to utility clash
VO-PKG-09-00939 | PKG-09 | 72341.4 | 61175.18 | Approved | 53 | 2026-03-03 | 2026-04-25 | Drainage box culvert capacity expansion for 100-year flood event
VO-PKG-03-00573 | PKG-03 | 182756.49 | 0 | Pending Approval | 25 | 2026-03-04 |  | Viaduct pier foundation redesign due to utility clash
VO-PKG-04-01654 | PKG-04 | 293233.53 | 260289.8 | Approved | 46 | 2026-03-04 | 2026-03-22 | Station box diaphragm wall water ingress mitigation
VO-PKG-10-02810 | PKG-10 | 213491.93 | 189446.87 | Approved | 42 | 2026-03-04 | 2026-04-23 | HVAC chilled water pipe rerouting around station concourse
VO-PKG-03-00683 | PKG-03 | 118804.27 | 0 | Pending Approval | 14 | 2026-03-05 |  | Viaduct pier foundation redesign due to utility clash
VO-PKG-04-02204 | PKG-04 | 275076.04 | 0 | Pending Approval | 0 | 2026-03-05 |  | Station box diaphragm wall water ingress mitigation
VO-PKG-04-02194 | PKG-04 | 41556.95 | 35682 | Approved | 10 | 2026-03-06 | 2026-04-04 | Station box diaphragm wall water ingress mitigation
VO-PKG-05-00905 | PKG-05 | 46670.75 | 43886.87 | Approved | 15 | 2026-03-06 | 2026-04-06 | HV substation redundancy transformer capacity upgrade
VO-PKG-05-01605 | PKG-05 | 318381.99 | 0 | Pending Approval | 22 | 2026-03-06 |  | HV substation redundancy transformer capacity upgrade
VO-PKG-06-00706 | PKG-06 | 96787.28 | 94551.89 | Approved | 34 | 2026-03-06 | 2026-03-22 | Additional smoke evacuation shafts in underground platforms
VO-PKG-06-00866 | PKG-06 | 96207.88 | 0 | Pending Approval | 12 | 2026-03-06 |  | Additional smoke evacuation shafts in underground platforms
VO-PKG-03-01083 | PKG-03 | 128677.61 | 109470.71 | Approved | 5 | 2026-03-07 | 2026-04-03 | Viaduct pier foundation redesign due to utility clash
VO-PKG-05-00105 | PKG-05 | 97559.12 | 91268.37 | Approved | 15 | 2026-03-07 | 2026-03-31 | HV substation redundancy transformer capacity upgrade
VO-PKG-05-02275 | PKG-05 | 226637.71 | 0 | Rejected | 0 | 2026-03-07 | 2026-04-15 | HV substation redundancy transformer capacity upgrade
VO-PKG-06-00716 | PKG-06 | 69336.32 | 59326.39 | Approved | 8 | 2026-03-07 | 2026-04-07 | Additional smoke evacuation shafts in underground platforms
VO-PKG-03-02473 | PKG-03 | 132786.44 | 0 | Pending Approval | 21 | 2026-03-08 |  | Viaduct pier foundation redesign due to utility clash
VO-PKG-04-01834 | PKG-04 | 214005.85 | 0 | Pending Approval | 14 | 2026-03-08 |  | Station box diaphragm wall water ingress mitigation
VO-PKG-06-01806 | PKG-06 | 78221.13 | 0 | Pending Approval | 16 | 2026-03-08 |  | Additional smoke evacuation shafts in underground platforms
VO-PKG-09-00429 | PKG-09 | 29862.02 | 24854.2 | Approved | 56 | 2026-03-08 | 2026-04-04 | Drainage box culvert capacity expansion for 100-year flood event
VO-PKG-04-00154 | PKG-04 | 266636.38 | 0 | Rejected | 0 | 2026-03-09 | 2026-04-08 | Station box diaphragm wall water ingress mitigation
VO-PKG-04-02164 | PKG-04 | 263506.12 | 0 | Rejected | 0 | 2026-03-09 | 2026-04-12 | Station box diaphragm wall water ingress mitigation
VO-PKG-01-01171 | PKG-01 | 296377.36 | 261394.9 | Approved | 20 | 2026-03-10 | 2026-03-26 | Unforeseen soft ground stabilization and grouting
VO-PKG-05-02385 | PKG-05 | 272765.88 | 0 | Rejected | 0 | 2026-03-10 | 2026-04-13 | HV substation redundancy transformer capacity upgrade
VO-PKG-08-00948 | PKG-08 | 198388.53 | 167719.18 | Approved | 9 | 2026-03-10 | 2026-04-20 | Track vibration damping rubber pads acoustic upgrade
VO-PKG-09-02709 | PKG-09 | 255431.95 | 0 | Rejected | 0 | 2026-03-10 | 2026-04-23 | Drainage box culvert capacity expansion for 100-year flood event
VO-PKG-01-02271 | PKG-01 | 332355.07 | 276766.88 | Approved | 38 | 2026-03-11 | 2026-03-27 | Unforeseen soft ground stabilization and grouting
VO-PKG-04-01684 | PKG-04 | 88258.61 | 0 | Pending Approval | 4 | 2026-03-11 |  | Station box diaphragm wall water ingress mitigation
VO-PKG-05-02545 | PKG-05 | 75766.36 | 0 | Pending Approval | 6 | 2026-03-11 |  | HV substation redundancy transformer capacity upgrade
VO-PKG-08-02478 | PKG-08 | 22900.04 | 19051.96 | Approved | 26 | 2026-03-11 | 2026-04-18 | Track vibration damping rubber pads acoustic upgrade
VO-PKG-09-00379 | PKG-09 | 130648.72 | 0 | Pending Approval | 32 | 2026-03-11 |  | Drainage box culvert capacity expansion for 100-year flood event
VO-PKG-10-01090 | PKG-10 | 118661.29 | 0 | Rejected | 0 | 2026-03-11 | 2026-03-27 | HVAC chilled water pipe rerouting around station concourse
VO-PKG-10-02610 | PKG-10 | 20483.32 | 18432.38 | Approved | 21 | 2026-03-11 | 2026-03-27 | HVAC chilled water pipe rerouting around station concourse
VO-PKG-01-00621 | PKG-01 | 269006.32 | 226490.68 | Approved | 58 | 2026-03-12 | 2026-04-17 | Unforeseen soft ground stabilization and grouting
VO-PKG-02-01642 | PKG-02 | 262191.87 | 225221.63 | Approved | 17 | 2026-03-12 | 2026-05-06 | TBM Cutterhead refurbishment and rock fissure sealing
VO-PKG-04-02064 | PKG-04 | 207399.7 | 197129.16 | Approved | 11 | 2026-03-12 | 2026-04-01 | Station box diaphragm wall water ingress mitigation
VO-PKG-02-00202 | PKG-02 | 301382.49 | 271068.42 | Approved | 46 | 2026-03-13 | 2026-05-09 | TBM Cutterhead refurbishment and rock fissure sealing
VO-PKG-04-01284 | PKG-04 | 326813.64 | 288840.06 | Approved | 5 | 2026-03-13 | 2026-04-09 | Station box diaphragm wall water ingress mitigation
VO-PKG-05-00925 | PKG-05 | 161332.78 | 129903.4 | Approved | 18 | 2026-03-13 | 2026-04-14 | HV substation redundancy transformer capacity upgrade
VO-PKG-05-02365 | PKG-05 | 169175.59 | 0 | Pending Approval | 37 | 2026-03-13 |  | HV substation redundancy transformer capacity upgrade
VO-PKG-07-01097 | PKG-07 | 43046.61 | 39491.27 | Approved | 6 | 2026-03-13 | 2026-04-09 | Fiber optic telemetry routing realignment along guideway
VO-PKG-07-02357 | PKG-07 | 340827.19 | 0 | Pending Approval | 6 | 2026-03-13 |  | Fiber optic telemetry routing realignment along guideway
VO-PKG-08-01788 | PKG-08 | 309169.25 | 281897.43 | Approved | 24 | 2026-03-13 | 2026-04-24 | Track vibration damping rubber pads acoustic upgrade
VO-PKG-10-02490 | PKG-10 | 29681.5 | 25697.43 | Approved | 49 | 2026-03-13 | 2026-04-13 | HVAC chilled water pipe rerouting around station concourse
VO-PKG-06-01526 | PKG-06 | 221294.7 | 205604.78 | Approved | 29 | 2026-03-14 | 2026-04-17 | Additional smoke evacuation shafts in underground platforms
VO-PKG-07-02317 | PKG-07 | 311055.57 | 0 | Pending Approval | 23 | 2026-03-14 |  | Fiber optic telemetry routing realignment along guideway
VO-PKG-01-02561 | PKG-01 | 332385.41 | 325215.02 | Approved | 48 | 2026-03-15 | 2026-04-08 | Unforeseen soft ground stabilization and grouting
VO-PKG-04-00854 | PKG-04 | 82314.47 | 0 | Pending Approval | 16 | 2026-03-15 |  | Station box diaphragm wall water ingress mitigation
VO-PKG-04-02854 | PKG-04 | 88265.17 | 77175.27 | Approved | 31 | 2026-03-15 | 2026-04-08 | Station box diaphragm wall water ingress mitigation
VO-PKG-06-01326 | PKG-06 | 192627.05 | 176919.04 | Approved | 37 | 2026-03-15 | 2026-04-13 | Additional smoke evacuation shafts in underground platforms
VO-PKG-01-02801 | PKG-01 | 280359.99 | 0 | Pending Approval | 2 | 2026-03-17 |  | Unforeseen soft ground stabilization and grouting
VO-PKG-04-01254 | PKG-04 | 338012.43 | 0 | Rejected | 0 | 2026-03-17 | 2026-04-19 | Station box diaphragm wall water ingress mitigation
VO-PKG-08-01268 | PKG-08 | 346902.64 | 297861.93 | Approved | 38 | 2026-03-17 | 2026-05-09 | Track vibration damping rubber pads acoustic upgrade
VO-PKG-06-02616 | PKG-06 | 15959.57 | 14885.14 | Approved | 47 | 2026-03-18 | 2026-04-05 | Additional smoke evacuation shafts in underground platforms
VO-PKG-03-00443 | PKG-03 | 101543.1 | 86827.38 | Approved | 53 | 2026-03-19 | 2026-05-10 | Viaduct pier foundation redesign due to utility clash
VO-PKG-06-00666 | PKG-06 | 172569.17 | 158744.21 | Approved | 7 | 2026-03-19 | 2026-05-14 | Additional smoke evacuation shafts in underground platforms
VO-PKG-08-02188 | PKG-08 | 172843.86 | 0 | Pending Approval | 11 | 2026-03-19 |  | Track vibration damping rubber pads acoustic upgrade
VO-PKG-04-01304 | PKG-04 | 68995.99 | 0 | Rejected | 0 | 2026-03-20 | 2026-03-30 | Station box diaphragm wall water ingress mitigation
VO-PKG-04-02324 | PKG-04 | 67649.59 | 54625.09 | Approved | 18 | 2026-03-20 | 2026-04-30 | Station box diaphragm wall water ingress mitigation
VO-PKG-10-02510 | PKG-10 | 336850.13 | 326265.74 | Approved | 24 | 2026-03-20 | 2026-04-13 | HVAC chilled water pipe rerouting around station concourse
VO-PKG-10-02860 | PKG-10 | 48764.17 | 0 | Pending Approval | 6 | 2026-03-20 |  | HVAC chilled water pipe rerouting around station concourse
VO-PKG-05-00705 | PKG-05 | 246996.1 | 0 | Pending Approval | 21 | 2026-03-21 |  | HV substation redundancy transformer capacity upgrade
VO-PKG-05-00855 | PKG-05 | 244833.74 | 214439.01 | Approved | 37 | 2026-03-21 | 2026-04-29 | HV substation redundancy transformer capacity upgrade
VO-PKG-07-02117 | PKG-07 | 203354.49 | 0 | Pending Approval | 41 | 2026-03-21 |  | Fiber optic telemetry routing realignment along guideway
VO-PKG-09-01689 | PKG-09 | 192814.39 | 170816.89 | Approved | 40 | 2026-03-21 | 2026-05-01 | Drainage box culvert capacity expansion for 100-year flood event
VO-PKG-04-00864 | PKG-04 | 151929.28 | 0 | Rejected | 0 | 2026-03-22 | 2026-04-09 | Station box diaphragm wall water ingress mitigation
VO-PKG-05-02245 | PKG-05 | 60348.23 | 0 | Pending Approval | 38 | 2026-03-22 |  | HV substation redundancy transformer capacity upgrade
VO-PKG-08-02248 | PKG-08 | 135407.18 | 115434.69 | Approved | 35 | 2026-03-22 | 2026-05-01 | Track vibration damping rubber pads acoustic upgrade
VO-PKG-09-02279 | PKG-09 | 127683.54 | 0 | Pending Approval | 3 | 2026-03-22 |  | Drainage box culvert capacity expansion for 100-year flood event
VO-PKG-04-01114 | PKG-04 | 274239.85 | 247244.44 | Approved | 56 | 2026-03-23 | 2026-05-10 | Station box diaphragm wall water ingress mitigation
VO-PKG-04-02304 | PKG-04 | 345806.98 | 306297.48 | Approved | 11 | 2026-03-23 | 2026-05-01 | Station box diaphragm wall water ingress mitigation
VO-PKG-06-02176 | PKG-06 | 275727.81 | 260173.58 | Approved | 59 | 2026-03-23 | 2026-04-25 | Additional smoke evacuation shafts in underground platforms
VO-PKG-01-01851 | PKG-01 | 233272.87 | 0 | Pending Approval | 16 | 2026-03-24 |  | Unforeseen soft ground stabilization and grouting
VO-PKG-02-02902 | PKG-02 | 17504.32 | 15949.75 | Approved | 13 | 2026-03-24 | 2026-05-13 | TBM Cutterhead refurbishment and rock fissure sealing
VO-PKG-04-01074 | PKG-04 | 95102.8 | 0 | Rejected | 0 | 2026-03-24 | 2026-04-29 | Station box diaphragm wall water ingress mitigation
VO-PKG-05-02655 | PKG-05 | 193576.01 | 0 | Pending Approval | 35 | 2026-03-24 |  | HV substation redundancy transformer capacity upgrade
VO-PKG-07-01467 | PKG-07 | 210980.23 | 0 | Pending Approval | 14 | 2026-03-24 |  | Fiber optic telemetry routing realignment along guideway
VO-PKG-03-00113 | PKG-03 | 255129.79 | 230230.69 | Approved | 10 | 2026-03-25 | 2026-05-11 | Viaduct pier foundation redesign due to utility clash
VO-PKG-05-02235 | PKG-05 | 272230.2 | 0 | Pending Approval | 41 | 2026-03-25 |  | HV substation redundancy transformer capacity upgrade
VO-PKG-05-02965 | PKG-05 | 16207.04 | 13578.72 | Approved | 54 | 2026-03-25 | 2026-04-09 | HV substation redundancy transformer capacity upgrade
VO-PKG-06-00766 | PKG-06 | 96424.39 | 91129.12 | Approved | 26 | 2026-03-25 | 2026-04-19 | Additional smoke evacuation shafts in underground platforms
VO-PKG-06-02146 | PKG-06 | 280640.98 | 253840.78 | Approved | 10 | 2026-03-25 | 2026-04-12 | Additional smoke evacuation shafts in underground platforms
VO-PKG-07-00277 | PKG-07 | 327414.8 | 0 | Pending Approval | 13 | 2026-03-25 |  | Fiber optic telemetry routing realignment along guideway
VO-PKG-02-00242 | PKG-02 | 329165.2 | 303565.48 | Approved | 6 | 2026-03-26 | 2026-05-16 | TBM Cutterhead refurbishment and rock fissure sealing
VO-PKG-02-00662 | PKG-02 | 207394.87 | 176136.52 | Approved | 52 | 2026-03-26 | 2026-05-07 | TBM Cutterhead refurbishment and rock fissure sealing
VO-PKG-04-02224 | PKG-04 | 345574.9 | 290417.08 | Approved | 42 | 2026-03-26 | 2026-04-17 | Station box diaphragm wall water ingress mitigation
VO-PKG-08-02938 | PKG-08 | 238546.05 | 0 | Pending Approval | 22 | 2026-03-26 |  | Track vibration damping rubber pads acoustic upgrade
VO-PKG-09-00289 | PKG-09 | 345050.6 | 323346.63 | Approved | 20 | 2026-03-26 | 2026-05-17 | Drainage box culvert capacity expansion for 100-year flood event
VO-PKG-10-02840 | PKG-10 | 294981.56 | 272633.08 | Approved | 48 | 2026-03-26 | 2026-04-15 | HVAC chilled water pipe rerouting around station concourse
VO-PKG-10-02870 | PKG-10 | 211144.43 | 184220.18 | Approved | 53 | 2026-03-26 | 2026-04-14 | HVAC chilled water pipe rerouting around station concourse
VO-PKG-08-02958 | PKG-08 | 97475.96 | 78740.63 | Approved | 32 | 2026-03-27 | 2026-05-09 | Track vibration damping rubber pads acoustic upgrade
VO-PKG-06-02656 | PKG-06 | 308058.97 | 0 | Pending Approval | 3 | 2026-03-28 |  | Additional smoke evacuation shafts in underground platforms
VO-PKG-05-00575 | PKG-05 | 292717.03 | 0 | Pending Approval | 42 | 2026-03-29 |  | HV substation redundancy transformer capacity upgrade
VO-PKG-07-00797 | PKG-07 | 131925.74 | 0 | Pending Approval | 9 | 2026-03-29 |  | Fiber optic telemetry routing realignment along guideway
VO-PKG-01-00891 | PKG-01 | 276924.3 | 0 | Pending Approval | 36 | 2026-03-30 |  | Unforeseen soft ground stabilization and grouting
VO-PKG-05-00885 | PKG-05 | 336969.97 | 0 | Pending Approval | 8 | 2026-03-30 |  | HV substation redundancy transformer capacity upgrade
VO-PKG-05-02375 | PKG-05 | 319707.89 | 0 | Rejected | 0 | 2026-03-30 | 2026-05-02 | HV substation redundancy transformer capacity upgrade
VO-PKG-07-02137 | PKG-07 | 202206.76 | 0 | Pending Approval | 31 | 2026-03-30 |  | Fiber optic telemetry routing realignment along guideway
VO-PKG-07-02177 | PKG-07 | 192462.23 | 0 | Pending Approval | 9 | 2026-03-30 |  | Fiber optic telemetry routing realignment along guideway
VO-PKG-08-01118 | PKG-08 | 77009.6 | 68599.13 | Approved | 53 | 2026-03-30 | 2026-05-04 | Track vibration damping rubber pads acoustic upgrade
VO-PKG-02-01732 | PKG-02 | 22712.82 | 0 | Pending Approval | 6 | 2026-04-01 |  | TBM Cutterhead refurbishment and rock fissure sealing
VO-PKG-10-01150 | PKG-10 | 164171.25 | 0 | Rejected | 0 | 2026-04-01 | 2026-04-20 | HVAC chilled water pipe rerouting around station concourse
VO-PKG-10-02850 | PKG-10 | 29416.78 | 28692.73 | Approved | 23 | 2026-04-01 | 2026-05-09 | HVAC chilled water pipe rerouting around station concourse
VO-PKG-01-00101 | PKG-01 | 127377.66 | 120476.22 | Approved | 16 | 2026-04-02 | 2026-05-05 | Unforeseen soft ground stabilization and grouting
VO-PKG-06-02976 | PKG-06 | 154494.27 | 0 | Pending Approval | 14 | 2026-04-02 |  | Additional smoke evacuation shafts in underground platforms
VO-PKG-07-00497 | PKG-07 | 179742.65 | 0 | Pending Approval | 4 | 2026-04-02 |  | Fiber optic telemetry routing realignment along guideway
VO-PKG-03-00543 | PKG-03 | 135800.01 | 0 | Pending Approval | 17 | 2026-04-04 |  | Viaduct pier foundation redesign due to utility clash
VO-PKG-10-02410 | PKG-10 | 259752.91 | 0 | Rejected | 0 | 2026-04-04 | 2026-05-02 | HVAC chilled water pipe rerouting around station concourse
VO-PKG-03-02083 | PKG-03 | 329472.64 | 0 | Pending Approval | 40 | 2026-04-05 |  | Viaduct pier foundation redesign due to utility clash
VO-PKG-04-02594 | PKG-04 | 226146.08 | 0 | Pending Approval | 1 | 2026-04-05 |  | Station box diaphragm wall water ingress mitigation
VO-PKG-09-00619 | PKG-09 | 60492.62 | 0 | Pending Approval | 42 | 2026-04-05 |  | Drainage box culvert capacity expansion for 100-year flood event
VO-PKG-09-02999 | PKG-09 | 255438.55 | 243741.02 | Approved | 52 | 2026-04-05 | 2026-05-30 | Drainage box culvert capacity expansion for 100-year flood event
VO-PKG-01-01531 | PKG-01 | 180835.22 | 174282.54 | Approved | 38 | 2026-04-06 | 2026-04-22 | Unforeseen soft ground stabilization and grouting
VO-PKG-01-02011 | PKG-01 | 233763.47 | 210361.57 | Approved | 13 | 2026-04-06 | 2026-06-04 | Unforeseen soft ground stabilization and grouting
VO-PKG-02-02592 | PKG-02 | 94391.93 | 0 | Pending Approval | 39 | 2026-04-06 |  | TBM Cutterhead refurbishment and rock fissure sealing
VO-PKG-03-00773 | PKG-03 | 90833.42 | 87742.99 | Approved | 30 | 2026-04-06 | 2026-05-24 | Viaduct pier foundation redesign due to utility clash
VO-PKG-03-01603 | PKG-03 | 154983.87 | 0 | Pending Approval | 14 | 2026-04-06 |  | Viaduct pier foundation redesign due to utility clash
VO-PKG-07-00577 | PKG-07 | 265415.17 | 0 | Pending Approval | 17 | 2026-04-06 |  | Fiber optic telemetry routing realignment along guideway
VO-PKG-07-01217 | PKG-07 | 88911.14 | 80603.49 | Approved | 50 | 2026-04-06 | 2026-04-24 | Fiber optic telemetry routing realignment along guideway
VO-PKG-07-01287 | PKG-07 | 251559.29 | 0 | Rejected | 0 | 2026-04-06 | 2026-05-19 | Fiber optic telemetry routing realignment along guideway
VO-PKG-07-02657 | PKG-07 | 136113.84 | 0 | Rejected | 0 | 2026-04-06 | 2026-04-23 | Fiber optic telemetry routing realignment along guideway
VO-PKG-09-00179 | PKG-09 | 288535.05 | 0 | Rejected | 0 | 2026-04-07 | 2026-05-01 | Drainage box culvert capacity expansion for 100-year flood event
VO-PKG-10-02540 | PKG-10 | 69394.37 | 67236.73 | Approved | 11 | 2026-04-07 | 2026-06-01 | HVAC chilled water pipe rerouting around station concourse
VO-PKG-03-02823 | PKG-03 | 277120.67 | 264408.55 | Approved | 30 | 2026-04-08 | 2026-05-05 | Viaduct pier foundation redesign due to utility clash
VO-PKG-08-01758 | PKG-08 | 136672.62 | 128928.64 | Approved | 16 | 2026-04-08 | 2026-06-04 | Track vibration damping rubber pads acoustic upgrade
VO-PKG-08-02128 | PKG-08 | 159226.94 | 0 | Pending Approval | 19 | 2026-04-08 |  | Track vibration damping rubber pads acoustic upgrade
VO-PKG-10-00220 | PKG-10 | 126707.53 | 0 | Pending Approval | 38 | 2026-04-08 |  | HVAC chilled water pipe rerouting around station concourse
VO-PKG-01-01521 | PKG-01 | 188745.88 | 152612.74 | Approved | 48 | 2026-04-09 | 2026-05-27 | Unforeseen soft ground stabilization and grouting
VO-PKG-02-02242 | PKG-02 | 214733.54 | 199840.68 | Approved | 5 | 2026-04-09 | 2026-05-23 | TBM Cutterhead refurbishment and rock fissure sealing
VO-PKG-05-01705 | PKG-05 | 142368.99 | 0 | Rejected | 0 | 2026-04-09 | 2026-05-14 | HV substation redundancy transformer capacity upgrade
VO-PKG-10-02350 | PKG-10 | 56533.81 | 46201.19 | Approved | 9 | 2026-04-09 | 2026-05-09 | HVAC chilled water pipe rerouting around station concourse
VO-PKG-01-02431 | PKG-01 | 19860.73 | 0 | Pending Approval | 30 | 2026-04-10 |  | Unforeseen soft ground stabilization and grouting
VO-PKG-06-01746 | PKG-06 | 53311.45 | 0 | Pending Approval | 24 | 2026-04-10 |  | Additional smoke evacuation shafts in underground platforms
VO-PKG-08-00438 | PKG-08 | 265066.8 | 232642.52 | Approved | 35 | 2026-04-10 | 2026-05-14 | Track vibration damping rubber pads acoustic upgrade
VO-PKG-09-01759 | PKG-09 | 266733.63 | 258514.48 | Approved | 59 | 2026-04-10 | 2026-05-20 | Drainage box culvert capacity expansion for 100-year flood event
VO-PKG-07-00737 | PKG-07 | 92777.95 | 0 | Pending Approval | 2 | 2026-04-11 |  | Fiber optic telemetry routing realignment along guideway
VO-PKG-08-02158 | PKG-08 | 205029.21 | 176721.43 | Approved | 24 | 2026-04-11 | 2026-05-12 | Track vibration damping rubber pads acoustic upgrade
VO-PKG-10-02600 | PKG-10 | 342352.68 | 276974.4 | Approved | 47 | 2026-04-11 | 2026-05-08 | HVAC chilled water pipe rerouting around station concourse
VO-PKG-03-01573 | PKG-03 | 324797.71 | 290019.41 | Approved | 9 | 2026-04-12 | 2026-04-27 | Viaduct pier foundation redesign due to utility clash
VO-PKG-06-02886 | PKG-06 | 26918.96 | 0 | Pending Approval | 17 | 2026-04-12 |  | Additional smoke evacuation shafts in underground platforms
VO-PKG-10-01000 | PKG-10 | 236297.07 | 215554.98 | Approved | 17 | 2026-04-12 | 2026-06-05 | HVAC chilled water pipe rerouting around station concourse
VO-PKG-02-01782 | PKG-02 | 344431.73 | 334395.28 | Approved | 21 | 2026-04-13 | 2026-06-03 | TBM Cutterhead refurbishment and rock fissure sealing
VO-PKG-03-00893 | PKG-03 | 152533.7 | 143892.99 | Approved | 52 | 2026-04-14 | 2026-05-22 | Viaduct pier foundation redesign due to utility clash
VO-PKG-04-00594 | PKG-04 | 135774.11 | 0 | Pending Approval | 4 | 2026-04-14 |  | Station box diaphragm wall water ingress mitigation
VO-PKG-04-01014 | PKG-04 | 221891.2 | 0 | Pending Approval | 4 | 2026-04-14 |  | Station box diaphragm wall water ingress mitigation
VO-PKG-06-01196 | PKG-06 | 156273.92 | 137851.21 | Approved | 52 | 2026-04-14 | 2026-05-02 | Additional smoke evacuation shafts in underground platforms
VO-PKG-06-01666 | PKG-06 | 251635.94 | 232035.23 | Approved | 36 | 2026-04-14 | 2026-05-05 | Additional smoke evacuation shafts in underground platforms
VO-PKG-09-01229 | PKG-09 | 122016.25 | 103912.45 | Approved | 46 | 2026-04-14 | 2026-05-14 | Drainage box culvert capacity expansion for 100-year flood event
VO-PKG-01-02101 | PKG-01 | 294440.57 | 246820.27 | Approved | 31 | 2026-04-15 | 2026-05-30 | Unforeseen soft ground stabilization and grouting
VO-PKG-10-00170 | PKG-10 | 82600.59 | 0 | Pending Approval | 30 | 2026-04-15 |  | HVAC chilled water pipe rerouting around station concourse
VO-PKG-04-01874 | PKG-04 | 240655.56 | 0 | Pending Approval | 16 | 2026-04-16 |  | Station box diaphragm wall water ingress mitigation
VO-PKG-07-00427 | PKG-07 | 303800.03 | 0 | Pending Approval | 43 | 2026-04-16 |  | Fiber optic telemetry routing realignment along guideway
VO-PKG-01-01761 | PKG-01 | 45385.47 | 0 | Pending Approval | 39 | 2026-04-17 |  | Unforeseen soft ground stabilization and grouting
VO-PKG-05-00535 | PKG-05 | 309450.4 | 295402.37 | Approved | 21 | 2026-04-17 | 2026-06-13 | HV substation redundancy transformer capacity upgrade
VO-PKG-08-00728 | PKG-08 | 253641.84 | 0 | Pending Approval | 7 | 2026-04-17 |  | Track vibration damping rubber pads acoustic upgrade
VO-PKG-08-00388 | PKG-08 | 70834.34 | 56887.5 | Approved | 59 | 2026-04-18 | 2026-05-29 | Track vibration damping rubber pads acoustic upgrade
VO-PKG-09-00169 | PKG-09 | 165078.85 | 145915.45 | Approved | 55 | 2026-04-18 | 2026-05-16 | Drainage box culvert capacity expansion for 100-year flood event
VO-PKG-01-01311 | PKG-01 | 58106.19 | 47086.41 | Approved | 48 | 2026-04-20 | 2026-06-13 | Unforeseen soft ground stabilization and grouting
VO-PKG-03-02153 | PKG-03 | 132889.95 | 0 | Pending Approval | 19 | 2026-04-20 |  | Viaduct pier foundation redesign due to utility clash
VO-PKG-06-02416 | PKG-06 | 227095.79 | 222228.23 | Approved | 29 | 2026-04-20 | 2026-05-23 | Additional smoke evacuation shafts in underground platforms
VO-PKG-08-01648 | PKG-08 | 277052.55 | 0 | Pending Approval | 20 | 2026-04-20 |  | Track vibration damping rubber pads acoustic upgrade
VO-PKG-09-00229 | PKG-09 | 342661.79 | 328783.78 | Approved | 6 | 2026-04-20 | 2026-05-22 | Drainage box culvert capacity expansion for 100-year flood event
VO-PKG-02-00362 | PKG-02 | 92372.77 | 76535.09 | Approved | 19 | 2026-04-21 | 2026-05-22 | TBM Cutterhead refurbishment and rock fissure sealing
VO-PKG-03-00383 | PKG-03 | 67049.11 | 63256.98 | Approved | 10 | 2026-04-21 | 2026-06-05 | Viaduct pier foundation redesign due to utility clash
VO-PKG-09-00849 | PKG-09 | 63957.44 | 58598.58 | Approved | 13 | 2026-04-22 | 2026-05-19 | Drainage box culvert capacity expansion for 100-year flood event
VO-PKG-01-02691 | PKG-01 | 146981.31 | 0 | Pending Approval | 42 | 2026-04-23 |  | Unforeseen soft ground stabilization and grouting
VO-PKG-09-00219 | PKG-09 | 245524.45 | 215073.15 | Approved | 5 | 2026-04-23 | 2026-06-05 | Drainage box culvert capacity expansion for 100-year flood event
VO-PKG-01-00121 | PKG-01 | 251273.9 | 0 | Pending Approval | 42 | 2026-04-24 |  | Unforeseen soft ground stabilization and grouting
VO-PKG-01-00421 | PKG-01 | 316606.91 | 255433.56 | Approved | 25 | 2026-04-24 | 2026-06-20 | Unforeseen soft ground stabilization and grouting
VO-PKG-08-00908 | PKG-08 | 310615.81 | 0 | Pending Approval | 37 | 2026-04-24 |  | Track vibration damping rubber pads acoustic upgrade
VO-PKG-09-02869 | PKG-09 | 315797.99 | 265265.09 | Approved | 25 | 2026-04-24 | 2026-05-18 | Drainage box culvert capacity expansion for 100-year flood event
VO-PKG-02-02602 | PKG-02 | 194313.73 | 0 | Pending Approval | 19 | 2026-04-25 |  | TBM Cutterhead refurbishment and rock fissure sealing
VO-PKG-05-01375 | PKG-05 | 88336.76 | 0 | Pending Approval | 4 | 2026-04-25 |  | HV substation redundancy transformer capacity upgrade
VO-PKG-07-01137 | PKG-07 | 142163.78 | 136639.22 | Approved | 43 | 2026-04-25 | 2026-06-19 | Fiber optic telemetry routing realignment along guideway
VO-PKG-07-02517 | PKG-07 | 265843.82 | 238409.16 | Approved | 14 | 2026-04-25 | 2026-05-15 | Fiber optic telemetry routing realignment along guideway
VO-PKG-09-01429 | PKG-09 | 200221.78 | 0 | Rejected | 0 | 2026-04-25 | 2026-05-27 | Drainage box culvert capacity expansion for 100-year flood event
VO-PKG-05-02725 | PKG-05 | 125354.4 | 122478.98 | Approved | 52 | 2026-04-26 | 2026-06-22 | HV substation redundancy transformer capacity upgrade
VO-PKG-07-00007 | PKG-07 | 157532.96 | 132440.33 | Approved | 13 | 2026-04-26 | 2026-06-04 | Fiber optic telemetry routing realignment along guideway
VO-PKG-03-02093 | PKG-03 | 145435.91 | 135729.43 | Approved | 27 | 2026-04-27 | 2026-06-08 | Viaduct pier foundation redesign due to utility clash
VO-PKG-04-00254 | PKG-04 | 59405.05 | 0 | Pending Approval | 26 | 2026-04-27 |  | Station box diaphragm wall water ingress mitigation
VO-PKG-06-00036 | PKG-06 | 112414.48 | 107825.55 | Approved | 56 | 2026-04-27 | 2026-06-13 | Additional smoke evacuation shafts in underground platforms
VO-PKG-08-00888 | PKG-08 | 197382.52 | 0 | Rejected | 0 | 2026-04-27 | 2026-05-22 | Track vibration damping rubber pads acoustic upgrade
VO-PKG-08-02058 | PKG-08 | 173546.7 | 155896.14 | Approved | 32 | 2026-04-27 | 2026-06-18 | Track vibration damping rubber pads acoustic upgrade
VO-PKG-10-02220 | PKG-10 | 132712.07 | 124700.8 | Approved | 27 | 2026-04-28 | 2026-06-22 | HVAC chilled water pipe rerouting around station concourse
VO-PKG-03-01093 | PKG-03 | 57991.16 | 47562.91 | Approved | 37 | 2026-04-29 | 2026-05-21 | Viaduct pier foundation redesign due to utility clash
VO-PKG-08-01928 | PKG-08 | 296238.44 | 289108.48 | Approved | 6 | 2026-04-29 | 2026-06-11 | Track vibration damping rubber pads acoustic upgrade
VO-PKG-01-01001 | PKG-01 | 152562.03 | 0 | Rejected | 0 | 2026-04-30 | 2026-06-13 | Unforeseen soft ground stabilization and grouting
VO-PKG-04-02744 | PKG-04 | 339119.31 | 328855.98 | Approved | 9 | 2026-04-30 | 2026-06-08 | Station box diaphragm wall water ingress mitigation
VO-PKG-08-02428 | PKG-08 | 231558.7 | 0 | Pending Approval | 11 | 2026-04-30 |  | Track vibration damping rubber pads acoustic upgrade
VO-PKG-02-00022 | PKG-02 | 38110.44 | 0 | Pending Approval | 13 | 2026-05-01 |  | TBM Cutterhead refurbishment and rock fissure sealing
VO-PKG-02-00832 | PKG-02 | 327980.35 | 0 | Pending Approval | 17 | 2026-05-01 |  | TBM Cutterhead refurbishment and rock fissure sealing
VO-PKG-03-02423 | PKG-03 | 107034.56 | 101759.73 | Approved | 51 | 2026-05-01 | 2026-05-20 | Viaduct pier foundation redesign due to utility clash
VO-PKG-04-01194 | PKG-04 | 328272.86 | 0 | Pending Approval | 21 | 2026-05-01 |  | Station box diaphragm wall water ingress mitigation
VO-PKG-05-01975 | PKG-05 | 311932.53 | 303545.75 | Approved | 28 | 2026-05-01 | 2026-06-20 | HV substation redundancy transformer capacity upgrade
VO-PKG-05-02315 | PKG-05 | 348093.94 | 308533.96 | Approved | 41 | 2026-05-01 | 2026-06-04 | HV substation redundancy transformer capacity upgrade
VO-PKG-05-02875 | PKG-05 | 183163.96 | 169953.1 | Approved | 20 | 2026-05-01 | 2026-06-01 | HV substation redundancy transformer capacity upgrade
VO-PKG-06-00256 | PKG-06 | 119572.01 | 112588.32 | Approved | 44 | 2026-05-01 | 2026-06-26 | Additional smoke evacuation shafts in underground platforms
VO-PKG-07-00877 | PKG-07 | 96232.84 | 0 | Rejected | 0 | 2026-05-01 | 2026-05-16 | Fiber optic telemetry routing realignment along guideway
VO-PKG-10-00250 | PKG-10 | 230062.55 | 214261.53 | Approved | 23 | 2026-05-01 | 2026-06-15 | HVAC chilled water pipe rerouting around station concourse
VO-PKG-10-01120 | PKG-10 | 248326.19 | 205131.04 | Approved | 15 | 2026-05-01 | 2026-06-05 | HVAC chilled water pipe rerouting around station concourse
VO-PKG-02-00132 | PKG-02 | 325897.1 | 267596.76 | Approved | 36 | 2026-05-02 | 2026-05-27 | TBM Cutterhead refurbishment and rock fissure sealing
VO-PKG-04-00024 | PKG-04 | 261750.52 | 229301.37 | Approved | 7 | 2026-05-02 | 2026-06-27 | Station box diaphragm wall water ingress mitigation
VO-PKG-06-01416 | PKG-06 | 23725.72 | 22005.95 | Approved | 36 | 2026-05-02 | 2026-06-23 | Additional smoke evacuation shafts in underground platforms
VO-PKG-02-01832 | PKG-02 | 29253.37 | 26433.29 | Approved | 44 | 2026-05-03 | 2026-06-19 | TBM Cutterhead refurbishment and rock fissure sealing
VO-PKG-06-00566 | PKG-06 | 283084.72 | 230558.32 | Approved | 24 | 2026-05-03 | 2026-05-23 | Additional smoke evacuation shafts in underground platforms
VO-PKG-06-01476 | PKG-06 | 258386.98 | 0 | Pending Approval | 8 | 2026-05-03 |  | Additional smoke evacuation shafts in underground platforms
VO-PKG-08-00048 | PKG-08 | 310785.38 | 284227.59 | Approved | 55 | 2026-05-03 | 2026-06-19 | Track vibration damping rubber pads acoustic upgrade
VO-PKG-01-01491 | PKG-01 | 119532.85 | 0 | Rejected | 0 | 2026-05-04 | 2026-06-05 | Unforeseen soft ground stabilization and grouting
VO-PKG-04-00554 | PKG-04 | 187674.68 | 165133.61 | Approved | 45 | 2026-05-04 | 2026-05-26 | Station box diaphragm wall water ingress mitigation
VO-PKG-05-00675 | PKG-05 | 347849.27 | 307704.43 | Approved | 59 | 2026-05-04 | 2026-06-16 | HV substation redundancy transformer capacity upgrade
VO-PKG-07-00667 | PKG-07 | 69347.06 | 60563.08 | Approved | 58 | 2026-05-04 | 2026-05-25 | Fiber optic telemetry routing realignment along guideway
VO-PKG-09-01289 | PKG-09 | 77584.6 | 71940.27 | Approved | 46 | 2026-05-04 | 2026-06-11 | Drainage box culvert capacity expansion for 100-year flood event
VO-PKG-04-01634 | PKG-04 | 161242.82 | 0 | Pending Approval | 9 | 2026-05-05 |  | Station box diaphragm wall water ingress mitigation
VO-PKG-06-00466 | PKG-06 | 219679.38 | 204525.08 | Approved | 44 | 2026-05-05 | 2026-07-02 | Additional smoke evacuation shafts in underground platforms
VO-PKG-10-02830 | PKG-10 | 94114.8 | 0 | Pending Approval | 9 | 2026-05-05 |  | HVAC chilled water pipe rerouting around station concourse
VO-PKG-01-02891 | PKG-01 | 148925.79 | 135279.51 | Approved | 11 | 2026-05-06 | 2026-07-04 | Unforeseen soft ground stabilization and grouting
VO-PKG-06-02576 | PKG-06 | 267146.43 | 232429.77 | Approved | 48 | 2026-05-06 | 2026-06-28 | Additional smoke evacuation shafts in underground platforms
VO-PKG-09-00479 | PKG-09 | 345975.82 | 310772.92 | Approved | 11 | 2026-05-06 | 2026-05-28 | Drainage box culvert capacity expansion for 100-year flood event
VO-PKG-05-01055 | PKG-05 | 153264.71 | 0 | Pending Approval | 4 | 2026-05-07 |  | HV substation redundancy transformer capacity upgrade
VO-PKG-10-01240 | PKG-10 | 348779.75 | 312739.35 | Approved | 56 | 2026-05-07 | 2026-05-29 | HVAC chilled water pipe rerouting around station concourse
VO-PKG-10-02990 | PKG-10 | 109007.54 | 87536.48 | Approved | 27 | 2026-05-07 | 2026-06-07 | HVAC chilled water pipe rerouting around station concourse
VO-PKG-03-00733 | PKG-03 | 345395.34 | 283087.15 | Approved | 7 | 2026-05-08 | 2026-06-05 | Viaduct pier foundation redesign due to utility clash
VO-PKG-04-02674 | PKG-04 | 334768.8 | 0 | Pending Approval | 31 | 2026-05-08 |  | Station box diaphragm wall water ingress mitigation
VO-PKG-06-02296 | PKG-06 | 195482.84 | 165224.1 | Approved | 15 | 2026-05-08 | 2026-05-29 | Additional smoke evacuation shafts in underground platforms
VO-PKG-08-02978 | PKG-08 | 134785.51 | 125112.54 | Approved | 10 | 2026-05-08 | 2026-06-11 | Track vibration damping rubber pads acoustic upgrade
VO-PKG-02-01352 | PKG-02 | 314033.33 | 300847.3 | Approved | 46 | 2026-05-09 | 2026-07-06 | TBM Cutterhead refurbishment and rock fissure sealing
VO-PKG-08-01688 | PKG-08 | 148520.23 | 0 | Pending Approval | 29 | 2026-05-09 |  | Track vibration damping rubber pads acoustic upgrade
VO-PKG-09-01399 | PKG-09 | 57775.38 | 52077.49 | Approved | 17 | 2026-05-09 | 2026-06-24 | Drainage box culvert capacity expansion for 100-year flood event
VO-PKG-06-00726 | PKG-06 | 180928.42 | 0 | Pending Approval | 26 | 2026-05-10 |  | Additional smoke evacuation shafts in underground platforms
VO-PKG-06-02936 | PKG-06 | 289807.27 | 0 | Pending Approval | 37 | 2026-05-10 |  | Additional smoke evacuation shafts in underground platforms
VO-PKG-08-02808 | PKG-08 | 141473.62 | 119947.53 | Approved | 52 | 2026-05-10 | 2026-06-15 | Track vibration damping rubber pads acoustic upgrade
VO-PKG-05-01015 | PKG-05 | 237573.06 | 219325.32 | Approved | 32 | 2026-05-11 | 2026-06-21 | HV substation redundancy transformer capacity upgrade
VO-PKG-06-00326 | PKG-06 | 278549.86 | 243415.27 | Approved | 59 | 2026-05-11 | 2026-06-03 | Additional smoke evacuation shafts in underground platforms
VO-PKG-09-00839 | PKG-09 | 255630.32 | 0 | Rejected | 0 | 2026-05-11 | 2026-05-30 | Drainage box culvert capacity expansion for 100-year flood event
VO-PKG-08-01398 | PKG-08 | 300132.34 | 0 | Pending Approval | 33 | 2026-05-12 |  | Track vibration damping rubber pads acoustic upgrade
VO-PKG-01-00381 | PKG-01 | 298982.42 | 248571.8 | Approved | 43 | 2026-05-13 | 2026-06-06 | Unforeseen soft ground stabilization and grouting
VO-PKG-01-01211 | PKG-01 | 176662.15 | 0 | Pending Approval | 39 | 2026-05-13 |  | Unforeseen soft ground stabilization and grouting
VO-PKG-08-00008 | PKG-08 | 314610.66 | 260846.51 | Approved | 29 | 2026-05-13 | 2026-07-03 | Track vibration damping rubber pads acoustic upgrade
VO-PKG-09-02369 | PKG-09 | 343057.64 | 0 | Pending Approval | 29 | 2026-05-13 |  | Drainage box culvert capacity expansion for 100-year flood event
VO-PKG-01-01571 | PKG-01 | 85779.58 | 0 | Rejected | 0 | 2026-05-14 | 2026-05-29 | Unforeseen soft ground stabilization and grouting
VO-PKG-02-00222 | PKG-02 | 316865.1 | 0 | Pending Approval | 22 | 2026-05-14 |  | TBM Cutterhead refurbishment and rock fissure sealing
VO-PKG-02-00862 | PKG-02 | 197981.33 | 176647.35 | Approved | 27 | 2026-05-14 | 2026-06-19 | TBM Cutterhead refurbishment and rock fissure sealing
VO-PKG-04-01594 | PKG-04 | 241026.19 | 206468.59 | Approved | 55 | 2026-05-14 | 2026-06-11 | Station box diaphragm wall water ingress mitigation
VO-PKG-01-00271 | PKG-01 | 117939.79 | 106217.67 | Approved | 53 | 2026-05-15 | 2026-06-13 | Unforeseen soft ground stabilization and grouting
VO-PKG-07-01637 | PKG-07 | 249925.73 | 233724.35 | Approved | 20 | 2026-05-15 | 2026-06-17 | Fiber optic telemetry routing realignment along guideway
VO-PKG-07-02547 | PKG-07 | 257055.13 | 236969.83 | Approved | 41 | 2026-05-15 | 2026-06-29 | Fiber optic telemetry routing realignment along guideway
VO-PKG-09-01959 | PKG-09 | 185569.61 | 0 | Pending Approval | 8 | 2026-05-15 |  | Drainage box culvert capacity expansion for 100-year flood event
VO-PKG-02-01472 | PKG-02 | 344575.89 | 336334.06 | Approved | 44 | 2026-05-16 | 2026-06-19 | TBM Cutterhead refurbishment and rock fissure sealing
VO-PKG-06-00266 | PKG-06 | 161821.54 | 0 | Pending Approval | 5 | 2026-05-16 |  | Additional smoke evacuation shafts in underground platforms
VO-PKG-06-00856 | PKG-06 | 304769.59 | 0 | Pending Approval | 16 | 2026-05-16 |  | Additional smoke evacuation shafts in underground platforms
VO-PKG-09-00299 | PKG-09 | 145941.02 | 135676.04 | Approved | 36 | 2026-05-16 | 2026-07-05 | Drainage box culvert capacity expansion for 100-year flood event
VO-PKG-10-00470 | PKG-10 | 281096.02 | 237178.82 | Approved | 47 | 2026-05-16 | 2026-06-28 | HVAC chilled water pipe rerouting around station concourse
VO-PKG-05-00085 | PKG-05 | 299125.56 | 291404.76 | Approved | 46 | 2026-05-17 | 2026-07-02 | HV substation redundancy transformer capacity upgrade
VO-PKG-01-02091 | PKG-01 | 304432.18 | 0 | Pending Approval | 1 | 2026-05-18 |  | Unforeseen soft ground stabilization and grouting
VO-PKG-04-00564 | PKG-04 | 16169.19 | 12976.44 | Approved | 13 | 2026-05-18 | 2026-07-14 | Station box diaphragm wall water ingress mitigation
VO-PKG-04-02534 | PKG-04 | 241365.11 | 0 | Pending Approval | 30 | 2026-05-18 |  | Station box diaphragm wall water ingress mitigation
VO-PKG-09-02749 | PKG-09 | 235870.58 | 0 | Pending Approval | 3 | 2026-05-18 |  | Drainage box culvert capacity expansion for 100-year flood event
VO-PKG-01-00651 | PKG-01 | 334391.48 | 0 | Pending Approval | 13 | 2026-05-19 |  | Unforeseen soft ground stabilization and grouting
VO-PKG-07-01797 | PKG-07 | 285097.56 | 278287.54 | Approved | 35 | 2026-05-19 | 2026-06-26 | Fiber optic telemetry routing realignment along guideway
VO-PKG-09-01939 | PKG-09 | 201562.95 | 191082.93 | Approved | 27 | 2026-05-19 | 2026-07-15 | Drainage box culvert capacity expansion for 100-year flood event
VO-PKG-10-00660 | PKG-10 | 53077 | 49159.77 | Approved | 16 | 2026-05-19 | 2026-07-09 | HVAC chilled water pipe rerouting around station concourse
VO-PKG-10-03000 | PKG-10 | 305135.8 | 292332.11 | Approved | 56 | 2026-05-19 | 2026-06-21 | HVAC chilled water pipe rerouting around station concourse
VO-PKG-02-01102 | PKG-02 | 105358.9 | 91671.51 | Approved | 58 | 2026-05-20 | 2026-07-10 | TBM Cutterhead refurbishment and rock fissure sealing
VO-PKG-04-01504 | PKG-04 | 111590.67 | 106236.85 | Approved | 30 | 2026-05-20 | 2026-07-09 | Station box diaphragm wall water ingress mitigation
VO-PKG-05-02205 | PKG-05 | 57539.98 | 0 | Pending Approval | 13 | 2026-05-20 |  | HV substation redundancy transformer capacity upgrade
VO-PKG-07-00057 | PKG-07 | 169120.57 | 0 | Pending Approval | 41 | 2026-05-21 |  | Fiber optic telemetry routing realignment along guideway
VO-PKG-08-01478 | PKG-08 | 262004.51 | 0 | Pending Approval | 38 | 2026-05-22 |  | Track vibration damping rubber pads acoustic upgrade
VO-PKG-08-02908 | PKG-08 | 194242.49 | 165288.98 | Approved | 54 | 2026-05-22 | 2026-06-10 | Track vibration damping rubber pads acoustic upgrade
VO-PKG-09-00959 | PKG-09 | 70674.34 | 0 | Rejected | 0 | 2026-05-22 | 2026-06-11 | Drainage box culvert capacity expansion for 100-year flood event
VO-PKG-05-01385 | PKG-05 | 38793.08 | 0 | Pending Approval | 2 | 2026-05-23 |  | HV substation redundancy transformer capacity upgrade
VO-PKG-05-01755 | PKG-05 | 270076.69 | 243952.1 | Approved | 41 | 2026-05-23 | 2026-06-22 | HV substation redundancy transformer capacity upgrade
VO-PKG-01-00191 | PKG-01 | 330434.45 | 317871.85 | Approved | 39 | 2026-05-24 | 2026-07-10 | Unforeseen soft ground stabilization and grouting
VO-PKG-04-00934 | PKG-04 | 243141.38 | 207605.23 | Approved | 46 | 2026-05-24 | 2026-07-18 | Station box diaphragm wall water ingress mitigation
VO-PKG-04-01894 | PKG-04 | 233154.71 | 200044.87 | Approved | 21 | 2026-05-24 | 2026-07-17 | Station box diaphragm wall water ingress mitigation
VO-PKG-05-01785 | PKG-05 | 318837.97 | 0 | Pending Approval | 11 | 2026-05-24 |  | HV substation redundancy transformer capacity upgrade
VO-PKG-04-02474 | PKG-04 | 176872.11 | 0 | Pending Approval | 17 | 2026-05-25 |  | Station box diaphragm wall water ingress mitigation
VO-PKG-05-00805 | PKG-05 | 328045.16 | 0 | Pending Approval | 41 | 2026-05-25 |  | HV substation redundancy transformer capacity upgrade
VO-PKG-05-01805 | PKG-05 | 267771.41 | 0 | Pending Approval | 44 | 2026-05-25 |  | HV substation redundancy transformer capacity upgrade
VO-PKG-06-02446 | PKG-06 | 303692.66 | 266687.55 | Approved | 20 | 2026-05-25 | 2026-06-10 | Additional smoke evacuation shafts in underground platforms
VO-PKG-09-01219 | PKG-09 | 54107.54 | 51841.18 | Approved | 38 | 2026-05-25 | 2026-07-17 | Drainage box culvert capacity expansion for 100-year flood event
VO-PKG-09-02269 | PKG-09 | 172732.72 | 0 | Pending Approval | 8 | 2026-05-25 |  | Drainage box culvert capacity expansion for 100-year flood event
VO-PKG-10-00650 | PKG-10 | 249520.86 | 221108.57 | Approved | 53 | 2026-05-25 | 2026-06-22 | HVAC chilled water pipe rerouting around station concourse
VO-PKG-02-00232 | PKG-02 | 57790.65 | 56302.99 | Approved | 37 | 2026-05-26 | 2026-07-01 | TBM Cutterhead refurbishment and rock fissure sealing
VO-PKG-03-01523 | PKG-03 | 108706.42 | 103487.56 | Approved | 7 | 2026-05-26 | 2026-07-18 | Viaduct pier foundation redesign due to utility clash
VO-PKG-08-00418 | PKG-08 | 291460.02 | 0 | Pending Approval | 17 | 2026-05-26 |  | Track vibration damping rubber pads acoustic upgrade
VO-PKG-08-00978 | PKG-08 | 155163.85 | 0 | Pending Approval | 23 | 2026-05-26 |  | Track vibration damping rubber pads acoustic upgrade
VO-PKG-09-01709 | PKG-09 | 92129.01 | 76199.11 | Approved | 35 | 2026-05-26 | 2026-07-06 | Drainage box culvert capacity expansion for 100-year flood event
VO-PKG-02-01602 | PKG-02 | 278327 | 260834.46 | Approved | 19 | 2026-05-27 | 2026-06-22 | TBM Cutterhead refurbishment and rock fissure sealing
VO-PKG-07-01727 | PKG-07 | 223699.47 | 187543.54 | Approved | 33 | 2026-05-27 | 2026-07-05 | Fiber optic telemetry routing realignment along guideway
VO-PKG-08-00128 | PKG-08 | 195585.73 | 172566.79 | Approved | 30 | 2026-05-27 | 2026-07-13 | Track vibration damping rubber pads acoustic upgrade
VO-PKG-06-00806 | PKG-06 | 269120.48 | 229997.35 | Approved | 35 | 2026-05-28 | 2026-07-12 | Additional smoke evacuation shafts in underground platforms
VO-PKG-01-02711 | PKG-01 | 314723.78 | 0 | Pending Approval | 0 | 2026-05-29 |  | Unforeseen soft ground stabilization and grouting
VO-PKG-08-01388 | PKG-08 | 229683.49 | 207238 | Approved | 14 | 2026-05-29 | 2026-07-18 | Track vibration damping rubber pads acoustic upgrade
VO-PKG-08-01538 | PKG-08 | 109232.39 | 90736.05 | Approved | 28 | 2026-05-29 | 2026-07-05 | Track vibration damping rubber pads acoustic upgrade
VO-PKG-10-00070 | PKG-10 | 61911.73 | 0 | Pending Approval | 8 | 2026-05-29 |  | HVAC chilled water pipe rerouting around station concourse
VO-PKG-02-02322 | PKG-02 | 65316.03 | 53377.18 | Approved | 36 | 2026-05-30 | 2026-06-30 | TBM Cutterhead refurbishment and rock fissure sealing
VO-PKG-03-01323 | PKG-03 | 65821.06 | 0 | Pending Approval | 37 | 2026-05-30 |  | Viaduct pier foundation redesign due to utility clash
VO-PKG-04-01334 | PKG-04 | 310281.45 | 0 | Pending Approval | 39 | 2026-05-30 |  | Station box diaphragm wall water ingress mitigation
VO-PKG-07-01957 | PKG-07 | 156204.04 | 126294.77 | Approved | 31 | 2026-05-30 | 2026-07-01 | Fiber optic telemetry routing realignment along guideway
VO-PKG-07-02637 | PKG-07 | 52789.8 | 44262.75 | Approved | 55 | 2026-05-30 | 2026-07-10 | Fiber optic telemetry routing realignment along guideway
VO-PKG-08-01138 | PKG-08 | 230732.29 | 0 | Pending Approval | 24 | 2026-05-30 |  | Track vibration damping rubber pads acoustic upgrade
VO-PKG-01-01671 | PKG-01 | 260731.62 | 247138.59 | Approved | 46 | 2026-06-01 | 2026-07-15 | Unforeseen soft ground stabilization and grouting
VO-PKG-07-01177 | PKG-07 | 89151.33 | 0 | Rejected | 0 | 2026-06-01 | 2026-07-11 | Fiber optic telemetry routing realignment along guideway
VO-PKG-02-02612 | PKG-02 | 69973.47 | 62370.09 | Approved | 6 | 2026-06-02 | 2026-07-27 | TBM Cutterhead refurbishment and rock fissure sealing
VO-PKG-04-02424 | PKG-04 | 318077.05 | 308099.84 | Approved | 37 | 2026-06-02 | 2026-07-17 | Station box diaphragm wall water ingress mitigation
VO-PKG-05-00275 | PKG-05 | 279343.22 | 0 | Rejected | 0 | 2026-06-02 | 2026-06-27 | HV substation redundancy transformer capacity upgrade
VO-PKG-05-00405 | PKG-05 | 100802 | 98571.36 | Approved | 9 | 2026-06-02 | 2026-07-26 | HV substation redundancy transformer capacity upgrade
VO-PKG-07-00237 | PKG-07 | 100948.78 | 0 | Pending Approval | 9 | 2026-06-02 |  | Fiber optic telemetry routing realignment along guideway
VO-PKG-07-02597 | PKG-07 | 73705.41 | 65453.59 | Approved | 6 | 2026-06-02 | 2026-07-18 | Fiber optic telemetry routing realignment along guideway
VO-PKG-01-00141 | PKG-01 | 196184.43 | 188375.51 | Approved | 39 | 2026-06-03 | 2026-06-23 | Unforeseen soft ground stabilization and grouting
VO-PKG-06-01276 | PKG-06 | 190442.13 | 173145.91 | Approved | 45 | 2026-06-03 | 2026-07-10 | Additional smoke evacuation shafts in underground platforms
VO-PKG-08-02778 | PKG-08 | 130240.98 | 0 | Pending Approval | 37 | 2026-06-03 |  | Track vibration damping rubber pads acoustic upgrade
VO-PKG-09-01259 | PKG-09 | 25216.81 | 0 | Rejected | 0 | 2026-06-03 | 2026-06-29 | Drainage box culvert capacity expansion for 100-year flood event
VO-PKG-03-01583 | PKG-03 | 178255.47 | 0 | Pending Approval | 23 | 2026-06-04 |  | Viaduct pier foundation redesign due to utility clash
VO-PKG-04-02524 | PKG-04 | 138272.47 | 118513.94 | Approved | 39 | 2026-06-04 | 2026-06-22 | Station box diaphragm wall water ingress mitigation
VO-PKG-06-02346 | PKG-06 | 33296.45 | 26903.53 | Approved | 15 | 2026-06-04 | 2026-07-03 | Additional smoke evacuation shafts in underground platforms
VO-PKG-01-02411 | PKG-01 | 174980.2 | 0 | Rejected | 0 | 2026-06-05 | 2026-07-07 | Unforeseen soft ground stabilization and grouting
VO-PKG-04-00874 | PKG-04 | 41645.64 | 0 | Rejected | 0 | 2026-06-05 | 2026-06-15 | Station box diaphragm wall water ingress mitigation
VO-PKG-04-01364 | PKG-04 | 185904.53 | 149476.3 | Approved | 53 | 2026-06-06 | 2026-07-16 | Station box diaphragm wall water ingress mitigation
VO-PKG-07-02847 | PKG-07 | 323537.48 | 263137.35 | Approved | 52 | 2026-06-06 | 2026-07-21 | Fiber optic telemetry routing realignment along guideway
VO-PKG-02-01512 | PKG-02 | 339546.27 | 313359.1 | Approved | 35 | 2026-06-07 | 2026-07-05 | TBM Cutterhead refurbishment and rock fissure sealing
VO-PKG-03-00273 | PKG-03 | 221212.46 | 0 | Pending Approval | 3 | 2026-06-07 |  | Viaduct pier foundation redesign due to utility clash
VO-PKG-04-01414 | PKG-04 | 116170.39 | 0 | Pending Approval | 8 | 2026-06-07 |  | Station box diaphragm wall water ingress mitigation
VO-PKG-10-02330 | PKG-10 | 268924.99 | 240933.91 | Approved | 50 | 2026-06-08 | 2026-07-07 | HVAC chilled water pipe rerouting around station concourse
VO-PKG-04-01974 | PKG-04 | 256247.13 | 0 | Pending Approval | 27 | 2026-06-09 |  | Station box diaphragm wall water ingress mitigation
VO-PKG-10-00320 | PKG-10 | 100315 | 0 | Rejected | 0 | 2026-06-09 | 2026-06-24 | HVAC chilled water pipe rerouting around station concourse
VO-PKG-02-01202 | PKG-02 | 310630.21 | 286232.74 | Approved | 56 | 2026-06-10 | 2026-07-02 | TBM Cutterhead refurbishment and rock fissure sealing
VO-PKG-06-00646 | PKG-06 | 293494.92 | 0 | Rejected | 0 | 2026-06-10 | 2026-06-21 | Additional smoke evacuation shafts in underground platforms
VO-PKG-07-00637 | PKG-07 | 58071.38 | 0 | Rejected | 0 | 2026-06-10 | 2026-06-30 | Fiber optic telemetry routing realignment along guideway
VO-PKG-10-00200 | PKG-10 | 46755.25 | 43758.76 | Approved | 33 | 2026-06-10 | 2026-07-25 | HVAC chilled water pipe rerouting around station concourse
VO-PKG-04-01314 | PKG-04 | 17118.56 | 13992.42 | Approved | 35 | 2026-06-12 | 2026-07-16 | Station box diaphragm wall water ingress mitigation
VO-PKG-01-02571 | PKG-01 | 190891.67 | 185216.7 | Approved | 27 | 2026-06-13 | 2026-06-28 | Unforeseen soft ground stabilization and grouting
VO-PKG-03-02483 | PKG-03 | 226854.8 | 210758.37 | Approved | 58 | 2026-06-13 | 2026-08-07 | Viaduct pier foundation redesign due to utility clash
VO-PKG-05-02395 | PKG-05 | 318875.88 | 285715.92 | Approved | 59 | 2026-06-13 | 2026-07-17 | HV substation redundancy transformer capacity upgrade
VO-PKG-06-01016 | PKG-06 | 248411.24 | 0 | Pending Approval | 34 | 2026-06-13 |  | Additional smoke evacuation shafts in underground platforms
VO-PKG-08-00818 | PKG-08 | 341453.62 | 300214.27 | Approved | 34 | 2026-06-13 | 2026-08-04 | Track vibration damping rubber pads acoustic upgrade
VO-PKG-09-00699 | PKG-09 | 338127.09 | 280247 | Approved | 11 | 2026-06-13 | 2026-07-04 | Drainage box culvert capacity expansion for 100-year flood event
VO-PKG-02-02262 | PKG-02 | 241388.43 | 220433.78 | Approved | 47 | 2026-06-14 | 2026-07-31 | TBM Cutterhead refurbishment and rock fissure sealing
VO-PKG-03-02273 | PKG-03 | 338829.43 | 319488.14 | Approved | 12 | 2026-06-14 | 2026-07-03 | Viaduct pier foundation redesign due to utility clash
VO-PKG-05-02755 | PKG-05 | 215137.05 | 198031.98 | Approved | 42 | 2026-06-14 | 2026-07-02 | HV substation redundancy transformer capacity upgrade
VO-PKG-09-01329 | PKG-09 | 286584.13 | 0 | Pending Approval | 13 | 2026-06-14 |  | Drainage box culvert capacity expansion for 100-year flood event
VO-PKG-01-02551 | PKG-01 | 18808.15 | 17445.81 | Approved | 29 | 2026-06-15 | 2026-08-07 | Unforeseen soft ground stabilization and grouting
VO-PKG-06-00236 | PKG-06 | 43970.8 | 40788.06 | Approved | 7 | 2026-06-15 | 2026-08-03 | Additional smoke evacuation shafts in underground platforms
VO-PKG-09-02689 | PKG-09 | 53581.91 | 49716.16 | Approved | 25 | 2026-06-15 | 2026-07-24 | Drainage box culvert capacity expansion for 100-year flood event
VO-PKG-10-02270 | PKG-10 | 148459.66 | 0 | Rejected | 0 | 2026-06-15 | 2026-07-29 | HVAC chilled water pipe rerouting around station concourse
VO-PKG-01-02771 | PKG-01 | 253659.53 | 239518.38 | Approved | 55 | 2026-06-16 | 2026-08-05 | Unforeseen soft ground stabilization and grouting
VO-PKG-10-00590 | PKG-10 | 87690.97 | 0 | Pending Approval | 25 | 2026-06-16 |  | HVAC chilled water pipe rerouting around station concourse
VO-PKG-01-00501 | PKG-01 | 284513.81 | 0 | Rejected | 0 | 2026-06-17 | 2026-07-30 | Unforeseen soft ground stabilization and grouting
VO-PKG-04-01124 | PKG-04 | 191361.12 | 158476.36 | Approved | 40 | 2026-06-17 | 2026-07-05 | Station box diaphragm wall water ingress mitigation
VO-PKG-04-01424 | PKG-04 | 108728.95 | 0 | Rejected | 0 | 2026-06-17 | 2026-07-08 | Station box diaphragm wall water ingress mitigation
VO-PKG-06-02826 | PKG-06 | 201894.48 | 0 | Rejected | 0 | 2026-06-17 | 2026-06-28 | Additional smoke evacuation shafts in underground platforms
VO-PKG-07-02527 | PKG-07 | 243769.34 | 208685.75 | Approved | 36 | 2026-06-17 | 2026-07-09 | Fiber optic telemetry routing realignment along guideway
VO-PKG-08-02208 | PKG-08 | 184666.77 | 0 | Rejected | 0 | 2026-06-17 | 2026-07-15 | Track vibration damping rubber pads acoustic upgrade
VO-PKG-08-00428 | PKG-08 | 134581.56 | 0 | Pending Approval | 32 | 2026-06-18 |  | Track vibration damping rubber pads acoustic upgrade
VO-PKG-02-01232 | PKG-02 | 76351.48 | 65488.45 | Approved | 26 | 2026-06-19 | 2026-07-28 | TBM Cutterhead refurbishment and rock fissure sealing
VO-PKG-06-02836 | PKG-06 | 244603.4 | 212140.42 | Approved | 55 | 2026-06-19 | 2026-08-16 | Additional smoke evacuation shafts in underground platforms
VO-PKG-10-02560 | PKG-10 | 286703.69 | 0 | Pending Approval | 20 | 2026-06-19 |  | HVAC chilled water pipe rerouting around station concourse
VO-PKG-01-01741 | PKG-01 | 103106.62 | 93016.04 | Approved | 29 | 2026-06-20 | 2026-08-14 | Unforeseen soft ground stabilization and grouting
VO-PKG-04-02004 | PKG-04 | 54580.86 | 44020.23 | Approved | 58 | 2026-06-20 | 2026-07-21 | Station box diaphragm wall water ingress mitigation
VO-PKG-09-00539 | PKG-09 | 290292.25 | 0 | Rejected | 0 | 2026-06-20 | 2026-07-16 | Drainage box culvert capacity expansion for 100-year flood event
VO-PKG-10-00140 | PKG-10 | 141111.16 | 114570.64 | Approved | 46 | 2026-06-20 | 2026-08-12 | HVAC chilled water pipe rerouting around station concourse
VO-PKG-01-01701 | PKG-01 | 24875 | 23115.12 | Approved | 58 | 2026-06-21 | 2026-07-28 | Unforeseen soft ground stabilization and grouting
VO-PKG-02-00532 | PKG-02 | 278201.99 | 242467.78 | Approved | 21 | 2026-06-21 | 2026-08-11 | TBM Cutterhead refurbishment and rock fissure sealing
VO-PKG-03-00643 | PKG-03 | 41700.04 | 38221.72 | Approved | 37 | 2026-06-21 | 2026-08-16 | Viaduct pier foundation redesign due to utility clash
VO-PKG-05-02485 | PKG-05 | 275120.5 | 241004.74 | Approved | 5 | 2026-06-22 | 2026-08-02 | HV substation redundancy transformer capacity upgrade
VO-PKG-09-00739 | PKG-09 | 125793.38 | 0 | Rejected | 0 | 2026-06-22 | 2026-07-02 | Drainage box culvert capacity expansion for 100-year flood event
VO-PKG-09-01099 | PKG-09 | 166444.5 | 159037.1 | Approved | 8 | 2026-06-22 | 2026-08-20 | Drainage box culvert capacity expansion for 100-year flood event
VO-PKG-01-02931 | PKG-01 | 33383.03 | 31442.36 | Approved | 58 | 2026-06-23 | 2026-07-13 | Unforeseen soft ground stabilization and grouting
VO-PKG-05-00485 | PKG-05 | 71526.81 | 62977.4 | Approved | 42 | 2026-06-23 | 2026-07-16 | HV substation redundancy transformer capacity upgrade
VO-PKG-06-00386 | PKG-06 | 121040.1 | 110865.89 | Approved | 38 | 2026-06-23 | 2026-07-28 | Additional smoke evacuation shafts in underground platforms
VO-PKG-07-00247 | PKG-07 | 155977.08 | 0 | Rejected | 0 | 2026-06-23 | 2026-07-21 | Fiber optic telemetry routing realignment along guideway
VO-PKG-01-02461 | PKG-01 | 179070.83 | 0 | Pending Approval | 39 | 2026-06-24 |  | Unforeseen soft ground stabilization and grouting
VO-PKG-06-01976 | PKG-06 | 157271.95 | 145052.95 | Approved | 58 | 2026-06-24 | 2026-07-29 | Additional smoke evacuation shafts in underground platforms
VO-PKG-08-00838 | PKG-08 | 200588.11 | 0 | Pending Approval | 32 | 2026-06-24 |  | Track vibration damping rubber pads acoustic upgrade
VO-PKG-10-00400 | PKG-10 | 39936.36 | 34527.36 | Approved | 20 | 2026-06-24 | 2026-08-03 | HVAC chilled water pipe rerouting around station concourse
VO-PKG-10-01200 | PKG-10 | 283668.76 | 229395.14 | Approved | 18 | 2026-06-24 | 2026-08-17 | HVAC chilled water pipe rerouting around station concourse
VO-PKG-10-02400 | PKG-10 | 163824.57 | 140570.56 | Approved | 6 | 2026-06-24 | 2026-08-05 | HVAC chilled water pipe rerouting around station concourse
VO-PKG-01-00151 | PKG-01 | 190290.76 | 152254.83 | Approved | 35 | 2026-06-25 | 2026-08-14 | Unforeseen soft ground stabilization and grouting
VO-PKG-01-02181 | PKG-01 | 141233.5 | 130494.16 | Approved | 25 | 2026-06-25 | 2026-08-05 | Unforeseen soft ground stabilization and grouting
VO-PKG-07-00767 | PKG-07 | 32165.02 | 0 | Pending Approval | 20 | 2026-06-25 |  | Fiber optic telemetry routing realignment along guideway
VO-PKG-07-01737 | PKG-07 | 161678.33 | 135544.24 | Approved | 55 | 2026-06-25 | 2026-08-22 | Fiber optic telemetry routing realignment along guideway
VO-PKG-05-00985 | PKG-05 | 207758.03 | 181149.75 | Approved | 44 | 2026-06-26 | 2026-08-22 | HV substation redundancy transformer capacity upgrade
VO-PKG-09-02779 | PKG-09 | 41006.55 | 39873.56 | Approved | 25 | 2026-06-26 | 2026-07-21 | Drainage box culvert capacity expansion for 100-year flood event
VO-PKG-01-00491 | PKG-01 | 307363.56 | 274355.69 | Approved | 8 | 2026-06-27 | 2026-08-21 | Unforeseen soft ground stabilization and grouting
VO-PKG-03-00173 | PKG-03 | 308716.24 | 283822.18 | Approved | 15 | 2026-06-27 | 2026-08-01 | Viaduct pier foundation redesign due to utility clash
VO-PKG-04-00774 | PKG-04 | 273520.04 | 0 | Rejected | 0 | 2026-06-27 | 2026-07-23 | Station box diaphragm wall water ingress mitigation
VO-PKG-02-02032 | PKG-02 | 23856.92 | 0 | Pending Approval | 19 | 2026-06-28 |  | TBM Cutterhead refurbishment and rock fissure sealing
VO-PKG-05-00075 | PKG-05 | 344355.33 | 279848.65 | Approved | 39 | 2026-06-28 | 2026-07-17 | HV substation redundancy transformer capacity upgrade
VO-PKG-09-00829 | PKG-09 | 22978.2 | 0 | Rejected | 0 | 2026-06-28 | 2026-07-21 | Drainage box culvert capacity expansion for 100-year flood event
VO-PKG-09-01529 | PKG-09 | 269741.55 | 0 | Pending Approval | 24 | 2026-06-28 |  | Drainage box culvert capacity expansion for 100-year flood event
VO-PKG-10-01600 | PKG-10 | 144488.38 | 0 | Pending Approval | 8 | 2026-06-28 |  | HVAC chilled water pipe rerouting around station concourse
VO-PKG-03-01833 | PKG-03 | 179796.46 | 166513.66 | Approved | 27 | 2026-06-29 | 2026-08-03 | Viaduct pier foundation redesign due to utility clash
VO-PKG-05-00255 | PKG-05 | 95050.21 | 91832.44 | Approved | 59 | 2026-06-29 | 2026-08-23 | HV substation redundancy transformer capacity upgrade
VO-PKG-07-00747 | PKG-07 | 262602.94 | 216522.43 | Approved | 15 | 2026-06-29 | 2026-08-01 | Fiber optic telemetry routing realignment along guideway
VO-PKG-10-00500 | PKG-10 | 142331.64 | 0 | Pending Approval | 39 | 2026-06-29 |  | HVAC chilled water pipe rerouting around station concourse
VO-PKG-04-00444 | PKG-04 | 304402.61 | 280045.82 | Approved | 47 | 2026-06-30 | 2026-08-08 | Station box diaphragm wall water ingress mitigation
VO-PKG-05-01875 | PKG-05 | 286964.08 | 0 | Rejected | 0 | 2026-06-30 | 2026-07-13 | HV substation redundancy transformer capacity upgrade
VO-PKG-01-00331 | PKG-01 | 239011.29 | 211672.31 | Approved | 8 | 2026-07-01 | 2026-07-25 | Unforeseen soft ground stabilization and grouting
VO-PKG-03-02353 | PKG-03 | 146571.4 | 0 | Rejected | 0 | 2026-07-01 | 2026-07-12 | Viaduct pier foundation redesign due to utility clash
VO-PKG-04-00634 | PKG-04 | 263480.9 | 214860.52 | Approved | 9 | 2026-07-01 | 2026-08-09 | Station box diaphragm wall water ingress mitigation
VO-PKG-05-02145 | PKG-05 | 244239.9 | 0 | Pending Approval | 27 | 2026-07-01 |  | HV substation redundancy transformer capacity upgrade
VO-PKG-07-02777 | PKG-07 | 268546.54 | 261381.28 | Approved | 14 | 2026-07-01 | 2026-07-29 | Fiber optic telemetry routing realignment along guideway
VO-PKG-01-00461 | PKG-01 | 220542.67 | 186640.99 | Approved | 9 | 2026-07-02 | 2026-08-07 | Unforeseen soft ground stabilization and grouting
VO-PKG-01-01611 | PKG-01 | 311967.73 | 0 | Pending Approval | 17 | 2026-07-02 |  | Unforeseen soft ground stabilization and grouting
VO-PKG-03-01113 | PKG-03 | 240498.91 | 227602.32 | Approved | 53 | 2026-07-02 | 2026-07-20 | Viaduct pier foundation redesign due to utility clash
VO-PKG-06-02946 | PKG-06 | 103860.94 | 88167 | Approved | 13 | 2026-07-02 | 2026-07-24 | Additional smoke evacuation shafts in underground platforms
VO-PKG-09-00639 | PKG-09 | 131530.61 | 113024.76 | Approved | 39 | 2026-07-02 | 2026-08-27 | Drainage box culvert capacity expansion for 100-year flood event
VO-PKG-09-01809 | PKG-09 | 327591.05 | 0 | Pending Approval | 24 | 2026-07-02 |  | Drainage box culvert capacity expansion for 100-year flood event
VO-PKG-09-02879 | PKG-09 | 253935.36 | 234210.54 | Approved | 58 | 2026-07-02 | 2026-08-19 | Drainage box culvert capacity expansion for 100-year flood event
VO-PKG-10-00210 | PKG-10 | 39617.63 | 32356.47 | Approved | 44 | 2026-07-02 | 2026-08-24 | HVAC chilled water pipe rerouting around station concourse

## Quality Control & Audit
QUALITY CONTROL & MATHEMATICAL RECONCILIATION AUDIT
Reconciliation Proof: Raw CSV Certified Total = Excel Certified Total ($0.00 Discrepancy)
Audit Verification Scorecard
Audit Category | Verification Item | Expected (Raw CSV / DB) | Actual (Excel Model) | Variance Delta | Status
Financial Reconciliation | Total Certified Sum ($) | 825453726.54 | 825453726.54 | 0 | VERIFIED PARITY
Integrity Check | Expenditures Transaction Count | 7000 | 7000 | 0 | EXACT MATCH
Integrity Check | Variation Orders Transaction Count | 3000 | 3000 | 0 | EXACT MATCH
Integrity Check | Work Packages Count | 10 | 10 | 0 | EXACT MATCH
Integrity Check | Total Baseline Budget ($) | 850000000 | 850000000 | 0 | EXACT MATCH
Integrity Check | Total Contingency Budget ($) | 68000000 | 68000000 | 0 | EXACT MATCH

## Package Dashboard
WORK PACKAGE PERFORMANCE DASHBOARD
Sheets 2–5 dashboard series ¦ Portfolio EVM, forecast and exposure by work package
BUDGET AT COMPLETION |  |  | ESTIMATE AT COMPLETION |  |  | VARIANCE AT COMPLETION |  |  | PORTFOLIO CPI
1148524151.69 |  |  | 1445379342.7186 |  |  | -296855191.0286 |  |  | 0.84353
PERFORMANCE VISUALS
LIVE ANALYSIS TABLES
Package | BAC | EAC |  | Package | CPI |  | Package | Net Exposure
PKG-01 | 75235645.23 | 101601247.0244 |  | PKG-01 | 0.7405 |  | PKG-01 | 42822733.62
PKG-02 | 195263315.55 | 111410640.2432 |  | PKG-02 | 1.7526 |  | PKG-02 | 30240483.66
PKG-03 | 144054576.04 | 124223274.4706 |  | PKG-03 | 1.1596 |  | PKG-03 | 36307524.88
PKG-04 | 160681709.85 | 134370768.3443 |  | PKG-04 | 1.1958 |  | PKG-04 | 30328686.82
PKG-05 | 105552444.97 | 149681670.1818 |  | PKG-05 | 0.70518 |  | PKG-05 | 40967349.2
PKG-06 | 90251338.57 | 159583006.5577 |  | PKG-06 | 0.56554 |  | PKG-06 | 41217408.46
PKG-07 | 116803347.78 | 175846610.1667 |  | PKG-07 | 0.66423 |  | PKG-07 | 36127358.56
PKG-08 | 91714200.63 | 184123330.2889 |  | PKG-08 | 0.49811 |  | PKG-08 | 42604291.44
PKG-09 | 105210787.59 | 202240471.3 |  | PKG-09 | 0.52023 |  | PKG-09 | 40364875.73
PKG-10 | 63756785.48 | 102298324.141 |  | PKG-10 | 0.62324 |  | PKG-10 | 43965570.08

## Payment Dashboard
PAYMENT & CERTIFICATE DASHBOARD
Payment status composition and package-level certified values from the interactive summary
TOTAL CERTIFIED |  | PAID |  |  | PENDING PAYMENT |  |  | UNDER REVIEW
825453726.54 |  | 594270538.81 |  |  | 119669669.15 |  |  | 82083656.29
PERFORMANCE VISUALS
LIVE ANALYSIS TABLES
Payment Status | Certified Amount | Package | Pending | Disputed | Paid | Under Review | Total
Approved Pending Payment | 119669669.15 | PKG-01 | 13304816.76 | 1287885.84 | 61646575.29 | 7073744.67 | 83313022.56
Disputed | 29429862.29 | PKG-02 | 12845642.53 | 2169609.25 | 57184025.06 | 10244596.94 | 82443873.78
Paid | 594270538.81 | PKG-03 | 11747320.55 | 2522079.55 | 62241962.93 | 7960463.61 | 84471826.64
Under Review | 82083656.29 | PKG-04 | 10257677.48 | 4103925.85 | 58859254.46 | 8745310.9 | 81966168.69
|  | PKG-05 | 14830241.76 | 2999648.99 | 55970517.58 | 8524510.27 | 82324918.6
|  | PKG-06 | 10915051.67 | 3443588.41 | 61878159.17 | 6746364.16 | 82983163.41
|  | PKG-07 | 12417553.47 | 2894960.21 | 60942765.43 | 8151093.77 | 84406372.88
|  | PKG-08 | 11831676.94 | 3472290.91 | 59724050.92 | 7827479.86 | 82855498.63
|  | PKG-09 | 10952569.8 | 3023804.75 | 57560967.61 | 9358846.36 | 80896188.52
|  | PKG-10 | 10567118.19 | 3512068.53 | 58262260.36 | 7451245.75 | 79792692.83

## Expenditure Dashboard
ACTUAL EXPENDITURE DASHBOARD
Transaction-level certified cost, retention, payment status and quarterly delivery trend
CERTIFIED AMOUNT |  | NET CERTIFIED |  | RETENTION HELD |  | TRANSACTIONS
825453726.54 |  | 784181039.96 |  | 41272686.58 |  | 7000
PERFORMANCE VISUALS
LIVE ANALYSIS TABLES
Quarter | Net Certified | Package | Net Certified | Payment Status | Net Certified
2024-Q1 | 64314000.83 | PKG-01 | 79147371.41 | Approved Pending Payment | 113686185.56
2024-Q2 | 75038804.16 | PKG-02 | 78321680.1 | Disputed | 27958369.14
2024-Q3 | 78205264.8 | PKG-03 | 80248235.26 | Paid | 564557011.65
2024-Q4 | 76182992.01 | PKG-04 | 77867860.2 | Under Review | 77979473.61
2025-Q1 | 78563791.13 | PKG-05 | 78208672.62
2025-Q2 | 76809428.37 | PKG-06 | 78834005.26
2025-Q3 | 70661775.57 | PKG-07 | 80186054.32
2025-Q4 | 74441208.46 | PKG-08 | 78712723.71
2026-Q1 | 74812991.21 | PKG-09 | 76851378.97
2026-Q2 | 72295347.51 | PKG-10 | 75803058.11
2026-Q3 | 42855435.91

## Variation Dashboard
VARIATION ORDER DASHBOARD
Claims, approvals, time impact and commercial exposure across all work packages
TOTAL CLAIMED |  |  | TOTAL APPROVED |  |  | APPROVAL VALUE RATE |  |  | AVG TIME IMPACT
549503437.24 |  |  | 298524151.69 |  |  | 54.33% |  |  | 25.2703
PERFORMANCE VISUALS
LIVE ANALYSIS TABLES
Package | Claimed | Approved |  | Status | Claimed Amount |  | Status | VO Count
PKG-01 | 55827332.99 | 30235645.23 |  | Approved | 334426583.62 |  | Approved | 1823
PKG-02 | 52220147.05 | 30263315.55 |  | Pending Approval | 154422130.76 |  | Pending Approval | 844
PKG-03 | 56016449.99 | 29054576.04 |  | Rejected | 60654722.86 |  | Rejected | 333
PKG-04 | 53779836.54 | 25681709.85
PKG-05 | 57457708.45 | 30552444.97
PKG-06 | 53373047.2 | 32251338.57
PKG-07 | 53194267.2 | 28803347.78
PKG-08 | 55203897.5 | 29714200.63
PKG-09 | 57642234.49 | 33210787.59
PKG-10 | 54788515.83 | 28756785.48